UNICEF Turkey Country Programme Evaluation (2016-19)

Inception Report

Final version – 24th September 2019

Table of Contents

List of Acronyms	2

Map of Turkey	4

1.	Introduction	5

2. 	Country context and child-related issues	6

2.1	Turkey’s economic and development profile	6

2.2	The political, security and social context in Turkey	7

2.3	Child protection: context and problem statement	8

2.4	Education: context and problem statement	11

2.5	Social inclusion, protection, cohesion: context and problem statement	12

2.6	Social Policy, Monitoring and Data: context and problem statement	14

3.	Subject of evaluation: UNICEF’s strategy and programme	17

3.1	UNICEF’s strategy	17

3.2	UNICEF’s programme	19

4.	Evaluation purpose, scope and approach	27

4.1	Evaluation purpose, intended use and expected users	27

4.2	Scope, focus and evaluability issues	28

4.3	Evaluation approach	30

5. 	Evaluation Framework	33

6.	Methodology	37

7.	Team roles and workplan	46

7.1	Team roles	46

7.2	Evaluation schedule	47

Annexes	50

A. Terms of Reference	52

B. Evaluation Matrix	52

C. CPD Theory of Change	52

D. People met during inception mission	52

E. List of primary stakeholders	52

F. Document list	52

## List of Acronyms

| 3RP | Third Regional Response Plan |
| --- | --- |
| AFAD | Disaster and Emergency Management Presidency |
| ASAM CCTE | Association for Solidarity with Asylum Seekers and Migrants Conditional Cash Transfer Education |
| CPE CPD | Country Programme Evaluation Country Programme Document |
| CRM CSO | Child Rights Monitoring Civil Society Organisation |
| CWD | Children with Disabilities |
| DAC | Development Assistance Committee (of the OECD) |
| DGMM | Directorate General of Migration Management |
| DHS | Demographic and Health Survey |
| ED | Executive Director |
| EM | Evaluation Manager |
| EQ | Evaluation Question |
| EQAS | Evaluation Quality Assurance System |
| ER | Evaluation Report |
| ERG | Evaluation Reference Group |
| ET | Evaluation Team |
| EU | European Union |
| GBV GBViE | Gender Based Violence Gender Based Violence in Emergencies |
| GoT INGO | Government of Turkey International non-governmental organization |
| IOM | International Organization for Migration |
| IR | Inception Report |
| KII | Key Informant Interviews |
| M&E | Monitoring and Evaluation |
| MoFLSS MoI | Ministry of Family Labour and Social Services Ministry of Interior |
| MoNE MoYS | Ministry of National Education Ministry of Youth and Sport |
| NGO | Non-Governmental Organisation |
| OECD PSEA SBO | Organisation for Economic Co-operation and Development Prevention of Sexual Exploitation and Abuse Strategy and Budget Office |
| SGBV | Sexual and Gender-based violence |
| TCO TEC | Turkey Country Office Temporary Education Centres |
| TL | Turkish Lira |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| TRC | Turkish Red Crescent |
| UN | United Nations |
| UNDP | United Nations Development Programme |
| UNDCS | UN Development Cooperation Strategy |
| UNEG | United Nations Evaluation Group |
| UNHCR | United Nations High Commissioner for Refugees |
| UNICEF | United Nations Children’s Fund |
|  | USD | United States Dollar |
| WFP | World Food Programme |
| WHO | World Health Organisation |

## Map of Turkey

# 1.	Introduction

1.1	This inception report sets out the evaluation team’s understanding and interpretation of the terms of reference for the UNICEF Turkey Country Programme Evaluation, including its proposed approach to the evaluation. It is based on review of relevant documentation, a four day visit to the Country Office in Ankara (2-5 July 2019), and discussions with staff in both the Country and Regional offices. Its purpose is partly to ensure agreement and clarity on the evaluation approach before the next phase of the evaluation – a three-week fact-finding mission to Turkey – takes place in September and October 2019. But it also provides a basic analysis of the relevant context and of the issues arising for UNICEF, as well as the theoretical and planning framework for the conduct of the evaluation, including the guiding questions, main lines of enquiry and the evaluation methodology.

1.2	The evaluation was commissioned by UNICEF’s Regional Office for Europe and Central Asia (ECARO) in discussion with the Turkey Country Office. As the terms of reference state, Country Programme Evaluations (CPEs) in UNICEF are ‘strategic evaluations that provide an assessment of the totality of UNICEF’s programme of work’, with a ‘strong focus on assessing the relevance of UNICEF’s programmatic approaches, position and selected priority issues as these have evolved in response to emerging needs, government priorities, partner inputs and the often changing geopolitical and socioeconomic environment in which UNICEF operates’. Such evaluations include a review of the use of partnerships and other implementation strategies, and they are mostly used (as in this case) to draw out lessons to inform current and future country programme design and implementation.

1.3	The objectives of the present evaluation are (i) to provide an independent assessment of the performance of the CP 2016-20; (ii) to assess UNICEF’s strategic positioning and use of change strategies, and (iii) to identify good practices and draw lessons and forward-looking recommendations. The evaluation covers UNICEF’s Turkey country programme from 2016 to date, and it is intended to serve both accountability and learning purposes. It is the second of two major review processes designed in part to inform the writing of the new CPD for 2021-25. The first was a Programme Review conducted in 2018/19, the results of which will be taken into account in the present evaluation.

1.4	Although it is consultative and participatory in nature, the evaluation is an independent one. The evaluation team consists of four international and one Turkish member: James Darcy (Team Leader); Francesca Ballarin (lead on education and child protection), Zarko Sunderic (social policy); Gurcharan Virdee (gender issues); and a Turkish expert, Gokce Baykal (social protection & social cohesion). The evaluation process is managed by Malene Molding Nielsen for ECARO, and Silvia Mestroni (Chief of Planning, Monitoring & Evaluation) is the main point of contact in the Country Office. An Evaluation Reference Group has been established as described in the ToR, and an external quality assurance process will be applied both to this inception report and the main evaluation report.

1.5	In the remainder of this report, we provide a selective context analysis; a description of the subject matter of the evaluation, i.e. the aspects of UNICEF’s programme that will form the main focus of the evaluation; a description of the proposed evaluation approach and methodology, including key questions and lines of enquiry, the proposed evaluation agenda and schedule, and a description of likely key informants and proposed site visits for the fact finding mission in September 2019. In the Annex, we include the terms of reference; a list of key stakeholders; the full evaluation matrix; a list of documents consulted; and the theory of change for the country programme 2016-20.

# 2. 	Country context and child-related issues

The country context is more fully described elsewhere. Here we highlight only some of the more salient features of the context for the purposes of this evaluation.

2.1	Turkey’s economic and development profile

2.1.1	Turkey is an Upper Middle-Income country with high levels of urbanisation. State institutions provide services throughout the country, and basic development indicators continue to improve: absolute poverty has been eradicated, child mortality rates substantially reduced, and Turkey’s human development index score has improved. Turkey is an OECD member, negotiating its accession to the European Union (EU) as a member state, and is a member of the G-20. Despite this, average living standards are around half the EU average and there are high levels of informal employment - 35% overall, 82.3% in agriculture. There are persistent equity gaps, including socioeconomic, regional and rural-urban disparities in decent work, household income and infrastructure.

2.1.2	With regard to children’s vulnerability, levels of relative poverty are twice the OECD average (7.4 million children, out of a total country population of around 80 million). As described in the Country Programme Document (CPD), particularly disadvantaged children who face multiple deprivations include children whose parents are poorly educated and have low-income, belong to large families, and live in rural areas, as well as children with disabilities (CWD). Roma children also face exclusion and heightened risks. Gender inequalities persist, for women and girls. The risks faced by children include child labour, child marriage, violence and discrimination, lack of access to quality inclusive education, threats to early childhood development, protection from violence and abuse, and opportunities for self-development and expression.

2.1.3	Despite strong growth in the past two years, Turkey is currently undergoing a recession. Following a pronounced deterioration in foreign financing conditions in the third quarter of 2018, domestic financial conditions sharply worsened with a substantial depreciation of the Turkish Lira. Though the economy is expected to recover, the short to medium-term economic outlook is uncertain, particularly given international risk factors (tensions with the US, EU and others). As a result, it is unclear what the government’s fiscal headroom will be to finance the social programmes to which it is committed.

High levels of informality in the Turkish economy have been exacerbated by the influx of refugees. This is a challenge for the reduction in levels of informality in the Turkish labour market, while it also complicates the social inclusion of these refugees.

2.1.4	Since 2011, the mass influx of Syrians fleeing the war in their country has made Turkey the country with the largest refugee population in the world. As the 2018/19 Programme Review describes, Turkey has invested heavily to provide refugees from Syria and refugees and asylum-seekers from other countries – about 4 million individuals in all – with services and opportunities, but the children among them remain particularly vulnerable. Turkey is also a main transit country for Syrians and other refugees moving towards Europe. A peak in migration towards Europe in 2015-2016 led to the signature of the EU-Turkey Statement in 2016, which contributed to an increase in the provision of international support for refugees. In parallel, it has contributed to a significant reduction in the flow of irregular migration from Turkey to Europe.’  The Turkish government’s policy has increasingly been to integrate the Syrian refugee response into mainstream public service provision, including the public school system, rather than to ‘contain’ the refugee population and provide separate services. This mirrors the de facto geographic integration (albeit in pockets of high concentration) of refugees into Turkish communities. In parallel, the significance of refugee camps (‘temporary accommodation centres’), temporary education centres etc. has diminished over the evaluation period.

## 2.2	The political, security and social context in Turkey

2.2.1	Turkey’s politics have been highly volatile over the past four years, during which time the political landscape has changed considerably. As the 2018 Programme Review describes: ‘Since 2015, Turkey has witnessed a series of terrorist attacks, although their incidence has declined in more recent years. In 2016, an attempted coup-d’état was followed by a declaration of a state of emergency, which remained in force until mid-2018. In 2017, a referendum approved changes to the constitution, shifting Turkey from a parliamentary to a presidential republic. This new presidential system of government came into effect after presidential and parliamentary elections in June 2018.’

2.2.2	The shift to a presidential system of governance and a subsequent re-structuring of government, with frequent turnover of government officials at all levels, has significantly changed the landscape. Changes to governmental policies and structures have altered the environment within which UNICEF and other international agencies work, as well as substantially constricting the space within which civil society organisations (including a number of UNICEF partners) can operate. Due to the shrinking space for civil society organisations (CSOs), TCO has signed new partnerships in 2017 with a diverse range of organizations and municipalities. These factors have to be taken into account in evaluating the 2016-20 programme, as well in assessing the prospects for future programming.

2.2.3	The politics – and related social attitudes – surrounding the refugee influx have become gradually more challenging over the past four years. While the status and right to remain of Syrian refugees is protected under the temporary protection legislation, they remain vulnerable in socio-economic terms, especially given their reliance on jobs in the (unregulated) informal economy. Despite the de facto moves towards integration mentioned above, the general political rhetoric still assumes that Syrians will (eventually) return home. Meanwhile for the significant numbers of unregistered Syrian refugees (and for illegal migrants) the climate has become particularly difficult, as evidenced by recent government edicts concerning unregistered refugees and migrants in Istanbul. There is no current route to Syrians or other refugee groups gaining Turkish citizenship, raising questions about their longer-term status in relation to the wider Turkish population.

2.2.4	These factors and hardening social attitudes in areas of high refugee concentration raise major issues about social cohesion and the potential for social conflict. As with ethnic minority groups in the Turkish population, issues relating to language and cultural differences compound political tensions, specifically for the refugees around access to services and to the labour market.

Social cohesion will be one of the main strategic themes for the evaluation, as it is for UNICEF. More broadly, the evaluation will look at the social inclusion agenda, particularly from a gender perspective, reflecting the priority that UNICEF has given to this. One particular focus will be on the empowerment of adolescent girls in Turkey.

Box 1 	EU-Turkey refugee agreement 2016

The EU's refugee agreement with Turkey was signed on March 18, 2016, in an attempt to solve one of Europe's most pressing problems: the enormous influx of refugees into Europe. Under the deal, migrants arriving in Greece are now expected to be sent back to Turkey if they do not apply for asylum or their claim is rejected. In return, Turkey will receive aid and political concessions. Under the agreement, Turkey was promised €6 billion in financial aid, to be used by the Turkish government to finance projects for Syrian refugees. The EU Facility for Refugees in Turkey has been established, managing a total of €6 billion (€3 billion for 2016-2017 and €3 billion for 2018-2019), provides for a joint coordination mechanism, designed to ensure that the needs of refugees and host communities in Turkey are addressed in a comprehensive and coordinated manner. The Facility focuses on humanitarian assistance, education, migration management, health, municipal infrastructure, and socio-economic support.

## 2.3	Child protection: context and problem statement

2.3.1	As the CPD describes, elements of a coordinated national child protection system are in place, including a national strategy and inter-sectoral provincial mechanisms, are in place. This includes a National Strategy for the Prevention of Violence against Children. But the CPD identifies weaknesses in the system and the need for remedial action. Specifically, ‘the prevention of, and response to, violence, as well as for the rehabilitation of victims need further and more sustained social engagement, requiring much-increased participation of civil society. In addition, Syrian children under temporary protection have an acute need for safe and friendly environments for recreation and socialization, and in many cases require psychosocial support to overcome traumatic experiences and ongoing hardship… Some urban adolescents face the risks associated with street life, including coming in conflict with the law and, a topic of great public concern, drug addiction’

Child care

2.3.2	Turkey has made some progress on alternatives for children deprived of parental care. According to Ministry of Family Labour and Social Services (MoFLSS) there were 14,189 children in residential care at the end of 2017. This included 1,640 children receiving temporary residential rehabilitation in various types of Child Support Centres for children under protective and supportive measures. There were 16,171 adopted children and 5,642 living in foster families.

2.3.3	Although minimum standards are in force, there is room for further professionalisation in the child care system and improvements in arrangements for all groups of children living permanently or temporarily without parental care, including an effective legal guardianship system, a national Best Interest Determination mechanism, more capacity for children with additional needs such as children with disabilities and refugee children, and increased monitoring.

2.3.4	Irregular migrants, including children who are intercepted with their families, are given the opportunity to apply for protection in Turkey, but they also risk deportation, and in certain cases may be placed in administrative detention pending deportation. There are concerns about the lack of alternatives to administrative detention for children and their families and the rights and services for those in detention, and the need for proper age assessment. Unaccompanied minors are taken into care by MoFLSS, but there are needs for additional professional capacity, legal guardianship and non-residential care options. MoFLSS intends to increase the number of foster families.

Refugees and migrant children

2.3.5	Syrians fleeing the conflict in Syria have entered Turkey in increasingly large numbers since 2011. There were 3.6 million registered Syrian refugees in Turkey as of end 2018 compared to 2.5 million three years earlier. Of these, 1.7 million were children. The population of refugees and asylum seekers from Iraq, Afghanistan, Iran and other countries has reached 370,000 as of end 2018, 32% of them children. Syrian refugees reside mainly in host communities or camps in provinces near the Syrian border, but also in Istanbul and other large cities. Despite the generous and vigorous response of Turkey to the crisis, including through registration and health services, many Syrians under temporary protection are living in poverty and working informally, with girls and boys facing differential risks and vulnerabilities including child labour, early marriage, and abuse. This situation has also affected host communities, including children, through pressure on housing, prices, infrastructure and services and potentially raising social cohesion issues.

Violence and abuse of children

2.3.6	Cases of missing children, abductions, child rape, child murders and sexual abuse have prompted widespread concern and public condemnation. In July 2018, political parties agreed to support a bill on sexual harassment and abuse. In dialogue with policy-makers, concerned UN agencies in Turkey pointed to the need to consider more preventive and rehabilitative measures and awareness-raising. TurkStat figures show that a total of 122,209 children were received into secure units as victims of crimes or other incidents and misdemeanours in 2017, of whom 62.4% were allegedly victims of (non-sexual) assaults and 10.4% of sexual offences. Nationally representative survey data to complement administrative statistics is not available.

Juvenile justice

2.3.7	The most recent TurkStat and Ministry of Justice data shows that the number of alleged child offenders brought into security units declined to 107,984 in 2018 from 108,675 in 2017. The number of children 12-17 years-old against whom cases were opened (or reconsidered) declined from 135,517 to 120,786.

2.3.8	About half of all children who went on trial were tried in specialised courts, as a result of the gradual establishment of child courts across the country. Fewer children received prison sentences in 2017 (11,264, down from 12,423 in 2016). However, the percentage of children convicted who received prison sentences rose to 31.1% in 2017 from 28.1% in 2016. Girls are a small proportion as compared to boys. A recent review on the implementation of Individualized Rehabilitation System for children under detention indicated that despite the increased number of child-specific detention centres and the improvements in the physical conditions and case-management schemes, systemic challenges in implementation prevail. To enhance the use of alternatives to imprisonment, a new risk evaluation system for children on probation was developed and is expected to be rolled-out nationally in 2019.

2.3.9	A 2019 report from the European Commission notes that “Juvenile courts are still not in place in all provinces, despite the clear wording of the law. The quality of legal aid for juveniles, and rehabilitation activities in prisons are a matter of concern. Closure by the authorities of several civil society organisations dealing with juvenile rights after the state of emergency led to a decrease in civil society support to victims”. This suggests some important lines of enquiry for the evaluation.

Gender-based violence and child marriage

2.3.10	The prevalence of sexual and gender-based violence (SGBV) and child marriage among the refugee population in Turkey has been a challenge to quantify: estimates vary, and those that are generally available are produced from small samples.  While the prevalence of GBVIE and child marriage among refugee children is uncertain, case studies and qualitative research indicate that key drivers of child marriage are socio-economic conditions of refugee children and facilitated by social norms and legal loopholes in Turkey and Syria. Other factors include lack of education, and belief amongst refugees that child marriage is a protection against SGBV. Under-reporting is also a factor.

2.3.11	Despite the steady increase in the median age of marriage among Turkish citizens, child marriage persists in some places and parts of society, including both legal marriages of girls aged 16 and 17, and unregistered marriages of girls by religious ceremony only. The most recent TurkStat statistics show that 23,906 16-17-year-old girls got married in 2017 either with parental consent or approval of a judge (4.2% of all women getting married) compared to 27,637 (4.6%) in 2016. The data also shows regional discrepancies. Child marriage is observed to be practised more among refugees, particularly as a coping strategy, but representative statistics are lacking. Updated data for both Turkish and Syrian refugee adolescents is expected with the 2018 DHS. Government institutions led by the MFLSS begun to work more systematically to combat child marriage among refugee and non-refugee children under a strategy adopted for 2018-2023. A UN joint programme led by UNICEF is ongoing to support these efforts.

2.3.12	The Turkish Disaster and Emergency Management Presidency (AFAD) estimated in 2014 that 15% of 15-18 years old Syrian refugee girls living in and outside camps were married. In a survey conducted in 2018 by UN Women and Association for Solidarity with Asylum Seekers and Migrants

(ASAM), with 1,291 Syrian women and girls across seven cities, more than half of the participants’ age at first marriage was below 18 years old. There appear to be links to trafficking, polygamy and/or sexual abuse and forced labour.

2.3.13	Among Turkish citizens, 22% of all women aged 25-49 were married by the age of 18; while this rate is 14,7% among women aged 20-24 (including 1.1% who were married by the age of 15). More common in Northeast, Centre and South-eastern Anatolia and among certain social groups from disadvantaged backgrounds.   Levels of physical and/or sexual intimate partner violence in Turkish society are high (reportedly 38% over a lifetime).

## 2.4	Education: context and problem statement

2.4.1	The Country Programme Document for 2016-20 (written in 2015) describes the education challenges facing children in Turkey as follows: ‘The uneven quality of teaching and the shortcomings in school environments remain the key bottlenecks that discourage participation in education and prevent disadvantaged students from taking full advantage of education. Access for adolescents to opportunities such as sports, recreation and social participation outside the school is also affected by uneven availability and cost barriers…’

2.4.2	The CPD noted that secondary enrolment among girls had increased rapidly but remained noticeably lower in some provinces than for boys. It also noted that enrolment did not necessarily translate into skills acquisition, social participation and empowerment for young women. ‘According to the OECD, 45 per cent of women aged 15-29 were not in employment, education or training in 2013, compared to 18 per cent for men.’

2.4.3	The situation for refugee children was much worse. The CPD described Syrian children under temporary protection as being ‘at risk of becoming a lost generation. It is estimated that, as of March 2015, only about a third of the approximately 595,000 school-age Syrian children under temporary protection in Turkey were accessing educational opportunities. While over 90 per cent of school-age children in camps were in school, only about 25 per cent of children outside camps were benefiting from education…

2.4.4	Currently, the education challenges for Turkish children remain largely as described in the CPD, though some progress has been made at least in policy terms. The strategy document “For a stronger tomorrow: Education Vision for 2023” unveiled by the Ministry of National Education in October 2018 plans to address key aspects related to the quality and inclusiveness of the education system, including addressing disparities in education, student assessment, challenges in vocational and technical high schools, and the need to reinforce learning of contemporary skills and foreign languages.

2.4.5	The Vision 2023 document also foresees renewed attention and opportunities for children with disabilities (CWDs).  Some CWDs are studying in regular schools, with access varying significantly among education levels. Access for CWDs in pre-primary and primary schools is relatively lower than access in upper-secondary schools. Institutional, physical and human capacity require further development for successful mainstreaming.

2.4.6	The education picture for refugee girls and boys has changed considerably since 2016. As of December 2018, some 645,140 (317,761 girls; 327,379 boys) were enrolled in formal education, representing about 62% of the refugee population in school age. However, despite this progress, about 400,000 refugee children are still out of school for various reasons including language barriers, child labour, gender norms, disability or illness, and lack of information regarding schooling opportunities. Access to pre-primary education is still limited (33%). Adolescents continue to face challenges in access to education, with a gross enrolment for refugee children in upper-secondary education of 26.3%. Education opportunities for out-of-school refugee children are provided mainly through Public Education centres. These education opportunities, including Turkish language courses and Accelerated Learning Programmes, are being strengthened to respond to the diverse needs of those children.

2.4.7	Since 2016, the Ministry of National Education has adopted a policy of gradually moving refugee children from Temporary Education Centres (where they are taught by Syrian volunteer education personnel based on a modified Syrian curriculum in Arabic) to Turkish Public Schools. As of end of 2018, about 85% of the Syrian refugee children enrolled in formal education were in Turkish public schools, as compared to 20% three years earlier.

## 2.5	Social inclusion, protection, cohesion: context and problem statement

Social Inclusion & Social Cohesion

2.5.1 	According to recent OECD Family Database, more than 25% of children live in relative poverty in Turkey, compared the OECD average of 13.4%. This figure relates to the Turkish population; although official statistics are not available for refugee children, the relative poverty rates are especially high among the refugee children living in Turkey.

2.5.2  	The Country Programme Document for 2016-20 (written in 2015) describes social inclusion and resilience building as a programme component that will ‘touch the lives of several million children in all parts of Turkey, particularly benefiting children from the most socioeconomically disadvantaged groups, including children with disabilities, Roma children, as well as children living in locations and provinces most affected by the Syrian influx, child labour and low school participation’.  The same document describes the particular challenges facing Syrian refugee children in Turkey as follows: ‘Syrian children under temporary protection have an acute need for safe and friendly environments for recreation and socialization, and in many cases require psychosocial support to overcome traumatic experiences and ongoing hardship’. A wide body of research supports this: refugees and asylum seekers face a series of obstacles when it comes to social inclusion in host societies, such as legal challenges, negative public opinion, lack of language, lack of information, labour market restrictions and bullying in schools.

2.5.3 	An increasing part of the challenge of social cohesion concerns hardening social attitudes of host communities towards refugees, asylum seekers and immigrants. The World Food Programme has conducted social cohesion online surveys since 2017, the results of which are intended to be used for ESSN programmatic adjustments and by external stakeholders. According to the recent survey findings conducted in July 2018: ‘Syrians tended to be more open to their Turkish hosts than vice versa. For example, refugees were considerably more likely to feel comfortable about working with Turks than Turks were with Syrians (84% vs 45% in January 2018) and more likely to want to share an apartment building with Turks than Turks with Syrians (70% vs. 39% in January 2018). The overwhelming majority of Syrians would be fine with their children being friends with Turkish children (rising by 5% to 86% by January 2018) compared to 46% of Turkish respondents.’ The results of a recent IPSOS survey suggest major public concerns about levels of immigration and suspicion concerning the refugee population (related to a feared influx of terrorists posing as refugees).

2.5.4 	In addition to these surveys, according to a little publicized report from Turkey’s Ombudsman, the Syrian presence is likely to become permanent. The study asserted that “it is necessary to produce policies based on [the expectation of] permanence.” It appears that Turkey is at least unofficially aware that the refugee agenda will be a longstanding one. The 2017 Ipsos survey found that 64% of refugees wanted to stay in Turkey, with that percentage increasing among young people. There is some evidence that in the areas with a high percentage of refugees, significant numbers of Turkish children have been moved from regular public schools into private schools, underscoring fears about social cohesion.

Limited social protection for refugees

2.5.5 	According to the findings of the Thematic Studies on the Extension of Conditional Cash Transfers to Syrian refugees (2018), a primary barrier to education among refugee children is believed to be economic. “The lack of financial means” is cited as the principal reason why the refugee children never attend school or dropped out of school in Turkey. Many families rely on income from child labour due to the parents’ inability to gain a fair wage and said that they could not afford to send their children to school.

2.5.6 	Existing national social protection schemes had limited application to refugee children, though some were covered by social assistance from ad-hoc / NGO sources. With rising rates of out of school children, UNICEF engaged in policy dialogue with the former Ministry of Family and Social Policy (now MoFLSS) which led to the Government of Turkey’s decision to expand the existing national program for education and include (Syrian and non-Syrian) refugee children. It has been made possible with the financial support of the European Union (EU), as well as from Norway and the United States.

2.5.7 	The number of children enrolled in the programme grew from 188,500 in January 2018 to nearly 411,000 in December 2018. Approximately 400 refugee children attending the UNICEF-MoNE Accelerated Learning Programme also began receiving Conditional Cash Transfers for Education (CCTE) payments in late 2018, enhancing the programme’s equity focus. Over 80 per cent of CCTE beneficiaries also benefit from the Emergency Social Safety Net, demonstrating the complementarity between the two programmes.

Child Labour

2.5.8 	Based on Child Labour Survey conducted by Turkstat, and is stated in Country Programme Document for 2016-2020, child labor still persists, and this includes children working in the street and in small industrial and service enterprises, as well as migratory and seasonal work in commercial agriculture: “in 2012, a total of 893,000 children (614,000 boys, 279,000 girls) were engaged in economic activity. This represents 5.9 per cent of children (15.6 per cent of children 15-17 and 2.6 per cent of children 6-14) and shows little sign of improvement since 2006”.

2.5.9 	With regard to refugee children, although there is little available data, several sources confirm that child labour is widespread among refugee children in Turkey. A monitoring exercise conducted by UNICEF and partners among over 5,000 families (11,444 children 5-17 years old) in 8 provinces between February and April 2017 suggests that approximately 15% of refugee children are involved in economic activities.

2.5.10 	The coverage of legislation against child labour is incomplete and enforcement has been very limited. In early 2017, a new ‘National Programme for Combating Child Labour 2017-2023’ was published by the Ministry of Labour and Social Security together with a related Action Plan and 2018 was declared as a year of struggle against child labour. However, there is little emphasis on refugee children although they are referred to as one of a number of vulnerable groups.

Early Childhood Development

2.5.11 	According to TurkStat data, infant and under-five mortality were 9.2 and 11.2 respectively, per thousand live births, in 2017 compared to 10.2 and 12.4 in 2015. Even though child mortality continues to decline among Turkish citizens, regional disparities persist, with the infant mortality rate rising to 10.2 in Southeast Anatolia. The 2013 DHS put full immunization at 74.1% and stunting at 9.5%. Child mortality continues to decline among Turkish citizens.

2.5.12 	No representative statistics are publicly available for specific groups of children, including refugee children who may face more difficulties in accessing health services. However, the upcoming report of the 2018 Demographic and Health Survey (DHS) is expected to provide updated data on child health and nutrition for Turkish and Syrian refugee children.

2.5.13 	According to 2023 Turkey’s Education Vision Document, the Ministry of National Education is working on a national policy to make at least one year of pre-school education compulsory in the near future.  In the 2017-18 school year, the net enrolment rate for 3-5-year-olds rose to 44.02% from 39.54% in the 2015-2016 school year. By December 2018, around 48,000 children were enrolled in school, community or home-based ECE activities across Turkey, a 20  increase over 2017.

2.5.14 	Although the importance of ECD is recognized and is becoming a national priority, there is limited coordination on this agenda and a lack of an integrated approach. The evaluation will consider UNICEF’s potential future role in this area.

## 2.6	Social Policy, Monitoring and Data: context and problem statement

2.6.1. 	There are insufficient arrangements for child rights monitoring in Turkey. Policy implementation is monitored through mechanisms that often do not hold government agencies accountable and do not support performance improvement. According to the 2015 EU Progress Report on Turkey, ‘the 2013 national children’s rights strategy and action plan were not implemented, and the Children’s Rights Monitoring and Evaluation Board did not meet’. The ombudsperson for women’s and child rights receives complaints concerning public institutions, but it is not fully independent. The child rights monitoring sub-committee in Parliament no longer meets. With the Ombudsperson’s Institution (OI), UNICEF contributed to developing new mechanisms for managing and investigating complaints, and enhanced systems to improve access for children to the institution.

2.6.2. 	According to the relevant UNICEF theory of change, there are two key bottlenecks leading to policies and service provision not being informed by (solid) evidence: the non-availability of evidence and the limited use of evidence.

(i) (Solid) evidence is often not available. Evidence is not available either because it is not (or is only partially) generated (e.g. on GBV, child abuse, violence and neglect, disabilities), or it is generated but not accessible, or it is not reliable and/or is outdated.

(ii) Available evidence may not be used for decision-making, especially in a context of low political transparency. There is some reason to think that, in Turkey, policy-making is at times discretionary and managed through ad-hoc mechanisms.

2.6.3. 	UNICEF planning documents note that there is a need not only to monitor individual child care cases better, but also to collect more quality data on the system and the profiles of its beneficiaries, to introduce stronger and more meaningful complaints and appeals mechanisms, and to break down the resistance of the child care authorities and personnel to transparency and independent monitoring.

2.6.4.	A critical factor leading to limited transparency are the gaps in the public accountability systems and the limitations in the freedom of expression. At the same time, another critical bottleneck is the limited capacity of independent CRM mechanisms (CSOs, NHRI) to leverage evidence for decision-making as well as for monitoring and hold policy-makers accountable. The CSOs’ constrained operating space and lobbying capacity along with the limited technical expertise translate into few opportunities for independent evidence generation, partnering with GoT for this purpose, and evidence-based advocacy.

2.6.5. 	The acute political polarization is an important structural factor influencing the CSOs’ capacity to mobilize independent resources and to properly fulfil their role. Another key structural factor is GoT’s tendency to restrict access to information and opportunities for collaboration with CSOs, with the aim to fully control decision-making processes. Even data collection is sometimes strictly forbidden. A 2015 decree of the Ministry of Interior restricts data collection about refugees and requires approval for such data collection from the Ministry for Interior. UNHCR has no involvement in the refugee registration process, which further limits availability of data.

2.6.6. 	Other independent CRM actors such as the National Human Rights Institution have limited leverage capacity. While evidence generation is part of the NHRI’s mandate, this is not fulfilled at the moment due to capacity gaps and its limited level of independence. The main structural causes behind the weaknesses of independent CRM systems relate to the weak separation of power and public accountability systems, reflecting the observed limitations to the freedom of expression in the country.

2.6.7. 	On judicial cooperation in civil matters, Turkey is now party to most international conventions in this area, including the 1996 Hague Convention on Jurisdiction, Applicable Law, Recognition, Enforcement and Cooperation in Respect of Parental Responsibility and Measures for the Protection of Children. The 2007 Hague Convention on the International Recovery on Child Support and Other Forms of Family Maintenance entered into force in February 2017. Turkey still needs to take effective measures to ensure shorter timeframes for proceedings in the context of the 1980 Hague Convention on civil aspects of the international child abduction. Turkey has not yet acceded to relevant international conventions in the area of civil justice. Turkey has signed, but not yet ratified, the 1983 European Convention on the Compensation of Victims of Violent Crimes.

2.6.8. 	UNICEF has been involved in the consultations for the preparation of the 11th National Development Plan for 2019-2023 and the nationalization of the Sustainable Development Goals (SDGs) led by the Strategy, Planning and Budgeting Office of the Presidency (earlier Ministry of Development). Both processes represent important opportunities to prioritize child-related issues within the scheme of national priorities and to advocate for inclusive strategies that advance the agenda for children in the longer term. In this context, the engagement with the Strategy, Planning and Budgeting Office of the Presidency (earlier Ministry of Development) and the Turkish Statistical Institute (TurkStat) opened up a dialogue on the measurement of indicators to set baselines and measure progress against the SDGs in Turkey.

# 3.	Subject of evaluation: UNICEF’s strategy and programme

## 3.1	UNICEF’s strategy and evolving priorities

3.1.1	UNICEF’s strategy in Turkey, as set out in the 2016-20 CPD and related documents, reflects both the particular nature of the Turkish context and UNICEF’s global priorities under successive corporate strategic plans. It is aligned with the Government of Turkey’s national priorities and the UN Development Cooperation Strategy (UNDCS) for Turkey. It has also been aligned with relevant frameworks concerning Syrian refugees. New global and national strategic frameworks have come into force since the CPD was developed, including the SDGs and the Agenda 2030, the Global agenda on Migration, the 2018-21 UNICEF Strategic Plan & the Gender Action Plans (2014-17 and 2018-21).

The volatile and rapidly evolving nature of the political, security and social context in Turkey over the evaluation period raises questions about the effective evolution of a strategy that was originally designed in 2015, and the evaluation will consider this issue in assessing both the past and future role of UNICEF in Turkey.

3.1.2	In seeking to address the priority issues facing girls and boys in Turkey (Turkish and other), UNICEF defined four Outcomes in the CPD to which the country programme is designed to contribute, based on the progressive realisation of rights. Related to this, and seen as key intermediate steps, are a series of Outputs that the programme is intended to deliver (relating to the removal of key bottlenecks and barriers to progress), together with a range of implementation or change strategies by which these will be achieved. The overall logic is set out in an overarching Theory of Change annexed to the CPD; and the logic of some (though not all) of the related programme components is spelled out in separate theories of change. These and the related strategies will be further analysed in the course of the evaluation (see further under ‘evaluation approach’ below).

3.1.3	UNICEF’s programme grew dramatically in response to the escalating influx of (mainly Syrian) refugees, from an operation with 56 staff members and a budget of USD 35 million in 2014, the CP deployed 122 staff members and had a budget of USD 181 million at the end of 2018. One major challenge for UNICEF over the evaluation period has been to effectively combine a major operational crisis response to the escalating refugee crisis with a more systems- and policy-based approach to the wider issues affecting children’s development and well-being in Turkey. This it has consciously tried to do by incorporating the refugee response into the wider country programme. The related humanitarian-development ‘nexus’ issues will be explored in this context, including issues of future sustainability and integration.

3.1.4	The 2018 COAR reflects the attempt to balance these priorities: ‘This year, UNICEF Turkey continued to maintain a balance between addressing the specific and urgent needs of refugee children and working to uphold the rights of all vulnerable children in the country. The humanitarian response is fully integrated in the Country Programme and refugee and migrant children are seen as one of the vulnerable groups of children who are at risk of being left behind – albeit a group which remains very large and continues to face particular vulnerabilities.’ The integration of the humanitarian and development strands of UNICEF’s programme in the 2016-20 CPD reflected a determination to take a system-strengthening approach to what has increasingly become a chronic situation for the refugees – and reflected the Government’s own de facto approach to integrating refugee service provision into mainstream services, most notably in education. The evaluation will consider the merits of this decision, and in particular whether the system-strengthening approach has worked.

3.1.5	The 2018 Programme Review highlighted the need for a more cross-sectoral and integrated approach particularly in certain programmatic areas – namely, early childhood development, adolescents, and out-of-school children. It concluded that addressing the child rights issues affecting these vulnerable groups of children requires a more integrated approach to tackling the multiple bottlenecks and barriers that span different sectors and stakeholders. The present evaluation will consider the extent to which UNICEF has made progress in this regard.

3.1.6	UNICEF Turkey has identified public finance for children as an emerging priority, notwithstanding the present contraction in fiscal space in 2019. In preparation for the next country program cycle, TCO therefore intends to build its expertise in this field and explore the possibility of engaging on priority issues in the short term. The 2018 Programme Review identified limited capacity and engagement on this issue as a constraint. UNICEF programming in this area has become common in other middle-income countries with greater fiscal space to fund large-scale national programmes for children, as well as to institutionalize related services. This an issue that will be considered (with a forward perspective) in the evaluation.

Figure 1		Outline of the UNICEF Turkey Country Programme 2016-20

3.1.7	The relative expenditure across different programme components for the years 2016-19 is shown in Tables 1 and 2 below, grouped according to UNICEF’s global Goal Areas as specified in the 2018-21 Strategic Plan. Total country expenditure is also shown for years since 2013. Two things in particular stand out. One is the trajectory in the scale of the programme: major growth from 2013, fuelled by the emergency response to the Syrian refugee influx, and continued growth from 2016-18. Budget figures suggest a levelling off in programme scale in 2019, perhaps reflecting a gradual shift away from direct service provision. The second feature is the dominance of certain programme components, particularly Education work (predominantly refugee / access-related), which constitutes around 60% of programme expenditure over the CPD period to date. Protection (predominantly community-based) constitutes around 15% over the same period, while Equitable Chance in Life (dominated by social protection for refugees) constitutes around 18%.

Patterns of budgeting and expenditure will be analysed in more detail in the full evaluation report, along with prospects for future funding. Here it is noted that a large (though as yet unquantified) proportion of programming is refugee-related and that much of this occurs in the southeast of the country in provinces and municipalities including Gaziantep, Sanliurfa, Kilis, Hatay/Antakya and Adana, where refugee communities live alongside host populations in relatively high concentrations. These programmes are overseen by the UNICEF Field Office in Gaziantep.

Table 1: Annual UNICEF expenditure in Turkey (USD) by programme component 2016-19

|  | 2016 | 2017 | 2018 | 2019* | Total |
| --- | --- | --- | --- | --- | --- |
| Survive and Thrive | 337,576 | 309,705 | 28,567 | 281,527 | 957,375 |
| Immunization, nutrition support |  |  |  |  |  |
| Learn | 73,545,123 | 87,255,609 | 81,528,173 | 51,056,609 | 293,385,514 |
| Educational access, quality, outcomes |  |  |  |  |  |
| Protection from Violence and Exploitation | 10,434,175 | 20,653,261 | 26,508,680 | 19,258,030 | 76,854,146 |
| Prevention, response, GBV, child marriage, access to justice |  |  |  |  |  |
| Safe and Clean Environment | 389,547 | 706,169 | 609,303 | 430,127 | 2,135,146 |
| Urban children, multi-sector interventions for Rs and migrants |  |  |  |  |  |
| Equitable Chance in Life | 6,591,631 | 17,453,381 | 46,817,602 | 36,969,737 | 107,832,351 |
| Child poverty, social protection, adolescent empowerment |  |  |  |  |  |
| Cross-Sectoral | 5,619,213 | 7,458,508 | 8,776,420 | 8,306,088 | 30,160,230 |
| M&E, data analysis, C4D, advocacy, logistic and operational costs |  |  |  |  |  |
| Development Effectiveness | 201,847 | 608,140 | 404,376 | 374,404 | 1,588,767 |
| External relations, coordination |  |  |  |  |  |
| Management | 104,679 | 366,892 | 479,570 | 232,237 | 1,183,378 |
| Special Purpose |  | 305,672 | 86,630 |  | 392,302 |
| Grand Total | 97,223,791 | 135,117,337 | 165,239,321 | 116,908,760 | 514,489,209 |

Table 2: Annual UNICEF expenditure in Turkey (USD) since 2013

| 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019* | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 17,728,126 | 33,645,903 | 54,316,300 | 97,223,791 | 135,117,337 | 165,239,321 | 116,908,760 | 620,179,538 |

## *Figures to July 2019

## 3.2	UNICEF’s programme

3.2.1	We set out below the UNICEF programme elements that (along with UNICEF’s strategy) will form the main subject of this evaluation. The rationale for this focus is explained in section 4 below. For the purposes of this evaluation, and for ease of reference, we group together related programme elements into distinct ‘Components’, some of which relate to two or more of the Outputs shown in the Figure 1 above.

Child Protection

3.2.2	CP Component 1: Strengthening Turkey’s child protection system (Output 1.C, 3B)

Under this heading, the evaluation will consider UNICEF’s work to help strengthen the Turkish child protection system as a whole, in addition to reviewing more specific areas of work listed below. As set out in the CPD, this includes strengthening the child protection system’s mechanisms for detection, referral, assessment, prevention and management of cases of Turkish and refugee CWDs, children victims or at risk of abuse, violence, neglect and commercial exploitation and children without parental care. It includes strengthening of the national system managed by Ministry of Family Labour and Social Services and also the child protection component of the Conditional Cash Transfer programme for Education of refugee children.

3.2.3	CP Component 2: Child care and social welfare (Outputs 1.D and 3.B)

This component includes the following elements:

- Investments in state capacities: outreach, case management, specialized child protection programmes (MoFLSS and DGMM)

- Social service workforce strengthening (MoFLSS)

- Strengthening gate-keeping mechanisms and introduce new models of family-based care (temporary foster care) (MOFLSS)

- Support efforts to strengthen policies and regulatory mechanisms (DGMM and MOFLSS)

- Strengthening linkages between child protection and social protection (Conditional Cash Transfer for Education including Child Care Component in selected areas) (MoFLSS, MoNE, other?)

- Strengthening state capacity to scale up child marriage prevention and response efforts (MoFLSS)

This component is realized through a mix of strategies: capacity development – including training and providing technical expertise – advocacy and policy dialogue, together with modelling and innovating (for the CP component of the CCTE). Strategies were implemented essentially as planned in the CPD, though the C4D element is more recent with its focus on positive modelling and innovation on gender roles. Also, the CCTE now includes adolescent boys as there is recognition that there are gender differential and different risks for boys and girls.

This mix of strategies, while addressing immediate humanitarian needs (e.g. CCTE) also contribute to realizing sustainable achievements for children (e.g. regulatory mechanisms and capacity development of specialized professionals). This component of the CP Programme equally addresses the needs of Turkish and refugees/migrant children, and no social cohesion issues are anticipated. The issues of the sustainability of the CCTE and related child-care work will be considered in the evaluation.

Related themes: Resilience, social inclusion, social cohesion, humanitarian-development nexus

3.2.4	CP Component 3: Child Protection Services (Output 1.C)

This component includes the following elements:

- Provision of critical Child Protection services to the most vulnerable refugee children and their families including psycho-social care; crisis counselling; case management services, safe and timely referral to specialized services; family tracing and reunification.

- Expand primary prevention services in refugee dense areas with a focus on reaching families and children with child rights and child protection information and awareness raising as well as positive parenting skills, including through outreach and mobile team, collaboration with municipalities and community schools

- Strengthen the capacity of relevant authorities to better address the specific needs of refugee children, including through attaching partner staff to municipalities with the aim to fill critical gaps in child protection services (AFAD, DGMM, MoI).

This component is realized through direct service provision in partnerships with NGOs and civil society. The political context has impacted on the number and quality of UNICEF partners and consequently on UNICEF’s reach. Capacity to deliver through local authorities may be influenced by social cohesion issues/political agenda; and one question is whether this alternative model can fully replace implementation though civil society (other than Turkish Red Crescent).

Related themes: Humanitarian-development nexus, resilience, social cohesion

3.2.5	CP component 4: Justice for Children and Child Rights Monitoring (Outputs 1.E and 2B)

This component includes the following elements:

- Ensure specialized administration, procedures and governance for children in contact with the justice system through situation analysis, policy formulation, and capacity development

- Promote alternatives to imprisonment (diversion) with a focus on probation services

- Mitigate and prevent the secondary victimization of children victims of crime (Child-Friendly Rooms)

- Strengthen advocacy actions to accelerate the realization of children’s rights, consolidate channels for redress mechanisms: collaboration with the Ombudsperson for Children

- Strengthen capacity of CSOs for advocacy on VAC (ECVAC)

- Policy dialogue vis-a-vis Parliament and other CRM bodies)

- Rolling work plan with the Government of Turkey’s Ombudsman Institution, etc.

Falling under Outcome 1 (Equity increased through social inclusion and resilience-building), the key Output here is 1.E: By 2020, the justice and protection systems have increased capacity to provide children and adolescents in contact with the law with a second chance. This output is mainly dedicated to improvements in relevant policy and institutional frameworks in Turkey and aligning it with UN and the EU frameworks.

The main strategies used to implement this output have been capacity development and evidence generation, policy dialogue and advocacy. These strategies have not changed during the observed strategic period.

Related themes: social inclusion, child rights, gender equality

3.2.6	CP Component 5: GBVIE and ending child marriage (Output 3B)

Interventions and strategies on ending child marriages and GBVIE (including PSEA) are largely embedded in child protection with the main focus on prevention (i.e. CBCP, CCTE) and education for adolescent girls and boys.  Main interventions have included:

- Local large-scale initiative for the prevention of child marriage initiated in 2016 in collaboration with Gaziantep Municipality.  Expanded to Kilis municipality.

- Joint UNCT Programme (UN Women, UNFPA, UNHCR and IOM) led by UNICEF on ending child marriage, builds on the Gaziantep model, with implementation commencing in 2018, funded by Sida.  The focus is to strengthen the policy environment, building and strengthening local institutions capacities (main partner is MoFLSS).

- Community-based prevention, referrals and response mechanisms on ending child marriages and GBV are strengthened through positive parenting, legal and rights-based capacity development.

- C4D interventions have changed its emphasis from challenging harmful social norms on gender to focusing on positive modelling and alternative role models on gender to promote gender equality at community level (in 12 target provinces).

- New partnerships have expanded to include the private sector.

This component builds on partnership and triangular cooperation by supporting development of local models and knowledge sharing on ‘what works’. It involves identifying and promoting innovative approaches – especially on data generation and girls’ empowerment.  UNICEF uses its convening power for to ensure cross-sectoral linkages – especially between child protection and education systems, but also with resilience, sexual health and right programmes.

Related themes: Gender equity, girls’ empowerment, resilience, social inclusion, humanitarian-development nexus

Education

3.2.7	Education component 1: Access to formal education for refugee children 3- 17 (Output 1.A)

This component includes the following elements:

- Scaled-up availability of inclusive and child friendly learning environment for refugee children.

- Strengthening package of policies and mechanisms regulating and managing the teachers’ and other education personnel’s remunerations and other kinds of incentives (education personnel management strategy).

- Supporting families of refugee children to sustain school-related costs.

- Distribution of school bags, stationery kits to Syrian and vulnerable Turkish students

- Increasing awareness of families of refugee children on access to education, inclusiveness and child-friendly education environments (this includes pilot actions on early childhood education).

- Strengthened planning and inter-sectoral coordination mechanisms.

This component is realised through a combination of service delivery, capacity development, and policy engagement and advocacy. While the mix of strategies has remained the same across the timeframe of the evaluation, country programme, their relative weight has changed, shifting from a prominent emphasis on service delivery at the beginning of the country programme, to increased focus on policy and advocacy and developing capacities of education personnel. Despite this shift, the service delivery strategy (direct financial support) is still important due to the CCT incentives and financial incentives to Syrian volunteer teachers. But there are questions about the sustainability of this approach.

Related themes: Humanitarian-development nexus, resilience, social inclusion, social cohesion

3.2.8	Education component 2: Access to quality and inclusive education for vulnerable children from 3 to 17 (Output 1.B)

This component includes the following elements:

- Strengthened professional development system for education personnel serving vulnerable children including refugee children and children with disabilities (CwDs). This includes package of policies and mechanisms, including pre- and in-service trainings, aiming at the professional development of both Turkish and Syrian teachers, counsellors and other relevant education personnel serving vulnerable children, including CwDs and refugee children (in TECs and in the mainstream education system). This includes pilot actions on early childhood education.

- Develop, provide, revise and/or upgrade standards, curricula and learning environments, including relevant age- and need-specific learning resources for children with special needs.

- Systematic and enhanced student assessment system (adapt a formative-type student assessment system for all children, 12th grade exam in Arabic for Temporary Education Centres and 8th grade exam for refugee children)

- Strengthened education information management systems for systematic analysis and for informing decision making.

- Public awareness on quality inclusive education.

This is realised through direct financial support for exams, capacity development of education personnel, technical assistance (curricula development), policy dialogue and advocacy, and     modelling and innovation (YOBIS IM system). C4D is used as a tool to support the development of communication strategies to address negative social norms against vulnerable groups and raise awareness on education benefits for CwDs and other vulnerable children.

Related themes: Social inclusion, social cohesion. This component provides good examples of the humanitarian-development nexus, including on sustainability.

3.2.9	Education component 3:  Education Opportunities for Adolescent Girls and Boys (Output 3.A)

This component includes the following elements:

- Supporting education systems to provide education opportunities relevant to specific needs of adolescents with a special focus on refugees, children at risk of non-attendance and drop-out and gender related issues.

- Expanding the quality educational offer within non formal education, informal education and other forms of education beyond the formal system for vulnerable adolescent girls and boys (including refugee adolescents).

- Refugee adolescents and their families with increased knowledge on education opportunities in Turkey

- Adolescents and their families with more supportive socio-cultural norms and behaviour toward education and economic barriers of vulnerable families and their children in relation to education increasingly addressed

This component is realised through provision of technical assistance, direct financial support, policy dialogue and advocacy (including promoting inter-ministerial coordination), and capacity-building of different stakeholders, including the relevant central and local governmental authorities. Again, C4D is used as a tool to support the development of communication strategies to address negative social norms related to traditional gender roles of adolescent girls and boys, and to raise awareness on education benefits for vulnerable adolescents

Related themes: Gender equity, girls’ empowerment, social inclusion, social cohesion

3.2.10	Education component 4:  Early Childhood Development

This component includes the following elements:

- Expanding early childhood education and making it available to refugee as well as Turkish children, e.g. via summer schools.

- Develop, provide, revise early learning materials and curricula, including development of home based ECE modules; and provision of age-appropriate and need-specific furniture, equipment and learning materials for children.

- Reaching out to refugee families to increase their knowledge and raise the importance of Early Childhood Education in Turkey by creating a mobile phone application translated into Arabic

- Creating public awareness of early childhood education via high-level initiatives and events in Ankara, including the launch Inclusive Early Childhood Education programme

This component is realized through capacity development targeting line Ministries staff, especially MoNE teachers, provision of service delivery and technical assistance, engagement in policy dialogue, partnerships with Ministry of National Education (MoNE), the WHO and the Ministry of Youth and Sport as well as national NGO partners such as ACEV (Mother and Child Education Association) with the aim of expanding the access to early childhood education for vulnerable Turkish children and refugee children, creating a robust and extensive network for young people in host communities. The outreach strategy of the vaccination campaign conducted by UNICEF and WHO involved NGOs in information dissemination and included a Communication for Development (C4D) campaign supported by UNICEF.

Related themes: Social inclusion, social cohesion and humanitarian-development nexus.

Social Protection and Social Cohesion

3.2.11	SP/SC Component 1: Conditional cash transfers for education + child protection (Output 1D)

The large Conditional Cash Transfer for Education (CCTE) programme for refugee children in Turkey aims to improve school enrolment and retention in school, recognizing the differential risks and barriers for girls and boys. It has two main sub-components:

- Cash component: This conditional cash transfer scheme tries to alleviate financial barriers in access to education, providing cash every two months under the condition that their children attended school on at least 80 percent of school days in preceding months. The cash component is aligned with the national CCTE programme in terms of eligibility, conditionality, amount and frequency of payments; and it uses the same application process and payment platform as the Emergency Social Safety Net (ESSN) programme. Both programmes are guided by that national Social Assistance Law, by which the family members of the applicant household are expected to be registered in Turkey and not have a regular income or social security. Hence, there is an overlap between beneficiaries of ESSN and CCTE programmes.

- Child protection component: The intended benefit of the CCTE is not limited to its financial contribution. It includes a child protection component, under which field teams reach out to households in which children attend school irregularly or have stopped attending school, in order to identify the needs of children and their families and facilitate access to appropriate services. This component, implemented in 15 Provinces with a high number of refugees, aims to mitigate and respond to risks that hinder children from going to school. The CCTE programme is implemented through a partnership between the Ministry of Family, Labour and Social Services (formerly Ministry of Family and Social Policies), the Ministry of National Education, the Turkish Red Crescent Society and UNICEF.

This component has been achieved through using the following implementation strategies: capacity development of implementing partners, such as Turkish Red Crescent (TRC), provision of technical assistance and system strengthening, direct service delivery, policy dialogue and partnerships with the former Ministry of Family and Social Policy (now MoFLSS), Ministry of National Education and TRC, and evidence-based advocacy on further revision of social policies based on the experience of the CCTE programme. C4D is also used as a tool to change attitudes to education among refugee families and to promote gender equality, though this is acknowledged to be a longer-term agenda.

Related themes: Humanitarian-development nexus, resilience, gender equity, social inclusion, social cohesion

3.2.12	SP/SC Component 2: Social cohesion interventions (with particular focus on adolescents and on refugee-host community cohesion) (Output 1F)

Already before 2016, UNICEF and its partners were working to empower Syrian and Turkish adolescents and young people through social cohesion and community-based peace-building activities, reaching 11,500 young people and adolescents in ten provinces in 2015. Under the umbrella of ‘No Lost Generation’, UNICEF and partners galvanized a global coordinated effort to protect the futures of Syrian children. International actors have come together to expand access to learning and psychosocial support, and to strengthen social cohesion and peacebuilding. However, there is no clear strategy and focus (yet) for the future work of UNICEF Turkey in the area of social cohesion.

Initiatives under this heading include:

- The Mobile Circus, which came through the Southeast Anatolia Project (GAP) Administration partnership with UNICEF’s ‘Child Friendly Cities’ initiative

- Social Cohesion Activities especially in SE provinces heavily populated by refugee population

- Initiation of ‘Girl Friendly’ and ‘Adolescent Friendly’ Centres

- Coordination workshops on social cohesion

This social inclusion component is realised through service delivery; provision of technical assistance to various line Ministries personnel; partnerships with line ministries including MoFLSS and the Ministry of Youth and Sports (MoYSP) and also NGOs, such as Southeast Anatolia Project (GAP); capacity development of different partners, such as ministry personnel, Ombudsman staff, etc.; and policy dialogue with ministries and relevant municipalities

Related themes: Social inclusion, social cohesion and humanitarian-development nexus.

Social Policy, Monitoring and Data

3.2.13	SPM&D Component 1: Strengthening the evidence base on child rights

Output 2A: By 2020, relevant line ministries, Turkstat (TUIK), National Human Rights Institution (NHRI) and CSOs have increased capacity to generate and use quality and disaggregated evidence on the situation of children for monitoring, reporting and advocacy purpose.

In this component, UNICEF mainly focuses on: 1) strengthening government and non-government capacities to generate reliable and quality evidence on children, especially vulnerable groups of children, through surveys/studies, administrative data systems and registry systems and 2) strengthening CSOs’ (NGOs, CBOs, the media, universities) capacity to report on the equitable realization of child rights.

The output targets all children of Turkey, including children refugees. Output 2A is mainly focused on creating enabling evidence basis for systemic strengthening of the child rights.

The main strategies applied to implement this output have been capacity development, identification and promotion of innovation, partnerships and evidence generation, policy dialogue and advocacy. These strategies have been applied during the implementation of the CPD and haven’t changed during the evaluation period.

Related themes: Social inclusion, child rights, gender equity, humanitarian-development nexus.

3.2.14	SPM&D Component 2: Strengthening child rights monitoring

Output goal 2B: By 2020, relevant human rights monitoring mechanisms have increased capacity to monitor child rights violations and activate redress actions in line with international standards and good practices.

Through this output UNICEF mainly focuses on: 1) strengthening the procedures to facilitate access to justice for children in contact with the law (all children living in Turkey) and 2) strengthening the ombudsperson’ and NHRI’s capacity to independently assess, address and report on individual and collective child rights violations.

The output targets all children of Turkey, including children refugees. Output 2B is mainly focused on creating and strengthening mechanisms to monitor child rights in line with international standards and practices.

The main strategies applied to implement this output were capacity development, evidence generation, policy dialogue and advocacy as well as integration and cross-sectoral linkages.

Related themes: Social inclusion, child rights, gender equity, humanitarian-development nexus.

# 4.	Evaluation purpose, scope and approach

## 4.1	Evaluation purpose, intended use and expected users

Evaluation purpose and intended use

4.1.1. As described in the ToR, this evaluation serves both accountability and learning purposes. We understand the primary rationale to be to analyse and draw lessons from the experience of the UNICEF country programme in Turkey from 2016 to date, in order to help inform the design and implementation of the future programme, including the drafting of a new CPD for 2021-25. It is expected that the conclusions and lessons drawn from the evaluation will also support preparations of the United Nations Development Cooperation Strategy (UNDCS) for 2021-25 with which the next CP will align.

This is a strategic evaluation rather than a more technical one, designed largely to help answer questions about UNICEF’s proper role in the Turkey context (and perhaps in Upper Middle-Income Countries more generally). In its summative (retrospective) aspect, it will evaluate performance to date across the whole programme and lessons arising from implementing that programme. In its more formative and forward-looking aspect, it will consider UNICEF’s strategic positioning and the programmatic and operational choices made during the CP implementation period in order to draw out good practices, and forward-looking lessons and recommendations.

Expected Users

4.1.2	The ToR distinguishes two groups of expected users. The first (primary stakeholders) are those involved in implementation of the CP or programmatic frameworks, plans or strategies towards which the CP contributes – including partners, donors and staff involved in the implementation of programme. The second (secondary stakeholders) consists of rights holders and duty bearers who benefit from the contributions of the CP, and organisations inside and outside Turkey with which UNICEF does not have any formal partnership but that work with similar programmes and for which lessons and good practices drawn from the CPE may be relevant.

The primary stakeholders are identified as follows:

The Government. The Government of Turkey constitutes the main partner – notably, the Strategy and Budget Office (SBO) that coordinates and oversees the CP document development and implementation and the UNDCS. The evaluation will also be of particular interest to the line ministries with which UNICEF collaborates (see Annex E).

UN partners. UNICEF works closely with other UN agencies In Turkey, most notably: the World Food Programme (WFP); the Entity for Gender Equality and the Empowerment of Women (UN Women); the United Nations Population Fund (UNFPA); the United Nations High Commissioner for Refugees (UNHCR); the  International Organisation for  Migration (IOM); the United Nations Development Programme (UNDP); the World Health Organisation (WHO) and the UN Resident Coordinator’s Office in Turkey. It is expected that the evaluation conclusions and lessons learned will be important for these collaborations, not least to optimize joint contributions, synergies and complementarity.

Other partners. Non-governmental organisations (NGOs) alongside other cooperating partners will also have a direct stake in the findings and recommendations (see Annex E)

Donors. UNICEF’s bilateral and multilateral donors – without which a programme of this scale and diversity would not be possible – have a direct stake in the evaluation findings, particularly as these related to UNICEF’s performance (accountability). A list of the donors is included in Annex E.

UNICEF stakeholders. Besides the UNICEF Turkey Country Office, this includes a variety of internal users including: the Regional Office for Europe and Central Asia (ECARO); the Regional Office for the Middle East and North Africa (MENARO) that plays an important role in the Syria refugee crisis response, and senior management in UNICEF who can draw upon the evaluation findings for regional and corporate learning and accountability purposes. The evaluation may inform future programme design; assessments of how regional and corporate priorities are implemented; and it may further UNICEF’s understanding of its role in Upper Middle-Income Countries (UMICs), and its work on the humanitarian - development nexus.

## 4.2	Scope, focus and evaluability issues

4.2.1	The UNICEF Turkey programme is a large and complex one. The terms of reference for the evaluation set a very ambitious agenda, including both summative and formative elements and a five-year timeframe. While stressing the strategic character of a CPE, and the overarching emphasis on the OECD Development Assistance Committee (DAC) criterion of relevance, the ToR expect that the evaluation will:

- Undertake a ‘performance review’ of the whole programme (humanitarian and development) against all of the DAC evaluation criteria over a period of five years;

- Assess progress made in that period towards planned results and contribution to the national development agenda;

- Assess UNICEF’s strategic positioning, its use of change strategies and its operational and programmatic choices; and

- Identify good practices and lessons learned.

All this with a view to making recommendations that will help inform the writing of the new UNICEF CPD for 2021-15, and potentially also the UNDCS for the same period.

4.2.2	To make the above task manageable, and following discussion with the TCO and ECARO, the team proposes to adopt the following more focused approach:

- Focus on the period 2016-19 (i.e. the period covered by the current CPD), with greatest emphasis placed on the more recent and current programme.

- Focus on three DAC criteria – relevance, effectiveness and sustainability – with due reference to complementarity and coordination with others. Timeliness of response will be considered under the heading of effectiveness. With regard to impact, the potential for impact will be considered, but no attempt will be made to assess actual impact. Rather, the evaluation will consider what mechanisms exist to gauge impact over time. With regard to coherence, the evaluation will consider the fit between UNICEF’s strategy and those contained in the UNDCS and Regional Refugee and Resilience Plan (3RP).

Issues relating to efficiency will be noted as they bear on programme performance, and the use of results-based management will be reviewed (relating as it does directly to effectiveness), but efficiency will not otherwise be separately evaluated. This means that there would be limited coverage of the operational aspects of delivering the UNICEF programme. However, the evaluation will consider whether the programme was adequately resourced, and how UNICEF managed to support the scale up the programme over time. Some attention will also be given to future resourcing (funding, HR).

- While the performance of all elements of the programme will be reviewed against the three main criteria above, for the more analytical and lesson-learning aspects of the evaluation,  it is proposed to focus in more depth on four main areas of intervention contained within Outcomes 1-3, namely: Education (Outputs 1A, 1B); Child Protection (Outputs 1C, 1D, 3B, J4C); Social Protection and Social Cohesion (Outputs 1D, 1F, 3A); and Social Policy, Monitoring and Data (Outputs 2A, 2B). Gender issues will be considered throughout. Outcome 4 will not be evaluated.

- Primary focus on the following implementation/change strategies: service delivery, capacity development (including technical assistance), partnership, system strengthening, evidence generation, policy advice & advocacy. Although the use of service delivery by UNICEF (and to some extent also capacity development) is diminishing, it has played an important part in the programme over the evaluation period. More emphasis, however, will be given to the growing areas of system strengthening, policy advice and advocacy, including an analysis of the political and operational scope for such approaches in the evolving context. Partnership will include both government (national and local, including municipalities) and civil society partnerships, including consideration of shrinking civil society space and traditional partnerships with INGOs.

Performance review

4.2.3	The evaluation team understands ‘performance review’ to entail (primarily) a review of results achieved against stated programme targets and objectives. Besides this ‘effectiveness’ focus, the evaluation will also review each programme component against the criteria of relevance and sustainability. More generally, with regard to the humanitarian – development nexus, the evaluation will consider how well UNICEF managed the links and transition between these two agendas.

Strategic focus

4.2.4	The evaluation team understands the CPE to be an essentially strategic exercise. Other planned or completed evaluations are focused on the more technical, design and delivery aspects of some key programme components. No attempt will be made to cover the same ground, although the results from these more technical evaluations will be reflected as appropriate in the CPE.

With regard to major cross-cutting issues, we propose a primary focus on the themes of:

Social cohesion (with the successful integration of refugees a specific focus), the humanitarian-development nexus and social inclusion/equity (with a focus on gender equity).

Evaluability issues and limitations

4.2.5	As described above, the scale and complexity of the UNICEF country programme, and the length of the period to be evaluated, mean that there are inevitable limits on what programme elements it is possible to cover in a time-limited evaluation, and in what depth. There is a matter of ongoing discussion with the TCO/ ECARO. The proposed dominant focus on the more recent and current programme is in part a reflection of this practical limitation.

4.2.6	Many of the evaluability challenges in this case are common to all large scale, multi-year programme evaluations. Staff move on, institutional memory is lost, and so on. Part of the reason for focusing more on the recent and current programme is that more ‘live’ lessons are likely to be identified. Lessons from further back in the programme cycle are to some extent documented or reflected in adaptations to the evolving programme, though it may be harder in some cases to answer the ‘why’ question in relation to decisions taken four or five years ago.

4.2.7	The timetable for the evaluation means that the sample of key informants and programme sites to be visited will be fairly small (i.e. highly selective), running the risk that conclusions may be drawn, and generalisations made, that are not valid for the whole programme. To counteract this, we rely on partly on our discussion with the TCO to ensure a reasonably representative sample, and partly on other sources (key informants, documentation, survey results) and feedback on the evaluation report to point out where a conclusion drawn based on limited evidence may not valid across the wider programme. We would seek to review countervailing evidence in such cases before revising a conclusion.

One particularly significant example of this ‘representativeness’ problem concerns interviews with relatively newly-appointed government officials (of whom there are many), who may lack knowledge of the history of UNICEF’s programme and work with government. The evaluation team will be careful not to interpret findings from such interviews in isolation.

Data limitations and sampling issues

4.2.8	Given the limited scope to generate primary data during the evaluation, or to test the validity of existing data, the team will be heavily reliant on UNICEF and its partners’ own reported results for the performance review component of the evaluation. UNICEF’s own RAM system will be a primary source here.

4.2.9	Another challenge is the availability of relevant contextual data. Although this appears a relatively data-rich environment, there are significant gaps as noted above, particularly with regard to the refugee and migrant population: general attitudes and practices, as well as specific topics like GBV and child marriage. This is a reflection in part of the political sensitivity surrounding data collection on refugee issues. Although this situation is perhaps not as acute as noted by the 2015 evaluation of UNICEF’s refugee response in Turkey, it remains a significant constraint.

## 4.3	Evaluation approach

4.3.1	The team’s approach to the evaluation will reflect the dual ambition of the CPE as both an accountability and learning exercise. It is noted that the ToR stress the formative and forward-looking nature of the evaluation, based on a review of learning from the past. The accountability dimension requires that the whole programme and its performance be reviewed, but (as described above) the learning aspect will be based on a more focused consideration of some of the ‘core’ elements of UNICEF’s strategy and programme.  This is a strategic evaluation more than a performance or management one: that, is, our concern is primarily with questions about UNICEF’s proper role in Turkey. So it is not proposed that the evaluation should focus on individual or team responsibilities for delivering on UNICEF’s strategy and programme commitments; although any apparent issues concerning UNICEF’s framework of accountability will be highlighted.

4.3.2	Reflecting the above, the team’s approach to the evaluation will be consultative and participatory, looking to identify lessons and ways forward in collaboration with the staff and partners involved in the programme – while maintaining objectivity, independence of judgment and a willingness to challenge accepted wisdom. It will involve the use of mixed methods, as described below, and will conform to UNEG and UNICEF ethical standards for the conduct of evaluations, as described below.

4.3.3	Given the strategic nature of the evaluation, and the fact that a number of more specific evaluations have been conducted (or are forthcoming) concerning particular elements of the programme, it is not proposed to consult formally with beneficiary groups. Indeed, from an ethical point of view, doing so might raise false expectations concerning the intended purpose of this evaluation. It is, however, anticipated that programme visits will include informal conversations with beneficiaries and community members (Turkish and refugee/migrant) as well as with staff and partners. This is a matter of ongoing consultation with the TCO – see further below under Methodology in Section 6.

4.3.4	The evaluation will be conducted in accordance with the UNEG Ethical Guidelines for Evaluation. We note here in particular the following provisions:

Obligations to participants

19.	Evaluators shall respect people’s right to provide information in confidence and make participants aware of the scope and limits of confidentiality. Evaluators must ensure that sensitive information cannot be traced to its source so that the relevant individuals are protected from reprisals.

Respect for Dignity and Diversity

20.	Evaluators shall:

a.	Respect differences in culture, local customs, religious beliefs and practices, personal interaction, gender roles, disability, age and ethnicity, and be mindful of the potential implications of these differences …

b.	Keep disruption to a minimum while needed information is obtained, providing the maximum notice to individuals or institutions they wish to engage in the evaluation, optimizing demands on their time, and respecting people’s right to privacy.

As a general rule, views expressed by informants to the evaluation will not be attributed to the individuals or organisations concerned, other than to distinguish views expressed by internal (UNICEF) sources from those expressed by external sources.

4.3.5	Although there is likely to be minimal direct involvement of children in the evaluation – given its strategic nature – the evaluation team will be guided by the general principles for ethical research involving children as defined by UNICEF and others. More generally, it will respect the principles for ethical evidence generation (respect, benefit and justice) as set out in UNICEF guidelines:

1. Respect

All evidence generating activities should ensure respect for all persons. Respect demands that individuals be treated as autonomous agents. An autonomous agent is an individual capable of deliberation about personal goals and of acting under the direction of such deliberation. To respect autonomy is to give weight to autonomous persons' values, preferences, and beliefs and to recognise their capability for self-legislation, their ability to make judgments, to state their opinions and to make choices.

In respecting an individual’s autonomy, recognition is required that personal agency may be limited due to age, circumstance or personal capacities. In this context, respect for autonomy requires recognition of capabilities, power differentials and the degree of agency that an individual may have. In the context of children and other vulnerable groups respectful evidence generation needs to be situated in their lived experience with recognizing the reality of unequal relationships of power that frequently exist, creating environments that support these individual’s personal agency and dignity.

2. Beneficence and Non-maleficence

The principle of beneficence refers to the requirement that actions within evidence generating activities promote the well-being of individuals, communities or society as a whole. The principle of beneficence requires the identification of clear benefits likely to arise from evidence and to reconsider proceeding if these cannot be articulated. Beneficence includes the concept of reciprocity, whereby the evidence generated is conveyed back to the participants so that they may triangulate findings, contextualize their participation and potentially gain from the knowledge disseminated.

The principle of non-maleficence, doing no harm, requires avoiding harm or injury to participants, both through acts of commission or omission. While the primary purpose of research, evaluation and data collection and analysis is to generate new evidence, this goal should never take precedence over the rights of individual participants. Non-maleficence requires an examination of the profile, competencies and skills of researchers and enumerators to ensure no harm comes to participants by virtue of inappropriate, unskilled or incompetent researchers or enumerators. It also requires explicit consideration of means to ensure the privacy of participants, their safety and any possible negative impacts arising from participation.

3. Justice

The principle of justice requires that consideration is given to who benefits and who bears the burden of the evidence generation. This requires that due reflection is given to determining the appropriateness of proposed methods of selecting participants. Selection should not result in unjust distributions of the burdens and benefits of evidence generation. Such considerations are required to avoid the injustice that arises from social, racial, sexual, and cultural biases institutionalized in society.

# 5. 	Evaluation framework and basis of analysis

5.1	The analytical framework for the evaluation is based on a set of guiding questions – see Box 2 below. The full framework is set out in the Evaluation Matrix in the Annex to this report, and includes subsidiary questions, indicators and sources of verification. As noted in the previous section, the evaluation is based around three main DAC criteria of relevance, effectiveness and sustainability. The questions are grouped accordingly and are based on a modified and expanded version of the guiding questions set out in the Terms of Reference. These modifications derive largely from the revised focus of the evaluation described in the previous section.

5.2	To help maintain strategic focus, the team will be guided by two overarching strategic questions concerning UNICEF’s role and programme, as follows:

- Has UNICEF found the appropriate role, position and areas of engagement in Turkey over the course of the present country programme (2016 to date)? Overall and by Output area.

- Given the lessons of the past three years and the emerging context, how should UNICEF now position itself through the new CPD? What are the strategic choices facing it?

In both cases, the answers will depend in part on analysis of UNICEF’s added value and comparative advantage in relation to others, as well as the demands of its mandate. The analysis will centre on whether UNICEF occupies a space that reflects (i) areas of priority need for vulnerable children in Turkey, (ii) UNICEF’s own mandate, policy priorities, and added value (in relation to others), (iii) the potential operating space given the political and institutional context, the availability of funds, and other relevant factors.

Box 2: Main guiding questions for the evaluation

A. Programme relevance and appropriateness to context A.1 Child vulnerability profile. What have been the main threats to children's security, well-being and development in Turkey during the period January 2016 to October 2019? A.2 Social, political and economic context What are the main social, political and economic factors bearing on the security, well-being, development of girls and boys in Turkey? How well has UNICEF responded or tried to influence them? A.3 Legal and policy context What are the key legal frameworks and policy commitments of the Turkish state as they relate to the situation of Turkish and refugee children? How has UNICEF engaged with these frameworks and sought to influence them? A.4 UNICEF programme relevance To what extent has UNICEF’s programme addressed the priority needs, vulnerabilities and inequities facing girls and boys in Turkey (including Turkish and refugee / migrant children)? A.5 Evidence-informed programming To what extent has the design and delivery of the CP been informed by evidence on the evolving situation of girls and boys (gendered assessment, surveys, situation monitoring, etc.), programme interventions (monitoring, evaluation, etc.) and analysis of related causal factors? A.6 Target setting and indicators Were targets set proportionate to need, appropriate and realistic, in light of other capacities? Were appropriate indicators set?

B. UNICEF strategy, programme coherence and compliance B.1 Strategic logic and coherence How cogent and coherent has UNICEF’s overall strategy been in Turkey over the evaluation period? B.2 Logic of programme interventions What sectoral strategies exist, how clear are they and how strong is their logic? B.3 Use of change strategies Were the implementation/change strategies utilized appropriate to the evolving context and the intended outputs? B.4 Programme integration and coherence How well integrated have the various programme components been? Has there been synergy between the component parts? B.5 Policy compliance How consistent has the programme design been with UNICEF’s own international policy commitments (including those on gender) and with sectoral guidelines? B.6 Accountability and community engagement How accountable have UNICEF and its partners been to affected populations? What has been extent / quality of community engagement (including children)? B.7 Role and position of UNICEF Overall, has the role played and position adopted by UNICEF in Turkey been appropriate over the evaluation period, given the evolving context and role of government and other actors?

C: Programme performance: results, effectiveness, quality C.1 Target achievement To what extent has UNICEF been able to achieve its targets in each of the sectors in which it has intervened? C.2 Effectiveness How effective have UNICEF's interventions been, in terms of delivering against stated Outputs and objectives? C.3 Monitoring, quality and results management How effectively has UNICEF been able to gauge the results and quality of its interventions? On gendered impact and results? C.4 Contribution to outcomes To what extent can contribution to outcomes (direct or indirect) be attributed to UNICEF and its partners’ interventions? Has implementation of the CP led to unintended results? C.5 Advocacy and communications How effectively has UNICEF used advocacy and communications in its programme? C.6 Programme lessons learned What lessons has UNICEF learned from the experience of implementing the CPD 2016-20? How well has it responded to those lessons? How should they inform the next CPD?

D. Sustainability, resourcing and partnerships D.1 Humanitarian – Development Nexus How well has UNICEF managed the links between these two aspects of its programme? D.2 Resilience building How appropriate and effective has UNICEF’s work on resilience been? D.3 System strengthening Has the system strengthening approach of the CP been appropriate, effective and sustainable given: (i) the existing and projected future capacity and priorities of the Government at national, provincial and municipal levels, and (ii) the capacity and role of relevant partners? D.4 Partnerships and capacity development Has UNICEF had the right partnerships to deliver on its programme objectives? Has it helped develop the capacity of partners in appropriate and effective ways? Including gender capacity. D.5 Collaboration and coordination How well has UNICEF collaborated with other actors and coordinated / harmonized its interventions with theirs? D.6 Mixed modalities To what extent have implementation strategies adopted by UNICEF been effectively combined to support achievement of sustainable results? D.7 Sustainability and resourcing Has the scale-up of human and financial resources been sufficient to meet the evolving needs of the programme over the CPD period? Are future prospects for funding consistent with UNICEF’s ambition in Turkey? D.8 Results-based management How well has the system of results-based management (including the use of RAM monitoring frameworks) been implemented in practice? D.9 Programme transition Does UNICEF have clear exit or transition strategies for its various programme components?

Basis of analysis

5.3	As reflected in the framework above, the evaluation team proposes to evaluate both the theoretical dimensions and the real-world effects of UNICEF’s programme. To do so, it will use the framework above as an organising structure for the analysis. Data will be coded and collated according to a simple system, using the numbering system in the framework (B1, D.6 etc.), in order to bring together data from multiple sources on related questions. The analytical framework will be applied both at the programme component level (e.g. child protection) and to the programme as a whole, based on a synthesis of results across the various programme components as well as more generic data from key informants, surveys, document analysis, etc. Data will thus be triangulated and tested across multiple sources to the extent possible within the limits of the evaluation process, bearing in mind the potential dangers of generalising from limited results (see s.4.2.7 above). Findings and conclusions will be qualified as appropriate, depending on the depth and credibility of the information on which they are based.

5.4	One major analytical issue in a programme of this kind is attribution of effect. The relative shift in implementation modalities away from service delivery partnerships and towards system-strengthening, policy engagement and advocacy raises some important evaluability challenges. In particular, it raises questions about how policy and system changes are to be identified, and whether (and how) such changes may be attributed at least in part to the intervention of UNICEF. The logic of the related theories of change will be tested in the evaluation, rather than assumed to hold true; and claims made about causal effects will be tested in part through triangulation of qualitative perspectives (through KIIs) as well as relevant quantitative sources. So for example, the evaluation team may ask respondents ‘Is it reasonable for UNICEF to claim in their reporting that their interventions had this effect?’

5.5	The language of the logic models at the Output level is based largely on the concepts of ‘removing bottlenecks/barriers’, particularly through achieving increased capacity in systems and institutions – raising the specific question of what constitutes significantly ‘increased capacity’, how this is measured, and whether ‘increasing capacities’ does in fact enable the greater fulfilment of child rights. The starting point of the evaluation will be to consider how UNICEF itself gauges its effectiveness in this regard, and whether the related indicators are adequate and appropriate.

# 6.	Methodology

6.1	Following the approach outlined above in section 4.3, the primary methods used in the evaluation will be documentary review, using mainly UNICEF materials; and key informant interviews (KIIs), both with UNICEF staff and those from other organisations. Specifically, the evaluation will begin with a review of secondary data and evidence from documentary sources and will use key informant interviews to test questions and observations arising from that review. Document review and key informant interview will be supplemented by site visits, field observations and online surveys (with staff and partners). It is not proposed to hold focus group discussions, either with communities or partners (see below for rationale).

The inception phase of the evaluation has allowed an initial documentary review to take place, and the enquiry has been shaped by that review, including the evaluation framework (guiding questions and evaluation matrix) and the proposed sample of key informants and site visits set out below.

Document review

6.2	Analysis of key documents and the data they contain will form a core part of the evaluation. They will be used both as information sources in their own right and as a basis for triangulating information gained through key informant interviews. A reference library of documents has been compiled during the inception phase of the evaluation, see Document List in Annex F.

Key informant interviews

6.3	These will be conducted with those individuals within and outside UNICEF judged to be best placed to help answer the top-line questions in the table in section 5 above, together with the subsidiary questions set out in the evaluation matrix. The guiding questions provide a framework within which questions can be asked, rather than a questionnaire to be followed for all interviewees. A semi-structured approach will be adopted, using selected questions from the list above to elicit broad responses, as well as issue-specific lines of enquiry (see interview protocol & template below). It is anticipated that new issues (additional to those already identified) will arise from these conversations. To date, around twenty interviews and meetings have been conducted during the inception phase of the evaluation. Subsequent interviews – some of them follow-up interviews with individuals already consulted – will be used to try to elicit answers to the more specific questions set out in the evaluation matrix.

6.4	Key informants from within UNICEF will be those staff involved (directly or indirectly) in the UNICEF programme, from the Country Office and field office; the Regional Office for Europe and Central Asia (ECARO) in Geneva; the Middle East and North Africa Office (MENARO) in Amman; and (as appropriate) from UNICEF Headquarters in New York. Implementing partner organisations, both national and international (i.e. those with which UNICEF has concluded PCAs) will be interviewed, together with staff from other UN bodies, including the Resident Coordinator’s office. Key UNICEF counterparts in the relevant Ministries and government departments will be consulted in Ankara and at provincial level, as will government staff in the municipality visited. The team will also meet in Ankara with major donors to UNICEF’s programme.

6.5	A general protocol and guidelines for the conduct of interviews and meetings is set out in Box 3 below, while the interview template is shown in Box 4. For reasons set out below (s.6.6), it is not proposed to hold meetings with children during the course of the evaluation, either individually or in groups. Key information from interviews will be compiled in a spreadsheet that allows data to be sorted according to topic, interview type, relevance to UNICEF Outputs and other criteria.

Box 3	Interview protocol and meeting guidelines

Protocol

- Agree the length of the interview or meeting (typically 45-60 minutes)

- Introduce the team members, explain the nature and purpose of the CPE (below), and why we wanted this interview/meeting

- Go through the following informed consent protocol: explain that we need to follow a certain protocol around informed consent and have some (brief) related questions.

1. Explain why we wanted to interview the person(s) in question, and what the interview process entails.

2. Explain that participation is voluntary, and informant(s) may choose not to respond to any or all questions or may withdraw at any time without consequences. Explain the process of note taking and information use:

- We will take written notes (no audio recording) of the interview, solely for our own reference in compiling our report

- In writing our evaluation report, we will not attribute views to individuals or specific organisations.

- We intend to list individuals and organisations as informants in an Annex to the evaluation report. Do you consent to this? Note consent or dissent.

Verbally confirm and note consent of subject(s) to be interviewed on the above basis.

2(a) (For KIIs with government officials) Are you content for us to refer to the Ministry/Municipality in connection with this interview? NB we will not name individuals or specific departments. Note consent or dissent.

3. Ask whether above is clear and also: Have you any questions for us about the process before we proceed? Advise that if they have any questions after this meeting, we can be contacted via the UNICEF Turkey Country Office.

- Record the names and positions of those you are interviewing or meeting with

- Set the agenda for the meeting and the issues you would like to cover – see notes below

- Be aware in advance of potential sensitivities by consulting UNICEF staff

- Be courteous – and in particular respect the primary role and responsibility of government officials. Thank people for their time.

Explaining the nature and purpose of the CPE

We are conducting an independent review of UNICEF’s country programme from 2016 to date, on behalf of the UNICEF regional office (explain this is standard practice). We are looking at how UNICEF has performed (accountability) – and most importantly, aiming to identify lessons to help inform adaptations to the programme and the design of the next country programme.

Stress in particular the strategic nature of the evaluation. This is not a technical evaluation, looking at the detail of programmes and their implementation. Rather our main concern is with questions about UNICEF’s role and position in Turkey (e.g. Has UNICEF found the appropriate role and position for itself in Turkey? Overall and on specific agendas. What should its future role be? What is UNICEF’s added value?). As a means to answering those questions, we are interested to know what the main issues/challenges in the external environment are on a given topic (e.g. preventing child labour) and what advice people may have concerning UNICEF’s role, performance and added value.

Box 3 cont’d

Setting the agenda and framing questions

Our approach to interviews and meetings is a semi-structured one. Decide before the meeting the topics, guiding questions and specific issues from the Evaluation Matrix that you wish to pursue in the meeting – but also allow participants to raise new issues. Do not try to cover too much ground (suggest focusing on 4-5 questions/issues).

Use open questions. Start with a broad/descriptive question to open the conversation, e.g. ‘can you explain to us how you/your organisation are involved in this agenda’ (e.g. GBVIE). But do not allow the meeting to become simply a descriptive briefing. This is an evaluative process, and we are trying to elicit evaluative judgements that can help UNICEF think e.g. about alternative approaches that might work better than those currently adopted. These should be backed up with evidence/examples, and we may need to prompt those involved to illustrate their judgements (‘can you give me an example of that?’).

END

Specific questions by key informant type

6.6	The interview template shown in Box 4 below is a generic one. While the same generic questions will be asked of all interviewees (modified as appropriate), more specific questions asked will depend in part on the category of interviewee. We distinguish in particular the following categories:

UN partners: will be asked about UNICEF as a strategic partner / collaborator. They will also be asked about UNICEF’s specific role within the wider UN family in Turkey, whether they believe has played the right role, and how that role might need to adapt to the evolving landscape.

Government partners: will be asked about their collaboration with UNICEF, strengths/weaknesses and suggestions for change; their priority agendas for children and scope for future collaboration with UNICEF on these.

Donors: will be asked for feedback on UNICEF as a partner, strengths/weaknesses and suggestions for change; their priorities with regard to children in Turkey and related potential areas of collaboration with UNICEF; and more generally about future funding prospects in Turkey.

NGOs: will be asked about UNICEF as a partner, and capacity development in particular; whether they think UNICEF has played the right role, and how this might need to change; about future priorities for children; and about the space for civil society organisations to operate.

Box 4	Interview template

1. Introductions

(i) Thank you for meeting with us. [Introduce team members]

(ii) Please could you introduce yourselves, including your post / role in the organisation? Length of time in post?

(iii) The meeting should take… (usually 45-60 minutes – agree a length with KIs)

2. Preamble

We are (part of) an independent evaluation team looking at UNICEF’s country programme in Turkey over the past 3 years. UNICEF is looking to learn lessons from its programming to date in order to inform its current and future programme. Our overall interest is a strategic one: is UNICEF playing the role that it should in Turkey? We are particularly interested to discuss with you [X, Y programme areas – e.g. Child Protection, and particularly child marriage], to get your perspective on this agenda and to help us reflect on UNICEF’s role.

Go through informed consent protocol at this point (see above)

Explain that we will be writing up a report towards the end of the year which will be published by UNICEF.

3. We understand that you are engaged with [X area of concern, Turkish/refugee children].

(i) Could you briefly describe how your organisation is engaged with this agenda [e.g. scope, nature, location of programme. Service delivery, system strengthening, policy making, other?]

(ii) Could you describe the nature of your collaboration with UNICEF?

4. Core questions

We are interested in getting your feedback on:

(i) Priority issues in this area of work and the main challenges to addressing them?

(ii) Whether UNICEF has played / is playing the right role on this agenda. What is its comparative advantage in relation to others? [Should it continue, or play a different role?]

(iii) How effective UNICEF has been on this agenda [e.g. contributions to change – examples?]

(iv) Have you any suggestions for what UNICEF might do differently/ better in future on this agenda?

For implementing partners: How well has the partnership worked? Any suggestions for the future?

5. Specific questions, drawn from the Evaluation Matrix and lines of enquiry, or arising from the above conversation. These may be interwoven with the core questions above.

6. Final comments / suggestions

Overall, have you any other comments or suggestions on the role that UNICEF is playing in this area – or the role it might play in the future?

7. Wrap-up

Thank you very much for your time.

[Agree any follow-up actions]

Focus Group Discussions

6.7	 Given the strategic nature of the evaluation, it is not proposed to conduct focus group discussions or other structured consultations with community groups or children’s groups. Other sector-specific evaluations have included such consultations, but following discussion with the TCO, it was agreed that the strategic nature of the present evaluation combined with the difficulties of attempting such consultations across the whole programme (as opposed to arbitrarily selected elements) meant that the use of group consultations of this kind was not warranted in the case of the present evaluation. Nor is it proposed to hold group discussions with partner organisations, since it is believed that more informative responses may be obtained in one-to-one interviews and through the use of an online survey.

Staff and partner surveys

6.8	The evaluation team proposes to use survey techniques to allow consultation with a wider group of stakeholders than will be possible through informant interviews alone. Specifically, it is proposed to use online survey techniques to gather qualitative information, for two main purposes. One is to consult UNICEF staff themselves on key lessons from the country programme and possible future directions for UNICEF in Turkey. This will include all current staff who have had direct or indirect involvement with the programme at some stage over the past three years. The second is to gather opinions from organisations with which UNICEF collaborates, including members of networks of which UNICEF is part, such as the networks for Prevention of Violence Against Children (VAC) and Children with Disabilities (CwD). The related process and precise details of sampling are subject to further discussion with the TCO and with the chairs of the relevant networks. In both cases, a short online survey process will be used. It is proposed to conduct these surveys following the field visit in October 2019. Surveys will be conducted in English, Turkish and (if necessary) Arabic.

A proposed format for each type of survey is included in Boxes 5 and 6 below.

Data collection: sampling proposal and rationale

6.9	In order to benefit from a wide range of perspectives in gathering qualitative data on UNICEF’s programme, the evaluation team will consult a range of informants selected from the primary stakeholder categories outlined in section 4.1.2 above. The more specific list organisations and government departments to be consulted is contained in the Annex, based on the list attached to the ToR. The actual sample size will be determined in part by the limitations of time and the availability of informants, but our intention is to cover a cross-section of organisation types (government and other) working on the relevant agendas as described in section 2. The sampling method will be purposive and will be informed by discussion with the relevant sections in the TCO. The team is likely to split in order to cover as much ground as possible.

6.10	The main criterion for selection of organisations to consult is UNICEF’s involvement with the organisation in question in the design or implementation of the country programme and its component parts; or else their shared interest and involvement in the areas of concern covered by the UNICEF country programme.

The main criteria for choosing locations in Turkey to visit during the fact-finding mission are (i) areas with highest concentration of child vulnerability issues, and (ii) locations that may best demonstrate the components of UNICEF’s programme that are the focus of this evaluation. As noted in section 3 above, this will require site visits in the southeast of the country, as well as meetings in Ankara and Istanbul.

6.11	In Annex F, we break down the organisations/ proposed locations to be visited by programme elements: Child Protection, Education, Social Protection/Cohesion and Social Policy. From this it appears that team members will need to visit Ankara, Gaziantep, Kilis, Adana, Izmir and Istanbul (although the team will split up in order to cover the necessary ground). The details and logistics of such visits are subject to further discussion with the TCO.

6.12	Annex F contains the list of informants who would ideally be consulted. As far as possible, we will aim to meet those in the relevant organisations who have had the most direct dealings with UNICEF. Practical considerations – and in particular limits of time and people’s availability – may mean that not all of those listed can be consulted. The evaluation team will discuss how to schedule and prioritise these meetings. Central government meetings in particular are likely to require scheduling well in advance of the September / October fact-finding mission.

# Box 5: UNICEF Turkey Country Programme Evaluation - Staff Survey

# Thank you for agreeing to take part in this evaluation of UNICEF’s country programme in Turkey from 2016 to date. The evaluation team has not been able to consult directly with all of the relevant staff, but we are keen to get your input to the evaluation. This survey should not take more than about 15 minutes to complete. Even if you do not feel able to answer all of the following questions, we would welcome a few sentences of feedback in the final text box.

Participation in this survey is entirely voluntary, and no consequences will follow from not doing so. Participants may withdraw at any time or answer only some of the questions. The results of the survey will be compiled and communicated in such a way that no comments can be attributed to specific individuals. All information provided will be held securely and kept confidential, so please feel free to express your views. If you have any questions, please contact UNICEF at ankara@unicef.org

This is a strategic evaluation, rather than a technical or operational one. Our overall question is: what role should UNICEF be playing in Turkey, on specific agendas and overall? Although we are looking at the programme from 2016, our particular focus is on the recent/current programme and future prospects.

- What is your role / area of responsibility in UNICEF?

- How long have you been in post?

- Are you based in the Ankara office, Gaziantep office or elsewhere?

- In your area of responsibility, how would describe (i) the main strengths of UNICEF's programme (ii) the main weaknesses? (iii) the main barriers to success (external or internal)?

- In your area of responsibility, what would you say have been the main lessons learned by UNICEF over the past two years or more recently?

- Given the evolving context, what changes in the way UNICEF works in Turkey could you suggest to better enable UNICEF to help meet the priority needs of children in future?

- Please write here any other points you would like the evaluators to consider.

Many thanks for completing this survey: your input is much appreciated.

The Evaluation Team

Box 6: UNICEF Turkey Country Programme Evaluation - Partner Survey

# Note: we use partner here in the broad sense of organizations with which UNICEF collaborates in some way on agendas concerning the development & security of children living in Turkey

# Thank you for agreeing to take part in this evaluation of UNICEF’s country programme in Turkey from 2016 to date. The evaluation team has not been able to consult directly with all of the organizations with which UNICEF collaborates, but we are keen to get your input to the evaluation. This survey should not take more than about 15 minutes to complete. Even if you do not feel able to answer all of the following questions, we would welcome a few sentences of feedback in the final text box.

Participation in this survey is entirely voluntary, and no consequences will follow from not doing so. Participants may withdraw at any time or answer only some of the questions. The results of the survey will be compiled and communicated in such a way that no comments can be attributed to specific individuals or organisations. All information provided will be kept confidential, so please feel free to express your views. If you have any questions, please contact UNICEF at ankara@unicef.org

This is a strategic evaluation, rather than a technical or operational one. Our overall question is: what role should UNICEF be playing in Turkey, on specific agendas and overall? Although we are looking at the programme from 2016, our particular focus is on the recent/current programme and future prospects.

- How would you describe your organization type? (E.g. government, national NGO, UN)

- What are your main areas/sectors of collaboration with UNICEF? (Please make more than one choice if necessary)

- In your main area(s) of partnership or collaboration with UNICEF, how would you rate UNICEF’s overall performance? (Quant 1-5)

- If you have a partnership agreement or shared workplan with UNICEF, how would you describe (i) the main strengths of the partnership, (ii) the main weaknesses?

- (Where relevant) How would you rate the quality of support and engagement you received from UNICEF over the partnership period?

- What could UNICEF be doing better/differently to be more effective or relevant in its work?

- Do you have any other comments or suggestions for the evaluation?

Many thanks for completing this survey: your input is much appreciated.

The Evaluation Team

6.12	The table below shows a summary of proposed site visit locations against programme components:

| Programme Component | To visit | Locations | Team members |
| --- | --- | --- | --- |
| CP Component 1: Strengthening Turkey’s child protection system | Ministry of Family, Labor and Social Services - Directorate General of Child Services UNICEF - Child Protection Team - Adolescent Development Team - Gender advisor - Chief of Field Office (Yannick Brand) – Gaziantep - CP evaluation team | - Ankara (Ministry of Family, Labor and Social Services), UNICEF, UNHCR - Provinces Support to Life centres GAP centres Turkish Red Crescent – Outreach teams; Mobile Units; Child Friendly Spaces RET – Girls Safe Spaces and Adolescent Centres Municipality Centres Youth centres | Ms. Francesca Ballarin |
| CP Component 2: Child care and social welfare | Ministry of Family, Labor and Social Services - Directorate General of Child Services Tohum Autism Foundation – Secretariat of the NGO Network for Children with Disabilities | - Ankara (Ministry of Family, Labor and Social Services), UNICEF Provinces | Ms. Francesca Ballarin |
| CP Component 3: Child Protection System and Services | Ministry of Family, Labor and Social Services - Directorate General of Child Services UNICEF - Child Protection Team - Adolescent Development Team - Gender advisor - Chief of Field Office (Yannick Brand) – Gaziantep - CP evaluation team Save the Children Child Protection Centers Support Society (COKMED) | - Ankara (Ministry of Family, Labor and Social Services), COKMED, UNICEF, Save The Children - Provinces Support to Life centres GAP centres Turkish Red Crescent – Outreach teams; Mobile Units; Child Friendly Spaces RET – Girls Safe Spaces and Adolescent Centres Municipality Centres Youth centres | Ms. Francesca Ballarin |
| CP component 4: Justice for Children and Child Rights Monitoring | Ministry of Justice |  | Mr. Zarko Sunderic |
| CP Component 5: GBVIE and ending child marriage |  |  | Ms. Francesca Ballarin |
| Education component 1: Access to formal education for refugee children 3- 17 | Ministry of National Education - Directorate General of Lifelong Learning UNICEF - Education section - Early childhood development specialists (pre-school education) - Adolescent Development team - Gender advisor - Chief of Field Office - Evaluation team (‘Evaluation of Support to Education Personnel’) | - Ankara (Ministry of National Education, UNICEF, UNHCR - Provinces (UNICEF Field Ofiice), Municipalities, Temporary Education Centres, Schools | Ms. Francesca Ballarin |
| Education component 2: Access to quality and inclusive education for vulnerable children 3 to 17 | Ministry of National Education | Ankara (Ministry of National Education, UNICEF | Ms. Francesca Ballarin |
| Education component 3: Education Opportunities for Adolescent Girls and Boys | Ministry of National Education - Vocational Qualifications Institution Ministry of Youth and Sports - Youth Centers for Refugees - Child and Youth Centers for Refugees | Ankara (Ministry of National Education, UNICEF | Ms. Francesca Ballarin |
| Education component 4: Early Childhood Development | Ministry of National Education - Directorate General of Basic Education - MoNE Provincial Directorates - Directorate General of Early Childhood Education | Ankara (Ministry of National Education, UNICEF Istanbul (ACEV) | Ms. Francesca Ballarin |
| SP/SC Component 1: Conditional cash transfers for education + child protection | Ministry of Family, Labor and Social Services - Directorate General of Social Assistance - FRIT Coordination Unit Ministry of National Education UNICEF - Social Policy Team - Adolescent Development Team - CCTE Evaluation Team - Chief of Field Office/Gaziantep World Food Programme - Head of Partnerships and Information Management Unit - Vulnerability Analysis & Mapping (VAM) Officer European Union - Directorate-General for European Civil Protection and Humanitarian Aid Operations (DG ECHO) Turkish Red Crescent - CCTE Cash team - CCTE Child Protection team Development Workshop Cooperative (Child Labor) | - Ankara (Ministry of Family, Labor and Social Services), UNICEF TCO, ASAM, WFP, TRC, DG-ECHO - Istanbul - Provinces (Local Social Solidarity and Assistance Foundations), Family, Labour and Social Services Provincial Directorate, Turkish Red Crescent (TRC) Service Centers, UNICEF Field Office (Antep), | Ms. Gokce Baykal |
| SP/SC Component 2: Social cohesion interventions | Ministry of Family, Labor and Social Services - Social Inclusion Department GAP Regional Development Association GAP CATOM Multipurpose Community Centres | - Ankara (Ministry of Family, Labor and Social Services), UNICEF - Istanbul - Provinces (GAP) CATOM, | Ms. Gokce Baykal |
| SPM&D Component 1: Strengthening the evidence base on child rights | - Monitoring and Assessment Board for the Rights of the Child - Strategy and Budget Office of the Presidency |  | Mr. Zarko Sunderic |
| SPM&D Component 2: Strengthening child rights monitoring | - Ministry of Justice - UNICEF - Ombudsperson’s Institution - National Human Rights Institution (NHRI) - Monitoring and Assessment Board for the Rights of the Child | Ankara (Ministry of Justice), Istanbul Izmir Adana - Provinces | Mr. Zarko Sunderic |

# 7.	Team roles and workplan

## 7.1	Team roles

In general terms, team roles for the evaluation team will be as specified in the terms of reference. More specifically, given the proposed areas of focus of the evaluation described above, lead responsibilities within the team will be allocated as follows:

Francesca Ballarin

Education

- Refugee children’s education, both in TECs and Turkish public schools (1A)

- Strengthening national education system (1B)

- Adolescent education, with gender perspective (3A)

- Early Childhood Development (pre-school education component) (1G)

Child protection (with Gurcharan Virdee)

- Community-based child protection, refugee and other (1C)

- GBV and child marriage (3B)

- CCTE child protection component (1J)

- Child protection system (1C)

Gokce Baykal

Social protection and social inclusion

- CCTE cash transfers for refugee families (1D)

- Child labour (1D) – including seasonal agricultural work

- Multi-sector assistance to refugees (strengthening local authorities’ capacity) (1H)

- Adolescent Development and Participation (ADAP) (1F)

Zarko Sunderic

Social policy, monitoring and data (ZS)

- Generation and use of quality disaggregated data on children (2A)

- Independent Child Rights Monitoring (2B)

- UNICEF policy engagement and advocacy on social policy (multiple)

- Public financing for children (multiple)

Gurcharan Virdee

Advice on gender-specific issues (including child marriage) and gender analysis overall.

(Note: each team member will have responsibility for reviewing gender mainstreaming in their respective areas).

James Darcy

Responsible as team leader for the overall design and conduct of the evaluation, within the framework set out in the ToR and this inception report. He will review the whole programme, write the context analysis (external and internal), edit and revise submitted material, and be responsible for writing the inception report and main evaluation report. In discussion with the team, he will define team member responsibilities, manage and support individual team members in completing their tasks, and be responsible for liaising with UNICEF TCO and ECARO, as well as other tasks specified in the ToR.

## 7.2	Evaluation schedule

7.2.1	The overall schedule for the evaluation set out in the ToR (reproduced here) remains valid. Delays in recruitment of the team meant that the time for documentary review in advance of the inception mission was limited, and this component (and the inception report writing) has continued into August. The schedule of activities otherwise remains the same at this stage.

| Activity | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inception and Desk review | x | x |  |  |  |  |  |  |
| Inception mission | X | X |  |  |  |  |  |  |
| Inception report |  | X |  |  |  |  |  |  |
| Report reviewed by evaluation stakeholders, ethical review and quality assurance conducted. |  |  | X |  |  |  |  |  |
| Finalization and approval of Inception Report |  |  | X |  |  |  |  |  |
| Field Mission |  |  |  | X |  |  |  |  |
| Field mission and presentation of preliminary observations and findings |  |  |  |  | X |  |  |  |
| First draft report |  |  |  |  |  | X |  |  |
| Report reviewed by evaluation stakeholders, ethical review and quality assurance conducted |  |  |  |  |  | X |  |  |
| Final Report |  |  |  |  |  |  | X |  |
| Final presentations |  |  |  |  |  |  |  | X |

7.2.2	The related timetable for deliverables and related days allocation for team members is set out in the ToR and reproduced below. This is subject to some further modification based on discussion between team members and UNICEF ECARO.

| Evaluation Deliverables | Completion Dates | # of days Team Leader | # of days team member | # of days gender expert |
| --- | --- | --- | --- | --- |
| Inception Mission with presentation | 2 weeks before submission of the IR | 5 | 3 |  |
| Inception Report (20 pages excluding annexes towards which team members will contribute with, at least, 5 pages) | 2 weeks after the inception mission | 16 | 9 | 6 |
| Field Mission and presentation to CO staff, the ERG and other stakeholders as requested (16 working days plus travel) | 2-4 weeks after the beginning of the Inception Phase. | 16 | 16 |  |
| Draft Report towards which each team member will contribute with, at least, 10 pages | 5 weeks after completion of the main mission. | 17 | 12 | 3 |
| Final Draft Report (40-60 pages excluding executive summary and annexes) | 3 weeks after internal review and external quality assurance on draft report have been completed. | 5 | 3 | 2 |
| A visit to present the evaluation to CO staff, the ERG and other stakeholders A PowerPoint presentation of the evaluation, its main findings, recommendations and conclusions. A skype presentation to RO staff | 1-2 week after approval of final report. | 2 |  |  |
| Management response and wider distribution | 1-5 weeks after the approval of the final report. |  |  |  |
| Total |  | 61 | 43 | 11 |

7.2.3	The agenda and schedule for the September-October fact finding mission is subject to further discussion with the TCO. Preliminary discussions suggest the following overall schedule:

Week 1	(23 - 27 September) - Meetings in Ankara

- UNICEF staff (as key informants)

- Government Ministries

- National NGOs

Weekend of 28/29 – team splits and travels to Gaziantep / Kilis, Adana and Izmir

Week 2 (30 Sept - 04 October) – Meetings and programme visits in Gaziantep/Kilis, Adana, Izmir

- UNICEF field office staff

- Government Ministries – Provincial offices

- Municipal authorities

- Site visits with local partners (TRC etc.)

Weekend of 05/06 – team returns from Gaziantep to Ankara

Week 3 (7 - 11 October) – Meetings in Ankara

- UNICEF staff (KIIs and feedback)

- Government Ministries

- Academic institutions

- Donors

This schedule is provisionally elaborated in the following table, subject to clarification and revision.

Turkey CPE Schedule – Week 1: Ankara

| Team member / Location | Monday KIIs with UNICEF staff | Tuesday KIIs with UNICEF staff + External | Wednesday Team meeting + external | Thursday External meetings | Friday External meetings | Saturday/Sunday |
| --- | --- | --- | --- | --- | --- | --- |
| James Darcy Ankara | - PM&E (Silvia/Farhod) - Deputy Rep KII - Head of resource mobilisation/funding | - Chief of Operations - Chief of Communications - Other TBC | AM: external meetings | - MoFLSS - Directorate General of Child Services (with FB) - DGMM - Turkish Red Crescent (with GB) | - UN Resident Representative - UNHCR (Rep) - WFP (with GB) - ILO (with GB) | Saturday: team planning |
|  |  |  | 3 PM: Evaluation team meeting |  |  | Sunday PM: Fly to Gaziantep |
| Francesca Ballarin Ankara | - PM&E - CP Section staff - Gender advisors | - Education Section - Adolescent Team (with GB) | AM: external meetings | MoFLSS - Directorate General of Child Services (relevant sections & individuals TBC) | MoNE - Directorate General of Lifelong Learning (relevant sections & individuals TBC) | Saturday: team planning |
|  |  |  | 3 PM: Evaluation team meeting |  |  | Sunday PM: Fly to Gaziantep |
| Gokce Baykal Ankara | - PM&E - Social policy team - CCTE Evaluation Team | - MoFLSS - Directorate General of Social Assistance - Adolescent Team (with FB) | AM: external meetings | - Ministry of Youth and Sports-- Directorate General of Youth Services/ - Turkish Red Crescent (with JD) | - ASAM (NGO) - Development Workshop - WFP (with JD) - ILO (with JD) - UNDP | Saturday: team planning |
|  |  |  | 3 PM: Evaluation team meeting |  |  | Sunday PM: Fly to Istanbul |
| Zarko Sunderic Ankara | - PM&E - Social policy team - Child rights team | - MoFLSS - (with GB) - Ombudsperson’s Institution - Grand National Assembly (??) | AM: external meetings | - Ministry of Justice - Ministry of Interior - National Human Rights Institution (NHRI) - SBO of the Presidency | - DGMM - Ministry of National Education (YOBIS department) - Turkstat (TUIK) | Saturday: team planning |
|  |  |  | 3 PM: Evaluation team meeting |  |  | Sunday PM: Fly to Istanbul |

Turkey CPE Schedule – Week 2: South-East Turkey + Ankara/Istanbul/Gaziantep/Kilis/Adana/ Izmir

| Team member / Location | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday/Sunday |
| --- | --- | --- | --- | --- | --- | --- |
| James Darcy Gaziantep | KIIs with UNICEF staff (Antep FO) | Gaziantep KIIs: - Municipality - Partner agencies Site visits | Killis KIIs: - Municipality - Partner agencies Site visits | Hatay KIIs: - Municipality - Partner agencies Site visits | Gaziantep meetings TBC | Saturday: Return to Ankara |
|  |  |  |  |  |  | Sunday AM: Team meeting |
| Francesca Ballarin Gaziantep | KIIs with UNICEF staff (Antep FO) | Gaziantep KIIs: - Municipality - Partner agencies Site visits | Killis KIIs: - Municipality - Partner agencies Site visits | Hatay KIIs: - Municipality - Partner agencies Site visits | Gaziantep meetings TBC | Saturday: Return to Ankara |
|  |  |  |  |  |  | Sunday AM: Team meeting |
| Gocke Baykal* Ankara & Istanbul * These meetings to be conducted one week in advance of main mission | Children - Mother and Child Education Foundation (ECD NGO) - UN Women (child early and forced marriages) | Refugees - Support to Life (NGO) - SGDD-ASAM (NGO) - Sultanbeyli Community Center (AND a School Visit?) | Academics - Bilgi University Cocuk Calismalari Birimi (Child Studies) - Dr. Pinar Uyan Semerci | Academics - Koc University Migration Studies Dr. Ahmet Icduygu - Migration Studies Association - Dr. Deniz Senol Sert | Istanbul or Ankara meetings TBC | Saturday: Return to Ankara |
|  |  |  |  |  |  | Sunday AM: Team meeting |
| Zarko Sunderic Gaziantep & Istanbul | Gaziantep: KIIs with UNICEF staff (Antep FO) Gaziantep KIIs: - Municipality - Partner agencies | Adana – meetings TBC Site visits | Izmir – meetings TBC Site visits | Istanbul: - Example of Child-specific detention centre in Istanbul - Example of Judicial Interview Rooms for Children (JIRC) in Istanbul | City of Istanbul representatives NGOs on CRM and Justice for Children in Istanbul UNICEF, UNDP offices | Saturday: Return to Ankara |
|  |  |  |  |  |  | Sunday AM: Team meeting |

Turkey CPE Schedule – Week 3: Ankara and Istanbul

|  | Monday External meetings | Tuesday External meetings | Wednesday KIIs with UNICEF staff | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| James Darcy Ankara | - Key donors for CP & Education (with FB) - KII with Country Representative | Other key UNICEF donors | - Debrief with PM&E | AM: Team meeting | AM: Team meeting |
|  |  |  |  | PM: Debrief with TCO | PM: Team fly home |
| Francesca Ballarin Ankara | Key donors for CP & Education (with JD) | Key UN counterparts and NGOs on CP/Education | Debrief with PM&E | AM: Team meeting | AM: Team meeting |
|  |  |  |  | PM: Debrief with TCO | PM: Team fly home |
| Gokce Baykal Ankara / Istanbul | Key donors for CCTE, such as DG-ECHO FRIT Unit | NGOs on Social Policy, Children CCTE Evaluation Team | Debrief with PM&E | AM: Team meeting | AM: Team meeting |
|  |  |  |  | PM: Debrief with TCO | PM: Team fly home |
| Zarko Sunderic Istanbul | Key donors for CRM and Justice for children, including EC Monitoring and Assessment Board for the Rights of the Child | NGOs on CRM and Justice for Children | Debrief with PM&E | AM: Team meeting | AM: Team meeting |
|  |  |  |  | PM: Debrief with TCO | PM: Team fly home |

# Annexes

## A. Terms of Reference

## B. Evaluation Matrix

## C. CPD Theory of Change

## D. People met during inception mission

## E. List of primary stakeholders

## F. List of proposed key informant interviews

## G. Document list

| Evaluation Matrix |  |  |  |
| --- | --- | --- | --- |
| A. Programme relevance and appropriateness to context | Sub questions | Indicators/means of analysis | Sources of verification |
| A.1 Child vulnerability profile. What have been the main threats to children's security, well-being and development in Turkey during the period January 2016 to October 2019? | A.1.1 What are the differential threats to girls and boys? How does this picture break down by time, location and demographic group (e.g. including refugee and Turkish, urban and rural populations; ethnicity; special needs)? A1.2 What inequities does this reveal overall and in the main UNICEF issues of concern (particularly education, child protection and social inclusion)? How is child vulnerability now evolving? A1.3 What are the gender dimensions of this and how explicitly are these articulated? | Disaggregated baseline data from CPD and other sources, and evolution over time. Particular focus on: - Access to education (primary, lower and upper secondary) – girls/boys, Turkish/refugee - Child Protection concerns and Gender Based Violence profile - Vulnerable groups analysis, including CWD and ethnic minorities | - GoT data (including DHS) - Turkstat data & analysis - UNICEF and partner surveys - Academic literature - Other background/ secondary sources KIIs with UNICEF staff and partners, including local and national government officials KIIs with selected non-UNICEF partners |
| A.2 Social, political and economic context What are the main social, political and economic factors bearing on the security, well-being, development of girls and boys in Turkey? How well has UNICEF responded or tried to influence them? | A.2.1 What are the prevalent social norms and attitudes for Turkish and refugees -including attitudes to gender and ethnicity? How have these evolved over time? A.2.2 How has household economic status and opportunity evolved over time, including access to employment and reasonable working conditions? A.2.3 How have macro-economic factors and limits of fiscal space evolved over time? A.2.4 How has the political context and the integration of refugees (Syrian, other) evolved over time? A.2.5 How has the role and space of the civil society evolved over time? | Analysis of the context over time Review of UNICEF’s analysis of political and economic factors Consistency between changing social, political and economic context and UNICEF strategies Analysis of results from KAP and other social surveys over time | Document review - Context documents - CDP - UNICEF strategic reviews - Surveys and statistics (e.g. Turkstat; KONDA Research Company, etc) - Other academic and background documents |
| A.3 Legal and policy context What are the key legal frameworks and policy commitments of the Turkish state as they relate to the situation of Turkish and refugee children? | A.3.1 What gaps exist in the legal and policy frameworks with regard to the security, well-being and development of girls, boys and women? A.3.2 How has UNICEF engaged with these frameworks and sought to influence them? How has it addressed sensitive issues concerning girls and women’s rights? A.3.3 What issues exist with regard to the implementation of relevant laws and policies? What are future prospects in this regard? | Analysis of relevant changes in the policy frameworks Analysis of UNICEF policy and advocacy strategies and reported results | Document review - National Development Plan (2014-2018) - Reporting to OHCHR and concluding observation on CRC, CEDAW, Committee on Migrant Workers, Committee on Economic, Social and Cultural Rights; and others - Other background documents KIIs with the stakeholders, main partners |
| A.4 UNICEF programme relevance To what extent has UNICEF’s programme addressed the priority needs, vulnerabilities and inequities facing girls and boys in Turkey (including Turkish and refugee / migrant children)? | A.4.1 How well did UNICEF’s programme reflect the needs analysis above ((i) scale and prioritization of UNICEF programme; (ii) nature of interventions; (iii) choice of implementation modalities) A.4.2 Were the sectors and forms of intervention chosen by UNICEF the rights ones, taking account of the context and the roles/capacities of others (e.g. government, UNs, donors, civil society)? A4.3 How consistent was the UNICEF Country Programme with Turkey’s National Development Plan? A.4.4 Were gender dimensions clearly articulated? Did they evolve to fit the changing context? What limitations did the programme face due to the restricted operating environment for civil society? How does UNICEF’s approach fit with the broader UN concern for preserving civil society space and UNICEF’s concern with participation of children and youth in society? | Correspondence between needs / vulnerabilities of different groups of children and UNICEF programming over time Extent to which UNICEF areas of intervention are aligned with needs assessment findings over time Analysis of the UNICEF positioning and programmatic constraints in relation to the evolving context (e.g. limitations due to the restricted operating environment for civil society) Coherence between UNICEF’s and UN’s approach (particularly but not exclusively on preserving civil society space and participation of children and youth in society) | Document review - National Development Plan (2014-2018) - Needs assessments and analysis, including regional needs assessments and analysis for Syrian refugees - GoT data (including DHS) - Turkstat data & analysis - Reporting to OHCHR and concluding observation on CRC, CEDAW, Committee on Migrant Workers, Committee on Economic, Social and Cultural Rights; and others - Other background documents KII with UNICEF, other UNs, Donors and NGOs. |
| A.5 Evidence-informed programming To what extent has the design and delivery of the CP been informed by evidence on the evolving situation of girls and boys (gendered assessment, surveys, situation monitoring, etc.), programme interventions (monitoring, evaluation, etc.) and analysis of related causal factors? | A.5.1 Was a sound evidence base available with respect to the situation of girls/boys & related programming on education, child protection, social Protection and Social Cohesion, and Social Policy, Monitoring and Data? A.5.2 Did UNICEF fully used available evidence to inform the evolving programme and its delivery? Are gender priorities and needs explicitly addressed? A.5.3 What efforts were made to generate and share further evidence on children (Turkish and refugee / migrant girls and boys) A.5.4 What limitations, sensitivities and constraints have surrounded the collection of relevant data and its use? How has UNICEF tried to overcome these constraints with its partners? Including analysis of CRM systems & their output | Trends of evidence over time in Education, Child Protection, Social Protection and Inclusion and Social Policy. Availability of data disaggregated by population type (Turkish, refugee/migrant), gender and age. Analysis of use of evidence in programme documentation (strategy, reports) | Document review - National Development Plan (2014-2018) - Sectorial needs assessments and analysis, including regional needs assessments and analysis for Syrian refugees - GoT data (including DHS) - Turkstat data & analysis - Reporting to OHCHR and concluding observation on CRC, CEDAW, Committee on Migrant Workers, Committee on Economic, Social and Cultural Rights; and others - Other background documents |
| A.6 Target setting and indicators Were targets set proportionate to need, appropriate and realistic, in light of other capacities? Were appropriate indicators set? | A.6.1 Were targets in the UNICEF areas of programming (Education, Child Protection, Social Protection and Social cohesion, Social Policy, and Monitoring and data) proportionate to assessed needs, taking account of other roles and capacities (e.g. government, UNs, donors, NGOs and civil society)? A.6.2 How relevant and appropriate were the related indicators? Are they gender responsive? A.6.3 Were targets realistic given operational and resourcing constraints, and implementing partner capacity and expectations? | Proportionality of targets versus needs over time broken down by areas and demographics and gender Analysis of the funding received vs. requested. Analysis of risks and constraints to delivery | Document review - Needs assessments and analysis, including regional needs assessments and analysis for Syrian refugees - CPD and sector strategies - RAM data - Annual reports - 3RP reporting - NGO shadow reporting on CRC KII with UNICEF staff, Government, Donors and NGOs |
| B. UNICEF strategy, programme coherence and compliance | Sub questions | Indicators/means of analysis | Sources of verification |
| B.1 Strategic logic and coherence How cogent and coherent has UNICEF’s overall strategy been in Turkey over the evaluation period? | B.1.1 Does the ToC underlying the CP provide a clear and compelling explanation of key causal factors, links between outputs and outcomes, choice of strategies? B.1.2 Is the UNICEF strategy overall balanced (e.g. balance between sectors, populations, vulnerabilities and gender) and coherent? B.1.3 How well are risks and assumptions formulated? B.1.4 Does the overall strategy properly take into account the role of other actors? B.1.5 Did the strategy draw on previous learning exercises and evaluations? B.1.6 Was it right to integrate the humanitarian and development programmes? How well is this achieved in the strategy? Was the right balance struck between refugee-specific and Turkey-wide priorities? How did this evolve over time? | Analysis of overarching CPD Theory of Change and subsequent revision Consistency between the strategy and national priorities Consistency between the strategy and regional priorities for refugee children Coherence between the UNICEF strategy and other UNs | Document review - CPD and related sector strategies KII with UNICEF (Turkey and regional), Government, other UNs |
| B.2 Logic of programme interventions What sectoral strategies exist, how clear are they and how strong is their logic? | B.2.1 In the CP is the current formulation of Outputs – and their grouping under the four Outcomes – the right one? B.2.2 How clear and logical are the sectorial strategies (Education, Child Protection, Social Protection and Social cohesion, Social Policy, and Monitoring and data)? | Analysis of sector strategies and related Theories of Change (actual/ inferred) Consistency between sectoral strategies and accepted good practice and UNICEF’s global learning on the relevant agenda | Document review - CP Implementation Strategy and related sectoral ToCs UNICEF’s and international Sectorial good practices and standards |
| B.3 Use of change strategies Were the implementation/change strategies utilized appropriate to the evolving context and the intended outputs? | B.3.1 Were the change strategies for education appropriate over time, given intended outputs? B.3.2 Were the change strategies for child protection appropriate over time, given intended outputs? B.3.3 Were the change strategies for social protection and social cohesion appropriate over time, given intended outputs? B.3.4 Were the change strategies for social policy, monitoring and data appropriate over time, given intended outputs? | Analysis of sectorial ToC and change strategy effectiveness over time Analysis of relative efficiency and added value of UNICEF’s role in relation to that of others | Document review - CP Implementation Strategy and related sectoral ToCs - COARs - Programme evaluations - 2018 Programme Review KIIs with UNICEF, Government, NGOs partners |
| B.4 Programme integration and coherence How well integrated have the various programme components been? Has there been synergy between the component parts? | B.4.1 What were the links, synergies and disconnects between programme elements? B.4.2 Were cross-sectoral linkages and multi-sectoral coordination mechanisms (national / local) effective? B.4.3 How well has gender been mainstreamed? | Mapping and analysis of the links in strategies, programme design and planning. Evidence of linkages in partnership documents. Existence and effective use of feedback mechanisms between different programme components | Document review - Strategy documents - Partnership documents - UNICEF reports - Gender Outcome Working Groups – key documents KIIs: UNICEF section, field staff, partners Programme site visits / observations |
| B.5 Policy compliance How consistent has the programme design been with UNICEF’s own international policy commitments (including those on gender) and with sectoral guidelines? | B.5.1 Is the programme consistent with UNICEF commitments in international law (CRC, CEDAW, etc.) and Core Commitments for Children (CCCs)? B.5.2 Is the programme consistent with Corporate Strategic Plans (global and regional) and Gender Action Plans? B.5.3 Is the programme consistent with UNDCS and with the Syria Regional Refugee & Resilience Plan (3RP)? B.5.4 To what extent has a human rights-based, a gender-sensitive and an equity focused approach been applied across all programmes areas? Mainstreamed in data collection? | Consistency of programme design and implementation against policy commitments Extent to which child participation is taken considered in the CP design and implementation Evidence of mechanisms to protect individual staff and beneficiaries from sexual abuse and exploitation and complaint mechanisms. Gender Assessment Follow up (revised July 2019 and previous ones), number of staff completing gender training, surveys, work plans, etc. Evidence that “twin approach” on gender targeted and integrated priorities increased gender results, for women, girls and boys over the period of GAP implementation. Compliance with UNICEF gender commitments (e.g. did the TCO implement the minimal standards for gender staffing as requirement in policy? Established a cadre of high-quality gender specialists? Strengthened leadership on gender? Gaps filled by consultants?) | Document review - External instruments (UNDCS etc.) UNICEF corporate policy documents and guidelines |
| B.6 Accountability and community engagement How accountable have UNICEF and its partners been to affected populations? What has been extent / quality of community engagement (including children)? | B.6.1 Did UNICEF design and implement adequate processes for Accountability to Affected Populations? B.6.2 How did UNICEF ensure community (including children’s) involvement in needs analysis, programme design and implementation? | Review against accepted good practice in AAP, child participation and UNICEF policy | Document Review: - AAP policy guidelines - Programme reports KIIs with NGO partners |
| B.7 Role and position of UNICEF Overall, has the role played and position adopted by UNICEF in Turkey been appropriate over the evaluation period, given the evolving context and role of government and other actors? | B.7.1 How did UNICEF strategically position itself with regard to main issues arising in the context (e.g. collaboration with sister UN agencies, civil society organizations, women and girls’ rights perceived as ‘sensitive’ etc.)? B.7.2 What was the UNICEF positioning on the main sectors of concern? B.7.3 Has UNICEF been able to fulfil its mandate & maintain independence while playing a constructive support & challenge role? B.7.4 Did UNICEF achieve the right balance in use of change strategies? B.7.4 How should UNICEF’s role evolve in the new CPD? What should UNICEF do more of? Less of? | Experts judgment against UNICEF mandate and policy priorities, capacities and operating space, demonstrated added value | Document Review: - Strategy documents - Partnership documents - UNICEF reports KIIs: UNICEF, Government, and partners |
| C: Programme performance: results, effectiveness, quality | Sub questions | Indicators/ways of analysis | Sources of verification |
| C.1 To what extent has UNICEF been able to achieve its targets in each of the sectors in which it has intervened? | C.1.1 Did UNICEF achieve its targets across all Outputs (Outputs 1A-1J; Outputs 2A, 2B; Outputs 3A, 3B; Output 4)? C1.2. What have been the enabling or constraining factors in each case? How were gender related barriers/bottlenecks addressed and/or mitigated? | Target achievement versus target set. Analysis of RAM data, performance against outcome indicators, data from annual reports Analysis of causal factors in success of failure | Document review: - UNICEF Monitoring system - NGOs reporting - MoNE official statistics - MoFLSS official statistics - MoJ official statistics - Other official datasets at Municipality level KIIs: UNICEF, Government, other UNs, UNICEF partners other civil society organisations |
| C.2 Effectiveness How effective have UNICEF's interventions been, in terms of delivering against the stated Outputs? | C.1.1 Did UNICEF deliver its planned outputs (Outputs 1A-1J; Outputs 2A, 2B; Outputs 3A, 3B; Output 4)? C.1.2 What have been the enabling or constraining factors in each case? C.1.3 How timely has the delivery of UNICEF’s programme been? | Programme performance vs indicators over time. Evidence of durability of effect. | Document review - UNICEF Monitoring system - NGOs reporting - Review of findings from 2018 Programme Review - MoNE official statistics - MoFLSS official statistics - MoJ official statistics - Other official datasets at Municipality level KIIs: UNICEF, Government, other UNs, UNICEF partners, other civil society organisations |
| C.3 Monitoring, quality and results management How effectively has UNICEF been able to gauge the results and quality of its interventions? On gendered impact and results? | C.3.1 What has been the quality of the results monitoring and reporting processes? Are these gender-responsive? C.3.1 What quality assurance mechanisms with partners were in place? | Review and analysis of RAM and other RBM sources against the following criteria: - Comprehensiveness of coverage - Reliability of data (check with KIIs and alternative data sources) - Disaggregation of data - Accessibility and use of data | Document review - RAM - Monitoring reports - Partner reports KIIs: UNICEF, Government, partners |
| C.4 Contribution to outcomes To what extent can contribution to outcomes (direct or indirect) be attributed to UNICEF and its partners’ interventions? Has implementation of the CP led to unintended results? | C.4.1 How does UNICEF seek to measure contribution to outcomes? How valid are these methods? C.4.2 What contribution did UNICEF make to social inclusion and equity? C.4.3What contribution did UNICEF make to social cohesion, particularly between host and refugee populations? C.4.4.What contribution did UNICEF make to better data availability/use C.4.5 What contribution did UNICEF make to gender equality? C.4.6 If negative unintended results are observed, have these been appropriately addressed? | Analysis of changes in priority outcomes, primarily using indicators specified in CPD and RAM | Document review - Official statistics from GoT Ministries (as under C.1 above) and Turkstat - COARs - 2018 Programme Review KIIs: UNICEF, Government, other UNs, UNICEF partners, other civil society organisations Programme site visits / observations |
| C.5 Advocacy and communications How effectively has UNICEF used advocacy and communications in its programme? | C.5.1 How effective has the communications and advocacy aspect of the UNICEF response been? C.5.2 How well has UNICEF used C4D and other modalities to promote positive social norms, e.g. on ending child marriage and gender equality? | Analysis of C4D and advocacy strategies Availability / analysis of evidence of changes in behaviours and attitudes Evidence of impact on adolescent girls’ empowerment Increase in school enrolment (or NFE, Vocational Training) and retention and decrease in child marriage. | Document review - C4D monitoring mechanisms - UNICEF Advocacy strategy and reporting - MoNE official disaggregated statistics on enrollment and retention - Baseline and end-line KAP surveys KIIs: UNICEF, Government, other UNs, UNICEF partners, other civil society organisations Partner survey (TBA) |
| C.6 Lessons learned What lessons has UNICEF learned from the experience of implementing the CPD 2016-20? How well has it responded to those lessons? How should they inform the next CPD? | C.6.1 Lessons learned on Education? C.6.2 Lessons learned on Child Protection? C.6.3 Lessons learned on Social Protection and Social cohesion, Social Policy? C.6.4 Lessons learned on Monitoring and data? C.6.5 Lessons learned on gender and gender equality? | Analysis of programme reports and key informant responses Analysis of UNICEF’s own programme review and reflection processes | Document review - COARs - 2018 Programme Review KIIs: UNICEF - Staff survey |
| D. Sustainability, resourcing and partnerships |  |  |  |
| D.1 Humanitarian – Development Nexus How well has UNICEF managed the links between these two aspects of its programme? | D.1.1 How well has UNICEF managed the ‘nexus’, i.e. the links and convergence over time between the refugee-focused humanitarian programme and the Turkey-wide development agenda? Links to / consistency with the 3RP agenda? D.1.2 How well has UNICEF supported the refugee response over the CPD period? Has the programme evolved appropriately since 2015 (as assessed in the 2015 evaluation)? D.1.3 To what extent has UNICEF enabled the effective integration of refugees into Turkish society (economy, services etc.)? D.1.4 How has UNICEF been able to share experience and learning in responding to the Syrian refugee crisis in the region? Focus on social cohesion issues and integration (including economy/education) | Analysis of evolution or UNICEF’s programme over time (taking account of the rapidly growing refugee population and the evolving policies of GoT in relation to the refugee population) Appropriateness of adaptation over time given sustainability and resourcing issues Analysis of transition from L3 crisis response Analysis of fulfilment of CCC commitments | Document review - Academic Literature on Integration such as Alastair Age, Alison Strang, “Understanding Integration: A Conceptual Framework”, Journal of Refugee Studies, Volume 21, Issue 2, June 2008, pp: 166-191 - COARs - 3RP and related reporting - UNICEF CCCs - UNICEF guidelines - World Humanitarian Summit commitments by UNICEF KIIs: UNICEF, Government, other UNs, Donors UNICEF partners, other civil society organisations |
| D.2 Resilience building How appropriate and effective has UNICEF’s work on resilience been? | D.2.1 How clear is the UNICEF theory concerning resilience (of people, systems, etc.)? D.2.2 How well was that theory applied through the CPD? D.2.3 Is the shift from emergency to resilience responses adapted to new demands and needs of the refugee population? To what extent does it address gender-based inequalities? | Analysis of strategy and implementation of programme components described as resilience-related How well informed by wider learning on resilience (UNICEF, other)? | Document review - UNICEF strategy documents - COAR and other reporting - UNICEF global guidance on resilience KIIs: UNICEF, Government, other UNs, Donors UNICEF partners |
| D.3 Has the system strengthening approach of the CP been appropriate, effective and sustainable given: (i) the existing and projected future capacity and priorities of the Government at national, provincial and municipal levels, and (ii) the capacity and role of relevant partners? | D.3.1 How appropriate and realistic have system strengthening efforts been in each of the sectoral areas in which UNICEF has intervened (Education, Child Protection, Social Protection and Social cohesion, Social Policy, and Monitoring and data)? D.3.2 How sustainable have system strengthening efforts been in each of the sectoral areas in which UNICEF has intervened (Education, Child Protection, Social Protection and Social cohesion, Social Policy, and Monitoring and data)? | Analysis of the evolution over time of relevant systems in priority sectors, and the extent to which UNICEF has contributed positively to this. Analysis of mix and evolution of operational modalities for system strengthening over time (e.g. technical support, training, coaching etc.) for government and partners. | Document review - UNICEF strategy documents - COAR and other reporting KIIs: UNICEF, Government, other UNs, Donors UNICEF partners |
| D.4 Partnerships and capacity development - Has UNICEF had the right partnerships to deliver on its programme objectives? - Has it helped develop the capacity of partners in appropriate and effective ways? Including gender capacity. | D.4.1 Has UNICEF established adequate and efficient partnerships for Education? D.4.2 Has UNICEF established adequate and efficient partnerships for Child Protection? D.4.3 Has UNICEF established adequate and efficient partnerships for Social Protection and Social Cohesion? D.4.4 Has UNICEF established adequate and efficient partnerships for Social Policy, Monitoring and Data? D.4.5 Has the partnership portfolio evolved appropriately over time? | Analysis of evolving partnership portfolio against potential alternatives Analysis of the capacity development investment and efforts and evidence of improved performance from programme monitoring reports. Competency of partners on the UNICEF’s gender mandate | Document review - Partnership lists for programme component - PCAs - UNICEF tracking records of capacity development - Partners reporting KIIs: UNICEF, Government, UNICEF partners |
| D.5 Collaboration and coordination How well has UNICEF collaborated with other actors and coordinated / harmonized its interventions with theirs? | D.5.1 How effective has collaboration and coordination been on Education? D.5.2 How effective has collaboration and coordination been on Child Protection? D.5.3 How effective has collaboration and coordination been on Social Protection and Social Cohesion? D.5.4 How effective has collaboration and coordination been on Social Policy, Monitoring and Data? D.5.5 How effective has collaboration and coordination been on gender? D.5.6 How has UNICEF compensated for the limited scope for partnership with some of its normal INGO partners? And more generally with civil society actors? D.5.7 Has the partnership portfolio evolved appropriately over time? | Analysis of key actual / potential areas of collaboration by sector Analysis of UNICEF engagement with coordination processes Analysis of specific co-ordination mechanisms on gender | D.5.1 How effective has collaboration and coordination been on Education? D.5.2 How effective has collaboration and coordination been on Child Protection? D.5.3 How effective has collaboration and coordination been on Social Protection and Social Cohesion? D.5.4 How effective has collaboration and coordination been on Social Policy, Monitoring and Data? D.5.5 How effective has collaboration and coordination been on gender? D.5.6 How has UNICEF compensated for the limited scope for partnership with some of its normal INGO partners? And more generally with civil society actors? D.5.7 Has UNICEFs partnership portfolio evolved appropriately over time? |
| D.6 Mixed modalities To what extent have implementation strategies adopted by UNICEF been effectively combined to support achievement of sustainable results? | D.6.1 How effective the combination of the implementation strategy was in Education? D.6.2 How effective the combination of the implementation strategy was in Child Protection? D.6.3 How effective the combination of the implementation strategy was in Social Protection and Social Cohesion? D.6.4 How effective the combination of the implementation strategy was in Social Policy, Monitoring and Data? D.6.5 To what extent are specific initiatives sustainable (e.g. the CCTE + Child Care component, incentives to Syrian volunteer teachers)? | Analysis of the sectorial change strategies used over time Programme performance over time against the change strategies Analysis of the UNICEF direct financial support over time and Govt financial planning | Document review - UNICEF strategy documents Key informant interviews |
| D.7 Sustainability and resourcing Has the scale-up of human and financial resources been sufficient to meet the evolving needs of the programme over the CPD period? Are future prospects for funding consistent with UNICEF’s ambition in Turkey? | D.7.1 What have been the key resource issues and operating constraints for delivering the CPD over the evaluation period? D.7.2 How well UNICEF has been able to address these? D.7.3 Has the availability of funding been a significant factor in this? What are the future funding prospects? | Analysis of required posts-position filled-vacant positions over time Analysis of planned vs received resources over time Contribution on the humanitarian funding to the wider programme | Document review - UNICEF financial reports KIIs UNICEF and Donors |
| D.8 Results-based management How well has the system of results-based management been implemented in practice? | D.8.1 Have the results and indicators been consistently monitored through the CPD period to date? Through RAM monitoring frameworks or otherwise. D.8.2 Has the resultant information been used to guide the programme? | Review of RAM data and results frameworks 2016-19 Evidence of data use for programme course correction within/between years | Document review: RAM data / results frameworks KIIs: UNICEF programme managers |
| D.9 Programme transition Does UNICEF have robust exit or transition strategies for its various programme components? | D.8.1 How robust is UNICEF’s forward planning in terms of programme evolution and transition? D.8.2 Does forward planning take due account of funding and other risks / opportunities? | Evidence of contingency plans are in place for e.g. withdrawal of funding Analysis of planning documents for evidence of forward / contingency planning and risk analysis Evidence of joint planning with the relevant government departments | Document review - Contingency planning documents - Communication with Government KIIs UNICEF, Government |

The 2018 Review led to some course correction in the current programme, including revision of some outputs and outcome-level indicators. For the sake of consistent reference, and reflecting the period covered, the evaluation uses the older formulation for the programme outputs and indicators, unless otherwise specified. These are as set out in Annex 3 (‘UNICEF Country Programme Overview’) to the Terms of Reference, current as of February 2019.

See for example Annex 2 to the ToR; and context descriptions in the CPD and 2018 Programme Review

The figures in this section are taken mainly from the 2016-20 CPD and 2018 Programme Review

As defined by the World Bank. Turkey currently has a GNI per capita of around $9000.

Turkstat, Household Labour Force Survey (HLFS), cited in the 2016-20 CPD

Turkstat, Children in Statistics 2014

See Government’s Economic Reform Programme https://www.sbb.gov.tr/wp-content/uploads/2019/04/PEP_2019-2021.pdf

As set out in the 11th Development Plan for Turkey (2019-23)

Interviews with UNICEF staff in Ankara

Ibid. See also Initial findings from the Ministry of Family Labour and Social Services Survey on the Perception of Host Communities to Syrians (2016)

The Syrian refugees are covered by the Law on Foreigners and International Protection (LFIP) of 2013 and the Temporary Protection Regulation of 2014, which entitles them to protection and various services and opportunities. The roughly 370,000 refugees & asylum seekers in Turkey from other countries of origin (Afghanistan, Iraq and Iran) are not covered by the temporary protection legislation but have temporary asylum seeker status under the 1994 Asylum Regulation, provided they are registered with the Directorate General of Migration Management (DGMM).

Interviews with UNICEF staff in Ankara

Data sources for this section are the CPD 2016-20 and Programme Review report 2019, except where otherwise stated. Full references will be provided in the main evaluation report.

Directorate General of Migration Management website, accessed 14 January 2019

UNHCR: https://www.unhcr.org/tr/unhcr-turkiye-istatistikleri, accessed 14 January 2019.

EC Turkey 2019 Report https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/20190529-turkey-report.pdf

AFAD, Syrian Women in Turkey, 2014

UN Women & ASAM, (June 2018) “Needs Assessment of Syrian Women & Girls Under Temporary Protection in Turkey.”

Based on a literature review and consultations with experts, stakeholders and NGOs conducted by UNICEF, in collaboration with the Country Result Group of Gender (RG-G)

The Turkish Demographic and Health Survey, 2013

Comparing within the ECARO region, rates of officially registered marriages involving girls aged 15-19 were highest in Albania (27.2%), Turkey (23%), and Krygyztan (19.1%) and lowest in Kazakhstan (0.9%), Ukraine (2.2%) and Serbia (5.9%). Source: Regional ECA Gender Equality RSF – August 2018, page 11.

Proportion of ever-partnered women aged 15-59 years experiencing intimate partner physical and/or sexual violence at least once in their lifetime. Source: Hacettepe University Institute of Population Studies, Ministry of Family and Social Policies, 2015. Research on Domestic Violence against Women in Turkey. Ankara, Turkey)

According to the UNICEF Programme Review Report 2018

Ibid.

Ibid.

UNICEF Programme Review Report 2018

Ibid.

OECD (2018), OECD Family Database, https://www.oecd.org/els/CO_2_2_Child_Poverty.pdf

World Food Programme, Social Cohesion Online Survey in Turkey (Rounds 1, 2, 3), July 2018, https://docs.wfp.org/api/documents/WFP-0000073545/download/

Global Views on Immigration and the Refugee Crisis,  Ipsos (September 2017) https://www.ipsos.com/sites/default/files/ct/news/documents/2017-09/ipsos-global-advisor-immigration-refugee-crisis-slides_0.pdf

T.C Kamu Denetçiliği Kurumu (Ombudsmanlık), “Türkiye’deki Suriyeliler (Syrians in Turkey)”,pp: 196-197  https://www.ombudsman.gov.tr/suriyeliler/files/basic-html/page8.html

Interviews with UNICEF staff in Ankara. Confirmation of this will be sought.

UNICEF Turkey Country Office (2018), Humanitarian Results Report, December 2018, https://reliefweb.int/sites/reliefweb.int/files/resources/UNICEF%20Turkey%20Humanitarian%20Situation%20Report%20No.%2028%20-%20January-December%202018.pdf

UNICEF Country Office Annual Report 2018

UNICEF Thematic study on extension of the Conditional Cash Transfer programme for Education (2018).

Updated data is expected with the new child labour survey scheduled by TurkStat in the last quarter of 2019

UNICEF Country Programme Document (2016-20)

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/pdf/key_documents/2015/20151110_report_turkey.pdf

Theory of Change – Quality of Evidence

Concluding Observations of the Committee on the Rights of the Child to Turkey, July 2012; 20. (…) the Committee remains concerned about the lack of regular data in areas such as child poverty and well-being, child labour, children with disabilities, injury and risk behaviour. It also regrets the lack of data disaggregated by gender, geographic location, ethnicity and socio-economic background, which would help to monitor the equal enjoyment of their rights by all children in the State party.    21. The Committee encourages the State party to set up a comprehensive data collection system to provide regular and timely data (…) and to analyse the data collected as a basis for assessing progress achieved in the realization of child rights and for designing policies and programmes to implement the Convention. The data should be disaggregated by age, sex, geographic location, ethnicity and socio-economic background to facilitate analysis of the situation of all children.

For example, the Freedom in the World 2015 report reports: “Having risen from the premiership to the presidency in August, he [President Erdogan] formed a “shadow cabinet” that allows him to run the country from the presidential palace, circumventing constitutional rules and the ministries of his own party’s government”.

Theory of Change – Quality of Evidence

Theory of Change – Quality of Evidence

Theory of Change – Quality of Evidence

The Freedom in the World 2015 report classifies Turkey as a “partly free” country, with a worsening trend.

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/20180417-turkey-report.pdf

Under the 10th National Development Plan 2014-18. The 11th NDP for 2019-23 has now been launched.

The Regional Refugee and Resilience Plan (3RP), Regional Refugee and Migrant Response Plans (RRMRP), and the “No Lost Generation” strategy

These are: Equity through social inclusion and resilience-building; Quality data, knowledge and advocacy for child rights; Gender equality among children and adolescents; Turkey-UNICEF expanded partnership beyond borders

Diagram taken from the CPE ToR, UNICEF 2019

Data source: Sheet 7 of Excel document entitled ‘CPE Financial Data 2013-19_ revised pivot – 11 July 2019’ made available to the evaluation team on the CPE Dropbox site.

Capacity is here intended in a broad sense, including the existence of legal frameworks aligned with international standards and provisions, as well as adequate procedures, technical expertise, resources and monitoring systems to ensure proper implementation of the policies (Theory of Change, Access to Justice).

The national CCTE programme has been running since 2002, and most recently in 2017, the programme was extended to the use of Syrian refugee households with school-age (and school-going due to the condition) children.

The Emergency Social Safety Net programme is a major unconditional humanitarian cash assistance initiative for refugees, funded by the EU and jointly run by the World Food Programme, Turkish Red Crescent and Social Assistance and Solidarity Foundations of the Ministry of Family and Social Policies. The programme was launched at the end of 2016, and in its first year the number of beneficiaries reached 1 million. Under the scheme, beneficiary households are entitled to about 120 TL per month per person in the household.

Sufficient reference back to 2015 and earlier years will allow comparison with the findings of the earlier evaluation of UNICEF’s response to the refugee crisis in 2012-2015.

The phrase ‘social policy’ here is used to encompass all child-related policy work. This cuts across the other programme components or areas of intervention listed here and would include (for example) work on public finance for children. It should be noted that the TCO uses the phrase ‘social policy’ in a much more restricted sense, to denote work on child labour, and child friendly cities.

Specifically, the evaluations on Community-based child protection services; UNICEF’s support to education personnel as part of the Syria crisis response; and the Conditional Cash Transfers for Education scheme for refugee children. The 2015 evaluation of UNICEF’s Response to the Syrian Refugee Crisis in Turkey will also be referred to.

March 2008. See http://www.unevaluation.org/document/detail/102. Clearance for the proposed protocols and questions for the field component (partner interviews and community-level focus group discussions) will be sought through UNICEF’s ethical review process as appropriate.

See in particular Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research - Innocenti.

See in particular UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis, April 2015