UNICEF Uzbekistan

Country Programme Evaluation 2019

Inception Report

Prepared for //UNICEF Uzbekistan

By //Charlie Buxton, Emily Delap, Gurcharan Virdee, Regina Safarova, Annalise Struwig and Jerry Adams

Date: 03 December 2019

IOD PARC is the trading name of International Organisation Development Ltd

Omega Court
362 Cemetery Road
Sheffield
S11 8FT
United Kingdom

Tel: +44 (0) 114 267 3620
www.iodparc.com

Table of Contents

Table of Contents	ii

Acknowledgements	iv

Acronyms and Abbreviations	v

1. Introduction and background	1

1.1 Introduction	1

1.2 Purpose of the Inception Report	1

Key activities undertaken in the inception period	1

1.3 Country Overview	2

External context	2

1.4 Key emerging issues from the desk research and inception visit	3

2.The UNICEF Uzbekistan Country Programme 2015 – 2020	5

2.1 The Goal of the Country Programme	5

2.2 Strategic Frameworks for the Country Programme	5

2.3 The main components of the country programme	7

2.4 The Rights Framework of the country programme	8

The rights-based approach of the country programme	8

Integrating gender priorities	8

2.5 Main Challenges Addressed by the Country Programme	9

2.6 Adjustments to the programme.	11

2.7 Programme theory of change	11

2.8	Financial analysis.	12

3. Evaluation Aims and Framework	13

3.1 Purpose, scope and rationale of the evaluation.	13

Evaluation object	13

Purpose and Scope	13

Rationale	14

3.2	Evaluation Criteria and Questions	14

3.3	Expected users and intended use	16

4. Evaluation Methodology	17

4.1	Approach and methodology	17

4.2 Data collection methods	17

Key informant interviews	17

Focus Group discussions	18

Triangulation	18

Debriefing meeting/workshop	18

4.3 Sampling methods for qualitative and quantitative data collection.	18

4.4	Methodological limitations and attribution of results	19

4.5	Ethical Considerations	20

4.6 Evaluation Workplan	20

Evaluation phases and timeline.	20

Deliverables and days	20

4.7 Roles and Responsibilities	21

4.8 Logistics	21

4.9 Quality Assurance	22

5. Annexes	23

Annex 1: Terms of Reference	23

Annex 2: Evaluation Matrix	42

Annex 3:  Data Collection Tools	60

Workshop with UNICEF staff	60

Interviews with UNICEF staff	62

Interviews with partners	65

Discussions with frontline workers	67

Discussions with youth (single sex/ mixed group depending on availability)	68

Interviews with regional advisors / long term consultants providing technical support to programme	69

Annex 4: Workplan	71

Annex 5: Meeting of Evaluation Reference Group	72

Annex 6: Bibliography	78

Annex 7: Stakeholder List	88

Acknowledgements

Many thanks to Malene Nielsen at Regional Office and Zhanar Sagimbayeva and the Monitoring and Evaluation team in the UNICEF Uzbekistan Country Office for providing the IOD PARC consultants with timely information and support, without which this report would have been impossible to produce.

# Acronyms and Abbreviations

| C4D | Communications for Development |
| --- | --- |
| CEDAW | Convention for Elimination of Discrimination Against Women |
| CO | Country office (UNICEF) |
| COAR | Country Office Annual Report |
| CP | Country programme |
| CPD | Country Programme Document |
| CPE | Country programme evaluation |
| CRM | Child Rights Monitoring |
| CS(O) | Civil society (organisation) |
| CWD | Children with disabilities |
| DEQS | Decentralised Evaluation Quality Assurance system |
| ECARO | Europe and Central Asia Regional Office (UNICEF) |
| EQUALS | Evaluation, Quality Assurance and Learning Service |
| ERG | Evaluation Reference Group |
| EU | European Union |
| GEROS | Global Evaluation Reports Oversight System |
| IR | Inception Report |
| M&E | Monitoring and Evaluation |
| NGO MNCAH | Non-governmental organization Maternal newborn and child healthcare |
| OECD | Organisation for Economic Cooperation in Development |
| SDGs | Sustainable Development Goals |
| ToC | Theory of change |
| ToR | Terms of reference |
| UN | United Nations |
| UNCRC | UN Committee on the Rights of the Child |
| UNDAF | UN Development Assistance Framework |
| UNEG | UN Evaluation Group |
| UNICEF | UN Children’s Committee |
| WB | World Bank |

1. Introduction and background

## 1.1 Introduction

- This Inception Report (IR) has been prepared by IOD PARC, a UK-based company specializing in results-based performance assessment in international development. IOD PARC has considerable experience of work with UNICEF on country programme evaluations. For example, in 2014 IOD PARC conducted the country programme evaluation (CPE) of the work carried out under UNICEF’s 2010-2014 programme of cooperation with the Government of Uzbekistan. The analysis and results of this previous evaluation serve as a useful starting point for this Country Programme evaluation

## 1.2 Purpose of the Inception Report

- The purpose of this Inception Report (IR) is to sum up the results of the inception phase and to define the purpose, scope, approach and methodology for the main evaluation study.  The IR is the result of an initial mapping of key UNICEF and country-related documentation, including UNICEF’s programme-level theories and strategies of change.  It is also based on discussions with key interlocutors in the Country Office (CO) and external agencies, including a meeting with the Evaluation Reference Group (ERG).  It includes:

- Confirmation of the boundaries of the evaluation as agreed with the CO, supported by the evaluation manager at the Regional Office (RO);

- A proposed list of the main stakeholders to be consulted in Uzbekistan;

- The overarching analytical framework (evaluation matrix) that will be used for the study;

- The approaches, tools and questions to be used in the evaluation;

- The sampling criteria to be used for data collection at national level and in three regions, and;

- The quality and ethics criteria to be applied.

### Key activities undertaken in the inception period

- Activities included:

- An initial meeting with the IOD evaluation team, ECARO evaluation manager and M&E team in Tashkent.

- Review and assessment of documentation presented in the UNICEF electronic library.

- Confirmation of key tasks collectively and individually within the IOD-PARC team.

- A three-day inception visit to Tashkent (7th– 9th October) to conduct a preliminary round of interviews with country office (CO) staff from the health, education, child protection and C4D components, the UNICEF Representative and Deputy representative, the UN Country Coordinator, and the evaluation review group. A total of 15 meetings were held.

- Discussions with the ECARO evaluation manager and M&E/CRME team in the Country Office of the best approaches and dates for the main fieldwork phase, identifying further interviewees and key partners in Tashkent and two other regions to be visited.

- Development and fine-tuning of the evaluation team’s understanding of key issues arising in the UNICEF programme in 2016-20. This enables the team to move on to phase two - the main country visit.

## 1.3 Country Overview

### External context

- Since the succession of Shavkat Mirziyoyev as President of Uzbekistan in December 2016, the country has proclaimed a new National Development Strategy 2017-21 and embarked on reforms focusing on economic development via strengthening market systems. This responds to an uncertain economic situation across the Eurasia region in which national growth rates had slowed (5.3% in 2017) and unemployment remains high (officially 7.2% in 2017) – only held in check by significant labour migration to Russia, Kazakhstan and the Gulf States. Poverty rates have fallen significantly over the past 10 years, but they remain high with GDP per head in Uzbekistan at only 2,138 USD (UN Data, 2014), and outlying regions and rural areas in Karakalpakstan and Surkhandarya have been more seriously affected. Young people under 18 make up one-third of the population and their expectation for decent jobs requires considerable investment from both government and the private sector. UNICEF’s own studies indicate that 42% of youth are not in education, training or education (2018). Many families (especially children and youth) are affected by work migration.

- The new National Development Strategy places emphasis on a greater role for the private sector but also promises reforms in social policy (in which UNICEF is playing an important role).  Uzbekistan has a strong record in state education and health provision (twice the global average for lower-middle-income countries) and defending its social welfare and equity gains will be a priority. However in both sectors improving (or just maintaining) quality of services is a growing challenge.

- Uzbekistan has made steady progress in improving the health, nutrition and well being for maternal and child health as well as address disparities that arise between rural and urban areas, gender and vulnerable groups.  This progress is evident on reforms to the overall health sector and child health systems.  Nevertheless, challenges remain such as lack of health management practices at all levels of the system and quality of maternal health care continuum. Despite high coverage of antenatal care and of skilled attendants at birth, around 49 per cent of maternal deaths are directly related to obstetric factors or incorrect management of complications.  These issues remain the Government’s priority to address.  In its 2013 Concluding Observation to Uzbekistan's report, the UNCRC highlighted that the quality of maternal, perinatal and early neonatal care is inadequate.

- A Listening to Citizens study in 2018 (World Bank 2108) showed that 80% of respondents felt optimistic about the country’s future.  However, concerns were expressed about rising prices and limited job opportunities for youth. As an indicator of the more open political climate, international agencies are now being inundated by requests for advice from the government. The requests for assistance from UNICEF now include areas that were previously not covered / considered sensitive, specifically in child rights monitoring and child protection. UNICEF has already worked to maximise emerging opportunities in these areas. For example, significant advances have been made in tackling the issue of children in closed institutions and in juvenile justice more broadly.

- Opportunities also exist for Civil Society Organisations to re-activate themselves after a decade in which only the official national associations for women, youth etc. were recognized and involved by government as social partners. A new law on Civil Society has been adopted. The Ombudsman’s Office now has a Deputy Ombudsman on Child Rights and the National Centre for Human Rights is an active UNICEF partner. President Mirziyoyev’s 2018 decrees on open budgets and public councils opens up opportunities for greater citizen engagement, and Uzbekistan’s improved relations with neighbouring countries like Kazakhstan, Kyrgyzstan and Tajikistan are beginning to enable exchange of experience in these areas. At local level, the inception team was told that the mahalla (neighbourhood committee) system has potential to support new social policy initiatives and social service mechanisms. However this will demand a careful balance between the top down and bottom up elements in the mahalla. In several areas of UNICEF’s programme, the importance of strengthening local government is stressed - for example, district level khokimyats (local government administration) and intersectoral working groups within the child rights monitoring programme.

## 1.4 Key emerging issues from the desk research and inception visit

- Several issues emerged from the inception phase including:

- The need to keep UNICEF analysis of the external (especially political) context continually under review and to reflect on how this is impacting on the design and implementation of programmes.

- How to assess the progress of medium and long-term policy and institutional: changes (the long path to achieving real tangible benefits for children).

- Finding a balance between interventions serving the whole population in certain service sectors, such as school children or mother and child health service users, on the one hand, and particular target vulnerable groups, such as people with disabilities or those living with HIV-AIDS, on the other.

- The risk of investments in complex system changes (eg data systems based on international standards) that may be vulnerable to external events (eg budget cuts, changes in key government personnel) or simply hard to achieve with limited government capacity.

- The question of how UNICEF can ensure the implementation of laws and policies it has helped bring into being (given the very rapid pace of reforms and adoption amount of new decrees and resolutions over the past three years).

- The question of how UNICEF can encourage the opening up of democratic processes and popular involvement in public administration (including via civil society in its various forms) necessary for promotion and consolidation of child rights

- How to encourage greater women and youth participation in decision-making (for greater equity).

- How to support government decentralization and development opportunities for the most remote and disadvantaged regions on Uzbekistan (for greater equity).

These challenges will be considered in the paragraphs below on UNICEF’s current programme. The methodology of the evaluation has been designed so as to address them.

2.The UNICEF Uzbekistan Country Programme 2015 – 2020

## 2.1 The Goal of the Country Programme

- The goal of the UNICEF Uzbekistan Country Programme (CP) 2016-20 was defined as:

“To accelerate progress towards the realization of the rights of children in Uzbekistan”.

Its main components are, in brief:

- Child health and well-being, working across the health system to enhance access to and improve health services.

- Quality learning for all, with provision of support to enhance the quality of education system at pre-, primary- and secondary school levels.

- Child protection and development of family support services as an alternative to residential care; strengthening of the social service workforce, and improving juvenile justice.

- Cross-sectoral. Communication for development, social policy (now including social protection and youth engagement) and child rights monitoring.

## 2.2 Strategic Frameworks for the Country Programme

- The CP is informed by strategic frameworks in two areas.  First, the priorities of the Uzbekistan Government. The box below shows the five priority areas in the Government’s Strategy of Actions for 2017-21, and how these relate to the UNICEF’s programme.

###### Government priorities and how these relate to the UNICEF programme Priority 1 – Enhancing the system of state and public construction. Includes: 1.2 Transparency of public authorities, access to public services. 1.3 Enhancing the public management system, public control, social partnership, civil society development, improving the effectiveness of mahalla, mass media.

Priority 2 – Rule of law and further reform of the judicial system. Includes: 2.2 Guaranteeing rights and freedoms of citizens, reduce bureaucracy, work better with citizen appeals 2.3 Enhancing law 2.6 Improving the legal aid system.

Priority 3 – Economic development and liberalization. Includes: 3.4 Reducing state role and enhance small and medium enterprises. Increase role of partners in social and economic development. 3.5 Ensuring balanced regional development, employment opportunities, especially in less developed areas.

Priority 4 – Development of the social sphere. Includes: 4.1 Incomes and employment: increasing real income and job creation 4.2 Social protection system: improving social security and health care systems with a focus on women and children 4.4 Education and science: focus on quality education at all levels with focus on affordability 4.5 Youth policy: including social protection, support for employment (engaging the private sector)

Priority 5 – Security, religious tolerance and inter-ethnic harmony. Includes: 5.1 Environment, security and ethnic/religious tolerance, environmental health, environmental/climate security

Second, the strategies of UN agencies:

- United Nations Development Assistance Framework (UNDAF): The UNICEF Uzbekistan Country Programme is focused on seven out of eight UNDAF Uzbekistan outcomes for the 2016-20 period. These are distributed across four thematic areas: 1) inclusive governance and rule of law; 2) improving livelihoods; 3) social inclusion; and 4) sustainable use of natural resources and disaster preparedness.

- UNICEF global strategies: The Uzbekistan CP was developed during the UNICEF strategic plan period 2014-17 but its implementation stretches into the new strategic plan period 2018-21. The ToR for this CPE specified that planning and implementation strategies up until the 2018 Strategic Moment of Reflection will be assessed against the previous strategic plan, whereas CP adjustments after this point can also refer to the current strategic plan.

- The Sustainable Development Goals: The CP is aligned with 11 out of the 17 SDGs, that is: SDGs 1, 2, 3, 4, 5, 6, 10, 11, 13, 16, 17.

## 2.3 The main components of the country programme

- The main components of the country programme can be seen in the box below.

Country programme outcomes and outputs 2016-2020 Outcome 1: By 2020 mothers and children, especially the most vulnerable, have access to quality healthcare services (individual and population based), including in emergency Output 1.1 - By 2020, health managers have increased capacity to implement evidence-based and equity-focused district health system strengthening plans, including in emergencies Output 1.2 - By 2020, national authorities have increased capacity to formulate evidence-based regulatory framework and budgets for key Maternal Newborn and Child Healthcare (MNCAH) packages of interventions Output 1.3 - By 2020, health providers and communities have increased capacity to provide counselling and support to caregivers and children pregnancy to adolescence Outcome 2: By 2020, girls and boys benefit equitably from improved preschool education and enhanced quality of basic education including in emergency Output 2.1 - By 2018, the government strengthened legislative and policy frameworks to improve access to equitable and inclusive quality preschool and general education services Output 2.2 - By 2019, the government has improved capacity to provide increased access to inclusive and quality early learning services Output 2.3 - By 2020, the government is equipped with tools and skills to better formulate and implement programmes for inclusive and quality general secondary education for all children Output 2.4 - By 2020, the government is equipped with tools and skills to promote safe behaviour practices among children and communities before and during emergencies Outcome 3: By 2020, the most vulnerable girls and boys, increasingly access prevention and response services to address neglect and abuse Output 3.1 - By 2020, the government has increased capacity to apply integrated approaches to delivering child protection and social protection services in line with international best practice Output 3.2 - By 2020, the justice system has increased capacity to manage cases involving children in contact with the law according to international standards Output 3.3 - By 2020, government capacity is increased to reform social protection policy and system to effectively address the needs of vulnerable groups Output 3.4 - By 2020, the government and CSOs have increased capacity to analyze and monitor the situation of children, youth and women and develop programmes to address bottlenecks and barriers identified (as expressed in the CPE TOR)

## 2.4 The Rights Framework of the country programme

### The rights-based approach of the country programme

- The 2016-2020 programme was drawn up to reflect the observations of the UN Committee on the Rights of the Child (UNCRC) and the Elimination of Discrimination Against Women (CEDAW) and to support the Uzbekistan ratification of the UN Convention of the Rights of Persons with Disabilities. The programme aims to address a range of child rights, including rights to protection and care, health and education.

- The programme has a strong component on Child Rights Monitoring which aims to ensure that all rights are assessed, that accurate information on progress against the CRC is collected and shared, and that the recommendations of the Committee on the Rights of the Child are implemented.

- The programme also adopts a rights-based approach through addressing issues of participation, through for examples its work on youth engagement.   The programme seeks to ensure that all children in Uzbekistan are able to achieve their rights through its approach to equity.  This includes efforts to work in the most impoverished regions of the country and to ensure that the needs of particularly vulnerable groups such as children with disabilities, and children affected by migration are met through the programme.  This also includes efforts to address gender as discussed in the following section.

- The evaluation will seek to explore the degree to which a rights-based approach has been successfully adopted by the programme through assessing:

- The extent to which the programme has been successful in its efforts to support the achievement of child rights.

- The extent to which the programme has successfully supported enhanced monitoring and reporting of child rights.

- The degree to which the programme has responded to the recommendations of the Committee on the Rights of the Child.

- The degree to which the programme is promoting child and youth participation.

- The ways in which the programme has addressed issues of diversity, gender and equity.

### Integrating gender priorities

- The gender aspect of the programme can be seen across child protection health, education, WASH and social policy, for example focusing on issues like maternal health, or the situation of girls in closed institutions. The programme includes a Communication for Development (C4D) component, which tackles social norms that affect gender such as traditional attitudes as negatively reinforcing a women’s place in the family; the sensitive topic of domestic violence, and the situation of families affected by migration.

- The evaluation will assess gender-related priorities and actions against UNICEF’s 2014-17 and 2018-21 Gender Action Plans (GAPs). The CPE TOR states: “In the current CP, gender is not a targeted intervention in the Government’s Strategy of Actions for 2017-21 as defined in the 2018-21 GAP. In the CPD, gender mainstreaming reflects quality maternal care, gender-based violence on prevention and response mechanisms; gender responsive WASH systems; and non-gender-discriminatory roles, expectations and practices for girls and boys as defined on the 2018-21 GAP.” The importance of the gender aspect was stressed in meetings with the UNICEF Country Representative, and has been highlighted recently, for example, in different outcomes for young men and women in the report on youth out of education and employment.

## 2.5 Main Challenges Addressed by the Country Programme

- The inception phase has identified several challenges within the country programme that will require more attention during the evaluation.

- First, the evaluation will assess the level of UNICEF cooperation and influence with government systems, budgets and services in the post-2016 political environment. The UNICEF programme is closely aligned with national strategies and action plans for child protection, education, reproductive health, maternal and child health and combating HIV-AIDS. Responding to the changes in government, the CO has reviewed its priorities and now emphasizes “upstream” system strengthening working on child protection, health, education and social policy and programmes with state bodies, public agencies, academic institutions and CSOs; all this within its global mandate to fulfil child rights with an equitable approach. But the challenges here are significant, including 1) how to process the large number of decrees and resolutions passed by the presidential Administration and Cabinet of Ministers; 2) the readiness and capacity of National Government agencies to coordinate new directions of work, including the need to further improve their analytical capacity and human resources; 3) the risks involved in implementing a market-oriented strategy in which poorer or vulnerable groups may be negatively affected.

- Second, institutional strengthening is a priority in all UNICEF’s main programme areas, but requires considerable time to show results. This applies to the support given to Uzbekistan’s new Pre-School Ministry, to the efforts to coordinate social and child protection reforms under a single agency, or to strengthen district level health care systems and tackle complex issues like healthcare financing with the Ministry of Health.  The sustainability of large investments is a linked issue for UNICEF, for example, the major immunisation programme soon to be handed over to Government. The GAVI-funded immunisation project represented over one-third of the UNICEF budget in CP 2016-20. It included not just the procurement of vaccines but also the repair and construction of cold storage facilities across 12 regions of Uzbekistan plus training of staff in the cold storage chain. Ensuring that the gains made in immunisation systems are maintained by government is a major issue for the final year of the programme.

- The challenge in all these areas here is how to maintain the dynamic of policy and institutional change. The evaluation team will continue to use the concept of “operating space” introduced in the 2014 CPE so as to assess opportunities gained and challenges remaining, with its three main components: 1) the level of dialogue between UNICEF and its national partners, 2) the degree of shared vision with government on key questions, 3) practical opportunities for partnership. The CPE will once again analyze the amount of operating space available for each programme component.

- A third task for the evaluation team is to investigate how far the programme is effective and efficient, working for long-term change as well as short-term outputs. For example, is there a risk that it is trying to do too much, and so might lose programme coherence?

- Fourth, the evaluation will consider how far the UNICEF programme has been able to focus on vulnerability and equity for its main target groups. Here one of the main problems identified in the previous CPE was the lack of quality data from government bodies. It is clear that considerable progress has been made during the CP period, beginning with the country Situation Analysis and continuing with specialized studies and surveys. The inception visit showed the need to balance between interventions for tightly specified target groups, on the one hand, and for the wider population to benefit from education, health, child protection, or social policy reforms, on the other.

- Fifth, the evaluation will assess the capacity and systems in UNICEF country office to learn from programme experiences, partners and beneficiaries. The inception visits highlighted the importance of regularly reviewing the theory of change (TOC) for each programme or component. It may be that they are of more practical help at the lower levels – we can see this in the fact that several component level TOCs have been revised during the CP. UNICEF does not have a TOC for the Country Programme as a whole, but the Programme Strategy Note 2018 partially serves this function.

- Finally, there is the challenge of working across sectors and the need to combine top –down and bottom up approaches, both identified as crucial for programme effectiveness.  The 2014 CPE was quite clear in its recommendation 1) not to get involved in too many disparate projects, 2) to focus more on policy influencing than, for example, building capacity or providing technical assistance through training at lower levels in the government structures. However, new government policies and programmes will rely on staff at regional, district and community level for effective delivery. Here, the evaluation also needs to explore the balance between national and local in UNICEF’s work. An example here is social work where there is a need to fully establish a strong child protection system with associated professional staff, case management systems, and appropriate policies and guidance; and to reduce the on-going reliance on institutional care for the care of children outside of parental care.

## 2.6 Adjustments to the programme.

- Several of the outputs and success indicators have been amended during the life of the programme. Thus, at the Strategic Moment of Reflection (July 2018) it was noted: “While the situation of children has not changed fundamentally, the significant reforms initiated in the country and the expanded opportunities as a result of UNICEF advocacy efforts and programmatic support call for modifications of the programme”.

- As a result:

- In Mother and Child Health, new indicators were added to reflect issues related to CWD and to incorporate elements of risk-informed programming. Interventions related to adolescent health and early interventions were expanded.

- In Quality Education for All, outputs were mainstreamed to better reflect regional priorities and align more closely with the SP outcomes. The Programme developed its focus on the second decade of life, for instance, by expanding the scope of curriculum reform to higher levels of general education.

- In Child Protection, new indicators were introduced to sharpen focus and make use of the expanded operating space. One of the results areas was expanded to include elements of social protection and child care services. A new output was added in social protection systems and the output on Child Rights Monitoring was expanded and new indicators added to include studies in the area of youth.

- During the country visit the evaluation team will have the opportunity to discuss the details of these changes with UNICEF staff and assess their consequences with programme stakeholders.

## 2.7 Programme theory of change

- There is no over-arching theory of change for the country programme.  However, each UNICEF programme component has its own theory of change that addresses cross-cutting components like Gender and C4D. The theories of change identify overall strategies, desired operational changes and immediate results. That is to say, they define a change pathway – and also list the main assumptions and risks involved. The CO reviews and adjusts the TOCs regularly at programme component level. It should be noted that many factors are 1) changing fast, 2) outside UNICEF’s control. Hence the recognition by the CO leadership of the need to be flexible and take up opportunities as they arise. Assumptions and risks will be examined in detail in the evaluation.

- The evaluation team will consult with the CO as to whether it would be useful to reconstruct an over-arching TOC or logic model – especially as this is a “theory- based” evaluation. The focus will be on the flexibility, adaptability and sensitivity to risk that the TOC tool allows – and how much it has helped (rather than simply adding another level of planning and reporting). As one respondent during the inception visit noted: “TOC helps us to realize that we don’t know everything already”

## Financial analysis.

- The Country Programme 2016-20 had a budget of approximately 32 Million USD. In September 2019, the financial results were presented within an outcomes analysis / rating as follows:

| ###### Outcome / Budget | Planned | Funded | Utilized | Unfunded |
| --- | --- | --- | --- | --- |
| Health | 9,555,000 | 13,859,064 | 11,794, 295 | (4,304,064) |
| Education | 11,000,000 | 3,285,119 | 3,168,422 | 7,714,881 |
| Child protection | 6,025,000 | 3,937,082 | 3,666,386 | 2,087,918 |
| Management | 0 | 1,143,520 | 1,108,116 | (1,143,520) |
| Cross-cutting | 5,270,000 | 5,695,029 | 5,624,482 | (425,029) |

- These figures showed that from an initial budget of 31,850,000 USD, by September a total of 25,361,701 USD had been spent (79.6%). There had been considerable variations in spending between outcomes in relation to the original plan. The evaluation team met staff from the Operations section during the inception visit and began a discussion about the structure of UNICEF budgeting, the opportunities and modalities of resource mobilisation, the procedures for financing operations and how these aspects can be assessed for effectiveness and efficiency. This analysis will continue in the next stages of work, for example, in relation to different strategies and modalities of work, or the changes in “planned, funded/unfunded and utilized” resources in the programme.

3. Evaluation Aims and Framework

## 3.1 Purpose, scope and rationale of the evaluation.

### Evaluation object

- The object of this evaluation is the UNICEF Uzbekistan country programme. Specifically the country programme (CP) of cooperation 2016-20 that UNICEF developed in partnership with the Government of the Republic of Uzbekistan.

### Purpose and Scope

- As defined by UNICEF in the ToR, the CPE has three objectives, which are to:

- Provide an independent performance assessment of the CP 2016-20 seen in relation to expected results and UNICEF’s contributions to realization of child rights in Uzbekistan for which inequity and gender are considered to form part;

- Assess UNICEF’s strategic positioning and programmatic choices made given government priorities and the changing socio-economic and political context in Uzbekistan; and

- Identify good practices and draw lessons and forward-looking recommendations from the assessment of 1) and 2) above that can inform the development of the next CP.

- The evaluation covers the entire portfolio for 2016-to date including cross-cutting issues and inter-sectoral support like Communications for Development (C4D), social policy, and gender. The scope of the evaluation is all areas - geographic location, thematic fields of interventions, administrative levels, population groups - covered by the Country Programme. But it does not entail a detailed assessment of any one CP component.

- While the CPE objectives span both accountability and learning, the emphasis is on learning that can inform future strategic decision-making with regard to UNICEF’s co-operation in Uzbekistan, using a theory-based approach. The Learning section in the 2018 Country Office Annual Report (COAR) identifies four main problems still holding back the programme which will be explored during the evaluation:

- Access to reliable data;

- Access to communities (to get feedback on how UNICEF or government programmes are working, to get inputs from CSOs);

- Challenges in strengthening government capacity at district level and in taking up opportunities to influence and engage at national level (the latter has been more successful than the former); and

- The absence of lead agency in Child Protection and Social Protection.

### Rationale

- The rationale for this evaluation is a requirement for the development of the new Country Programme Document (CPD). It is formative as the current CPD is due to finish in 2020. Its prime purposes are for accountability and learning. The CPE sets out to document and account for UNICEF’s performance and contribution towards national development goals. The CPE will look back and assess the relevance, effectiveness, sustainability, efficiency, synergies and longer-term changes associated with UNICEF’s portfolio, and programmatic and strategic choices made in the design and implementation of the CP to identify good practices, and draw lessons and forward-looking recommendations that can inform the 2021-25 CP planning process, which will commence during the last quarter of 2019. Finally, points made in this Inception Report can be used to inform the UNSDCF planning round taking place in the last quarter of   2019.

## Evaluation Criteria and Questions

- The TOR for the CPE employs the evaluation criteria created by OECD and sets a number of key questions that will provide the basis for the data collection methodologies and tools to be used. These questions are shown in the box below. The CPE Evaluation Manager in collaboration with the CO has invited the evaluation team to decide what emphasis to place on the different criteria. Having reviewed the questions the team propose that whilst addressing each of the question areas they will highlight issues around relevance, effectiveness, efficiency and synergies as highlighted in UNICEF’s TOR for the evaluation. Whilst judgments about sustainability and longer-term change are more difficult especially as the programme has one more year to run. However, it will be possible to examine some aspects of sustainability and longer-term change.  For example, sustainability will be explored through examining the possibility of scale-up, and some aspects of the programme may have started to show impact.

Evaluation criteria with key questions Relevance - To what extent has UNICEF ensured that the needs of vulnerable boys and girls have been considered in the planning and implementation of UNICEF-supported interventions defined to advance child rights? - To what extent has UNICEF managed to advance child rights focusing on the most vulnerable boys, girls and youth at risk of being left behind whilst simultaneously making a contribution at scale? - Were the implementation strategies utilized relevant for the context and the way it has evolved? - To what extent have the strategic recommendations of the previous CPE been addressed regarding the particular operating conditions in Uzbekistan, ie the need to a) adopt a politically astute and pro-active approach with a greater emphasis on targeting key entry points for dialogue and cultivating strategically important relationships; b) build a common ground with the Government on areas where a lack of shared understanding or collective intent prevails; and c) develop a CP with a strong focus that reflects clarity on the political and governance context in Uzbekistan and the short=, medium- and longer-term results of investments made. - To what extent do the recommendations made by the previous CPE remain relevant? Effectiveness - To what extent were programme results achieved? - Were there any unintended negative or positive outcomes and, if so, were they appropriately managed? - To what extent has gender been effectively mainstreamed in the CP design and implementation and, if not, how should it be done? - To what extent has the CO effectively deployed C4D across the CP? - To what extent do the individual CP components reinforce each other to leverage the contribution that UNICEF makes towards expected results? - Have opportunities to enhance program effectiveness and mitigate risks been appropriately managed? Efficiency - To what extent are the resources (financial and human resources) allocated by the CP appropriate to support the implementation of strategies and achievement of CP results and, if not, what could be done to ensure resources match programmatic ambitions and needs? - To what extent has the CO demonstrated capacity to take appropriate actions when funding opportunities arose? Sustainability - To what extent are the results of the CP at district, regional and national levels sustainable? - In the shorter and longer-term, what opportunities can be identified to enhance sustainability of the programme and diminish risks? Synergies - To what extent has the CP been designed and implemented in line with the SDGs and targets? - To what extent is UNICEF coordinating with development partners and other UN agencies to avoid overlaps, leverage contributions and catalyze joint work? Long-term change/impact - To what extent can UNICEF be considered to have made a contribution to observed progress in the realization of children’s rights?

- The team have reviewed the questions in the above box and have concluded that they provide a sound basis for focusing the evaluation. IOD-PARC does not plan a significant divergence from this agenda or the emphasis on particular criteria contained in it. At the same time the questions have been used to develop a set of supporting interview protocols that will be used in interviews with government and non-government key informants. These are given in Annex 3.

- The results of programme work will be measured against the indicators set by UNICEF in its country programme, annual and other plans and amended in some cases during the period.  These are based on the most recent theories of change and work-plans for each of the components of the country programme (as noted above, these changed in 2018 following the strategic moment of reflection).   This provides the basis for the evaluation matrix that gives the evaluation questions, their related sub-questions, indicators and related data collection tools in Annex 2.

## Expected users and intended use

- The evaluation will bring together learning generated during the current CP during a period of political and economic reform in Uzbekistan.  It will help design UNICEF’s next strategy, ensuring alignment with gender, other cross-cutting objectives, and synergy with the relevant Uzbekistan government, SDGs and UNSDCF outcomes. In a high-level analysis of this kind, attributing results to UNICEF’s work will be a challenge and Contribution Analysis techniques will help to identify and qualify key expected and unexpected outcomes. The inception visit and Evaluation Reference Group meeting provided the chance to begin a stakeholder analysis that will continued in the main data collection visit. A focus on easy utilisation of evaluation results will be achieved by using simple, clear language and the production of timely and concise evaluation outputs. For example, during inception meetings, the CO leadership requested early feedback from the evaluation for their planning process, which the team will aim to provide through an end of field visit workshop giving a presentation of provisional findings.

4. Evaluation Methodology

## Approach and methodology

- The evaluation will take a theory-based approach to assessing the Country Programme and sectoral as well as individual ToC’s. This means not just that it will take a strategic, overall view of the programme, but that it will base itself in the theories of change and UNICEF’s global analytical frames in attempting to understand and assess the contribution of the different programmatic interventions to the anticipated chain of results (short-term outputs, medium-term outcomes) and contribute towards longer term impacts. This approach seems best in order to take account of the formulation of the Country Programme under UNICEF’s 2014 – 2017 Strategic Plan as well as revisions made to ensure the alignment of the Country Programme into the current UNICEF Strategic Plan (2018-2021).

## 4.2 Data collection methods

### Key informant interviews

- A range of data collection tools have been selected to ensure that appropriate tools for each stakeholder group, and to enable the triangulation of data.  Key informant / expert interviews will be the main tool used with national partners during the country visit, reflecting the upstream nature of the programme and the status of the respondents. The interviews will have a semi-structured character, allowing flexibility and greater focus on key topics. Speaking to these individuals in groups would not be appropriate as they are likely to have very differing experiences and perspectives that it may be hard to capture in a group setting. In some cases, political sensitivities or organizational hierarchies may also make it hard for individuals to express their opinions in a group setting. A set of tools for semi-structured interviews applying the questions and sub questions in the evaluation matrix for government and non-government respondents is given in Annex 3. The evaluation team will work individually or in pairs, where necessary with an interpreter, so as to give maximum focus and flexibility. In some cases it may be appropriate and relevant (taking into account the points made above) to arrange small group interviews with respondents from linked agencies or stakeholders (government, public agencies, academia, CSOs) working on the same topic or in the same field. In these meetings the methodology will be further adapted and key questions selected for discussion.

- To help triangulation and richness of results the team proposes to run a workshop with CO staff at the outset of the visit. This will allow joint discussion of key issues in programme design and performance, enabling insights to emerge quickly across the different teams and from different levels in the UNICEF office organigram.  The workshop plan is shown in Annex 3.

- The majority of the meetings will be with government and other partners at national level. However, the team will visit three regions – Tashkent city, Khorezm and Republic of Karakalpakstan - to conduct interviews at both district and regional levels. Given the strategic focus of the evaluation and the up-stream nature of the CP interventions, interviews with children are not included in this evaluation.

### Focus Group discussions

- Focus groups. The Country Office has agreed to organise 2-3 focus groups during the country visit. The objective of these meetings will be to gain the experience and views of UNICEF programme beneficiaries (e.g. social work training recipients) or participants in community or C4D activities (e.g. youth networking). The size of the groups will depend on availability. An instruction set for focus groups, including discussions with youth, is attached in appendix 3.

### Triangulation

- Triangulation of the data received will begin during the field mission. As well as the data received from interviews and focus groups, the team will continue its analysis of documentation – the desk research phase that began before the inception visit. For example, it will devote special attention to the resourcing of the programme, the success or otherwise in accessing other donor resources, and financial analysis of budgets and spending. Appropriate coding will be developed and data will be disaggregated, particularly along gender and exclusion lines. Counterfactual explanations will be explored and reviewed. Data gaps will be identified, and mitigation methods identified where feasible (and reported where unfeasible).

### Debriefing meeting/workshop

- The debriefing with UNICEF staff at the country office after the field visit, followed by a feedback meeting with the ERG, plays a very important role as a validation exercise, to test key/emerging findings and to identify any further substantive analysis which needs to be conducted prior to report drafting. A short summary of preliminary findings will be sent to CO senior management before submission of the full report.

## 4.3 Sampling methods for qualitative and quantitative data collection.

- Sampling criteria will consider the following contextual and operational factors:

- The character of CP activities, the implementation strategies used, and the current status of the programme component. For example, some components are quite new, while others are well developed. Some programmes have recently been evaluated (e.g. CRM) or are about to be evaluated in detail (education). The IOD-PARC evaluation has taken this into account in choosing its sample;

- The socio-economic conditions of vulnerable children and families who will ultimately benefit from UNICEF’s support. This factor has been considered in making a choice of the three regions to be visited; and

- The extent to which UNICEF has achieved expected results in the area. This factor relates to the decision to spend more time with stakeholders at national levels than in the regions – because many of the planned results are at policy level.

- The sample has been provisionally agreed with UNICEF, and includes around 80 stakeholders from the UNICEF CO, government and CSOs, chosen after a preliminary stakeholder analysis. Please note that the data collection plan includes skype interviews with ECARO advisors that have been ongoing since the beginning of the inception period.

- The evaluation will be mainly based on qualitative information, obtained in the different ways described above. The qualitative sampling strategies to be applied are a mix of ‘purposeful’ ‘confirming and disconfirming’ and ‘combination/mixed’. Applying these approaches will ensure triangulation of views and information received, with maximum flexibility and consideration of different interests and needs. The presence of the team in Uzbekistan for three weeks allows for a limited snowball or opportunistic sampling approach too – it will consider meetings with other respondents that may be suggested during the visit.

- The evaluation team and CO have agreed a list of stakeholders to be approached using the above criteria. The majority of meetings will be held in Tashkent following the focus of the UNICEF CP on policy making and institutional support at national level. However, the team has not set itself the aim of making a detailed assessment of any one programme area and hence the regional visits occupy 3-4 days in total. The list of planned meetings with stakeholders is not attached since this is a working document and has to be amended by the CO to reflect new mission dates.

- Quantitative analysis of results of the CP will mainly be done by reference to secondary documents – for example, the programme results framework agreed with the Uzbekistan government, the country office annual reports, and outcome/output reviews in the different components. This includes analysis of the financial information referred to briefly in Section 3.

## Methodological limitations and attribution of results

- When designing the evaluation, IOD-PARC identified a number of possible  challenges. These are briefly outlined below, with mitigating strategies to be used by the team:

- Data constraints – both in terms of volume and reliability – are a likely limitation, particularly within sensitive information on child rights and gender, since despite intensive work done on data improvement by UNICEF in all the main programme components, many gaps remain. The team will make full use of previous reports on this topic.

- Complexity and documentation of conceptual frameworks and change strategies. The evaluation stretches over two UNICEF strategic periods, during which the organisation amended its view of the key roles it plays in development. These changes need to be taken into account. The major studies completed by UNICEF will complement the field visit in addressin this challenge.

- External context. It was emphasized by the CO that arrangements for meetings with officials at all levels have to be made formally and well in advance. They also warned that staff turnover affects government departments adversely. This means that the evaluation programme needs to access several different sources of information for all the main questions.

- Attribution of results at outcome or impact level is difficult to achieve when the programme has still one year to run. The question of causality was nonetheless raised during inception meetings: e.g. what was the reason why government changed its policy, created a new implementing agency, or passed a new law? These questions will be pursued further and the success indicators and means of verification will be used to attribute results to UNICEF where possible.

## Ethical Considerations

- The evaluation will observe the ethical principles and standards set by both UNICEF and IOD-PARC. The IOD PARC ethical code contains IOD PARC’s ethical framework for all its work including field visits and has been used in UNICEF evaluations in several countries. This is based on international guidelines for all contexts:

- UNEG Ethical Guidelines for Evaluation, UNEG, March 2008

- UNEG Code of Conduct for Evaluation in the UN System 2007

- DFID Ethics Principles for Research and Evaluation 2011

- ESRC Framework for Research Ethics principles 2012

## 4.6 Evaluation Workplan

### Evaluation phases and timeline.

- The workplan was revised by IOD-PARC in consultation with UNICEF in September and has not changed since then. It includes associated activities, number of days for each team member, locations and deliverables. The amended timeline is included in Annex 4.

### Deliverables and days

- A revised workplan sent to UNICEF on 12 September 2019. Inception meetings in the CO confirmed key dates and deliverables:

- Delivery of inception report – 22 November.

- Visit of evaluation team – 15 working days from 13-31 January 2020.

- Team debrief with CO – 31 January.

- Skype call with senior management on preliminary findings – 21 or 24 February

- Draft report to UNICEF – by 6 March.

- Final report submitted – by 10 April.

- Presentations in Tashkent and Geneva – to be confirmed by ECARO.

## 4.7 Roles and Responsibilities

- Roles and responsibilities of team members have been apportioned according to the needs expressed in the TOR and discussions with the ECARO evaluation manager. IOD-PARC has appointed a team of four people led by Charles Buxton with Quality Assurance and specialist support from Jerry Adams.  The team have extensive experience of working with multilateral organisations, INGOs, CSOs and donors. Their bios are attached to this report.

- Team roles and responsibilities are as follows:

- Jerry Adams from IOD PARC is the contract manager. His role is to provide overall leadership and Quality Assurance.

- As the team leader, Charles Buxton will coordinate work on the evaluation as outlined in the TOR. He visited Uzbekistan for the inception report and will lead the main field mission. He will also lead on the education component.

- Emily Delap will lead the work on child rights monitoring, child protection, and social policy.

- Gucharan Virdee, will lead on the health component and cross-cutting gender issues. Gurcharan will be supported remotely by Annalize Struwig, IOD PARC staff member/Associate with expertise in Health, specifically knowledge of GAVI.

- Regina Safarova, national consultant, will support work in all areas for both the inception and field mission phases.

All team members will contribute sections to both the inception report and the main report.

## 4.8 Logistics

- The evaluation team relies on full cooperation and assistance from UNICEF’s CO for interview arrangements, field visits etc. as noted under Sampling, the team has provisionally agreed two stakeholder lists – one for Tashkent and the other for the regions – with the CO. Approximately 80 respondents have been identified for meetings during the country visit in November. The stakeholder lists define the relation of each person or organization to UNICEF outcomes and components, indicating what kind of meeting is envisaged: individual or group interview, focus group.

## 4.9 Quality Assurance

- IOD PARC has well established approaches to evaluation quality assurance which will provide the team with tools and processes to document and maintain a high standard throughout the evaluation cycle. We are well-versed in UNEG standards and guidelines and have built our approach to quality control systems on our foundation as a centre of excellence in the provision of both innovative and pragmatic M&E assistance. Clients include organisations such as UN agencies and bilateral donors (including UNICEFs GEROS, DFIDs EQUALS, WFPs DEQS, and UN Womens GERAAS).  The team has been introduced to IOP PARCs QA approach from the planning stage. For this evaluation the Inception and Evaluation Reports are also assessed against UNICEF Regional QA standards and frameworks.

- Quality assurance mechanisms will inform both key points in the consulting cycle (e.g. the development of outputs) and the ongoing processes (e.g. our overall project management). A dedicated quality assurance plan has been drawn up for the assignment with the following elements:

- A named senior IOD PARC consultant, Jerry Adams, with specific relevant contextual, methodological and organisational experience who cross references progress and quality standards.

- A progress review at key points with clients (UNICEF and its ERG – see above) to confirm progress and document changes, decisions and client feedback during the evaluation. The CO and ERG meetings and skype call with management provide key points for this review.

- Agreed reporting standards and assessment criteria drawn on UNEG guidance for clients to assess the standard and quality of reports.

- Transparent and systematic responses to client feedback on outputs through a comments tracker for documenting product (report) commentary processes.

- An internal post-project review process to further interrogate our use of QA.

5. Annexes

## Annex 1: Terms of Reference

Terms of References for an Evaluation of the UNICEF – Government of

Uzbekistan Country Programme 2016-2020
1. Introduction: Country Programme Evaluations in UNICEF

These terms of references (ToRs) have been drafted for the evaluation of the country programme (CP) of cooperation 2016-20 that UNICEF developed in partnership with the Government of the Republic of Uzbekistan.

CP Evaluations (CPEs) in UNICEF are strategic evaluations that provide an assessment of the totality of UNICEF’s programme of work in a country. They come with a strong focus on relevance as they assess UNICEF’s programme portfolios, deployed programme approaches, UNICEF’s position and priorities made in response to emerging needs, government priorities and the changing geopolitical and socioeconomic environment in which UNICEF operates. Applied change strategies, country office (CO) operational and workforce planning and UNICEF’s engagement with partners may also form part of these evaluations.

Being strategic evaluations, CPEs are mostly used to draw out lessons to inform the formulation of a proceeding CP. At national level, CPEs may also inform the United Nations Sustainable Development Cooperation Framework (UNSDCF) planning and evaluation processes and, at regional and global levels, they may inform multi-country evaluations, synthesis and strategic evaluations undertaken to assess and/or document UNICEF’s performance, management decisions and policy and programme development.

CPEs in UNICEF align with UNICEF’s 2018 Evaluation Policy with which it has become a requirement for COs to commission CPEs, at least, once every two programme cycles, and once per programme cycle, if monitoring information or audit point to a significant shift in the programme context, or a significant increase in the level of risk. To guard independence, CPEs are manged from regional office (RO) level in close collaboration with COs and with final quality assurance undertaken by UNICEF’s evaluation office in New York.

Evaluation Rationale

Aligned with corporate policy requirements, this formative evaluation of the CP in Uzbekistan serves both accountability and learning purposes. The CPE sets out to document and account for UNICEF’s performance and contribution towards national development goals. The CPE will look back and assess the relevance, effectiveness, sustainability, efficiency, synergies and longer-term changes associated with UNICEF’s portfolio, and programmatic and strategic choices made in the design and implementation of the CP to identify good practices, and draw lessons and forward-looking recommendations that can inform the 2021-25 CP planning process, which will commence during the last quarter of 2019. Finally, the CPE will inform the UNSDCF evaluation undertaken during the second half of 2019 and the UNSDCF planning process that is expected to be completed by November 2019.

Stakeholders

The evaluation may be used by a broad range of stakeholders of which some have a direct stake in the evaluation because they are involved in implementation of the CP or programmatic frameworks, plans or strategies towards which the CP contributes. These stakeholders are referred to as Primary Stakeholders. Other stakeholders, i.e., Secondary Stakeholders, refer to rights holders and duty bearers who benefit from the contributions of the CP, and organisations in- and outside of Uzbekistan with which UNICEF does not have any formal partnership but that work with similar programmes and on child rights issues for which lessons and good practices drawn from the CPE may be relevant.

This section focuses primarily on stakeholders whose perceptions of the CP should be represented in the CPE and who should, ideally, be informed about the evaluation process, its findings and recommendations that may support optimization of joint work. A complete list of primary stakeholders is attached to these ToRs as Annex A. Primary stakeholders include but may not limited to:

- State Bodies. UNICEF’s main Government partner in Uzbekistan refers to the Cabinet of Ministers that is a coordinating agency leading the planning, monitoring and evaluation of the CP from the Government side jointly with UNICEF. In addition, UNICEF collaborates with relevant state bodies on the coordination and detailed contents of each CP component. The line ministries and state agencies include: the Ministry of Health; the Ministry of Preschool; the Ministry of Public Education; the State Inspectorate for the Supervision of the Education Quality under the Cabinet of Ministers; the Ministry of Finance; the Ministry of Employment and Labour Relations; the Ministry of Emergency Situations; the Prosecutor General Office; the Supreme Court; the Ministry of Interior; the Higher Judicial Council; the State Statistics Committee (SSC); and the local governments (Hokymyats). UNICEF is also establishing a partnership with the President’s Office and the National Agency of Project Management under the President of Uzbekistan.

- Public Agencies. Implementation of the CP has been undertaken in collaboration with agencies in Uzbekistan that work with children in areas of particular relevance to the CP such as the Oila (Family) Centre under the Cabinet of Ministers; the National Human Rights Centre; the Youth Union; the Women’s Committee; the National Association of electronic mass media; and the Office of the Ombudsperson.

- Civil Society Organizations (CSOs). UNICEF has also collaborated with CSOs, primarily, as implementing partners and in relation to piloting of CP activities. These include the SOS Children’s Villages, the Republican Centre for Social Adaptation of Children, the Yuksalish (Uprising) Movement, and the Association for Support of Families and Children.

- The Private Sector. During the 2016-20 CP, UNICEF has collaborated with the private sector in relation to fundraising and public advocacy campaigns on promotion of child rights in the country. These include the UCELL telecom operator that contributed to implementation of a WASH programme in schools and supported various advocacy campaigns for children of Uzbekistan.

- The academia: Through the CP implementation period, UNICEF has collaborated with the National University of Uzbekistan, the Tashkent State University of Law and the Tashkent Pediatric Medical Institute on Research and Studies.

- Donors. UNICEF’s multilateral and bilateral donors – without which the CP would not be possible – have a direct stake in the evaluation findings as these will account for UNICEF’s performance. Donors include the European Commission (EU); the Department for International Development (DFID), UK; the Government of Switzerland; the Government of UK and the Global Alliance for Vaccines and Immunization (GAVI).

- UN agencies and international finance institutions. The UN system in Uzbekistan comprises twelve UN agencies resident in country and four agencies contributing from abroad. The UNSDCF that UNICEF signed for the period 2016-20 involved inputs from the WHO; the UNDP; the UNFPA; the UNODC; the UNAIDS; the UNESCO; the ILO; the FAO; the UN Woman; the UNECE; the UNCTAD; IAEA and UNV. In addition, UNICEF partnered with the World Bank.

- UNICEF stakeholders. Finally, stakeholders inside UNICEF who have a particular interest in the CPE evaluation include: Staff in UNICEF’s CO in Tashkent (UCO); the Regional Office for Europe and Central Asia (ECARO), and senior management in UNICEF who can draw upon the evaluation findings for regional and corporate learning and accountability purposes.

Context

Socio-economic Overview

Uzbekistan is a land-locked Central Asian country that borders Kyrgyzstan and Tajikistan to the east, Afghanistan to the south, Turkmenistan to the south-west and Kazakhstan to the north. Uzbekistan has the largest population in Central Asia. In 2017, it totalled 32,656,700 million people of which 33 per cent were children under 18 years. Following a period of economic growth, the country was classified as a lower-middle income country (LMIC) in 2010 with a GDP growth rate of 8.5 per cent. During the period that followed, the GDP growth declined from 8.5 per cent in 2010 to 7.8 in 2016 after which it fell to 5.3 per cent reflecting the recent economic crisis. National income poverty rates have been decreasing, nevertheless, from 24.9 per cent in 2006 to 12.3 per cent in 2016, and the unemployment rate fell from 8.2 per cent in 2010 to 7.2 in 2017. Despite the latter overall encouraging trends, economic disparity and inequity prevail challenging the situation of children, particularly, vulnerable boys and girls. The youth unemployment rate, e.g., remains at 19 per cent, which is significant taking into consideration that youth represent a large proportion of the total population, and 42 per cent of youth are not in employment, training or education.

In Uzbekistan, poverty varies across regions being higher in rural areas, notably, in the north-western region of Karakalpakstan and in the southern regions of Kashkadarya and Surkhandarya. In 2017, Uzbekistan’s Human Development Index (HDI) was 0.71 points, ranking it as the 105th out of 189 countries reviewed and below the average of 0.77 for countries in Europe and Central Asia. With a substantial proportion of the population under 18, the government has placed considerable emphasis on meeting children’s needs, which comes across in the state budget expenditures of which around 54 per cent were allocated to the social sectors in 2017. Despite these investments, social assistance provided by the Government to vulnerable and low-income families have been steadily decreasing in recent years where a significant increase in labour migrants from Uzbekistan has been observed alongside fluctuating remittances. According to World Bank estimates, remittances made 10.1 per cent of GDP in 2008, in 2009 they fell to 6.1 per cent, in 2013 they peaked at 11.6 per cent and declined again in 2016 to a reported 3.7 per cent .

In Recent Years

Following the presidential election in 2016, Uzbekistan embarked on a new path with ambitious economic and social reforms as per the National Development Strategy 2017-21, and the Government has increasingly expressed interest in liberalization of the economy. To this end, the Government has announced launch of administrative reforms; it has initiated reform of the law enforcement agencies and the judiciary, and it has initiated development of social sector programmes and strategies while, simultaneously, enhancing engagements with CSOs.

In January 2019, the Government adopted a National Development Strategy covering the period 2019–21. The National Development Strategy  outlines how the country will achieve its social and economic goals over the medium term in relation to which the Government intends to implement a comprehensive program of reforms defined by five priorities: 1) maintaining macroeconomic stability; 2) accelerating the transition to a market economy; 3) strengthening social protection and citizen services; 4) transforming the Government’s role in the market economy; and 5) preserving environmental sustainability.

It is against this dynamic socio-political context that has provided new entry points and opportunities for engagement with Government partners and public agencies – such as the newly established Ministry of Preschool – that the composition and development of UNICEF’s CP portfolio must be understood.

Programme                                                                                                                       The CP that represents a response to inequity and rights issues affecting vulnerable children in Uzbekistan was signed with a projected budget of US$ 32,795,000. The primary documents that frame the CP are the Country Programme Document (CPD) and the Country Programme Action Plan (CPAP) both of which align with key national policy and strategic documents including but not limited to: the 2014-16 Universal Periodic Review National Action Plan;  the 2013-17 Education Sector Plan; the 2014-18 State Programme on Strengthening the Reproductive Health of the Population, and Maternal, Child and Adolescent Healthcare; the 2013-17 Strategic Programme on combating HIV and AIDS; and the 2015-18 National Action Plan on prevention and treatment of helminthiasis among children.

The goal of the CP is to accelerate progress towards realization of the rights of all children in Uzbekistan.  Aligned with the Convention on Rights of the Child (CRC), the Convention on Eliminations of all Forms of Discrimination Against Women (CEDAW) and reflecting a human rights-based approach, the CP is defined by a strong sector-based approach and an emphasis on up-stream systems strengthening.

As per the CPD, the main components can be summarized as:

- Child health and well-being, which involves work across the health system to enhance access to and improve individual and population-based health services;

- Quality learning for all, which encompasses provision of support at national and regional levels to enhance the quality of the education system at pre-, primary- and secondary school levels;

- Child protection, which involves work with development of family support services and family-based care as an alternative to residential care; strengthening of the social service workforce dealing with child protection issues, children in closed institutions,  children affected by migration, children in conflict with law, and victims and witnesses of crimes. Finally, this component involves provision of support to establishment of a social protection system;

- Cross-sectoral in relation to which communication for development (C4D), social policy and child rights monitoring are implemented to support work across the CP components.

The CP comes with three main outcomes and associated outputs that integrate work defined as cross-sectoral.

These are summarized in Table 1 below:

| Table 1. CP Outcomes and Outputs |  |  |
| --- | --- | --- |
| Outcome 1: By 2020 mothers and children, especially the most vulnerable,2 have access to quality healthcare services (individual and population based), including in emergencies Output 1.1: By 2020, health managers have increased capacity to implement evidence-based and equity-focused district health system strengthening plans, including in emergencies Output 1.2: By 2020, national authorities have increased capacity to formulate evidence-based regulatory framework and budgets for key maternal, new-born, child and adolescent health packages of interventions Output 1.3: By 2020, health providers and communities have increased capacity to provide counselling and support to caregivers and children from pregnancy to adolescence | Outcome 2: By 2020, girls and boys benefit equitably from improved preschool education and enhanced quality of basic education including in emergencies Output 2.1: By 2020, Government has strengthened legislative and policy frameworks to improve access to equitable and inclusive quality pre-school and general education services Output 2.2.: By 2020, Government has improved capacity to provide increased access to inclusive and quality early learning services Output 2.3.: By 2020, Government of is equipped with tools and skills to better formulate and implement programmes for inclusive and quality general secondary education for all children Output 2.4.: By 2020, Government is equipped with tools and skills to promote safe behavior practices among children and communities before and during emergencies | Outcome 3: By 2020, the most vulnerable girls and boys, increasingly access prevention and response services to address neglect and abuse Output 3.1: By 2020, government has increased capacity to apply integrated approaches to delivering child protection and social protection services in line with international best practice. Output 3.2: By 2020, justice system has increased capacity to manage cases involving children in contact with the law according to international standards Output 3.3: By 2020, Government capacity is increased to reform social protection policy and system to effectively address the needs of vulnerable groups. Output 3.4: By 2020, Government and civil society organizations have increased capacity to analyze and monitor situation of children, youth and women and develop programmes to address bottlenecks and barriers identified |

The CP was formulated under UNICEF 2014-17 Strategic Plan (SP) towards which it contributes to all SP outcomes. Under the current SP (2018-21) that is defined by five goal areas with accompanying outcome statements, the CP also aligns with all outcomes. As the CP implementation stretches into the 2018-21 SP period, the current SP has informed definitions of outputs and output indicators that were incorporated into a revised CP results framework following a Strategic Moment of Reflection (SMR) organised during the second half of 2018.

As per both SPs, gender has been considered a cross-cutting issue to be mainstreamed into the CP as per UNICEF’s 2014-17 and 2018-21 Gender Action Plans (GAPs). In the current CP, gender is not a targeted intervention as defined in the 2018-21 GAP. In the CPD, gender mainstreaming reflects quality maternal care; gender-based prevention and response to violence against girls and boys; gender responsive WASH systems; and non-gender-discriminatory roles, expectations and practices for girls and boys as defined in the 2018-21 GAP.

The CP aligns with the Sustainable Development Goals (SDG) goals where it contributes to 11 of 17 goals, namely: SDG 1 (No Poverty); SDG 2 (Zero Hunger); SDG 3 (Good Health and Well-Being); SDG 4 (Quality Education); SDG 5 (Gender Equality); SDG 6 (Water and Sanitation) ; SDG 10 (Reduced Inequalities); SDG 11 (Sustainable Cities and Communities); SDG 13 (Climate Change); SDG 16 (Peace, Justice and Strong Institutions); and SDG 17 (Partnerships for the Goals).

Furthermore, the CP contributes to seven out of eight UNSDCF 2016-20 outcomes formulated around four strategically chosen areas of intervention. These are: 1) Inclusive economic development, with a focus on employment and social protection; 2) Quality health and education, to fully realize human potential; 3) Environmental protection, to ensure sustainable development, and 4) Effective governance, to enhance public service delivery and the protection of rights.

Under the UN country collaboration, UNICEF chairs/co-chairs two working groups, i.e., the UNSDCF Result Group on Social Protection and the UN Youth Task Team. To this end, in 2018, the CO has been identified as a fast track CO for implementation of the UN strategy on youth.

Implementation Strategies

A range of implementation strategies are utilized to achieve outputs and outcomes defined for the CP. These include: 1) evidence generation, policy dialogue and advocacy: 2) cross-sectoral linkages; 3) partnerships; 4) south-south and triangular corporation: 5) identification and promotion of Innovation; 6) service delivery; and 7) capacity development.

Recent CP Changes

To ensure that the CP reflects recent political and social changes and as a result of the aforementioned SMR, UNICEF introduced amendments into the CPAP. With the amendments, an enhanced programmatic focus was introduced in relation to the following areas of intervention:

Objectives and Scope of the Evaluation

Objectives

The CPE has three objectives, which are to:

- Provide an independent performance assessment of the CP 2016-20 seen in relation to expected results and UNICEF’s contributions to realization of child rights in Uzbekistan for which inequity and gender are considered to form part;

- Assess UNICEF’s strategic positioning and programmatic choices made given government priorities and the changing socio-economic and political context in Uzbekistan; and

- Identify good practices and draw lessons and forward-looking recommendations from the assessment of 1) and 2) above that can inform the development of the next CP.

a) adolescents and youth;

b) social protection;

c) child care services;

d) early child development;

e) early childhood education (ECE); and

f) expansion of access to data through CR

Lessons and recommendations should include but not be limited to reflect upon: a) UNICEF’s role and strategic position looking back and thinking ahead into the CP 2021-25; b) the appropriateness of type and combined use of implementation strategies; c) what UNICEF could do better and differently to enhance its contribution in Uzbekistan; d) how UNICEF has strategically steered implementation of its CP in a constrained governance contexts; and e) how UNICEF should mainstream gender in the 2021-25 CP.

While the CPE objectives span both accountability and learning, the emphasis will be on learning.

Scope

The evaluation will cover the period 2015 to date to document and account for programme activities implemented after the CPE that covered the period 2010-14. As per the corporate guidance for CPEs, the evaluation will assess the totality of the CP portfolio including cross-cutting issues and inter-sectoral support involving C4D, social policy, gender and communication. The assessment will be provided against the situation of children in Uzbekistan at large and it will not provide a detailed assessment of any one CP component.

The organizational scope of the evaluation goes beyond the CO and includes provision of technical support and oversight from UNICEF’s regional office in Geneva and, when relevant, UNICEF’s headquarters in New York.

The CP was developed during the previous strategic plan period (2014-17), but the implementation period stretches into the new strategic plan covering the period 2018-21. This implies that the CP design, and the composition and planning of implementation strategies until the SMR in 2018 will be assessed against the previous strategic plan, whereas CP adjustments made thereafter may also refer to the current strategic plan. The same applies to other corporate guidance aligned with the SP cycles such as the GAPs. The 2014-17 GAP informed mainstreaming of gender into the CP design, and from 2018 the next GAP that is defined by gender mainstreaming and gender targeted programmes, among other, provides a basis for assessment of amendments to the CP after 2018.

The CPE covers the entire portfolio including cross-cutting issues, C4D and Communication and implementation of the same in the geographical areas in Uzbekistan where UNICEF works.

Evaluation Questions

The questions that will guide this evaluation are aligned with the evaluation criteria developed by the OECD Development Assistance Committee (DAC). To this end, the criteria in use reflect the new draft DAC guidelines in which the criteria “Synergies” is introduced, and the former criteria of “Impact” has been replaced by “Longer-term Changes”. Additional criteria in use refer to: relevance, effectiveness, efficiency and sustainability as outlined below:

Relevance

- To what extent has UNICEF ensured that the needs of vulnerable boys and girls have been considered in the planning and implementation of UNICEF-supported interventions defined to advance child rights?

- To what an extent has UNICEF managed to advance child rights focusing on the most vulnerable boys, girls and youth at risk of being left behind whilst simultaneously making a contribution at scale?

- Were the implementation strategies utilized relevant for the context, and the way it has evolved?

- To what extent have the strategic recommendations of the previous CPE been addressed regarding the particular operating conditions in Uzbekistan, i.e., the need to: a) adopt a politically-astute and pro-active approach with a greater emphasis on targeting entry points for dialogue and cultivating strategically important relationships; b) build  a common ground with the Government in areas where lack of a shared understanding or collective intent prevails; and c) develop a CP with a strong focus that reflects clarity on the political and governance context in Uzbekistan and the short-, medium- and longer-term results of investments made.

- To what an extent do the recommendations made by the previous CPE remain relevant?

Effectiveness

- To what extent were programme results achieved?

- Were there any unintended negative or positive outcomes and, if so, were they appropriately managed?

- To what extent has gender been effectively mainstreamed in the CP design and implementation and, if not, how should it be done?

- To what an extent has the CO effectively deployed C4D across the CP?

- To what an extent do the individual CP components reinforce each other to leverage the contribution that UNICEF makes towards expected results?

- Have opportunities to enhance programme effectiveness and mitigate risks been appropriately managed?

Efficiency

- To what extent are the resources (financial and human resources) allocated by the CO appropriate to support the implementation of strategies and achievement of CP results and, if not, what could be done to ensure resources match programmatic ambitions and needs?

- To what an extent has the CO demonstrated capacity to take appropriate actions when funding opportunities arose?

Sustainability

- To what extent are the results of the CP at district, regional and national levels sustainable?

- In the shorter and longer-term, what opportunities can be identified to enhance sustainability of the programme and diminish risks?

Synergies

- To what extent has the CP been designed and implemented in line with the SDGs and targets?

- To what extent is UNICEF coordinating with development partners and other UN agencies to avoid overlaps, leverage contributions and catalyse joint work?

Long-term Change

- To what extent can UNICEF be considered to have made a contribution to observed progress in the realisation of children’s rights?

Methodology

The evaluation will be guided by the “Norms and Standards” and the “Ethical Guidelines for Evaluation” developed by the United Nations Evaluation Group (UNEG) and UNICEF’s corporate guidance for equity focused evaluations. It will be planned and implemented with a non-experimental design, using mixed-methods and drawing upon secondary data when possible, generating primary data, only, when credible secondary data is not available. The team will mostly be expected to generate primary data through Key Informant Interviews, however, UNICEF welcomes use of alternative data generating approaches that add further value, e.g., administration of surveys.

During the field mission phase, primary data generation will involve visits to three regions including Tashkent where interviews will be conducted at both district and regional levels. Given the strategic focus of the evaluation and the up-stream nature of the CP interventions, interviews with children are generally not foreseen, unless, the evaluation team considers it necessary. Regions to be visited will be selected during the inception phase among the regions in which UNICEF works. The evaluation team is expected to clarify sampling criteria and strategies related to all primary data generation. In selection of regions to visit, sampling criteria will, but may not be limited to, consider the following contextual and operational factors: a) The scale and type of CP activities and applied implementation strategies in each region; b) the concentration and the socio-economic conditions of vulnerable children and families who will, ultimately, benefit from UNICEF’s support; and c) the extent to which UNICEF has achieved expected results in the area.

Assessment Frameworks and TOCs

The team will clarify strategies for conducting analyses and disaggregation of data with a view to assess UNICEF’s contribution to diverse beneficiary groups. The team will, furthermore, review the TOCs for the individual programme components with a view to verify evaluability, device strategies for how to manage possible data limitations, and as an input to development of evaluation questions. The team will be expected to explain its approach to triangulation and quality assurance of all evaluation deliverables and to clarify, how it plans to engage key evaluation stakeholders to promote participation, ownership and utilization of the evaluation. Finally, the team will draw upon Appreciative Inquiry to generate lessons and recommendations. The proposed evaluation methodology should reflect a human rights-based and equity-focused approach with data being disaggregated by sex, ethnicity, age, disability, etc., and it should pay diligent attention to ethical issues.

Evaluability

Evaluations and Studies Informing the CPE

A number of evaluations have been undertaken that affect the evaluability of the CP. Of particular importance are the following.

- A formative Evaluation of UNICEF’s Child Rights Monitoring (CRM) Programme that was completed during the last quarter of 2018, and that covered the period 2016-18. Aligned with the DAC OECD evaluation criteria, the evaluation set out to assess the programme’s contribution to building national capacity for monitoring and reporting on child rights issues assessing relevance, efficiency, effectiveness, sustainability and, to the extent possible, impact of the programme results. The CPE will be expected to draw upon the findings of this formative evaluation and structure data collection for the CPE so as to complement primary data already collected and avoid duplication of effort.

- A summative evaluation of UNICEF’s programme for Improvement of Mother and Child Health Services (IMCHS)-Phase 2 that was completed in 2016, and that covered the period 2010-15 looking at relevance, effectiveness, efficiency and sustainability, coherence and impact. The evaluation of the IMCHS-Phase 2 programme extends into the evaluation period, and it is a requirement, therefore, that the CPE evaluation team draws upon the findings of this summative evaluation and collects only complementary data for the CP component, if required.

- An evaluation of the CP 2010-14 that was completed in December 2014. The CPE focused on assessing the relevance, efficiency, effectiveness, sustainability, coherence and, to the extent possible, impact of the strategies adopted to achieve the results of the former CP. The 2015 CPE documented implementation right until the timeframe for this CPE begins, and it will serve, therefore, as a starting point against which progress may be assessed and play a central role in answering to evaluation questions number four and five that explores the extent to which recommendations made by the previous CPE were addressed and remain relevant.

A number of relevant studies will be completed during 2019 that will inform, particularly, the contextual analysis to be undertaken during the Inception Phase but also the ongoing analysis of the evaluation team. These studies that are listed below complement other relevant documentation. A bibliography will be provided for the inception phase.

- A Nutrition Survey. In 2017, UNICEF in collaboration with the Ministry of Health commissioned a nutrition survey for which data was collected in 2017.

- A Country Situation Analyses. The UCO produced situation analyses in 2014 and 2016, and an up-dated version is expected in draft by mid-year and the final report by September 2019.

- A Situation Analysis of people and CWD that is expected to be finalized during the first half of 2019.

- Health strengthening and home-visiting baseline data. Under the health component, baseline data was collected in 2016 for district level health strengthening interventions and home visiting. While baseline data will be made available to the evaluation team, end-line data will be collected in 2020 after completions of the CPE.

- National Learning Achievement Study. This study that is based on a nation-wide sample of grade IV students aims to profile the socio-economic and school characteristics of children with different learning levels. The final report will be available by July 2019.

- Social Protection System Assessment. Assessment of effectiveness of social protection system particularly regarding children and young people. The report is based on national representative survey “Listening to Citizens of Uzbekistan” conducted jointly with the World Bank and the National Development Centre.

- Youth of Uzbekistan: Aspirations, Needs and Risks. The emphasis of the study is on aspirations, needs and risks of young people aged 14-30 years in diverse spheres of their lives, including education, employment and civic participation. The draft and final reports are expected by, respectively, September 2019 and the end 2019.

- Assessment of potential effects of the health care reform on the quality and access to immunization. The study that is primarily qualitative is expected to commence in June 2019 and be reported in September 2019.

Theories of Change

A TOC for the entire CP has not been developed, but different generations of TOCs have been drafted for the diverse CP components. In all TOCs, the 2016 outcome statements have remained the same during the CP implementation period, but outputs and output indicators have been altered as follows.

- Education: A TOC was drafted for the education component in 2016 that was redrafted in 2017 where both outputs and output indicators were changed. In preparation of the CPD planning process, an up-dated TOC is expected by August 2019.

- Child Protection: In relation to child protection (CP), a TOC was drafted in 2015 that was moderated in April 2017 where both outputs and output indicators were changed. In the spring of 2019 and in preparation for the forthcoming CPD planning process, another version of the TOC with an accompanying strategy for CP has been drafted. In the 2019 version, new output indicators have been added relating to Justice for Children.

- Health: For the health component, TOCs were drafted in 2015 and 2017, however, outputs and indicators remained unchanged. As with education, an up-dated TOC is expected to be ready by August.

- Cross-cutting and sectoral: In 2015, the CO developed TOCs for, respectively, C4D, Communication, Disaster Risk Reduction (DRR) and Child Rights Monitoring and Evaluation (CRM&E). While after the 2018 SMR exercise DRR was integrated under the TOC for education, cross-cutting functions, i.e., C4D, communication and CRM&E have maintained separate TOCs. In addition, when social policy became an independent unit in 2018, a separate TOC was developed. Finally, outputs and indicators related to cross-cutting and intersectoral issues remain streamlined into the TOCs of each sector.

Following the SMR held during the second half of 2018, the CO created a revised results framework for the CPAP that was signed with the Government. In the new results framework, outputs and output indicators were once again changed for education and protection, and output indicators were added to the health component. The new results framework is attached to these TORs together with the recent TOCs in Annex C. While changes made to the TOCs during the course of implementation may add complexity to the assessment of progress made towards achievement of expected results, the evolving TOCs will help document both the performance story and the responsiveness of the CO to changes in the operational environment.

Data Availability and Reliability

While the CO has been able to report annually on output indicators in UNICEF’s Results Assessment Module (the RAM), challenges in accessing data for selected outputs and outcomes prevail in relation to Child Protection, most notably, before 2017. The evaluation team will also find that outcome level disaggregation of data, at times, is limited, and baseline date unavailable, which will influence assessment of changes.

Other Limitations

Lack of systematic documentation of the design and implementation of some programme interventions may limit the evaluation. In addition, due to ongoing structural reforms in the government, a high staff turn-over has been observed in recent years, which does influence availability of institutional memory. In addition, not all key informants might be available or reachable at the time of evaluation. During the inception phase, the evaluation team is expected to suggest how it will manage these limitations.

Evaluation Process

Once the evaluation team is on board, the evaluation will be structured in three main phases defined by accompanying activities as described below:

The Inception Phase

- A Desk Review

The evaluation team will commence the evaluation with a document review for which an electronic library will be established comprising relevant documentation that will be updated on an ongoing basis during the evaluation process. Documentation made available to the team may include but will not be limited to: CP financial information; programme monitoring data covering the timeframe for the evaluation; work plans; available TOCs for CP components; management plans and strategy notes; situation analyses; Multiple Indicator Cluster Surveys (MICS) and other relevant surveys; donor reports; ToRs for ongoing evaluations that will inform the CPE; needs assessments; corporate key policies, strategies and normative guidance that has informed the development of the CP; reports and studies relevant for the operational context; and Government and partner key policy and strategy documents.

- Initial Briefings

In addition to the desk review, brief introductory interviews with staff from UNICEF’s Regional Office in Geneva and the CO will inform the prioritization of evaluation questions and the detailed planning of the evaluation methodology.

- An inception mission (IM). Once the initial desk review is completed, an inception mission to the CO will be organised for the Team Leader. One important purpose of the IM is to introduce the evaluation and the team to CO staff and key evaluation stakeholders, including members of an Evaluation Reference Group (ERG) established as a sounding board for the evaluation to foster transparency and participation and to review key evaluation deliverables. In addition to discussing with CO staff the practicalities of the evaluation field mission, other important purposes of the IM refer to verification of: a) the TOCs; b) evaluability vis-à-vis the planned evaluation focus and programme of work; c) the team’s understanding of the chronology of external and internal events – also referred to as the established events timeline; and d) the stakeholder analysis conducted during the desk review.

- An Inception Report (IR)

An inception report will be submitted that demonstrates impartiality, and that aligns with UNICEF’s quality standards. The IR will be subject to quality assurance performed by the evaluation manager, a review conducted by internal evaluation stakeholders and the ERG, an ethical review – should proposed data gathering involve vulnerable groups, sensitive subjects and/or use of confidential data – and, finally, an external quality assurance check that requires a satisfactory rating for the field mission to proceed. The approval of the IR marks the completion of the Inception Phase.

- Based on the desk review, the IR will: a) provide a contextual description and summary of initial findings; justifications of proposed changes to the evaluation ToRs; an outline of the detailed methodology (including sampling strategies for all primary data collection); theoretical frameworks against which the CP will be assessed; a description of the quality assurance mechanism of the evaluation team. The IR will also outline evaluation team strategies for management of data gaps, or data reliability issues, and it will include ethical considerations relating to primary data generation. Attached to the IR will be an evaluation matrix outlining evaluation questions, sub-questions, judgement criteria/indicators, data sources and instruments/methods; a stakeholder analysis; a timeline; the CP TOC; a work plan; and an overview of the division of labour between the evaluation team members.

The Field Mission Phase

Following the inception phase, a three-week field mission with full participation of all team members will be organised during which primary and, if relevant, secondary data will be generated. At the end of the field mission, the evaluation Team Leader will present preliminary observations and finding to CO staff, the ERG (ERG) and, if required, other stakeholders.

The Reporting Phase

- The evaluation team will prepare a draft evaluation report that will be subject to a review undertaken by CO staff, members of the ERG and the evaluation manager; an external quality assurance that requires a satisfactory rating and, if required, an ethical review. Following the first review of the draft report and the initial quality assurance, the evaluation team will incorporate the comments provided and prepare a final report. If the first draft report does not pass UNICEF’s external quality assurance with a satisfactory rating, a second draft report will be submitted for quality assurance. As with the IR, it is a requirement for evaluation reports to have a satisfactory rating before they can be considered final.

- Once a final draft report has been approved, the evaluation Team Leader will travel to the CO to discuss the evaluation findings and recommendations with CO staff, the ERG and, if relevant, other national stakeholders. The Team Leader will, furthermore, present the evaluation findings to relevant stakeholders from UNICEF’s RO in Geneva and, if required, selected headquarter staff. The report will comply with UNICEF’s reporting standards and be no longer than 40-60 pages excluding annexes. Upon completions of the evaluation report, it will be rated in UNICEF’s Global Evaluation and Research Oversight System (GEROS), and it will be published on UNICEF’s global website.

Organization of the Evaluation

Timeline, Work Plan and Deliverables

| The evaluation will be managed by UNICEF’s Regional Office for Europe and Central Asia in close collaboration with the CO in Uzbekistan. A workplan and timeline is provided in Table 2 below.Activity | Sep | Oct | Nov | Dec | Jan | Feb | March |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Inception and Desk review | X |  |  |  |  |  |  |
| Inception mission | X |  |  |  |  |  |  |
| Inception report | X |  |  |  |  |  |  |
| Report reviewed by evaluation stakeholders, ethical review and quality assurance conducted. |  | X |  |  |  |  |  |
| Finalization and approval of Inception Report |  | X |  |  |  |  |  |
| Field Mission |  | X | X |  |  |  |  |
| Field mission and presentation of preliminary observations and findings |  | X | X |  |  |  |  |
| First draft report |  |  |  | X |  |  |  |
| Report reviewed by evaluation stakeholders, ethical review and quality assurance conducted |  |  |  |  | X |  |  |
| Final Report |  |  |  |  | X | X |  |
| Final presentations |  |  |  |  |  | X |  |

The evaluation main deliverables are outlined in Table 3 below.

| Table 3. Evaluation main deliverables and deadlines |  |  |  |  |
| --- | --- | --- | --- | --- |
| Evaluation Deliverables | Completion Dates |  |  | # of days Team Leader | # of days per Team Members |
| Inception Mission with presentation | 2 weeks before submission of the IR |  |  | 5 |  |
| Inception Report (20 pages excluding annexes towards which team members will contribute with, at least, 5 pages). | 2 weeks after the inception mission begins |  |  | 10 | 8 |
| Field mission and presentation to CO staff, the ERG and other stakeholders as requested | 4-6 weeks after the beginning of the Inception Phase. |  |  | 19 | 19 |
| Draft Report (40-60 pages excluding executive summary and annexes towards which each team member will contribute with, at least, 10 pages) | 5 weeks after completion of the main mission. |  |  | 15 | 10 |
| Final Report (as above) | 3 weeks after internal review and external quality assurance on draft report have been completed. |  |  | 4 | 3 |
| A country office visit to present the evaluation to CO staff, the ERG and other stakeholders as requested A PowerPoint Presentation of the evaluation, its main findings, recommendations and conclusions. A skype presentation to RO staff | 1-2 week after approval of final report. |  |  | 2 |  |
| Total |  |  |  | 55 | 40 |

Team Composition and Requirements

General Competency Requirements

The evaluation team will be gender balanced and consist of one team leader and two team members. All three team members will be professionals with a relevant higher academic/post-graduate degree and, as a team, they should have expertise in the sectors relevant to the CP in Uzbekistan specified below. All team members should have knowledge of UNICEF’s mandate and experience of working closely with Government partners and/or UN agencies. Relevant experience from Uzbekistan and/or neighbouring countries is considered an asset for the international team members. It is considered an advantage, if one or more team members have knowledge of, or professional experience in working with Appreciative Inquiry.

- At least, two team members should have experience of working in a MIC.

- At least, two of three evaluation team members should have an in-depth understanding of the implementation strategies used by UNICEF, especially capacity development, policy dialogue and advocacy.

- At least, one team member should be a national policy expert familiar with of the socio-economic, political and institutional environment in the country.

The Team Leader

The Team Leader must have documented professional experience in conducting rigorous independent evaluations that meet professional evaluation standards - and more than 12 years of professional experience. The Team Leader should, furthermore, have a strong development background with a profound understanding of development and Human Rights-Based programmes. It is also a requirement that the Team Leader has expertise in strategic planning, and evaluation experience from the Europe and Central Asian Region or a MIC is considered an advantage. In addition, he/she must have expertise relating to one or more of the sectors in which UNICEF works (outlined below under team members).  As the leader of the evaluation, the candidate will demonstrate previous experience in managing a multi-disciplinary team and delivering quality evaluation outputs.

The Team Members

Each of the two team members should have relevant higher academic/post-graduate degrees and a minimum of five to seven years of relevant professional experience including in research or/and evaluation, and sector expertise in two, ideally more, of the following five sectors:

1) education;

2) mother and child health;

3) social policy;

4) child protection; and

5) gender.

The ideal evaluation team will cover the sectors listed above.

Roles and Responsibilities

As per UNICEF’s evaluation policy, the evaluation will be managed by an evaluation expert from UNICEF’s RO in Geneva who will collaborate closely with the CO evaluation expert to ensure evaluation utility and relevance, among other. The Team Leader will be overall responsible for the quality and submission of all main evaluation deliverables towards which all team members will contribute as explained below.

Role and Responsibility – Team Leader

The Team Leader has the overall responsibility for the CPE. Specific tasks of the Team Leader will include but may not be limited to:

- Guide the extensive desk review of existing information on the context including national policies and priorities and UNICEF’s work and all relevant programme and project documents and reports, previous studies, research and evaluations;

- Develop and provide detailed methodological guidance for the team with regards to the tool development and define the overall direction for data analysis and quality assurance;

- Provide guidance in preparation of evaluation deliverables;

- Review all relevant documentation related to the CPE;

- Undertake an IM to verify the CP TOC, an events timeline, the stakeholder analysis developed during the desk review, present the evaluation to the CO, ERG and, if relevant, other stakeholders and organize the practicalities related to the planning of the field work.

- Lead the field mission and decide upon the division of roles and responsibilities among team members during the entire evaluation process;

- Coordinate the work of the evaluation team and consolidate inputs from team members to ensure
timely delivery of evaluation products;

- Conduct interviews with a range of key stakeholders and informants as per the inception report;

- Lead the planning and conduct of analyses and discussions of evaluation questions and issues common to the whole team;

- Lead the consolidation of the teams’ inputs for the inception and field mission;

- Undertake the IM and present the evaluation to CO staff, the ERG and, in relevant, other stakeholders, and verify main deliverables associated with the inception mission;

- Submit the IR, the draft and final CPE reports, and develop and deliver a power point presentation on the main findings and recommendations emerging from the evaluation once the evaluation report has been finally approved;

- Manage the evaluation work plan, respecting deadlines for specific activities and deliverables;

- Maintain a high level of communication with the team members and UNICEF staff involved in management of the evaluation.

Common tasks and duties for all team members

All team members are requested to refer attentively to the documentation made available in the electronic library developed for the evaluation, including the ToRs, context information and information on UNICEF’s interventions.

- All team members are requested to familiarize themselves with UNICEF’s global normative products in the substantive areas for which they are responsible. These are available on the UNICEF website www.unicef.org.

- All team members will contribute to concise written reports as per their specific area of expertise and the division of labor outlined in the IR: a) at the end of the desk review phase and prior to the start of the field mission they will contribute with, at least, 5 pages; and b) for the draft evaluation report, they will contribute with, at least, 10 pages. Team members will also contribute to the revision of the final draft report and provide inputs to team discussion during all evaluation phases. Evaluation team members will participate actively in all phases of the evaluation engaging in analyses and discussions of findings.

- Complementary to the evaluation ToRs, the evaluation Team Leader will prepare a number of orienting documents and tools (including an evaluation matrix) in discussion with the evaluation team. These documents should be read by all team members and will be used as a framework for guiding the questions to be asked and data to be gathered during the evaluation.

- All team members will be requested to participate during the entire field mission during which primary data will be generated.

The ERG

The ERG does not have any formal evaluation management responsibilities. It will act in an advisory capacity and provide inputs on all main evaluation deliverables that are expected to strengthen the quality and credibility of the evaluation. The reference group members will be expected to:

- Be a sounding board for feedback during the evaluation;

- Provide feedback on the evaluation approach presented by the Evaluation Team Leader when the IM is organized;

- Enable access to key informants during the evaluation process;

- Participate in interviews with evaluators as relevant;

- Review and comment on the IR;

- Participate in the presentation of evaluation preliminary findings;

- Review and discuss the final report, in particular, findings and recommendation that concern possible strategic shifts UNICEF should make in a CP.

## Annex 2: Evaluation Matrix

| Evaluation Questions | Evaluation sub-questions | Indicators | Data Collection Tools and Sources | Stakeholders to be consulted |
| --- | --- | --- | --- | --- |
| Relevance |  |  |  |  |
| - To what extent has UNICEF ensured that the needs of vulnerable boys and girls have been considered in the planning and implementation of UNICEF-supported interventions defined to advance child rights? | - How and why were decisions made on priority areas to address within the programme? - To what degree does the programme address the needs and priorities of children in Uzebkistan? - Were gender dimensions and social exclusion issues clearly articulated? Did they evolve to fit the changing country content? - What are the key implementation strategies (interventions/ activities) used in this programme? How were decisions made to use these strategies? Are these the right strategies for achieving the goals of the programme? - How do they fit with Uzbekistan’s National Development plans? - If piloting or modelling has been used, what is the potential for scale-up? - To what extent is the programme reaching the most vulnerable groups? Strategies explicitly reference an analytical basis (i.e. an inclusive strategy) and resources to focus on the most vulnerable. Which, if any, groups are being left out? | Rating scales for alignment/consideration: 0= Not aligned/ considered (or even recognition of need). 1= minimal alignment/consideration. Not aligned/effective in key areas. 2= Reasonable alignment/ consideration . Evidence of alignment/effectiveness across a number of key areas 3= Full alignment/ consideration. Fully aligned / evidence of effectiveness across all areas. Evidence that programmes (e.g.health, education, etc) have been informed by a gender analysis and vulnerabilities assessments. Here and for all evaluation questions, the team will refer to indicators defined in the original country programme plan and the revised results framework. Some indicators have a wide remit, while others relate to specific vulnerable groups (eg persons living with HIV) | Desk research (e.g. situation analysis, existing evaluations/ rapid appraisals, Uzbekistan’s National Development Plans) Key informant interviews and survey Group interviews | UNICEF CO/RO staff UN agency staff Government line ministries Public agencies and NGOs |

| - To what extent has UNICEF managed to advance child rights focusing on the most vulnerable boys, girls and youth at risk of being left behind whilst simultaneously making a contribution at scale? | - To what extent has the programme been designed to support the achievement of child rights? - To what extent has the programme been deisgned to support enhanced monitoring and reporting of child rights? - Are gender priorities and needs explicitly addressed? - To what extent has UINICEF successfully used advocacy to influence government policy, planning and for resource allocation. - To what degree has the programme responded to the recommendations of the Committee on the Rights of the Child? - To what extend are strategies effectively addressing gender equality and girls/women’s empowerment? - To what degree is the programme promoting child and youth participation? - In what ways has the programme addressed issues of diversity and equity? - What limitations, gender sensitivities and constraints have surrounded the collection of relevant data and its use? How has UNICEF tried to overcome these constraints with its partners? | Rating scale for contribution/attribution: 0= No evidence of contribution 1= Very limited evidence of attribution contribution 2= Some evidence of attribution and good evidence of contribution 3= strong evidence of attribution (key contributor) | Desk research (e.g. situation analysis, existing evaluations/ rapid appraisals, CRC reports) Key informant interviews and survey Group interviews | - UNICEF CO/RO staff - Government line ministries Public agencies and NGOs |
| --- | --- | --- | --- | --- |

| - Were the implementation strategies utilized relevant for the context and the way it has evolved? | - Has the programme been evaluated or research/ studies carried out in relation to the programme? Have these findings led to changes within the programme? How? - How have the programme objectives and interventions changed since the start of the programme? Why have these changes been made? - How have these changes (e.g on health systems strengthening approach) affected the achievement of results? - To what extent is the programme operating at the national vs regional/ district levels? How and why have these decisions been made? How were decisions reached on which regions the programme should operate in? - Who are the key programme partners? How were decisions made on who to partner with? - What has been the degree of government Vs. CSO engagement, and why? | Rating scale on relevance: 0=No evidence of relevance 1= Limited evidence of relevance 2= Good evidence but impacted by change in context etc) 3=Strong evidence of relevance and achievability within CP timeframe | Desk research (e.g. existing evaluations, CPAP, ToCs, documents relating to the SMR, workplans and partnership agreements) Key informant interviews and survey Group interviews | - UNICEF CO/ RO staff - Government line ministries Public agencies and NGOs |
| --- | --- | --- | --- | --- |

| - To what extent have the strategic recommendations of the previous CPE been addressed regarding the particular operating conditions in Uzbekistan? | - Has the programme been shaped by the previous CPE? - In what ways? e.g. on design, decisions and changes on the health programmes as a results of previous CPE? | Rating scale on relevance/ application: 0=No evidence of application/ not relevant 1= Limited evidence of application/ some relevance 2= Good evidence application and relevance 3=Strong evidence of relevance and contribution to taking CP forwards (application/development of new thinking, concepts etc. | Desk research (e.g. previous CPE and management response, CPAP, TOCs and workplans) Key informant interviews and survey Group interviews | UNICEF CO staff |
| --- | --- | --- | --- | --- |

| - To what extent do the recommendations made by the previous CPE remain relevant? | - Are the recommendations of the previous CPE still relevant? - adopt a politically astute and pro-active approach with a greater emphasis on targeting key entry points for dialogue and cultivating strategically important relationships; - build a common ground with the Government on areas where a lack of shared understanding or collective intent prevails; - develop a CP with a strong focus that reflects clarity on the political and governance context in Uzbekistan and the short=, medium- and longer-term results of investments made. | As above | Desk research (e.g. documents relating to / following the SMR: revised TOCs, workplans and results frameworks) Key informant interviews and survey Group interviews | UNICEF CO staff Government line ministries Public agencies and NGOs |
| --- | --- | --- | --- | --- |

| Effectiveness |  |  |  |  |
| --- | --- | --- | --- | --- |
| - To what extent were programme results achieved? | - What have been the key achievements of the programme? (both impact/ outcome/ output level achievements) - To what extend has the programme strategies enhanced key achievements/results? - Has the programme achieved all it intended to? - What were the programmes contributions to gender equality and women’s empowerment? - What have been the key factors that have enhanced these achievements? - How timely has the delivery of UNICEF’s programme been? - Have the regional office team supported the effectiveness of the programme? How? How could support from the regional office be enhanced? | To be assessed against outcomes/ outputs indicators outlined in the revised results framework. Rating scale on achievement: 0 = Output/ outcome not achieved 1= Output/ outcome partially achieved 2= Output/ outcome mainly achieved 3= Outcome/ output fully achieved A rating scale may also be employed to measure UNICEF’s contribution to results. | Desk research (e.g. annual reports, evaluation and donor reports, RAM reports, MICS) Key informant interviews and survey Group interviews Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries Public agencies and NGOs UN agency staff Frontline workers Youth (via FGDs) |

| - Were there any unintended negative or positive outcomes and, if so, were they appropriately managed? | - What have been the key factors that have prevented the programme from reaching its goals? - Have there been any negative or positive or unintended results from the programme? - How have these been addressed/ responded to? | - Where appropriate, a rating scale on unintended negative and positive outcomes may also be used. | Desk research (e.g. annual reports, evaluation and donor reports, RAM reports) Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries Public agencies and NGOs UN agency staff Frontline workers Youth (via FGDs) |
| --- | --- | --- | --- | --- |

| - To what extent has gender been effectively mainstreamed in the CP design and implementation and, if not, how should it be done? | - How has gender been integrated/mainstreamed within the programme design and implementation? - Evidence/impact of gender mainstreaming priorities increased gender results. What have been the main challenges? | Rating scale on gender mainstreaming: 0=Gender not mainstreamed into programme design and implementation 1 = Gender partially mainstreamed into programme design and implementation 2= Gender mainly mainstreamed into programme design and implementation 3 = Gender fully mainstreamed into programme design and implementation M&E frameworks and processes on disaggregated data and measuring results are gender responsive (e.g on health for men and women)? Disaggregated data from relevant outcome/ output level indicators from the CPAP revised results framework. For example: - % of girls/ boys aged 2-59 months receiving medical care by general practitioners according to approved protocols/ standards; - Preschool enrolment of boys/ girls Annual rate of placement into residential care disaggregated by gender | Desk research (e.g. GAPS, annual reports, evaluation and donor reports, CPAP, workplans, TOCs) Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries Public agencies and NGOs UN agency staff Frontline workers Youth (via FGDs) |
| --- | --- | --- | --- | --- |

| - To what extent has the CO effectively deployed C4D across the CP? | - How do social norms affect the achievement of programme goals across all programme areas? - To what extent have efforts been made to address these social norms through the C4D component of the programme? - Are C4D interventions contributing to changing social norms (e.g. around immunisation and stigma on HIV/AIDs)? | Rating scale on use of C4D: 0= C4D has not been used to effectively address social norms that affect the achievement of programme goals 1 = C4D has partially been used to effectively address social norms that affect the achievement of programme goals 2 = C4D has mainly been used to effectively address social norms that affect the achievement of programme goals 3 = C4D has fully been used to effectively address social norms that affect the achievement of programme goals | Desk research (e.g. C4D ToC/ workplans, annual reports, evaluation and donor reports) Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries Public agencies and NGOs UN agency staff |
| --- | --- | --- | --- | --- |

| - To what extent do the individual CP components reinforce each other to leverage the contribution that UNICEF makes towards expected results? | - What efforts have been made to ensure inter-sector collaboration within the UNICEF CP? - What efforts have been made to promote greater inter-sectoral collaboration within government? - To what extent have cross sectoral strategies enabled and enhanced efficiency (e.g. in health) towards achievements of results. - To what extent have cross sectoral collaboration (e.g.between education and health) enhanced efficiency in achieving results. - How do the cross-cutting components of the programme (such as gender, child rights monitoring and social policy) contribute towards the achievement of programme goals? | Use of matrix to show levels of contribution from other programmes. Levels from 0 – 5: 0= no support/link 1= minimal at level of sporadic activity or involvement 2= some linkage primarily focused on one or 2 specific areas not significant or sustained 3= Reasonable level of engagement. Some indications of significance and sustainability 4= Strong linkages with strong significance. Emerging evidence of transformation and synergy 5= linkages are transformational and dynamic Use levels of contribution matrix to show levels of support and effectiveness of Regional Team | Desk research (e.g. CPAP, TOCs, workplans, annual reports, evaluation and donor reports) Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries |
| --- | --- | --- | --- | --- |

| - Have opportunities to enhance program effectiveness and mitigate risks been appropriately managed? | - What are the risks to the programme? - How has risk been addressed? | Rating scale on risk: 0= no efforts have been made to address risk 1= minimal efforts have been made to address risk 2 = extensive efforts have been made to address risk 3 = maximum efforts have been made to address risk | Desk research (e.g. ToCs, Workplans) Key informant interviews and survey Group interviews | UNICEF CO |
| --- | --- | --- | --- | --- |

| Efficiency |  |  |  |  |
| --- | --- | --- | --- | --- |
| - To what extent are the resources (financial and human resources) allocated by the CP appropriate to support the implementation of strategies and achievement of CP results and, if not, what could be done to ensure resources match programmatic ambitions and needs? | - Have sufficient resources been allocated to implement each element of the programme effectively,? (considering financial (including gender budgeting) and human resources/ capacities). - If not, why not? - What more could be done to enhance resource allocations? | Assess against timeliness of fully translating inputs to outputs and outcomes – logframe milestones. | Desk research (e.g. workplans, budgets, evaluations and donor reports) Key informant interviews and survey Group interviews | UNICEF CO Government line ministries Public agencies and NGOs |

| - To what extent has the CO demonstrated capacity to take appropriate actions when funding opportunities arose? | - How has the programme responded to changing funding opportunities? e.g. on matching resource mobilisation strategy and capacity to programming ambitions. | Funding matrix to show current and new funding/ overlay against efficiency of translating inputs to outputs to outcomes | Desk research (e.g. grant applications) Key informant interviews and survey Group interviews | UNICEF CO Donors |
| --- | --- | --- | --- | --- |

| Sustainability |  |  |  |  |
| --- | --- | --- | --- | --- |
| - To what extent are the results of the CP at district, regional and national levels sustainable? | - Which factors impact on the sustainability of the programme? - How have these factors been addressed through the programme? | Sustainability matrix based on enabling environment – policy funding, staffing, action involvement The extent to which UNICEF has successfully used advocacy to leverage the operating space to ensure programme sustainability e.g. immunisation (GAVI). | Desk research (e.g. evaluations, workplans, ToCs) Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries Public agencies and NGOs UN agency staff |

| - In the shorter and longer-term, what opportunities can be identified to enhance sustainability of the programme and diminish risks? | - What more could be done to address the sustainability of the programme? - To what extent have strategies on partnership, innovation, policy advocacy and partnership contributed on the sustainability of programmes? | Rating scale sustainability: 0= no efforts have been made to enhance the sustainability of the programme 1= minimal efforts have been made to enhance the sustainability of the programme 2 = extensive efforts have been made to enhance the sustainability of the programme 3 = maximum efforts have been made to enhance the sustainability of the programme Here the same rating scale on risk can be used as under Effectiveness (see above). | Desk research (e.g. evaluations, workplans, ToCs) Key informant interviews and survey Group interviews | UNICEF CO Government line ministries Public agencies and NGOs UN agency staff |
| --- | --- | --- | --- | --- |

| Synergies |  |  |  |  |
| --- | --- | --- | --- | --- |
| - To what extent has the CP been designed and implemented in line with the SDGs and targets? | - To what extent does the CP seek to contribute to the achievement of SDGs? | Ratings scale on contribution to the SDGs: 0 = UNICEF has made no contribution to the achievement of SDGs relevant to programme goals 1 = UNICEF has made minimal contribution to the achievement of SDGs relevant to programme goals 2 = UNICEF has made extensive contribution to the achievement of SDGs relevant to programme goals 3 = UNICEF has made maximum contribution to the achievement of SDGs relevant to programme goals | Desk research (e.g. SDGs, annual reports, evaluations, donor reports) Key informant interviews and survey Group interviews | UNICEF CO UN agency staff |

| - To what extent is UNICEF coordinating with development partners and other UN agencies to avoid overlaps, leverage contributions and catalyze joint work? | - How is this programme engaging with other UN agencies, including through the framework of the UNDAF? - How is the programme engaging on gender equality and on gender leadership within the UN family? - What are the lessons learned from UINICEF's donor coordination (e.g. health sector? | Ratings index on coordination efforts: 0= No effort to coordinate with development partners and UN agencies 1= Minimal effort to coordinate with development partners and UN agencies 2=Extensive effort to coordinate with development partners and UN agencies 3 = Maximum effort to coordinate with development partners and UN agencies | Desk research (e.g. evaluations, donor reports, joint workplans) Key informant interviews and survey Group interviews | UNICEF CO UN agency staff |
| --- | --- | --- | --- | --- |

| Long-term Impact |  |  |  |  |
| --- | --- | --- | --- | --- |
| - To what extent can UNICEF be considered to have made a contribution to observed progress in the realization of children’s rights? | - To what has the programme contributed to the realization of children’s rights, as articulated by the UN CRC and SDGs? - To what extent has the programme contributed to the achievement of gender equality? - To what extent has CP led to changes to social inclusion (positive or negative)? - To what extend has a human rights-based, gender-sensitivity and an equity approach been applied across all programmes areas? Has this been mainstreamed in data collection? - To what degree has the programme responded to demand for services and support from communities beneficiaries already engaged in UNICEF supported interventions? | Reference ratings scale above on contribution to the SDGs and on gender mainstreaming. Assessment of outcome indicators included in the revised CPAP results framework against CRC/ SDGs. | Desk research (e.g. SDGs, CRC, reports from the Committee on the rights of the Child, evaluations, annual report, donor report, MICS) Key informant interviews and survey Group interviews | UNICEF CO/RO Government line ministries Public agencies and NGOs UN agency staff Frontline workers Youth (via FGDs) |

## Annex 3:  Data Collection Tools

The tools shown below represent the evaluation team’s plans for data collection with different categories of respondents. The workshop with UNICEF staff will provide triangulation with the results of individual interviews, if enough staff can be made available for it. The lists of questions for individual interviews with UNICEF CO and ECARO, national partners and front-line staff  will be adjusted as per standard rules for semi-structured interviews.

### Workshop with UNICEF staff

Introduction

Allow 1.5 hours for this workshop

The workshop introduces the evaluation team to the office, and enables discussion of issues of relevance across the whole programme.  The workshop is open to all programme staff, with representatives required from each team if possible.

Understanding the operating space

Ask: Over the reporting period (since 2015) what have been the key factors that have affected programme design and effectiveness?

- Probe on:

    - Internal opportunities

    - Internal constraints

    - External opportunities

    - External constraints

For the external context – consider the political, economic and social context, the space for dialogue, the degree to which a vision is shared between UNICEF and external stakeholders, and the degree to which partners have the capacity to implement change.

- Using sticky notes record this information on a large flip chart Matrix

|  | Internal | External |
| --- | --- | --- |
| Opportunities |  |  |
| Constraints |  |  |

- Discuss findings in the matrix.  Explore how this has changed over the course of the reporting period, and what they anticipate for the future.  Ask how this has affected the programme.

Key achievements and biggest challenge

- Ask staff to anonymously write the achievement of their programme that they are most proud of on yellow sticky notes.

- Ask staff to anonymously write the greatest challenge that they face in their work on blue sticky notes.

- Organise the notes on the wall in common themes and review together.  Are they surprised?

Understanding connections within the UNICEF programme

- Ask staff to collectively complete the below matrix (which will be placed on large flip charts on the wall).

- Using sticky notes, ask staff to rank their connection to other teams as follows:

- 0= no support/link

- 1= minimal at level of sporadic activity or involvement

- 2= some linkage primarily focused on one or 2 specific areas not significant or sustained

- 3= Reasonable level of engagement. Some indications of significance and sustainability

- 4= Strong linkages with strong significance. Emerging evidence of transformation and synergy

- 5= linkages are transformational and dynamic

- Explore barriers to/ reasons for effective cross-sector working.

|  | Health | Education | Protection | Child rights monitoring | Social policy | C4D |
| --- | --- | --- | --- | --- | --- | --- |
| Health |  |  |  |  |  |  |
| Education |  |  |  |  |  |  |
| Protection |  |  |  |  |  |  |
| Child rights monitoring |  |  |  |  |  |  |
| Social policy |  |  |  |  |  |  |
| C4D |  |  |  |  |  |  |

### Interviews with UNICEF staff

Introduction

- Allow 1.5 – 2 hours for these meetings.

- Meetings can take place in small sector teams or with individual staff members.

These questions will be adjusted depending on which staff are being interviewed.  For staff such as the Representative and Deputy Representative, with an overview of the programme, the focus will be on:

- The operating space.

- The overall relevance of the programme to the context.

- Strategic decisions around overall programme priorities, design and partnership

- How the different components of the programme fit together and the integration of cross cutting issues/ programmes into the wider programme.

- Linkages with other UN agencies.

For sector leads, the focus will be on their sector/ aspect of the country programme, and its relevance, effectiveness, efficiency and sustainability, as well as on lessons learnt from this programme.  If the interviewees have participated in the workshop, some questions may be skipped.

Understanding the operating space

- Over the reporting period (since 2015) what have been the key factors that have affected programme design and effectiveness?

  - Probe on:

    - Internal opportunities

    - Internal constraints

    - External opportunities

    - External constraints

- For the external context – consider the political, economic and social context, the space for dialogue, the degree to which a vision is shared between UNICEF and external stakeholders, and the degree to which partners have the capacity to implement change.

- Explore how this has changed over the course of the programme.

Relevance

- How and why were decisions made on priority areas to address within the programme? (probe on degree of child/ youth participation/ responsiveness to the demands of service users)

- To what degree do you feel that programme addresses the needs and priorities of children in Uzebkistan?  (probe on the evidence/ information used to make this assessment)

- To what extent does the programme fit with Uzbekistan’s National Development plans?

- Has the programme responded to the recommendations of the Committee on the Rights of the Child?  How?

- To what extent do you feel the programme recognizes and addresses the differing needs of girls and boys in Uzbekistan? How have these needs changed over time and how has the programme responded to these changing needs?

- To what extent do you feel that the programme is reaching the most vulnerable groups?  Which, if any, groups are being left out?

- To what extent is the programme operating at the national vs regional/ district levels?  How and why have these

decisions been made? How were decisions reached on which regions the programme should operate in?

- What are the key implementation strategies (interventions/ activities) used in this programme?  How did you decide

to decide to use strategies?  Do you feel they are the right strategies for achieving your goals?  (probe: strategies

that were considered and rejected? other strategies could have been more effective? If piloting or modelling has

been used, probe on the potential for scale-up)

- Who are the key programme partners? How were decisions reached on who to partner with?  (probe on the degree

of government Vs CSO engagement)

- How have the programme objectives and interventions changed since the start of the programme?  Why have these

changes been made? (probe on how the programme has responded to a changing political and economic context in

Uzbekistan; on the strategic moment of reflection and the changes that were main at this point, and on comparisons

between the 2015 and 2018 theories of change)

- Has the programme been evaluated or research/ studies carried out in relation to the programme?  Have these

findings led to changes within the programme?  How?

- Has the programme been shaped by the previous CPE?  In what ways? Do you feel that the key recommendations of

the previous CPE are still relevant today?

Effectiveness/ longer-term impact

- What have been the key achievements of the programme? (probe on impact/ outcome/ output level achievements)

- Has the programme achieved all it intended to?  What have been the key factors that have enhanced these achievements?  What have been the key factors that have prevented the programme from reaching its goals?

- Have their been any negative or positive unintended results from the programme?  How have these been addressed/ responded to?

- How has gender been considered in programme design and implementation? Has the programme contributed to enhanced gender equality? How?  How about addressing other issues of inequity?

- Do social norms affect the achievement of programme goals?  How?  Is there a C4D component to this programme?  Does it adequately address these social norms?

- Which other programmes within UNICEF does this programme interact with? Why and how?  Are there other sectors/ programmes within UNICEF that this programme should be interacting with?  Why is this not happening? (probe on how this programme interacts with other cross-cutting programmes within UNICEF such as C4D, and child rights monitoring – if the programme team did not contribute to the group discussion, use the matrix listed above to get perspectives on cross sector working)

- What are the risks to the programme?  How has risk been addressed?

- Have the regional office team supported the effectiveness of the programme?  How? How could support from the regional office be enhanced?

Efficiency

- Do you feel there are sufficient resources to implement this programme effectively? (probe on financial and human resources/ capacities)?  If not, why not?

- What more could be done to enhance resource allocations?

- How has the programme responded to changing funding opportunities?

Sustainability

- Which factors do you feel impact on the sustainability of this programme?

- How have these factors been addressed through the programme? (probe on: level of government commitment and investment, degree of capacity to implement changes instigated by the programme, extent to which changes have been institutionalised)

- What more could be done to address the sustainability of the programme?

Synergies

- How is this programme engaging with other UN agencies?  (probe on general engagement and engagement specifically in relation to gender)

Lessons learnt

- What are the key lessons learnt from this programme? (prompts: What would you have done differently?  What advice would you give to others running a similar programme?)

- What challenges have you faced along the way?  What have you done to address these challenges?

### Interviews with partners

Introduction

- Allow approx. 1 hour for these meetings

- Meetings can take place in groups of 2-4 people if necessary

These questions will be adjusted depending on who is being interviewed.  In general, questions will focus on UNICEF’s contributions in a particular sector.  In some cases where a stakeholder has an overview of all of UNICEF’s work, questions will focus on UNICEF’s wider contributions across sectors.

Understanding the operating space

- What have been the major political, economic and social changes in Uzbekistan in the last 5 years?

- How have these changes affected UNICEF’s work in the country?

- Do you feel that UNICEF understands these changes?  Is it responding to them appropriately?

Relevance

- What do you feel are the main priorities for children in Uzbekistan? Does UNICEF’s work respond to these priorities?

- Which groups of children in Uzbekistan are particularly vulnerable?  Do UNICEF’s programmes meet the needs of these groups?

- To what extent do you feel the programme recognizes and addresses the differing needs of girls and boys in Uzbekistan?

- Do you know how UNICEF decides which areas it will focus on?  Do you feel that you or other stakeholders are consulted and listened to here?

- To what extent do UNICEF’s priorities match those of government/ your organisation? (probe on the extent to which the programme fits with national policy priorities and plans)

- Do you feel it is important for UNICEF to work at the national level, regional level or both?  Why?  Where should UNICEF prioritise its efforts?  Has it got the balance right at the moment?

- What do you think you about the implementation strategies (interventions/ activities) used within UNICEF’s programme?  Are they appropriate?

- What changes have you seen within UNICEF’s programme?  Do you know why these changes have been made?  What do you think about these changes?

Effectiveness/ longer term impact

- What do you think have been the key achievements of the UNICEF’s programme?

- Has the programme achieved all it intended to?  What have been the key factors that have enhanced these achievements?  What have been the key factors that have prevented the programme from reaching its goals?

- Have their been any negative or positive unintended results from UNICEF’s programme that you are aware of?  How have these been addressed/ responded to?

- How has gender been considered within UNICEF’s programme?  What about the needs of other particularly vulnerable or excluded groups?

- Does the programme work across sectors?  How?  Is this cross-sector work carried out effectively?

- What are the risks to the programme?  How has risk been addressed?

Efficiency

- Do you feel there are sufficient resources to implement this programme effectively? (probe on financial and human resources/ capacities)? If not, why not

Sustainability

- Which factors do you feel impact on the sustainability of UNICEF’s programme? (prompts – do you think this programme would carry on if UNICEF stopped funding it?  Why?  Why not?)

- How have these factors been addressed through the programme? (probe on: level of government commitment and investment, degree of capacity to implement changes instigated by the programme, extent to which changes have been institutionalised)

- What more could be done to address the sustainability of the programme?

Lessons learnt

- What are the key lessons learnt from UNICEF’s programme? (prompts: What should have been done differently?  What advice would you give to others running a similar programme?)

- What challenges have been faced within the programme?  How have they been addressed?

### Discussions with frontline workers

Introduction

- Allow 45 minutes to 1 hour for these discussions

- Frontline workers includes social workers, judges, health workers or teachers supported through UNICEF interventions

- Discussions can involve one to one interviews, small group discussions or focus groups (with 5-8 participants).

Understanding the operating space

- A lot has changed in Uzbekistan in the last five years.  Have these changes affected you and your work?  How?

Relevance

- Can you tell us about some of the vulnerable children and families that you work with?  What are the main problems that they face?  Do girls and boys face the same challenge or are they different?  How?

- Are there any groups of children who you work with who are particularly vulnerable?

- What are the main issues or challenges that you face in your work?  (focus here on the aspects of their work most relevant to UNICEF’s programme)

- To what extent do you think UNICEF’s programme is addressing these needs/ challenges?

Effectiveness/ longer term-impact

- What kinds of support have you received from UNICEF/ UNICEF partners?

- What do you think about this support?  Has it made a difference (to you?  To children/ families?) ? How?

- What did you gain from this support?

- Are there ways in which support could have been improved/ provided more effectively?  How?

- Have there been any unintended negative or positive outcomes from this support?

For groups, sticky notes and flips charts could be used to complete a simple matrix to explore some of these questions:

|  | What do you need to support vulnerable children and their families well? | What support has been provided by UNICEF/ UNICEF partners |
| --- | --- | --- |
| Skills and trainings |  |  |
| Resources |  |  |
| Other |  |  |

### Discussions with youth (single sex/ mixed group depending on availability)

Introduction

- The questions for partners can be adapted for interviews with youth who have been involved in implementing UNICEF’s work on youth participation.  Key questions are listed below.

- Allow 45 minutes to 1 hour for this discussions

- Discussions can take place individually or in groups

Relevance

- What is life like for young people In Uzbekistan?  What are the main challenges you face? Are challenges different for young women as compared to young men?  How?

- Are there any groups of young people that face particular challenges? Which groups? What challenges do they face?

- How have things changed for young people?  Are they getting better, worse or staying the same? How? Why?

- Is the work that UNICEF is supporting helping to address any of these challenges?  How?  (probe on degree to which addressing the needs of both young men/ women, and different vulnerable groups)

Effectiveness

- Has the work that UNICEF supports made any difference to your life or to that of other young people (probe on differences for young women and men)?   How?

- How have you been involved in this work?  What contributions have you made?

Sustainability

- What do you think about the sustainability of this work?  Do you think it could continue without UNICEF’s support or does it rely on this?

Lessons learnt

- Are there any ways in which the work that UNICEF supports could be improved?  How?

- What challenges have there been with this work?  How have these been addressed?

### Interviews with regional advisors / long term consultants providing technical support to programme

Introduction

- Allow 45 minutes to 1 hour for these discussions

- Discussions to take place remotely following field work

Understanding the contributions of the regional advisor/ consultant

- Can you explain how you have contributed to/ engaged with the Uzbekistan programme over the last 5 years? (probe on number of visits/ types of activities)

Understanding the operating space

- Please provide us with some background on working in Uzbekistan.  Which factors limit programme effectiveness?  What factors enhance this?

- (For regional advisors only) How is working in Uzbekistan different from working in other countries in the sub-region?

Relevance

- What is your understanding of the key issues facing children in Uzbekistan in your sector?  Do you feel that the programme is addressing these issues?

- What are your views on the balance within the programme between work at the national and regional levels?

- What are your views on the implementation strategies deployed by the programme?

- Have you been involved in decisions regarding the strategic direction of the programme?  How were these decisions made?  What is your view of the decisions made?

- Have you been involved in any research or evaluations on the programme?  How has the programme responded to recommendations or findings from this research/ evaluations? (ensure get details of studies in case we do not have them)

- (For regional advisors only) What are the UNICEF regional priorities in your sector?  Is the programme aligned to these priorities?

Effectiveness/ longer term impact

- What have been the key achievements of the programme? (probe on impact/ outcome/ output level achievements)

- Has the programme achieved all it intended to?  What have been the key factors that have enhanced these achievements?  What have been the key factors that have prevented the programme from reaching its goals?

- Have there been any negative or positive unintended results from the programme?  How have these been addressed/ responded to?

- Who are the key programme partners?  How were decisions made on who to partner with? (probe on degree of government and CSO engagement)

- Do you feel you were able to contribute effectively to the programme?  What factors hindered or enhanced your ability to contribute?

Lessons learnt

- What are the key lessons learnt the Uzbekistan programme?

- What challenges are the main challenges they have faced?  How have they addressed these challenges?

## Annex 4: Workplan

## Annex 5: Meeting of Evaluation Reference Group

Meeting of the Evaluation Reference Group for the Country Programme 2016-2020 Evaluation

Co-Chairs:

The Ministry of Preschool Education

UNICEF

Participants

The Ministry of Finance

The Ministry of Health

TheMinistry of Public Education

The General Prosecutor Office

The National Human Rights Centre

The Republican Centre for Social Adaptation of Children

The Women’s Committee

The “Yuksalish” Nationwide Movement

The Republican Centre for Social Adaptation of Children

The Cabinet of Ministers

UNFPA

WHO

Evaluation Management

UNICEF, M&E Specialist

UNICEF, Child Rights Monitoring Specialist

UNICEF, M&E Officer

UNICEF, Country Programme Manager, Regional Office for Europe and Central Asia

Evaluation Team

Evaluation Team Leader

National Evaluation Specialist

Introduction and welcome

UNICEF’s Representative welcomed the participants. He thanked them for accepting the invitation to join the Evaluation Reference Group (ERG) established to support the evaluation of the current country programme of cooperation (CP) between the Government of Uzbekistan and UNICEF covering the period 2016-2020. The Representative explained that the evaluation offers opportunity to critically assess the programme, identify lessons learnt and best practices to accelerate the achievement of equitable and sustainable outcomes for the children. He underlined that the findings and conclusions generated by the evaluation will be used to inform the planning and design the new CP (2021-2025) between the Government of Uzbekistan and UNICEF. The Representative reminded the participants that the ERG acts as an advisory body to support the evaluators during the evaluation phases reviewing key deliverables and facilitating dissemination of the evaluation results. He emphasized that the participation and inputs of the ERG members are considered essential, as they help reinforce the relevance, quality and credibility of the evaluation.

The Representative explained that a UK-based evaluation company, IOD PARC, has been contracted to conduct the evaluation with an evaluation team comprising consultants with substantive evaluation expertise and professional experiences from Europe and Central Asia. He introduced the evaluation Team Leader, and the national evaluation specialist, and he gave the floor to the Country Programme Evaluation (CPE) Manager from UNICEF’s Regional Office for Europe and Central Asia.

The CPE Manager welcomed the participants and reviewed the overall purposes of evaluation in UNICEF referring to, respectively, accountability and learning. At times, accountability is given more weight in an evaluation than learning and vice-versa, and in the current evaluation of UNICEF’s CP in Uzbekistan, learning is particularly important. The CPE Manager underlined the importance of distinguishing between an evaluation and an audit where the latter refers to an internal control function. Furtherore, the CPE Manager reiterated that learning and reflection are key words in the CPE that is a strategic evaluation in relation to which critical and constructive observations on UNICEF’s performance are perfectly acceptable and very welcome.

The CPE Manager explained that evaluations in UNICEF are guided by a set of internationally recognized principles referring to independence, credibility and utility. Independence is honoured because evaluations are conducted by independent evaluators who represent outsiders’ perspectives (not involved in programme’s design or implementation) and who are well positioned, therefore, to help UNICEF reflect upon its programme and think “out of the box”. In addition to referring to independence, credibility also refers to the fact that evaluation findings and conclusions must be based on systematic collection, review and analysis of data. The third principle towards which evaluations must adhere was introduced: use. To ensure evaluation usefulness, they must provide timely information that can inform decision-making processes, they must ask and answer relevant questions, and stakeholders must be informed about the evaluation and engaged in it – all of which speaks to the importance of the ERG. The CPE Manager provided an overview of the evaluation phases, i.e., the Inception Phase, the Field Mission Phase and Reporting Phase, and the expected inputs and engagement of the ERG in relation to each phase. The CPE Manager clarified, furthermore, that the ERG doesn’t have any management responsibiltities. It is expected to serve as a sounding board and an advisory group to the Evaluation Team that is not obliged to follow the instructions of the ERG (thus ensuring independence). The overview that was delivered on a PowerPoint slide is attached to these minutes together with the presentation of the evaluation Team Leader.

Presentation of Evaluation Team

The Evaluation Team Leader expressed gratitude for having the opportunity to evaluate the CP 2016-2020, which represent an interesting programme of work. The Team Leader expressed content with the establishment of the ERG that provides a platform for discussion with partners during the evaluation process where the ERG will be meeting with the evaluation team on three occasions, i.e., in each phase and that all team members will be in Uzbekistan during the Field Mission Phase. With reference to the evaluation team BIO shared with ERG members , the Team Leader presented the four-person evaluations team and explained that each evaluation team member will be providing inputs to the evaluation during all phases. With a PowerPoint presentation, the Team Leader reviewed the purpose of the CPE and the objectives of the CP, and he outlined the main tasks to be undertaken during the Inception Phase during which the evaluation team will establish the analytical framework for the evaluation. The Team Leader also shared the team’s preliminary observations on the current CP and the dynamic context in which it has been implemented before presenting some key questions towards which ERG members were invited to respond. The reactions of the ERG members to each question are briefly presented below.

First question: From your knowledge of the collaboration with UNICEF, can you identify one main success in the 2016-2020 country programme that the evaluation team should examine?

WHO emphasized that one success of the programme refers to UNICEF’s ability to establish its work in collaboration with partners and respond to the geo-political changes including the national reform process in areas of social protection for children. WHO identified the flexibility with which it was done as essential for UNICEF’s success.

The Ministry of Preschool Education expressed its agreement with WHO’s analysis. Compared with other international partners, UNICEF had provided support to establishment of the law on preschool education with provision of an in-depth analysis of root courses to existing challenges and support to development of quality pre-schooling and a new state education programme. The Ministry emphasized that one advantage in the approach taken by UNICEF – possibly also a lesson learned – referred to the fact that the support provided was defined not as a ready-made product but as capacity development where UNICEF had supported the efforts of the Ministry in developing the required founding documents.

The General Prosecutor’s Office explained that UNICEF had made several contributions that deserved mentioning, e.g., its support in areas associated with children in conflict with the law and protection of child witnesses. Other important and successful contributions refer to development of the plan to reintegrate children from closed educational institutions and, when possible, reunite them with their families – in relation to which, UNICEF had worked extensively with partners. The General Prosecutor’s Office added that during the CP implementation period, two of four specialized closed educational institutions for children had been closed, and UNICEF had assisted with establishment of social and psychological support to repatriate children coming from Syria.

The National Human Rights Centre pointed to its collaboration with UNICEF on the drafting of the law on the Ombudsman for Children and emphasized the flexibility with which UNICEF had approached this work and the efforts it had made to take into account the needs of national partners. Lastly, the National Human Rights Centre emphasized the high utility value of the studies that UNICEF had prepared in collaboration with its national partners.

The Women’s’ Committee had found its collaboration with UNICEF very useful. The Committee had worked on the rights of children, most notable on the CRC convention - in relation to which UNICEF had provided technical support both to the preparation of the document and the monitoring of the implementation of CRC recommendations. Other areas in which UNICEF had successfully contributed refer to the reintegration of girls from specialized schools  and support to children  affected by migration.

The Centre for Social Adaptation explained it is working to prevent institutionalization of children in orphanages and to provide social and psychological support to children including children of migrants, and it added that the centre is also involved in drafting laws on social protection. It clarified that UNICEF had provided support by bringing to the attention of the centre international experiences of relevance to its work and, furthermore, that UNICEF had trained staff in the centre as part of UNICEF’s work in capacity development. The Centre for Social Adaptation also emphasized that the centre had seen a lot of success stories that it would be happy to discuss further with the evaluation team.

Question 2: Could you identify one question or challenge that has emerged during the 2016-2020 CP implementation period that will be important to tackle in the future?

WHO pointed to the importance of global vaccine strengthening, in particular the system of immunization where provision of warehouses with cold chains to store vaccines represent one important challenge as large numbers of vaccines are in danger of being destroyed.

The General Prosecutor’s Office explained that there is a need to develop a system for repatriation of children to Uzbekistan; a system through which children can effectively reunite with their families. Uzbekistan currently doesn’t have agreements neither with the European Union nor with countries in Asia with regards to repatriation, which means that families lose track of and contact with their children, in particular families residing in other Asian countries. It also pointed to the introduction of a new criminal code in the national legislation in which there was no mentioning of minors and for which , therefore, a subsequent article had to be introduced. The General Prosecutor’s Office explained that there is a need to build experience and gather evidence on good practices in working with children in contact with the law, children on the move and child sex tourism, and it mentioned that UNICEF had been requested to provide information on good practices.

The Ministry of Pre-school Education clarified that it had not identified any particular problem, but added there are issues that must be addressed in the future, e.g., in relation to social inclusion where the perception of parents and a negative attitude from the broader population represent a challenge. To this end, the Ministry urged the need to develop a communication strategy to promote inclusion principles in education, enlighten the general population on its importance and help clarify that it does not pose a threat to “normal” children. It added that there is a need to develop an Education Management Information System (EMIS) and that while UNICEF had helped the Ministry establish an EMIS, there is a need to recruit IT specialists, because it is challenging to find local specialists who can manage the system.

The Republican Centre for Social Adaptation of Children explained that efforts were being made to address the handling of juvenile delinquents and that there is a need to strengthen crime prevention. It emphasized, it would be important to implement recent decrees on  deinstitutionalization of children left without parental care. The Centre added that a foster care system and procedures for adoption of those children are currently not in place. The centre had received help, so far, in organizing workshops and Training of Trainers. Another issue that will require attention is provision of support to children who have been affected by labour migration.

The Evaluation Team Leader thanked the participants for the points raised and introduced the third question.

Question 3: What examples of collaboration and partnership between government authorities and UNICEF should we examine during our country visit in November?

WHO pointed to the need to establish if it would be possible to mobilise financial means to buy vaccines and outcast expenditure and procurement of equipment for vaccine cold chains.

The Ministry of Finance clarified that in allocation of funds, the Ministry of Finance works with the Ministry of Health for procurement of vaccines. The Ministry highlighted, furthermore, the important role of the Government in overseeing that public funds are being used efficiently. To this end, it welcomed any findings or observations from the evaluation team on the efficiency of the programmes that have been implemented during the past two years.

The General Prosecutor’s Office explained that criminal courts and the Ministry of Interior are also working with children and  that there is a need to partner with them to further enhance supervision of implementation of the legislation.

The Ministry of Health noted that research undertaken in 2017 on food and nutrition had been useful informin efforts to address anaemia, and the sanitary and hygiene practices and conditions within the households.

The Team Leader once again thanked the participants for their useful inputs before asking the 4th and final question.

Question 4: Are there any additional sources of information relevant to the UNICEF programme that we should access in our evaluation?

The Team Leader explained that the evaluation team had already been equipped with extensive programme documentation and relevant national strategies and development plans and invited the participants to point to the attention of the evaluation team any other material or sources of information of relevance to the evaluation from which the team might benefit. To this end, the Team Leader encouraged the participants to send any such recommendations to the National Evaluation Specialist on email: rsafari@mail.ru

Closure

The Team Leader thanked the participants for the interesting dialogue and emphasized the the team was looking forward to the next meeting with the ERG in November where it will be sharing its preliminary observations on the country programme.

Attachments:

The PowerPoint Presentation

The Evaluation Brief

The Evaluation Team BIOs

## Annex 6: Bibliography

| # | Description | Source |
| --- | --- | --- |
| 1. Core CP Docs |  |  |
| CPD and CPAP |  |  |
|  | UNICEF Uzbekistan Country Programme Document (CPD) 2016-2020 | UNICEF |
|  | Country Programme Action Plan (CPAP) 2016 -2020, Programme of Cooperation between the Government of the Republic of Uzbekistan and the United Nations Children’s Fund (Signed), 2016 | UNICEF |
|  | Uzbekistan Country Programme Action Plan (CPAP), 2016 | UNICEF |
| Situation Analysis |  |  |
|  | UNICEF Uzbekistan CO - situation analysis of children and women 2016. | UNICEF |
| Strategic Moment of Reflection |  |  |
|  | Revised Country Programme Action Plan of the Government of Uzbekistan and UNICEF 2016-2020 (as a result of the Strategic Moment of Reflection in 2018). | UNICEF |
|  | UNICEF and Government of Uzbekistan Country Programme 2016-2020, Strategic Moment of Reflection. Strategic Intent Memo, Tashkent, July 2018 | UNICEF |
| Theories of Change |  |  |
|  | Child Protection, Theory of Change 2016-2010, UNICEF Uzbekistan, Child Protection Section, 16.02.2015. | UNICEF |
|  | Child Protection, Theory of Change 2016-2010, UNICEF Uzbekistan, Child Protection Section, 2017. | UNICEF |
|  | Theory of change c4d (Uzbekistan Country Programme 2016-2020) – generic, 2016-2017 | UNICEF |
|  | Theory of Change for external communication (Uzbekistan Country Programme 2016-2020), 2016-2017 | UNICEF |
|  | CRM&E ToC Uzbekistan 2015 Matrix | UNICEF |
|  | UNICEF Uzbekistan, monitoring and evaluation theory of change 2016-2020, draft – 16 February 2015 – for UNICEF internal use only | UNICEF |
|  | UNICEF Uzbekistan, child rights monitoring and evaluation theory of change 2017-2020, February 2018– for UNICEF internal use only | UNICEF |
|  | UNICEF Uzbekistan Country Office, Country Program Document (2016-2020), Disaster Risk Reduction Program Theory of Change, 2015. | UNICEF |
|  | UNICEF Uzbekistan Country Office, Country Program Document (2016-2020), Education Program Theory of Change (Version 1), Updated: 16 February 2015 | UNICEF |
|  | UNICEF Uzbekistan Country Office, 2016-2020 Country Program, Quality Learning for All Program Theory of Change, (1st Revision), Updated: April 2015 | UNICEF |
|  | Schematic Description of Theory of Change for Quality Learning for All Program1st Revision; February 2017 | UNICEF |
|  | Young Child Survival and Wellbeing (RKLA 6, 7, 5), Theory of Change, Health, 2015. | UNICEF |
|  | Schematic theory of change Child health and wellbeing (RKLA 5, 6, 7, 10), Health short detailed graphic version, 2017. | UNICEF |
|  | Young Child Survival and Wellbeing (RKLA 6, 7, 5), Health 2017 | UNICEF |
|  | Theory of Change for Social Protection Programme – April 2018. | UNICEF |
| 2. CP Management |  |  |
| Annual Work Plans |  |  |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Social Policy - Social Protection Systems, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Youth Union, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Child Protection -Children in contact with the law – Violence Abuse and Neglect, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Child Rights Monitoring, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Child Protection – child health and well-being, social policy and quality education, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Inter-sectoral corporation on Child Protection, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Inter-sectoral corporation on Child Protection, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Child Rights Monitoring on Child Protection, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Inter-sectoral corporation on Child Protection, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Child Health and Well-being, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Quality Learning for All – Early Childhood Education, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Quality Learning for All Pre-school -CWD, 2018 Collaborative Annual Work Plan | UNICEF |
|  | Uzbekistan – UNICEF Programme of Cooperation 2016-2020, Children in contact with the law – justice for children, 2018 Collaborative Annual Work Plan | UNICEF |
| Multi-year Workplans |  |  |
|  | Multi-year Workplan 20016-2017 Child Protection | UNICEF |
|  | Multi-year Workplan 20016-2017 for cooperation Program Between Ministry of Higher and Specialized Secondary Education and UNICEF Uzbekistan Country Office | UNICEF |
|  | Multi-year Workplan 20016-2017 for Cooperation program between Ministry of Public Education and UNICEF Uzbekistan Country Office | UNICEF |
|  | Multi-year Plan 20016-2017 for Communication Section | UNICEF |
|  | Multi-year Plan 20016-2017 Monitoring and Evaluation | UNICEF |
|  | Multi-year Plan 20016-2017 Child Health and Well-being | UNICEF |
|  | Ministry of Finance of the Republic of Uzbekistan and UNICEF, Multi-year Collaborative Work Plan 20016-2017 | UNICEF |
| Financial Information |  |  |
|  | Read Me – Introduction to Financial Information CPE Uzbekistan | UNICEF |
|  | Financial Information Uzbekistan 2013-2019 | UNICEF |
|  | Revised PIDB Guidance, Strategic Goal Areas 2018-2021 | UNICEF |
| 3. Reporting |  |  |
| COARs |  |  |
|  | UNICEF Country Office Annual Report 2015 | UNICEF |
|  | UNICEF Country Office Annual Report 2016 | UNICEF |
|  | UNICEF Country Office Annual Report 2017 | UNICEF |
|  | UNICEF Country Office Annual Report 2018 | UNICEF |
| Donor Reports |  |  |
| MICS |  |  |
|  | Multiple Cluster Indicator Survey 2006 | UNICEF |
| RAM and SMQs |  |  |
|  | Outcome Indicator Status 2010-2015 by Business Area | UNICEF |
|  | Outcome Indicator Status 2016-2019 by Business Area | UNICEF |
|  | Outcome Ratings with the Latest Progress 2019 | UNICEF |
|  | Output Indicators Status 2010-2015 by Business Area | UNICEF |
|  | Output Indicators Status 2016-2019 by Business Area | UNICEF |
| Evaluations, Studies and Research |  |  |
|  | UNICEF CPE 2014 Final Report Annexes | IOD PARC/UNICEF |
|  | UNICEF CPE 2014 Final Report. Eds. Julia Betts and Gucharan Virdee. | IOD PARC/UNICEF |
|  | CRM Evaluation Final Report 2018 Uzbekistan - Annexes | CORAM International/ UNICEF |
|  | CRM Evaluation Final Report 2018 Uzbekistan. Formative Evaluation of the Child Rights Monitoring Programme in Uzbekistan 2016-2018. Eds. Awaz Raoof, Charlotte Baker and Professor Dame Carolyn Hamilton | CORAM International/ UNICEF |
|  | Summative Evaluation of Improvement Of Mother And Child Health Services In Republic of Uzbekistan – Phase II. Eds. Ivdity Chikovani, MD. ,Maya Kherkheulidze MD., PhD Konstantin Osipov | Curation International Foundation/ UNICEF |
|  | OPM Perinatal 2017 Costing. Institutional consultancy on costing perinatal care services across three different levels in selected regions of Uzbekistan, Final Report. Eds. Tim Ensor, Afeef Mahmood and Adrian Gheorghe. | Offord Policy Management Group/UNICEF |
|  | Country Situation Analysis, 2019 | UNICEF |
|  | A situation analysis of CWD, 2019 | UNICEF |
|  | Health strengthening and home-visiting baseline data 2016 (endline data doesn’t exist yet) | UNICEF |
|  | National Learning Achievement Study, 2019 | UNICEF |
|  | Social Protection System Assessment | UNICEF |
|  | Youth of Uzbekistan: Aspirations, Needs and Risks | UNICEF |
|  | Assessment of potential effects of the health care reform on the quality and access to immunization, 2019 | UNICEF |
| UN Collaboration |  |  |
|  | UNDAF 2016-2020 Final ENG | United Nations Uzbekistan |
|  | UBZ CCA 2014 ENG | United National Uzbekistan |
| JWP 2016-17 |  |  |
|  | Education_JWP_2016-2017 Approved SC_Eng | UN/Government |
|  | Environment_JWP_2016-2017-approved_SG_eng | UN/Government |
|  | Governance_JWP_2016-2017-approved_SG_eng | UN/Government |
|  | Health_JWP_2016-2017-approved_SG_eng | UN/Government |
|  | Livelihoods_JWP_2016-2017-approved_SG_eng | UN/Government |
|  | Social Protection_JWP_2016-2017-approved_SG_eng | UN/Government |
| 4. Corporate and Regional Guidance and Data |  |  |
|  | Adolescent and Youth Engagement Strategic Framework, 2017 | UNICEF |
| C4D |  |  |
|  | Communication for Development: Strategic Vision and Policy Framework for Implementation of UNICEF Strategic Plan 2014-2017, June 1, 2014 | UNICEF |
| CWD |  |  |
|  | Take us Seriously - Engaging Children with Disabilities in Decisions Affecting their Lives, 2013 | UNICEF |
| ECD |  |  |
|  | CP Profiles Uzbekistan, 2018 | UNICEF |
| Education |  |  |
|  | RKLA 3 & 4, Regional Education Strategy, Inclusive Quality Education and Early Learning, Final version – 17 August 2016 | UNICEF |
|  | RKLA 3 & 4, Output Indicators, 2016 | UNICEF |
| Gender |  |  |
|  | Country Gender Profile, Uzbekistan 2018 | UNICEF |
|  | Gender, agriculture and rural development in Uzbekistan country gender assessment series, 2018 | Food and Agricultural Organization |
|  | Child Marriage Prevention and Burden, Europe and Central Asia, 2018 | UNICEF |
|  | UNICEF Gender Action Plan, 2018–2021, E/ICEF/2017/14, September 2017 | UNICEF |
|  | UNICEF Gender Action Plan 2018-2021, Brochure | UNICEF |
|  | UNICEF Gender Action Plan 2014-2017, E/ICEF/2014/5, 2014 | UNICEF |
|  | Situation Analysis. Quality Assurance Checklist for Gender Integration in Country programme Documents | UNICEF |
|  | ECA Regional Gender Strategic Framework, August 2018 | UNICEF |
|  | Revised Staff GAP Analysis April 2019 | UNICEF |
|  | UNICEF Central Asia Gender Counts Report Digital, 2018 | UNICEF |
|  | Gender Equality and Women’s Empowerment, Briefing Note for MAPS mission, 23-27 April 2018 | UNICEF |
|  | Uzbekistan Country Gender Assessment Up-date, 2018 | UNICEF |
| Health |  |  |
|  | UNICEF Health Strategy 2016-2030 | UNICEF |
| Human Rights |  |  |
|  | The Convention on the Rights of the Child, 1989 | UNICEF |
|  | Committee on the Rights of the Child. General comment No. 20 (2016) on the implementation of the rights of the child during adolescence | UN CRC |
| Protection |  |  |
|  | 15 years of De-Institutionalization Reforms in Europe and Central Asia. Key results achieved for children and remaining challenges | UNICEF |
|  | 15 years of Juvenile Justice Reforms in Europe and Central Asia. Key results achieved for children and remaining challenges | UNICEF |
| Regional Results and Priorities |  |  |
|  | Central Asia- Sub-regional Guidance Note for Flagship Results, April 2019 | UNICEF |
|  | Regional Priority 1: Survive and Thrive | UNICEF |
|  | Regional Priority 2: Reduce Stunting | UNICEF |
|  | Regional Priority 3: Quality Education and Learning, 2017 | UNICEF |
|  | Regional Priority 4: Results for Adolescence, 2017 | UNICEF |
|  | Regional Priority 5: Social Protection, 2017 | UNICEF |
|  | Four Regional Results Areas four regional results headings | UNICEF |
|  | Flag thriving by sub-region (ECARO) | UNICEF |
|  | Learning Discussion on Central Asia 2019 | UNICEF |
|  | Regional Headline Results 2018-2021 | UNICEF |
|  | Sub-national Regional Programme Analysis Learning 2019 | UNICEF |
|  | Flagship participation | UNICEF |
|  | Participating Regional Headline Results Final 2019 | UNICEF |
|  | Central Asia Protecting, A PowerPoint Presentation | UNICEF |
|  | Sub-Regional Programme Priority Analysis for UNICEF Results Central Asia (Turkmenistan, Tajikistan, Uzbekistan, Kazakhstan) | UNICEF |
|  | Protecting Regional Headline Result – _Option One Zero Children in Institutional Care1 (ASPIRATIONAL) | UNICEF |
|  | ECD Thriving February 2019 | UNICEF |
|  | Protecting Regional Headline Result – _Option One Zero Children in Institutional Care1 (ASPIRATIONAL) | UNICEF |
|  | Flagship Thriving by Flagship, A PowerPoint Presentation | UNICEF |
|  | Thriving Regional Headline Results Final | UNICEF |
|  | Thriving | UNICEF |
| Social Policy |  |  |
|  | Toolkit: new generation situation analysis, 2019 | UNICEF |
|  | Making cash transfers work for children and families child poverty and social protection, 2017 | UNICEF |
|  | Social Policy in CPD Countries, 2019 | UNICEF |
|  | UNICEF Engagements in Influencing Domestic Public Finance for Children (PF4C), A global programme framework, 2017 | UNICEF |
|  | Integrated Social Protection Systems: Enhancing equity for children, 2012 | UNICEF |
| Strategies |  |  |
|  | UNICEF Strategic Results Framework 2018-2021, 2017 | UNICEF |
|  | UNICEF Strategic Plan 2018-2021, Summary, 2017 | UNICEF |
|  | UNICEF Strategic Plan, 2018-2021E/ICEF/2017/14, 2017 | UNICEF |
|  | UNICEF Strategic Plan 2014-2017, 2013 | UNICEF |
| 5. CPE Planning Process and Contextual Documents |  |  |
| CRC Report |  |  |
|  | 3&4 CRC Report Uzbekistan 2010 | UN CRC |
|  | Concluding Observations CRC 2013 | UN CRC |
|  | Concluding observations OP Armed Conflict 2013 | UN CRC |
|  | Concluding Observation 2013 OP Sale of Children | UN CRC |
| National Main Strategies |  |  |
|  | The state program for implementation of the national action strategy on five priority development areas 2017-2021 in the year of active investments and social development | Government |
|  | Draft national development strategy for the republic of Uzbekistan 2017-2021. UNICEF’s recommendations | Government |
|  | Strategy of Actions on the five priority areas for the development of the Republic of Uzbekistan in 2017-2021 | Government |
| 6. Previous CP |  |  |
|  | CPAP 2010-2015 | UNICEF |
|  | CPD Uzbekistan 2010-2015 | UNICEF |
|  | UZBA CPAP Results Matrix Final Approved 2009 | UNICEF |
|  | UZBA CPAP Results Matrix Modified Approved Jan 2014 | UNICEF |
| 7. Essentials |  |  |
|  | Attachment VI UNICEF or Ethical Standards, 2015 | UNICEF |
|  | Evaluation Report Review Template | UNICEF |
|  | GEROS Handbook Final Summary, 2017 | UNICEF |
|  | Inception Report Review Template | UNICEF |
|  | UNEG Norms and Standards, 2017 | UNEG |
|  | UNICEF adapted reporting standards up-dated June, 2017 | UNICEF |
|  | Added by the Evaluation Team |  |
| - ; | Assessment of the Patronage Nursing System with equity analysis in Uzbekistan, (September 2018) by Tamar Cotsadze (MD, PhD), | Curatio International Foundation |
|  | Knowledge, Attitude and Practices of the population on children immunisation in the Republic of Uzbekistan (Research Report, November 2018 (no authors mentioned) | UNICEF |
|  | Prevention of mother-to-child transmission of HIV and Syphilis: Situational Analysis (Uzbekistan (Approved by Deputy Minister of Health, E I Basitkhanova, 9.04.2019) | Ministry of Health |
|  | Light Gender Assessment of UNICEF Uzbekistan Country Office by Sanja Boezak and Sarita Ranchod (2015) | UNICEF |
|  | Uzbekistan Country Gender Assessment (2018) | Asian Development Bank |

## Annex 7: Stakeholder List

| Initial National Institution List | Name | Function | Location | UNICEF Programme component linked with |
| --- | --- | --- | --- | --- |
| State bodies |  |  |  |  |
| The Cabinet of Ministers | Mr. Rustam Azimov | Senior Specialist on Social Protection | Tashkent City | CPE/CPD Focal Point, Social Policy |
| The Ministry of Finance | Mr. Rafael Klivleev | Lead Specialist, Financing of Social Sectors | Tashkent city | Social Policy/Social Protection |
| The Ministry of Employment and Labour Relations | Mrs. Shakhnoza Rustamova | Lead Specialist on Social Allowances | Tashkent City | Social Policy/Social Protection |
| Ministry of Health | TBC | Deputy Minister | Tashkent city | Maternal and Child Health |
|  | Mrs. Dilorom Akhmedova | Director, Republican Specialized Scientific Practical center of Pediatrics, Chief Pediatrician | Tashkent city | Child Health, Nutrition |
|  | Mrs. Dilorom Tursunova | Deputy Head, Main Department of Sanitary-Epidemiology Surveillance | Tashkent city | Immunization, Validation of elimination of HIV and syphilis transmission from mother to child |
|  | Mrs. Malika Usmanova | Deputy Director, Tashkent city Perinatal Center | Tashkent city | Neonatal Health |
| Ministry of Health | Mr. Dilmurod Mirzabaev | Head of Main Department of Sanitary-Epidemiology Surveillance | Tashkent city | Immunization |
|  | Mr. K. Yuldashev | Director, Republican AIDS Center | Tashkent city | HIV/AIDS, validation of elimination of HIV and syphilis transmission from mother to child |
|  | Mr. Alisher Inakov | OIC Director, Agency of Socio-Medical Services | Tashkent city | Social Policy/Social Protection |
|  | Mr.K. Jumaniyazov | Deputy head of Khorezm regional Health department | Urgench city, Khorezm region | Maternal and child health, DHSS |
| The Ministry of Public Education | Mr. Alisher Umarov | First Deputy Minister, MOPE | Tashkent city | Quality learning for all – general secondary education |
|  | Mr. Dilshod Kenjaev | Deputy Minister of Public Education | Tashkent city | Child Care System Reform Policy Development |
|  | Mr. Fayzulla Akhmedov | Head of Department of Social Protection and Support of children | Tashkent city | De-institutionalization process (children in institutions) |
|  | Mr. Khikmatilla Daminov | Head of Department on Improving Methodic Provisions | Tashkent city | Quality Education |
| The Ministry of Preschool | Ms. Yelena Ten | Head of the Main Department, MOPSE | Tashkent city | Quality learning for all – Early Childhood Education |
| State Inspectorate for the Supervision of Education Quality (SISEQ) | Mr. Ulugbek Tashkanbaev | Head, SISEQ | Tashkent city | Quality learning for all |
| Higher Judicial Council | Mr. Dilshod Aripov | Director, Research Center under Higher Judicial Council | Tashkent city | Justice for Children (Research and Policy Development) |
| The Ministry of Emergency Situations | Mr. Jakhongir Isaev | Head of international department | Tashkent city | Disaster Risk Reduction |
| The National Agency of Project Management | Mr. Ziyod Mirakhmedov | Head of International Cooperation Department | Tashkent City | Evidence Generation (MICS) |
| The Local Governments (Hokymyats) | Ms. Mavluda Qobulova | Deputy Head of Surkhandarya Region | Termez City, Surkhandarya region | Children affected by Migration project realization |
| The State Statistics Committee (SSC) | Mr. Khabibilla Murodkhujaev | Head of Department, Department of Social and Sustainable Development Statistics | Tashkent city | Evidence Generation (MICS, TransMonEE, UN IGME, CRAVE) |
|  | Mr. Odiljon Mamadaliyev | Head of Department, Department of Information Dissemination, International Cooperation and Data Exchange | Tashkent city |  |
|  | Mr. Jakhongir Yuldashev | Head of Department, Department of living standards and surveys | Tashkent city |  |
| The Prosecutor General Office | Mrs. Laylo Fayzimurodova | Senior Prosecutor of the Prosecutor General’s Office | Tashkent city | Justice for Children (Children in closed institutions) |
|  | Mr. Uygun Negmatjanov | Deputy Director of the Academy of Prosecutors | Tashkent city | Justice for Children (Diversion and Restorative Justice) |
| The Supreme Court | Mr. Aziz Mirzaev | Assistant of the Chair of the Supreme Court | Tashkent city | Juvenile Justice System reform (capacity building) |
| The Ministry of Interior | Mrs. Nilufar Muinova | Director of Social and Legal Center under MOI | Tashkent city | Children in closed type institutions |
|  | Mr. Jasur Saidov | Head of Investigation Unit | Tashkent city | Child friendly Investigations of victims and witnesses |
| Public agencies |  |  |  |  |
| The Office of the Ombudsperson | Mr. Saidbek Azimov | Head of Secretariat | Tashkent city | Child Rights Monitoring |
| The Oila (Family) Centre | Mrs. Dildora Karimova | Deputy Director | Tashkent city | Planning of social service workforce development |
| The National Human Rights Centre | Mrs. Dilnoza Muratova | Deputy Director | Tashkent city | Child Rights Monitoring, Child Protection |
|  | Mrs. Farida Bakaeva | Head of Department of Analysis and Research | Tashkent city |  |
|  | Mr. Yaroslav Kvitkov | Specialist, Department of Analysis and Research | Tashkent city |  |
| The National Association of electronic mass media | Mr. Firdavs Abdukhalikov | Chairperson | Tashkent city | Communication |
| The Youth Union | Mr. Alisher Sadullaev | First Deputy Chairman | Tashkent City | Youth |
| The Yuksalish (Uprising) Movement | Mr. Akmal Burkhanov | Director | Tashkent | Social Policy, Youth |
| The Yuksalish (Uprising) Movement | Sherzod Saparov | Head of Department | Tashkent city | Social Policy, Youth |
| Civil Society Organisations |  |  |  |  |
| The SOS Children’s Villages | Ms. Farida Akhmatiy | OIC Head of Programme | Tashkent city | Child Care (family based alternative care) |
| The Republican Centre for Social Adaptation of Children | Mrs. Vasila Alimova | Director | Tashkent city | Social work and case management services |
| The Women’s Committee | Mrs. Dilorom Kuzieva | Head of International Department | Tashkent city | Child Rights Monitoring, Migration, Child Care (children affected by migration) |
| The Association for Support of Families and Children. | Mrs. Inqilob Tursunova | Director | Tashkent city | Child Rights Monitoring, Communication |
| Private sector |  |  |  |  |
| UCELL telecom operator (Note: As UCELL management has changed, we may or may not have any personnel who knows about partnership.) | Ms. Kamila Biktimorova | Director Communication | Tashkent City | Communication/Partnership |
| UN Agencies and IFIs |  |  |  |  |
| UNDP | Mrs. Matilda Dimovska | Resident Representative | Tashkent city |  |
|  | Ms. Kamila Mukhamedkhanova | Head of Governance Cluster | Tashkent city |  |
|  | Mr. Azizkhan Bakhadirov | Programme Analyst, Governance Cluster | Tashkent city |  |
| UNFPA | Mrs. Mieko Yabuta | Representative | Tashkent city | Social Policy, Youth, Gender |
|  | Mr. Kamolkhon Inomkhodjayev | Assistant Representative | Tashkent city | Social Policy, Evidence Generation |
|  | Ms. Dilfuza Nabieva | Programme Analyst on Gender and Youth | Tashkent City | Gender, Youth, Social Policy |
|  | Mr. Behruz Yusupov | Programme analyst on reproductive health | Tashkent city | Reproductive and maternal health |
| UNODC | Ms. Ashita Mittal | Regional Representative | Tashkent city |  |
| ILO | Ms. Jasmina Papa | Regional Social Protection Specialist | Moscow city | Social Policy/Social Protection |
| WHO | Mrs. Lianne Kuppens | Representative | Tashkent city |  |
|  | Mrs. Elena Tsoy | NPO on NCD and Life Course Approach | Tashkent city | Health Information System, Health Financing, Adolescent Health |
|  | Mrs. Kamola Safaeva | NPO Vaccine Preventable Diseases and Immunization |  | Immunization |
| World Bank | Mr. Janssen Edelweiss Teixeira | Senior Education Specialist | Washington D.C. | Quality Learning for All |
|  | Mr. William Hutchins Seitz | Economist, Poverty and Equity Global Practice | Almaty city, Kazakhstan | Social Policy |
| UNESCO | Mr. Fuad Pashabayev | Representative | Tashkent city | Quality learning for all – general secondary education |
|  | Mr. Bakhtiyor Namazov | Education Specialist | Tashkent city | Quality learning for all – general secondary education |
| FAO | Mrs. Dono Abdurazakova | Senior Advisor, Gender and Social Protection, ECA Regional Office | Budapest, Hungary |  |
| OHCHR | Mrs. Guljakhon Amanova | National Programem Officer | Tashkent | Human Rights, CSOs |
| Resident Coordinator Office | Mrs. Helena Fraser | Resident Coordinator | Tashkent city | Cross-sectoral |
|  | Mrs. Matluba Umurzakova | Coordination Specialist | Tashkent city | Cross-sectoral |
|  | Mr. Zarif Jumaev | UN Coordination Analyst | Tashkent city | Cross-sectoral |
| UN Communication Group (UNSG) | Anvar Meliboev | Communication Officer, UNRCO | Tashkent | Communication |
| UN Social Policy UNDAP Result Group | Mr. Yulia Oleinik | RG | Tashkent | Social Policy |
| Academia |  |  |  |  |
| The National University of Uzbekistan | Mrs. Marifat Ganieva | Senior Professor of University | Tashkent city | Social Work Profession Development, Social Protection |
| The Tashkent State University of Law | Mrs. Umida Tukhtasheva | Head of Specialised Department | Tashkent city | Promotion of International Juvenile Justice Standards |
| The Tashkent Paediatric Medical Institute | Mrs. Sh. Mukhamedkhanova | Dean | Tashkent city |  |
|  | Mrs. Sevara Ubaydulaeva | Head of Department, Department of education quality control | Tashkent city | Home Visiting, Maternal and Child Health |
| Donors |  |  |  |  |
| Donor Governments | Government of Switzerland (Embassy of Switzerland) | Mr. Muzaffar Madaminov, Chief of Finance | Tashkent city | Child victims and witnesses |
|  | Government of UK (Embassy of UK) | Mrs. Evelina Artikova, Head of Programme | Tashkent city | Children in closed institutions |
| The European Union | Mr. Akmal Rustamov | Head of Programme | Tashkent city | Children Affected by Migration |
| GAVI | Nilgun Aydogan | Senior country manager | Global Health Campus Chemin du Pommier, 1218 Grand-Saconnex, Geneva Switzerland | Immunization |
| Regional Bodies |  |  |  |  |
| Regional and District health depts | TBC Regional and Bogot district health authorities | District health managers, health professionals | Khorezm | District Health strengthening, Home Visiting |
| Regional and health authorities (12 regions) | TBC | Managers of infrastructure and | Khorezm | Immunisation |
| Medical education institutions | TBC | Teachers in medical colleges | Tahkent city | Immunisation |
| Regional or district health authorities, finance depts | TBC | Budgeting for health services | Khorezm | Health reforms / budgeting – perinatal care |
| Regional and health authorities – primary health care | TBC | Home visitors and their managers, day care centres (Visit to primary health care facility)- SVP and/or Maternity | Khorezm | Adolescents living with HIV |
| NGOs representing people with disabilities, Ilkhom theatre (Tashkent) | Natalya Plotnikova | Chair of PWD NGO | Tashkent region, Kibray | Education policy on inclusive education |
|  | Ms. Irina Bharat | Deputy general manager, Ilkhom Theatre | Tashkent city | Partnership for creating platforms (ex. Exhibitions, Aktivaciya) pro-bono |
| Ministry of Interior, regional and district level | Child Friendly Room | Police and court officials | Karakalpakstan | Child protection reforms |
| Media professionals in regions | TBC (Karakalpakstan) | Managers, journalists | Karakalpakstan | C4D |
| Youth Union and other youth groups | Ms. Bibijan Aralbayeva | Deputy Head of Youth Union | Karakalpakstan | Social policy, youth, C4D |
| U report | Focus Groups with 5-8 young people | U-Report Activists | Karakalpastan | Youth, U-Report |
| Youth Union, Tashkent branch | Focus Group Discussion with U-Report Steering Committee Focus Group Discussion of U-Report Youth Committee | Leaders, experts | Tashkent city | Social and youth policy, communications |
| Guardianship and Trusteeship authority | TBC | Guardinaship and Truststeeship specialist | Khorezm | Child Protection, Migration Project, |

Uzbekistan National Development Strategy 2017-2021. Adopted following public consultation. Tashkent Times2017-02-08

Situation Analysis of Children in Uzbekistan. 2019. UNICEF Uzbekistan. Section 4.1 Regional Disparities.

WHO, UNICEF, UNFPA and the World Bank, Trends in maternal mortality: 1990 to 2010, WHO, UNICEF, UNFPA and the World Bank estimates, May 2012.

United Nations, CRC/C/UZB 3-4 Concluding observations of the combined third and fourth periodic reports of Uzbekistan, adopted by the Committee at its sixty-third session (27 May-14 June 2013) at http://www2.ohchr.org/english/bodies/doc/co/CRC-UZB-CO-3-4.pdf

World Bank, 2018. Listening to Citizens of Uzbekistan. https://www.worldbank.org/en/country/uzbekistan/brief/l2cu

National household survey (UNICEF and World Bank) “Listening to Citizens of Uzbekistan”. (2018)

UNICEF Uzbekistan, Outcome Ratings with Latest Progress, 22 September 2019.

UNICEF 2015.

The rolling Country Situation Analysis is expected to be finalized in September to inform the drafting of UNICEF`s Programme Strategy Note (PSN) that will begin during the third quarter of 2019 and is expected to be finalized by October 2019. Together with other relevant exercises and documents, the PSN will inform the CPD planning process that is expected to be completed by May 2020.

As of 10 December 2019 the DAC Criteria were revised to include Coherence as a separate criteria. The revisions to the DAC Criteria, specifically to Coherence will be covered. At present it is covered under the other criteria.

The Tool of Contribution Analysis provides a structured approach to assessing the contribution of a programme/s to outcomes, especially suited to assessing the contribution of policy advocacy work. See Mayne (ILAC Brief 2008).

Typology of Sampling Strategies in Qualitative Inquiry (Kuzel, 1992; Patton, 1990) in Miles and Huberman, 1994. Qualitative Data Analysis (2nd Ed.). Page 28; Fig 2.6

Stakeholder consultation List National; Stakeholder Consultation List Regional

UNICEF 2015.

UNICEF 2019).

In UNICEF’s Strategic Plan 2014-17, change strategies refer to: 1) Capacity Development; 2) Evidence Generation, Policy Dialogue and Advocacy; 3) Partnerships; 4) South-south Collaboration and Triangular Corporation; 5) Identification of Innovation; 6) Integration and Cross-sectoral Linkages; and 8) Service Delivery (UNICEF 2013).

CPEs may also be commissioned if the programme of work or context in which UNICEF operates undergo radical changes, or if audit reports recommend, they are done (UNICEF 2018A).

With the UN reform process the UNDAF will be referred to as the UN Sustainable Development Framework (United Nationas Sustainable Development Group (UNSDG) 2019).

The rolling Country Situation Analysis is expected to be finalized in September to inform the drafting of UNICEF`s Programme Strategy Note (PSN) that will begin during the third quarter of 2019 and is expected to be finalized by October 2019. Together with other relevant exercises and documents, the PSN will inform the CPD planning process that is expected to be completed by May 2020.

The UN system in Uzbekistan comprises the United Nations Development Programme (UNDP), United Nations Population Fund (UNFPA), United Nations Children’s Fund (UNICEF), World Health Organization (WHO), United Nations Educational, Scientific and Cultural Organization (UNESCO), United Nations Office for Drugs and Crime (UNODC), Joint United Nations Programme on HIV/ AIDS (UNAIDS), UN Entity for Gender Equality and the Empowerment of Women (UN Women), United Nations Regional Centre for Preventive Diplomacy in Central Asia (UNRCCA), International Labour Organization (ILO), Food and Agriculture Organization (FAO) and UN Volunteers (UNV) administered by UNDP. Additional contributions to the UN System’s work are made by a number of non-resident Agencies, including the United Nations Industrial Development Organization (UNIDO), United Nations Environmental Programme (UNEP) and United Nations Economic Commission for Europe (UNECE). The World Bank, as an independent, specialized Agency, also significantly contributes to the work of the UN in the country. http://www.un.uz/eng/pages/display/un-in-uzbekistan

At the time, this was referred to as the United Nations Development Assistance Framework (UNDAF).

State Committee on Statistics as cited in TransMonEE

Please refer to the WB Data Bank on Uzbekistan:  https://data.worldbank.org/indicator/NY.GDP.MKTP.KD.ZG?locations=UZ

UNICEF 2016.

State Committee on Statistics as cited in TransMonEE

Please refer to: https://tradingeconomics.com/uzbekistan/unemployment-rate

UNICEF 2018B.

Centre for Economic Research, MDG Report, 2015 citing Statistic Committee figures.

Human Development Indices and Indicators: Uzbekistan 2018 Statistical Update available at http://hdr.undp.org/sites/all/themes/hdr_theme/country-notes/UZB.pdf

UNDP 2018.

State Committee on Statistics as cited in Uzbekistan in the 2018  publication.

UNICEF 2016, Situation Analysis of Children and Women.

Personal remittances received, World Bank at: https://data.worldbank.org/indicaToRs/BX.TRF.PWKR.DT.GD.ZS?end=2016&locations=UZ&start=2006&view=chart

Ibid.

Please refer to World Bank in Uzbekistan – Country Context on: http://www.worldbank.org/en/country/uzbekistan/overview#context

The 2014-17 SP came with a total of seven outcomes that were formulated under the following headlines: 1) Health; 2) HIV&AIDS; 3) Water sanitation & Hygiene; 4) Nutrition; 5) Education; 6) Child Protection; and 7) Social Inclusion (UNICEF 2013A).

The 2018-21 SP goal areas that are aligned with nine SDGs (1, 2, 3, ,4 5, 6, 10, 11 and139) are entitled; 1) Every child Survives and Thrives; 2) Every Child learns; 3) Every Child is Protected from Violence and Exploitation; 4) Every Child Lives in a Safe and Clean Environment; and 5) Every Child has an Equitable Chance in Life (UNICEF 2017A).

UNDAF 2016.

In UNICEF’s 2014-17 strategic plan (SP) implementation strategies refer to: Capacity Development; Evidence Generation, Policy Dialogue and Advocacy; Partnerships; South-South and Triangular Cooperation; Identification and Promotion of Innovation; Integration and Cross-Sectoral Linkages and Service Delivery. Under the SP 2018-21 the equivalent to implementation strategies is “Change Strategies” and refer to: Programming at-scale Results for Children; Gender-Responsive Programming; Winning Support for the Cause of Children from Decision-Makers and the Wider Public; Developing and Leveraging Resources and Partnerships for Children; Leveraging the Power of Business and Markets for Children; United Nations Working Together; Fostering Innovation in Programming and Advocacy for Children; and Using the Power of Evidence to Drive Change for Children. The change strategies listed in this document are defined in relation to the SP 2014-17 (UNICEF 2013B).

UNICEF 2017C

UNICEF 2013B and 2017B

The DAC evaluation criteria of relevance, effectiveness, efficiency, impact and sustainability were first outlined in 1991 under the OECD, and they are currently under revision. Please refer to OECD 2019.

Through an explicit policy advocacy role.

UNICEF 2017.

UNICEF 2011

This will include consideration on the disparities described in these ToRs, among other, the rural-urban divide.

The evaluation team will collaborate closely with the TCO on the organization of the field mission to set up interviews with the relevant government authorities, development and humanitarian partners, institutions, duty bearers, rightsholders and other key stakeholder and, if relevant, organize site visits.

Please refer to Annex D

For details on UNICEF’s external quality assurance review, please refer to Annex D

Longer term impact will be explored alongside effectiveness as there is overlap between these two subject areas.