TERMINAL EVALUATION:

Catalytic Support to Peace building in Sri Lanka

(Outcome # 4 - UN catalytic engagement with resettlement and durable solutions has supported wider political transition, peace-building and reconciliation efforts in Sri Lanka)

Evaluation Report

Submitted by:

Institute for Participatory Interaction in Development (IPID)

No. 23, P. Ruban Peiris Mawatha, Kalubowila, Dehiwala, Sri Lanka

Telephone: 0112723833, 0117417587 / 0117417588, Fax: 0112723225

14 October 2019

Contents

Acronyms and Abbreviations	iii

Executive Summary	iv

1.	Introduction	1

2.	Project Description	4

2.1.	Project Objective	4

2.2.	Baseline Indicators	4

2.3.	Implementation timelines	5

2.4.	Key Stakeholders and beneficiaries	5

2.5.	Expected Results	5

2.6.	Project Management	6

3.	The Evaluation	8

3.1.	Purpose and Scope	8

3.2.	Evaluation Principles	8

3.3.	Evaluation Design	9

3.4.	Evaluation Approach and Methodology	10

3.5.	Limitations	11

4.	Analysis of Findings in relation to Project Results	13

4.1.	Project Design	13

4.2.	Output 4.1	14

4.3.	Output 4.2	17

4.4.	Output 4.3	18

4.5.	Cross-Cutting Areas	47

a)	Gender	47

b)	Social Equity	50

4.6.	Project Implementation and Management	51

5.	Project Performance	54

5.1.	Relevance	54

5.2.	Effectiveness	55

5.3.	Efficiency	58

5.4.	Sustainability	59

6.	Evaluative Conclusions	61

6.1.	Conclusions	61

6.2.	Lessons Learnt	61

6.3.	Recommendations	63

7.	Annexes	67

# Acronyms and Abbreviations

| CBO | Community-based Organisation |  | PWJ | Peace Winds Japan (CSO) |
| --- | --- | --- | --- | --- |
| CCCD | Coordinating Centre for Community Development or 3CD (CSO) |  | RDS | Rural Development Society |
| CDF | Child Development Fund (CSO) |  | SAM | Severe Acute Malnutrition |
| CEPA | Centre for Poverty Analysis (CSO) |  | SDP | School Development Plan |
| CRPO | Child Rights Promoting Officer |  | SGBV | Sexual and Gender-based Violence |
| CSO | Civil Society Organisation |  | SOND | Social Organisations Networking for Development (CSO) |
| DPCCS | Department of Probation and Child Care Services |  | SSA | School Self-Assessment |
| DS | Divisional Secretary |  | UN | United Nations |
| ECCD | Early Childhood Care and Development |  | UNDP | United Nations Development Programme |
| EHED | Eastern Human & Economic Development (CSO) |  | UN-Habitat | United Nations Human Settlements Programme |
| ELC | Essential Learning Competencies |  | UNICEF | United Nations International Children's Emergency Fund |
| ELDS | Early Learning Development Standards |  | USD | United States Dollar |
| FGD | Focus Group Discussions |  | VCDC | Village Child Development Committee |
| FHH | Female-headed Households |  | WASH | Water, Sanitation and Hygiene |
| GBV | Gender-based Violence |  | WPC | Woman Police Constable |
| GNDs | Grama Niladhari Divisions |  | WRDS | Women’s Rural Development Society |
| GoSL | Government of Sri Lanka |  | YED | Youth Enterprise Development |
| ha | Hectare |  |  |  |
| IDPs | Internally Displaced Persons |  |  |  |
| IPID | Institute for Participatory Interaction in Development |  |  |  |
| KII | Key Informant Interviews |  |  |  |
| LKR | Sri Lankan Rupee |  |  |  |
| M&E | Monitoring & Evaluation |  |  |  |
| MAM | Moderate Acute Malnutrition |  |  |  |
| MC | Mothers’ Club |  |  |  |
| MEL | Monitoring, Evaluation and Learning |  |  |  |
| MoRRHRA | Ministry of Rehabilitation, Resettlement and Hindu Religious Affairs |  |  |  |
| MoE | Ministry of Education |  |  |  |
| MoH | Medical Officer of Health |  |  |  |
| MT | Metric ton |  |  |  |
| NGO | Non-governmental Organisation |  |  |  |
| NWSDB | National Water Supply & Drainage Board |  |  |  |
| OfERR | Organisation for Elangai Refugees Rehabilitation (CSO) |  |  |  |
| PHI | Public Health Inspector |  |  |  |
| PHN | Public Health Nurse |  |  |  |

# Executive Summary

Background: The civil conflict during 1993-2009 severely affected the people of Sri Lanka, particularly in the North and Eastern Provinces, displacing nearly 400,000 people. The Human Rights Council’s resolution in 2015, ‘Promoting reconciliation, accountability and human rights in Sri Lanka’, had underscored the need for addressing issues of IDPs as a priority.

After the end of the civil war, the Government of Sri Lanka started resettling families and rebuilding infrastructure to improve the living conditions of the communities.  Today, almost all the displaced persons have been resettled in the Eastern Province which was liberated in 2007. However, in the Northern Province, liberated in 2009, resettlement has been slow due to several reasons, in particular inadequate opportunities for livelihoods, poor living conditions, and lack of social protection including psychosocial care.

Contextual differences: Jaffna and Trincomalee:

The socio-economic conditions differ considerably between Trincomalee and Jaffna.  Trincomalee has a much smaller population (412,000) than Jaffna (608,000).  However, Jaffna is more densely populated than Trincomalee, which is a multi-ethnic society whereas Jaffna has a predominantly Tamil population.

The Government has invested heavily in the development of infrastructure; utilities are now available even in the remote areas of the North and the East thereby significantly improving the living conditions of the communities. Yet, attention to IDPs and matters related to resettlement and rehabilitation have not received adequate consideration.  There is considerable emotional stress as families try to re-establish family connections.  Uncertainty is high as people need to rebuild life and livelihoods from scratch - putting behind them life in the camps.  The situation is particularly difficult for children born in the camps (i) who know no one else and now have to integrate with the rest of the community; and (ii) have to understand how children outside the camps have been brought up.  There are also issues relating to the re-integration into the community especially of ex-combatants, and families with missing family members.

The project: The Project, Catalytic Support to Peace building in Sri Lanka  with four Outcomes was conceived to assist the Government of Sri Lanka by providing an integrated package including secured land and services for resettlement, with an underlying policy framework to provide a non-discriminatory, fair, just, and equitable solutions to IDPs, assist in securing the original lands of IDPs. The Project sought to create a ‘conducive environment for displaced persons to return, resettle and integrate into the area’ by having inclusive access to quality services, and providing secure and inclusive livelihoods.

This evaluation was limited to the interventions implemented under one of the four outcomes (Outcome 4) - Catalytic support to Peace-Building Programme by UNICEF, UNDP and UN-Habitat and targeting resettled communities in districts of Jaffna (in Telippalai and Kopay Divisional Secretariat Divisions covering 12 GN Divisions) and Trincomalee (in Muttur DS Division covering five GNDs).

Evaluation scope and objectives: The scope of the evaluation was limited to the following three outputs:

- Output 4.1: Evidence based strategy for implementation of the National Policy on Durable Solutions for Conflict Affected Displacement is in place

- Output 4.2: Vulnerable households in the Northern Province supported to secure their land tenure rights

- Output 4.3: Targeted resettled communities have access to an integrated and sustainable package of socio-economic services to help them rebuild their lives

The objectives of the evaluation are to (a) assess the DAC criteria and the alignment of results with the Theory of Change, (b) analyse integrated approaches, synergies, multi-stakeholder coordination, monitoring and social accountability systems implemented and piloted by UN agencies; (c) document best practices and lessons learnt, and (d) provide recommendations to identify the optimal modality of delivery of resettlement support.

The Project was implemented by three UN Agencies:

- Output 4.1 by UNDP with the Ministry of Resettlement (MRRHRA);

- Output 4.2 by UN-Habitat with the Northern Departments of Surveys and Lands; and

- Output 4.3 by both UNICEF and UNDP through CSO Partners.

The 18-month Project started on 22 April 2017, but was extended for 24 months (up to 21 April 2019). The Project was implemented in 17 Grama Niladhari Divisions in Telippalai and Kopay DS Divisions (in Jaffna) and in Muttur DS Division (Trincomalee). The total number of families targeted by the project is 11,449 of IDPs.

Evaluation Methods used: Perspectives of inclusion, equity, gender and child safeguards as well as conflict sensitivity were assured in the evaluation. Ethical norms and principles were followed during the interviews.  Confidentiality was maintained and special care was taken when conducting interviews regarding child abuse and domestic violence.

The evaluation adopted a participatory approach and was conducted in an independent manner upholding evaluation ethics. Data an information needed for the evaluation were drawn from desk Review of documents, 25 Focus Group Discussions (FGD), 123 Key Informant Interviews (KII), 22 field and site visits, and telephone Interviews.

Evaluation focus: The evaluation design focussed on the key interventions implemented under the project, inter alia, development and implementation of the national policy (National Policy on Durable Solutions for Conflict Affected Displacement); actions for resolving land issues; and provision of services for resettled people (education, health and nutrition, WASH and protection), and livelihood support.

Limitations: Several limitations of the evaluation are important to note.  The scope of the evaluation is limited to Outcome 4.  Significant delays in starting and completing many interventions has precluded the examination of potential outcomes. Lack of a final report and comprehensive progress reports as well as the lack of output-based budgets/expenditure and incomplete database of beneficiaries was also a constraint.  The Theory of Change reflected limited interventions. These constraints have made it difficult to conduct a fuller examination of the Terms of Reference of the evaluation.

Project outputs and achievements:  Summarised below are the major achievements and shortcomings of the Project.

Output # 4.1 – The National Policy on Durable solutions for Conflict- Affected Displacement was launched in March 2019. Although policy development has taken about two years, the Ministry of Resettlement as well as higher authorities in the Provinces are appreciative of the assistance extended by the Project and are well informed on the elements of the Policy. The Project and its interventions are well-aligned with the Policy.  Awareness and education on the Policy are on-going.

Output # 4.2 –The Project surveyed 26,244 land parcels and prepared 12,619 LDO diagrams. The Project facilitated issuance of 8,884 land permits. The title-deeds have provided the holder an instrument to seek bank loans and to access other financial resources thus making the returnees self-reliant. The Project also facilitated allocation of new lands [about 0.05 ha (20 perches)] to those without lands.

Output # 4.3 – This output has helped resettled communities to have access to an integrated and sustainable package of socio-economic services to help rebuild their lives.

Education: The Project supported eight good quality schools in the Jaffna District and four in the Trincomalee District. The Early Childhood Development programme supported five and six pre-schools in Jaffna and Trincomalee respectively.

In the formal education sector, schools have been refurbished conforming to MoE standards. Resource materials for enhancing quality of learning and the achievement of learning outcomes have been developed. School Self-Assessments (SSA) have been completed. School Development Plans have been drawn up.  However, the availability of teachers, which is the responsibility of the Government, has been uneven. Improvements are needed on teacher training, active teaching and learning methodologies, integration of service sectors targeting the most vulnerable children, and teachers’ awareness on behaviour management in the classroom, abuse against children, and child safety and disaster preparedness.

In general, essential learning competencies have not been assessed by most teachers. The school curriculum focuses on preparing students for Grade-5 scholarship examination, rather than competency-based learning.

Improvements in the Early Childhood Development sector are impressive. Ninety-seven per cent (97%) of children aged 3-5 are enrolled in a pre-school and most of the pre-schools are within 10 minutes of travel time.  Pre-schools have a conducive learning and play environment. The infrastructure as well as the learning and play environment have been well maintained.

Health: The Project’s interventions in health are well recognised and appreciated.  In general, Mothers’ Clubs are functioning effectively, and are able to address matters relating to child care, nutrition, domestic violence, leadership and child protection. There is evidence of positive changes to health and welfare of children and expectant mothers.

Upgrading the hospitals and ancillary services at Telippalai, Muttur and Sampur has shown positive results. Establishing a well-equipped and operational Baby Care Unit at Telippalai has reduced the pressure on the Jaffna Hospital. Returnees now have ready access to better health care. The rural health care staff is better trained and equipped to handle health concerns of the returnees.

Water and Sanitation: Work in the pre-school WASH is generally satisfactory.  Children have adequate, comfortable, and age-appropriate sanitation facilities with water. The toilets and water supply are well-maintained, and body hygiene and hand-washing are satisfactory. The evaluation team noted that children act as agents of change by influencing the parents and siblings in hand washing. In schools, students have adequate, comfortable, age-appropriate and gender-sensitive sanitation facilities with accessible water. Body hygiene and hand-washing are satisfactory.  Provision of toilets within the households has changed the habits of people.

Menstrual Hygiene Management has been satisfactory. Both girls and boys have received MHM training, and are attuned to manage emergency menstrual situations. MHM training has improved school attendance of girls, and contributed to changing socio-cultural attitudes and beliefs related to menstruation.

Ground water discharge: The Project has supported ground water recharge pits in selected households. However, the beneficiaries’ understanding of the concept and the value of these interventions remains limited.  The Project has influenced the Kopay Pradesheeya Sabha to enact regulations to the effect that all households with more than 92 square metres roof area should construct a recharging pit.

Protection Services:  The Project has been able to revive community-based protection mechanisms with the active support of the Grama Niladharis, Community leaders, prelates of religious places, and others. Work has been carried out closely with child care staff and the Police. The Project has strengthened the Village Child Development Committees (VCDCs) to deal with child protection issues, and reporting of abuses is now better. VCDCs were found to be effective, and working closely with the relevant agencies.

The Project established a Children’s Desk at Telippalai Base Hospital and a Women’s and Children Desk at the Sampur Police Station. These have improved protection and psychosocial counselling services to children and women.

The Project provided psychosocial care, and worked in tandem with Psychiatric units of the hospitals and other relevant agencies. These activities have changed the mind-set of people, and have dispelled misgivings of the community on how to identify psychosocial disorders and sources for redress. Overall, the Project interventions have improved the psychological and mental health of the conflict-affected people. However, the future of a cadre of well-trained Psychosocial Counsellors built by NGOs in the districts is uncertain.

The Community Centres of the Project established various committees and fora, often with overlapping functions thus confusing the community of their functions.   Instances of discontent within RDS arising out of caste and religious discrimination have been reported. . The utility of the Community Centres has also been questioned by the community as there have been no activities to promote social cohesion.

Livelihood interventions:  These were primarily intended to guarantee secure and inclusive livelihoods for the resettled populations. The interventions included: homestead agriculture and animal husbandry, support the Soodaikuda Fisheries Society (Muttur), support to producer groups, and support to ‘micro-enterprises’ (Youth Enterprises).

Overall, there has been an inordinate delay in implementing the livelihood component, with many receiving the assistance package rather late in the Project. A fuller examination of Youth Enterprises was not possible due to delayed start of the enterprises.  Notwithstanding this, it is generally recognised that these ‘enterprises’ have increased family income.  In most cases, homestead agriculture and small-scale animal husbandry are able to only supplement family incomes.  This has however increased egg consumption has increased in the households. The beneficiaries face difficulty in accessing extension services.

Although beneficiaries have been trained in and helped with the preparation of business plans, in most instances, these plans have not been used for growing the businesses or seeking bank loans. A majority of the enterprises are not registered with the relevant authorities.  The Project has made significant investments in the construction and renovation of economic infrastructure, including the establishment of a 50 MT capacity seed paddy processing centre for Murutham Seed Growers. Aside from one milk collecting centre, other enterprises were not functional yet.  It was therefore too early to make an assessment.

Overall, the Project’s interventions have been gender-sensitive, and the returnees have grasped the fundamentals of gender equality. Project Partners have been sensitized on adopting gender-sensitive approaches. Women-headed families are better informed now on gender-based violence.  Reporting of gender-based violence has improved. Women have been weaned away from micro-credit and directed to seek loans from banks. Animal husbandry options offered by the Project have also become the responsibility of women.

In regard to Project management, the Project identified the need to deliver an integrated package of services backed by a Policy and land tenure interventions. A full demonstration of the effectiveness of the package was not seen due to delays in delivery and implementation.

The Project was managed by three UN agencies using a suite of CSOs. Although the implementation model is appropriate, implementation has suffered due to inadequate coordination amongst UN Agencies, between UN agencies and CSOs and amongst CSOs as well as between the two districts. The Project’s premise of setting up a close dialogue between the implementing agencies has not been fulfilled. The interaction with state agencies was activity-based. Project’s district level staff and the implementing Partners had little understanding of the Policy work. Implementation also suffered due to lack of a single ‘Project Manager’.  Project’s monitoring and evaluation remains weak.

Project performance: The performance of the Project on a scale of 1 to 4 can be summarised as follows:

- Relevance of the project: ‘Highly Satisfactory’ (4).

- Effectiveness of the Project: Satisfactory (3).

- Efficiency of the Project: Less-than-Satisfactory to Satisfactory (2.5).

- Sustainability of the Project: Less-than-Satisfactory to Satisfactory (2.5).

Lessons Learnt: There are seven key lessons from the evaluation.

- Theory of change:  A more realistic ‘theory of change’ needs to be developed for such short duration projects.  More realistic pathways of change need to be articulated for such time bound projects.

- Project design:  More effort and thought should go into the designing of the interventions – drawing on the lessons learned from similar interventions tried out earlier in Sri Lanka itself and elsewhere.  Also, the interventions should fit into more comprehensive medium term strategies that should be developed for the different areas of work.

- Implementation Modality: Collaboration between Government partners (e.g. MoE, Dept. of Health) and UN agencies has contributed to effective implementation. Operating through CSOs can be made more effective by having a closer collaboration and integration as well as sharing of experiences between CSOs both inter and intra districts.

- Beneficiary Selection: Applying a set of transparent and well defined criteria has resulted in the identification and selection of, by and large, a majority of well deserving returnees.

- Psychosocial care:	The Project has demonstrated the value of psychosocial care in the post-conflict context as a prelude to providing other forms of assistance, and should constitute an essential component of similar projects.

- Community involvement and ownership:  Community ownership is critical for such projects to be sustained.  Consultations with the communities to assess their needs, the formation of various community-based groups, and the engagement of volunteers go a long way in ensuring effective implementation of projects.

- Sustainability: Questions of sustainability surround many of the Project’s interventions.  In some of the cases, such as the building of health infrastructure, the maintenance and upkeep have become the responsibility of the government itself.  However, in other cases, such as with psychosocial counselling, care should be taken upfront to plan ways of continuing with the service once the project funding stops.

Recommendations: Recommendations relating to (i) Project strategy, (ii) Programme strategy; and (iii) Reporting, monitoring, evaluation and learning strategy are listed below:

Project strategy: Appropriate phasing out strategies should be developed for education, WASH, psychosocial care, and enterprise development in particular.  Mechanisms should be evolved for better interaction amongst UN Agencies, amongst Partners, and between districts in order to improve delivery and quality. The appointment of a ‘leader’ who could coordinate the work programme might be an effective way to improve coordination and implementation. The duration of such a Project should be sufficient to ensure proper planning, design, execution and evaluation of outcomes, if not impacts, with attention to scaling up.

Programme strategy: Specific recommendations are summarised below:

- National Policy: Greater awareness about the Policy needs to be created particularly at the local government levels and among communities at the grassroots level. More work is needed to translate Policy into action including enhancing capacities of agencies to translate Policy into well directed and coherent sets of actions, addressing significant caste-based discrimination especially among the IDP communities, and addressing issues of the ageing population amongst the returnees.

- Education:  Efforts should be made to improve training of teachers with Training of Trainers at site to reduce cost, quality of inputs into ECD as well as teaching and learning, , and coordination between the service sectors of health, child protection.  Better psychosocial support and livelihood support  to affected children and families would have enhanced the quality of education delivered.

- WASH:	 The Project should pay more attention to detail in regard to WASH facilities including fencing in schools, establishing waste water and solid waste management systems, and extending regular MHM training to children, particularly 13/14 year-olds who become adolescents.

- Land Tenure:	A suitable post-project arrangement should be put in place to facilitate communities to convert their temporary land permits to deeds.

- Psychosocial care: The UN agencies should supplement Government efforts in rehabilitation of affected communities through provision of psychosocial support and mental health care.

- Protection Services: Effectiveness of the Project can be enhanced by linking Mothers’ Clubs, Women’s Committees, Children’s Clubs, Children’s Societies and VCDCs to the Child Protection Units.

- Livelihood: It will help to reassess the appropriateness of small scale agriculture and animal husbandry ventures for individuals and communities, as against collective ventures, consider providing extension services post-project, and offer the material support in two stages, so that those who show promise can be further supported in the second stage.  It will be necessary to extend further technical and managerial assistance to YED programmes given that the commencement has been delayed, business plans have not been fully understood, and, in some instances, business registration has not been completed.

- Economic infrastructure:	UNDP should urgently address concerns expressed by the communities of alleged malpractices relating to the Seed Paddy Facility in order to avoid reputational risks to UN Agencies.  It should continue to extend technical and managerial assistance to operate the Seed Paddy Facility as well as milk chilling plants for at least six months until teething problems are resolved.

- Integrated Approach adopted by the Project:	Improved coordination amongst implementing and UN agencies backed by a rigorous monitoring mechanism can further enhance the effectiveness of the integrated approach used in the Project.

Reporting, monitoring, evaluation and learning strategy:  A more rigorous and systematic M&E protocol that identifies delays in implementation, highlights stakeholder concerns and strengthens institutional linkages is needed to improve implementation.  Equally important is to demonstrate better the Project’s visibility and achievements. An evaluation plan should be built into the design of the Project itself.

In conclusion, the Project has made significant contributions to promoting the wellbeing of IDPs and has supported re-integration of them with the community. More however needs to be done, and adopting the recommendations can contribute to sustaining the efforts of the Project.  It is nevertheless important to recognize that the commitment of the Government and active engagement of the community, are essential for maximising the contribution of any form of catalytic support to peace building efforts.

# Introduction

Development Context

The civil conflict which started in 1983 has been the single most debilitating factor affecting the people of Sri Lanka. The areas directly affected by the conflict are Vavuniya, Mannar, Kilinochchi, Mullaitivu in the Jaffna District in the Northern Province and Trincomalee, Batticaloa and Ampara districts in the Eastern Province.

In 2007, the Government of Sri Lanka liberated the Eastern Province.  Since then, almost all the displaced persons have been resettled.  However, resettlement of Internally Displaced Persons (IDPs) following the liberation of the Northern Province in 2009, has been on-going, albeit slowly.  The nature and magnitude of the problems in the Northern Province are different from and surpass those in the Eastern Province.

Developments in the Post Conflict Era

It is estimated that during the three decades of conflict, nearly 400,000 people were displaced. At the end of the conflict in 2009, it was estimated that there were about 253,000 IDPs in temporary shelters, provided with water supply and sanitation facilities, food subsidies and healthcare. However, the conditions in most temporary shelters were cramped, and people lacked privacy.

In the post-conflict era, the Government has invested heavily in the development of infrastructure such as roads, hospitals, administrative buildings, schools, electricity, telecommunication and water supply.  As a result, utilities are now available even in the remote areas of the North and the East. While this has contributed significantly to improving the living conditions of the communities, attention to IDPs and matters related to resettlement and rehabilitation have not received adequate consideration.  The return of displaced people living with host families and in welfare centres, estimated to be about 43,000 in 2016, has been slow.  More needs to be done for improving livelihoods, restoring civil, political and other rights and finding durable solutions for the IDPs.   Of particular societal concern is the situation of an estimated 40,000 female-headed households displaced by conflict in the Northern Province.

The Resolution of the Human Rights Council

The pace of returnees has been slow for a variety of reasons.  There remain unresolved issues relating to land titles and ownership.  Provision of adequate ancillary services has been exacerbated by geographic isolation.  Poor coordination amongst state agencies involved in resettlement has led to problems with the provisioning of water, sanitation and hygiene.   In some pockets, lack of social cohesion has given rise to tensions between neighbouring communities.  There has also occurred marginalisation of some groups.  In particular, concerns have been raised on issues relating to violence including sexual and gender-based violence (SGBV), and the lack of suitable livelihood options for the returnees to re-commence a normal life.  Policies focussing on various components of the transitional justice agenda show gaps.  The capacity and available expertise to address these concerns are limited.

In October 2015, the Human Rights Council adopted a resolution titled ‘Promoting reconciliation, accountability and human rights in Sri Lanka’. The resolution welcomed the commitment of the Government of Sri Lanka to undertake a comprehensive approach to dealing with the past, and set the ground for the Government to move forward with a nationally-owned and victim-centric transitional justice process that addresses the needs of the people of Sri Lanka and advances accountability and reconciliation for all.  In particular, the Resolution called upon the International Community, including the United Nations, to support the Government for IDPs.

The Human Rights Council Resolution underscores the need for addressing many of these deficiencies and gaps as a priority.  It calls for putting in place credible and robust processes, including the establishments of strong institutions to fulfil Government’s commitment towards ensuring ‘ethnic and religious reconciliation’.

Contextual differences: Jaffna and Trincomalee

There are contextual differences in the two Provinces where the Project has been implemented.

From the data of 2017, Trincomalee has a smaller population (412,000) than Jaffna (608,000). The population density in Jaffna and Trincomalee are 654 persons/km2 and 163 persons/km2, respectively.

Trincomalee is a multi-ethnic society whereas Jaffna has a predominantly Tamil population (Table 1.1).

Table 1.1 : Ethnic composition (2012 Census)

| Ethnicity | Jaffna | Trincomalee | Sri Lanka |
| --- | --- | --- | --- |
| Sinhalese | 0.4 | 26.7 | 74.9 |
| Sri Lankan Tamil | 98.9 | 30.7 | 11.2 |
| Indian Tamil | 0.3 | 0.3 | 4.1 |
| Sri Lankan Moor | 0.4 | 41.8 | 9.3 |
| Others | 0.0 | 0.4 | 0.5 |

Religion in the two Provinces closely follows ethnicity (Table 1.2).

Table 1.2: Religion (2012 Census)

| Religion | Jaffna | Trincomalee | Sri Lanka |
| --- | --- | --- | --- |
| Buddhist | 0.4 | 26.2 | 70.1 |
| Hindu | 82.8 | 25.9 | 12.6 |
| Islam | 0.4 | 42.0 | 9.7 |
| Roman Catholic | 12.9 | 3.8 | 6.2 |
| Christian | 3.5 | 2.0 | 1.4 |

Both Jaffna and Trincomalee report a higher proportion of population below the poverty line than the national average of 4 per cent.  However, Trincomalee reports much higher rates of crude birth rates, and higher levels of stunting among children than Jaffna.  A lower proportion of women in Trincomalee complete secondary schooling, and enjoy exposure to media than in Jaffna (Table 1.3).

Table 1.3 : Other indicators for Jaffna and Trincomalee

|  | Jaffna | Trincomalee | Sri Lanka |
| --- | --- | --- | --- |
| Poverty: |  |  |  |
| Poverty headcount Index (%) 2016 | 7.7 | 10.0 | 4.1 |
| Crude birth rate (2017) | 14.9 | 20.4 | 15.2 |
| Total Fertility Rate (2016) | 2.1 | 2.3 | 2.2 |
| Nutritional status |  |  |  |
| Low Birth weight babies (%) | 6.2 | 15.0 | 15.7 |
| Height-for-age below 2 SD: children under 5 (stunted) % | 13.7 | 15.5 | 17.3 |
| Education: |  |  |  |
| Female population completed secondary school (2016) | 18 | 13.6 | 20 |
| Other indicators: |  |  |  |
| % women 15-49 who have experienced at least one violence | 38.9 | 29.4 | 16.6 |
| % of ever-married women 15-49 who have no access to newspaper, TV or radio at least once a week | 12.5 | 28.1 | 11.1 |

Situation in regard to IDPs

At the planning stage, the Project noted the following:

- There is low rate of returnees due to lack of services, uncertainty on land titles, lack of societal cohesion and conflicts with the neighbourhood, geographic isolation – all of which makes it difficult to provide the required services, prevent exclusion/ marginalisation of some groups, and address other societal issues including SGBV;

- There is no long-term resettlement plan; general lack of coordination between state agencies; inadequate capacity to provide the services; and lack of data on the protection needed for returnees;

- Poor living conditions (e.g. nutrition and hygiene); lack of livelihood support to bring the returnees to normalcy; and lack of social protection including psychosocial care.

It is against this backdrop that the two-year joint project, “Catalytic Support to Peace building in Sri Lanka” was launched in April 2017 to provide an integrated package for resettlement, within the policy framework, offering non-discriminatory (e.g. on the grounds of ethnicity, religion, caste, gender or age), fair, just, and equitable solutions to IDPs, assisting in securing the original lands of IDPs or giving new lands with legal titles, and ensuring access to a suite of supporting actions including livelihoods, psychosocial care, utilities, schools, and health.

# Project Description

## Project Objective

The overall objective of the project is: “Early confidence building measures build trust and contribute positively to peace-building in Sri Lanka.”

The Project sought to create a ‘conducive environment for displaced persons to return, resettle and integrate into the area’ by multi-pronged improvements in four areas, viz:

- Inclusive access to quality services: Returning/Resettled communities have equal access to quality social services to move towards normalcy with support such as psychosocial care including mental well-being, health care, education, access roads, community spaces etc.

- Secure and inclusive livelihoods: Returning/Resettled communities including marginalized people have secure and inclusive livelihoods for long-term socio-economic development to help in re-establishing them in the society;

- Effective collective action: Engage the socially disadvantaged communities in collective and constructive dialogue for social and economic actions by restoring community cohesion; and

- Secure and protective society: Returning/Resettled communities are free from all forms of violence (e.g. physical, psychological, sexual, and neglect) and living in a cohesive society

## Baseline Indicators

The Centre for Poverty Analysis (CEPA) was entrusted to carry out a detailed needs assessment in early 2018; it was required to set up a baseline, develop a Monitoring, Evaluation and Learning (ME&L) plan and implement the ME&L plan for the project. CEPA also developed a Theory of Change for Output 4.3. The needs assessment reflects the needs of the returnees in the Grama Niladhari divisions selected for implementation of Output 4.3 of the Project, and has been used in selecting project interventions to meet the needs of the community.

Baseline data available relate to living conditions and household assets, livelihood types, occupations, health services, pre-school education, vocational training, transport services and roads, waste management, electricity, access to public structures, discriminations in accessing services, GBV etc. Likewise, CEPA has undertaken an end-line survey, and have reported on the results. Again, the survey is confined to Output 4.3 (cf. Section ‘Purpose and Scope of the Project’).

Since the beneficiaries were selected after the baseline study, some important indicators relevant to the beneficiaries are not available (e.g. income at the beginning of the Project) in these surveys.

## Implementation timelines

The original project period for implementation was 22 April, 2017 to 21 April, 2019. However, activities relating to Outputs 4.1 and 4.3 were on-going at the time of the evaluation in June, 2019. The Project has no formal extension of time; work is carried out with funds advanced to the Partners, whose contracts have expired.

## Key Stakeholders and beneficiaries

Key Stakeholders

The key stakeholders are listed below:

- Ministry of Resettlement, Colombo

- District Secretaries of Jaffna and Trincomalee

- Divisional Secretaries of Telippalai and Kopay (Jaffna), and Muttur (Trincomalee)

- Provincial/Zonal Directors of Educations

- ECCD Officers

- Pre-school and School teachers; School Principals

- Pre-school children and School children including Adolescent female students

- Regional Directors of Health

- Medical Superintendent /MoH /PHN /PHI, Telippalai and Muttur

- Officers-in-Charge and Women’s Desk Officers of Police Stations (Telippalai & Sampur)

- Provincial Dept. of Irrigation (Jaffna)

- Dept. of Probation and Child Care Services

- Child Protection Authority

- Development Officers from DS Office, Telippalai and Muttur

- Grama Niladharis in the Project area

- Provincial Land Commissioner, Northern Province

- Provincial Survey Department, Northern Province

- Small Industries Bureau, District Secretariat, Jaffna and Trincomalee

- National Water Supply & Drainage Board, Jaffna

- Provincial Department of Agriculture

- Provincial Dept. of Animal Production and Health

- Provincial Department of Fisheries

Beneficiaries

The direct beneficiaries are returnees to the settlements in Telippalai and Kopay DS Divisions (in Jaffna) and in Muttur DS Division (Trincomalee). The total number of families targeted by the project is 11,449 of IDPs returning to their original lands or those being resettled.

## Expected Results

Theory of Change

The Project has developed a detailed Theory of Change; however, this is confined to Output 4.3 only, and does not show relationships with the other Outputs.

Four specific results were identified by the Project:

| Result # 1 | Significant progress made in the implementation of the Government’s commitment on transitional justice as expressed in the UNHRC Resolution |
| --- | --- |
| Result # 2 | Public display greater awareness and willingness to engage constructively in the peace-building process |
| Result # 3 | Key state institutions and processes strengthened through provision of technical support |
| Result # 4 | UN catalytic engagement with resettlement and durable solutions has supported wider political transition, peace-building and reconciliation efforts in Sri Lanka |

This evaluation is confined to Result #4 which envisaged the following three outputs:

Output 4.1: Evidence based strategy for implementation of the National Policy on Durable Solutions for Conflict Affected Displacement is in place

Output 4.2: Vulnerable households in the Northern Province supported to secure their land tenure rights

Output 4.3: Targeted resettled communities have access to an integrated and sustainable package of socio-economic services to help them rebuild their lives

## Project Management

Project locations

The Project has been implemented in 17 Grama Niladhari Divisions (GNDs) in Tellippalai and Kopay Divisional Secretariat Divisions in Jaffna and Muttur Divisional Secretariat Divisions in Trincomalee. The implementing GNDs are given below:

Telippalai DS Division

- Kankasanthurai South

- Kankasanthurai West

- KankasanthuraiCentre

- Palai Veemankamam South

- Palai Veemankamam North

- Palali North

- Palali East

- Palali South

- Thyiddy South

- Varuththalaivilan

- Vasavilan

Kopay DS Division

- Valalai

Muttur DS Division

- Kadatkaraichchenai

- Kooniththivu

- Navaratnapuram

- Sampur East

- Sampur West

Implementation arrangements

Project implementation arrangements vary according to the Output.

Output 4.1 is directly implemented by UNDP through the Ministry of Resettlement. For this purpose, UNDP has established a cell in the Ministry.

Output 4.2 has been implemented by UN-Habitat through the Northern Department of Surveys and Department of Lands. The Project work has been in the larger Northern Province with some inputs into the project areas.

Output 4.3 has been implemented by both UNICEF and UNDP through CSO Partners, who have been formally contracted by the UN Agencies. The implementation responsibilities of agencies are presented in Annex 2.1.

# The Evaluation

## Purpose and Scope

The purposes of this final evaluation are (i) to assess the extent to which Outcome # 4 of the project, Catalytic Support to Peace Building Programme, has achieved the expected results, (ii) analyse the implementation approach adopted, and (iii) make suitable recommendations for supporting resettlements in Jaffna and Trincomalee districts.

Specific Objectives:

The following are specific objectives of the evaluation:

- Assess the Relevance, Effectiveness, Efficiency, Impact and Sustainability (the DAC criteria) of interventions implemented and results achieved in line with Theory of Change and results framework;

- Analyse the integrated approaches, synergies, multi-stakeholder coordination, monitoring and social accountability systems implemented and piloted by UN agencies;

- Document the best practices and lessons learnt from the project and disseminate the learnings among all right holders and duty bearers to ensure accountability of the findings; and

- Provide recommendations to identify the optimal modality of delivery of resettlement support in line with the Policy on Durable solutions and Peace building Priority Plan. The Terms of Reference for this evaluation is at Annex 3.1.

This evaluation has beenlimited to the interventions implemented under Outcome 4 (Catalytic support to Peace-Building Programme) by UNICEF, UNDP and UN-Habitat and targeting resettled communities in districts of Jaffna (in Telippalai and Kopay Divisional Secretariat Divisions covering 12 GN Divisions) and Trincomalee (in Muttur DS Division covering five GNDs).  The evaluation focussed on the following three outputs:

Output 4.1: Evidence based strategy for implementation of the National Policy on Durable Solutions for Conflict Affected Displacement is in place

Output 4.2: Vulnerable households in the Northern Province supported to secure their land tenure rights

Output 4.3: Targeted resettled communities have access to an integrated and sustainable package of socio-economic services to help them rebuild their lives

## Evaluation Principles

The physical reconstruction in both Jaffna and Trincomalee is impressive.  It is difficult for a first-time visitor to these regions to imagine the extent of devastation caused by the conflict and the Tsunami.  The new buildings and roads mask the real tragedy that the people have had to face.

The evaluation took particular notice of the circumstances observed during the Scoping Mission in March, 2019.  It took special notice of the high insecurities in the lives of people and families that are being rehabilitated and resettled. Given this, the evaluation has considered the elements and innovations that the UN agencies have introduced to address the special needs and conditions of people living in these two districts.  It is important to keep in mind the many insecurities in the lives of people and families being rehabilitated and resettled in the two populations.  There is considerable emotional stress as families try to re-establish family connections.  There is high uncertainty as people need to rebuild life and livelihoods from scratch - putting behind them life in the camps.  The situation is particularly difficult for children born in the camps (i) who know no one else and now have to integrate with the rest of the community; and (ii) have to understand how children outside the camps have been brought up.  Additionally, there are issues relating to the re-integration into the community especially of ex-combatants, and families with missing family members.  Latent social divisions are beginning to surface as well.

Perspectives of inclusion, equity, gender and child safeguards as well as conflict sensitivity have been assured in the evaluation by adopting the following:

- obtaining consent from all participants, particularly child participants;

- incorporating child-friendly interview techniques;

- collecting data disaggregated by sex, ethnicity, and age and conducting interviews in the local languages;

- examining the extent to which elements of gender responsive programming have been incorporated into the design; and

- assessing efforts at gender mainstreaming in budgeting, analysing issues, planning and implementing activities that target both men and women, selection of beneficiaries, reporting, and analysis of data, disaggregated by sex.

Ethical norms and principles have been followed during the interviews.  Confidentiality was maintained and special care was taken when conducting interviews regarding child abuse and domestic violence.

The evaluation was conducted in an independent manner upholding evaluation ethics. Special emphasis was placed to respecting human rights and differences in culture, customs, religious belief and practices while being mindful of gender roles, ethnicity, ability, age, sexual orientation, language and other differences when carrying out the evaluation.

The evaluation adopted a participatory approach, combining self-reporting with external validations, extensive discussions and feedback loops with the respondents, which included women, men, boys and girls.  In soliciting the engagement of groups, the facilitators first explained the purpose of the meeting, and sought their cooperation, commitment and inputs into the evaluation.

## Evaluation Design

The evaluation design focussed on the following key interventions implemented under the project.

- Actions for implementation of the national policy (National Policy on Durable Solutions for Conflict Affected Displacement);

- Actions for obtaining state lands for resettlements;

- Improvements to education of resettled people;

- Health and nutrition of resettled people;

- Child protection aspects relating to resettled people;

- Water, Sanitation and Hygiene aspects of resettled people;

- Livelihood support provided to resettled people, including ‘enterprises’;

- Supporting infrastructure development (community centres, roads, agro-wells etc.)

The interviews were based on a stratified purposive sampling to ensure (i) equal representation of girls and women; (ii) representation of different occupations under the livelihood promotion schemes; and (iii) representation of different age groups.

## Evaluation Approach and Methodology

The evaluation has adopted a participatory and inter-active approach. A mix of quantitative and qualitative methods and techniques in terms of their relevance to the characteristics or performance of Outcome # 4 was used to collect data and information. Qualitative data were selected from specific sources of information including primary and secondary information related to the Project.

The data collection methods and tools were customized to obtain answers to the evaluation questions stipulated in the Terms of Reference under the given criteria (Relevance, Efficiency, Effectiveness, and Sustainability, and cross cutting issues such as Gender, visibility, etc.). Data collection was conducted in an independent and objective manner and followed a participatory and ethically accepted approach, ensuring participation of males and females, elderly, people with special needs and youth, children and addressed accountability, equity and non-discrimination.

#### Evaluation Methodology and Tools

Data an information needed for the evaluation were drawn from different sources using the following tools:

- Desk Review of documents

- Questionnaires

- Focus Group Discussions (FGDs)

- Key Informant Interviews (KIIs)

- Field and site visits

- Telephone Interviews

Desk Review of documents

Documents relating to the Project, its implementation, progress review etc. were reviewed. A list of documents reviewed is in Annex 3.2. There is no terminal report of the Project.  Information was collected from (i) the progress reports made available, (ii) the presentations made to the evaluator during the Scoping Mission in March 2019, and (iii) interviews during the field mission in June 2019.

Questionnaires

A series of questions were developed to assess the relevance, effectiveness, efficiency (including management flexibility; value for money), equity (inclusiveness and participation, conflict sensitivity, gender sensitivity, and sustainability. These questions were used as tools especially for KIIs and FGDs.

Focus Group Discussions (FGD):

Altogether 25 Focus Group Discussions covering all project interventions were held, as against 18 that were proposed in the Inception Report.  The FDGs covering all stakeholders and beneficiaries ensured gender–balance and equal participation by both males and females (specifically female-headed households).  They helped to assess, in particular, the extent to which resettled women, youth and children have participated in and benefitted from the Project. The FDGs were convened by the Project’s implementing Partners, and the discussions were based on a structured set of questions. A summary of FDGs is given in Annex 3.3.

Key Informant Interviews (KII):

One hundred and twenty-three (123) Key Informant Interviews were held, using a semi structured interview framework. The list of interviewees is in Annex 3.4.

Field Visits:

Twenty-two field visits were made to observe project achievements/results and to seek additional information from the beneficiaries. Visits included: pre-schools, schools (rehabilitation and refurbishing including WASH facilities); Base Hospital, Telippalai and Muttur Hospital (for infrastructure development); multiple-use community centres; Women’s and Children’s Desks; water recharging mechanisms in Jaffna and latrines/water connections in Trincomalee; Seed Paddy Facility of Marutham Seed Growers’ Society; Muttur East Fisheries Union Co-op Ltd; Milk chilling Centres operated by the Muttur East Dairy Development Coop Society; and resettlement areas in Telippalai, Kopay and Kankasanturai (Jaffna) and Sampur (Trincomalee). The Team visited Patalipuram resettlement village which has received little attention from the Government. In addition, 25 project beneficiaries who received assistance for ‘enterprise development’ were visited to observe their enterprises and to seek their views. A full list of visitations is in Annex 3.5.

Telephone Interviews:

Since there is no end-line survey to assess results of the livelihood/enterprise component, a telephone survey of about 20% representative sample of the beneficiaries from each ‘vocation’ was conducted using a structured questionnaire.

## Limitations

The final evaluation was limited to Outcome # 4 of the Project, ‘Catalytic Support to Peace Building Programme’. The evaluation has therefore not related its findings to the main Project results and outcomes.

The Project, originally of 18 months duration, was later extended to 24 months. This is a very unrealistic time-frame, given the depth of work involved. As it turned out, many of the Project interventions have not been completed.  A reasonable time has not elapsed between completion and the evaluation to examine even any potential outcomes, let alone impacts. Indeed, some activities were on-going at the time of evaluation, largely because of delayed starts. The evaluation team has not been able to comment on the effectiveness of the holistic model to bring about durable solutions to the resettled communities because implementation of interventions has not been completed.  A better picture could have been captured if the evaluation was undertaken after completion of all activities.

Added to this situation was the non-availability of the Project’s final report.  As a result, the evaluation team has not been able to assess the documented achievements. The only Progress Reports available are from CEPA, which reported on a limited number of Outputs. Some of the Project implementing Partners appear to have produced a ‘final report’ on their responsibilities as per their contracts.  However, these were not made available to the Evaluation Team.

The relative importance of outputs vis-à-vis Outcome # 4 could not be examined as output-based budgets or expenditures had not been maintained by the Project.

A telephone interview of enterprise development beneficiaries was planned but only a limited number of beneficiaries from Trincomalee could be contacted as contact details of beneficiaries from Jaffna were not available.

As a result of these limitations, the evaluation has not been able to fully address some items listed in the Terms of Reference ToR).  For instance, the ToR calls for recommendations to identify the optimal modality of delivery of resettlement support in line with the Policy on Durable solutions and Peace building Priority Plan and policy recommendations pertaining to resettlement solutions.  This has not been possible because of shortcomings in the modalities of implementation.  To begin with, the Policy itself was officially released only during the first quarter of 2019.  Its effectiveness at the ground level is yet to be determined.  Similarly, many of the deliverables have not been completed. As a result, only a limited exploration on the optimal modality of delivery has been possible. Similarly, the ToR calls for documenting best practices and lessons learnt from the project.  As many of the project interventions are still on-going and some are yet to start, the evaluation could not identify best practices.

Moreover, the Theory of Change focuses specifically on few outputs. Yet it identifies the important role of duty bearers, most of which remain to be fulfilled due to delays in implementation. This precluded a comprehensive assessment of the Theory of Change and attribution to the Project.

# Analysis of Findings in relation to Project Results

## Project Design

The Project, Catalytic Support to Peace-building in Sri Lanka, has the following four over-arching Outcomes:

Immediate Outcome 1:	Significant progress made in the implementation of the Government's commitment on transitional justice as expressed in the UNHRC Resolution

Immediate Outcome 2:	Public display greater awareness and willingness to engage constructively in the peace-building process

Immediate Outcome 3: 	Key state institutions and processes strengthened through provision of technical support

Immediate Outcome 4: 	UN catalytic engagement with resettlement and durable solutions has supported wider political transition, peace-building and reconciliation efforts in Sri Lanka

The evaluation is however confined to Outcome 4 only. It has therefore not examined the project logic and strategy in a holistic manner.

Gaps in Theory of Change: Outcome 4 and its three Outputs are logically constructed. The Theory of Change acknowledges that the change sought by the Project is dependent on full realisation of all four Outcomes. However, it notes that Outcome 4 “related to inclusive access to quality services is seen to carry more weight given the multiple sectors and components embedded within it.”  As a result, development of evaluation tools for some of the Outputs has been constrained.

An example is the Theory of Change for health, education and WASH (Outputs 4.3.2 to 4.3.4). These were to be evaluated based on three envisaged changes: (i) Enabling factors: targeted social service providers have appropriate governance system that enable functionality; (ii) Supply factors: key social services have the infrastructure, capacity and mechanisms to effectively meet the needs of the population, and (iii) Demand factors: communities have the capacity to monitor and advocate for quality social services in partnership with service providers, and strengthened linkages between community platforms and duty bearers in relation to targeted social services,  The assumptions give high priority to the role of the duty bearers: the Provincial Ministries of Health and Education and Local Government Institutions to deliver services and for social accountability.  Many of these assumptions have not been fulfilled especially for health, education and WASH.  Over the short duration of the Project, it was not possible to (i) ensure effective Government ownership and extension of adequate support (partly due to resource constraints, both human and financial), (ii) create all the necessary roads and other infrastructure, (iii) ensure that the existing public service delivery capacity is not overburdened, and (iv) strengthen linkages between community platforms and duty bearers in relation to targeted social services.

Furthermore, the Theory of Change has been of limited use in terms of identifying indicators. Additionally, many of the assumptions in the Theory of Change (developed in December 2017) are not fully reflected in the Risks developed by the Project sourced from the document prepared in May 2018 (see Table 4.1).

Risks:

The Project has identified several risks relating to the entire Project. Those relevant to Outcome 4 have been excerpted, and their current risk situation is in Table 4.1:

Table 4.1 : Updated risk analysis (Outcome #4)

| Original risk statement | Current status of the risk |
| --- | --- |
| Slow progress in physical return and resettlement in the released areas due to lack of basic and essential infrastructure facilities | This risk is now low; the Government, together with other development Partners are providing the basic infrastructure needed for the returnees. The plan for the current financial year is 12,000 housing units. |
| Absence of coordinated sustainable local economic development plans/strategies to ensure decent employment opportunities for resettled families of welfare camps and others | This risk remains medium. Investments and public-private partnerships for providing long-term employment opportunities have been slow. |
| Individuals, long dependent on relief and aid and externally supported livelihoods are likely to be resistant to risk-taking despite coming up with viable business ideas and plans. | This risk remains medium. Business coaching has not been very successful, and business plans developed for micro-enterprises have not been practically used. Linkages to financial institutions and marketing remain weak. |

GOSL Responsibility:

It was expected that during design and planning stages, GOSL’s commitment to operationalise Project’s inputs would be obtained. For instance, GoSL was to provide sufficient number of teachers to rehabilitated schools, ensure the required medical staff for upgraded health facilities, and for the newly-established Women’s and Children’s Desks. In some instances, these commitments, as with the Police, were not fulfilled.

## Output 4.1

Evidence based strategy for implementation of the National Policy on Durable Solutions for Conflict Affected Displacement is in place

This component is managed by UNDP and implemented by the Ministry of National Polices, Economic Affairs, Resettlement & Rehabilitation, Northern Province Development, Vocational Training and Skills Development and Youth Affairs (under the Prime Minister’s office). UNDP has established a cell in the Ministry with appropriate staff to facilitate work of this component. At the time of the evaluation, work was still in progress.

Under this component UNDP provided technical assistance towards the development of the Policy which included an extensive consultation process, awareness building on the Policy (on-going at the time of evaluation) and setting up a monitoring and evaluation protocol with the requisite capacity for assessing impacts.

An important expectation of the Policy is to ensure that all development work in the provinces fall within the framework of the Policy so that all stakeholders make an integrated effort for economic development, social integration, transitional justice and reconciliation.

The Policy sets out and guarantees rights of IDPs, refugee returnees and other persons of concern and to promote measures to address their immediate, medium and long-term protection and assistance needs for durable solutions to their problems. The Policy sets out principles and standards, conforming to the national laws and UN Guiding Principles on Internal Displacement and the Inter-Agency Standing Committee to be fulfilled by stakeholders in assisting displaced persons.  It documents the general principles, rights and entitlements, needs, concerns and perspectives of IDPs, and delineates the responsibilities of relevant state agencies and their partners. It identifies problems that need urgent attention (e.g. land tenure issues; landless people; providing shelter and basic needs; supporting livelihoods, ensuring justice and reparation, de-mining etc.). Following the formal launch of the Policy, the Ministry has established Steering Committees at National and Provincial levels to monitor the implementation of strategies set out in the Policy. Their observations are reported to the Inter-Ministerial Committee on Resettlement and the National Policy Committee chaired by the President.  The Policy was launched on 15 March, 2019, and is available in all three languages.

Project funds made available to the Ministry enables it to continue work at the ground level.  Additionally, work with the legal aid commission is also on-going.

Achievements and observations:

- Positive response: The Ministry is appreciative of the assistance received for this component, which has enabled the development of the Policy. During the gestation period of nearly two years, the Ministry as well as higher authorities in the Provinces were well informed on the elements of the Policy, and these are embedded in their daily routine; this is corroborated from evidence collected during the evaluation from the Provincial Authorities (e.g. District Secretariat, Divisional Secretariat etc.) wherein it was clear that these authorities worked within the framework of the Policy, although the Policy itself was not formally launched until March 2019. Thus, many of the initiatives of the Project fall directly within the provisions of the Policy.

- High value addition: ‘Value addition’ to the policy framework has taken place through leveraging complementary strengths of the project’s partners, who have experience on the needs of IDPs.  An important outcome has been that injuries from mines have been greatly reduced.   No injuries have been reported during the first quarter of 2019 indicating success of the de-mining awareness building programme which has been incorporated into the school curriculum as well.

- Well aligned and coherent actions: Several actions are well aligned with the Policy and can be attributed to the effects of the Policy development process.  These include, for instance:

  - the establishment of a Rehabilitation Centre by the Bureau of the Commissioner General of Rehabilitation for vocational and spiritual training of ex-combatants;

  - the promulgation of a new act on reparations (Office for Reparations Act, No. 34 of 2018);

  - the application of the official language policy for providing options for language of choice;

  - the establishment of District Reconciliation Committees (which include religious leaders); and

  - the integration of collaborative initiatives by national level NGOs such as National Peace Council, Office for National Unity and Reconciliation, Aequitas Legal, the Asia Foundation and the Centre for Policy Alternatives.

The Ministry’s resettlement work has followed the Policy framework, and this is reflected in some of the following actions:

  - provision of houses and purchase of land for landless families;

  - provision of health services and schooling (including making 1,500 temporary teachers permanent);

  - extending livelihood support of LKR 150,000/enterprise;

  - providing socialisation and spiritual guidance for the most vulnerable groups (including ex-combatants); and

  - efforts to reduce stigmatisation of ex-combatants.

According to the Assistant Director of Planning, DS Office Telippalai, the camps now have only less than 500 people. Most of them have not been able to return to their lands because the lands have not been released by the security forces.

- Need for greater awareness: Although the provisions in the Policy are generally known in the higher echelons of administration, there is a need to improve awareness amongst the second level of public service including those working in the villages (e.g. Grama Niladhari, Development Officer, Probation Officer etc.) so that the full effects of the Policy can percolate to the grass-roots level. The Project has developed a comprehensive module for awareness building; it includes aspects such as the objectives of the policy; need to ensure that returnees have appropriate humanitarian and development assistance; and reduce grievances of IDPs. These awareness programmes were being conducted even during the evaluation mission – it is therefore, expected that greater understanding of the Policy will result from these programmes. In support of this approach, Project has developed outreach materials.

- Weak monitoring: The Ministry is fully aware of the need to have a proper M&E mechanism and the importance of assessing impacts.  However, the Monitoring and Evaluation component is yet to be established. Work on establishing a database for monitoring is on-going. This will provide valuable information on matters germane to resettlements, and will be available online at both national and district levels.  Although mechanisms are not yet in place to assess the extent to which an integrated effort has been made for economic development, social integration, transitional justice and reconciliation, the District Secretariats and Divisional Secretariats are in the process of addressing this important requirement.

## Output 4.2

Vulnerable households in the Northern Province supported to secure their land tenure rights

This component was implemented by UN-Habitat in the Northern Province in partnership with the Survey Department, Land Commissioner General, Department of Land Settlement and the Registrar General’s Office.

At the end of the conflict in 2009, there were about 160,000 land claims or complaints, largely based on loss andlack of documents, land disputes and multiple ownership claims. Additionally, there were IDPs and refugee returnees who were landless and needing support.

In order to accelerate resolution of problems, the Government issued a special circular in 2013 (Accelerated Programme for Solving State Land Issues in the Northern and Eastern Provinces). Consequently, decisions had been made on 160,803 land parcels out of 167,778 land related claims. However, implementation of these decisions required a tremendous amount of work with human, material and time investments. Besides, the management of these activities is  institutionally and functionally fragmented.  A critical step was surveying and demarcating the plots as a survey diagram, produced through land surveillance. This needed the services of professional surveyors who had to physically visit each parcel of land.

The Survey Department, with its limited cadre of 30 surveyors and resources, would have taken about 10 years to complete this task, given that their survey capacity was about 10,000 plots per year. In these circumstances, the Project decided to provide surge support to the Survey Department to expedite surveys in priority areas (e.g. lands released from the high security zones); the support was in the form of overtime payments and payments for private surveyors and related equipment and transport costs.

The Project sought to support, in line with the Government’s Bim Saviya Programme, about 20,000 families with surveys and official land registration to obtain security of tenure of land. These official documents provide a durable solution in that they could be used by the settlers as collateral to access finance and for investment.

Achievements and observations:

As a part of UN-Habitat work in the Northern Province, 26,244 land parcels have been surveyed and 12,619 LDO diagrams prepared. In the Project area (Tellippalai DS Division), 520 government-owned allotments have been surveyed.  The Project facilitated issuance of 8,884 land permits (and the work is on-going).

- High security of land tenure: Addressing land tenure issues is at the centre of building sustainable and resilient communities.  Thus granting of land permits is very much appreciated by the community, and has been a significant boost towards providing a durable solution as land assets are considered very important by the community. Land tenure security for both women and men appear to have had a greater impact on household income, food security, and equity.

The temporary permits issued by the District Secretary will be converted to formal deeds in due course. Some have already received deeds. The Project has conducted awareness sessions to educate the community on how to convert the permit to a deed. However, the process is tedious and bureaucratic for the communities.

The deed provides the holder an instrument to seek bank loans and to access other financial resources. This too is a significant step towards self-reliance of the returnees, and weaning them away from micro-credit suppliers.

The families who got new land received a parcel of 0.05 ha (20 perches) land, which is quite spacious and provide an area for homestead cultivation. Many of the resettled households have used the land to produce different vegetable crops, fruits and poultry and livestock products for home consumption and to supplement their income.

- Fair process: The communities were very happy with the process adopted in identifying land for the returnees. Beneficiary selection, resettlement assistance, and service and deliverables have been purely on priority and needs basis, and the communities confirmed that there was no discrimination based on religion, race or caste. The communities appreciated that women-headed families and the disabled have been given priority.

As to be expected in a programme of this nature, there are unhappy families because of difficulties in cultivation in the new land due to water scarcity. These are families who have been traditionally cultivating lands, and are therefore in a difficult situation now.

## Output 4.3

Targeted resettled communities have access to an integrated and sustainable package of socio-economic services to help them rebuild their lives

Activity: 4.3.2 Support the renovation/repair and equipping of damaged schools in resettlement areas, as well as improve teaching/learning practices to ensure that boys and girls have access to quality education with minimum disruption

During the civil conflict, the school system broke down in the Northern and Eastern Provinces. About 200 schools in the Eastern Province were fully or partially damaged by 2007, and 877 schools in the Northern Province were damaged or gradually shut down. It is estimated that more than 48,000 school-going children returned to their home towns after the conflict in 2010 but needed substantial educational assistance to offset the long-term consequences of missed education.

The issues in education at the national level as well as in the conflict-affected areas can be summarised as follows:

| National level issues | Issues in the Conflict areas |
| --- | --- |
| - Gaps in Access, enrolment and retention - Lack of equity and equality in educational services - Poor quality of education - Poor governance and administration of education services | - Availability, enrolment and retention - Equity and equality - Poor Quality of Education (Lack of integrated service delivery; (working across the health, nutrition, education, child protection and, water and sanitation platforms to integrate already developed and implemented service offerings to address holisitic development needs of children affected by protracted social conflict) - Breakdown and disruption to education administration resulting in poor governance and Education Services |

The Project was expected to address the following issues:

- lack of basic Infrastructure such as school buildings, water supply and sanitation in schools that serve children of returning populations,

- lack of trained teaching cadre resulting in poor teaching-learning practices in schools leading to poor learning outcomes,

- lack of referral systems and coordination of services for children who are resettled after conflict and for those who have different forms of vulnerability ranging from disability, learning difficulties and lack of parental care and protection from different forms of violence,

- poor attendance and dropouts at junior secondary level due to poor integration of services including child protection and livelihood services that support parents to keep children in school and to promote their learning.

- lack of ECD facilities for early learning and development for children aged 3-5 years of age resulting in poor readiness for formal learning.

The Education component was implemented by UNICEF through its implementing partners, the Child Development Fund (in Trincomalee), and OfERR Ceylon (in Jaffna) with support from the Provincial Ministries of Education of the Northern and Eastern Provincial Councils. In formal education the project has supported 12 schools of which eight schools are in the Jaffna District and the balance in the Trincomalee District. The Early Childhood Development programme has been implemented in 11 preschools of which six are in the Trincomalee District.

In regard to modality of implementation, infrastructure development has been carried out by the respective Provincial Ministries of Education with funds allocated to them; training and other software have been carried out by the implementing Partners with technical facilitation from the Provincial Department of Education.

The data and information were analyzed under a learning framework that has three critical elements: the teaching learning process, school related factors and student/family related factors.

Formal Education

The evaluation covered four schools, viz., Sampur Sri Murugan Vidyalayam (Grades 1-5) and Sampur Maha Vidyalayam (Grades 1-13) [in Trincomalee] and Kuddiyapulam Government Tamil Mixed School (Grades 1-11) and Veemankaman Maha Vidyalayam (Grades 1-11) [in Jaffna]. These schools represented a student population of 995 comprised of 354 primary students and 641 secondary students and made up by 520 girls (52%) and 475 boys (48%).

Achievements

The achievements are summarised in Table 4.2.

Table 4.2 – Achievement in formal education sector

| Intervention | Jaffna District | Trincomalee District |
| --- | --- | --- |
| Infrastructure and learning environment | - Learning environment improved through construction of two pre-schools and renovation of 20 classrooms; - Supplies provided to nine schools | Improvement to learning environment: 7 new class rooms and 27 renovated class rooms; a Play park with equipment; new toilets and renovated toilets; water storage tanks; and furniture |
| Inclusive teaching and learning practices | - Capacity of primary teachers in nine (9) schools enhanced to provide quality primary education; - Teachers trained in Multi-Level learning; primary teachers trained on use of supplementary material on peace education and social cohesion; and on classroom management and positive disciplining | Twenty-one (21) teachers fully trained on ML/ACCCL methodology; re-set and finalized learning material (ML/ACCCL) with the review by the provincial education officials |
| School governance and parental engagement | - Community participation strengthened in nine (9) schools through community mobilisation and participatory planning; - School Self-Assessments/School Development Plans developed in nine schools and School Attendance Committees (SACs) formed; - School drop outs identified and re-enrolled and children with irregular attendance identified and their attendance regularised | - Child rights-based reporting mechanism is familiar to parents, school management; irregular attendance issues been reduced; PCM Training Guide line and Training Manual are ready for implementation in future; - Grade 1 and 2 classes are equipped with materials to conduct classes; parental involvement in ML/ACCCL implementation been improved |

Observations on the formal education component:

- Infrastructure development: Infrastructure development meets the standards of MoE and creates a conducive learning environment. The schools have a planned layout including the school garden and its environs, classrooms that are well ventilated and have natural lighting and the school is a safe place with fences. The school plant has the name board of the school displayed clearly, sign boards, information about the school, a clean environment and WASH facilities provided or facilitated by the Project. In terms of availability of schools, the children have access to schools that are within the specified distances of the MoE. A review of the School Development Plans showed that all children in the school catchment areas were enrolled in the schools and Out of School Children are monitored, making enrolment and retention in primary grades a target achieved by the project.

- Quality of learning: Quality of learning and the achievement of learning outcomes are seminal issues in education. Application of inclusive practices has started with teacher training sessions on multi-level teaching and the provision of learning resource material for teachers to practice multi-level teaching. The methodology and resource materials provided by the project are of high relevance but not all of the teachers in the specified primary grades have been trained on the multi-level teaching methods. Of the teachers who reported that they were trained only one teacher has been able to adapt the methodology in the classroom while meeting the demands of an extensive curriculum and competency-based learning system. The full understanding of this concept and principles was found wanting for full utilisation of these methods. Teachers need further training and on-site supervision to improve the practice of multi-level teaching including grouping strategies and how to practice multi-level teaching that pays individual attention while promoting group learning.

- School Self-Assessment: The School Self-Assessment (SSA) which is part of the planning process in the Child-friendly school approach seeks to engage parents and the community to assess the education needs of children living within the catchment area of the school.  The needs assessment is a participatory and reflective process that leads to a three-year School Development Plan (SDP). All schools have carried out the SSA and identified the number of children who have not enrolled in school or have left school without completing their basic education which was a marginal number of children. The engagement of parents in the School Development Plan varied across the four schools. In two schools the engagement was high and the parents continued to be proactive in the school development process. The engagement of parents was marginal in one school in the Jaffna District which has the most recently resettled population.  As the SDP offers an opportunity for using the funding allocated by the MoE for quality inputs and for generating funds locally, greater participation of parents in regular monitoring and reflection would have strengthened the utilization of the SDPs for developing the schools based on practical needs. This is specifically relevant to the areas with returning populations where the capacity of parents to generate resources for developing facilities in the school is limited. It is also observed that the high level of motivation for the SSA and SDP has not been sustained to monitor children with prolonged absenteeism or are likely to drop out of school due to family related factors.

- Limited coordination: Integration between the service sectors of health, child protection, psychosocial support and livelihood support for parents has been implemented by different partners under UNICEF offices in Kilinochchi and Batticaloa. In this regard, the evaluation team observed that the required level of coordination and synchronization was not evident in targeting the most vulnerable children and in providing targeted and complementing services for their education;

- Poor M&E systems: An efficient outcome monitoring mechanism with feedback loops at the level of the child, school, family and community and an inbuilt learning process across the partners is not available. Such a process would have given the opportunity for remedial action and consolidation of complementary activities resulting in synergy in outcomes.

- Outputs

  - School environment and facilities:	The school plants were in good order; all schools have a fenced in area that was safe for chidlren, a safe water supply, adequate numbers of toilets for girls and boys and for male and female teachers, nameboard, sign boards and notice boards to display information. The Sampur Mahavidalayam has a school garden and facilities for the separation and disposal of waste. However, none of the schools has a composting pit.

The play areas that are important for the development of gross motor skills of children was available in all four schools. The schools have a demarcated play area with play equipment but the teachers and the parents lacked understanding of the importance of specific play equipment such as the balance bar which is not available in any of the schools.

Display of information in the school principal’s office is taken as an indicator of transparency in management and the use of data and monitoring information in decision-making. All schools have made an effort to display the most important information but there is a lack of evenness in maintaining important information related to the achievements of children, the management and decision-making process and how children engage in feedback either through school clubs or other methods of feedback.  Table 1 in Annex 4.1 shows that none of the schools have mapped the catchment area or are monitoring enrolment and retention, specifically for children with specific physical and mental needs.

  - Adequate number of qualified and competent Teachers and School Principals: Deployment of qualified teachers to teach the curriculum is an important indicator of the quality of learning in schools. All primary schools have the required number of staff to teach the curriculum except for teachers to teach the Sinhala language. The two schools in the Trincomalee District have vacant cadre positions for secondary education especially graduate teachers to teach a more diversified subject streams such as Science and Commerce for the GCE A/L. As the school serves a large student population, diversification of subject streams and subjects would make secondary education available and accessible to children who cannot afford out-of-pocket expenditure to travel more than 40 km to Muttur or Trincomalee to access education in the Science, Commerce and Technology streams for the GCE A/L.

Although the Project targeted training of teachers from grades 1-3, not all have participated in the trainings.  Teachers in one school visited in the Jaffna District are not using the learning resource material in the classrooms and claimed that they were not trained.

Teachers’ awareness on (i) behaviour management in the classroom offering alternatives to corporal punishment and verbal abuse (ii) detection and referrals of different forms of abuse against children, and (iii) child safety and disaster preparedness was inadequate.

  - Active teaching and learning methodologies: The study team observed the learning resources and the layout of the classroom to understand what changes have taken place in the classroom to support activity-based teaching methods. The classrooms of the selected schools (grades 1- 5) were observed using the standards set by the MoE to determine if active teaching methods are adopted by the teachers.  The observations are given below:

- The recommended sitting arrangements for primary grades is to sit in groups of 4 or 5 so that chidlren learn to share resources and work as a group. However, the teachers have not followed the  recommended sitting arangement and the furniture is not made for such an arrangement.

- The teacher table and the black board at the appropriate height of the child are available. However the positioning of the teacher table varied which should be positioned at the back of the classroom.

- There were no aesthetic, mathermatics and environment corners in any of the schools. However, the teachers have improvised environmental corners in some of the classes. In the absence of such learning corners the teachers could have improvised by taking the chidlren  out to observe the natural habitat  and economic and social activity in their community which have not been done.

- The book corners are available in the classrooms but the books are not age appropriate and not education resource materials. However, all schools have libraries that are used by the chidlren.

- None of the grade 1 or 2 classes has a sand pit or board which is very important for physical development, group work and to increase sensory skills, fine motor skills, hand-eye coordination, creativity, and language development at key stage 1. As the schools are in proximity to the sea and sea sand is freely available this would be a most relevant way of promoting activity-based learning. This would be specially relevant for students  who learn at a rate and depth below their average same age peers.

- The primary grades did not have work tables and children did not have aprons for activity based learning and outdoor work indicating that activities are not an important part of learning. This is not taking place even in key stage 1. As all of the schools are well served with water supply facilities at proximity activity based learning can be facilitated with ease but no such effort has been made.

  - School curriculum is adapted to bring in local environment, culture and knowledge: Adaptations are necessary to make the curriculum relevant to the changing context and new approaches and concepts in learning. The evaluation team heard from authorities that the curriculum is vast and children of returning populations who do not have the readiness for learning such as ECD experience, good nutrition and a healthy living environment are expected to grasp concepts and demonstrate aptitudes that are beyond the child’s capacity. This was particularly relevant to the curriculum of the English language where the child is expected to understand contexts that are not associated with the child’s environment or cultural context and learn a language that is not even heard in the child’s home environment. Much needs to be done in this respect.

The evaluation team noted that the teachers are under pressure from the parents and school administrators to teach the curriculum and prepare students for the year 5 scholarship examination rather than adapt the curriculum to the local context and engage in competency-based learning.

  - Classroom atmosphere that is inclusive, stress-free, and conducive for learning: In the limited time available, the evaluation team did not come across any evidence of the use of canes or sticks to beat children and the children were active and not afraid of the teachers. However, none of the teachers or parents have participated in training or awareness sessions on preventing and reporting child abuse, but there were posters on identifying abuse and reporting displayed in the schools.

  - Regular assessment of Essential Learning Competencies and effective remedial measures:  The Essential Learning Competencies (ELC) are structured around the following key stages of learning in the primary grades:

    - Key stage 1 is grades 1 and 2

    - Key stage 2 is grades 3 and 4

    - Key stage 3 is for grade 5

Each child is expected to achieve 80 per cent of the age specific competencies in each grade before moving on to the next grade.

The evaluation team noted that a majority of the primary grade teachers have not assessed the achievement of each competency as it should be done. This raises the question as to whether the teachers have a good understanding of how to assess the competencies and support children who fall behind in achieving their age specific competencies. The multi-level teaching methods if applied appropriately within the context of this competency-based learning system would benefit all children especially those who learn at a slower pace than their same age peers. However, it was observed that teachers would need on-site coaching and supervision from well-trained In-Service Advisors for this to happen.

The teachers are pre-occupied with covering the syllabus rather than pay individual attention to each child. The effect of not assessing the ELC is that children who do not achieve the learning competences will go undetected and unsupported and will progressively find it difficult to study in the next grade.

The evaluation team could not undertake an assessment of the learning competencies of children due to lack of time. However, it was possible to analyse the results of the year 5 scholarship examination. The analysis shows that children in the Sampur Sri Murugan Viddiyalayam have fared the best and the children in the two schools in the Jaffna District have not performed well (Table 2 - Annex 4.1). However, it has to be noted that the analysis of the grade 5 scholarship examination is not an indicator for inclusive learning practices in schools.

A participatory exercise has been carried out with the girl and boy children of grade 5 in two primary grades to understand their interest and motivation in coming to school and in learning selected subjects. It was a proxy indicator to understand what immediate changes have taken place in the teaching learning process in the schools. However, it has to be noted that it is very difficult to establish a relationship between the level of motivation and the project. The survey indicated that 12 per cent of the boys and 14 per cent of girls did not like to come to school (Table 3 - Annex 4.1). Also, the children did not like to learn English which confirms that the curriculum is not culturally and context appropriate. It shows that the way the curriculum is adapted and applied needs to change in the schools.

  - Family related factors:	The study assessed family related factors to understand how the family supports children in learning and to what extent the project activities have mobilized the parents to support learning. The most significant factor is that 6 per cent of boys and 9 per cent of girls have no parents and 17 per cent of boys and girls are from female- headed families. With the limited information available, it is not possible to draw an analysis on how the family status has affected children and their learning.

The evaluation team noted that all children depend on extra coaching either through tuition or extra coaching in school. This is indicative of the focus on the grade 5 scholarship rather than competency-based learning. Raising the awareness of parents on home-based stimulation and the need for learning through reading newspapers and books is the need.

As some of the critical project activities (e.g. awareness sessions for parents and follow up sessions for teachers) and the phasing out activities are pending or are on-going, it was not possible to capture the outcomes related to how the family and home environment contribute to the readiness of children for learning.

  - School Governance and Parental Engagement:	All schools have completed School Self-Assessment and the SDPs; however, schools have limited understanding of monitoring the SDP, engaging children in school activities and resource mobilization.

  - Standardisation of Outputs:	Qualitative activities such as teacher training, awareness sessions for parents and caregivers on home-based stimulation, safety and protection, and participation of children and their parents in project activities (School Self-Assessment and planning and school safety plans) differed in the two districts. Both Districts have good practices that have not been shared and replicated. These shortcomings demonstrate (a) a weak project outcome monitoring system, and (b) a lack of inherent learning and information sharing amongst implementing Partners. Improvements in these two areas would have made a significant technical contribution to promoting home-based stimulation, male engagement in child care and rearing and safety and protection in the home.

Early Childhood Development Component

The evaluation covered three pre- schools, viz., Pulenthiran Pre-school (Muttur), and St James Pre-School (Palaly South) and Mahalaikal Pre-School (Valalai) with a total student population of 77.

ECD is an important element of early education that is not provided by the state and the regulatory mechanisms have failed to maintain standards of access and quality. The following activities were initiated under the Project:

- Multi stakeholder discussion and coordination facilitated in divisional and provincial level in provision of integrated pre/primary education services;

- A detailed action plan on integrated ECCD service delivered; (working across the health, nutrition, education, child protection and, water and sanitation platforms to integrate already developed and implemented service offerings to address holistic development needs of children)

- Capacity of 11 pre-schools strengthened to deliver pre-primary education in child friendly environment and with appropriate teaching methodology;

- Community capacity and participation strengthened in 11 pre- schools;

- Twelve (12) pre-school improvement plans adopted

The project has mainly focused on construction of preschools, provision of play and learning equipment and teacher training.

Achievements and Observations

- Infrastructure: The infrastructure is well maintained. It is noted that 97 per cent of children aged 3-5 are enrolled in a preschool. For most of the students (63 per cent), the preschools are located within 10 minutes of travel time and all of them attend. In general, pre-schools have a conducive learning and play environment and the project activities have been implemented well.

- Teacher training: The teachers have been trained both by the project partners and the ECCD Authorities of the Northern and Eastern Provincial Councils. The two preschools in the Jaffna District have a well maintained learning environment and the teachers are more closely supervised and supported by the ECCD Authority. However, it was observed that the teachers and parents needed additional training and awareness on early detection of children who learn at a slower pace than their peers, how to support and promote learning with such children, and child safety and protection.

- Village Child Development Committees:	The preschool teachers were members of the Village Child Development Committees (VCDCs). The parents are a vital link in promoting, preventing and reporting child abuse but none of the parents who participated in FGDs have been trained and are not aware of the role and functions of VCDCs.

- Standardisation of Outputs:	Little attempt has been made  to standardize the quality of outputs. The preschools in the Jaffna District demonstrated quality inputs such as training of preschool teachers for assessing the Early Learning Development Standards of children aged 3-5 years, monitoring the ELDS, using lesson plans and activity guides and more guided play, as standardised by the Early Childhood Care and Development Authority of the Northern Province. These practices were not evident in the preschools in the Trincomalee District.

- Learning and Play environment:	In general, this component has been implemented well. A summary of observations on key requirements in pre-school buildings in Table 4 of Annex 4.1. Overall, the learning process as well as the engagement of parents especially fathers need improvement. In the limited number of pre-schools visited, the only concern relates to WASH compliance including lack of toilets in one school.

Activity 4.3.3 - Restore access to health services through the construction/repair and equipping of Health infrastructure; provision of ambulatory services and anthropometric equipment for growth monitoring; establishment of community groups on nutrition and training of health officers.

This component is implemented by UNICEF through its implementing partners SOND (in Jaffna) and CCCD (in Trincomalee). Civil works in hospitals have been undertaken by the Health authorities directly with funds allocated to them. Procurement of key equipment has been handled directly by UNICEF.

Achievements:

Jaffna:

- At Telippalai hospital, a Special Care Baby Unit (SCBU) with 12 cot capacity, four on-call  duty room for SCBU /Paediatric and obstetric doctors and extension of paediatric ward to provide  isolation unit established;

- The maternity unit of the base hospital improved its functions on imaging and outreach services of the consultant VOG are facilitated to augment the services at clinic level in the PHM areas.

- Ten (10) Rural Health Assistants supported throughout the project period to cater the vacant PHM areas with a close monitoring by MOH, Tellipalai.

- Staff technical capacity and skills enhanced on maternal and child health and Nutrition in Telippalai and Kopay MOH areas and staff at Base Hospital Telippalai maternity and paediatric units.

- Forty nine mothers clubs reformed and all 49 have undergone capacity development programmes and some are fully functional.

Trincomalee:

- Support to development of Muttur and Sampur hospitals (Construction of a maternity ward and ambulance for the District Hospital Sampur refurbishment of the maternity ward and labor room at Base Hospital, Muttur)

- SAM Management training; a detailed plan of action launched to reduce the prevalence of SAM in children under 5-years; these included formation of Communities Support Groups; provision of Suposha, a highly nutritious cereal; and management of SAM at home.

- Pre-natal and perinatal death review services and introduction of preventive measures

- Training provided health staff on safe drinking water, hygiene practices, obstetrics care, new-born care, anaemia and teenage pregnancy.

Observations

- Mothers’ Clubs:	In general, Mothers’ Clubs are functioning effectively. The members have received training in child care, nutrition, leadership and child protection. The members are all returnees, and have some form of livelihoods. They welcome the opportunity to serve in the Club and be of a service to the community. As a result of the training received, and with regular guidance from the PHM and PHI, they have been able to make positive changes to health and welfare of children and expectant mothers. MOHs have treated Mothers’ Clubs as an integrated part of the preventive health system. Children’s weight is assessed regularly; malnutrition reduced and SAM and MAM substantially reduced; and vaccination is regular with Mothers’ Club members visiting the households on their own. They have addressed other issues such as domestic violence, excessive use of alcohol, and have been engaged in peace-building.

A matter of concern is the disinterest shown by some mothers in the Clubs.  In Jaffna, the attendance at the meetings of the Club met during the evaluation is now down to about 50 per cent of the membership. In Muttur, the interviewed group admitted not having a meeting for six months, and the last meeting was attended by only five members.

A few Mothers’ Clubs have started income generating activities. One Club met during the evaluation produces Samaposha (a breakfast cereal), and the income is deposited in the Bank. Another Club has supported a member to purchase machines for popcorn production and packaging for sale.

Mothers’ Clubs have been engaged in educating their members on cash and loan management, and have been able to wean away the influence of micro-finance dealers who visit the villages. As a result of these advocacy and protection functions, micro-finance agents no longer visit some of these villages.  This has freed women from taking high-interest loans.

- Upgrading of hospitals: The upgrading of the hospitals at Telippalai, Muttur and Sampur has shown positive results. Both health authorities and the community are highlyappreciative of the better service from the hospital including the ready availability of ambulance service. The Baby Care Unit at Telippalai is well-equipped and is now operational.  Pre-mature births and other complicated births are being treated at the hospital and there is no longer a need to transfer them to Jaffna. Returnees no longer have to go to the Jaffna hospital.  They have greatly benefitted from the upgrading of facilities including on-call doctors rooms, the maternity ward and the expansion of the paediatric ward.

The hospitals are able to provide imaging and outreach services, which was not previously available to the returnees.

Similarly, improvements to Sampur and Muttur hospitals have helped the returnees immensely. Sampur hospital is now equipped with special equipment for maternity cases, and the visiting Obstetrician is able to provide a better service than referring cases to other hospitals. Assistance of UNICEF and the modality of operation (through direct funding via PDHS) are very much appreciated by the authorities as UNICEF’s approach is more appropriate to the context than other donors.

- Capacity development: Training provided to rural health care staff (e.g. PHM, PHI) has been most useful. They work largely through the Mothers’ Clubs, identify SAM and MAM children, visit homes, and attend to minor health issues of the returnees. With these developments, SAM and MAM management has been streamlined. Furthermore, they advise returnees on hygiene aspects, safe drinking water, teenage pregnancies etc. Thus children and women have access to essential health services through outreach health clinics and services.

The evaluation team noted that investments made for enhanced capacity building and training for creating a dedicated health staff, civil society and NGO partners and Rural health assistants have been productive and cost effective in the implementation of health and nutrition interventions. Rural health care staff maintain that the Project’s capacity development efforts has made them more effective in carrying out their duties, a fact corroborated by the health authorities.

Activity 4.3.4 - Increase access to safe water and adequate sanitation through the construction/renovation of water and sanitation facilities, together with community groups, and promotion of good hygiene practices in resettlement areas

This component is managed by UNICEF through its implementing partners OfERR (in Jaffna) and CCCD (in Trincomalee).

Achievements:

Jaffna:

- WASH facilities provided for Special Care Baby Unit (SCBU) at the Telippalai hospital; on call duty room for SCBU doctors and extension of paediatric ward together with infrastructure development.

- WASH in schools and pre –schools: Toilets, hand-washing units, water storage tanks and repairs to male toilets undertaken in eight (8) schools; Seven (7) pre-schools provided with WASH facilities;

- As a software approach, hand washing with soap on critical times (before, having meals, after using toilet and after playing...) and menstrual hygiene management training and action plan preparation carried out in secondary schools.

- Ground water recharge mechanisms in operation at 70 locations; further 46 under construction; in one Pradesheeya Saba, a decision has been made on including a recharging pit together in new housing units.

- Menstrual Hygiene Management(MHM)plans and facilities provided to three (3) schools;

- Water management and WASH training for nine schools as well as for community;

- Training of about 450 stakeholders in WASH;

In Jaffna, there has been a general delay in constructions, and work was on-going at the time of the evaluation.

Trincomalee:

- Provided safe drinking water to 24 individual households;

- Constructed 60  toilets and soakage pits in houses;

- Built MHM Facilities in Secondary Schools to facilitate adolescent female students;

- Improving the sanitary facilities of Patalipuram and Muttur hospitals.

Observations

Pre-school WASH

The evaluation covered three preschools in Trincomalee (Pulenthiran Preschool, Sampoor; Arasadi Vinayagar Preschool, Sampoor; and Santhosapuram Preschool) and St. James Pre-School, Palaly South in Jaffna.

In general, children have adequate, comfortable, and age-appropriate sanitation facilities with water. The number of latrines complies with minimum standards. The locations of latrines are children-secure with privacy and are easily reached at all times.

Toilets are clean with detergents used for cleaning. Pre-school teachers or parents have taken the responsibility of cleaning the toilets. Adequate drinking water on tap is provided by NWSDB. The taps are lever types and are easily operated by children. Hand washing facility was sufficient, age appropriate and designed for individual hand washing.

Body hygiene is satisfactory and hand-washing with soap/ hand wash is observed. No diarrhoea cases or worm infections have been reported in the school during the last three months. Children have been taught the hand washing song and the critical times to wash their hands with soap. According to parents, these children act as agents of change by influencing the parents and siblings in hand washing with soap at home.

Pre-school buildings are clean and neat. School area is also clean, and solid waste is collected and burnt. There is no source separation of waste as there waste is not collected by the local authorities. Preschool premises are separated using a fence. A child-friendly and a clean school environment were observed.

Some short-comings were observed: in Trincomalee, the Pulenthiran pre-school did not have a toilet and proper hand washing facilities. Children brought drinking water from home since there was no drinking water supply at the school. The students have to use toilets in the main school, located at a distance resulting in children using the open area for urination. Teachers stated that it is time consuming to take each and every child from time to time to the primary school toilets. The only existing water tap was not child-friendly due to height of construction. In St. James Pre-School, Palaly, Jaffna, the toilet is located in one side of the building whilst the hand washing tap is located on the other side of the building, requiring children to walk a distance to wash hands after using the toilet, which is not user-friendly. Moreover, there was only one tap provided for hand washing, which is not sufficient, and there was no foot washing tap.

Preschool management committees made up of parents have taken the responsibility of operation and maintenance of the WASH infrastructure and to provide continuous supply of soap/hand wash liquid. In addition, parents clean the toilets.

School WASH

The evaluation covered Sri Murugan Vidyalayam, Sampoor and Kuddiyapulam GTMS, Vasavilan.

Students have adequate, comfortable, and age-appropriate and gender-sensitive sanitary facilities with accessible water. The number of latrines complies with minimum standards. The locations of the toilets are secure, have privacy, and are accessible at all times. Adequate drinking water is available and is provided by NWSDB, dug wells or tube wells. Toilets are cleaned by students on a roster. In both locations, maintenance of taps was less than satisfactory. There were unattended leaking pipes.

Toilets in the school in Trincomalee were clean, and detergents have been used for cleaning. However, in the Jaffna school, toilets were dirty; according to the Principal, toilets are used by outsiders as they are not locked and there is no fence/wall around the school, allowing free access to outsiders.

Body hygiene was observed to be good and hand washing with soap was observed. Taps are lever type, which are easy to operate by children. In Jaffna, the hand-washing areas were unhygienic.

In Sri Murugan Vidyalayam, Sampoor, the dug well was not covered properly.

Menstrual Hygiene Management was satisfactory. Both girls and boys have received MHM training. In Trincomalee, both parties have participated in the first session, while only girls have participated in the second session, whereas both groups have received the same training in Jaffna. The attitudes of boys have changed after the MHM training and they have a better understanding of the situation of girls. Both boys and girls are attuned to any unexpected situations, and boys, having understood the situation, support the girls to manage emergency menstrual situations.

During menstruation, girls wear sanitary napkins, which are available in the class room or in the female teachers’ staff room. The canteen in the school in Trincomalee have these napkins for sale. The toilets are constructed with facilities for sanitary pad disposal and incineration. The evaluation team noted that the incinerator is being regularly used for incinerating sanitary pads. Female teaches also use the MHM facility in the girls’ toilet.

With the introduction of MHM, school attendance of girls has improved; previously girls did not come to school during their menstrual days, since there have been difficulty in disposing the used napkins combined with lack of sanitary napkins in emergencies, and lack of water and soap. MHM training has made the girls to participate in sports and other school activities even during their menstrual days. The attitudes of girls have changed; they bathe and take normal food during menstruation. However, they are not allowed to do heavy work at home, and Hindu girls avoid the temple during menstruation as they strongly believe that tradition must follow. The puberty ceremony, after the first menstrual cycle, is very common in the North. After the MHM training, these ceremonies have been reduced, allowing the parents to save money.

Solid Waste Management – There were three bins for waste (for polythene, paper and degradable waste). However, waste is finally collected together and burnt, as the Pradesheeya Sabha is not regular in collecting waste. Solid waste disposal needs improvements.

Household WASH

Four houses in each district were inspected.

Water was available in both districts; in Jaffna, two houses have tube wells. Many houses get water from NWSDB; others get water from the neighbours. In Trincomalee, people in temporary shelters or old houses did open defaecation in the forested area before the Project. The Project provided both hardware and training on sanitation, maintenance of toilets, and on hand washing. The new toilets have therefore changed the lives of people.

Households who received the toilets got adequate, spacious, comfortable and accessible sanitation facilities. One of the toilets in Trincomalee is disable-friendly. All toilets inspected have squatting pans except the disable-friendly toilet, which has a commode. The location of the toilet is in accordance with the ground plan of the owner, with concurrence of the PHI. The toilets are cleaned by women, and detergents are used for cleaning. Except in a very few cases, households practice hand washing with soap at critical times, i.e., after defaecation, after handling faeces of children, and before meals.

In Jaffna, almost all toilets were in poor order. Door locks of toilets are unserviceable due to poor construction (built by UNDP in 2010) and are not maintained.

In the households visited in Trincomalee, soap was available for hand washing; good personal hygiene was evident. The household environment was clean in a majority of the houses. In one house, the toilet was unhygienic and the surrounding area was full of waste with potential for mosquito breeding. Toilets of households visited in Jaffna were poorly maintained and dirty.

In both districts, there were no systematic practices, either in schools or in households for liquid waste disposal. Often, in schools, there was free waste water collection near taps. Similarly, solid waste management was poor.

Ground Water Recharge

Lack of recharge has been identified as one of the 13 causes of poor ground water management in the Jaffna Peninsula. One of the sub-components of the Project is to introduce a ground water recharging mechanism at the community level. This involved directing rain water into a filtering tank located within the premises, which would allow filtered water to seep into the ground thereby improving the volume of the ground water lens.

Three community holdings were visited. Discussions with the community revealed the following information:

- The community did not see the recharge mechanisms installed in their premises improving their individual water sources (as to be expected). As a result, they used the tank as a storage tank (by blocking the seepage mechanism) for using water when needed;

- The community was ignorant of the overall benefit of improving ground water situation, and lacked overall vision of the interventions.

In spite of these set-backs, the Project continued with its advocacy work in relation to the need for setting in place mechanisms for effective ground water management. As a result of these efforts, the Kopay Pradesheeya Sabha will enforce regulations to the effect that all households with more than 92 m2 roof area should construct a recharging pit.

4.3.5 Facilitate access to protection services, including psychosocial support, by restoring institutional and community level protection systems, to ensure the safety and security of persons, particularly women, boys and girls, at risk of violence, abuse and exploitation and alleviate the suffering they may be experiencing.

This component is implemented by UNICEF and UNDP through its implementing partners Shanthiham and SOND (in Jaffna) and EHED Caritas (in Trincomalee).

Achievements:

Jaffna:

- Draft Training module to train day-care centre staff and to train eligible parents for adoption is available. Draft is under consultation with professionals;

- UNICEF together with DPCCS (Northern Province) trained 203 police officers to re-familiarize on the CYPO and how to enforce it;

- Probation officers, CRPOs and NCPA officers overlapping roles and responsibilities identified which helped DPCCS to amend their department statute.

- Child desk established in Telippalai Police station.

- Eighteen (18) qualified youths available as child befrienders as trained voluntary resource in the community. Seventy-eight (78) identified persons benefited from psychosocial support;

- Ten VCDCs are functional and up to now 89 issues were handled by VCDCs and 53 were solved. and 15 major child protection issues unresolved at the VCDC were taken up at the divisional child rights monitoring committee meeting

- About 34,000 people newly-settled in Telippalai received mine risk education resulted in the identification of mines (UXO - 816, Mines – 239, Bullets   - 1856, ERW – 4); No causalities reported in the targeted GN divisions

- Forty-nine Mothers’ Clubs formed, and members empowered by providing training in leadership, ECCD and child protection

- A number of training events on nutrition and health, leadership and communication, SAM management conducted to variety of audiences including government officers

Trincomalee:

- New Women’s and Children’s Desk established at Sampur; 42 Police officers from 11 Police Divisions trained on Child protection;

- Conducting psychosocial counselling and mobile clinics (mental health);

- Mine risk training for 1,093 community members and children

- Five VCDCs formed and members trained on Child rights, responsibility of VCDC, how to prevent child abuses and referral process and systems;

- Leadership and life skills trainings were conducted for youth at 05 resettled locations for 204 youth;

- Drama training to youth and children;

- Positive parenting training for 155 parents

- Children Club formed/reorganized; Youth Club formed/reorganized; Divisional Child Development Committee formed in Muttur; District Child Development Committee formed.

Child Protection and Gender-Based Violence

Gender-based Violence:	The Project identified several issues relating to gender-based violence. These included: physical, sexual, verbal, emotional, and psychological abuse, threats, and coercion, especially intimate partner violence (IPV) in the case of relocated populations. The evaluation team noted the claims that the perpetrators of violence are almost always husbands resulting largely from alcoholism, and drugs and substance use.

Fundamentally, the cause of gender-based violence lies in gender-based inequalities and discrimination.  GBV prevention strategies should be strongly linked to efforts to increase gender equality that:

- Shift focus from seeing women as victims to seeing them as survivors, actors and agents of change;

- Increase women’s political participation and public influence;

- Increase women’s economic empowerment to correct for power imbalances within the household;

- Promote women’s sexual and reproductive health and rights; and

- Engage with men and boys.

Child Protection:	The issues identified include: corporal punishment at home, sexual abuse of girls and boys, verbal abuse, neglect, child labour and child marriage.

Strategies to end childhood violence should be based on five foundational principles: respecting women’s children’s rights, freeing children from fear, enhancing their capabilities, practising non-discrimination, and promoting gender equality.   The focus should be on:

- Empowering caregivers and children: Any effort to end violence against children has to recognize the capacity of children themselves to prevent abuse, which is the primary focus of Project interventions.  Children and adolescents need to be aware of their rights, and the importance of gender equality and of ensuring mutual respect – and learn about safe sex and self-protection. At the same time, it is important to sensitize and equip frontline workers and families with skills and resources to manage stress and aggression, nurture children with empathy and care, and build resilience to violence.

- Building safer communities: Local authorities need to be vigilant to ensure that young people do not get drawn into drugs and crime.  It is important to offer young people more productive outlets for their energy and strengthen community cohesion. Investing in sports facilities, public infrastructure and appropriate design of community spaces can make a substantial dent in community and public violence.

- Reducing structural vulnerabilities: It is important to address patriarchal norms that perpetuate gender inequality and underpin interpersonal violence especially against women and children. This requires long-term engagement with local communities, effective use of multiple media to change behaviour and attitudes, and formulation of targeted strategies to work with different constituencies.

- Embedding violence prevention in educational and care institutions, and social services:  Making schools and other institutions ‘violence-proof’ should become a priority. Departments for health, education, social welfare, justice, finance, and home affairs – all relevant agencies -- need to be robust, functioning, resourced and embed violence prevention in their goals, strategies, plans, policies and programmes.

The interventions in this component were in line with the Policy, and to ensure a safe environment for IDPs, particularly women, youth and children. These interventions could be classified into three groups, as follows:

- Prevention - parent’s awareness, community awareness, training for children, community centres and Children’s Clubs, and psychosocial support.

- Responding – Initiatives such as Women and Children’s Desks at the Police Stations, establishing VCDCs, empowering the members of VCDC, training of state officers for receiving reports, case management standards and procedures, referral and support mechanisms, victim support, as well as psychosocial support.

- Promoting child participation - through awareness raising and integrated approaches and advocacy.

The conflict of nearly 30 years has eroded the community-based traditional systems for safety of women and children by the immediate family and neighbours. Likewise, the Government’s systems were ineffective with inexperienced newly-recruited staff; breakdown of PHM services due to heavy work pressure often requiring large areas to be covered and their other official priorities; lack of motivation and resource limitations in the child protection services. Some of the standard practices such as case management, referral services and remedial measures for the identified issues have not taken place on regular basis.

Observations

- Revival of Community-based Protection Mechanisms: The Project focused on restoring the proven community-based protection systems. These included mobilisation of the community to consider all children as “our children” and all young girls and boys as “our youth” so that neighbourly protection services could be provided. The approaches used by the implementing agencies contained effective methods and good practices (e.g. involvement of the trust-worthy adults, Grama Niladhari, Community leaders, prelates of religious places etc.).

In both districts, implementing partners worked closely with Probation and Child care staff as well as the Police. Actions included formation of Children’s Clubs, conducting children-friendly activities usually in the Community Centres, sports and drama, stage plays etc. The Children’s Clubs seem effective. The Clubs have provided children and youth an avenue for collective action. According to the respondents, team games are frequent, and they also organise group events such as dramas and talent skill shows. Overall, these activities have brought out harmony and unity amongst the communities; furthermore, children work as change agents at home often bringing the messages of unity to home. These actions brought about closer relationships among children and promoted reporting of abuses.

The parents were trained on disciplining children. Forming groups to support the community (e.g. funeral assistance) also expanded this approach.

- Strengthening Institutional Mechanisms: An important contribution at the village level is the formation of Village Child Development Committees (VCDCs) to deal with child protection issues. VCDC members have been trained in a number of areas such as identification and reporting of incidence of abuse or violation of child rights. VCDC’s first point of contact is Grama Niladhari, with whom a close rapport has been established. GNs too have been educated on how to respond to incidences of violation of child rights. VCDCs were found to be effective, and work closely with the relevant agencies, although the members were not sure of their mandate.

At the Divisional level, staff have been trained on child protection and for handling practical issues of victimized women and children based on a sound conceptual understanding with a legal base. CRPOs have been provided opportunities to follow Diploma Courses in Psychosocial counselling and Child Care. The Project facilitated the development of District level Child Development Action Plans 2018–2020 for Jaffna and Trincomalee Districts to ensure continuation of key activities of the current Project.

At the national level, the Project worked closely with the Ministry of Women and Child Affairs and the Department of Probation and Child Care to develop formal operational guidelines for the VCDCs. These Guidelines (available in all three languages) set out the mandate of VCDCs, which are considered as the nucleus to create awareness and enhance child rights within the resettlement areas and prevent violation of child rights.

- Women’s and Children Desks: A Children’s Desk has been established at Telippalai Base Hospital and a Women’s and Children Desk established at the Sampur Police Station.

The Desk at the Telippalai Hospital is to provide protection and psychosocial counselling services to children referred to the hospital for medical assistance. During the last six months the Unit handled 28 cases of children. Although the unit lacks some basic utilities and is not well known outside the hospital, its services are very much appreciated by the health authorities, who consider this as a replicable model for the country.

The Women’s and Children Desk of the Sampur Police Station is in a new building constructed by the Project and is fully operational. Before the building was available, there was no space with privacy to conduct investigations relating to victimized women and children – the open investigations created many problems as the reporting could be overheard by many, including suspects brought for other offences including sexual violence. With the new building, this issue has been satisfactorily resolved, and the new facility provides an environment for systematic investigation of cases, timely actions and case management so that victims are better supported and violence against children and women are addressed. Two Police officers (one PC and a WPC) have been permanently attached to these Women and Children Unit. Its work is currently hampered due to the non-availability of a Tamil-speaking WPC required to speak with women victims (UNICEF has insisted on increasing the cadre of Tamil-speaking WPCs). The facility lacks basic requirements for investigations (e.g. equipment for documenting statements) and transport resources. Although required, the Unit has not developed its plans yet. An important development is that all religious institutions of the area have decided to conduct child protection counselling programmes for affected children and their families on voluntary basis in collaboration with the Women’s and Children’s Desk of the Police Station.

- Overall, child protection system is now well recognised by the authorities in both Districts. In this regard, Project’s interventions are well received. The reported cases of child abuses have reduced, and school drop-outs have not been reported during the last six months. At the community level, many activities focussing on child protection are continuing after the Project, and case management methodologies are being implemented in a much more systematic manner.  Notwithstanding these, the evaluation team noted the need to strengthen child protection systems further by undertaking a comprehensive study on the root causes of gender inequality and the social norms and practices that sometimes enforce GBV.

Psychosocial Welfare

The main psychosocial issues identified by the Project include: deprivation of land assets and livelihoods; separation from family and sufferings in the welfare camps, ill-treatments and discriminations meted out due to displacement, poverty, caste discrimination, livelihood-based social stigmas, excessive consumption of alcohol by male adults, domestic violence, insecurity of women, incest in the family, early marriages of female children, break away of early marriages, and family separations. Some cases of abuse of drugs and substance addiction were noted. The evaluation team noted a strong re-emergence of caste issues after the end of the conflict. The so-called lower caste people are discriminated at the school, temple and at other public places. Even school play grounds are divided. Added to this conundrum is the influence of politicians to grab land based on caste issues. A case was reported to the evaluation team where the winner of an athletic competition was denied the trophy because of the caste.

The Partners focused on psychosocial well-being through a suite of actions. These included: trained Counsellors, Befrienders and Core Groups. In reality, the same members functioned in these Groups. These groups worked in tandem with Psychiatric units of the hospitals, Health Department’s psychosocial Counsellors, field-based staff, Counselling Assistants, and other NGO workers (e.g. Relief Sisters) as well as staff of the Probation and Child Care Department ( Probation Officers and Child Care Assistants).

Another related activity undertaken by the Project is awareness creation on land-mines.

Observations

- Changing mind sets: The Programme has been able to change the mind-set of people. Previously, psychosocial issues and resultant mental conditions have been considered a stigma in the society. Counselling has brought about a change and has dispelled misgivings of the community through education on how to identify psychosocial disorders and where to go for redress.

- Trained cadre: The cadre of volunteers (Counsellors, Befrienders, Core Groups etc.) is a well-trained valuable human resource capable of working closely within the community. The psychosocial methodologies included using children’s theatre groups for street drama (on themes such as alcoholism, abuse of children, early marriages and separation of families, domestic violence, mother migration), home visits and family care programmes. They are trusted by the community, and are able to discuss personal and confidential matters. The Health Department authorities appreciate the contributions by this cadre as important so much so that they refer patients to the Counsellors.

An important corollary is that the well-trained cadre of counsellors will have no work after the Project is over. They are committed to continue supporting their communities, but it is acknowledged that they themselves are from the community and have no resources at their disposal to help others.

- Visible impacts: The Counsellors have succeeded in bringing down alcoholism and domestic violence, and have become very popular in the community for their voluntary work. They have contributed to unite individuals and provide important social and emotional stability to the community, in particular for women and children.

There was evidence that Project interventions have improved psychological and mental health of the conflict-affected people. There is improvement to community psychosocial well-being in terms of positively influencing to revive their culture, traditions, spirituality, and interpersonal family and community relationships. There is also improvement of life skills, education of children, and re-commencement of livelihoods after the conflict.

Mine-risk education is well received, and mine injuries are now non-existent.

- Uncertainty in the future: A significant drawback is that the Counsellors (including Be-frienders) are not always officially recognised by some Government officials.

Activity 4.3.6 - Establish or strengthen an existing community services centre in each pilot site that would serve as an information centre; facilitate referrals to relevant services and support outreach services in areas of return.

This component is implemented by UNICEF and UNDP through its implementing partners SOND (in Jaffna) and Peace Winds Japan (PWJ) (in Trincomalee).

Achievements:

Jaffna:

- Ten (10) CBOs forums are functional in the project location. Each CBOs forum include: RDS, WRDS, VCDC, Mother Support Groups, Youth Club/ Sports Club, Children Club, Community centre and other functioning body members at village level.

- Twelve (12) Trainings were conducted to 10 CBO Fora to develop the capacity of CBO Fora such as Official responsibility of CBO Fora, CBOs Management and resource mobilization, with the participation of 203 members.

- One stop service center is equipped.

Trincomalee:

- Five community centres built;

- Six community centres renovated and equipped (work still in progress);

Observations:

The evaluators visited two Community Centres (also referred to as One-stop Centre). The buildings are spacious with a hall for meetings; additionally, office rooms are available and usually the Grama Niladhari office is situated there. The Centres are managed by the Grama Niladhari. At one centre, the hall was being used to train dress-making to young girls. The Rural Development Society is expected to maintain the buildings, and pay for utilities.

- Low awareness: Community members were not aware and have been confused by the various committees and fora established by the Project. Many felt that there were too many ‘committees’ in the village, often with overlapping functions.  The Members are not certain of the functioning and value of these committees. Also, members are confused about the training received on resource mobilisation and CBO management, and are unsure of the training events. It would appear that the Project did not carry out a post-training evaluation.

- Social exclusion: The Project has supported the establishment of new RDSs and empowering the members to undertake activities for the welfare of the IDPs. However, the evaluation team noted instances of discontent within RDS due to caste and religious discrimination.

- Additional concerns: According to GN, there is uncertainty about funds for maintenance. The officers who have offices in the Centre (e.g. Grama Niladhari and Development Officer) do not pay a rent.

The reactions of the community to the utility of the Centre were uneven; some felt that the funds could have been used for a better purpose to improve their livelihood – and they did not see the potential for using these Centres for activities on social cohesion  because there have been no activities undertaken so far. Work on these Centres has been delayed; as a result the Project has not been able to put to use these Centres to fulfil the purpose for which they were built.

4.3.7 Provision of support for sector-based livelihood assistance for resettled communities who engaged and willingness to engaged in Agriculture, Fisheries and Livestock related sectors and enterprise development support specially for youth through Inputs, equipment & accessories with required skills

This component is implemented by UNDP through its implementing partners OfERR (in Jaffna) and PWJ (in Trincomalee).

The livelihood interventions are primarily intended to guarantee secure and inclusive livelihoods for the resettled communities with special focus on socially excluded and the marginalized people. The livelihood strategy focussed on revival of traditional livelihoods (farming, home gardening and livestock; fishing); introduction of new livelihood avenues (e.g. self-employment and micro- businesses etc. by women and the youth of the affected families); expansion of labour market opportunities (the medium sized businesses, paddy and highland agriculture usually demanded hired labourers so that some of the resettled people could engage in labour work with seasonal variations); and encouraging returnees to engage in multiple livelihoods in view of the vulnerabilities associated with each specific livelihood.

Palmyra industry remains an important cottage industry assisted by the state and the cooperative movement providing opportunities for handicraft production especially by women.

These livelihood interventions were also expected to foster partnerships with the private sector, generate market opportunities, ensure value additions in the value chains and rehabilitation of economic assets through alternative longer term funding sources.

The assistance provided is as follows:

- Homestead agriculture and animal husbandry in the Jaffna district – about 300 beneficiaries each receiving materials worth about LKR 125,000 – 150,000 depending on the type of activity;

- Support for members of the Soodaikuda Fisheries Society (Muttur);

- Support to producer groups in Jaffna; and

- Support to ‘micro-enterprises, with each beneficiary receiving materials worth about LKR 150,000.

In general, launch of these programmes has been delayed.

Achievements:

Jaffna:

- Livelihood packages provided to returnees [Animal husbandry (159); Agriculture (125)];

- Micro-enterprise support to 431 beneficiaries;

- Two (2) producer groups (Food in Valali; Palmyrah products in Telippalai) formed, each with 15 members.

- In addition to the fishing boats, engines and fishing nets have been given to the Myliddythurai North and Thaiyiddy South Fishermen; they were trained on the using GPS Technology for productive and safer fishing operations.

Trincomalee:

- Fishing boats and engines provided to 32 beneficiary members of the Soodaikuda Fisheries Union;

- Thirty-one (31) Youth Enterprise Development grants provided for enterprise development;

Homestead Agriculture and Animal Husbandry

The resettlement areas are not covered by a major irrigation system. Therefore, the returnees have to depend on rain and minor irrigation tanks for agricultural pursuits.  The returnees were supported with grants to start homestead cultivation and small scale animal husbandry, again in the homesteads. Many of the returnees have been engaged in agriculture prior to their displacement.

Observations:

- Beneficiary selection:	According to the Implementing Partner, beneficiary selection was based on a number criteria including being IDPs, lack of sustainable livelihood, and past experience in agriculture/animal husbandry. Although it was indicated that the relevant Grama Niladharis were consulted, this does not seem to be the case always. The DoA raised the concern that they were not involved in the selection process. During the evaluation, the Team visited several beneficiaries – a number of them have significant assets. For example, one beneficiary who received a cow already had several heads of cattle, a tractor and other agricultural machinery.

- Engagement of DoA:	Notwithstanding the non-engagement in beneficiary selection, DoA was appreciative of the homestead cultivation programme. On their own, DoA would not have had resources to start a homestead cultivation programme; in that regard, assistance of the project was welcome. DoA pledged to support the farmers and to serve them, and this was an opportunity for DoA to engage in improving agricultural infrastructure such as renovation of agro wells for irrigation, and to transfer technology (introduction of drip irrigation, soil testing and fertilizer application, accessing quality seeds by farmers, introduction to Good Manufacturing Practice – GAP, etc.). The DoA however was concerned on the payment of the full material grant to the beneficiaries without any substantive contribution from the farmers. Normally, DoA provides only 50% of the grant so that there will be a sense of ownership by the farmers, and would not create a dependency syndrome. A closer dialogue between DoA and the Project during the planning stage would have been useful to address issues such as this.

Some of the lands are not fertile and therefore not suitable for agriculture. Beneficiary selection should have taken into consideration land and soil suitability.

- Benefits from homestead agriculture: DoA is of the view that the majority of the beneficiaries would have benefitted from this initiative with supplementary income derived from agriculture. Additionally, household consumption of vegetables was noted. DoA noted that those who did not follow DoA recommendations in regard to planting type, seed materials, irrigation etc. suffered.

- Animal Husbandry:	Many beneficiaries received a cow, one or two goats or a flock of chicken. The evaluation team noted that in the case of milch cows and chicken, the average income would be about LKR 5,000 – LKR 7,500 per month. In the case of goats, income would be a lump sum from selling the goat for meat. In a number of cases involving goat husbandry, the beneficiaries decided not to sell the goats due to sentimental reasons; others claimed they died prematurely. It is clear that the animal husbandry initiatives only provided a meagre supplement to their income. The Government representatives too felt that a close review is needed on the usefulness of this kind of support which brings supplementary income. The evaluation team however noted that in the case of cattle and chicken, there is a direct contribution to household nutrition. The beneficiaries claimed that household consumption of milk and egg has increased.

Many women have very little knowledge on rearing chicks. They were not sure whether to focus on meat or eggs, and were also unaware of scientific rearing methods.

The beneficiaries have difficulties in accessing veterinary services; as a result animal death was higher than usual.

A returnee mother of three children from Vasavalan East commenced a small domestic poultry farm for livelihood support. She started the farm with 100 chicks in December 2018 and all of them survived up to the second month. During the last six month 70 birds died from time to time due to reasons unknown to her. At the time of the visit she had only 30 live birds. She complained that all her efforts to get the services from the veterinary services have been futile.

Support to Fishers

The Project supported Soodaikuda Fisheries Union; beneficiary members were selected using a set of criteria including the family size, previous fishing experience etc. The Members and officials are satisfied with the selection of beneficiaries.

A group of four members has been given a boat and an engine; altogether eight boats have been given in 2018. The boats and engines are registered with the Society, and are insured. Each group of four has paid LKR 40,000 to the Society, as a one-time payment.

A membership fee is paid by the members, and they are entitled to obtain loans from the Society.

Observations:

- The Members are happy with the turn of events, and they are able to earn a living from fishing.

- Since this component was started in late 2018, there has been very little fishing in the last quarter of 2018 due to monsoons. It is therefore too early to comment on performance. The evaluation team noted that one group has already lost its engine, and a Police inquiry is pending.

- The Members requested fish storage facility to overcome lower prices during the heavy catch period.

- The Project organized Sri Lanka Navy to provide training to fishers, which is appreciated by the latter.

Support to Producer Groups (Jaffna)

The Project supported two Producer Groups (Food preparation in Valali; Telippalai Palm Development Coop Society Ltd).

The evaluation team visited the Palm Development Coop Society, established in 1972, which collects palmyrah toddy to make spirits, bottled toddy (Kankesan Toe) and jaggery, in addition to a variety of handicrafts. The Society has 1,800 members, who have paid LKR 100 as admission fees. The members can seek loans at 14% annual interest.

Observations:

- The main business is collection and sale of toddy, including bottled toddy made in their plant; monthly sales are around LKR 2.5 million.

- The Project supported the Society with modernizing the building, and providing some equipment.

- The Society is well run, and is profitable. However, it needs further technical assistance to improve its product range and sales. For example, their jaggery was of high quality, but lacked value addition such as packaging, bar-coding and a marketing mechanism.

- The Society also trains youth from the IDPs on handicrafts. Occasionally, large orders are received benefitting the youth.

Micro-enterprises

The sector-based livelihood assistance package for the settlers with productive inputs, skills trainings, equipment and vital infrastructure was expected to revitalize economic opportunities at the community level in order to catalyze local employment opportunities and create more sustainable sources of income generation.

Enterprise development was a significant investment in the Project, with emphasis in Jaffna where over 400 individual benefitted as against 31 in Trincomalee. The assistance provided to individuals was around LKR 150,000. The Project supported a range of ‘vocations’ – the more popular being carpentry, masonry, tailoring, electrical work and plumbing, grocery shops and eateries, and food preparation.

Observations:

- Enhanced family incomes: It is generally recognised that these ‘enterprises’ have increased family income; most beneficiaries pretended to be unaware of the income they generated, but a good guess is that it ranged from about LKR 25,000/month upwards, depending on the type of business.

- Developing a business plan:  All beneficiaries have been trained on preparing a business plan, as a compulsory requirement; however, there was very scanty evidence that these plans have been used in running the enterprises. Some of the elderly beneficiaries did not understand these plans at all. The evaluation team met with only a few females who claimed that the business plans were helpful to understand the overall direction of their businesses and seek bank loans.

- Informal and unregistered enterprises: Majority of the micro enterprises have not registered the businesses with the relevant authorities.  In Sri Lanka, in the case of single owner, micro enterprises are registered at the DS Office as “Business Name Registration.”  This is a somewhat bureaucratic process needing a number of pre-requisites. This has been a hindrance to register businesses, and the difficulty associated with the process was a deterrent for the beneficiaries to register. Some of them were reluctant to register fearing that they will have to pay income tax. Lack of registration meant that the facility could not be used as collateral for seeking loans. However, it was mandatory to register grocery shops and eateries with the local authorities due to hygiene issues.

In Jaffna, the Project adopted a different approach for the beneficiaries to start a grocery shop. The beneficiaries were expected to build the shop, and payments have been made at intervals based on progress. This was not a favoured option of many, as they have been struggling to construct their own houses. Consequently, building the shop took longer than desired, and the livelihood started much later than expected.

- Limited access to credit: Although a Bankers Forum was fostered by the Project, it did not progress to the extent where the beneficiaries could obtain loans.  Like in many parts of the country, micro enterprises had certain limitations to access financial facilities from banks, including a clear collateral, viable business model and continuous business performance.  Given that the enterprises have been in operation only for a few months, it is too early to link these micro-enterprises to the banks for financial facilities.

Telephone Interviews

Since there is no baseline and an end-line to capture economic and other benefits of the micro-enterprise component, a telephone interview was planned to obtain more information on income and sustainability to supplement the information provided in the preceding sections.

As already noted elsewhere, there are 431 beneficiaries in Jaffna and 31 in Trincomalee. However, out of the 431 beneficiaries, the Project has telephone contact details of only 117 beneficiaries. About 15 per cent of the beneficiaries representing different ‘vocations’ were randomly selected for telephone interviews to be conducted based on a structured questionnaire (Table 4.3).

Characteristics of Respondents:	In terms of age, 20 per cent of the respondents were less than 30 years old; and 44 per cent were between 30 – 40 years. Twenty-three (23) or 92 per cent have bank accounts, and 15 (60 per cent) have taken bank loans for various purposes. Twenty-four out of 25 respondents (96%) were engaged in the same vocation for which they received assistance. A number of respondents earned between LKR 30,000 – LKR 40,000 per month before the project.

Table 4.3 – Selection of beneficiaries for telephone interviews

| Vocation | Jaffna |  | Muttur |  |
| --- | --- | --- | --- | --- |
|  | No. of beneficiaries | No selected for interview | No. of beneficiaries | No selected for interview |
| Mechanic | 10 | 2 | 4 | 1 |
| Carpentry | 11 | 2 | 7 | 2 |
| Grocery/food | 28 | 3 |  |  |
| Mason | 27 | 3 | 1 |  |
| Tailoring | 16 | 2 | 7 | 2 |
| Electrician | 5 | 1 | 5 | 1 |
| Other jobs | 20 | 4 | 7 | 2 |
| TOTAL | 117 | 17 | 31 | 8 |

Main findings:

Eighteen (18) respondents or 72 per cent received their assistance package only during the first quarter of 2019; five (5) or 20 per cent received their assistance during the last quarter of 2018. Some of the ventures were not fully operational. Thus the period available for a realistic assessment of benefits is limited, as was indicated by many of the beneficiaries. All respondents stated that if not for the Project, they would not have been able to obtain a grant for improving livelihoods.

Twenty-four (24) out of 25 respondents (96 per cent) were engaged in the same vocation for which they received assistance. The YED programme enhanced income generation of the beneficiaries largely by providing new trade equipment, rather than creating new enterprises.

The Project prepared Business Plans as a part of this component. However, 60 per cent did not use it, largely because they did not understand the concepts or had difficulty to follow them.

Twenty (20) respondents (or 80 per cent) received some form of training for the vocation for which they received funding. One respondent stated that the training was ‘very useful’ whist the others stated that training ‘useful’.

Nineteen (19) respondents (76 per cent) have not registered their businesses; the reasons were: they do not have time for registration, do not understand the process, and the process is too cumbersome.

Nine (9) (or 36 per cent) of the respondents employed others either as temporary or permanent assistants. Six respondents who have not registered their businesses employed others.

As most of the ventures have begun only in 2019, it was too early to assess impacts. However, according to the perceptions of the respondents, 11 (or 44 per cent) stated that the venture was ‘modestly successful’ whilst 14 (or 56 per cent ) stated that the ventures were ‘modestly unsuccessful’. Yet all expected that the ventures would modestly improve household income. Some of the respondents have used the extra income for expanding/upgrading their houses, purchasing household items, and on occasion to settle loans.

Annex 4.2 has further details.

Activity 4.3.9 - Construction/renovation of economic infrastructure and also promotion of alternative energy solutions such as Solar Panel Lighting in common places and street.

This component is implemented by UNDP through its implementing partners OfERR (in Jaffna) and Peace Winds Japan (PWC) (in Trincomalee).

Achievements:

Jaffna:

- Twenty-five (25) agro-wells renovated;.

Trincomalee:

- Construction of a 50 MT capacity seed paddy processing centre with a Drying yard, Vehicle and machinery to Murutham Seed Growers, Sampur (work progressing);

- Construction of dry fish processing centre;

- Construction of Milk collection Centres with Sale units in Sampur & Pattalipuram with chilling plants (Muttur East Dairy Development Co-op Society)

Observations:

Jaffna

- The agro-wells are expected to serve several households; the evaluation team noted community concerns on water sharing. It would appear that water sharing arrangements agreed at the beginning of the Project are not followed. For example, the evaluation team came across two instances where beneficiaries have not settled their electrify bills with the water supplier. At the moment, there is no one to mediate in this matter.

Trincomalee

There has been an inordinate delay in completing the commercial projects. It is therefore too early to make an assessment; these should have been in operation under the Project for at least 6-12 months to assess any teething problems, both technical and managerial. Some comments in these facilities are provided hereunder.

- Dry fish processing centre:	The building has been renovated by UNDP and an ice-making machine and a fish dryer have been provided by the implementing Partner, PWJ. Completion of the facility has been delayed, and the facility was not in operation at the time of visit due to lack of fish.

- Milk-chilling Centres:	The Project has established three (3) milk-chilling centres with sales outlets for the Muttur East Dairy Farmer Development Cooperative Society. The evaluation team visited all; one was functional and made ice cream and yoghurt, in addition to selling fresh milk. Work on the other centres has been unduly delayed, and the centres are not operational. One of the centres visited did not have the chiller yet. In the circumstances, it is too early to comment on the success of these centres.

Discussions with stakeholders and an analysis of available information indicate that the business model used in these Centres is not risk-free. This observation is based on three factors; i) dairying is a supplementary livelihood for the members who do not give high priority for milk production; ii) most cattle owned by the members are indigenous cattle breed with a low milk yield of about 3-4 l/day; and iii) MILCO and other private milk processing companies are vigorously exploring expansion of their milk collection and are paying a higher price than the cooperative. The situation is compounded by the fact that members are not committed to sell their milk to the cooperative and the purchase price of milk is not based on the fat content. As a result, the functional centre has difficulty in procuring milk. Urgent attention is needed to examine the business model adopted for these Centres.

- Marutham Seed Paddy Facility:	This is one of the largest investments; the facility has not commenced operations. The Society representatives pointed out that a similar facility was established a few years ago by a donor about 4 km away from the current location – however this facility is out of order, and no action has been taken to repair the machinery.

Notwithstanding this, the Project decided to establish a new paddy seed facility at Munnampodivetta. Some members participated in the planning, but decisions have been taken without due consideration to the wishes of the Members. The facility is established in a land belonging to the Department of Agriculture, and the Members are uncertain of the future ownership of the facility, although the Implementing Partner is in the process of handing over the facility without making it operational.

The Society representatives are very much displeased with the turn of events; their voice has not been heard, and they have complained to various authorities, including UNDP (by letter dated 29 May 2019) requesting an inquiry. They complain about lack of transparency in project management including procurement, and allege financial misappropriation in the purchase of some machinery and vehicles. In this regard, the representatives handed over a set of documents to the evaluation team. Currently there is a deadlock between the partners, including the Provincial Director of Agriculture.

There has been no training on maintenance and operation of this facility to the Members of the Society. PWJ reported that they would provide technical back-stopping for the period of six-months after the completion of the Project.

## Cross-Cutting Areas

### Gender

The Project assisted gender mainstreaming in its components primarily through awareness and education programmes to supplement its interventions at the grassroots level.

As a cross-cutting issue, specific analytical elements have been applied in the study. These include:

- Identify and address issues arising from gender inequality or discrimination, and project interventions aimed to improve conditions of women and children: All issues addressed in the project were analyzed to understand how they impact men and women and girls and boys separately and how the project activities have addressed issues of women and girls (education, WASH, livelihood, health, protection of women and girls from all forms of violence and social participation). Inclusion, especially in education, was analyzed in terms of which girls and boys or groups of parents are left out of processes which results in their being systematically blocked from opportunities and resources;

- Project addressing root causes of gender inequality: The evaluation team examined how unequal gender relations between men and women, girls and boys and different caste and social groups have been addressed by the project. This was particularly relevant to analyzing how the project has addressed issues in child protection and SGBV and structured the prevention and protection of all forms of violence and promoted protection from violence at the different levels ranging from the community, division, district and provincial levels; and

- Project’s explicit intentions to transform unequal gender power relations, improving social position of girls and women, and focus on their empowerment (or of men and boys): These aspects were applied in analyzing violence against children and SGBV where the project has made explicit efforts to address issues that disempower girls and women.

Observations

- Overall, the Project’s interventions have been gender-sensitive, and the returnees have grasped the fundamentals of gender equality. Women are more assertive and are more involved in day-to-day affairs of the family and the community along with their male counterparts.  The Project has created an environment where women in the resettlements in general have a better sense of security in their families including safety of their children with support from family members and the neighbourhood communities.

The Project has sensitized the Partners on adopting gender-sensitive approaches, and these requirements are incorporated into the Partner agreements. The evaluation team noted that over 80 per cent of the field staff and the volunteers of the partners (particularly Shanthiham, SOND and OfERR) in Jaffna District and 55 per cent in Trincomalee were women. The Implementing Partners have produced outreach materials including posters, leaflets, and brochures and have conducted creative campaigns for changing attitudes on violence against women.

- Special care has been taken by the Project to address the concerns of women-headed households and to inculcate gender sensitivity through awareness building of returnees as well as Government officials (e.g. GN, WDO, FHM, SDO). Similar programmes have been conducted for Police officers both in Jaffna and Trincomalee to facilitate managing Women’s and Children’s Desks at the police stations. Special attention has been given to ensure that they (a) do not follow  judgmental and stereotype attitudes towards women and provide sensitive and effective responses to the complaints of violence against women, (b) provide whatever the possible services for women who report violence and assure confidentiality and respectful treatment (c) behave in a friendly and sincere manner that would motivate more women will report violence to the police station, and (d) take measures to prevent violence against women.

The Project has integrated gender sensitivity in all interventions in order to guarantee that displaced and affected women receive equal treatments. This was evident in selecting beneficiaries where women-headed households have been given priority in the allocation of lands and houses. It is noted that Land Permits are issued under the Land Development Ordinance. There is an inherent weakness LDO permits in regard to succession of ownership if the holder dies intestate. In that event, males have a right over females.

- It was difficult to openly discuss gender-based violence against women and girls given the cultural context of the Project area. Issues relating to GBV were not brought out during the project discussions, for protecting privacy and goodwill of the victims or their families. However, better reporting of gender-based violence is observed in the Project interventions.

- The evaluation team observed that women-headed families are better informed now on gender-based violence and other areas (e.g. vulnerability, harassments,  incest  and sexual abuse of young girls in the event the single parent mothers re-marry) and have gathered relevant knowledge and skills and developed positive attitudes required for collaborative activities in the community. The training programmes conducted by the implementing partners to empower them to face situations with ‘gendered’ identity of women and their unequal power relations and consequential discriminations, negative and harmful gender norms, facing negative community attitudes, gender-based violence in the community, handling issues of children out of schools through peer mentoring and pressure, child marriages and early pregnancies have been productive.

- The evaluation team noted instances of equal opportunities and economic empowerment where husband and wife have shared income-earning burdens. Whilst they do not feel any form of discrimination, assistance to the husband is considered as the correct decision of the family. Instances were observed where husband attends to household chores when the wife is either sick or engaged in livelihood activities away from home. A few cases were observed in Muttur where mothers have migrated on employment and husbands have mutually consented and undertaken the burdens of household chores, and children’s education and welfare. Problems of migrated mothers due to leaving the responsibilities of their children in the hands of trusted care givers were also observed.

- Another related aspect addressed by the Project is early marriage of young girls and early separation of married couples making the children vulnerable, which was happening in the conflict areas due to a variety of reasons. The parents are better educated now, and the trend of early marriages is reported to be on the decline.

- The evaluation team noted that on many occasions, men grab employment opportunities, particularly in labour work by offering more work for less pay. Women stand disadvantaged in these situations. Equally, there is pay discrimination for women’s labour work.

- Women often become prey to micro-credit operators who offer loans at higher interest rates. Often times these loans are taken without the explicit knowledge of the husband, leading to family disputes etc. Instances have been noted where micro-loan operators used undue power on indebted women and their grown up female children to redeem these loans. The project has systematically guided these women to get out this debt-trap by way of linking them to the mainstream banking system and introducing the path way for savings and micro-finance system of their own.

- Outwardly, women are actively engaged in the society. However, an in-depth discussion revealed that in general, women are given the main burden and drudgery of routine household chores and the sole responsibility for child rearing. The animal husbandry options offered by the Project, in particular chicken farming, goat and cattle rearing have become the responsibility of women; by extension, the project has unknowingly exacerbated the issues.

- Women have received equal opportunities for skills development. The Project’s micro-enterprise options provided for ‘vocations’ ideally suited for women (e.g. tailoring and dress making, grocery shops, eateries, etc.).

- The Project has trained girls in menstrual hygiene management, which has improved school attendance and has given confidence to the girls to be active normally during the difficult times.

- Women have taken leadership in societies and in decision-making on subjects related to the community welfare. Women have also taken a lead in group savings and revolving funds including group-based emergency micro-loans, and are supporting the families in financial discipline and management of the household economy.

### Social Equity

A majority of Sri Lankans recognize caste for some purpose or other. There are three parallel caste systems in Sri Lanka: Sinhala, Sri Lankan Tamil and Indian Tamil, and some form of caste discrimination is not uncommon. Silva et al., states that ‘the caste system among Sri Lankan Tamils in Jaffna can be seen as the most rigid and the one with clearly defined patterns of inequality, discrimination and social rejection driven by a religiously articulated notion of untouchability. The power, influence and high status in Jaffna society have been held by the land-owning Vellâlar caste, considered as the dominant caste for all intensions and purposes. At the bottom in the Jaffna caste system are the group collectively called “Panchamar”, who have been subjected to many forms of discrimination ranging from prohibiting wearing respectable clothing to denial of access to public transport, drinking water, kovils and temples etc.

The conflict situation in the 1980’s brought to the fore the non-Vellâlar groups who asserted themselves in the struggle. The LTTE banned caste discrimination. Silva (ibid) also states that lower castes remained very long as IDPs even after the cessation of the conflict, due to their inability to exert influence on the authorities for their release.

The evaluation team noted resurgence of caste discrimination in the resettled communities. Instances of denial of access to play grounds, temples and water sources to ‘lower’ caste people were brought to the notice of evaluators. An instance of discrimination at a school was reported, and the solution of the authorities was to divide the school, rather than integrating them. Although caste discrimination was not that serious in Trincomalee, ethnic tensions combined with subtle political biases seem to be influencing decisions there.

## Project Implementation and Management

Management and Implementation Arrangements

A key feature of the Project is its identification of the need for delivering an integrated package of services to fulfil the objective of providing durable solutions to the IDPs. The Outcome 4.3 provides this ‘package’ in the form of policy base, settlement of land tenurial issues, and providing the essential services such a access to health, education including pre-schools, water and sanitation facilities, protection services including psychosocial welfare, especially for girls and women, facilitating social cohesion through community activities, developing the capacity of CBOs, and finally providing a suite of livelihood and enterprise packages.

The Project is managed by three UN agencies, UNICEF, UNDP and UN-Habitat; field implementation follows three modalities – direct implementation by UN Agencies, implementation through stakeholder government agencies (particularly civil works), and through CSOs. The roles and responsibilities of Partners are given in Annex 2.1.

Engagement of CSOs is through partnership agreements, which specify the targets to be achieved by each Partner. However, it is unclear whether the Partners reported on the targets specified in the Contracts.

In the overall Project, Outcomes 1-3 were implemented by UNDP whereas Outcome 4 is the joint responsibility of UNDP, UNICEF and UN-Habitat. In regard to effective management of Output 4.3, the proposed arrangements are set out below:

To promote coherence, ensure joint planning and implementation, the agencies will establish a working level group from among the UN agencies (drawing in the relevant government and other partners as required) on a monthly basis. Additionally, a resettlement working group at the Colombo level chaired by the Ministry of Resettlement would be proposed to be established, meeting at least quarterly, and will be linked with District level working groups in Jaffna and Trincomalee. The District working groups, under the leadership of the respective District Administration, with the support of UNDP will bring together UN field colleagues (including the Regional Coordinator of the Resident Coordinator’s Office), relevant representatives from the District and Provincial Administration and civil society.

The evaluation team noted the need for very close dialogue between the implementing agencies and partners in order to deliver an integrated package. The strategy proposed (see above) would have provided the back-drop for an effective delivery.

The ground situation, however, was quite different. The evaluation team noted very low level of interaction between UN agencies, and more importantly, between implementing CSO partners. There was hardly any interaction between personnel in the two districts. The interaction with the Government agencies were more based on specific activities (e.g. infrastructure). The grassroots level Government officials were involved in the Project but overall coordination and interaction at higher level of the Government was inadequate.

The low level of interaction between UN Agencies and amongst CSOs resulted in varying quality of deliverables. The opportunity for sharing lessons from the two districts and thereby bringing in standardization of deliverables has been lost. The level of involvement of CSOs in the two districts was also variable. For example, psychosocial welfare in Jaffna appears to be better suited for the context than what was observed in Trincomalee. Another noteworthy observation is the relatively little understanding by the Project’s district level staff and the implementing Partners on Policy work (Output 4.1) implemented by UNDP and the Ministry.

The model used for implementation of the Project through CSOs is appropriate and workable. However, several limitations observed in the modus operandi of implementation have significantly affected performance. These are: inadequate coordination amongst CSOs and their relatively low focus on the overall ‘objective’ of the Project; compartmentalization of activities as detailed out in the CSO contracts without due regard to the relevance of other interventions; inadequate coordination amongst UN agencies; and lack of a lead agency (a ‘Project Manager’) for Outcome 4 to provide overall coordination of activities, both at national and district levels.

Monitoring and Evaluation

The Centre for Poverty Analysis (CEPA) has been contracted for M&E work on Output 4.3, as this output involves a significant amount of on-the-ground activities. It carried out a needs analysis of the returnees (not necessarily in the Project intervention populations) as a part of the baseline report. CEPA has conducted periodic monitoring and evaluation, and the reports have been submitted to UNICEF. However, follow-up actions on the M&E findings are not reported. CEPA has also produced an end-line report.

Major delays in implementation of activities relating to Output 4.3 have not been addressed by the Project. CEPA has highlighted some of the critical concerns of stakeholders (e.g. location of the Seed Paddy Facility); these do not appear to have drawn the attention of UN agencies.

There is no evidence of formal and regular M&E activities at the field level undertaken by UN Agencies and Partners.

The Ministry of Resettlement has internally reviewed progress relating to Output 4.1. The Ministry places high priority for M&E work as well as on impact monitoring later on.

As the Project ended only in April, 2019, there is no terminal report of the Project.  The Partners have produced their terminal reports as part of their contractual agreements with the donor UN Agencies. These reports were not available to the Evaluator.

Project Finances

The financial progress (without indirect costs) as at 31 December 2018 is in Table 4.1.

Table 4.1: Financial Progress (US Dollar)

| UN Agency | Budget | Expenditure | Commitments | Utilisation | Balance |
| --- | --- | --- | --- | --- | --- |
| UNDP | 2,081,714 | 966,399 | 269,955 | 1,236,354 | 845,360 |
| UNICEF | 1,564,500 | 1,299,510 |  | 1,299,510 | 264,990 |
| UN-Habitat | 394,000 | 129,368 | 78,803 | 208,171 | 185,829 |
| TOTAL | 4,040,214 | 2,395,277 | 348,758 | 2,744,035 | 1,296,180 |

As output-based budgets and expenditures are not available, no further analysis was undertaken. There are no records of counterpart financing.

# Project Performance

Overall, the integrated approach adopted by the Project is logical.  The stakeholder views confirm that providing durable solutions require a suite of actions to provide communities with necessary services to resume normal life.  Key outcomes of the Project are presented in Table 5.1.

Table 5.1 – Key Outcomes

| Result Area | Achievements/Outcomes |
| --- | --- |
| National Policy on Durable Solutions | - Policy developed and adopted by the Government; actions for IDPs are implemented in accord with the provisions in the Policy. |
| Land Tenure | - The Project has surveyed 26,244 land parcels and 12,619 LDO diagrams; the targets have been exceeded mainly due to the fact more LKR was available to the Project due to depreciation of LKR against USD. In addition, 8,884 land permits issued. |
| Improved access to an integrated and sustainable socio-economic services | - Improvements to schools and pre-schools, and improvements to teaching methods, curriculum and school environment. - Improved WASH facilities in schools, pre-schools and in houses; introduction of ground water recharge mechanism in Jaffna. - Improved health services for IDPs with access to better care by improving infrastructure, including ambulance services at Telippalai, Muttur and Sampur hospitals; better maternity facilities and child care facilities. The IDPs are no longer required to travel to distant hospitals for these services. - Improved protection services for girls and women; establishment of women and child desks at Telippalai hospital and Muttur Police Station; access to psychosocial care and counselling. - Additional income from livelihoods; income of women-headed households increased from LKR 5,000/month up to LKR 10,000. Increase in income of men-headed households also reported. - Youth Enterprise Development programme shows indications of improved income. - Introduction of economic infrastructure; due to delays in implementation, it is too early to make an assessment. |
| Gender | - Introduction of gender sensitivity in the interventions; better reporting on gender-based violence and better understanding of gender equality. |

Discussed below are the relevance, effectiveness, efficiency and sustainability of the Project’s outcomes.

## Relevance

Six features of the Project contribute to its relevance for Sri Lanka.

- The Project is well aligned with the Government’s policies and strategies to introduce equity, provide relief to conflict-affected people, and reduce poverty, as reflected in the current Government policy. It directly addresses several recommendations relating to conflict-affected people in the North and Eastern provinces made by the Lessons Learned and Reconciliation Commission (LLRC). The Project also strongly supports Sri Lanka’s efforts at promoting gender equality and women's empowerment.

- The Project’s objective falls within the realm of European Union’s Multi-annual Indicative programme for Sri Lanka 2014-2020 under the broad category of "Support to Integrated Rural Development". It now focuses on country reform process following post-humanitarian and development assistance in four priority provinces, including Northern and Eastern Provinces.

- The Project addresses key needs of the IDPs.  This is particularly so in the two chosen areas, viz., Telippalai (and to a lesser extent Kopay) and Muttur in the post-conflict development period.  Government’s national and provincial authorities as well as ground-level officials (e.g. Grama Niladharis) who were interviewed, whilst admitting that Government itself has certain constraints both financial and human resources, are of the unanimous view that the Project significantly supplemented their own rehabilitation and resettlement efforts.

- The Project’s interventions are well aligned with the National Policy on Durable Solutions for Conflict Affected Displacement –the development of which was facilitated by the Project itself. The formal announcement of this Policy makes explicit an implicit policy that was in the making and provided the over-arching policy for activities at the grassroots level since about 2016.

- UNDP and UNICEF support is consistent with the priorities set by the Government.  The Government, as part of its rehabilitation and resettlement efforts, has identified (a) a set of immediate activities including reconstruction of physical and social infrastructure (in health, WASH, education etc.); and (b) livelihood opportunities across sectors for individuals are based on consultations with the communities – which also takes into account the competencies of the individuals.

- Due to budget constraints, the Government has not been able to allocate sufficient financial resources for the two programmes outlined above.  Financial support through this Project is seen by Government officials as a critical gap filling exercise.

## Effectiveness

The Project has provided key services and offered a comprehensive package of interventions to provide durable solutions to bring normalcy to the resettled families – in keeping with the Government’s policy and land tenure interventions.  The package provides the essential support for the resettled communities to begin a new life.  However, given the short period of time over which the activities have been implemented, it is difficult to comment on the effectiveness of the interventions.  The evaluation has noted the following:

Output 4.1: The Project’s support has demonstrated positive changes.  The Policy has provided the background strategies for the welfare of IDPs, and all actions by the Government will follow the Policy.

Output 4.2:  The interventions have been effective and have exceeded the original commitments made. Providing some form of land titles, even as a permit, has brought significant relief to IDPs not only in securing tenure but also in the ability to use these instruments as collateral for bank loans.

Output 4.3: Interventions have been ‘somewhat effective’ in addressing the provision of sufficient basic services needed for returnees.  Construction/refurbishment of schools, pre-schools and health facilities have been well received and have contributed to reducing the burden of the IDPs. Child protection services too have been, by and large, effective although some form of violence remains. The Youth Enterprise Development component, albeit with limitations, has provided much-needed support to youth. This component has been effective in starting up livelihood projects for these people, though the benefits from individual livelihoods are limited.

In regard to land tenure work, it has become the responsibility of IDPs to convert the temporary permits issued by the District Secretariat into proper legal deeds. There is no agency to support the community through this bureaucratic process.  There are instances of IDPs being dejected as they felt that the process stopped half-way. There is an expectation from the IDPs that the Project would ensure issuance of deeds. This has not happened in a majority of the cases.

Discussed below are factors that have contributed to and also limited the effectiveness of the Project’s implementation.

Factors contributing to effectiveness: The following factors have contributed to enhancing the Project’s effectiveness

- Close collaboration with the Government:  The Project has been implemented in close partnership with Government agencies – feature frequently highlighted and appreciated at different levels by officials including Grama Niladhari, Development Officers and Public Health personnel.

- Small yet catalytic and flexible financial support: Providing small yet catalytic and flexible financial support has contributed to enhancing the effectiveness of the Project.   The Project has addressed gaps in government assistance by providing financial support for critical physical infrastructure and psychosocial needs that Government funding has left out due to budget constraints.  This includes, for instance, support for physical infrastructure, building of schools and improving the quality of education both at formal level as well as pre-school level.  Similarly, the Project has helped finance water and sanitation facilities, and  health infrastructure.  A special feature has been the support for addressing mental health issues and disabilities through psychosocial support to affected people.

- Identification and engagement of intermediate partners (CSOs): The Project’s approach to implementation by engaging intermediate partners (CSOs) has enhanced effectiveness. CSOs have provided the connectivity with the communities which UN Agencies would have otherwise found difficult.

Factors limiting effectiveness: The following factors have limited the Project’s effectiveness:

- Absence of strategic vision and pathways: While the activities undertaken under the Project may all be necessary, their effectiveness has been limited by the absence of an overall strategic vision and an understanding of pathways.  By and large, the focus of the implementing agencies was on individual outputs rather than on the overall outcomes of the Project.  This seems to have limited the extent to which the Project could have been effective in realizing the overall objective. For example, it would have been useful to develop an overall business opportunities and employment plan for Jaffna and Trincomalee into which the individual livelihood enterprises fit in.  Similarly, the UN Agencies could have developed a regional plan to end violence in childhood into which the setting up of child desks in the hospital or in the police station fits in.  The rainwater recharging interventions should have ideally fitted into a well-developed groundwater plan.  The partners could have developed an overall plan to promote the health of children and women into which the WASH interventions fits in. Had the Project dovetailed its interventions with a broader focus on the health of women and children, concerns of indoor air pollution problems associated with use of wood for cooking might have been addressed better. As a result, many of the activities undertaken by the Project may not be sufficient to make a long term impact.

- Insufficient attention to re-designing traditional livelihood interventions:  Past experience in Sri Lanka and elsewhere points to the high failure rate of individual enterprises especially goat, cow, and poultry.  This knowledge was not used by the Project to redesign such traditional livelihood interventions.  Similarly, the Project could have better factored in the background of the families that have been resettled and rehabilitated.  Returning to their homes after almost three decades, many such families have little links and understanding of the surrounding markets.  As a result, the economic enterprises promoted under the Project remain tiny enterprises with very few offering a sustainable source of income. The Project has also not helped beneficiaries establish effective linkages with markets and credit.  In the case of some enterprises such as the seed paddy facility or the milk collection and chilling centres, the Project has not made sufficient arrangements for extending at least short term technical support or establishing management systems before handing over the enterprises to the cooperatives.

- Insufficient attention to recognizing and resolving conflict within the communities:  There are a few instances where conflicts within the communities have not been resolved in a transparent and amicable manner.  This was brought to the attention of the evaluation team, for example, at the seed paddy facility.  Critical documents signed between the Government, UN agencies and partners are in English – not translated into Sinhalese and Tamil for the benefit of the community.  Similarly, the Project did not fully factor in the caste tensions giving rise to growing insecurities and fears of, for example, land appropriation by the influential communities in Jaffna.

- Capacity gaps:  The evaluation team observed gaps in the functioning of various community groups that have been formed or strengthened.  These include, for instance, the VCDC, Mothers’ Clubs, Children’s Clubs, psychosocial counselling groups, Befrienders.  In many cases, the formation of such groups was tied solely to the Project.  As a result, such groups are likely to become defunct after the Project is over.

- Gaps in inter-agency coordination:  Although this model is most appropriate (cf. Section 4.6), the effectiveness of implementation has suffered due to inadequate coordination amongst UN Agencies and CSOs. As a result, limited synergies have accrued from the sharing of expertise and experiences between CSOs and UN agencies as well as between the two districts. Also, limiting the effectiveness was the absence of a lead agency (or a designated ‘Project Manager’) for Outcome 4 that could extend overall coordination and improve implementation. Uncoordinated delivery of outputs has diluted the efforts. For example, in order to address issues of vulnerable children, there should have been well-coordinated services relating to health and nutrition, protection, and education. The engagement of the relevant Government Agencies was activity-specific, rather than on the holistic system. The situation has been exacerbated by lack of a rigorous monitoring system with information fed back to the CSOs/UN Agencies for improving coordination of delivery of services.

## Efficiency

Detailed budgets and end-of-the Project expenditures were not available. Thus no attempt has been made to analyse output-based expenditures. However, the following factors have adversely affected efficiency of Project implementation.

- Delays in implementation:	Inordinate delays in project implementation have diminished the efficiency of interventions especially in the promotion of livelihoods. Of particular concern are the large investments in the milk chilling centres (some of which are yet to commence operation) and the Seed Paddy facility, which is yet to start operations.  Ideally, these should have been operated and managed for some time to assess their functioning, and to fix any teething problems. Furthermore, since the Project is now over, there are no earmarked funds for any urgent maintenance of machinery.

- Livelihood initiatives:	A more careful assessment of individual versus group livelihood enterprises may have led to more efficient use of limited financial resources. For example, to what extent does promoting of individual enterprises give rise to additional employment?  What kind of additional employment is likely to be generated? Anywhere close to decent work? Against this backdrop would be the consideration for establishing common income generating facilities. For example, would a common facility with 10-12 tailors resulted in long term benefits through more efficient use of resources than handing over sewing machines to 10-12 individuals who compete with each other for limited local markets (as was observed by the evaluation team)?

## Sustainability

Sustainability is assured by the commitment of the Ministry which considers the Policy as the blueprint for future resettlement. Given the fact that the Policy has been drafted within a framework of international covenants, there is a good chance that other donors will continue to support follow-up and related work on Policy dissemination and implementation.

As noted earlier, many of the interventions have been delayed, and are yet to take off. As a result of delays in delivery, evidence of sustainability could not be gleaned.  However, many aspects of sustainability have not been factored into the design of the Project even at the time of its launch.  The evaluation team, for instance, has identified three broad concerns surrounding sustainability:

- Sustainability can be ensured only with continued advocacy on socio-cultural issues that tend to separate communities and prevent social cohesion.  This has not been planned.  As a result, social tensions arising out of ethnic and other differences might continue to fester and prevent integration of the different communities.

- Not considering group livelihood ventures could adversely affect the sustainability of the individual enterprises. The individual livelihood promotion interventions currently provide a minimal support at the household level.  In most cases, they are at best supplementing family earnings.  It is not obvious how such individual enterprises (such as tailoring) will pan out in the future especially with increasing competition in the markets.

- Questions of sustainability surround many of the Project’s interventions.

  - A major concern is the future of economic infrastructure (e.g. Seed Paddy facility, milk chilling centres). Some of these facilities are yet to operate, and the Societies that are expected to take over have no wherewithal to maintain them. For instance, the Office bearers of the Seed Paddy Society are sceptical about the viability of the facility.

  - Addressing the psychosocial needs of the families has been an important contribution of the Project.  The Partners have developed a well-trained cadre of psychosocial counsellors and befrienders who will not be supported in the future to continue their good work in the rural areas. The evaluation team noted the commendable work of the Counsellors supplementing the work of Health Department. This definitely needs to be continued.  However, the sustainability of these psychosocial welfare activities is doubtful given that the CSOs implementing the intervention do not have sources of funding to carry on the activities after the Project ends. The Partner in Jaffna, Shanthiham will use them in a limited way for their other projects, but the absence of a strategy to keep them in service is a matter of concern.

  - The interest among village level groups such as the Mothers’ clubs and Children’s Clubs has begun to wane.   There is no strategy to continue these Clubs, which are providing a service towards maintaining the health and nutritional status of mothers and children.

  - Questions of sustainability surround interventions on improving the quality of education. The Principals were sceptical about receiving funds to maintain the infrastructure provided by the Project. Another example is the application of multi-level teaching. The lack of interest among teachers is a matter of concern. Unless the school authorities and teachers show better commitment, the efforts of the Project may not be sustained.

Some activities that would ensure sustainability of improvements for teaching and learning processes are yet to be implemented (e.g. training the ISAs and the pre-school coordinators). There are presently no models for adaptation and localisation in its totality, and therefore scaling up is a challenge.  Similarly, the inability of school authorities to maintain WASH facilities is a matter of concern. Maintaining toilets in the some of the schools visited has been a problem.

  - In order to sustain protection initiatives, much needs to be done for strengthening the child protection system as well as the support for women affected by SGBV. Addressing the root causes of gender inequality requires a deeper study of social norms and practices that underlie gender-based violence.

  - Several youth enterprises have been launched in  2019.  At the time of evaluation, there was no mechanism to address any teething problems of beneficiaries and to provide the necessary technical assistance during the nascent stage of these enterprises to build the confidence of the beneficiaries. The evaluation team ha been informed that the relevant CSOs have been contracted for a six-month period post-project to provide this assistance.  This might be insufficient to firmly establish viability and sustainability of the enterprises. Similarly, the Project has not established formal links with credit and markets and this is likely to impact future sustainability.

# Evaluative Conclusions

## Conclusions

The Project has addressed a felt-need of conflict-affected IDPs by attempting to provide a package of relief to normalise their life on return to their original settlements. The pivotal actions include: development of a Policy for providing durable solutions to returnees, resolving land tenure issues, and offering a package of services needed for leading a normal life. Some of the actions which have demonstrated success are replicable, and would provide lessons for the Government as blueprints for action in similar contexts elsewhere.

The performance of the Project on a scale of 1 to 4 is summarised as follows:

- Relevance of the project: ‘Highly Satisfactory’ (4), as it addresses priorities of the Government, District and local authorities, communities, UN Agencies and its Partners, the donor, as well as the European Union.

- Effectiveness of the Project: Satisfactory (3). Beneficiary selection has been rational. However, poor inter-agency coordination, gaps in community structures, issues with livelihood interventions, and community conflicts have adversely affected this grading.

- Efficiency of the Project: Less-than-Satisfactory to Satisfactory (2.5). Due to limited information available, there was no opportunity to review project expenses via-a-vis outputs. Most outputs are not of the required quality and have not been achieved in a timely manner. The Project could not establish formal links with credit and markets, and the Bankers’ Forum did not get off the ground. The individual livelihoods provide only a supplementary income, sometimes not sufficient.

- Sustainability of the Project: Less-than-Satisfactory to Satisfactory (2.5). Apart from the rolling out of the National Policy and improvements to health infrastructure, there has been no time in the Project to demonstrate sustainability. However, sustainability of operations of the various groups established by the Project is highly uneven.  For instance, the Counselling Programme, the core groups and the mental health care components are struggling to maintain the services, although the community members and implementing partners are willing to provide intellectual support.

## Lessons Learnt

There are seven key lessons from the evaluation.

- Theory of change:  A more realistic Theory of Change encompassing all interventions needs to be developed for such short duration projects.  Pathways of change need to be realistic and well-articulated for such time bound projects. Many of the context, process and sectoral elements articulated in the Project’s Theory of Change could not be acted upon. Similarly, many of the initial or catalytic activities for re-establishing lives of people displaced by the war and also to establish a return to “normal” could not be realized given the short duration of the Project (cf. Section 4.1).

- Project design:  More effort and thought should go into the designing of the interventions – drawing on the lessons learned from similar interventions tried out earlier in Sri Lanka.  Also, the interventions should fit into more comprehensive medium term strategies that should be developed for the different areas of work.  If this had been done, many of the factors adversely affecting the effectiveness, especially of the livelihood component of the Project, could have been avoided.     Time lines for project implementation should be more realistic so as to ensure that the interventions can be stabilized.  More thought should be given to the potential for scaling up of the interventions.  Similarly, indicators for monitoring and tracking effective implementation and ‘success’ should be built into the project from the very beginning.

- Implementation Modality:	The Project has chosen CSOs for field-level implementation. Although their duration is around nine months, many of them have individually provided a commendable service, possibly through their own expertise, commitment, and field presence. Such a model can be made more effective by having a closer collaboration and integration as well as sharing of experiences between CSOs both inter and intra districts. Better CSO integration could have been realized with closer collaboration between UN agencies.

Equally, collaboration between Government partners (e.g. MoE, Dept. of Health) has worked well in infrastructure development and supply of furniture and equipment. In these instances, the success has been due to government agencies undertaking work directly with funds provided by UN agencies.

The Project has also used Cooperatives in a positive way.  An example is the Fisheries Society in Muttur where decision-making has been entrusted to the Society. This has brought a sense of ownership to the Society, and has encouraged the Society to be self-reliant.

- Beneficiary Selection:	A key feature of the Project is beneficiary selection.  Applying a set of transparent and well defined criteria has resulted in the identification and selection of, by and large, a majority of well deserving returnees. This approach could have been improved further by consulting the relevant officials (e.g. Agriculture officials in selecting beneficiaries for homestead agriculture).

- Psychosocial care:	The Project has provided much-needed psychosocial support to stabilise people, often times, before they took up livelihoods and other activities. This is a replicable model particularly in areas where people have experienced psychological trauma.

This approach has demonstrated the value of psychosocial care in the post-conflict context as a prelude to providing other forms of assistance, and should constitute an essential component of similar projects.

- Community involvement and ownership:  Community ownership is critical for such projects to be sustained.  Consultations with the communities to assess their needs, the formation of various community-based groups, and the engagement of volunteers go a long way in ensuring effective implementation of projects.

- Sustainability: The Project highlights the importance of focusing on the sustainability of the interventions once the funding ends.  In some of the cases, such as the building of health infrastructure, the maintenance and upkeep has become the responsibility of the government itself.  However, in other cases, such as with psychosocial counselling and infra-structure provided to the Police, care should be taken upfront to plan provision of staff and ancillary services and ways of continuing with the service once the Project funding stops.

## Recommendations

Recommendations relating to (i) Project strategy, (ii) Programme strategy; and (iii) Reporting, monitoring, evaluation and learning strategy are listed below:.

- Project Strategy

- Lack of a proper exit strategy for the Project has resulted in an uncertainty on the sustainability of some of the Project’s interventions. Appropriate phasing out strategies should be developed for education, WASH, psychosocial care, and enterprise development in particular.

- A Project of this nature requires close interaction amongst the parties. Mechanisms should be evolved for better interaction amongst UN Agencies, amongst Partners, and between districts in order to improve delivery and quality. The appointment of a ‘leader’ who could coordinate the work programme might also improve coordination and implementation.

- The duration of such a Project should be sufficient to ensure proper planning, design, execution and evaluation of outcomes, if not impacts.  Even though the duration of the Project has been extended from 18 months to 24 months, many actions remained either incomplete or were just completed without time to assess effectives. It is not clear why the UN Agencies agreed to this time duration, given their experience in projects of this nature.

- UN Agencies may consider establishing protocols to record in-kind contributions from themselves and the Partners (as required in the Agreements), which would form an important side-line to report.

- Sufficient attention should be paid to scaling up efforts.

- Programme Strategy

- National Policy:

  - Awareness building:	Greater awareness about different aspects of the Policy needs to be created particularly at the local government levels and among communities at the grassroots level.

  - Action Plan:	More work is needed to translate Policy into action. The bureaucracy in the Government has to adjust its thinking to ensure that all development work falls within the framework of the Policy. For this, the capacities of various agencies should be assessed to ensure that they have the necessary skills and competencies to translate Policy into well directed and coherent sets of actions  that can provide durable solutions.

  - Issues relating to Caste discrimination:		A special effort should be made to address significant caste-based discrimination especially among the IDP communities.  A similar effort is also needed to address the concerns of a larger-than-normal ageing population amongst the returnees who have very little family support.

- Education:

  - Improve training: Training on multi-level teaching should be made systematic as there are no quality circles in schools to discuss the learning from the application of the methodology and adapt the methodology to the education context. It is also important to train the ISAs to monitor the teachers and to promote learning and replication in other schools;

  - Focus on cost-effectiveness of teacher training: For future initiatives, options should be explored on cost effective ways of training teachers in schools rather than getting them out of the school for Centre-based training. School-based training using teachers who have demonstrated good practices rather than depending on the ISAs for adaptation and localization may be a better option;

  - Extend support to improve quality: UNICEF should consider providing technical support to the Partners so that the qualitative inputs in ECD and teaching and learning could be improved. The technical standards and advocacy of UNICEF is not reflected at the ground level in the Project; and

  - Tap the engagement of communities and children: The engagement of children and communities should be part of the project delivery model rather than tokenistic. Participatory tools should be used with children and parents throughout the project cycle. If children are empowered through the use of such tools they will be active in the learning process.

  - Improve coordination: Improved coordination between the service sectors of health, child protection, psychosocial support and livelihood support would have enhanced the quality of education delivered.

- WASH

  - The Project should pay more attention to detail in regard to WASH facilities. For example, special efforts should be made to avoid open area urinating in schools, provide fencing as necessary, establish waste water and solid waste management systems, ensure use of high quality materials (e.g. taps, door locks), maintain cleanliness of toilets, extend regular MHM training to children, particularly 13/14 year-olds who become adolescents, and revitalise school health clubs in order mainstream children in WASH.

- Land Tenure:

  - A suitable post-project arrangement should be put in place to facilitate communities to convert their temporary land permits to deeds.

- Psychosocial care:

  - Supplementing Government efforts in rehabilitation of affected communities through provision of psychosocial support and mental health care has been an important contribution of the Project, especially because the Health authorities have not been able to provide the required psychosocial support in remote areas. UN Agencies and Partners should explore with the Provincial Health Department ways of sustaining these important efforts.

  - The Project should present its contributions and findings, particularly on psychosocial support and mental health to higher authorities such as the District Secretaries, Divisional Secretaries, and the Department of Health to explore possibilities of absorbing the cadre of trained staff into an appropriate service for sustainability.

- Protection Services:

  - Link Mothers’ Clubs/ Women’s Committees and Children’s Clubs/ Children’s Societies and VCDCs to the Child Protection Units.

  - Launch a study on the social norms and practices that sometimes enforce gender-based violence in order to gain a deeper understanding of the root causes of gender inequality..

- Livelihood:

  - Reassess the appropriateness of small scale agriculture and animal husbandry ventures for individuals and communities, as against collective ventures.

  - To improve the viability and sustainability of small scale agriculture, consider providing extension services post-project, and offer the material support in two stages, so that those who show promise can be further supported in the second stage.

  - Customise the livelihood support model to suit the many dimensions and features of the IDPs, such as pre-displacement setting, IDP camp environment, duration of displacement, agro-ecological setting, and resource potential of the area and surrounding environment.

  - In regard to YED programmes, extend further technical and managerial assistance given that the commencement has been delayed, business plans have not been fully understood, and, in some instances, business registration has not been completed.

- Economic infrastructure:

  - UNDP should urgently address concerns expressed by the communities including the documentation of alleged malpractices relating to the Seed Paddy Facility in order to avoid reputational risks to UN Agencies and boost confidence of the stakeholders.

  - UNDP should continue to extend technical and managerial assistance to operate the Seed Paddy Facility as well as milk chilling plants for at least six months until teething problems are resolved.

- Integrated Approach adopted by the Project:

  - Improved coordination amongst implementing and UN agencies backed by a rigorous monitoring mechanism can further enhance the effectiveness of the integrated approach used in the Project.

- Reporting, Monitoring, Evaluation and Learning Strategy

  - Adopt a more rigorous and systematic M&E protocol that identifies delays in implementation, highlights stakeholder concerns and strengthens institutional linkages needed to improve implementation.

  - Demonstrate better the Project’s visibility and achievements. This can be done by improving the prominence of signage (which were often missing).

  - Build an evaluation plan into the design of the Project itself.

  - Organize regular meetings of partners, stakeholders and community members to understand and disseminate  learnings from different interventions

- Recommendation for Advocacy with GoSL:

- Ancillary support from Police Department:	GoSL is expected to provide ancillary support including staff in order to ensure full utilisation of the infrastructure created under the Project.  Given the investments made on the newly-established Children’s Desk Unit at Muttur Police station, UN agencies should work with GOSL to:

  - provide a female police officer fluent in speaking in Tamil and understanding of legal implications and rights of women and children for effective functioning of the Unit;

  - offer the victimized women and children free and easy access to the Unit without being interrogated by the male police officers at the main entrance of the police station (at Muttur); and

  - strengthen the Units with adequate transport and office facilities.

In conclusion, the Project has made significant contributions to promoting the wellbeing of IDPs and has supported re-integration of them with the community. More however need to be done, and adopting the recommendations can contribute to sustaining the efforts of the Project.  It is nevertheless important to recognize that the commitment of the Government and active engagement of the community, like in Sri Lanka, are essential for maximising the contribution of any form of catalytic support to peace building efforts.

# Annexes

| Annex 2.1: | Project Implementation Responsibilities/Technical contributions |
| --- | --- |
| Annex 3.1: | Terms of Reference |
| Annex 3.2: | List of documents |
| Annex 3.3: | List of Focus Group Discussions |
| Annex 3.4: | List of Key Informant Interviews |
| Annex 3.5: | Field Visits |
| Annex 4.1: | Key Observations (Education) |
| Annex 4.2: | Telephone Survey to assess Youth Enterprise Development Component |

Annex 2.1 – Project Implementation Responsibilities/Technical contributions

| Activity | IMPLEMENTATION |  |  |
| --- | --- | --- | --- |
|  | Responsible UN Agency | Government Partners | CSO Partners |
| Output 4.1: Evidence based strategy for implementation of the National Policy on Durable Solutions for Conflict Affected Displacement is in place |  |  |  |
| Activity 4.1.1. Provide dedicated technical expertise to operationalize the Policy, through the placement of technical expertise…. | UNDP | Ministry of Resettlement | None |
| Activity 4.1.2. Conduct workshops with Provincial and District Officials… | UNDP | Ministry of Resettlement | None |
| Activity 4.1.3. Production of informational materials…. | UNDP | Ministry of Resettlement | None |
| Activity 4.1.4. Support the District level officials to conduct meetings with displaced populations and resettled persons | UNDP | Ministry of Resettlement/ GA | None |
| Activity 4.1.5. Provide technical support to the Ministry of Resettlement on monitoring/database…. | UNDP | Ministry of Resettlement/ GA | None |
| Activity 4.1.6. Conduct a survey among IDPs (linked also to 4.1.5)… | UNDP | Ministry of Resettlement | None |
| Activity 4.1.7. Support to monitor and evaluate development programmes and projects implemented areas of the Northern and Eastern provinces…. | UNDP | Ministry of Resettlement/GA | None |
| Activity. 4.1.8. Support the legal aid commission to provide legal support to displaced and resettled communities | UNDP | Ministry of Resettlement | None |
| Output 4.2: Vulnerable households in the Northern Province supported to secure their land tenure rights |  |  |  |
| Activity 4.2.1: Provide critical surge support to the Survey Department in the Northern Province | UN-Habitat | Provincial Survey Department | None |
| Activity 4.2.2: Facilitate issuance of legal land tenure documents by supporting government land titling programmes | UN-Habitat | Provincial Land Development Dept. | None |
| Output 4.3: Targeted resettled communities have access to an integrated and sustainable package of socio-economic services to help them rebuild their lives |  |  |  |
| Activity 4.3.1: Design, document and assess the delivery of a package of integrated and sustainable socio-economic services for returnees… | UNDP UNICEF | District Secretaries Divisional Secretaries | Jaffna OfERR Ceylon Trincomalee CCCD; Caritas; CDF; PWJ |
| Activity 4.3.2: Support the renovation/repair and equipping of damaged schools in resettlement areas, and improve teaching/learning practices… | UNICEF | PDoE and its agencies including ECCD | Jaffna OfERR Ceylon Trincomalee CDF |
| Activity 4.3.3: Restore access to health services…. | UNDP UNICEF | RDHS; MOH, Telippalai | Jaffna SOND Trincomalee CCCD |
| Activity 4.3.4: Increase access to safe water and adequate sanitation through….. | UNDP UNICEF | NWSDB; PDoE and its agencies; RDHS; MoH; PDoI | Jaffna OfERR Ceylon Trincomalee CCCD |
| Activity 4.3.5: Facilitate access to protection services…. | UNDP UNICEF | PDoP&CC | Jaffna Shanthiaham & SOND Trincomalee EHED |
| Activity 4.3.6: Establish or strengthen an existing community services centre in each pilot site…. | UNDP UNICEF | DS; WDO, Grama Niladhari, DO, Samurdhi Officer | Jaffna SOND Trincomalee PWJ |
| Activity 4.3.7 Provision of support for sector-based livelihood assistance for resettled communities…. | UNDP | District Secretaries Divisional Secretaries | Jaffna OfERR Ceylon Trincomalee PWJ |
| Activity 4.3.8 Support to improve CBO capacity development, extension/ administrative services… | UNDP | District Secretaries Divisional Secretaries | Jaffna OfERR Ceylon Trincomalee PWJ |
| Activity 4.3.9 Construction/renovation of economic infrastructure… | UNDP | District Secretaries Divisional Secretaries | Jaffna OfERR Ceylon Trincomalee PWJ |

Annex 3.1 – Terms of Reference

The UN catalytic engagement with resettlement and durable solutions provides immediate support to several of the Government’s priorities that are designed to enable families to more quickly return to their land, secure their land tenure and in so doing start re-building their lives and attaining durable solutions.

Through outcome 4 of this project, the UN collaboration are committed to pilot an integrated package of support, which includes:

- Livelihood and income generation support at community level with provision of productive inputs, skills trainings, equipment and vital infrastructure to catalyse local employment opportunities and create more sustainable sources of income generation as well as service delivery improvements;

- Support to improve teaching/learning practices in schools/pre-schools and support the renovation/repair and equipping of damaged schools/pre-schools;

- Restoration of access to health services and safe water and adequate sanitation through the construction/repair of infrastructure. Establishment of community groups on nutrition and training of health officers;

- Facilitate access to protection services, including psychosocial support, by restoring institutional and community level protection systems;

- Land surveys of newly-released and resettled lands.

The specific objectives of the final evaluation are:

- Assess the DAC criteria (Relevance, Effectiveness, Efficiency, Impact and Sustainability) of interventions implemented and results achieved in line with Theory of Change and results framework;

- Analyse the integrated approaches, synergies, multi-stakeholder coordination, monitoring and social accountability systems implemented and piloted by UN agencies;

- Provide recommendations to identify the optimal modality of delivery of resettlement support in line with the Policy on Durable solutions and Peace building Priority Plan. Provide necessary policy recommendations pertaining to resettlement solutions; and

- Document the best practices and lessons learnt from the project and disseminate the learnings among all right holders and duty bearers to ensure accountability of the findings.

Scope:

- The evaluation will be limited to the interventions implemented under Outcome # 4 (provision of durable solutions) by UNICEF, UNDP and UN-Habitat and targeting re-setlle communities in districts of Jaffna (in Telippalai and Kopay DS Divisions covering 12 GN Divisions) and Trincomalee (in Muttur DS Division covering 8 GN Diviisons). Sampling methodology to be discussed and agreed with UN agencies during Inception Phase.

- Interventions implemented during the entire project period from April 2017 to April, 2019 will be subjected to the evaluation;

- The main stakeholders of the evaluation will be the European Union Delegation, UN Agencies, Government counterparts at all levels, NGO Partners, community groups and beneficiaries, especially vulnerable and marginalised groups;

- The project will be evaluated against the criteria relevance, effectiveness, efficiency, impact and sustainability. The evaluation should analyse coordination monitoring and social accountability systems and provide recommendations regards to the optimal package of integrated services for resettlement and distil lessons learnt and best practices for future programmes;

- The design of the evaluation should be guided by an equity and gender perspective and conducted in transparent, inclusive, and participatory manner;

- The evaluation should be carried out in there phases: 1) Inception 2) Data collection 3)Analysis and Reporting and 4) Knowledge dissemination.

- The evaluation should be guided by commonly accepted evaluation norms, standards and approaches such as UNED guiding framework methodology and UNEG Ethical Guidelines and Code of Conduct;

- The evaluation should be carried out by a Team of consultants led by an international consultant.

- The evaluation will be managed by UNICEF with technical inputs coming from all UN Agencies concerned.

Annex 3.2 – List of documents

- Annual Report 28 May 2018

- Baseline Report, CEPA; May 2018

- Consolidated Financials; 31 December 2018

- Dossier of documents presented by the Marutham Seed Producers’ Society

- List of Beneficiaries, Jaffna

- List of Beneficiaries, Trincomalee

- List of Partnership Contracts with CSOs

- Monitoring and documenting Resettlement Support – EU Catalytic Support to Peace Building in Sri Lanka; CEPA; April, 2019

- MoU and Contract Addendum I

- National Policy on Durable Solutions for Conflict-Affected Displacement

- Needs Assessment, Jaffna; CEPA

- Needs Assessment, Trincomalee; CEPA

- Outcome Note; 3 December 2017 (Theory of Change Explained; CEPA)

- Pictures and Media References; UNICEF (undated)

- Progress against Logical Framework; 27 May 2018 (Partial)

- Project Document and Agreement

- Project Presentation by UNICEF – June 2018

- Q 1 Progress Report; CEPA

- Q 2 Progress Report; CEPA

- Q 3 Progress Report; CEPA

- Resettlement locations; Jaffna (Map)

- Resettlement locations; Jaffna and Trincomalee

- Resettlement locations; Sampoor (Map)

- RFP for Final Evaluation (UNICEF)

- UNICEF Work-plan

Annex 3.3 – List of Focus Group Discussions

| Date and Time | Group | Venue |
| --- | --- | --- |
| JAFFNA |  |  |
| 2 June 2019; 15 30 h | A mixed Group of Returnees including Members of Core Group, VCDC, Mothers’ Club, and representatives of Community Counsellors, Befrienders, and Youth involved in Micro enterprises | Community Centre, Nallinakkapuran, Maviddapuram, Kankesanthurai |
| 3 June 2019; 09 30 h | Fishery beneficiaries | Myliddythurai North Village Centre |
| 3 June 2019; 10 30 h | Mothers’ club | Palaly East |
| 3 June 2019; 14 15 h | Returnees and Livelihood beneficiaries | Myliddythurai North |
| 4 June 2019; 09 30 h | Ground-water recharge Group | Palai Veemenkamam |
| 4 June 2019; 09 30 h | Returnees and Livelihood beneficiaries | Antonypuram Community Centre , Valalai |
| 10 June 2019; 09 30 h | Children aged 10/11 years, | Kuddiyapulam Government Tamil Mixed School (GTMS) |
| 10 June 2019; 10 00 h | Parents of children aged 5/6-10 years | Kuddiyapulam GTMS |
| 10 June 2019; 10 30 h | Adolescent Female Students (WASH) | Kuddiyapulam GTMS, Vayavilan |
| 10 June 2019; 11 00 h | School Health Club (WASH) | Kuddiyapulam GTMS, Vayavilan |
| 11 June 2019; 09 30 h | Parents of preschool children | St. James Preschool, Palali South, Wajavilan |
| TRINCOMALEE |  |  |
| 6 June 2019; 09 45 h | Parents of children aged 5/6-10 years | Sri Murugan Vidyalayam, Sampoor |
| 6 June 2019; 09 45 h | Children aged 10/11 years, | Sri Murugan Vidyalayam, Sampoor |
| 6 June 2019; 12 00 h | School Teachers | Sri Murugan Vidyalayam, Sampoor |
| 6 June 2019; 13 00 h | Principal and Teachers (WASH) | Sri Murugan Vidyalayam, Sampoor |
| 6 June 2019; 11 45 h | Members of VCDC | Grama Niladari Office, Sampur East, |
| 06 June 2019; 15 00 h | Educational support Group | Sampur West-Community Centre |
| 06 June 2019; 16 30 h | Youth Group & Children’s Club (Navarathnapuram) | Navarathnapuram - Community Centre |
| 6 June 2019; 11 00 h | Members of the Soodaikuda Fisheries Society | Soodaikuda Multipurpose Building |
| 6 June 2019; 11 45 h | Members of the Dairy Farmers’ Development Co-op society | Muttur |
| 6 June 2019; 15 00 h | Members of the Marutham Seed Growers’ Society | Munnampodivettai Seed Processing centre |
| 7 June 2019; 10 00 h | Parents on home-based early stimulation and community outreach in ECD | Pulenthiran Preschool Sampoor |
| 7 June 2019; 12 00 h | School Teachers | Sri Murugan Vidyalayam, Sampoor |
| 7 June 2019; 09 45 h | Adolescent Female Students (WASH) | Sri Murugan Vidyalayam, Sampoor |
| 7 June 2019; 11 00 h | School Health Club (WASH) | Sri Murugan Vidyalayam, Sampoor |

Annex 3.4 – List of Key Informant Interviews

Jaffna District

Aathavan, Gnanalingam (Mr) (SLEAS III), Deputy Director of Education (Admin), Vaikamam

Ajanthan, J (Ms), Public Health Midwife, MOH Office, Telippalai

Anjanadevi, Srirangan (Ms), Deputy Director, Provincial Department of Agriculture, Jaffna District

Anurathan,S (Mr), Grama Niladari, J/252

Arudkumaran,  Uma (Ms), Science Teacher, Kuddiyapulam GTMS, Vayavilan

Bamini, S (Ms), Development Assistant, Divisional Secretariat, Telippalai

Derittan, T (Ms), Public Health Midwife, MOH Office, Telippalai

Elangeeran,P (Mr), Development Officer, Divisional Secretariat, Telippalai

Ensilirukman, Pathma (Ms), Principal - Kuddiyapulam GTMS, Vayavilan

Hesho, Prabakaran (Ms), Valalai Malalaika Preschool, Valalai East

Iddamalgoda, I D S D (Ms), Nursing Officer, Special Baby Care Unit, Base Hospital, Telippalai

Jeya,T (Ms), WDO, Divisional Secretariat, Telippalai

Kandeepan, Nadarajah (Mr), Deputy Director of Education (Development), Vaikamam

Kayathry,Rajan (Ms), Grama Niladari, J/250

Krishnakanes,T (Mr), CRPO, Divisional Secretariat, Telippalai

Majuran,P (Mr), Grama Niladari, J /244

Marin Benita,B (Ms), Grama Niladari, J/236

Mathanaruban,S (Mr), Development Officer, Divisional Secretariat, Telippalai

Merlin, Alex Ravindran (Ms), Pre-School Teacher, St. James Pre-school, Palaly South

Nadunsaralathan, (Mr), Development Officer, Divisional Secretariat, Telippalai

Nagasuganthini, Jeyaseelan (Ms), Child Desk Officer, Base Hospital, Telippalai

Nandani , Sudarshan (Ms), Pre-School Teacher,  St. James Pre-school, Palaly South

Nirmalanathan,N (Mr), Public Health Inspector, MOH Office, Telippalai

Pieris, S T (Mr), Programme Coordinator (School Health, Nutrition & WASH Unit), Provincial Department of Education, Northern Province

Raageev, Kayathri (Ms), Grama Niladhari J/250

Ramanathan, S (Mr), Principal, J/Veemankaman Maha Vidyalayam

Raveendran, N (Mr), Grama Niladari, J/235

Rukmen, Pathma Ensili (Ms), Principal, Kuddiyapulam Government Tamil Mixed School

Sanjitha, Sadagoban (Ms), Probation Officer, Base Hospital Telippalai

Saranja, T (Ms), Nursing Officer, Special Baby Care Unit, Base Hospital, Telippalai

Sarvaraja, S (Eng), Irrigation Engineer, Jaffna

Sathees, Ashokathasan(Mr), Grama Niladari, Valalai, Kopay

Sivakumar, Veerasingam (Mr), ADP, Divisional Secretariat, Valigamam North

Sivakumar, Veerasingham (Mr), Assistant Director of Planning, Divisional Secretariat, Telippalai

Sivathasan,S (Dr), Medical Officer of Health, MOH Office , Telippalai

Sutharsan, Joyce (Ms), Grama Niladari, J/237

Tharshika, K (Ms), Development Officer, Divisional Secretariat, Telippalai

Thayaparan,T (Mr), Development Officer, Divisional Secretariat, Telippalai

Thayaparan,T (Mr), Grama Niladari, J/233

Thuraisamy, T (Ms), Special Grade Nursing Officer, Base Hospital, Telippalai

Vinotha,K (Ms), CRPO, Telippalai

Wimalasena, H (Dr), Medical Superintendent, Base Hospital, Telippalai

Yogaveny, R(Ms), Public Health Nursing Sister, MOH Office , Telippalai

Trincomalee District

Amarasinghe, A G S(Dr), Muthur Hospital

Arafath, Packeer, (Mr), ADP, Divisional Secretariat, Muthur

Arulkumaran, S (Dr), Provincial Director of Health Services, Trincomalee

Aruselvam (Mr), Probation Officer -Muthur

Ashani, W A M Anuruddhika (Ms), WPC/ OIC, Women’s and Children’s Desk, Women and Children Bureau  Police Station Sampur West

Charles,  Rousia (Ms), Pre-School Teacher, Pulenthiran Pre-school

Garusingha, S D (Mr), Officre-in-Charge, Crimes Division, Muthur Police Station

Jegan, T (Mr), Treasurer, Marutham Seed Producers Society

Kanudeen,Nishos (Mr), Administration Officer, Divisional Secretariat, Muthur

Kayalvili, B (Dr), Medical Superintendent, Muthur

Krishnavaani (Ms), Psycho-Social Counsellor, Trincomalee Base Hospital

Mansoor, M K M (Mr), PDE Office, Trincomalee

Naufeek (Mr), CRPO-Divisional Secretariat Muthur

Nishanthini, U (Ms), Development officer, Sampur West

Pakkiyaeswaran, T (Mr), Principal, T/Mu/Sampoor Maha Viddiyalayam

Pakkiyeswaran, S (Mr), Principal, Sri Murugan Vidyalayam, Sampoor

Parameshwaran, B (Mr), Deputy Director, Provincial Department of Agriculture, Trincomalee District

Pratheepan, N (Mr), Assistant District Secretary, Trincomalee

Premananth, Y (Dr), Regional Director of Health, Trincomalee

Priyadharshana, Upul (Dr), Psychiatrist, Trincomalee Base Hospital

Puwaneswaran, S (Mr), Agricultural Instructor, Sampoor

Rafeek, M S M (Mr), Community Development officer, DS Office, Muthur

Rajapaksha, M B D (Mr), Officer In Charge, Police Station, Muthur

Rajarathanm S (Mr), President, Marutham Seed Producers Society

Rajaroopan, G (Mr), Secretary, Marutham Seed Producers Society

Ratnakala,M (Ms), S P O, Sampur West

Renuka, V (Ms), Grama Niladhari, Sampur West

Rizath, A M (Mr), Community Development officer, DS Office, Muthur

Satchthanandathan, M (Mr), Principal, T/Mu/Sampoor Sri Murugan Viddiyalayam

Satheeskumar, A (Dr), Muthur Hospital

Sathyadevi,S (Ms), S D O, Sampur West

Sivashakthy, S (Ms), PHM, Sampoor

Siyanthan, P (Mr), Development officer, DS Office, Muthur

Sutharshini, J (Ms), PHM, Jayanagar

Teachers (2), Pulenthiran Preschool, Sampoor

Thanapal,  Alfred (Mr), President, RDS, Santhosapuram

Thevarajani, R (Ms), PHM, Chenaiyoor

Umashankar, S (Mr), Development officer, Sampur West

Uthayakumar, Y (Ms), SPHM, Sampoor

Vijayakumari ,Uthayakumar (Ms), Pre-School Teacher, Pulenthiran Pre-school, Sampoor

Other

Anushyanthan, Vaidehi (Ms), Assistant Director, Ministry of National Policies, Economic Affairs, Resettlement and Rehabilitation, Northern Province Development and Youth Affairs

Gunarathna, Buddhima (Ms), Project Management Assistant, UNDP

Lokuge, Gayathri (Ms), Senior Research Professional, CEPA

Romeshun, K (Mr), Programme Officer, CEPA

Senthilnanthanan, P (Mr), Additional Secretary, Ministry of National Policies, Economic Affairs, Resettlement and Rehabilitation, Northern Province Development and Youth Affairs

Sivagnanasothy, V (Mr), Secretary, Ministry of National Policies, Economic Affairs, Resettlement and Rehabilitation, Northern Province Development and Youth Affairs

Project-related Staff

Ajithkumar, J D (Mr), UNICEF

Andrew, N (Mr), Programme Officer, UNICEF

Ariyaretnam, R (Mr), Federation Manager, CDF

Arunthini, K (Ms), Counsellor, Shanthiham

Buhari, A W M (Ms), Secretary, CCCD

Fernando, Shanek, UNICEF

Francis, G A (Mr), Programme Manager, EHED

Gnanapragasam Antony, Francis (Mr), EHED Caritas, Trincomalee

Jeevamuhunthan, S (Mr), PSW, Shanthiham

Jeevathas, A C (Mr), EHED

Jeyanathan, A T, UNICEF

Jothirajah Karunenthira, UNDP

Kathiramalaivaganan,N (Mr), EHED Caritas, Trincomalee

Kulasegaram Partheepan, UNDP

Mayuran, A (Mr), Programme Manager, OfEER Ceylon

Mohanaprasath, A (Mr), EHED Caritas, Trincomalee

Mugunthan, K (Mr), M&E Associate, UNDP

Mugunthan, V (Mr), Programme Officer Education, CDF

Partheepa, K (Mr), FPS-UNDP

Patterson, R (Ms), CFO, UNICEF

Prakalathan,K (Mr), EHED Caritas, Trincomalee

Rizmy, M A M (Mr), Coordinator, EHED

Rizmy, M A M (Mr), EHED Caritas, Trincomalee

Sabaratnam Karthikeyini  (Ms), Consultant, UNICEF, Kilinochchi

Sathe, Samitha (Ms), Programme Officer, Child Protection, UNICEF

Sayanthan, T (Mr), Programme Manager, Shanthiham

Selvar, Rodney (Mr), UNICEF

Seyon, P (Mr), Field Project Associate, UNDP

Sharvanandha, R (Mr), Field Programme Specialist, UNDP

Sivakumara, Radika (Ms); Programme Officer, CSD, UNICEF

Sugarma, K (Ms), Counsellor, Shanthiham

Sutharman, Nadaraja (Mr), Chief, Field Office, UNICEF North

Sutharsan, S (Mr) , District Programme Manager, OfEER Ceylon

Thavaseelan, Rajan (Mr), Director, Shanthiham

Zanfara, M (Ms), CCCD

Annex 3.5 - Field Visits

Jaffna District

| Date and Time & Location | Visit details |
| --- | --- |
| ENTERPRISE DEVELOPMENT-RELATED |  |
| 3 June 2019 11 00 – 13 30 hrs Vasavilan East, Kuttiyappulam & Thaiyyidi South | - Wasantharaja, Shihamani (Mr) (Agricultural business) - Jeyawardhan, Sinnarasa (Mr) (Carpentry Workshop) - Viji, Selvarasa (Ms) (Grocery Shop) - Jeganathan, Pillayakutti (Mr) (Grocery shop – still not operational) - Jeyarasa, Practixy (Mr) (mobile fish sales business) |
| WASH-RELATED |  |
| 6 June 2019, 14 00 hrs Santhosapuram | Beneficiary houses for WASH |
| EDUCATION-RELATED |  |
| 10 June 2019 09 30 tp 13 30 hrs Kuddiyapulam Government Tamil Mixed School | - Secondary data collection of demographics of children, teacher qualifications and facilities; - Classroom observations of teaching learning practices, classroom layout, use of learning corners and use of work tables for application of activity based teaching learning methods; - Review of work books and work bags of children and use of learning resource material especially for multi-level teaching, classroom Based Assessments of children, lesson plans of teachers and how learning resource materials are planned and carried out in the classroom. (Frequency of documentation and availability of assessments, remedial action for inclusive learning and additional support for children who learn at rate and depth below the average of same age peers) |
| 11 June 2019 09.30-11.00 St. James Preschool, Palali South, Wajavilan | - Secondary data collection of demographics of children, teacher qualifications and facilities; - Observations of learning environment and guided play practices including how all children are included in guided play according to their capacities and stages of development. |
| 11 June 2019 11.30-12.45 Walalai Malalaika preschool, Walalai East | Observed model preschool. - Secondary data collection of demographics of children, teacher qualifications and facilities; - Observation of learning environment and guided play practices including how all children are included in guided play according to their capacities and stages of development. |
| 11 June 2019 01.00-02.30 J/Veemankaman Maha Vidyalaya | - Secondary data collection of demographics of children, teacher qualifications and facilities |
| RESETTLEMENT-RELATED |  |
| 2 June 2019-5.30pm Nallinakkapuram Maviddapuram, Kankesanthurai | Field visit to observe and collect information/data: - The situation of the resettled families and their housing and availability of facilities such as water, toilets, electricity, access roads; - Land tenure issues; - Situation of women and children’s education, recreation facilities; - Level of community/social cohesion. Visit to beneficiaries for livelihood activities: - Sinnarasa, Parmeswary (Ms) (Cement Block-making) - Mahalingam, Kamalampikai (Ms) (Grocery shop) - Paskaran, Sellaih (Mr) (Agricultural machinery) - Selvakumar, Thaskumar (Mr) (Welding plant) |
| 3 June 2019 11 20 – 12 30 hrs Telippalai | Observations on the refurbishment of the Base Hospital, Telippalai; Paediatric ward; Special baby-care unit, and ancillary facilities; rest room for doctors; medical equipment provision |
| 3 June 2019 13 00 – 14 00 hrs Thaiyaddy South | Visit to the Multi-purpose Centre and meetings with the Grama Niladhari and collecting information on the utility of the Centre. |
| 4 June 2019 09 30 - 11 00 hrs Palai Veemankamam | Visit to Rain water recharging beneficiaries and collecting information and their perceptions - Nagasothy, Nadarasa (Ms) - Ammal, Baskaran Annapoorny (Ms) - Selvamalar, Balasubramaniam (Ms) - Paviththira, Kartheepan (Ms) Livelihood Activities of: - Murugaiyah, Muthan (Mr) (Livestock – Goat) - Rasanayagam, Vinod (Mr) (Mechanic) - Poothan, Poobalasingham (Mr) (Livestock-Cattle) - Sudharshana, Ravindrakumar (Ms) (Tailoring) |
| 4 June 2019 11 30 - 12 15 hrs Palm Cooperative Society, Telippalai | Visit to the office of the Telippalai Palm Development Cooperative Society to collect information on project interventions and outcomes, as well as observe their work. Met the following officials - Ramesh, V (President) - Thavapalan, K (Cashier) |
| 4 June 2019 12 45 – 13 45 hrs PVK North | Livelihood activities of: - Maluswaran, Sinnakutty (Mr) (Cultivation of banana) - Edward, Marusalin Claude (Mr) (Fishery) |
| 4 June 2019 11 00 hrs onwards Valalai, Palali East, and Vasavalan East | Livelihood activities of: - Kilbert Ramesh Kalpana, Amalarani (Ms) (block making, and currently owning a hardware shop) - Kovinthukandasamy, Saradadevi (Ms) (Livestock –Goat) - Sivanesan, Kavinthu (Ms) (Tailoring) - Sriharan, Mangaleswary (Ms) (Livestock –Cattle) - Murugupillai, Sinnathamby (Mr) (Homestead cultivation) - Tharmalingam, Pragashthanan (Mr) (Carpentry) - Kathiramalai, Thabotharan (Mr) (Electrician) - Selvanayagam, Senthalan (Mr) (Motor mechanic) - Kandaiyah, Rasathurai (Mr) (Homestead cultivation) - Mayurani, Sasikaran (Ms) (Livestock – poultry) |

Trincomalee District

| Date and Time & Location | Visit details |
| --- | --- |
| ENTERPRISE DEVELOPMENT-RELATED |  |
| 6 June 2019 12 00 – 13 45 hrs Sampoor 05, Muthur Sampoor West GN Division | - Ms Kajendran Vinoja’s enterprise (Grocery Shop, Photocopy services, battery charging for flashlights used by boat owners) - Mr S Pathmasiri’s enterprise (Welding Shop) - Mr Nandarasa Mithunarasa’s enterprise (Motorbike Repairing / Mechanical Workshop) - Mr Sachchithanantham Kajendran’s enterprise (Cement Blocks and other Concrete works) - Ms. Yogan Rohini’s enterprise (Tailoring Shop / Tailoring Business) |
| WASH-RELATED |  |
| 10 June 2019, 13 30 – 14 35 hrs Suthanthirapuram, Vayavilan | Resettled households for WASH compliance |
| EDUCATION-RELATED |  |
| 6 June 2019 09 45 – 13 00 hrs T/Mu/Sampoor Sri Murugan Viddiyalayam | - Classroom observations of teaching learning practices, classroom layout, use of learning corners and use of work tables for application of activity based teaching learning methods; - Review of work books and work bags of children and use of learning resource material especially for multi-level teaching, classroom Based Assessments of children, lesson plans of teachers and how learning resource materials are planned and carried out in the classroom (Frequency of documentation and availability of assessments, remedial action for inclusive learning and additional support for children who learn at rate and depth below the average of same age peers). |
| 7 June 2019 09 30 – 13 00 hrs T/Mu/Sampoor Maha Viddiyalayam | - Secondary data collection of the school demography and facilities, performance of children and teacher qualifications and cadre positions; - Observation of facilities including laboratory facilities, WASH, sports and extracurricular activities. |
| 7 June 2019 09 45 – 11 30 hrs Pulenthiran Preschool | - Secondary data collection of demographics of children, teacher qualifications and facilities - Observation of learning environment and guided play practices including how all children are included in guided play according to their capacities and stages of development. |
| RESETTLEMENT-RELATED |  |
| 6 June 2019 11 00 – 12 00 hrs Sampoor | Observation visit to Divisional Hospital, Sampoor and collection of information on project interventions and outcomes |
| 6 June 2019 12 45 – 13 30 hrs Kadatkaraichenai | Observation visit to dry fish & ice block making centre (Building renovated under the Project and equipment supplied) |
| 6 June 2019 16 30 17 30 hrs Munnampodiuthai | Observation visit to the Seed Paddy Processing Centre on project interventions and outcomes; meeting with officials of the Society: - Rajarathan, S (President) - Rajaroopan, G (Secretary) - Jegan, T (Treasurer) |
| 7 June 2019 14 00 – 17 15 hrs Patalipuram –Sampoor | Observed and collected information on the status of resettled temporary and permanent housing; poverty situation in the settlements, status of women and children, land tenure issues, and the status of the rural Hospital. Also visited the following livelihood activities: - Padmarani C (Ms) (Grocery shop) - Sugunadevi, H (Ms) (Grocery shop) - Thilakawathy, L (Ms) (Fishing) - Thusikaran T (Mr) (Carpentry work) - Palaninathan, Vijayatharshini (Ms) (Tailoring) Visited and observed the status of: - Milk collecting Centre, Patalipuram - Milk collecting Centre, Sampoor West |

Annex 4.1 – Key Observations (Education)

Table 1 - Essential information that needs to be displayed and monitored

| What is displayed | T/Mu/ Sampur Sri Murugan Viddiyalayam | T/Mu/ Sampur Maha Viddiyalayam | Kuddiyapulam Government Tamil Mixed School | J/ Veemankaman Maha Vidyalaya | Yes (%) |
| --- | --- | --- | --- | --- | --- |
| Vision and Mission statements | Yes | Yes | Yes | Yes | 100.0 |
| Educational goals of Sri Lanka | Yes | Yes | - No - | Yes | 75.0 |
| School catchment area map | - No - | - No - | - No - | - No - | 0.0 |
| Child population data | Yes | Yes | - No - | Yes | 75.0 |
| Data on teachers | Yes | - No - | Yes | Yes | 75.0 |
| Results analysis | - No - | Yes | Yes | - No - | 50.0 |
| Management structure | - No - | - No - | - No - | Yes | 25.0 |
| Updated notice board | Yes | Yes | Yes | Yes | 100.0 |

Table 2 - Results of the Grade Five Scholarship Examination

| Name of school | Year | Total sat |  |  | Passed (70 marks) |  |  | Cut-off marks |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Girls | Boys | Total | Girls | Boys | Total | Girls | Boys | Total |
| - T/Mu/Sampur Sri Murugan Viddiyalayam | 2016 | 5 | 4 | 9 | 5 100 | 4 100 | 9 100 | 2 40.0 | 1 25.0 | 3 33.3 |
|  | 2017 | 9 | 4 | 13 | 5 55.5 | 3 75.0 | 8 61.5 | 0 | 0 | 0 |
|  | 2018 | 8 | 5 | 13 | 8 100 | 5 100 | 13 100 | 0 | 0 | 0 |
| - T/Mu/Sampur Maha Viddiyalayam | 2016 | 9 | 14 | 23 | 7 77.7 | 12 85.7 | 19 82.6 | 0 | 2 14.2 | 2 8.6 |
|  | 2017 | 15 | 19 | 34 | 10 66.6 | 13 68.4 | 13 38.2 | 0 | 2 10.5 | 2 5.8 |
|  | 2018 | 17 | 20 | 37 | 11 64.7 | 15 75.0 | 26 70.2 | 0 | 0 | 0 |
| - Kuddiyapulam Government Tamil Mixed School | 2016 | 27 | 15 | 42 | 17 62.9 | 8 53.3 | 25 59.5 | 0 | 0 | 0 |
|  | 2017 | 12 | 14 | 26 | 6 50.0 | 7 50.0 | 13 50.0 | 0 | 0 | 0 |
|  | 2018 | 13 | 14 | 27 | 7 53.8 | 5 35.7 | 12 44.44 | 0 | 0 | 0 |
| - J/Veemankaman Maha Vidyalaya | 2016 | 1 | 4 | 5 | 0 0.0 | 1 25.0 | 1 20.0 | 0 | 0 | 0 |
|  | 2017 | 8 | 7 | 15 | 1 12.5 | 1 14.2 | 2 13.3 | 0 | 0 | 0 |
|  | 2018 | 2 | 4 | 6 | 0 0.0 | 1 25.0 | 1 16.6 | 0 | 0 | 0 |

Table 3 - The Perceptions of children

| School/subject | Level of motivation for learning |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Highly motivated |  | Somewhat motivated |  | Not motivated |  |
|  | Boys | Girls | Boys | Girls | Boys | Girls |
| To come to school | 75.0% | 76.2% | 12.5% | 9.5% | 12.5% | 14.3% |
| First Language (Tamil) | 75.0% | 76.2% | 6.3% | 14.3% | 18.8% | 9.5% |
| Second Language | 25.0% | 28.6% | 75.0% | 57.1% | 0.0% | 14.3% |
| English language | 0.0% | 0.0% | 0.0% | 0.0% | 100% | 100% |
| Environmental studies | 93.7% | 90.5% | 6.3% | 9.5% | 0.0% | 0.0% |
| Mathematics | 75.0% | 81.0% | 12.5% | 14.3% | 12.5% | 4.8% |
| Religion | 93.7% | 81.0% | 6.3% | 14.3% | 0.0% | 4.8% |

Table 4 - preschool building (Data collected from three preschools)

| Parameter | Yes | Somewhat/ sometime | No |
| --- | --- | --- | --- |
| Preschool building is a permanent structure | 3 (100%) | - | - |
| The preschool environment is safe and clean (without construction materials, deep pits, overgrown with weeds and littered.) | 1 (33.3%) | 2 (66.7%) | - |
| There is adequate space for play and learning corner (play house, sand pit, and toys) | 2 (66.7%) | 1 (33.3%) | - |
| The building is used only for the preschool | 3 (100%) | - | - |
| There is adequate lighting | 3 (100%) | - | - |
| There is adequate ventilation | 3 (100%) | - | - |
| There is a protective gate at the main door to stop children from going out | 3 (100%) | - | - |
| All electricity sockets and wires are covered | 2 (66.7%) | 1 (33.3%) | - |
| There is no heavy furniture in the areas where children play/ work | 2 (66.7%) | 1 (33.3%) | - |
| There is adequate furniture for children to sit and for desk activity (as specified for the height of children) | 3 (100%) | - | - |
| The creative work of children is displayed at their eye level | - | 3 (100%) | - |
| The preschool has reading corners, a sandpit, playhouse, a play kitchen and other activity corners | - | 3 (100%) | - |
| There is equipment for guided play such as water colours, clay, drawing paper, shapes and toy utensils | - | 3 (100%) | - |
| There is adequate storage space for play equipment and toys at a level that children can reach | 3 (100%) | - | - |
| There is an attractive learning environment (pictures, use of colours) | 3 (100%) | - | - |
| There is adequate (uninterrupted, potable supply from protected source) water facilities inside the preschool | 2 (66.7%) | - | 1 (33.3%) |
| The taps used by children are at their height | 1 (33.3%) | - | 2 (66.7%) |
| There are preschool toilets in the school (commodes for children and with half doors) | 1 (33.3%) | - | 2 (66.7%) |
| The preschool has a separate kitchen with utensils and equipment | 1 (33.3%) | - | 2 (66.7%) |

Annex 4.2 – Telephone Survey to assess Youth Enterprise Development Component

- Introduction

Outcome # 4 of the Project, Catalytic Support to Peace building in Sri Lanka seeks to provide a suite of benefits to ensure durable solutions to the returnees. One of the components of this Project is to support sector-based livelihood assistance for resettled communities who engaged in Agriculture, Fisheries and Livestock related sectors and enterprise development support especially for youth through Inputs, equipment & accessories with required skills.

Since the Project’s end-line survey has not specifically examined the situation with Project’s beneficiaries, it was proposed to undertake a telephone survey of representative recipients of ‘enterprise development support’ to assess benefits and the perceptions of the beneficiaries.

The telephone survey was conducted using a structured, pre-tested questionnaire in June/July, 2019. The interviews were conducted in Tamil language, as it was the mother tongue of the respondents.

- Selection of Respondents and their key characteristics

The Project was implemented in Jaffna and Trincomalee districts. The youth enterprise development (also called micro-enterprise development) consisted of 431 beneficiaries from Jaffna district (mainly from Telippalai, Kopay and Kankesanturai DS divisions) and 31 beneficiaries from Trincomalee (from Muttur DS Division). The Project’s database from Jaffna had telephone numbers of only 117 beneficiaries from Jaffna, whereas telephone contacts of all Trincomalee beneficiaries were available. A sample of 25 beneficiaries (about 17%) was selected randomly to represent ‘vocations’. Every effort was made to have gender equality.

Table 1 gives the summary of selections from the two districts.

Table 1 – Selection of beneficiaries for telephone interviews

| Vocation | Jaffna |  | Muttur |  |
| --- | --- | --- | --- | --- |
|  | No. of beneficiaries | No selected for interview | No. of beneficiaries | No selected for interview |
| Mechanic | 10 | 2 | 4 | 1 |
| Carpentry | 11 | 2 | 7 | 2 |
| Grocery/food | 28 | 3 |  |  |
| Mason | 27 | 3 | 1 |  |
| Tailoring | 16 | 2 | 7 | 2 |
| Electrician | 5 | 1 | 5 | 1 |
| Other jobs | 20 | 4 | 7 | 2 |
| TOTAL | 117 | 17 | 31 | 8 |

The key characteristics of the respondents are summarised below:

- In terms of age, 5 (20%) were less than 30 yrs; 11 (44%) were between >30 – 40, and nine (36%) over 40 years;

- Of the 25 respondents, 24 did not have any other earning member in the family;

- Twenty-three (23) or 92% had bank accounts, and 15 (60%) had taken bank loans for various purposes;

- Twenty-four out of 25 respondents (96%) were engaged in the same vocation for which they received assistance. The other person had a different vocation. One respondent earned LKR 40,000 per month, and several others between LKR 30,000 to LKR 40,000.

- Eighteen (18) respondents (or 72%) owned a permanent house;

- Only four (4) respondents (or 16%) did not have some form of transport; 11 had motor-cycles, and three owned three-wheelers. The means of transport of others was bicycle.

- Twenty-two (22) or 88% came to know about this assistance programme from the village level officials such as the Grama Niladhari and the Development Officer.

- Findings of the Survey

A commentary on the main findings of the survey is provided below.

- Delay in launching of the YED component

Eighteen (18) responded or 72% received their assistance package only during the first quarter of 2019; five (5) or 20% received their assistance during the last quarter of 2018. The findings confirm the field observations (and information from KII and FGD) that there was a delay in providing this assistance.  Some of the ventures were not fully operational. Thus the period available for a realistic assessment of benefits was limited, as was indicated by many of the beneficiaries.

- Enhancing Incomes

The baseline of CEPA identifies lack of livelihood opportunities for youth. Although the original proposal is not explicit about Youth Enterprise Development, it appears that this component was launched to support youth with sustainable livelihood options. However, the telephone survey confirms observations from the field that those who received YED assistance in fact were engaged in some form of livelihoods and were not strictly unemployed. The telephone survey shows that 24 out of 25 respondents (96%) were engaged in the same vocation for which they received assistance. The other person had a different vocation.

It is therefore safe to conclude that YED programme enhanced income generation of the beneficiaries largely by providing new trade equipment.

- Business Plans

The Project prepared Business Plans as a part of this component. All respondents confirmed the availability of a Business Plan, but 15 respondents (or 60%) said that they did not use it, largely because they did not understand the concepts, or had difficulty to follow. This pattern confirms the observations from the field.

- Training

Twenty (20) respondents (or 80%) stated that they received some form of training for the vocation for which they received funding. One respondent stated that the training was ‘very useful’ whist the others stated that training ‘useful’.

- Relevance of Assistance

All respondents stated that if not for the Project, they would not have been able to obtain a grant for improving livelihoods.

- Registration of Businesses

Nineteen (19) respondents had not registered their businesses (76%); the main reason was they do not have time for registration, do not understand the process, and the process is too cumbersome.

- Providing employment

Nine (9) (or 36%) of the respondents employed others either as temporary or permanent assistants. One person employed four each of temporary and permanent assistants. Six respondents who had not registered their businesses employed others.

- Current status/Impacts

As most of the ventures have begun only in 2019, it was too early to assess impacts.

However, according to the perceptions of the respondents, 11 (or 44%) stated that the venture was ‘modestly successful whilst 14 (or 56%) stated that the ventures were ‘modestly unsuccessful’ (Fig. 1). Yet all expected that the ventures would modestly improve household income.

Some of the respondents had used the extra income for expanding/upgrading the house, purchasing household items, and on occasion to settle loans.

Tables 2.1, 2.2 and 2.3 excerpted from Central Bank of Sri Lanka, “Economic and Social Statistics of Sri Lanka 2018” and Department of Census and Statistics, “Demographic and Health Survey 2016.

Monitoring and Documentation of Resettlement Support – EU Catalytic Support to Peace-building in Sri Lanka; Centre for Poverty Analysis, Colombo; 1 May 2018

Monitoring and Documentation of Resettlement Support – Final Report; CEPA (April, 2019)

Theory of Change document; CEPA (December, 2017)

Development Assistance Committee (DAC) – OECD Principles for Evaluation of Development Assistance (2008)

This survey was limited due to the non-availability of telephone numbers of many beneficiaries.

ToC Outcome Note of the Project (2017)

Description of the actions – May 2018

The National Policy on Durable solutions for Conflict- Affected Displacement (undated); Ministry of Resettlement, Rehabilitation, Northern Development & Hindu Religious Affairs

See <https://interagencystandingcommittee.org/system/files/guiding_principles_on_internal_displacement.pdf> accessed on 30 June 2019

See <http://www.lk.undp.org/content/srilanka/en/home/presscenter/pressreleases/2019/03/15032019.html> accessed on 30 June 2019

Source: Partner proposal of UN-Habitat (undated)

Surveying exceeded the target due to availability of more than expected LKR resulting from LKR depreciation against the project currency, USD.

Ministry of Education, (2008), School Census 2008, Ministry of Education

Institute of Policy Studies of Sri Lanka, Sri Lanka: State of the Economy 2010, ‘Post Conflict Economic Development Challenges’, 2010

Developed by the National Education, Research and Evaluation Centre of the Faculty of Education, University of Colombo (2007).

The Project’s position is that there is an agreement with the Department of Education to cover the training part whereas UNICEF will provide materials.

The teachers were unable distinguish between Project-conducted training and ECCD training.

UNICEF has since brought to this issue to the notice of the School Works Branch of Muttur Zone who has agreed to undertake corrective actions necessary.

School management, particularly in Muslim schools did not allow participation of boys in the advance training. In deference to these sentiments, the implementing partner agreed.

Proceedings of the International Conference on Northern Waters (ICNW); Office of the Governer of of the Northern Province (undated)

Additionally, the International Conference on Northern Waters, held in December, 2018 has recommended that recharge wells/infiltration wells should be established at house hold level, schools, and in common buildings, and infiltration galleries should be introduced to recharge the ground water through the cavities.

Preventing and responding to violence, exploitation and abuse against children – including commercial sexual exploitation, trafficking, child labour and harmful traditional practices, such as female genital mutilation/cutting and child marriage (UNICEF).

Gender-based violence is violence that is directed against a woman because she is a woman or that affects women disproportionately.  It includes acts that inflict physical, mental or sexual harm or suffering, threats of such acts, coercion and other deprivations of liberty. “The underlying principle is “zero tolerance of sexual and gender-based violence”.

IPV refers to any behaviour within an intimate relationship that causes physical, psychological or sexual harm to those in the relationship. Examples of types of behaviour are listed below. Acts of physical violence, such as slapping, hitting, kicking and beating. Sexual violence, including forced sexual intercourse and other forms of sexual coercion. Emotional (psychological) abuse, such as insults, belittling, constant humiliation, intimidation (e.g. destroying things), threats of harm, threats to take away children. Controlling behaviours, including isolating a person from family and friends; monitoring their movements; and restricting access to financial resources, employment, education or medical care.

The Project has recompensed their travel expenses during the Project period.

The Telippalai Palm Development Coop Society Ltd had been established in 1972.

Some of these issues are highlighted in the end-line report of CEPA.

Kalinga Tudor Silva; P P Sivapragasam & Paramsothy Thanges (2009) Caste Discrimination and Social Justice in Sri Lanka: An Overview; Indian Institute of Dalit Studies; Working Paper Series Vol III (6)

Kalinga Tudor Silva; Address to the National Academy of Sciences (Induction Ceremony, 2018)

Partner reports were not available for perusal.

Excerpted from Description of Activities; July 2018

Monitoring and documentation of Resettlement Support – Baseline data; CEPA (May, 2018)

Monitoring and documentation of Resettlement Support – Final Report, CEPA (April, 2019)

The Implementing Partners were required to provide about 20% of the cost as counterpart funding.

(http://www.mnpea.gov.lk/web/index.php?option=com_content&view=article&id=62:economic-policy-statement-made-by-hon-prime-minister-ranil-wickremesinghe-in-parliament-on-5th-november-2015&catid=20&lang=en)

Report of the Commission of Inquiry on Lessons Learnt and Reconciliation, November 2011; Presidential Secretariat; xii+388

European Union (Sri Lanka) – Development Cooperation Areas 2016

CEPA in its baseline survey recommended collective livelihood support as against individual livelihood support. CEPA’s end-line reports that IDPs are still not in favour of collective livelihoods – the reasons attributed are caste differences and formation of new communities (by the Returnees) [cf. End-line Report (Section on Collective Livelihood Support) – no pagination.

At the ‘Presentation of Findings’ meeting held at UNICEF on 10 September 2019.

Graded on a scale Highly Satisfactory (4)[several significant positive factors with no defaults or weaknesses]; Satisfactory (3) [positive factors with minor defaults or weaknesses ]; Less than Satisfactory (2) [moderate to notable defaults or weaknesses]; and Unsatisfactory (1) [negative factors with severe defaults or weaknesses]

An example in terms of Project’s identity and visibility is in the end-line report of CEPA. The survey found that 49 per cent of the respondents thought health services to be ‘improved a little’ whereas 37 per cent saw ‘no difference’. Forty-five per cent had no idea of UNICEF support for improving health services. cf. Figs. 19 and 20 of the End-line Report, CEPA.