UNICEF Malaysia

LRPS-2018-9143757

MDF Training & Consultancy

Bart van Halteren

Hari Ramalu Ragavan

Indonesia, June 2020

# INCEPTION REPORT- Formative Evaluation of the Role and Engagement of the Business Sector to Respect and Promote Child Rights UNICEF Malaysia (LRPS-2018-9143757)

# Assess and guide UNICEF Malaysia’s business sector engagement and partnerships to respect and promote child rights

February – October 2020

UNICEF Malaysia

LRPS-2018-9143757

June 2020

MDF Pacific-Indonesia

Jl. Bypass Ngurah Rai 379

Sanur, Bali, Indonesia

mdfpi@mdf.nl

www.mdf.nl

## Contents

Contents	1

Acronyms	3

1.	Introduction	5

1.1.	The assignment, context and justification of changes	5

1.2.	Purpose of this inception report	6

2.	Context and evaluation object	7

2.1.	Defining business sector engagement and partnerships; the UN context	7

2.2.	Malaysian context	10

2.2.1.	Malaysian government policy and strategy on business engagement	11

2.2.2.	UNICEF Malaysia	12

2.2.3.	The business sector	13

2.2.4.	The civil society sector	16

2.3.	Business engagement strategies of other UN agencies	16

2.4.	Summative and formative object of the evaluation	18

2.5.	Details on the object of the evaluation	19

3.	Evaluation purpose, objectives and scope	27

3.1.	Purpose and object of the evaluation	27

3.2.	Objectives and scope of work of the evaluation	27

3.3.	Rationale, users and intended use of the assignment	28

4.	Approach and methodology	30

4.1.	Design and approaches	30

4.2.	Stakeholders	35

4.3.	Methodologies and data collection tools	37

4.4.	Working definitions	42

4.5.	Evaluation Matrix	42

4.6.	Data gaps	49

5.	Evaluation workplan	50

5.1.	Summary of phases	50

5.2.	Deliverables	52

5.3.	Team composition, roles and responsibilities	53

5.4.	Timeline	53

5.5.	Quality assurance	54

5.6.	Ethical considerations	55

5.7.	Limitations, risks and mitigation strategies	56

4.	Budget	58

Annexes	59

Annex 1	Original ToR	60

Annex 2	List of most relevant documents reviewed	61

Annex 3	Proposed types of interviewees/ respondents	64

Annex 4	Interview Guidelines	67

Annex 5	Survey questions	70

## Acronyms

| AR | Annual Report |
| --- | --- |
| BCSDM | Business Council for Sustainable Development Malaysia |
| BEAs | Business Engagement Approaches |
| BP | Boundary Partner |
| BS | Business Sector |
| CBO | Community Based Organisation |
| CP/ CPD | Country Programme/ Country Programme Document |
| CRBP | Children’s Rights and Business Principles |
| CRM | Corporate Resource Mobilisation |
| CSO | Civil Society Organisation |
| CSR/CS | Corporate Social Responsibility/ Corporate Sustainability |
| DB | Duty-Bearers |
| DS | Desk Study |
| EBP | Evidence-Based Practices |
| EGH | Equity, Gender Equality and Human Rights |
| EPU | Economic Planning Unit |
| ESG | Environmental, Social and Governance |
| FGD | Focus Group Discussion |
| FSDR | Financing for Sustainable Development Report |
| GCMY | Global Compact Network Malaysia |
| GLC | Government Linked Company |
| INT | Interviews |
| IOM | Integrated Organisation Model |
| KII | Key Informant Interview |
| MCO | Malaysia Country Office |
| MCO | Movement Control Ordinance |
| MEA | Ministry of Economic Affairs |
| MICCI | Malaysian International Chamber of Commerce & Industry |
| MTR | Mid-Term Review |
| NGO | Non-Governmental Organisation |
| OM | Outcome mapping |
| PFSR | Private Sector Fundraising |
| PFP | Private Sector Fundraising and Partnership |
| PSN | Programme Strategy Note |
| RAM | Results Assessment Module |
| RC | Results-Chain |
| RH | Rights Holders |
| SC | Securities Commission |
| SDGs | Sustainable Development Goals |
| SDSN | Sustainable Development Solutions Network |
| SH | Stakeholders |
| SIDC | Securities Industry Development Corporation |
| SME | Small and Medium-sized Enterprises |
| SRI | Sustainable and Responsible Investment |
| SUHAKAM | Human Rights Commission of Malaysia |
| SV | Survey |
| SWOT | Strengths, Weaknesses, Opportunities and Threats |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UNCT | UN Country Team |
| UNDP | United Nations Development Programme |
| UNESCAP | United Nations Economic and Social Commission for Asia and the Pacific |
| UNFPA | United Nations Population Fund |
| UNGC | United Nations Global Compact |
| UNHCR | United Nations High Commissioner for Refugees |
| UNSDCF | United Nations Sustainable Development Cooperation Framework |
| UNSDG | United National Sustainable Development Group |
| WBCSD | World Business Council for Sustainable Development |
| WHO | World Health Organisation |
| WS | Workshop |

## Introduction

### The assignment, context and justification of changes

UNICEF Malaysia hired an independent evaluation team to conduct a forward-looking and learning-oriented formative evaluation of the role and engagement of the business sector to respect and promote child rights. As per the original ToR, the assignment was to take place between March and June 2019. The original assignment was given to MDF in July 2019. UNICEF later informed MDF that the study will be postponed until February 2020. There were no reasons cited for this.

In February 2020, when the evaluation team commenced its activities, during the inception phase, progressive insight and discussions with UNICEF led to the need for changes in the purpose, scope, and objectives of the formative evaluation due to:

- Changes that have taken place within the country programme (CP) 2016-2020 and the new programmatic process in the UNICEF Malaysia Country (MCO) office (i.e. developing a new Country Programme Document-CPD)

- A change/ turnover in UNICEF Malaysia staff.

The original TOR had required the assignment to:

- Conduct an impact evaluation of the past business sector engagement activities between 2010-2015, and 2016-2020, focusing on UNICEF engagements with the private sector vis-à-vis child rights and UNICEFs CP objectives.

- Provide recommendation on strategic direction for business sector engagement to be implemented in the remaining period of 2016-2020 CP and to provide input to the development of future country programme of 2021-2025.

Currently the CP 2016-2020 is almost at its end and the draft new CPD 2021-2025 is almost completed. As such, this evaluation will focus on providing recommendations on the operationalisation of the strategic direction for business sector engagement approaches for the rolling work plans for the CP 2021-2025. This will be done based on:

- The lessons learned from the past programme period

- Programmatic approach and focus in the CP 2021-2025

- Current trends and opportunities for business sector partnership in Malaysia.

The overall purpose of the evaluation will almost be the same as per the original ToR. However, the objectives will be adjusted to suit the above mentioned justification. The timeline of the evaluation will also be adjusted to meet the focus and time needed to develop evidence-based, clear, specific and actionable recommendations. The change in focus will necessitate more time for increased external stakeholders’ engagement and to facilitate internal discussions with UNICEF staff in regards to capacity and knowledge (new objective 4, see below, chapter 3). Lastly, the timeline has changed as compared to the original ToR also due to COVID-19 situation.

The object, purpose, objectives, scope and time line of the evaluation are further detailed in chapters 2 and 3.

### Purpose of this inception report

As per the Terms of Reference, this Inception Report will be key in confirming a common understanding of what is to be evaluated and delivered. At this stage, evaluators will review the proposed CP 2021-2025 Theory of Change in order to refine and confirm evaluation questions, collect documents to be able to review the business engagements strategies, guiding interview questions, confirm the object and scope of the evaluation, and improve on the methodology proposed.

As per the ToR, during the inception phase and initial desk study and meetings with UNICEF were to take place in order to:

- Identify a preliminary list of UNICEF’s activities with the business sector in the past

- Identify the business sector’s participation in SDGs and wider corporate sustainability and partnership context in Malaysia

- Identify a map of various relevant stakeholders

- Review and finalise the evaluation matrix.

The assignment hence started with an intake in the week of 10-14 February, during which the UNICEF Malaysia office was visited. After intensive discussions with relevant UNICEF staff (including a mini workshop) the decision was taken to revise the purpose, objectives and evaluation questions as now presented in this Inception Report. This was then followed up with a survey to all UNICEF Malaysia staff to identify past business engagement approaches (BEAs) and the partners involved. The results of the visit to the UNICEF Malaysia country office and the survey are included in this inception report.

As such, this inception report will:

- Confirm changes to the purpose, object, objective, scope and outcome of the evaluation

- Provide a brief summary of UNICEF Malaysia’s past business sector engagement activities that will be evaluated, on the basis of the survey findings

- Identify a tentative list of stakeholders to be interviewed/ met (see Annex 3)

- Propose the finalised evaluation matrix (with evaluation questions and guiding interview/ workshop questions)

- Refine the methodology and timeline

- Agree on deliverables

- Confirm the management and process of the evaluation.

## Context and evaluation object

### Defining business sector engagement and partnerships; the UN context

In 2000, the UN launched the United Nations Global Compact (UNGC) which is a leadership platform for the development, implementation and disclosure of responsible corporate practices. It is the UN’s strategic policy initiative for businesses that are committed to take action to do business responsibly by aligning their strategies and operations with Ten Principles on human rights, labour, environment and anti-corruption, and take strategic actions to advance broader societal goals, such as the UN Sustainable Development Goals, with an emphasis on collaboration and innovation. The UNGC supports businesses to contribute towards the SDGs and achieve business excellence via 10 principles, programmes and tools while providing access to partnerships with a range of stakeholders to share best practices and emerging solutions. It is the largest corporate sustainability initiative in the world, with more than 9,000 companies and 3,000 non-business signatories based in over 160 countries, and more than 70 local networks.

The UNGC also developed the SDG Compass together with the World Business Council for Sustainable Development (WBCSD) as a guide to support companies in aligning their strategies with the SDGs and in measuring and managing their contribution to achieving these.

Recognizing the need for an explicit child rights perspective and guidance for companies on how to prevent and address risks to children's rights, Save the Children, UNICEF and the UN Global Compact led a process to develop the Children's Rights and Business Principles (CRBP) in consultation with business, child rights experts, civil society, governments and children. Launched in 2012, the CRBP are the first set of principles that identify a comprehensive range of actions that all business should take to respect and support children's rights in everything they do – in the workplace, marketplace, community and environment – and in conjunction with the government's duty to protect human and children's rights. The CRBP do not create new obligations for businesses. Instead, they build on internationally recognized standards and provide an operative framework for companies to respect children's existing rights. In order to meet their responsibilities, the CRBP call on businesses to put in place appropriate policies and processes, as set out in the UNGP, including a policy commitment and a due diligence process to address potential and actual impacts on human rights (UNICEF, 2019).

The 2030 Agenda for Sustainable Development (the 2030 Agenda) and the Addis Ababa Action Agenda emphasize business as a key player in implementing, investing and achieving SDGs. According to the Better Business Better World report by the Business & Sustainable Development Commission (2017), it is estimated that achieving the SDGs could open an estimated US$12 trillion in market opportunities for business. To leverage this potential, the United Nations Secretary General has called for an enhanced engagement with the private sector. Goal 17 of the SDGs, “Strengthen the means of implementation, and revitalize the global partnership for sustainable development,” is acknowledged to be a crucial mechanism for achieving the other 16 goals. The public–private partnerships can combine the strengths of private actors, such as innovation, technical knowledge and skills, managerial efficiency and entrepreneurial spirit, and the role of public actors, including social responsibility, social justice, public accountability, and local knowledge, to create an enabling environment to deliver the outcomes of SDGs.

The 2019 Financing for Sustainable Development Report (FSDR) of the Interagency Task Force on Financing for Development warns that mobilizing sufficient financing remains a major challenge in implementing the 2030 Agenda. At the national level, the report puts forward a roadmap for countries to revamp their public and private financial systems to mobilize resources for sustainable development investment.

The United Nations Economic and Social Commission for Asia and the Pacific’s (UNESCAP) Sustainable Business Executive Council estimated that no country in the Asia Pacific can achieve (any of) the SDGs by 2030, and that achieving them requires a massive new investment of US$1.5 trillion. It was concluded that the private sector needs to play a bigger role and help to provide the needed financing and other efforts to achieve the SDGs.

In 2018, the WBCSD conducted a global survey to explore trends around how business is currently working to align activities with the SDGs. The main barrier to integrating the SDGs organisationally was a lack of understanding of the business case among internal stakeholders.

#### Definitions of private sector and business sector, engagement and partnership

The United Nations Sustainable Development Group (UNSDG), in its concept note “Common Approach to Prospect Research and Due Diligence for Business Sector Partnerships” (2019) defines the private sector, the business sector, partnership and business engagement as follows:

Private sector: “part of the economy that is run by individuals and companies and is not state controlled. Therefore, it encompasses all for-profit businesses that are not owned or operated by the government and includes privately-owned organisations that might not be for-profit (e.g. family foundations or associations) and/or include influential individuals such as high net worth individuals”.

The same document defines the business sector as:

- “For-profit and commercial enterprises of any size, whether privately or publicly owned, fully or partially governed by governments

- Corporate foundations and foundations that are directly funded and/or governed by businesses

- Business associations, coalitions and alliances, including for example chambers of commerce, employers’ associations, cooperatives, and industry and cross-industry initiatives where the participants are for-profit enterprises”.

Partnership: is defined as “a voluntary and collaborative agreement or arrangement between one or more parts of the United Nations system and the business sector, in which all participants agree to:

- Work together to achieve a common purpose

- Invest their respective resources (e.g. time, knowledge and expertise, research and technological development, funding, core assets, etc.)

- Acknowledge mutual benefits as an integral aspect to the engagement

- Share risks”.

Engagement with businesses, according to the UNSDG, refers to: “any type of interaction with business sector entities, with different objectives, ranging from informal talks and discussions to knowledge-exchange platforms to full-fledged partnerships entailing funding or brand asset exchanges. These engagements may be implemented through different modalities, including but not limited to partnering, and may entail different levels of public exposure

UNICEF defines the private sector as “the general public, civil society, businesses, private foundations and other social groups that can individually or collectively contribute to

positive changes in the lives of children”. The business sector is defined as “all companies (small enterprises and community-level entrepreneurs to large global multi-nationals and

corporations), multi-stakeholder platforms and industry bodies, business leaders (as influencers and philanthropists) as well as corporate and family foundations”.

Taken the above into account, a working definition of business engagement will be presented in the Approach and Methodology chapter (paragraph 4.4).

### Malaysian context

The 10th Malaysia Plan (2010-2015) made clear reference to corporate social responsibility by mentioning successful partnerships, particularly between the Government and NGOs in welfare initiatives and between public and private sector in corporate social responsibility programmes such as in education and environmental conservation. These would be extended in the next Plan.

In 2015 Malaysia embraced the SDG’s and in 2016 the Malaysian government developed the 11th Malaysia Plan 2016-2020, with a clear intention to progress on the Sustainable Development Goals. The Plan emphasised human centred development to bring the country to high-income status by 2020. During 2017, the Government launched a consultative process to define Malaysia's vision for 2050 to become one of the top 20 nations in economic development, social advancement and innovation. Despite a challenging global economic environment and increasing social inequities, the Malaysian economy performed well, with GDP per capita increasing from USD 9,666 to USD 11,197 in 2019 and a further reduction in the national incidence of poverty (at 0.4 per cent in 2016) was reported (Ministry of Economic Affairs, 2019).

The 11th Malaysia Plan, is heavily focused on achieving further economic growth but also encourages the business sector to implement corporate social responsibility programmes and identifies national commitments towards children. The commitment to the 2030 Agenda has been mapped with the 11th Plan to align strategies and initiatives to support the Sustainable Development Goals. The first phase of a roadmap is being developed to provide guidance for the smooth implementation of the 17 SDGs. The roadmap takes into account the nation’s capacities and capabilities in achieving identified goals and targets of the 2030 Agenda.

Currently, the government of Malaysia is developing the 12th Malaysia Plan (2021-2025) which will be aligned with the shared prosperity initiative introduced by the new Pakatan Harapan government in 2018, encompassing three dimensions, namely economic empowerment, environmental sustainability and social re-engineering. The economic empowerment dimension will include new sources of growth, including Industrial Revolution 4.0, digital economy, aerospace industry, integrated regional development as well as growth enablers such as sustainable energy sources and infrastructure connectivity. The environmental sustainability dimension, among others include the blue economy (sustainable use of ocean resources), green technology (the use of technology and science to create products that are more environmentally friendly), renewable energy as well as adaptation and mitigation of climate change. The social re-engineering dimension comprises enhancing societal values, improving purchasing power of the people, building resilient Bumiputera (the Malay and indigenous) community, strengthening social security networks and improving the wellbeing of the people.

Very recently, the government has appointed the country’s first Children’s Commissioner in the SUHAKAM (Human Rights Commission of Malaysia). This appointment is among the new measures taken by the government to protect the interests of children, which can be explored as an opportunity to work with the Commissioner to engage the business sector to improve their impact on children’s rights.

The SDG’s, the Malaysian government’s national objectives, UNICEF Malaysia’s objectives, the business CSR/ CS objectives and civil society’s objectives all need to be considered in this evaluation.

### Malaysian government policy and strategy on business engagement

The government published the Silver Book by the Putrajaya Committee on Government Linked Companies (GLCs) which provides the guidelines of CSR reporting to GLCs and also launched the CSR framework by Bursa Malaysia (the Malaysian stock exchange) for private companies to do their CSR reporting, in 2006. In the 2007 Budget Speech, the Prime Minister announced that private sector contributions to the community would be recognised and awarded through the Prime Minister’s CSR Awards Sponsorship. CSR awards given by the top level of the government is considered a significant recognition of the impact that a business can have on a community.

Bursa Malaysia (the Malaysia Stock Exchange) and FTSE (the Financial Times Stock Exchange) launched an Environmental, Social and Governance (ESG) index i.e. FTSE4Good Bursa Malaysia Index for the Malaysian market to support investors making ESG-compliant investments in Malaysian listed companies. This is an important step in encouraging the business sector to invest in SDGs related undertakings.

In ensuring the successful implementation of SDGs in Malaysia, the government has established five cluster working groups, namely Inclusivity, Well-being, Human Capital, Environment & Natural Resources and Economic Growth, and 17 taskforces, as per the SDGs. Private sector organisations and CSOs have been invited on both the cluster groups and the taskforces.

In 2010 the Agensi Inovasi Malaysia (AIM) was created to jump start wealth creation through knowledge, technology and innovation to stimulate and develop the innovation eco-system in Malaysia. Together with MAGIC, the Malaysian Global Innovation & Creativity Centre, these two organisations invest in entrepreneurship and supporting start-ups and social enterprises, as well as (recently) the digital economy. These types of investments have the potential to influence social enterprise creation.

In 2019, the government conducted a National SDG Summit where, among others, a business leaders SDG forum was held to discuss private sector leadership actions for a sustainable Malaysia.

### UNICEF Malaysia

Since 1954, UNICEF has joined forces with the Government and the people of Malaysia to transform the lives of children across the nation. It has helped achieve improvements in health, nutrition, water and sanitation, formal and informal education as well as welfare services for children in rural and poor urban areas. With the Convention on the Rights of the Child, the SDGs, and the successive Malaysia plan as guides, UNICEF collaborates with Malaysian partners in government, corporations or civil society organisations, and other UN agencies in the country to “change minds, change policies, and in turn change the lives of all children in Malaysia” (UNICEF Malaysia website).

The 2018 Mid Term Review of the UNICEF Malaysia country programme affirmed that the priorities of the CP 2016-20 remained relevant, and that UNICEFs strategic focus on strengthening the enabling environment (policies, plans, legislation, budgets, social norms) for child rights be maintained.  Among lessons learned noted in the Mid Term Review were that policy and implementation influence on child rights is greatest when the analysis and recommendations are conducted and presented by Malaysian institutions and respected experts, and when the child rights imperatives for reforms are complemented with evidence on the economic and national development benefits of investing in children; that the appetite, capacity and potential of the private sector in mobilising public opinion and government action on critical child rights issues might have been under- estimated and inadequately leveraged; and the need to strengthen platforms for enabling young people’s engagement and participation; and explore the potentials for stronger private sector engagement leveraging on the benefit of being a hybrid programme and Private Sector Fundraising (PSFR) office. Moving forward, these are some of the challenges in a high middle-income developing country like Malaysia where core resource funding will be less for UN agencies and where business engagement strategies need to be devised. Currently, UNICEF Malaysia is finalising its Country Programme 2021-2025 in which these challenges will (need to) be addressed.

Given the Malaysia Government’s support for corporate governance, transparency and responsible business practices as a means of differentiating the business investment climate in Malaysia and addressing youth employment, UNICEF identified in recent years the opportunity to have a stronger impact on the lives of children in Malaysia and internationally through deeper engagement of the corporate sector, and more specifically its non-financial corporate social responsibility practices.

#### Internal organisation and capacity

In pursuing its goals, UNICEF Malaysia is currently organised into four separate units, namely Programme, Operations, Communications, and Private Sector Fundraising and Partnership (PFP).

It is noted that the business sector engagement has been the responsibility of both the PFP and programme sections. Currently there is a vacancy for a person to be in charge of CRM within the programme section.

There is collaboration between the programmes (specifically between communication and innovation) and the PFP section as noted in the practice like the use of U-Report to poll donors on issues, and use of social marketers to engage the public.

An internal training (led by RO) on business sector engagement has been done for staff within the sections.

#### Support from UNICEF EAPRO and HO

Currently there are no global or regional programmes conducted on business sector engagement at higher than country level that involves UNICEF Malaysia. However, higher level UNICEF offices have produced guidelines and some examples of other country office’s engagements. In 2019, UNICEF HQ published the “UNICEF Engagement with Business, Programme Guidance for Country Offices”. to support country offices in determining how to engage with business programmatically and promote business respect and support for child rights UNICEF’s history of working with business and provides examples of engagement at country, regional and global levels.

In addition, there is the “Private Sector Fundraising Strategic Plan (2016-2020)” to mobilise financial resources from the private sector and UNICEF IMPACT Plan and Cause Framework (2018-2021) and the Investor Guidance on Integrating Children’s Rights into Investment Decision Making, 2019. This Guidance is directed at investors and ESG research providers interested in exploring how companies and investors can mitigate risks and identify opportunities that advance children’s rights while generating both societal and upside financial benefits. So far, that is all the regional and HQ support we have been able to identify.

### The business sector

In relation to corporate sustainability, the business sector in Malaysia can be divided into 3 types of companies; namely Government Linked Companies (GLCs), large private corporations, including multinational companies, and Small and Medium Enterprises (SMEs) (the latter two are mostly PLCs-Private Limited Companies). The willingness and capacity of these different types of companies to engage stakeholders in corporate sustainability efforts, varies depending on motivation, regulation and market pressure.

GLCs are the most dominant in corporate sustainability given the government’s Silver Book initiative which provides the guidelines of CSR reporting to GLCs and the reporting requirements of the Securities Commission. In 2017, a survey done by KPMG revealed that Malaysia is in the top 10 countries in the world with the highest rates of corporate responsibility information in companies’ annual financial reports. Most of the companies mentioned in the report are GLCs, which have a large impact on the economy of Malaysia in terms of production and employment. The GLCs have developed their own internal sustainability units that help to monitor and report on its corporate responsibility. It is noted, however, that the political influence on GLCs creates an entirely different business (and business engagement) dynamic which should be considered during this evaluation.

The second type of companies, which are large private corporations including multinationals, are also increasingly embrace corporate sustainability to meet the requirements of the regulation as well as corporate branding and marketing. Some of these GLCs, together with large private corporations, have won the annual CSR Malaysia Award for outstanding public listed companies. There are other sustainability awards given to businesses in Malaysia. The Sustainability Business Award given by Global Initiatives, a regional organisation based in Singapore, the Prime Minister’ Hibiscus Award by the Malaysian International Chamber of Commerce & Industry (MICCI), and a new award introduced in 2019 by the EU-Malaysia Chamber of Commerce and Industry called Europa Award for Sustainability.

The Standard Chartered SDG Investment Map study in 2020, noted that the combined potential private-sector investment opportunity in Malaysia by 2030 – across 3 indicators of SDG, namely SDGs 6 (Clean Water and Sanitation), SDG 7 (Affordable and Clean Energy) and SDG 9 (Industry, Innovation and Infrastructure) – is estimated at USD 35 billion. This demonstrates the huge opportunity to partner with the private sector to increase social impact in Malaysia.

However, there appears to be a lack of coordination and cooperation between businesses, within and across all sectors, to support the SDGs. Many companies are carrying out various CSR programmes but these appear to be mostly company-based initiatives rather than partnerships, in spite of quite a few network organisations, as mentioned below. This could provide an opportunity for UNICEF to bring like-minded businesses together to form a coalition to tackle a specific (child-related) issue within UNICEF Malaysia’s CP 2021-2025, in conjunction with working with individual companies.

The Global Compact Network Malaysia (GCMY) is the local chapter of the UNGC, that supports Malaysian members in enabling them to contribute towards the SDGs. It says its aim is to position the Malaysian private sector as a benchmark and a primary agent in driving a sustainable world.

The Business Council for Sustainable Development Malaysia (BCSDM) was formed in 2011 through a merger of the Business Council of Sustainable Development (1992) and the Institute for Corporate Responsibility Malaysia (2006). BCSDM Malaysia strives to raise awareness, share knowledge and build capacity; advocate the case for sustainability as a business opportunity; bring a collective business voice to engage with policymakers and regulation authorities, and initiate projects and programmes in collaboration with stakeholders in Malaysia and Southeast Asia.

The Securities Commission (SC), the statutory body entrusted with the responsibility to regulate and develop the Malaysian capital market, has launched the Sustainable and Responsible Investment Roadmap (SRI Roadmap), which aims to chart the role of the capital market in driving Malaysia’s sustainable development.

At the CSR Malaysia Awards 2019, 50 Malaysian listed and private companies together with GLCs were recognized and awarded as outstanding Malaysian corporations that have excelled tremendously in the corporate sustainability and social responsibility arena in boosting the socio-economic transformation of Malaysia. One of the criteria used for the awards include creative implementation of the CSR activities that involved partnerships with other stakeholders. Among the recipients of the awards were DIGI Telecommunications and Sunway; both corporations have partnered with UNICEF in the past. This might indicate an increased importance given to partnership modalities between the business sector and the civil society or public sector.

Besides the above mentioned larger companies, there is also a growing potential importance of SMEs impact on the economic and social wellbeing of children in Malaysia, and there may be an opportunity to reach out to them as a collective platform. Although, there is no regulation on them to report their corporate sustainability initiatives, these SMEs are increasing facing market pressure through consumer’s demand as well as supply chain sustainability requirements. According to a CSR Malaysia survey on yearly spending amounts on CSR-related activities among 550 SMEs in 2018, about 35% of them spent up to RM10,000 (USD2,400) on their CSR efforts while 13% spent up to RM50,000 (USD12,200). Another 7% spent more than RM50,000 (USD12,200) while about 28% spent between RM1 (USD0.24) and RM1,000 (USD242). Most of these SMEs include corporate sustainability initiatives under their Environmental, Health and Safety (EHS) programme. As everywhere, ad-hoc corporate sustainability activities are being undertaken depending on the budget and requirements of their clients. SMEs often don’t have extensive corporate sustainability plans. The current situation regarding Covid-19, however, will impact SMEs hard: The impact to business is dire, and many firms are struggling to stay afloat. A survey done by SME Association in March 2020 highlighted that nearly 82 per cent of SMEs predicted a loss for the financial year 2020, with nearly 7 in 10 of the SMEs have just enough cash flow for them to pull through until April 2020. Another survey done by the Federation of Malaysia Manufacturers (FMM) in April reported that nearly two in three (63%) manufacturers will need to undertake cost-cutting measures such as retrenchment, unpaid leaves and freeze in hiring in order to stay in business, and about one in two (47%) stated that the cost-cutting measures will be implemented within three to six months. Strikingly, more than three-quarters (78.7%) of surveyed firms said they might have to lay off up to 30% of their workforce. Latest statistics from the Department of Statistics show that 68% of firms reported zero income during the MCO, and had to use internal funds to stay afloat.

The current trend in CSR strategies of both GLCs and large private corporations in Malaysia is to move away from handing out donations and cash to CSOs or individual families to support social impact activities, to creating their own programme for targeted issues. This is mainly done through the companies’ internal CSR units who are engaged in developing and implementing these CSR activities. Some have appointed Chief Sustainability Officers to provide dedicated focus on internal and external corporate sustainability issues at the top management level. Another trend in recent years is the formation of foundations by large companies to facilitate the CSR work. The foundation can streamline the CSR mandate of the company and work with various partners including CSOs, NGOs, communities, schools, social enterprises, etc. They also diversify their contribution and engagement to many different areas, including arts, sports, culture, health, education as well as the traditional themes of poverty reduction, the environment, women and skills training. In order to have greater publicity and brand exposure, these foundations are also looking for credible partners to enjoy greater mutual benefit from their CSR activities. Besides these sectors, foundations and the business sector are also moving into impact investing, of which, the Malaysia Business Angels Network (MBAN) is one of the coordinating platforms.

The above mentioned trends, however, have not been well-researched recently and this assignment aims to look into this in order to identify trends with mutually beneficial opportunities for business engagement strategies.

### The civil society sector

Traditionally, UNICEF has strengthened collaboration and enhanced capacities, partnerships and engagement with CSOs for child rights advocacy, outreach and monitoring, and for mobilization of national resources.

In 2013 the Sustainable Development Solutions Network (SDSN) Malaysia was set up to support the localization of the SDGs and their implementation. It aims to mobilize a community of experts and influencers to translate ideas and expertise into practical action towards the sustainable development for the country.

The CSO-SDG Alliance was formed in 2015 and has been active in the national SDG alignment, participating in the National Symposium hosted in 2016 by the Malaysian government and the UNDP. The CSOs in the Alliance presented their SDG findings and recommendations and called for space for active CSO engagement in the SDG process at all levels.

Many of the CSOs are now looking for financial support from the business sector to sponsor their programmes. This support typically is obtained through the sustainability foundations set up by large companies in Malaysia, like the Hasanah Foundation, the CIMB Foundation, the Sime Darby Foundation and the PETRONAS Foundation. At the moment it is unclear how these, larger and smaller, (I)NGOs in Malaysia partner with these foundations and whether they engaged in an actual partnership or are simply beneficiaries of funding.

The current assignment will obtain inputs from CSOs, particularly larger (I)NGO’s, on their experiences working with the business sector in various areas and use lessons learned from these cases.

### Business engagement strategies of other UN agencies

UNICEF Malaysia is part of the UN Country Team (UNCT) in Malaysia, which is led by the UN Resident Coordinator, and is represented by United Nations Development Program (UNDP), United Nations Children’s Fund (UNICEF), United Nations Population Fund (UNFPA), United Nations High Commissioner for Refugees (UNHCR), World Health Organisation (WHO), World Food Program (WFP), International Organisation for Migration (IOM), United Nations University-International Institute for Global Health (UNU-IIGH), UN Department for Safety and Security (UNDSS) and WHO-Global Services Centre (WHO-GSC), which are a part of UN agencies in Malaysia.

Other UN organisations such as UN Educational, Scientific and Cultural Organisation (UNESCO), UNAIDS, Office of the High Commissioner for Human Rights (UNOHCHR), International Labour Organisation (ILO), and UN Industrial Development Organisation (UNIDO) are non-resident but cooperates with the Malaysian Government.

The UNCT organised the SDG Business Summit 2017 with The Global Compact Network Malaysia (GCMY) and Securities Industry Development Corporation (SIDC). The UNCT Malaysia, comprising various UN funds, programmes and agencies, expressed the intent to build strategic partnerships with business enterprises, under the 17 goals and 169 targets of the SDGs. The UNCT also initiated a study to develop a strategic document for Private Sector SDG Engagement by 2018.

In 2019 the UNCT and government of Malaysia conducted a National SDG Summit where, among others, a business leaders SDG forum was held to discuss private sector leadership actions for a sustainable Malaysia. Recently, Bank Rakyat became the first national organisation to partner under the UNCT’s ‘Together for Sustainable Development Goals (SDGs)’ programme. The “TOGETHER for SDGs Hub” is designed on the principles of ‘crowdsourcing’ and responds to the need for effective resource mobilisation by matching financial and non-financial contributors in developing initiatives to address SDG-related gaps in areas of Leaving No One Behind, Gender Equality and Women’s Empowerment and Environmental Sustainability.

The UNCT, through the SDG group, also has been leading the efforts for a Malaysian SDG dashboard. A launch was held with several business sector partners in March/April 2019. This relatively new dashboard is supposed to function as a platform where also private sector partners contribute their data for their contribution to the SDGs. There is, however, no data on the dashboard (yet) regarding civil society - business engagements.

With the United Nations Sustainable Development Cooperation Framework for Malaysia (UNSDCF) being finalised, there is a greater need for UNICEF to strengthen its internal capacity and focus on working with the private sector within the context of One UN to deliver the SDGs.

The other UN agencies are also pursuing the private sector partnership for their resource mobilisation and programmatic impact, but at the moment we have not been able to obtain documents providing details of these programmes. That will be part of the second phase, the main research phase.

### Summative and formative object of the evaluation

The object of the evaluation is split into two parts: the object of the summative part of the evaluation and the object of the formative part of the evaluation, further detailed below.

#### Object of the summative part of the evaluation

The object of summative part of the evaluation is primarily the past business engagement approaches/ actions of UNICEF Malaysia under the CP 2016-2020, and secondary the business engagement strategy within the CP 2016-2020 itself.

The past business engagement approaches and the overarching strategy will be evaluated for their relevance, coherence, effectiveness and sustainability towards the CP 2016-2020 business engagement objectives, with the main aim to identify lessons learned for future (CP 2021-2025) business engagement strategies, which will hence feed into the formative part of the assignment, see below.

During this inception phase, 12 past UNICEF Malaysia business engagement approaches/ activities (BEAs) during the CP 2016-2020 period have been identified (see below). However, the inception phase identified a rather substantive lack of documentation of these activities. No clearly formulated results frameworks or Theories of Change (ToCs) have (yet) been found. Furthermore, it is in many cases unclear who the actual beneficiaries or intended beneficiaries were/ are and what result was intended to be achieved. In paragraph 2.5 these details are presented.

This means that the evaluation will need to collect a lot more information during the main research/ data collection phase, using secondary data (reports, if any) and the planned interviews, Focus Group Discussions (FGDs) and (mini-) workshops in order to find out what was actually intended, who the beneficiaries and other stakeholders were, and what their contribution to the CP 2016-2020 Objectives was. This means that the evaluation will not assess each of the 12 past business engagement approaches, but rather their collective relevance, coherence, effectiveness and sustainability towards the CP 2016-2020 business engagement objectives, with the primary aim to draw lessons learned for the future. For this, we will mostly use recall by the direct stakeholders involved (UNICEF and (business) partners).

#### Object of the formative part of the evaluation

As clearly expressed by the management of UNICEF Malaysia, the formative part of the evaluation is a priority. However, it is recognised that the summative part is needed to capture lessons learned to inform the formative part of the evaluation.

This formative part of the evaluation will also focus on relevance, coherence, effectiveness and sustainability of the (potential of) UNICEF Malaysia’s planned and unplanned business engagement approaches. The object of the formative part of the evaluation is UNICEFs business engagement strategies/ approaches in the CP 2021-2025; to what extent are these business engagement approaches clearly mentioned, formulated and based on a sound knowledge and understanding of needs and opportunities of the various stakeholders, and how can these be operationalised better to contribute to achieving the CP2021-2025’s objectives.

Hence, the formative evaluation object is the CP 2021-2025, but not merely to assess the current write up, but mostly to actively identify promising business engagement partners, opportunities and examples of existing approaches by other UN or (inter)national NGOs, and the translation of these findings into concrete recommendations on how to operationalise (planned and unplanned) partnerships and business engagement strategies to address issues affecting children as outlined in UNICEF’s CP 2021-2025, and to advance its programmatic, advocacy and fundraising goals and leveraging business sector partners’ CSR to common goals. Hence, the primary object of the evaluation is indeed UNICEF’s CP 2012-2025, but a strong focus of the evaluation will be on (learning from) other UN/(I)NGOs business sector engagement strategies and an identification of opportunities and needs for leveraging business sector’s corporate sustainability/ corporate social responsibility (CS/CSR) approaches.

At the time of this inception phase, the CP 2021-2025 was not completely (formally) finalised, but draft ToCs and results frameworks existed. These have been reviewed below.

### Details on the object of the evaluation

This paragraph briefly discusses the details that emerged from the desk study, the intake phase interviews and mini-workshop, and the survey. These details helped us shape our understanding of the object of the evaluation, the approaches and methodologies in this next chapter and the final Evaluation Matrix (paragraph 4.5).

Between 2010-2011 and 2015, UNICEF’s work on corporate social responsibility included the establishment of a relationship with the Companies Commission of Malaysia (SSM), the launch of the Children’s Rights and Business Principles (CRBP) and training to raise awareness and strengthen capacities. Since 2007, UNICEF has also increased its focus on resource mobilisation for investment in children in Malaysia and globally.

In the 2016-2020 Country Programme, UNICEF Malaysia has renewed its non-financial engagement with the corporate sector through a three-pronged approach. This included (a) changing business practices through building the capacity of business to translate the CRBP into tangible actions and sustainability policies such as due diligence guidelines; (b) promoting the application of corporate social responsibility as a process towards achieving results for children, and; (c) leveraging non-financial resources from the business sector in the form of technical expertise, technology applications, research, marketing and market shaping through sector best practices (e.g. child care centres in the workplace, DIGI and MOCRIA, the study of the palm oil sector, and also currently with Sime Darby properties), amongst others. Child rights and business principles activities are currently undertaken with a network of corporate partners.

In 2013, UNICEF Malaysia produced a background study on CSR titled, “Corporate Social Responsibility Policies in Malaysia: Enhancing the child focus”. There was another attempt to develop a draft Corporate Social Responsibility strategy for UNICEF Malaysia sometime after that.

In the Annual Report 2018, UNICEF Malaysia noted that there are substantive opportunities to engage the business sector in sustained interventions for children, beyond one-off events or projects. It acknowledged that its capacity to tap into this will require a strategic shift and internal capacity-building to better understand industry players and how to engage to scale up results for children. This will require UNICEF Malaysia to research and draw on the expertise of its private sector fundraising team to market development and rights-based language into shared-value propositions with industry and individual corporations. UNICEF Malaysia recruited a Corporate Alliance officer to strengthen this important pillar of cooperation with the long term intention of integrating the corporate social responsibility and fundraising initiatives when approaching the business sector with the children’s agenda.

#### Country Programmes 2016-2020 and 2021-2025

The business sector engagement was integrated into the country programme 2016-2020 as per the global UNICEF Strategic Plan related to business sector partnerships. The Country Programme 2016-2020 has specific outcomes and targets for business sector engagements, such as Output 1.5: “The Malaysian private sector has increased knowledge and commitment to its responsibility to respect children’s rights…”. Other outputs include a number of companies that incorporate elements of CRBP, a number of regional and global forums where Malaysia promotes children’s rights and the private sector financing net income.

The 2018 Mid Term Review of the UNICEF Malaysia programme affirmed that the priorities of the 2016-2020 programme remained relevant, and that UNICEFs strategic focus on strengthening the enabling environment (policies, plans, legislation, budgets, social norms) for child rights be maintained. In terms of gaps, the MTR signalled the need to upscale UNICEF’s support to address the double challenge of malnutrition (stunting and overweight). The MTR also signalled the need to strengthen platforms for enabling young people’s engagement and participation; encouraged further efforts to promote integrated multi-sectoral approaches to achieve results for children; social protection and policy development (partnerships with academia) and to explore the potentials for stronger private sector engagement leveraging on the benefit of being a hybrid programme and PSFR office. This would certainly allow for a stronger business sector engagement approach, including potentially a more Outcome Mapping (OM) oriented approach which would see the business sector as Boundary Partners (BPs). The review also led up to UNICEFs intensified support for the government’s roll-out of its Zero Reject Policy to ensure that all children in Malaysia, particularly those with disabilities and undocumented, have access to education; and strengthen evidence generation and policy dialogue on adolescent mental health and the impacts of climate change and environmental contamination on children.

Currently UNICEF Malaysia is developing its country programme for 2021-2026, which includes the above mentioned lessons learned. There is an intent to make business sector engagement approaches a key partnership strategy, ensuring UNICEF systematically looks for means to strategically engage with the private sector across its work to advance results for children (similar to innovation than gender or disability). This means that all outcomes and targets will ensure the business sector engagement approaches are strengthened. In the Programme Strategy Note (PSN) 2021-2025 the assessment is made that the “…appetite, capacity and potential of the private sector in mobilising public opinion and government action on critical child rights issues might have been under- estimated and inadequately leveraged”.

Figure 1 – UNICEF 2021-2025 Country Programme at a Glance

However, given all the above and within the context of this assignment, a preliminary assessment of the Results Framework, which is based on a Theory of Change analysis in the PSN, leads to the following comments on the (very tentative) Results-Framework:

- The Outcomes and Outputs are sometimes rather vaguely formulated and indicators for measurement are lacking.

- In the PSN it is stated that “UNICEF’s role and value addition will be primarily directed to strengthening the enabling environment for effective action for children”. This focus on an enabling environment is noted by the consultants and will need to be taken into account in the assignment, as it will have implications for the type of business engagement strategies UNICEF Malaysia might pursue.

- The PSN would probably benefit from a clearer visualisation of the Outcomes and matching Outputs, by means of a more elaborate (cascading?) Results Framework. For this evaluation the clarified outcomes and outputs are deemed important to assess to what extent cross-cutting business engagement approaches are incorporated correctly.

- Business sector actors are not often mentioned in the Outputs as (potential) partners along the lines of the above-mentioned Output 1.5: “The Malaysian private sector has increased knowledge and commitment to its responsibility to respect children’s rights…” etc. Where the business sector has been mentioned is in:

- On Outcome 1: Child Wellbeing, Equity and Inclusion programme, business sector organisations are mentioned in the Theory of Change of Output 1- Evidence-based Social Policy, where the business sector is referred to as duty bearers which should be held to account by governance mechanisms, rather than as stakeholders, partners in implementation of programmes or even as Boundary Partners whose attitude or behaviour we would like to see changed. The business sector is also mentioned in Output 3- nutrition: “Private sector appetite to support community-based nutrition work assessed”.  Also, Output 6- Adolescent Development and Participation briefly mentions “Partnerships strengthened with child and youth organisations and private sector to mobilise a network for adolescent development and skills building”, but on the related Outputs level there does not appear to be any business sector organisation mentioned.

- On Outcome 2: Ending Violence Against Children, the business sector is not mentioned at all.

#### Inventory of UNICEF Malaysia’s business engagements actions 2016-2020

From the Annual Reports, the Results Assessment Module (RAM), the Mid-Term Review of the CP 2016-2020 and the internal survey conducted by MDF (which was limited to get a better understanding of the universe of past partnerships and see what documents are available), the following initiatives emerged as business sector engagement activities:

- Sime Darby Property: first inclusive playground in Malaysia in the new township of Elmina, Selangor, to include end-user consultations with children with disabilities and their families to ensure that the playground is fit for purpose. UNICEF has invested in documenting this initiative for further scaling-up, with the aim of making inclusive playgrounds an industry standard

- SUNWAY University: Develop a module on Child Rights and Business under a new Masters of Sustainable Development with Jeffrey Sachs Centre for Sustainable Development, SUNWAY University

- Johor Corporation: Pilot model childcare centre at the workplace in the newest township in Malaysia, Pengerang

- Digi Telecommunications Bhd: two videos targeted at business stakeholders on how businesses can be drivers of change for achieving results for children

- Petrosains Malaysia: UNICEF disability training to adjust its exhibits to cater to children with disabilities

- Digi Telecommunications Bhd: Digital Learning as part of their Yellowheart Initiative on online digital learning skills for hard to reach and out of school populations in Sabah.

- Digi Telecommunications Bhd and The Star: SayaSayangSaya, Youth Townhalls campaign to raise public awareness about internet- related sexual crimes against children in Malaysia

- The Star media company: Predator in My Phone with R.AGE for the editorial campaign to raise public awareness about internet- related sexual crimes against children in Malaysia; and to call for laws to protect children from cyber-sexual grooming

- Digi Telecommunications Bhd: CyberSafe Bootcamp for 100 adolescents in Malaysia

- SP Setia Berhad: #standtogether Campaign against youth bullying with The Star media company and construction company SP Setia.

- NECD: Centre for Excellence Malaysia Evaluation Society, UNITAR National Evaluation Systems and Capacities for Evaluating Progress Towards the Sustainable Development Goals – the Malaysia Case Study.

- Mobile Operator Child Rights Self-Impact Assessment tool (MOCRIA) – to assess business impact on children, Digi Telecommunications Bhd. Apparently, the findings report was embargoed and no more information could be found.

For many of the above engagements, however, documentation is (so far) lacking. Some of these were mentioned in the annual report and country programme but without details or references to documents or responsible persons. The below table shows the findings on the attempt during the inception phase to identify goals/ objectives of the above actions and documents.

| Business Engagement Action | Partner(s) | Documents/ references | Clear object-tives /results | Beneficiaries (derived from limited data) |
| --- | --- | --- | --- | --- |
| 1-First inclusive playground in Malaysia | Sime Darby Corp. | - Handover notes by CSR officer - MOU document - UNICEF Annual Rep. | No data | Children with disabilities and families |
| 2-Module on Child Rights and Business under a new Masters of Sustainable Development | SUNWAY University | - Handover notes by CSR officer - MOU document - UNICEF Annual Rep. | No data | Future CEOs and corporate leaders |
| 3-Pilot model childcare centre at the workplace | Johor Corp. | - Handover notes by CSR officer - UNICEF Annual Rep. | No data | Children, Employees |
| 4-Businesses as drivers of change - supporting children’s rights through business | DIGI Comms | - Handover notes by CSR officer - 2 videos (not provided) | No data | business sector |
| 5-Disability training - exhibits to cater to children with disabilities | Petrosains Malaysia | - Handover notes by CSR officer - MOU document - UNICEF Annual Rep. | No data | Children |
| 6-Digital Learning - online digital learning skills for Sabah inland | DIGI Comms | Not available | No data | Students/ teachers? On-going |
| 7-SayaSayangSaya - public awareness about internet related sexual crimes against children | DIGI Comms | Project report and video report (not provided yet) | No data | Children |
| 8-Predator in My Phone - campaign to raise public awareness about internet- related sexual crimes | The Star media | Not available | No data | Children and youth |
| 9-CyberSafe Bootcamp for adolescents | DIGI Comms | Not available | No data | Children |
| 10-#standtogether - Campaign against youth bullying | The Star Media/ SP Setia Property | - Articles and videos (on website of #standtogether) - UNICEF Annual Rep. - No reports on role of UNICEF or monitoring notes on contribution so far | No data | Students/ children, teachers On-going |
| 11-National Evaluation Systems /Capacities for Evaluating Progress Towards SDGs | UNITAR Internat. University | Case study (not provided to us yet) | No data | Children? |
| 12-Mobile Operator Child Rights Self-Impact Assessment tool (MOCRIA) – to assess business impact on children | DIGI Comms | - Handover notes by CSR officer - Findings report embargoed | No data | Children, business sector? |

This is not to say that no documents on the above exist, but merely that this data gap will need to be addressed during the main research/ data collection phase.

Survey respondents also mentioned the following on the question of key elements that made a strategy, activity or partnership a ‘business engagement' strategy, activity or partnership in the last programme period (2016–2020):

- Public private partnership with government/Ministry of Education to manage project with other partners to ensure greater effectiveness, strategic value, sustainability and scalability of programme. This was also especially crucial in strengthening systemic and stakeholder capacity on issues related to SDG4, equity, inclusion and quality in education

- A shared vision, values and a common goal to realise

- A shared value proposition - with common goal, - joint ownership - contributions in kind or monetary from both sides, - Clear KPIs - with view to scale - not one off but longer term engagement, - sustainable in the long run - will no longer require UNICEF intervention, - demand driven - stakeholder (including government) interest in the outcome or product developed

- Companies/businesses that are keen to incorporate/strengthen children's rights and CRBP, relevant industry regulators, and CSOs/NGOs representing children & communities that are impacted by businesses.

- For corporate fundraising goals is to, i) maximize impact for children from the corporate sector ii) optimizing value for business and iii) driving sustainable funding through partnerships

- Tapping private sector's expertise to maximize programme results and to create a social movement with private sector

- Companies have a sustained engagement/buy-in for a programme initiative, and their advocacy around it

- Sound understanding of the private/corporate sector in the country context. Recognition of current political climate. Linking partnerships with private sector to statutory sector strategy/objectives

- The CRBP that drives the business sector engagement

- Shared vision & trust, mutual interest beyond just PR, continuity

A quick clustering of the above leads to a preliminary set of key elements which UNICEF staff think are important for a business engagement strategy, in order of most mentioned:

- Shared: vision, values, goals, results to be achieved (incl. maximising impact)

- Longer-term, sustainable partnership

- Understanding of the private sector context

- Value for business (mutually beneficial)

The above is interesting to understand UNICEF staff’s mind-set regarding business engagement and the (perceived) key elements that would make an engagement a successful business engagement strategy, activity or partnership.

The survey question on what made certain (above mentioned) business engagement strategies, activities or partnerships a success, most of the answers were very limited and variations on either: ‘the project results were met’ (which doesn’t necessarily answer the question or leads to a lesson learned) or: ‘the objectives and values of the business and UNICEF were/ were not aligned’. The assignment will need to look further into the possible reasons and lessons learned on why certain engagements were or were not deemed successful in their contribution to the CP 2016-2020’s objectives.

#### Geographic scope

Geographically, the summative part of the evaluation will focus on any area where business engagements of UNICEF Malaysia have taken place, which is mostly confined to Kuala Lumpur and Sabah (see above). Furthermore, the geographic focus of the formative part of the evaluation will be Kuala Lumpur and Putrajaya, given the policy advocacy and advisory focus of UNICEF Malaysia and the presence of the (policy and strategic nexus of the) major business sector stakeholders. Sabah State will also be included in a geographic scope for the formative part of the evaluation, as it is specifically mentioned in UNICEF Malaysia’s Programme Strategy Note 2021-2025: “…UNICEF… will be supporting joint initiatives in Sabah on accelerating results for children and addressing equity issues by leveraging resources, enhancing adolescents’ participation and strengthening key partnerships”. Other UN country offices and the regional office may be consulted as well.

## Evaluation purpose, objectives and scope

### Purpose of the evaluation

As mentioned in chapter 1, the evaluation’s purpose, objectives and scope have changed as compared to the original ToR (see Annex 1), based on the discussions during the intake phase and inception phase meetings. Together with UNICEF staff the following purpose and object have been agreed upon:

#### Purpose:

Assess and guide UNICEF’s business sector engagement and partnerships to respect and promote child rights. The findings, conclusions and recommendations of this evaluation will assist with the operationalisation of the future Country Programme strategies to engage the business sector to promote, respect and enhance the realisation of children's rights.

The purpose also is to provide concrete and tangible examples, suggestions and recommendations that will allow UNICEF Malaysia staff to design and implement business engagement strategies/ actions in line with UNICEFs standards and guidelines (among others on human rights, equity and gender) and the Country Programme 2021- 2025.

### Objectives and scope of work of the evaluation

During the intake and inception phase of the evaluation, the following objectives and scope of work has been agreed upon, in line with the above mentioned object of the evaluation:

#### Objectives

- Assess the extent to which UNICEF's 2016-2020 business engagement approaches and partnerships have been appropriately designed, efficiently and effectively managed (results-based oriented), and integrated across the Country Programme 2016-2020 (including the incorporation of equity, gender equality and human rights considerations), and to what extent they matched the mentioned CP business engagement objectives;

- Review the 2021-2025 CP Theory of Change to assess to what extent business engagement approaches have been sufficiently integrated and (visibly and explicitly) embedded in the ToC of the CP– particularly as it relates to the link between outcomes, outputs and the SDGs, as well as a link with the analysis of barriers and bottlenecks for changes in business behaviour;

- Identify what (other) business engagement opportunities, strategic approaches, partnerships and interventions can help UNICEF Malaysia achieve its CPD 2021-2025 objectives, and how to go about materialising these;

- Assess to what extent the Private Sector Fundraising and Partnership (PFP) approaches and the 2021-2025 programme strategies are reinforcing each other, to the mutual benefit of both, and provide recommendations for improvement, and assess to what extent UNICEF Malaysia is appropriately set-up (willingness, mind-set, capacity) to implement the CPD 2021-2025 business engagement approaches.

#### Scope

The scope of the assignment is hence to learn from the business engagement approaches of UNICEF Malaysia that have been carried out in the previous country programme period (2016–2020), as per objective 1, above. Furthermore, the assignment will be mostly forward looking, in line with the purpose and the objectives 2 – 4: a programme- and strategic planning focus combined with an organisation assessment. Some of the business engagement approaches, partnerships and interventions of the previous country programme are still ongoing, while some have ended. Hence, the evaluation will be partly summative and partly formative, but with a focus on learning for the future country programme period.

The assignment will cover all programmes and programme areas of UNICEF Malaysia in the period 2016-2020, the country programme 2021-2025 and its three inter-linked results-oriented programmes (1- Child Wellbeing, Equity and Inclusion; 2- Ending violence against children; and 3- Programme Effectiveness) and all three UNICEF Malaysia’s organisational sections. As mentioned in paragraph 3.1, the purpose of the evaluation is also to assist with the operationalisation of the future country programme strategies to engage the business sector and align with UNICEFs strategic plan, in which business sector engagement is specifically mentioned as a change strategy (“Harnessing the power of business and markets for children”, UNICEF Strategic Plan 2018-2021). In other words, we will include the draft country programme 2021-2025 in this evaluation (and part of that assessment is already in this inception report) in order to assist with the future work plans for the new CP 2021-2025.

Building on the inception phase’s intake discussions and meetings with UNICEF Malaysia staff and a preliminary desk study, the above mentioned purpose, objectives and scope have been further detailed out by means of an Evaluation Matrix (see paragraph 4.5).

### Rationale, users and intended use of the assignment

The assignment’s rationale is to explore pathways to align with UNICEFs strategic plan, in which business sector engagement is specifically mentioned as a change strategy, and to assist with the operationalisation of the future country programme strategies to engage the business sector to promote, respect and enhance the realisation of children's rights. UNICEF Malaysia acknowledges that the business sector is a potentially powerful and effective actor in bringing about socio-economic changes in society, but it currently has limited experience and understanding on how to go about engaging the business sector. UNICEF Malaysia is looking for answers on what modalities of business sector engagements exist, what can be learnt from them and which private business partners would be the best to partner with for which objective (programme, behaviour change, policy advocacy, influencing public opinion, market shaping (nutrition) and leveraging their CSR /CS programmes to common goals – including influencing sector wide business practices and opportunities for PPPs. Those are some of the questions that explain the rationale of this assignment. Furthermore, the PSN notes that the ”…MTR also signalled the need to… explore the potentials for stronger private sector engagement leveraging on the benefit of being a hybrid programme and PSFR office.”

The evaluation will be public, as per UNICEF guidelines, but it is expected that the interested audience will be mostly internal UNICEF (Malaysia and potentially wider UNICEF) staff, and secondary other UN agencies, as the purpose is heavily on how to best improve UNICEF engagements with the private sector: which private business partners would be the best to partner with for which objective (programme, behaviour change, policy advocacy, influencing public opinion, market shaping (nutrition). Hence, the evaluation is mostly an internal learning assignment and, as mentioned above, will be partly summative and partly formative, but with a focus on learning for the future country programme period.

## Approach and methodology

### Design and approaches

As mentioned in the previous paragraphs and in good discussion with the UNICEF Malaysia CO, the evaluation is designed to clearly address the four leading objectives (see paragraph 3.2). This leads to an evaluation that is partly summative (addressing objective 1), but mostly formative (objectives 2 - 4). The summative part will focus on the past business engagements of UNICEF Malaysia, while the formative part will review the ToC and PSN of the CP 2021-2025 and UNICEFs organisational readiness (see paragraph 2.4, Object of the evaluation).

In line with our understanding of the assignment, we suggest a learning-oriented and participatory approach of the research methodology and analysis, in which we would work in close collaboration with UNICEF and partner staff members involved in the business engagement strategies and actions over the last years and all staff involved in the design (and implementation) of the Country Programme 2021-2025.

MDF adheres to the definition and principles of the UNEG Norms and Standards for Evaluation, of which the first paragraph of the definition of evaluation reads:

An evaluation is an assessment, conducted as systematically and impartially as possible, of an activity, project, programme, strategy, policy, topic, theme, sector, operational area or institutional performance. It analyses the level of achievement of both expected and unexpected results by examining the results chain, processes, contextual factors and causality using appropriate criteria such as relevance, effectiveness, efficiency, impact and sustainability.

An evaluation should provide credible, useful evidence-based information that enables the

timely incorporation of its findings, recommendations and lessons into the decision-making

processes of organisations and stakeholders.

This evaluation, as detailed out per objective in the Evaluation Matrix, will mostly address the OECD/DAC evaluation criteria: relevance, coherence, effectiveness and sustainability.

Relevance: Is the intervention doing the right things? The extent to which the intervention objectives and design respond to beneficiaries’, global, country, and partner/institution needs, policies, and priorities, and continue to do so if circumstances change.

Coherence: How well does the intervention fit? The compatibility of the intervention with other interventions in a country, sector or institution.

Effectiveness: Is the intervention achieving its objectives? The extent to which the intervention achieved, or is expected to achieve, its objectives, and its results, including any differential results across groups.

Sustainability: Will the benefits last? The extent to which the net benefits of the intervention continue, or are likely to continue.

As per the ToR and discussion with UNICEF, impact and efficiency will not be part of the evaluation criteria. We would like to add that the evaluation focuses on a contribution analysis rather than attribution analysis (which would require a counterfactual- i.e. control groups and control areas).

Furthermore, the evaluation will include cross-cutting evaluation criteria on human rights, gender equality and equity, where the latter two are defined as (UNICEF Regional Office for South Asia, Glossary 2017, and UN.org website):

Gender equality: The concept that women and men, girls and boys have equal conditions, treatment and opportunities for realizing their full potential, human rights and dignity, and for contributing to (and benefitting from) economic, social, cultural and political development.

Gender equity: The process of being fair to men and women, boys and girls, and importantly the equality of outcomes and results.

Equity: equity means that all children have an opportunity to survive, develop and reach their full potential without discrimination, bias or favouritism.

Human Rights: Human rights are rights inherent to all human beings, regardless of race, sex, nationality, ethnicity, language, religion, or any other status. Human rights include the right to life and liberty, freedom from slavery and torture, freedom of opinion and expression, the right to work and education, and many more.  Everyone is entitled to these rights, without discrimination.

#### Some reflections on the ToR and the reasons for the proposed methodologies

Reading the ToR and the various documents, we feel there is a need to better define the beneficiaries, target groups and other stakeholders, whether they are called ‘rights holders’ or beneficiaries, ‘duty bearers’ or ‘boundary partners’ (which is the term used by the Outcome Mapping approach: individuals or groups that contribute to and are part of the programme’s vision, and which the project or programme can communicate with and affect change in). As the beneficiaries/ stakeholders of past (and potential future) business engagement approaches are currently unclear but crucial for the evaluation, this would need to be addressed during the first stages of the assignment. As there is no clear ToC or Results Framework, or other programme document, that clearly stipulates this, it is one of the reasons we propose a learning-oriented and participatory design of the research methodology and analysis. Also within UNICEF Malaysia there is a desire to explore possibilities, learn from other UN offices and businesses and try to define better how to go about the business engagement partnerships. This is relatively new terrain for many UN organisations, it is very context- and programme specific, and to a large extend depends on the willingness and choices made within the country office.

The above means that we intend to approach both the summative as well as the formative part of the evaluation as an explorative and learning-oriented process that does not aim to provide UNICEF Malaysia with ‘the’ business engagement strategies to pursue, but rather a description of the conditions, policies and opportunities related to potential business engagement strategies, combined with an analysis of examples and current abilities within UNICEF Malaysia, to better understand the enablers or drivers of success, leading to suggestions and recommendations.

In line with the above and the new objectives as stipulated in this Inception Report, MDF proposes a theory-based (reconstructing/ reviewing the theory of change) and a mixed methods approach (recall, perception surveys, opportunities identification and document review) drawing on key documents and programme approaches which will be used interchangeably, depending on the data and respondents available: Theory of Change, Results-Based Management (the Results Chain) and Outcome Mapping.

#### Theory of Change analysis (objectives 1 - 3)

The ToC process hinges upon defining all of the necessary and sufficient conditions required to bring about a given long term outcome. ToC uses backwards mapping requiring planners to think in backwards steps from the long-term goal to the intermediate and then early-term changes that would be required to cause the desired change. This creates a set of connected outcomes known as a “pathway of change”. A “pathway of change” graphically represents the change process as it is understood by the initiative planners and is the skeleton around which the other elements of the theory are developed. In both the summative as well as formative part of this evaluation reconstructing and reviewing the ToC (of the business engagement strategy, not of the entire UNICEF programme or of each business engagement action/ programme), is considered a useful approach to carefully (re-)formulate and analyse UNICEF’s intended and desired outcomes and assumptions for its overall 2016-2020 business engagement strategy, particularly where business engagement was placed (should have been placed) or should be placed in its own right as change strategy. This will then be reviewed on the basis of the various UNICEF strategy documents, other UN agencies strategies and the policies of the Malaysian government to assess coherence.

The above (summative) reconstruction and review of the CP 2016-2020 ToC for business engagement strategies of UNICEF Malaysia is needed to understand better the reasons for the programmatic choices made, the (intended) beneficiaries and the intended outputs and outcomes. Only when that is clear, and the reconstructed ToC is discussed and validated (by the reference group and selected UNICEF Malaysia stakeholders, the actual results can be evaluated.

For the (formative) reconstruction and review of the ToCs of the current PSN of the CP 2021-2025: these ToCs are rather basic at the moment and do currently not mention the business sector at all. A review of the PSN of the CP 2021-2025 with UNICEF staff should reveal the context of the design of these ToCs, the reason for the choices made and how these have been translated into the Results Chain/ Results Framework. The review of the ToC of the CP 2021-2025 will be limited to business engagement approaches/ strategies, as per the limitations of this assignment.

#### Results-based management: a results chain analysis (objectives 1 - 4)

Results-based management is complementary to the more in-depth (and less linear) ToC approach. In the context of this UNICEF Malaysia evaluation the most useful aspect of a Results-Based Management approach is the results chain, which will be reviewed after the reconstruction and validation of the ToC. Furthermore, the results chain (sometimes called results framework, usually with added indicators, assumptions etc.) is an important methodological framework to evaluate past and ongoing business sector engagements.

After the reconstruction and review of the overall business engagement ToC of the CP 2016-2020 (see above), each business engagement action/ programme (or clusters of them, grouped on the basis of beneficiaries or outcomes) will be translated into a results chain and its results evaluated based on recall (interviews, FGDs, KIIs) and document review (data from M&E systems and other documents), with the help of evaluations questions which have been formulated and grouped on the basis of the OECD/ DAC criteria (see the Evaluation Matrix in paragraph 4.5 below). The subsequent lessons learned will feed into the (formative) review and validation of the business engagement ToC of the current PSN of the CP 2021-2025 and will be used to address objectives 2-4. As mentioned above, the evaluation will not assess each of the 12 past business engagement approaches, but rather their collective relevance, coherence, effectiveness and sustainability towards the CP 2016-2020 business engagement objectives, with the primary aim to draw lessons learned for the future. For this, we will mostly use recall by the direct stakeholders involved (UNICEF and (business) partners).

In this assignment we understood that the CP 2021-2025 Outcomes are mostly a given, but that Outputs nevertheless might be up for discussion and review, particularly in terms of incorporating business engagement strategies.

#### Outcome Mapping (objectives 1 - 3)

Outcome Mapping is a participatory monitoring and evaluation methodology that seeks to understand the ways in which organisations contribute to (policy) changes in behaviour, relationships, activities and/or actions of people, groups, and organisations (including the business sector) with whom a programme works, or tries to influence, directly. Outcome Mapping is based on the principle of actor-centred development and behaviour change: it is only when the actors involved in / targeted by an intervention change their ways of working, progress towards desired outcomes can be achieved. For this UNICEF evaluation it is deemed an appropriate methodology as it assesses behaviour change and changes in the enabling environment, which, as indicated above, are major components of UNICEF Malaysia’s CP 2021-2025, and allows to match the actions with the stated (policy) goals of the CP 2021-2025.

How this Outcome Mapping approach will be used is that we will place the various elements of the results chains in a Strategy Map of the Outcome Mapping methodology and review/ validate the formulated Outcomes and Outputs in terms of wider UNICEF and governmental strategies and their potential to contribute to the (enabling environment of) SDGs. It will also be used to test coherence, by matching identified programmes and strategies of other UN agencies, INGOs and potentially the government and companies by means of the Strategy Map.

The Strategy Map would be of help to understand what actions were done/ undertaken in/ with the partnerships of UNICEF and the business sector, and its coherence, which would then be analysed for its effectiveness and relevance in achieving the desired results, which in turn will inform UNICEF Malaysia’s future business sector engagement strategies.

#### Organisational readiness (objective 4)

In order for MDF to address the 4th objective (“…assess to what extent UNICEF Malaysia is appropriately set-up (willingness, mind-set, capacity) to implement the CPD 2021-2025 business engagement approaches), we propose to use the SWOT (Strengths, Weaknesses, Opportunities and Threats) approach, based on the Integrated Organisation Model. The Integrated Organisation Model (IOM) will assist the organisational readiness analysis by focusing on the external (outside) analysis, primarily actors and factors in society, the internal analysis, by focusing on the various elements that make up an organisation, and subsequently analyse and build an understanding of the organisation and its capacities to implement the CP 2021-2025 and the identified business engagement approaches.

### Stakeholders

In terms of stakeholders to be met and interviewed for this assignment, the following categories were identified:

| Stakeholder types | For past engagements | For future strategies | Potential stake/ interest |
| --- | --- | --- | --- |
| Internal UNICEF Malaysia (incl. RO) | Ѵ | Ѵ | - Past lessons learned - Understand compliance with UNICEF guidelines - Identification of best practices of relevant others - Identification of types of business interest and preferred modalities - Identification of UNICEF SWOTs for increased effectiveness of the BEAs - Practical suggestions for future BEAs |
| Business sector actors and sectoral bodies (incl. private academic institutions) | Ѵ | Ѵ | - Compliance and access to partners to achieve CSR goals - Identification of (other) mutual interests and cooperation modalities - Visibility of CSR efforts |
| National level government | Ѵ | Ѵ | - Advancement of implementation of the SDGs - Progress on CS/CSR policies |
| Other UN Malaysia agencies | Ѵ | Ѵ | - Lessons learned of others (for) - Identification of possible future BEAs |
| Other UN outside Malaysia |  | Ѵ | - Lessons learned of others (for) - Identification of possible future BEAs |
| Selected INGOs/CSOs |  | Ѵ | - Identification of best practices of relevant others - Identification of types of business interest and preferred modalities - Identification of possible future BEAs - Identification of cooperation modalities with UNICEF and each other |

As for the above-mentioned selected INGOs/CSOs: these will mostly be interviewed to better understand possible future business engagement approaches for UNICEF, through lessons learned of these INGOs’ business engagement strategies, their experiences working with the business sector, and their interest in working with UNICEF on future business engagement approaches.

A list proposed types of interviewees/ respondents is presented in Annex 3, where it is also indicated who of those interviewees/ respondents are UNICEF Malaysia’s engagement partners in the past CP 2016-2020. For now, we don’t foresee to be meeting or otherwise engaging children directly in this assignment.

At the moment, the exact names of interviewees/ respondents are not know/ have not been selected, as we foresee that this will take quite a bit of time and will need involvement of UNICEF staff. Furthermore, the number of interviewees for each category will need to be be determined by the number of key people involved in the activity.

However, we do estimate that for each business engagement approach at least two UNICEF and two business sector interviewees will be identified. Of all categories, we will strive for at least 66 organisations covered by the surveys (see Annex 3) and hence at least 66 external respondents, and 20 internal respondents.

The following criteria for selection of interviewees/ respondents will be applied:

| Stakeholder types | Criteria for selection |
| --- | --- |
| Internal UNICEF Malaysia | - All staff involved in programmes and PFP, including management |
| Business sector organisations and sectoral bodies (incl. private academic institutions) | - Organisations and individuals involved with UNICEF Malaysia in past business engagement approaches/ programmes (see paragraph 2.5) - Management level, preferably strategic management level, of organisations mentioned in Annex 3 - CS/CSR staff of organisations mentioned in Annex 3 |
| National level government | - Key management level of government agencies that are involved in UNICEF’s country programme development, implementation and monitoring - Staff from government agencies that were involved in UNICEFs business sector engagement activities |
| Other UN Malaysia agencies | - Staff engaged in (recent past) business engagement approaches - Management staff who is interested to explore future business engagement approaches |
| Other UN outside Malaysia (other country offices as well as RO) | - Staff engaged in (recent past) business engagement approaches - Management staff who is interested to explore future business engagement approaches |
| Selected INGOs/CSOs | - Staff engaged in (recent past) business engagement approaches - Management staff who is interested to explore future business engagement approaches |

Please note, in terms of selecting interviewees we strive to uphold the principle of non-discrimination, whether on the basis of sex, age, religion, race, ethnicity, economic status, caste, citizenship, sexual identity, ability/disability or urban/ rural locality.

### Methodologies and data collection tools

MDF proposes mixed methods of desk studies, Key Informant Interviews (KIIs), surveys, Focus Group Discussions (FGDs), on-line questionnaires and mini-workshops, based on the approaches as described above (Theory of Change, Results-Chain analysis, Outcome Mapping and IOM). Additionally, we will be using a specific case study for the evaluation, in close cooperation with the UNICEF staff involved. The case study, however, has not easily been identified from our desk study, and we believe more research and feedback from potential business partners is needed before a relevant case study can be selected. Hence, we will be selecting the case study after the first round of interviews/ consultations with the business sector and in close cooperation with the innovation specialist. We propose to use a case study of UNICEF Malaysia and use a similar case study of another UN organisation/ INGO, which will be identified by means of a survey among UN organisations and INGOs, to test if a similar approach would have worked/ work in the case of the UNICEF Malaysia case study. The lessons to be drawn from this exercise would provide valuable insight and assist to understand and draw out any UNICEF context-specific realities. Some of the preferred criteria to select the case studies can be mentioned:

- Preferably the external case study is also from a UNICEF organisation, or from an (I)NGO working on child rights

- Preferably both case studies (the other UN/ INGO’s case study as well as UNICEF Malaysia’s) are in Malaysia

- Both cases involve a similar type of business engagement partner (business sector organisation) but no necessarily the same type of engagements

- The external case study has been positively evaluated, and both the business sector organisation as well as the UN organisation/INGO expressed a (very) favourable opinion of the engagement

- The external case study’s engagement has taken place recently (within the last 2 or 3 years) or is still ongoing.

#### Intake: key informant interviews and mini-workshop

The assignment started with an Intake in the week of 10-14 February, during which the UNICEF Malaysia office was visited. After intensive discussions with relevant UNICEF staff (including a mini workshop) the decision was taken to revise the purpose, objectives and evaluation questions as now presented in this inception report.

#### Desk study and reconstruction of the ToCs

The consultants conducted an elaborate desk study of key documents provided by UNICEF Malaysia, ranging from the Programme Strategy Notes to Malaysian government strategies.

During the desk study, the ToC of the CP 2021-2025 has been preliminary reviewed and comments provided (see above, paragraph 2.5). The preliminary review helped us to assess and refine the proposed methodology of this assignment. The assignment also foresees to reconstruct the ToC of the CP 2016-2021, but only for the business engagement approaches, as a participatory analytical exercise to answer some of the objectives of this assignment. The reconstruction of the ToCs (both of the CP 2016-2020 and the CP 2021-2025) will allow us to answer the evaluation questions (see the evaluation matrix) on the designs of the results-chains of both Country Programmes.

The list of initial documents for review is provided in Annex 2. More documents will likely be provided during the main data collection and analysis phase and added to the list.

#### Surveys

Three surveys will be conducted:

- A survey has been sent out to relevant UNICEF Malaysia staff in the week of 3 March. The short survey centred on the following three questions:

        - What were the key elements that made a strategy, activity or partnership a ‘business engagement' strategy, activity or partnership in the last programme period (2016 –2020)?

        - What business engagement strategies, activities or partnerships (please note the definition in the introduction) have you worked on in the past UNICEF Malaysia programme period (2016-2020)? Who were involved?

        - How successful was this/ were these engagements: What were the criteria for success, to what extent were they fulfilled and what were the major contributing factors to success or failure?

The answers to this survey took a bit of time, due to the deadlines related to the CP 2021-2025, and were ready to be collected by 20 March, when 11 respondents (partly) had answered the survey. The results of this survey have been mentioned in paragraph 2.5 of this Inception Report. The survey mostly identified what engagement strategies UNICEF Malaysia had engaged in. Further probing into the reasons for success of these engagements will be done by means of Key Informant Interviews (KIIs) with the staff involved.

- A second survey will be sent to other 26 UN agencies and international and national NGOs (see Annex 3). The objective of this survey is to:

        - Identify relevant business engagement approaches/ strategies of other UN organisations/ INGOs, their successes and failures, and to select an external case study (criteria mentioned above).

        - Identify key foci and elements of the UN organisations’ and (I)NGOs business engagement approaches and strategies.

        - Understand the pros and cons of different modalities of business sector engagements.

        - Identify potential interviewees/ respondents with expertise in business engagement approaches to probe further by means of interviews and/ or mini-workshops.

The survey, using SurveyMonkey, will include UN agencies and (I)NGOs selected with the help of the UNICEF Malaysia team. We aim to reach at least 20 UN agencies and international and national NGOs within Malaysia, and 20 outside Malaysia, of which as many as possible with a child rights’ focus. As we aim to learn from others regarding possible business engagement approaches, we deliberately have very few selection criteria for which types of engagements can be identified/ mentioned by the respondents. These criteria are:

- The engagement/ action is with a business sector entity, as defined in paragraph 4.4.

- The engagement fulfils de definition of business sector engagement, as defined in paragraph 4.4.

The survey will be sent out as a link in an explanatory email preferably send from a UNICEF Malaysia email address, in order to get as many replies as possible. MDF will collect, compile and analyse the results.

- A third survey will be sent out to 40 business sector organisations and relevant sectoral organisations that operate within Malaysia (see Annex 3), and at least 10 that operate in the wider ASEAN region, to:

        - Examine the key foci of the companies’ CSR/Corporate Sustainability (CS) strategies, including their match with/ contribution to the SDGs.

        - Understand the perception of UNICEF by the business sector in regard to UNICEF’s mandate, objectives, and achievements, and the match with their CSR/CS strategies.

        - Understand to what extend the business sector considers the UNICEF ‘brand’ of interest to collaborate with (more or less than with others).

        - Understand the key elements/ interests and contributions of the business sector to engage in a partnership engagement with UNICEF Malaysia (what, how, when, etc.?).

Sampling will include both business sector organisations that have worked with UNICEF before as well as those who have not. We strive to have a representation of organisations from a diverse range of Global Industry Classification Standard (GICS- 2018) business sectors, notably:

        - Energy

        - Education

        - Plantations

        - Consumer Discretionary

        - Consumer Staples

        - Health Care

        - Financials

        - Information Technology

        - Telecommunication Services

        - Utilities

        - Real Estate

For the 10 companies based outside Malaysia, these will be determined on the basis of the findings from survey 2 and interviews with regional UN organisations and INGOs.

The business sector organisations will be asked to focus on CSR/CS strategies with a (potential) impact on child rights and children’s wellbeing, but not necessarily exclusively focusing on children as beneficiaries.

This survey will be complemented by interviews with the responding organisations. We foresee to use the (national as well as international) CSR Awards winners as well as the Bursa Sustainable Reporting companies list as a source for which companies to include in the survey.

#### Interviews, FGDs and mini-workshops

15 Main Evaluation Questions have been formulated to address the 4 objectives of this assignment and match the OECD/DAC evaluation criteria relevance, effectiveness and sustainability. These evaluation questions, per objective, are spelled out in the Evaluation Matrix in paragraph 4.5, below, and data on these will be collected not only through the surveys and desk studies, but also through a variety of respondent interaction: either through interviews, Focus Group Discussions or mini-workshops.

These three modalities basically address the same questions and collect similar data, with the notable difference of the number of people involved, and interacting, at each event. For the interviews, FGDs and mini-workshops we will deploy a semi-structured approach, with the help of guiding evaluation questions. These guiding evaluation questions are mentioned in the evaluation matrix. Interview guidelines are presented in Annex 4. Which exact modality will be used, interview, FGD or mini-workshop, depends on the number of people that the respondent can and wants to make available. At the moment that is hard to gauge, as we first need to establish the individual contacts per organisation.

During the data collection the evaluation matrix will be used as a guide by the assignment team members to ensure the evaluation covers the key issues and incorporates sufficient variety of perspectives required for effective triangulation. The data collection will use mixed methods, using in parallel qualitative tools (desk studies, interviews, FGDs and mini-workshops with semi-structured guides mentioned in Annex 4, based on the evaluation matrix) and quantitative tools, if available (M&E data, statistics from the survey, etc.).

#### Assessment of the BEAs; a focus on qualitative data

The above-mentioned absence of project documentation (and hence absence of BEA-based reporting on outputs, outcomes or impact) means that this evaluation will have to rely heavily upon the collection of primary data through KIIs and FGDs to assess progress (basically: recall). This reliance on stakeholder information for the assessment of the collective BEAs contribution to the CP 2016-2020 objectives can be restricting insofar as interviewees tend to have limited experiences. The evaluators will attempt to mitigate this through saturation of potential participants and triangulating the data (interview findings from other interviewees, desk studies, surveys). A reliance on research participant information also hinges upon the availability of participants, their willingness, openness and ability to recall the needed information (if they are aware of the results of the BEAs in the first place), and a sufficient number of participants (Covid-19 constraints particularly might limit the number of FGDs and KIIs participants).

With the help of the above mentioned recall (FGDs and KIIs) the assessment will be done mostly based on the following three assessment criteria:

- Are the BEAs clearly linked to the CP 2016-2020 objectives (evaluation questions 1-3)?

- Are the BEAs clearly linked to Malaysian government’s objectives (evaluation questions 1-3)?

- How do both UNICEF Malaysia as well as the business sector partner assess the success (achievement of results) of the BEA (see evaluation question 4)?

Assessment rubric for each of the BEAs and the scoring (1-4) criteria

| Criteria | Not satisfactory (0) | Partially satisfactory (1) | Satisfactory (2) | Good (3) | Excellent (4) | Total score |
| --- | --- | --- | --- | --- | --- | --- |
| The BEAs objectives are clearly linked to the CP 2016-2020 objectives | - No documented references - Link is unknown - Program area is unclear - BEA vs CP objectives/ results not assessed | - Program area is clear - Some BEA references to CP objectives - BEA vs CP objectives/ results not assessed | - BEA objectives clearly align with CP objectives - BEA objectives have clear indicators that match with CP objectives - BEA vs CP objectives/ results not assessed | - BEA objectives and indicators clearly align with CP objectives - BEA vs CP objectives/ results have been assessed | - BEA objectives and indicators clearly align with CP objectives - BEA vs CP objectives/ results have been assessed and results found to be positive |  |
| The BEAs objectives are clearly linked to specific thematic areas within the 11th Malaysia Plan | - Same as above | - Same as above | - Same as above | - Same as above | - Same as above |  |
| Assessment of results by UNICEF Malaysia (scale of 1-5) | - Unknown and no results documented - No systematic monitoring and assessment of objectives done | - Some monitoring was done - No systematic assessment of objectives done, but informal assessment scores minimum 3 | - Clear monitoring was done - Formal assessment was done (documented) - Assessment of the BEA scores minimum a 3 | - Clear monitoring was done - Formal assessment was done (documented) - Assessment of the BEA scores minimum a 4 | - Clear monitoring was done - Independ. assessment was done (documented) - Assessment of the BEA scores minimum a 4 |  |
| Assessment of results by the business sector partners (scale of 1-5) | - Same as above | - Same as above | - Same as above | - Same as above | - Same as above |  |

### Working definitions

During this assignment the following working definitions will be used (for an explanation on the context of these definitions, see the context and findings chapter 2):

Business sector is defined as all companies (small enterprises and community-level entrepreneurs to large global multi-nationals, corporations and private sector academic institutions), multi-stakeholder platforms and industry bodies, business leaders (as influencers and philanthropists) as well as corporate and family foundations.

Business engagement: refers to any type of interaction with business entities, with different objectives, ranging from informal talks and discussions, to knowledge-exchange platforms, to full-fledged partnerships entailing funding or brand asset exchanges. These engagements may be implemented through different modalities, including but not limited to partnering, and may entail different levels of public exposure.

### Evaluation Matrix

The Evaluation Matrix (EM) will be organized around the four objectives of the evaluation (see paragraph 3.2, which are then matched in the EM with the OECD/DAC evaluation criteria relevance, effectiveness, coherence and sustainability. Furthermore, we included considerations on gender equality, equity and human rights in each of the objectives.

Abbreviations used for methods and approaches: ToC: Theory of Change. RC: Results-Based Management (the Results Chain). OM: Outcome Mapping. IOM: Integrated Organisation Model

Abbreviations used for data collection methods: KIIs: Key Informant Interviews. INT: Interviews. DS: Desk Study. FGD: Focus Group Discussions. WS: (mini-) workshop. SV: Surveys. Other abbreviations: BEAs: Business Engagement Approaches. SH: Stakeholders. DB: Duty bearers. BS: Business Sector

| Objective (see §2.2) | Evaluation Question | Criteria (DAC) | Analysis Method/ approach | Guiding questions per DAC criterion | Data collection methods | Data sources |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1-To what extent have business engagement approaches (BEAs) been integrated across the CP 2016-2020 and aligned with national priorities and development plans? | - Relevance - Effectiveness - Coherence | - ToC - RC - OM | Relevance: - What BEAs have been done? By whom? Why? For whom? (list) - Were equity, gender equality and human rights beneficiaries and aspects clearly stipulated? Split up and examine. - Analyse the evaluations done. To what extent were these objects of the evaluation already planned for in the CP? Were gender and human rights aspects addressed? Coherence: - Were the BEAs well-formulated and in line with the CP 2016-2020? With national plans? With GBSE? Effectiveness: - What were the dominant approaches? Which ones worked best, which ones not to achieve the goals? Why? How did gender and human rights approaches contribute to success? - What are the main lessons learned of these past BEAs’ contribution to achieving the CP objectives, specifically in terms of equity, gender equality and human rights? | - SV - KIIs/ INT - DS | - Unicef staff - Documents - SH, DB |

| Objective (see §2.2) | Evaluation Question | Criteria (DAC) | Analysis method/ approach | Guiding questions | Data collection methods | Data sources |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2-How did the design of the 2016-2020 business engagement approaches and partnerships take into consideration: - The CP 2016-2020 objectives - Identified needs of the beneficiaries or stakeholders - major external factors (enabling and disabling) - UNICEF global and regional guidelines - National context (legislation, business practices, - UNICEF comparative advantage - UNICEF brand considerations - Sustainability considerations - Office capacity (financial, human resources, willingness, skills) | - Relevance | - ToC - RC - OM | Relevance: - How did/ do you define and decide who is the SH, DB, RH for BEAs? EGH sensitive? - What did you do to come to a decision on what BEAs to pursue? What were your criteria? In hindsight, what should have been the criteria? - Could the BEAs be well- implemented by UNICEF itself? | - SV - KIIs/ INT - DS | - Unicef staff - Documents - SH, DB |
| 1 | 3-How effective has UNICEF been at integrating these business sector engagements across (and matching with) its CP 2016-2020 and in its work with partners? | - Effectiveness | - ToC - RC - OM | Effectiveness: - To what extent are different BEAs contributing to the implementation of sectoral programme interventions that promote equity, gender equality and human rights? - How effective have these partnerships been in the implementation of sectoral programme interventions that target children and adolescents, particularly most marginalised? - What can be said about different modalities of partnerships and their comparative efficiency to achieve planned CP results? | - KIIs/ INT - DS | - Unicef staff - Documents - SH, DB - Other UN offices |
| Objective (see §2.2) | Evaluation Question | Criteria (DAC) | Analysis method/ approach | Guiding questions | Data collection methods | Data sources |
| 1 | 4-How effective have UNICEF’s approaches been at changing business policies and practices (directly or indirectly) and how did these contribute to achieving UNICEF’s programmatic results? | - Effectiveness | - ToC - RC - OM | Effectiveness: - Were any of the programmes specifically targeting a change in business policies and/ or practices? If so, how did these policies take into account equity, gender equality and human rights? - Were these planned together with SH, DB, BS? - What can be said about their success rate? And what about their contribution to the CP results? | - KIIs/ INT - DS | - Unicef staff - Documents - SH, DB - Other UN offices - BS |
| 2 | 5-Is business engagement specifically mentioned (embedded) in any outcome or outputs of the CPD 2021-2025, and to what extent are they aligned with UNICEF global and regional guidelines? | - Relevance | - ToC - RC | Relevance: - Are, in any document, BEAs mentioned as strategies to (contribute to) achieve CP results? - How strong is their ToC and their RC formulation as per UNICEF guidelines? - To what extent are these BEAs clearly and sufficiently addressing equity, gender equality and human rights? | - DS | - Documents |
| 2 | 6-Are the results and assumptions of the ToC (outcome 1 & outcome 2), or at least the key results and assumptions, well-defined and measurable (visibly and explicitly) to allow for the inclusion of business engagement approaches and connection to the SDGs? | - Relevance | - ToC - RC - OM | Relevance: - How strong is the ToC and the RC formulation as per UNICEF guidelines, and in general, taking into account UNICEFs enabling environment focus? - Do they allow for inclusion of BEAs and connection to SDGs? - If so, which ones and how? Do they address equity, gender equality and human rights? | - DS | - Documents |
| 2 | 7-Has a proper analysis of barriers and bottlenecks for changes in business behaviour been carried out and translated into business engagement approaches? | - Relevance | - ToC - RC - OM | Relevance: - Who or what has been consulted and what tools were used? Was this done in a gender and equity sensitive manner? | - DS - KIIs/INT | - Unicef staff - Documents |

| Objective (see §2.2) | Evaluation Question | Criteria (DAC) | Analysis method/ approach | Guiding questions | Data collection methods | Data sources |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | 8-What are the most promising programme areas within the CPD 2021-2025 where business sector engagement strategies (approaches, partnerships and interventions) could yield the most effect to achieve the CP objectives? What engagement strategies could be pursued to achieve this? | - Relevance - Effectiveness | - ToC - RC - OM | Relevance: - What clusters of social impact policies/ CS/ CSR strategies are at the moment pursued by the BS at large? How do they fit with UNICEFs CP 2021-25? - How and where do BS leaders see a match between the CP and their social impact policies/ CS/ CSR strategies? What does this entail, practically? How do these CS/CSR strategies match with UNICEFs equity, gender equality and human rights approaches? Effectiveness: - How does the BS see the UNICEF ‘brand’ and what are the pros and cons for collaboration? - What are the conditions under which BEAs and a partnership with UNICEF are more or less favourable for the BS? How is the match with UGEB? - How does the BS think this can be translated into a fruitful partnership? And UNICEF? - Practically, what potential mutually interesting engagement strategies emerge from the assignment? How do these align with UNICEFs equity, gender equality and human rights focus? - To what extend do these potentially contribute to achieving the CPs objectives? | - SV - KIIs/ INT - DS - FGDs/ WS | - BS - BS sectoral bodies - Unicef staff - Documents - Other UN offices |
| 3 | 9-What are (other) areas of interests of the business sector to partner with MCO that could help achieve the CP objectives? | - Relevance - Effectiveness | - ToC - RC - OM | - As above (case study approach to identify opportunities that can feed into strategy for business sector engagement and programme priorities) | - SV - KIIs/ INT - DS - FGDs/ WS | - BS - BS sectoral bodies - Unicef staff - Case study |

| Objective (see §2.2) | Evaluation Question | Criteria (DAC) | Analysis method/ approach | Guiding questions | Data collection methods | Data sources |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | 10-What partnership modalities and other best practices in UN/ INGO business sector engagement strategies are ‘out there’ that MCO can learn from? How could they be applied to MCO? | - Relevance | - ToC - RC - OM | Relevance: - What partnership modalities and other best practices in UN/ INGO business sector engagement strategies does your organisation have? - How do they match with UNICEFs equity, gender equality and human rights’ focus? - What are the pros/cons, what makes them work not work to achieve your objectives? - How could they be applied to MCO? | - SV - KIIs/ INT - DS | - BS - BS sectoral bodies - Other UN offices - Selected (I)NGOs - Documents |
| 3 | 11-What are the key preconditions and elements (based on the above) for the development of a strategy for business sector engagement? What are the major enabling and disabling factors which influence achievement of sustainable results towards child rights? | - Effectiveness - Sustainability | - OM - Sense making | Effectiveness: - What are the key preconditions and elements (based on above) for the development of a strategy for business sector engagement? Sustainability: - What are the major enabling and disabling factors which influence achievement of sustainable results towards child rights and equity, gender equality and human rights? | - Analysis of the above findings | - Findings of the assignment |
| 4 | 12-What is the current situation on synergies between PFP and programmes (priorities, joint programmes/ programming, coordination, risks and repositioning, structure etc.), and to what extent do they complement each other? | - Coherence | - TOC - RC - IOM | Coherence: - To what extent do PFP and programmes collaborate, on what, with who, how? - Where and to what extent do they complement each other? | - KIIs/ INT - DS - FGDs/ WS | - Unicef staff - Documents |

| Objective (see §2.2) | Evaluation Question | Criteria (DAC) | Analysis method/ approach | Guiding questions | Data collection methods | Data sources |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | 13-What are the areas of synergies between PFP and programmes that can be further enhanced, and in what way, to achieve the CPD objectives (including roles, responsibilities and resources)? Are we both sitting at the right tables, reinforcing each other? | - Coherence | - IOM | Coherence: - What could be improved in that collaboration to maximize effectiveness in achieving the CP results? - What and how can be improved in order to maximise the benefit of BEAs for both PFP and programmes? | - KIIs/ INT - DS - FGDs/ WS | - Unicef staff - Documents |
| 4 | 14-What capacities does MCO need to implement the above mentioned business sector engagements and what are the major enabling and disabling factors to strengthen UNICEF’s engagement with the business sector for its long-term operating modalities as an organisation? | - Sustainability | - IOM - SWOT | Sustainability (of UNICEF): - Is/are the SWOTs clearly defined to achieve the CP results with the help of BEAs? - If not, what are they? - What are the major enabling and disabling factors to strengthen MCOs capacities? | - KIIs/ INT - DS - FGDs/ WS | - Unicef staff - Documents |
| 4 | 15-Given all the above, what does MCO need to know and/or do in order to limit reputational risks concerning business sector engagements? | - Sustainability |  | - What, according to the findings of the assignment, are the main risks to MCOs reputation when it comes to BEAs? - What are suggestions on how to limit these risks? | - Analysis of the above findings - DS | - Findings of the assignment - Other UN offices |

### Data gaps

After the desk study and preliminary findings, there are still certain categories of data gaps that need to be addressed in the next phase, particularly related to:

- Information on what were the objectives and what were the results achieved by each of the business engagement actions/ partnerships

- Aimed for business sector engagement outputs (and even outcomes) of the CP 2021-2025, or related enabling environment objectives and/ or the role of the business sector

- Documents of (examples/ case studies of) business engagement strategies of other UN agencies and INGOs

- Clarity on the roles and functions of UNICEF areas and staff related to business engagement

- It is not clear yet who we should be meeting/ interviewing at each organisation (even though the organisations and criteria are clear)

It is expected that all of the above data gaps can be addressed in the next data collection phase.

## Evaluation workplan

### Summary of phases

#### Inception phase

#### Intake/ kick-off phase

MDF always start any assignment, no matter how big or small, with an intake in which MDF and the clients will try to come to an increased mutual understanding of the process, outputs, the organisations (stakeholders) and individuals involved, reflection and feedback process and moments, timings, locations and much more. This intake will set the minimum parameters for a successful assignment, increases understanding between the individuals involved and builds trust. This intake meeting was held at UNICEF Malaysia’s office on Monday 10 February.

#### Inception visit

A face-to-face meeting/ mini-workshop was held on Thursday 13 February during which 8 participants, all UNICEF staff, attended. During this workshop the Purpose, Objectives and Evaluation Questions were discussed and (largely) decided. The results of this mini-workshop have been incorporated in this Inception Report.

#### Desk study 1 and survey

In the weeks after the consultants conducted an elaborate desk study of key documents provided by UNICEF Malaysia, ranging from the Programme Strategy Notes to Malaysian government strategies. The list of initial documents for review is provided in Annex 2.

A survey has been send out to relevant UNICEF Malaysia staff in the week of 3 March. The short survey centred on the following three questions:

        - What were the key elements that made a strategy, activity or partnership a ‘business engagement' strategy, activity or partnership in the last programme period (2016 –2020)?

        - What business engagement strategies, activities or partnerships (please note the definition in the introduction) have you worked on in the past UNICEF Malaysia programme period (2016-2020)? Who were involved?

        - How successful was this/ were these engagements: What were the criteria for success, to what extent were they fulfilled and what were the major contributing factors to success or failure?

The answers to this survey took a bit of time, due to the deadlines related to the CP 2021-2025, and were ready to be collected by 20 match, when 11 respondents (partly) had answered the survey. The results of this survey have been mentioned in paragraph 2.5 of this Inception Report.

#### Inception Report

The above culminated in the current Inception Report, which first draft was submitted on Friday 10 April. The delay between the availability of the first survey results (20 March) and the delivery of the Inception Report are mostly due to personal matters related to the Covid19 outbreak.

#### Main research phase; Review of the ToC, Interviews and Desk study 2

The main research phase starts after approval of the Inception Report and is set up along the lines of the 4 objectives and their evaluation questions (per OECD/DAC evaluation criteria), as per the evaluation matrix in .5, above:

#### a (joint) review of the ToC 2016-2020 (evaluation questions 1-4)

The assignment will start with a review/ clarification of the CP 2016-2020’s business engagement strategies, to better understand the context and reasons for the outputs and outcomes, and turn this into a tentative results chain. This results chain will be the benchmark for the evaluation of past business engagement strategies and is needed to address the first objective of the assignment and its matching evaluation questions (per the OECD/DAC criteria). The ToC will be discussed and validated by the reference group and relevant UNICEF Malaysia staff.

The methodologies for data collection for this evaluation will be the survey, interviews with relevant UNICEF Malaysia staff and a desk study of retrieved documents.

During this stage, the two surveys (for the business sector as well as for the UN/INGO agencies) will be send out.

At the end of this stage, a UNICEF Malaysia and external UN case study will have to be identified that can be used to answer evaluation questions and highlight some of the findings.

#### Assessment of the business engagement strategies; successes, failures and lessons learned (evaluation questions 1-4)

Per identified business engagement programme we will be organising interviews with involved UNICEF Malaysia staff, business sector actors and national government staff (to the extent that they were/are stakeholders in the business engagement programme) in order to be able to answer the evaluation questions. It is expected that this phase will generate more documents to be reviewed to address the data gaps mentioned above, particularly in paragraph 4.6.

#### a (joint) review of the ToC 2021-2025 (evaluation questions 5-7)

This step will involve a review of the various documents (part of which has been done during the inception phase, but updates to the PSN/CP 2021-2025 are expected) and interviews with relevant involved UNICEF staff. As in the first step, it is expected that the ToC review (for business engagement strategies only) will lead to a tentative results chain and, crucially, an Outcome Mapping strategy map, as explained in the above sections. This will highlight potential gaps in the CP 2021-2025 strategies and programming (and also addresses the OECD/DAC coherence criterion).

#### Identification of business engagement/ CSR/CS strategies by business sector organisations as well as other UN agencies and INGOs, and match with the CP2021-2025 (evaluation questions 8-11)

This step will start with the two surveys, described above, for the business sector as well as the UN/INGO organisations (timing-wise, the surveys can be send out already during the first step). After analysis of the survey results, this will then be followed up with interviews, FGDs or mini-workshops with as many of the identified organisations in Annex 3 in order to be able to answer the evaluation questions.

The data collection methods used: surveys, interviews/ FGDs, desk studies and case studies.

#### Interim sense-making phase

To a large extent the above steps/phases have addressed and enabled us to answer evaluation questions 1-11, which corresponds with evaluation objectives 1-3. At this point we would like to synthesise the findings and discuss these with the Reference Group, before we move to the next phase, which is related to the capacity of the UNICEF Malaysia office to implement business engagement strategies.

#### Integrated Organisation Assessment phase (evaluation questions 12-15)

We hope that by this time the Movement Control Order, limiting movements in Malaysia, might have been lifted and it would be possible to meet in UNICEF Malaysia staff face-to-face. We will then proceed with interviews and/ or FGDs addressing the internal capacity of UNICEF Malaysia, related to the evaluation questions 12-14 The interviews and FGDs, guided by the Guiding Questions, on all of the above phases, will yield findings and conclusions that will be presented and discussed in a (mini-) workshop with all UNICEF Malaysia staff. We will then proceed to do a joint SWOT analysis on the successful future implementation of UNICEF Malaysia’s business engagement strategies. Evaluation question 15 will also be addressed in this workshop, as well as in the next phase.

#### Analyse findings, validation and reporting

After the second phase, we will proceed to analyse the findings and engage in a process of validation with selected stakeholders (including the Reference Group) in order to discuss the findings, analyse these and validate. By this time, we expect that a face-to-face validation workshop will be possible. The next step would be to transform these into a clear report, with credible, reliable and useful evidence and actionable recommendations.

#### Presentation of results

The final result will be presented by means of a Final Report and, if so desired, a presentation to selected UNICEF Malaysia staff.

### Deliverables

As per the agreement during the intake phase, the following deliverables will be produced:

  - Results of the intake phase and inception visit (done)

  - Inception Report (in English only)

  - Final Report (in English, Executive Summary in the Malay language)

### Team composition, roles and responsibilities

#### MDF

MDF considered the requirements of the assignments and identified a capable mixed team which will ensure a high level of international knowledge and the national context, and rigorous evaluation and field study experience. Both consultants will be involved in the assignment equally in each phase.

| Name | Role |
| --- | --- |
| Mr. Bart van Halteren | Team Leader, corporate sustainability consultant and evaluator |
| Mr. Hari Ramalu Ragavan | Corporate sustainability consultant and evaluator |

#### UNICEF Malaysia

Unicef Malaysia will make available all relevant documents and assist in identifying interviewees/ respondents, and in connecting the evaluators with these interviewees/ respondents, including other UN organisations, national level government actors and business sector actors.

Furthermore, UNICEF Malaysia’s Reference Group and Evaluation Management Team will be involved in reviewing the deliverables produced by the evaluators and provide feedback at the end of each phase. The Reference Group will also be available for advise to the evaluators, upon request. The Management Team and Reference Groups consists of:

#### List of Members of the Developmental Evaluation Management Team

| Name | Title | Organisation |
| --- | --- | --- |
| Juanita Vasquez-Escallon | Evaluation Specialist (Evaluation Manager) | UNICEF Malaysia |
| Fairuz Alia Jamaluddin | M&E Officer | UNICEF Malaysia |
| Radoslaw Rzehak | Deputy Representative | UNICEF Malaysia |

#### List of Members of the Reference Group

| Name | Title | Organisation |
| --- | --- | --- |
| Riccardo Polastro | Regional Adviser, Evaluation | UNICEF EAPRO |
| Karla Correa | Corporate Alliances Specialist PFP-Offset Budget – EAPRO | UNICEF EAPRO |
| Marc Vergara | Chief Communications | UNICEF Malaysia |
| Sylvia Jihyun Yoon | Private Fundraising (PFP) Chief |  |
| Kenneth Wong Dai Jhin | Partnerships Specialist |  |
| Issmail Nnafie | Innovations Specialist |  |

### Timeline

The original time line for the assignment has been affected in several ways, ranging from a major change to the objectives and scope of the assignment, to a delay in survey results and a delay caused by the impact of the Covid19 on one of the evaluators. Furthermore, the government of Malaysia has implemented a Movement Control Order (MCO) from the 18th of March 2020, initially for two weeks until the 31st of March 2020, and then extended it until the 28th of April 2020. At the time of the completion of Inception Report, it was noted that the government may extend the MCO until mid-May 2020. This MCO affects the availability of stakeholders for the interviews, surveys etc., and the planned in-country missions by the consultants have been postponed. We also expect that this MCO limits the availability of interviewees/ respondents and the efficiency of organising meetings (on-line or otherwise).

However, as discussed with UNICEF Malaysia staff, the assignment focuses mostly on lessons learned and strategies for the operationalisation of the CP 2021-2025. Hence, there is no urgency or a specific deadline for the assignment to be finalised. Nevertheless, MDF of course strives to have the assignment finalised within a reasonable time-frame, suggested below:

The current document is based on the limited information available after the reformulation of the objectives. Furthermore, we realize that the timing of the assignment also depends heavily on the availability of the partners, resource persons and respondents in the field, particularly given the situation surrounding covid-19. Hence, flexibility is key.

### Quality assurance

MDF’s seal of quality assurance is its ISO certification and the client inclusive approaches as outlined above. Every step of the way the client will be on board and will understand what is being done and why. This allows for modification and corrective measures to improve quality and mutual agreement with the activities being implemented.

Furthermore, the two evaluators will constantly keep in mind to review and triangulate each finding, conclusion and recommendation, in order to ensure that the evaluation findings and conclusions are relevant and recommendations are implementable, as articulated in the UNEG Norms and Standards for Evaluation and UNICEF-adapted UNEG Evaluation Reports Standards. This includes:

- Ensuring the quality of data collected and integrity of analysis reflected in the evaluation deliverables;

- Ensuring that the data collection processes adhere to UNEG Norms and Standards;

- Ensuring that the qualitative and quantitative evidence gathered is comprehensive and robust enough to make an informed assessment in line with the evaluation’s objectives, and in support of the conclusion and recommendations put forward by the evaluation;

- Managing all data collection (e.g., interview processes, focus group discussions, survey, workshops, and desk study of documentary sources relating to the subject of the evaluation), analysis, reporting, and communication; and

- Finalizing travel arrangements, accommodation and equipment to be used during the evaluation (subject to discussion with the Evaluation Management Team).

The Reference Group, detailed above, will function as a quality assurance body and will be consulted at the end of each phase (see paragraph 5.1).

### Ethical considerations

Ethically, MDF is an organisation which applies the do-no-harm (DNH) approach in our field level work. The DNH approach used to be applied to contexts in conflict situations but it now is increasingly applied to other development contexts as well. The Do No Harm framework is an approach that is highly compatible with community-based participatory processes and may in fact help strengthen local capacities. Do No Harm is a concept that encourages development workers to examine how their interventions might reinforce and support conflict and inequalities.

This evaluation will be conducted in accordance with the UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis and the UNEG Norms and Standards, taking into account the following:

- Integrity, independence and impartiality:

The evaluators will be independent, impartial and unbiased. There are no conflicts of interest related to this assignment.

- Privacy and respects of rights:

The evaluators will conduct this assignment in a transparent way, but will respect the privacy of all involved. This means that although records will be kept, these will be kept confidential unless the respondent has given clear consent to the opposite. Respondents will at all-time be able to withdraw this consent.

- Avoidance of harm and fair representation:

As mentioned above, the Do-no-harm approach will be applied. We don’t foresee to engage with any vulnerable groups.

- Accuracy, completeness and reliability:

All data will be triangulated with the help of multiple sources. If only one source exists and the data is anyhow mentioned in any of the reports, this will be mentioned. The evaluation matrix is in all phases guiding and deviations, if any, will be carefully documented and reported. The Reference Group serves as one of backstopping entities to ensure accuracy, completeness and reliability.

- Reporting and acknowledgement:

If during the assignment any ethical issues arise, these will be documented and reported to the evaluation manager, including how these issues were mitigated.

As no vulnerable populations are included in the fieldwork, there is no ethical clearance needed for this evaluation.

### Limitations, risks and mitigation strategies

The assignment as planned now is methodologically very dependent on individual’s viewpoints and opinions as no independent evaluations or reviews have been carried out pertaining to UNICEF Malaysia’s past business engagement approaches. It has also become apparent that there is no uniform definition of what constitutes a ‘business engagement’, let alone a successful business engagement. While that is exactly what this assignment aims to bring out, it also poses limitations in terms of reviewing and assessing past engagement strategies.

Furthermore, the realm of CSR/ CS is very diverse and wide, and there are only so many business sector actors which can be met/ interviewed, all with different views and approaches towards CSR/CS. Lastly, the CP 2021-2025 hasn’t been finalised yet, and hence some limitations in terms of reviewing the CP are unavoidable.

| Identified risks | Likelihood and risk level | Mitigation strategies |
| --- | --- | --- |
| Availability and willingness of resource persons, interviewees/ respondents | Low likelihood, low risk | -UNICEF assistance in identifying involved persons (previous partners) -UNICEF introduction letter -Understand and accept that methodologies and approaches need to be adjusted, based on the availability, findings and discussions |
| Availability of documents, including in-depth reviews and evaluation documents | High likelihood, medium risk level | -We know the availability of documents is limited, hence the emphasis on interviews, FGDs and mini-workshops - Understand and accept that methodologies and approaches need to be adjusted, based on the availability, findings and discussions |
| Possible continued limitations on meetings due to the Covid-19 MCO in Malaysia. There are two factors to this risk: - MDFs preparedness and availability - The respondents willingness/ ability to engage in on-line meetings | High likelihood, medium risk level | 1-We propose to continue the assignment as much as possible, but replace the face-to-face interviews and meetings with on-line based methods and tools. MDF is set up for this, with platforms such as Moodle, Zoom and Skype Teams, as well as tools such as Murals. We do expect this to take more time in terms of preparation, though 2-It is our assessment that with our tools and platforms we can make the engagement as simple as possible, so all respondents can engage easily 3-For companies reluctant to use Zoom or any other platform, we can offer encrypted (usually WhatsApp) calls |
| Very limited relevant business sector engagement case studies and experiences within UNICEF Malaysia and in other UN agencies and INGOs | High likelihood, low risk level | The risk has been addressed in this inception report by means of revising the objectives, as discussed above. Furthermore, even if no similar experiences can be found at other UN agencies or INGOs, there will still be business engagement experiences to learn from |

## Budget

As we expect that the MCO in Malaysia, and other countries affected by Covid-19, will be gradually lifted during the course of this assignment, enabling travel, no changes to the approved budget are foreseen.

# Annexes

Original ToR

List of most relevant documents reviewed

- Report on Continuing inclusive Dialogues on implementation of the post-2015 Development Agenda, Malaysia, 2015

- UNICEF Strategic Plan 2018–2021

- UNSPF 2016-2020: Prosperous, Inclusive and Resilient Futures, Draft V1.1, 2 February 2014

- 12th Malaysia Plan 2020 to 2025, Development Dimension, Ministry of Economic Affairs 2019

- 11th Malaysia Plan 2016-2020

- 10th Malaysia Plan 2011-2015

- Annual Review Meeting Economic Planning Unit (EPU) – UNICEF 2018

- Evaluability Assessment UNICEF Malaysia Country Programme 2016-2020

- UNICEF Malaysia Annual Report 2018

- UNICEF CSO Procedure and Partnerships 2018

- Review of National Evaluation Systems and Capacities for Evaluating Progress Towards the Sustainable Development Goals 2018

- Mapping of UNICEF partnerships and collaborative relationships 2009

- UNICEF MALAYSIA MID-TERM REPORT 2018

- Programme Strategy Note for UNICEF Malaysia 2021-2025 Under 2021-25 UNDSCF Malaysia framework, 2019

- Malaysia UNICEF Country Office Theory of Change narrative for Country Programme 2016-2020

- ENGAGEMENT WITH BUSINESS Programme Guidance for Country Offices, 2019

- Corporate Social Responsibility Policies in Malaysia 2013

- UNICEF Private Fundraising and Partnerships, Annual Report 2018

- The KPMG Survey of Corporate Responsibility Reporting 2017

- Asia and the Pacific SDG Progress Report 2019

- Sustainability Reporting Guide, Bursa Malaysia 2018

- UNICEF due diligence process for corporate engagement, 2018

- UNICEF Malaysia Country programme document, 2016-2020

- 2018-RAM Assessment History - Output 3.2

- UNICEF Rolling Workplan 2019-2020 Final Approved by MEA

- UNICEF-SSM Toolkit How to set up a child care centre at work place, 2015

- United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation, 2016

- Sustainability Reporting in Malaysia-The Extent and Quality, 2019

- Opportunity 2030: The Standard Chartered SDG Investment Map, 2019

- Malaysia SDG summit 2019 Accelerating Progress on the SDGs” Whole of Nation Approach, UNCT

- UNICEF Investor Guidance on Integrating Children’s Rights into Investment Decision Making, 2019

- UNSDG Common Approach to Prospect Research and Due Diligence for Business Sector Partnerships, 2019

- CSR Malaysia Awards 2019

- UNICEF Evaluation Policy 2018

Proposed types of interviewees/ respondents

Tentative mapping of relevant stakeholders to be surveyed for surveys 2 and 3, and subsequently interviewed, + additional ‘internal’ interviewees

Marked with an ѵ are UNICEF Malaysia’s past engagement partners.

| Survey 3: Companies |  | Survey 2: UN organisations, INGOs and CSOs |  |
| --- | --- | --- | --- |
|  | Energy |  | UN organisations |
| ѵ 1. | PETRONAS Holdings (incl. Foundation) | 1. | International Federation of Red Cross and Red Crescent Societies |
| ѵ 2. | Petrosains Malaysia | 2. | Third World Network |
| 3. | SHELL Malaysia | 3. | Raleigh International |
|  | Education | 4. | United Nations Development Programme |
| 4. | SEGI University | 5. | UN High Commission For Refugees |
| 5. | Monash University Malaysia | 6. | World Health Organisation |
| 6. | Sunway University | 7. | United Nations Population Fund |
| ѵ 7. | UNITAR |  | World Food Programme |
|  | Plantations | 8. | International Organisation for Migration |
| 8. | TH Resources Bhd | 9. | United Nations University |
| 9. | IOI Bhd | 10. | United Nations Educational, Scientific and Cultural Organisation |
|  | Consumer Discretionary | 11. | United Nations Industrial Development Organisation |
| 10. | PADINI Holdings | 12. | United Nations Environment Programme |
| 11. | Berjaya Land Bhd | 13. | Food and Agriculture Organisation |
|  | Consumer Staples | 14. | International Labour Organisation |
| 12. | NESTLE Malaysia Bhd |  | INGOs |
| 13. | F&N Holdings | 15. | Greenpeace |
| 14. | Munchy Food Industries Sdn. Bhd | 16. | Care International |
|  | Health Care | 17. | Amnesty International |
| 15. | TMC Life | 18. | Mercy Corps Malaysia |
| 16. | IHH HEALTHCARE BERHAD | 19. | World Vision International |
|  | Financials | 20. | WWF Malaysia |
| 17. | MAYBANK |  | CSOs |
| 18. | CIMB | 21. | Malaysian Child Resource Institute |
| 19. | Bank Rakyat | 22. | Malaysian Council for Child Welfare |
|  | Information Technology | 23. | Yayasan Generasi Gemilang |
| 20. | IRIS Corporation | 24. | CSO-SDG Alliance |
| 21. | Star Media Group | 25. | Sustainable Development Solution Network |
| 22. | Google Malaysia | 26. | Teach For Malaysia |
| 23. | Microsoft Malaysia | Internal |  |
|  | Telecommunication Services |  | HQ |
| 24. | DIGI Communications |  | Global Partnership Advisor |
| 25. | Maxis Communications |  | Regional Office |
|  | Utilities |  | Michael Copping, Reg. Partnerships Advisor |
| 26. | Tenaga National Bhd |  | Country Office |
| 27. | YTL Corporation |  | Radoslaw Rzehak, Deputy Rep. |
|  | Real Estate |  | Issmail Nnafie, Innovations Specialist |
| 28. | Eco-World |  | Sylvia Jihyun Yoon, (PFP) |
| 29. | IGB Bhd |  | Kenneth Wong Dai Jhin, Partnerships spec. |
| ѵ30. | Sime Darby Bhd |  | Zoe Gan, Child Protection Specialist |
| ѵ31. | Johor Corporation |  | Indra Kumari Nadchatram, Comms Spec. |
| 32. | SP Setia Bhd |  | Stephen Barrett, Chief Social Policy |
|  | National Business Platforms |  | HR Manager |
| 33. | Bursa Malaysia |  | Iris (UNICEF’s ex-staff with CSR portfolio) |
| 34. | Securities Commission |  | Karla Correa, Corporate Alliances Specialist |
|  | Business Council for Sustainable Development |  |  |
| 35. | Federation of Malaysian Manufacturers |  |  |
| 36. | MICCI |  |  |
| 37. | MDEC (ecommerce) |  |  |
| 38. | EUMCCI |  |  |
| 39. | CSR Malaysia |  |  |
| 40. | Malaysia Business Angels Network (MBAN) |  |  |

Interview Guidelines

Interview Guidelines per stakeholder type

Stakeholder interviews will be a major set of data generated by this evaluation.

They will serve as a means to draw evidence from informants, but are also important

for consultation and to generate buy-in for the evaluation process.

All interviews will be conducted on confidential terms, to facilitate candid responses.  Reports will not include direct quotation or attribution without prior consent. It is likely that the majority of interviews will be carried out on an individual basis, but group interviews (and FGDs) may be considered where the quality of responses is unlikely to be compromised, for instance with representatives of business sector for a or one business organisation. Most will take place using telephone or e-conferencing facilities, as mentioned in this inception report.

We will employ an interview targeting strategy that is being developed based on the stakeholder analysis and criteria as presented in this inception report, and will report transparently on the names of people consulted, their principal organisational affiliation and gender. We strive for an equal number of male and female respondents, but this heavily depends on availability. A stocktake of respondents at regular intervals during the evaluation process will help identify any gaps and, if possible, the interview targeting strategy will be adjusted accordingly.

The evaluation team has adopted a protocol and standard format for writing up and sharing interview notes (in confidence). The basic standard template is illustrated below. The format is designed to strike a balance between standardisation and flexibility (given that the interviews are only semi-structured). Interviewers will use the Evaluation Questions and Guiding Questions as guideline questions, and in advance of the interview itself, will refer to the Evaluation Matrix and select from the detailed issues and questions the ones that seem most pertinent to the interview (bearing in mind that in-depth responses to more than a few such questions are beyond the scope of most interviews, so that prioritisation is extremely important). At the end of every interview, respondents’ suggestions on contacts to interview and documentation for follow-up, will be noted.

Below the steps of the interviews/ FGDs:

| Stakeholders | Steps |
| --- | --- |
| - All interviewees | - Introduction to the interviewers and the respondent(s) - Explaining the purpose, scope and steps of the interview - Explaining confidentiality and rights - Explain the focus of this interview by explaining the objective, the related evaluation question and start with the (selected) guiding question - The semi-structured interview will then proceed - Closure: the interview will be closed by thanking the respondent(s) and giving him/her/them a chance for asking questions, make comments, etc. |
| - Internal UNICEF Malaysia | - As above, 1, plus: - Stress the confidentiality of their assessments of past programmes and organisational ability |
| - Unicef HQ and Regional office | - As 1, plus: - Ensure we have received supporting documents beforehand, such as evaluations or promising programmes, etc. |
| - Business sector actors (past engagements) | - As 1, plus - Stress that confidentiality regarding business strategies/ competition is guaranteed, and offer to sign a non-disclosure agreement |
| - Business sector actors and sectoral bodies (new) | - As 1 |
| - National level government | - As 1 |
| - Other UN Malaysia agencies | - As 1 |
| - Other UN ex-Malaysia (other country offices as well as RO) | - As 1 |
| - Selected INGOs/CSOs | - As 1 |

Below the format for interview notes:

| Date: Name of respondent(s): Organisation: Email: | Location: Gender: Section/ Dept: Function: |
| --- | --- |
| Evaluation team members |  |
| Comments on introduction |  |
| Comments on confidentiality and rights |  |
| Comments on topic A |  |
| Comments on topic B |  |
| Etc. |  |
| Data/ documents recommended |  |
| Contacts/other respondents recommended |  |
| Closure comments by respondent(s) |  |

Survey questions

### Survey questions for the UN/INGOs

#### Objectives

        - Identify relevant business engagement approaches/ strategies of other UN organisations/ INGOs, their successes and failures, and to select an external case study.

        - Identify key foci and elements of the UN organisations’ and INGOs business engagement approaches and strategies.

        - Understand the pros and cons of different modalities of business sector engagements.

        - Identify potential interviewees/ respondents with expertise in business engagement approaches to probe further by means of interviews and/ or mini-workshops.

The survey will include UN agencies and INGOs selected with the help of the UNICEF Malaysia team, according to the criteria mentioned in this inception report.

#### Survey questions

        - Do you have business engagement plan/strategy, and what would you say is the main purpose of the strategy?

        - What are the modalities of engagement that your organisation has explored (only consultation, joint programme collaboration, funding only)?

        - What are the business sector engagement activities that your organisation has implemented in the past? Please list and briefly describe them (incl. a tick box on whether the engagement was only consultation, joint programme planning and collaboration, or only funding)

        - Please tick and describe if, who and how the following was addressed in your business engagement activity: (then three separate tick boxes: one on gender equality, one on equity and one on human rights, each followed by a blank box for them to write the beneficiary in and then a blank box for them to briefly write key words of the engagement).

        - Can you for each engagement describe if the engagement overall was a success or not (scale of 1-5), and describe the main reasons for success/ failure?

        - Specifically, for gender equality, equity and human rights, what were the main positive and negative drivers for success? (then three separate tick boxes: one on gender equality, one on equity and one on human rights, each followed by a blank box for them to write the positive drivers and a blank box to write the negative drivers in).

        - Can you for each engagement describe if the engagement was a success or not (scale of 1-5), and describe the main reasons for success/ failure?

        - How did you ensure that your organisation’s reputation/ brand name would not be negatively affected by the business sector engagement activity?

        - What would you do differently in future business engagement activities?

### Survey questions for the business sector organisations

#### Objectives

        - Examine the key focus of the companies’ CSR/Corporate Sustainability (CS) strategies, including their match with/ contribution to the SDGs.

        - Understand the perception of UNICEF by the business sector in regards to UNICEF’s mandate, objectives, and achievements, and the match with their CSR/CS strategies.

        - Understand the key elements/ interests and contributions of the business sector to engage in a partnership engagement with UNICEF Malaysia (what, how, when, etc.?).

#### Survey questions

        - What key areas of your Corporate Sustainability goals/strategies? (Economic, Social, Environment, please describe). How did you come to this selection and have you considered the SDGs when making this choice?

        - What is the main interest, the main purpose, of a CSR/CS strategy for your organisation?

        - How is equity, gender equality and human rights addressed in your Corporate Sustainability goals/strategies/ actions?

        - Has your organisation engaged with external partners to deliver your Corporate Sustainability goals/strategies? If so, what type of activities and with who? (Table + national CSOs, international CSOs, international multilateral organisations like the UN, government agencies, business associations, other: please specify)

        - What are the modalities of engagement that your organisation has explored? (Only consultation, joint planning and programme collaboration, funding only) and why?

        - Can you for each engagement describe if the engagement was a success or not (scale of 1-5), and describe the main reasons for success/ failure?

        - How familiar are you with the role and objectives of UNICEF Malaysia? (tick box 1-5: not aware to very aware)

        - How would you rate your perception of the work UNICEF is doing in Malaysia, and why? (tick box 1-5: negative perception to very positive perception+ explanation space)

        - Would you be considering engaging in a partnership with UNICEF Malaysia to jointly contribute to a social cause/ impact (tick box 1-5: absolutely not to yes, very much so)? Can you indicate what areas you would like to consider working on together with UNICEF?

        - Lastly, do you have any requirements or strong preferences when it comes to engaging in a partnership with UNICEF? Please name them.

Ten Principles: https://www.unglobalcompact.org/what-is-gc/mission/principles

http://report.businesscommission.org/report

UNICEF Engagement with Business - Programme Guidance for Country Offices (2019)

Idem

“…corporate responsibility is concerned with the relationships that a company maintains with its shareholders, clients, suppliers, creditors and employees, as well as with the communities in which it operates”. https://www.un.org/esa/socdev/rwss/docs/2001/20%20Corporate%20social%20responsibilities.pdf

https://www.unicef.org/malaysia/what-we-do

https://smemalaysia.org/

https://www.fmm.org.my/

http://mysdg.dosm.gov.my/

https://www.oecd.org/dac/evaluation/revised-evaluation-criteria-dec-2019.pdf

https://en.wikipedia.org/wiki/Global_Industry_Classification_Standard