Evaluation of the Nutritional Improvements through the Cash and Health Education (NICHE) II Program 	
(April 2021 – March 2022)

EVALUATION INCEPTION REPORT

Kenya Country Office

Date: May 9 2021

EVALUATION INCEPTION REPORT

Kenya Country Office

Date: May 9 2021

INCEPTION REPORT

Evaluation of the Nutritional Improvements through the Cash and Health Education in NICHE II Program

The purpose of publishing evaluation reports produced by the UNICEF Evaluation Office is to fulfil a corporate commitment to transparency through the publication of all completed evaluations. The reports are designed to stimulate a free exchange of ideas among those interested in the topic and to assure those supporting the work of UNICEF that it rigorously examines its strategies, results, and overall effectiveness.

The contents of the report do not necessarily reflect the policies or views of UNICEF.

The text has not been edited to official publication standards and UNICEF accepts no responsibility for error.

The designations in this publication do not imply an opinion on the legal status of any country or territory, or of its authorities, or the delimitation of frontiers.

The copyright for this report is held by the United Nations Children’s Fund. Permission is required to reprint/reproduce/photocopy or in any other way to cite or quote from this report in written form. UNICEF has a formal permission policy that requires a written request to be submitted. For non-commercial uses, the permission will normally be granted free of charge. Please write to the UNICEF Nutrition at the address below to initiate a permission request.

This inception report is part of the Formative Evaluation of the NICHE II program, which was commissioned by UNICEF Kenya and conducted by the American Institutes for Research (AIR). This report has been prepared by the evaluation team consisting of Juan Bonilla, Marlous de Milliano, Hannah Ring, Varsha Ranjit, Anaïs Toungui, Tamsin Walters and Emily Mbelenga.

Attribution: Please cite the work as follows: United Nations Children’s Fund, Inception Report of NICHE II evaluation, UNICEF, Kenya, 2021.

For further information, please contact:
Nutrition Section, UNICEF Kenya
United Nations Children’s Fund
UN Complex Gigiri, Block Q Upper Level
P. O. Box 44145 – 00100 Nairobi

Contents

Acronyms	v

Introduction	1

Context and Object of evaluation	2

Context of key social, political, economic, demographic, and institutional factors	2

Scale and complexity of object	5

Theory of change and Expected Results Chain	8

Key stakeholders involved	8

Purpose, objectives and scope of evaluation	10

Purpose of evaluation	10

Evaluation objectives	10

Scope	11

Timeline of evaluation	11

Evaluation Framework and Questions	12

Methodology	23

Component 1 & 2: Review of the NICHE II program and Refinement of the Theory of Change	24

Component 3: Development of the M&E framework	28

Component 4: Baseline evaluation	30

Limitations and Mitigation Strategies	40

Quality Assurance and Ethical Principles	41

Evaluation work plan	45

Phase 1: Inception (April-July 2021)	45

Phase 2: Formative evaluation (July- November 2021)	46

Phase 3: M&E framework (October-November 2021)	46

Phase 4: Baseline evaluation (August-December 2021)	46

Dissemination Plan	49

Regular stakeholder engagement	49

Dissemination workshops with stakeholders	49

References	51

ANNEXES	54

Annex A – Theory of Change	55

Annex B – Ethics Approach	57

Strategies to ensure active and equitable participation of diverse groups	57

Mitigating risks related to COVID-19	58

Annex C – Qualitative Protocols 	62

Annex D – Quantitative Survey Tools	114

Annex E – Team Composition and Responsibilities	167

Annex F – Terms of Reference	169

TABLES

Table 1. Refined Evaluation Matrix	14

Table 2. Document review Sources	24

Table 3. Proposed KIIs at National Level and in Kitui County	27

Table 4. RQA Methods and Sampling	33

Table 5. NICHE Treatment and Assigned Comparison Areas	36

Table 6. Project Tasks and Timeline 	47

FIGURES

Figure 1. Geographic Scope of Work	5

Figure 2. Timeline for the Evaluation of the NICHE Program	11

Figure 3. Research Components and Data Sources	12

Figure 4. Overview of the Evaluation Approach	23

Figure E1. Evaluation Team Composition	167

# Acronyms

AIR - American Institutes for Research

AMREF - African Medical and Research Foundation

ASAL - Arid and semi-arid lands

BFCI - Baby Friendly Initiative approach

CCC- Core Commitments for Children

CEDAW – Convention on the Elimination of All Forms of Discrimination Against Women

COG - Council of Governors

CRC – Convention on the Rights of the Child

CRDP - Convention on the Rights of Persons with Disabilities

CT-OVC - Cash Transfers for Orphan and Vulnerable Children

DCS - Department of Children Services

ERG – Evaluation Reference Group

FCDO - Foreign, Commonwealth Development Office

FES - Focused Ethnographic Studies

FGD - Focus Group Discussions

GoK - Government of Kenya

HIV – Human Immunodeficiency Virus

HRBA - Human rights-based approach

HSNP - Hunger Safety Net Program

ICCPR - International Covenant on Civil and Political Rights

ICESCR – International Covenant on Economic, Social and Cultural Rights

IYCF - Infant and Young Child Feeding

IRB – Institutional Review Board

KCO – Kenya Country Office (see also UNICEF KCO)

KEQ – Key Evaluation Questions

KII – Key Informant Interview

KNBS – Kenya National Bureau of Statistics

KNAP – Kenya Nutrition Action Plan

KSEIP - Kenya Social Economic Inclusion Program

M&E – Monitoring and Evaluation

MD&ASAL - Ministry of Devolution and Arid and Semi-Arid Lands

MEAL - Monitoring Evaluation, Accountability and Learning

MIS - Management Information System

MLSP - Ministry of Labor and Social Protection

MoH - Ministry of Health

NACOSTI - National commission for Science, Technology and Innovation

NDMA - National Drought Management Authority

NICHE - Nutrition Improvements through Cash and Health Education Program

NSNP - National Safety Net Program

OP-CT - Older Persons Cash Transfers

PWSD-CT - People With Severe Disabilities

QA – Quality Assurance

RDD - Regression Discontinuity Design

RFP – Request For Proposals

RQA - Rapid Qualitative Assessment

SBCC - Social and Behavioural Change Communication

ToC - Theory of Change

ToR - Terms of Reference

UN – United Nations

UNICEF KCO – United Nations Children’s Fund Kenya County Office

UNEG - United Nations Evaluation Group

# Introduction

Although Kenya has made great strides in reducing maternal, newborn and child mortality in recent years (UNICEF, 2019a), significant health and poverty disparities persist. Child poverty continues to affect 45 per cent of children in the country, and Kenya faces high levels of acute and chronic malnutrition, especially in the arid and semi-arid lands (ASAL) region (UNICEF, 2019a; KNBS, 2014). Because malnutrition is a major contributor to early childhood deaths worldwide, there is an urgent need to address poverty and related nutrition challenges in Kenya.

To respond to these challenges, the Government of Kenya (GoK) supported by the UNICEF Kenya County Office (KCO) developed and is implementing the Nutrition Improvements through Cash and Health Education Program (NICHE II). A program, which integrates nutrition as well as social and child protection into existing cash transfer programs to foster resilience and improve well-being among households living in poverty. The American Institutes for Research (AIR) together with our partners, Dalberg Research, nutrition and monitoring and evaluation expert Tamsin Walters and nutrition planning and research expert Emily Mbelenga have been contracted by UNICEF KCO to conduct a formative evaluation, including a baseline study. The purpose of this evaluation is to provide early evidence on the design, implementation and initial performance of the NICHE II program. The evaluation also contributes to refining the monitoring and evaluation (M&E) framework and serves as a basis for future impact evaluation.

The purpose of this inception report is to detail the evaluation design, methodology and plans as agreed with UNICEF KCO during the inception phase. During this phase, the AIR research team had weekly meetings with UNICEF KCO and some of its partners to discuss key aspects of the evaluation in more detail, such as the NICHE II beneficiary registration process, plans for the child protection component, the quantitative and qualitative methodologies and the development of the M&E framework. The outcomes of these meetings were used to refine the design and methods presented in this inception report. The design and planned activities are still in line with the original Terms of Reference (ToR) (see Annex E). In addition, during the inception phase we collected and started assessing documents for the document review, we initiated the internal and local ethical clearance process, and we developed draft data collection tools. Emerging issues included the international travel restrictions due to COVID-19, and uncertainty in the implementation timeline of the NICHE II. Regarding COVID-19, the AIR team recruited an additional team member, Emily Mbelenga, a local expert who will contribute to in-person data collection and verification of contextual appropriateness of tools and findings. Ms. Mbelenga is based in Nairobi. On the second issue, AIR proposes an evaluation design which does not interfere with the program implementation. The beneficiary and non-beneficiary samples are selected to adhere to integrity of the evaluation without disrupting the implementation schedule of the NICHE II.

Following this introduction, we briefly outline the context and object of the evaluation. We then describe the purpose, objectives and scope of the evaluation, followed by a detailed description of the evaluation framework. After that, we present our methodology including our quality assurance process, considerations of ethical principles. Finally, we discuss our evaluation work plan and dissemination plan.

# Context and Object of evaluation

## Context of key social, political, economic, demographic, and institutional factors

Background

Between 2015-2019, Kenya was one of the fastest-growing economies with a yearly economic growth of approximately 5.7% (World Bank, 2021). Several factors supported this consistent economic growth, including a stable macroeconomic environment, a favorable investor confidence, low oil prices, a dynamic tourism industry, strong remittance practices, and government-led infrastructure development (USAID, 2018, p.1). As such, in 2020, Kenya ranked 123 out of 193 UN member states in progress toward achieving seven sustainable development goals. Indeed, between 2005-6 and 2015–16, the proportion of people living below the absolute poverty line declined by 9.8 per cent (from 45.9 percent to 36.1 per cent) (UNICEF, 2019a). Further, between 2000 and 2015, the country successfully improved its net enrolment rates in education and advanced the promotion of gender equality and of empowerment of women (UNICEF, 2018).

Kenya has also made significant progress in reducing maternal, newborn and child mortality. For instance, maternal mortality decreased from 506 maternal deaths per 100,000 live births in 2003 to 362 per 100,000 live births in 2014 (KNBS, 2014). Similarly, under-5 mortality has experienced an annual rate of reduction of 3.4 per cent from 1990 to 2018 (UNICEF, 2019b). However, significant health and poverty disparities persist. The rate of dying under the age of 5 remains at 52 per 1,000 live births, which means that in Kenya “one in every 19 [children] do not survive to age 5” (KNBS, 2014). In addition, the incidence of child poverty continues to affect 
45 per cent of children (UNICEF, 2019a).

However, several human development targets are still lagging, including poverty and hunger, child mortality, HIV and AIDS, malaria and other diseases, and ensuring access to clean water supply and sanitation (UNICEF, 2018). Moreover, since 2020 the COVID-19 pandemic has significantly disrupted the country’s economy causing a decrease of 0.3% which is particularly reflected in the manufacturing and services sectors such as tourism and education (World Bank, 2021). The World Bank reports that the pandemic has caused “a weaker than expected global economic recovery undermining Kenya’s export, tourism and remittance inflows, renewed disruption to domestic economic activity from the pandemic, fiscal slippages, and weather-related shocks” (World Bank, 2021).

In terms of nutrition, the Kenyan Food Security Steering Group’s 2019 Short Rains Assessment reports that approximately 2.6 million people are facing acute levels of food insecurity due to “persistent droughts, high costs of domestic food production, high global food prices, low purchasing power, and displacement of farmers during election violence in 2007” (KFSSG, 2019; USAID, 2018, p. 1). For adults, adolescent girls from 15 to 19 years old are reported as the most malnourished group of women (USAID, 2018). Additionally, 27.2 per cent of women of reproductive age suffer from anemia, while 6.2 per cent of women have diabetes (Global Nutrition Report, n.d.). Simultaneously there are also 34.3 per cent of women over 18 years who experience overweight with 11.1 per cent being obese (BMI>20) (Global Nutrition Report, n.d.). Perhaps most alarming, inadequate infant and young child feeding practices are more frequent than in other countries and despite some progress the country still has considerable levels of undernutrition. For example, only 39 percent of children less than 6 months are not exclusively breastfed while 38 percent of children 0 to 23 were not initiated on breastfeeding within an hour of birth (KNBS, 2014). And among children 6 to 23 months old who are breastfed, only 22 per cent receive a minimum acceptable diet (KNBS et al., 2014). At the national level, 26 per cent of them are stunted, 11 per cent are underweight and 4 per cent are wasted (KNBS, 2014). These levels of inadequate feeding practices and undernutrition are important since children under 5 years represent 13 per cent of the Kenyan population in 2019, and their nutrition issues can have longer term effects. In addition, the national averages mask the differences by county. For instance, in 2019, among children 6 to 59 months wasting is up to 26 per cent in Turkana county, 12 percent in Marsabit, 12 per cent in West Pokot (Kenya SMART, 2019).

Child protection issues are another major challenge in Kenya. According to the NICHE inception report, 32 per cent of females and 18 per cent males experience sexual violence during childhood, and 66 per cent of females and 73 per cent of males experience physical violence. Similarly, the prevalence of violent discipline affects 52.5 per cent of young children aged 1–2 years – with 64.3 per cent of children aged 1–14 years in Turkana County. Much more needs to be done to improve health and nutrition outcomes in Kenya.

Nutrition and Social Protection

Social protection programs are effective tools to address the multidimensional nature of poverty. For instance, cash transfer programs provide poor households with supplementary income that can help to smooth their consumption curve, whether used for the purchase of food or to cover the costs of schooling and health care (DFID, 2011). Supplementary income is particularly important, as research has shown that poor households tend to cope with shocks by selling assets or reducing nutritional intake (DFID, 2011).

Evidence from Kenya in particular reveals that well-designed cash transfers integrated with quality welfare services can contribute to reducing nutrition and food insecurity. For example, the evaluation of the Hunger Safety Net Program (HSNP; Merttens et al., 2013) suggested that while the program had no statistically significant effect on dietary diversity after two years, poorer HSNP households experienced increases in the diversity of their diets (Bastagli et al., 2016). Another study, evaluating the impact of the Cash Transfers for Orphan and Vulnerable Children (CT-OVC) in Kenya, found significant impacts on food expenditure, food frequency and dietary diversity as well as health expenditures (Kenya CT-OVC Evaluation Team, 2012). Finally, an evaluation of the Kenyan Safety Net Program by MacAuslan and Schofield (2011) found a statistically significant decrease of 23.7 per cent in severe food insecurity.

However, most global interventions on anthropometric outcomes (height and weight of children) have not yielded statistically significant effects, which suggests that programs are mainly effective for improving intermediary nutrition outcomes (Bastagli et al., 2016). Further, there is still mitigated evidence in health outcomes because of the poor quality of the health care system, which emphasizes the importance of health care services quality in conjunction with the provision of social protection services.

National Safety Net Program and UNICEF’s contribution

In 2011, the Government of Kenya (GoK) reaffirmed its commitment to reducing poverty by launching the Kenya Social Protection Policy, which aims to increase access to social welfare services by vulnerable groups using cash-oriented programs and nutrition and child protection services. Under the Kenya National Safety Net Program (NSNP), the government established four cash transfer programs: Cash Transfer for Orphans and Vulnerable Children (CT-OVC), Older Persons Cash Transfers (OP-CT), Cash Transfers for People With Severe Disabilities (PWSD-CT) and the Hunger Safety Net Program (HSNP) (Government of Kenya, 2021). Eligible households for the CT-OVS, OP-CT and PWSD-CT receive a bimonthly sum of 4,000 Kenyan shillings to alleviate poverty, while recipients of the HSNP receive a bimonthly sum of 5,400 Kenyan shillings.

Despite these important initiatives, the GoK noted the urgency to complement cash transfer programs with “services which would foster resilience and improve well-being” (ToR). To do so, the GoK collaborated with the World Bank and the United Kingdom’s Foreign, Commonwealth Development Office (FCDO) to design the Kenya Social and Economic Inclusion Project (KSEIP). The KSEIP seeks to promote social and economic inclusion by providing NSNP beneficiaries with a variety of complementary services – beyond the simple delivery of cash transfers. The KSEIP is comprised of three components:

- Component 1: Enhancing institutional capacity and social protection delivery systems, particularly the coverage and functionality of the Social Registry, as well as continuing to improve the efficiency of other delivery mechanisms;

- Component 2: Investing in the scale-up of the existing nutrition-sensitive safety net, and testing customized economic inclusion models as a complement to the regular cash transfers to improve human capital and the self-sufficiency of poor and vulnerable households;

- Component 3: Improving the shock responsiveness of the safety net system by expanding its coverage and strengthening financing arrangements for enhancing households’ resilience and providing timely support to cope with recurrent climate-induced droughts.

UNICEF Kenya is supporting the second component of these initiatives, which focuses on integrating nutrition and social as well as child protection through the Nutrition Improvements through Cash and Health Education (NICHE II) program. The program’s theory was built on a pilot conducted in Kitui County from 2015 to 2017, which found higher improvements in nutrition knowledge within the intervention group. NICHE II is aligned with UNICEF’s country program and global targeted outcomes to reduce child undernutrition and its determinants through social and behavioural change communication (SBCC) and the provision of cash transfers. NICHE is also in line with the GoK’s social protection, nutrition and child protection priorities, in particular, the Cash plus agenda, the Social Protection Policy and the National Children Policy, the Kenya Nutrition Action Plan (KNAP) 2018-2022, specifically Key Result Area 14 in the KNAP (Government of Kenya, 2021). The program reflects the implementing agencies’ commitment to a human rights-based approach (HRBA) framework. In fact, while it is evident that NICHE is aligned with various human rights treaties ratified by Kenya, including the International Covenant on Civil and Political Rights (ICCPR), International Covenant on Economic, Social and Cultural Rights (ICESCR), Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW), Convention on the Rights of the Child (CRC), and Convention on the Rights of Persons with Disabilities (CRPD), our preliminary analysis of programmatic documents found limited reference to this alignment with the framework and the treaties. The research team plans to explore this question further during interviews with key stakeholders.

## Scale and complexity of object

Geographic coverage

Figure 1. Geographic Scope of Work

The NICHE program targets 23,500 households by December 2024 in five counties across Kenya: Kitui, West Pokot, Turkana, Marsabit and Kilifi (see Figure 1) (UNICEF, 2020).While Kitui was already covered by the initial pilot of the NICHE program, the additional four counties were selected based on the levels of deprivation and poor human development outcomes on poverty, chronic malnutrition, low food security, low county-level capacities, and prevailing challenges in the delivery of healthcare, nutrition and WASH-related. In 2014, 85 per cent of children in Turkana were multidimensionally poor, while West Pokot was the second county with the highest share of child poverty (KNBS & UNICEF, 2017). Kilifi and Kitui have among the highest reported levels of chronic malnutrition– with 46 per cent of children in Kitui and West Pokot being stunted (KNBS, 2015). In Kilifi, stunting affects 39 per cent of children and approximately 20 per cent to 29 per cent of children in Turkana and Marsabit (KNBS & UNICEF, 2017). In general, according to the GoK-UNICEF Kenya Country Program 2018–2022, the most deprived children in terms of nutrition (i.e., stunting and wasting) are found in the five selected counties. Distance to healthcare facilities in Turkana and Kitui remains one of the major barriers for women to giving birth in safe conditions (KNBS & UNICEF, 2017). Further, 87 per cent of children are deprived either through housing material or air pollution in West Pokot (KNBS & UNICEF, 2017). Finally, Kilifi and Marsabit, particularly, were one of the hardest hit counties during the 2017 floods caused by water drainage in the Western lowlands around Lake Victoria.

Program resources – HR and budget

NICHE is a five-year program funded by the World Bank and FCDO through the Kenya Social Economic Inclusion Program (KSEIP). Leaderships at the Department of Children Services (DCS) within the State Department of Social Protection, the Ministry of Labor and Social Protection (MLSP), as well as collaborations from the Ministry of Health (MoH), the National Drought Management Authority (NDMA) and County Governments manage the NICHE program (Government of Kenya, 2021). The DCS delivers NICHE through the CT-OVC program within the Ministry of Health to provide health and nutrition services in health facilities and communities as well as support all monitoring and reporting efforts.

UNICEF partners with the Government of Kenya to provide technical assistance on planning and budgeting processes, financial support, capacity building, systems strengthening and monitoring and routine quality assurance. UNICEF also brings unique expertise implementing integrated service delivery programs in the areas of nutrition, child protection and social protection. Under NICHE II, UNICEF has provided a three-year budget of USD 12,900,000 to cover the needs of approximately 23,000 beneficiary households (Government of Kenya, 2021; UNICEF, 2020).

Program interventions

The objective of the NICHE program is to improve the nutritional status of children in the first 1,000 days of life. The GoK is implementing NICHE II in five counties (Kitui, Kilifi, Marsabit, Turkana and West Pokot) through UNICEF’s technical support (Government of Kenya, 2021). As part of NICHE II, eligible NSNP beneficiary households that have a child under two years or a pregnant or lactating woman (i.e., households currently receiving the transfer under the CT-OVC, OP-CT, PWSD-CD, HSNP) receive an additional cash top-up of 500 shillings per month – for a maximum of two beneficiaries per household (Government of Kenya, 2021). Households receiving the cash top-up are also offered intensive nutrition counselling through the community health strategy platform and Baby Friendly Initiative approach (BFCI) (Government of Kenya, 2021). In Kilifi NICHE II includes additional counselling on child protection and serves as a pilot for integrating child protection SBCC with nutrition SBCC (Government of Kenya, 2021). The goal of the pilot is to secure children from violence, abuse, exploitation and neglect within the NSNP beneficiary households and surrounding communities (Government of Kenya, 2021). This is particularly relevant as Kilifi County has one of the highest reported rates of sexual exploitation and violence against children. Due to limited resources, the remaining counties are excluded from the child protection education training at this stage (Government of Kenya, 2021).

The BFCI – a community initiative to improve Infant and Young Child Feeding (IYCF) practices using packages of standardized-evidenced based complementary interventions promoting breastfeeding, complementary feeding, maternal nutrition, water, sanitation and hygiene, and early childhood development - delivers the counselling in nutrition and child protection (Government of Kenya, 2021). The Ministry of Health has adopted the BFCI approach to deliver community-based nutrition services to young children and mothers, but the model has not been implemented throughout the country. To support the NICHE interventions, the BFCI will be rolled out in all the counties where NICHE is implemented.

UNICEF plans to conduct several activities to support the implementation of the BFCI package. As stated in the ToR, these activities include:

Raising awareness to decision and policy makers on optimal feeding and hygiene practices for children and mothers;

Training of health workers and community volunteers on promotion of optimal hygiene, health-seeking and feeding practices for young children as well as pregnant and lactating women;

Mentoring community volunteers in providing community-based counselling;

Supporting community-based structures (mother-to-mother support groups, community groups) for peer support on optimal practices as well as community engagement in the provision of nutrition services; and

Establishing and supporting feedback mechanisms and platforms where the community provides feedback on delivery of nutrition services within the health facilities.

Finally, UNICEF will provide technical assistance for the program implementation during the first three years. In the last two years of the program, key stakeholders within GoK (Ministry of Labor and Social Protection, the Ministry of Health, Ministry of Devolution and Arid and Semi-Arid Lands, Council of Governors) will implement the program without support from UNICEF.

Implementation status

The COVID-19 pandemic caused an implementation delay of eight months, particularly for activities related to community mobilization and beneficiary registration. By adopting virtual modalities of working, UNICEF implemented the Operational Manual development for each county, drafted county workplans and budget reviews, established national coordination structures and finalized the NICHE MIS systems requirements specification and registration module.

CHASP Advisory recently completed the registration of beneficiaries in all five counties, along with providing technical support to GoK in the registration process for the NICHE program. The mass registration took place through a process of household selection from NSNP, community listing and registration was part of the efforts to scale up the NICHE program from one to five counties. During the process 12,582 households were registered in Kilifi (14.6 per cent), Kitui (15.8 per cent), Marsabit (20 per cent), Turkana (37.8 per cent) and West Pokot (11.8 per cent). At the time of this report, the registration lists are undergoing community validation. After validation, the final beneficiary list will be entered in the NICHE MIS, which will allow the Directorate of Children services to make the payments available to all beneficiaries registered CHASP, 2021).

In addition to the registration process coordination, structures among the various program components for the NICHE were also established at the national level. Coordination at the county levels (e.g., for the coordination among the parenting component, cash transfer and nutrition counselling) is underway.

## Theory of change and Expected Results Chain

UNICEF Kenya shared the preliminary Theory of Change (ToC) with the research team (see Annex A). The preliminary ToC resulted from a consultative process from NICHE working groups with technical support from the various UNICEF sections. AIR developed a research design to rigorously and thoroughly examine UNICEF’s ToC to explain the pathways through which the NICHE program is aiming to affect mothers’ and children’s well-being with regard to nutrition, health, and social and child protection. AIR will assess the linkages and pathways of the ToC to analyse the relevance, coherence and sustainability of this health education and cash transfer program in changing behavioural practices by caregivers and improving the functionality of community and institutional systems to deliver integrated nutrition and social and child protection services using the lessons learned from the NICHE pilot, our Document review and input from UNICEF, GoK and other key stakeholders. As further described in the Methodology section, we will consult with UNICEF, GoK and other key NICHE stakeholders to refine the ToC during the formative research in the second component of this evaluation. We will also assess the pathways that connect the program activities to the ultimate impacts and outcomes and confounding factors. Lastly, we will identify critical risks and assumptions so that appropriate mitigation strategies can be adopted during the implementation of the program and so that these factors are accounted for in further evaluation of the program.

UNICEF’s current ToC divides program activities into two main pillars. The first pillar focuses on the effect of the program at the individual and household levels. The inputs involve the cash transfer top-up, nutrition counselling and the parenting education component, each of which promotes household well-being through its own pathway. The pathways incorporate medium-term outputs on knowledge about health behaviours, availability of information about services and referral systems (if needed), resources to obtain goods and services, and knowledge about parenting. During the period in which the program focuses on inputs at the household level, it will also address the capacity of community and institutional systems to deliver integrated nutrition, cash and child protection services (second pillar). Medium-term outputs through this pillar include strengthening knowledge among health workers and improving delivery mechanisms for integrated nutrition and child protection services. In addition, target counties will also improve beneficiary identification for the existing cash transfer system. Together, these medium-term inputs will contribute to the program’s objectives, which are to strengthen the county-level integrated health and child protection strategy and improve the well-being of women and children in the longer term.

## Key stakeholders involved

The key stakeholders in the NICHE II Program are the Ministry of Labor and Social Protection, the Ministry of Health, Ministry of Devolution and Arid and Semi-Arid Lands (MD&ASAL), National Drought Authority, Council of Governors (COG) and UNICEF. In our evaluation design, we incorporated key informant interviews in two essential stages of the evaluation: first, during the formative research phase to provide inputs in the logical framework and research instruments for this evaluation and, second, during the baseline component to conduct a qualitative assessment of early stages of implementation of the NICHE II. We provide more detail and a list of key informants in the Methodology in the discussion of the first two components of this evaluation.

# Purpose, objectives and scope of evaluation

## Purpose of evaluation

The purpose of this evaluation is to conduct a formative evaluation of the NICHE II program to improve its design based on the initial performance as well as build the framework for systematically conducting monitoring and evaluation activities. The evidence from the formative evaluation will inform the GoK and its collaborating partners on future decisions regarding the Kenya Social and Economic Inclusion Project (KSEIP). The work under this formative evaluation aligns with the programmatic goals of UNICEF KCO. As outlined in the UNICEF Kenya 2018–2022 Country Program Document, the KCO plans to reduce stunting and mortality (Outcome 1) and improve programming through multisectoral program integration in the areas of nutrition, social policy and child protection sections and management. This goal supports the UNICEF global nutrition strategy to improve infant dietary practices and reduce stunting. Thus, UNICEF expects that the evidence resulting from this evaluation will contribute to guiding the organization’s overall operationalization of its global nutrition strategy.

## Evaluation objectives

As noted in the ToR, the NICHE II program encompasses four key objectives:

To identify and document key lessons learned, good practices and innovations from the NICHE pilot as well as the completed NICHE II inception phase, with a focus on gender, equity and child rights, that can inform and support NICHE II implementation

To refine NICHE II program design and the ToC

To improve monitoring and evaluation processes and systems for the implementation of the NICHE II program and its future evaluability

To establish a baseline against which the impact of NICHE II can be evaluated in the future

## Scope

This formative evaluation covers program design and implementation of the NICHE program in five counties (West Pokot, Kitui, Kilifi, Marsabit and Turkana). Programmatically, the evaluation will focus on each program component as elaborated in the implementation design. For instance, in Kilifi, the research team will evaluate the social protection, nutrition and child protection services. In the remaining counties, the evaluation will concentrate on the social protection and nutrition components.

Further, this formative evaluation goes beyond the work to be conducted under NICHE II and will also examine what worked and what did not work under NICHE pilot to better identify potential issues in the current program.

## Timeline of evaluation

The evaluation will take place from April 2021 until March 2022. During that time, AIR will conduct in-person (ensuring observance of COVID-19 prevention measures) and phone interviews with key regional and national informants, draft the formative evaluation report, develop an M&E framework and lead the quantitative data collection for a baseline survey alongside our local partner, Dalberg Research. The cumulative findings from this evaluation will be presented in the baseline assessment report. The following timeline illustrates the various phases of this intervention (see Figure 2), a more detailed timeline is included in the Workplan section.

Figure 2. Timeline for the Evaluation of the NICHE Program

# Evaluation Framework and Questions

In this section we describe the key components of this evaluation and present our evaluation matrices.. We link these research components to indicators, data sources, methods and tools that we intend to use. Based on the results of the formative research components (Components 1 and 2) we will further refine the evaluation questions, along with the indicators, if needed. Below we first briefly describe each of the four components guiding the evaluation design (see Figure 3).

Figure 3. Research Components and Data Sources

Component 1: Review of the proposed NICHE II program

This component comprises (a) a review of past work on the NICHE I pilot and what it has contributed to NICHE II’s inception phase and (b) an assessment of NICHE II’s objectives using an evaluation matrix that follows detailed questions organized along the relevance, coherence and sustainability criteria. We will focus on lessons learned, good practices and innovations coming from the pilot and inception phase. We created an evaluation matrix which we further refined in discussion with UNICEF and key stakeholders. This component also includes a document review and formative key stakeholder interviews. The results of this component will feed into Components 2 and 3.

Component 2: Refinement of the program design and ToC

The second component uses the results from the review to feed into the existing ToC, as discussed previously. The assessment of the ToC contributes to the strengthening of the programmatic design of the NICHE II Program. The recommendations of the key stakeholders, together with consultations with UNICEF, will be used to further refine the ToC. The revised theory of change will be presented using an accessible diagrammatic model as well as a narrative description explaining pathways, drivers, barriers and assumptions.

Component 3: Development of the M&E framework

The results from the first two components will provide expected program outcomes, evaluation indicators and an understanding of what is valued by key stakeholders, all of which will be used to develop a comprehensive M&E framework. The M&E framework and plan will build on the preliminary results framework developed by UNICEF and will include the plans for the NICHE MIS.

Component 4: The baseline evaluation

AIR, together with Dalberg, will conduct a baseline evaluation that serves three purposes. First, an initial assessment of the situation in terms of nutrition and social and child protection contributes to understanding whether the programmatic design is aimed at addressing the key challenges. Second, the baseline enables future rigorous evaluation of the program to measure the effectiveness of the components. Lastly, the added focus on collecting costing data facilitates future efficiency analysis to provide insight on how to optimise the program.

The evaluation questions cover a modified set of the relevant OECD-DAC evaluation criteria (OECD, 2019). The evaluation matrix includes evaluation questions on relevance, coherence, sustainability, efficiency, effectiveness and impact that will be answered in the formative and baseline stages of the program evaluation. During the inception and formative research phase we have adjusted and added questions to ensure that the evaluation matrix reflects a holistic view of the multi-sectoral data we aim to collect and assess for this evaluation. The adjustments have been made as part of a consultative process with the various section representatives at UNICEF KCO. All questions marked with an asterix are questions which were not in the original ToR (see Annex E) and were added throughout the evaluation process.

Since the baseline is the groundwork for the future impact evaluation, we have added an impact evaluation questions column. Understanding what the key questions will be during the impact evaluation will help us to ensure that we are collecting all the necessary indicators at this stage. Within the column we have included ‘adjusted questions’ which generally focus on the impact or change in indicators. For these questions the baseline values will be used to compare any future values. We also indicated those questions that are most pertinent to the formative research only (e.g. questions on design or inception) and questions which we suggest to revisit in any follow-up survey (i.e. these do not necessarily have to focus on impact or change, but we think the topics will still be relevant in the future).

Lastly, the indicators, reference data tools and reference components refer to how we plan to answer and include the evaluation questions in the baseline and formative assessment. In particular, the reference component indicates the main component(s) under which we will collect, analyse and report the data (see Methodology for more details). Those indicators for which we have indicated an impact evaluation question, we also expect to use in the future impact evaluation.

Table 1. Refined Evaluation Matrix

| (1) Evaluation questions | (2) Impact evaluation (IE) question | (3) Indicators | (4) Reference data tools | (5) Reference Component to Formative and baseline assessment |
| --- | --- | --- | --- | --- |
| Evaluation criteria: Relevance |  |  |  |  |
| 1. How are the NICHE II theory of change and results framework aligned with the UNICEF core sector areas: nutrition, social policy and child protection? | Formative research only | Level of alignment of NICHE II’s objectives with UNICEF’s country program and strategic plan Level of alignment of NICHE II’s objectives with human and child rights Level of proportional representation of female participants (e.g. age, position in the household), their household (e.g. ethnicity, household size, location) and beneficiary child (e.g. gender) Perceived accessibility for women and vulnerable populations by key stakeholders | Document review KIIs with key stakeholders (KII 1, Q3, KII 2, Q9) | 1: Review of NICHE program 2: Refinement of ToC |
| 2. And to what extent do they integrate gender equality and human rights? | Formative research only |  |  |  |
| 3. Have the lessons learned from NICHE I pilot been incorporated into NICHE II’s design? | Formative research only | Extent to which lessons and recommendations of the pilot are incorporated into NICHE’s II inception phase (in the operational manual) | Document review KIIs with key stakeholders (KII 1, Q7,KII 2, Q8; KII 3, Q15) | 1: Review of NICHE program |
| 4. Have the social protection and child protection and nutrition challenges and landscape in counties as well as at the national level been sufficiently taken into account to justify the implementation approach and strategic priorities of NICHE II? | Formative research only | Perceived accessibility of the program according to implementers and other stakeholders Level of integration of key nutrition challenges into NICHE II’s design (as set out in the operational manual) Level of integration of social protection or previous cash transfer programs challenges into the NICHE II’s design | Document review, KIIs with key stakeholders (KII 1, Q9, KII 2, Q7,) | 1: Review of NICHE program |
| - 5. How well is NICHE II aligned to the nutrition, social policy and child protection priorities of the MLSP and MoH, UNICEF global and regional offices, and key donors? More specifically: - How is NICHE aligned with a) the Big 4 Agenda for the Kenyan government b) The Kenyan Nutrition Action Plans c) The National Social Protection Policy* | Both in formative and impact evaluation | Level of alignment of NICHE II’s objectives with UNICEF’s regional and global objectives. Perceived alignment according to key stakeholders Level of alignment of NICHE II’s objectives with a) the Big 4 Agenda for the Kenyan government b) The Kenyan Nutrition Action Plans c) The National Social Protection Policy | Document review, KIIs with key stakeholders (KII 1, Q2, Q10; KII 2, Q4; KII 3, Q4-14; KII 4, Q5) | 1: Review of NICHE program |
| 6. To what extent is the NICHE II design and implementation approach supportive of gender transformation at the beneficiary household level and to what extent does it take into account different roles and responsibilities, the needs of each gender and the support required to overcome gender biases? | Both in formative and impact evaluation. In the impact evaluation we propose to add a separate (sub-)question on: Decision-making and use of cash by beneficiary women. | Perceived accessibility of services by female beneficiaries Level of proportional representation of female participants (e.g. age, position in the household), their household (e.g. ethnicity, household size, location) and beneficiary child (e.g. gender) Extent of documented efforts to ensure equitable participation in NICHE II especially with regards to gender biases Decision-making on the NICHE transfer | Document review, KIIs with key stakeholders (KII 1, Q4, Q5; KII 2, Q11), Baseline household survey (Section 14: Q25, Q28-30) | 1: Review of NICHE program, 2: Refinement of ToC 4. Baseline evaluation |
| 7. In what ways can the NICHE II interventions embrace a rights-based approach at different program stages (design, implementation, impact measurement)? | Both in formative and impact evaluation | Alignment of activities as each program stage with human rights–based approach and normative guidance such as the CRC | Document review, KIIs with key stakeholders (KII 1, Q4, Q5; KII 2, Q11) | 2: Refinement of ToC |
| 8. How is the NICHE program aligned to key sources of normative guidance such as Core Commitments for Children (CCCs) in development and humanitarian situations? | Formative research only | Alignment of project objectives with normative guidance such as the CCC and CRC | Document review | 2: Refinement of ToC |
| 9.To what extent has the allocation and use of NICHE II resources for targeted groups taken into account the need to prioritize women, children and individuals/groups who are marginalized and/or discriminated against? | Both in formative and impact evaluation | Level of proportional representation of female participants (e.g. age, position in the household), their household (e.g. ethnicity, household size, location) and beneficiary child (e.g. gender) Perceived accessibility of services according to KIIs and beneficiaries by women and individuals from marginalized groups | Document review, KIIs with key stakeholders (KII 2, Q11), FGDs (FGD 1, Q25-26) | 2: Refinement of ToC 4: Baseline evaluation |
| 10a. What potential does the program have in bridging the development and humanitarian nexus?* 10b. To what extent can the NICHE program serve as a platform for emergency response and preparedness?* And how does the program fit with the Ending Drought Emergency (EDE) pillar of the National Drought Management Authority?* | Both in formative and impact evaluation | Alignment between the Ending Drought Emergency pillar of the NDMA and the NICHE program design Extent to which the NICHE program design includes flexibility to respond to humanitarian needs | Document review KIIs with key stakeholders on COVID-19 (KII 1, Q18; KII 2, Q24; KII 3, Q21; KII 4, Q15) | 1: Review of NICHE program, |
| Evaluation criteria: Coherence |  |  |  |  |
| 11. What are existing interventions in the areas of nutrition and social and child protection in the NICHE counties and how can NICHE II’s implementation approach leverage these to maximize resources? | Adjusted question for IE: What are existing interventions in the areas of nutrition and social and child protection in the NICHE counties and how is NICHE II’s implementation approach leveraging these to maximize resources? | Number and type of nutrition and social and child protection activities in the selected counties | Document review, KIIs with key stakeholders (KII 2, Q12-16) Baseline household survey (Section 9 and 14) | 1: Review of NICHE |
| 12a. How could the NICHE II’s implementation approach be designed in such a way that it strengthens existing GoK programs in the area of food security, resilience, cash transfer, child protection and nutrition? - 12b. Does the program coordinate effectively with other related program, both government and non-government, both at central and woreda level? | Adjusted question for IE: How is the NICHE II’s implementation approach strengthening the existing GoK programs in the area of food security, resilience, cash transfer, child protection and nutrition? | Extent to which service implementation and objectives are aligned with NICHE II’s program objectives Extent to which M&E systems and NICHE MIS are integrated and aligned Perceptions on coordination between sectors and programs | Document review, KIIs with key stakeholders (KII 2, Q12-16; KII 5, Q3,) | 2: Refinement of ToC; 3: M&E framework |
| 13. To what extent will NICHE II support national processes such as strategic plans, policy development, and development of guidelines as proxies of supporting sustainable efforts?* | Adjusted question for IE: To what extent does NICHE II support or incorporate national processes such as strategic plans, policy development, and development of guidelines as proxies of supporting sustainable efforts? | Extent to which NICHE II aligns with national strategic plans on nutrition and health | Document review, KIIs with key stakeholders (KII 1 KII 4, Q5, p.16; KII 5, Q4) | 1: Review of NICHE 2: Refinement of ToC |
| 14. How has the registration process of beneficiaries been undertaken? To what extent were county government teams involved? What were the challenges in the registration process?* | Only formative | - Level of involvement with registration process by county stakeholders Perceived challenges by stakeholders | KIIs with key stakeholders (KII 1, Q5, p.2; KII 2, Q11) Document review | 1: Review of NICHE |
| 15. Is there a system for addressing complaints and grievances? To what extent is it functional and how can it be enhanced?* | Both in formative and impact evaluation | Availability of platforms to provide feedback | KIIs with key stakeholders (KII 7, Q11; KII 8, Q14) Document review | 1: Review of NICHE |
| 16. How is the national coordination set up arranged? And how is the distribution of roles and responsibilities across the different governmental stakeholders in relation to the NICHE MoU? Are there ways in which this could be enhanced? How is planning between the different sectors undertaken?* | Adjusted question for IE: How is planning between the different sectors undertaken? Are there ways in which this could be enhanced? | Linkages between the various sectors. Perception of these relationships Availability of shared information systems Adequacy of current linkages Plans to establish linkages | KIIs with key stakeholders (KII 2, Q10; KII 5, Q10, Q14) Document review | 1: Review of NICHE |
| Evaluation criteria: Sustainability |  |  |  |  |
| 17. Does the NICHE II have strategies (e.g. systems, capacity, resources) in place to ensure that social and child protection and nutrition capacities will be developed at both the national and county levels during the three years of the NICHE implementation and be sustained without UNICEF’s TA support? | Adjusted questions for IE: What nutrition, child protection, and social protection capacity has the GoK developed at the national and county level to implement and maintain the NICHE program? What are the commitments of the GoK on the sustainable continuation of the NICHE program? | Existence of long-term commitments from key stakeholders (GoK, donors and implementers) to support NICHE II Extent to which long-term strategies are documented | KIIs with key stakeholders (KII 2, Q17-20; KII 3, Q17-19; KII 5) Document review | 1: Review of NICHE |
| 18. To what extent does the implementation approach of NICHE II foster GoK’s self-reliance in the context of devolution? | Adjusted question for IE: Did the NICHE program built capacity and/or transferred responsibilities to the county level? | Extent to which planning and implementation is organized at the county level Extent to which the NICHE MIS will be able to provide ongoing M&E data | KIIs with key stakeholders (KII 2, Q17-20; KII 3, Q17-19) Document review | 1: Review of NICHE 2: Refinement of ToC 3: M&E framework |
| Evaluation criteria: Effectiveness |  |  |  |  |
| 19. What knowledge do beneficiary women have of appropriate feeding practices for pregnant women, lactating women and young children?* | Adjusted question for IE: Did the NICHE program change households’ knowledge and skills on nutrition and hygiene? | Accurate knowledge on (breast)-feeding practices by beneficiaries Understanding of cultural drivers of feeding behaviours, such as food taboos and other beliefs Knowledge about handwashing Knowledge about breastfeeding and IYCF | Baseline household survey (Section 13) FESs (FES 1) FGDs (FGD 1, Q2) | 4: Baseline evaluation |
| 20. What knowledge do beneficiaries currently have about access to cash and knowledge on cash expenditure practices?* | Adjusted question for IE: Do NICHE households have improved access to cash and knowledge on cash expenditure practices? | Knowledge about NICHE Knowledge of other social protection programs | Baseline household survey (Section 6-7, 10) | 4: Baseline evaluation |
| 21. What knowledge do community health workers have of appropriate feeding practices for pregnant women, lactating women and young children?* | Both in formative and impact evaluation | Accurate knowledge on (breast)-feeding practices Type of training received by health care workers Knowledge about child protection activities and social behavior communication change (SBCC) | KIIs with health workers (KII 8, Q8, Q7, Q10, Q11) | 4: Baseline evaluation |
| Evaluation criteria: Impact |  |  |  |  |
| - 22. What are the main nutrition challenges in the specified counties?* | Adjusted question for IE: Does NICHE impact the nutrition status of children and beneficiary women? | Measures on feeding practices (i.e. breastfeeding, meal frequency, dietary diversity) Anthropometrics Food insecurity measures Perceptions of local nutrition challenges | KIIs with health workers (KII 8, Q4) Baseline household survey (Section 5, 8, 10A, 15) FESs (FES 1) FGDs (FGD 1, Q3-4 p. 59) | 4: Baseline evaluation |
| - What are the main expenditure patterns for NICHE beneficiaries?* | Adjusted question for IE: Does the NICHE program impact the cash expenditure of beneficiaries? | Per capita expenditure on food and non-food Reported use of the NICHE transfer Perceived usefulness of the transfer Perceived wealth status | Baseline household survey (Section 6-7; 13B) FGDs (FGD 1, Q5-6) | 4: Baseline evaluation |
| - What hygiene and health seeking practices are beneficiaries currently using?* | Adjusted question for IE: Does NICHE impact the hygiene and health seeking practices of children and beneficiary women? | - Access to a place (with soap and water) for handwashing - Child immunization - Health seeking behavior when sick (e.g. doctor visits) - Antenatal care (e.g. iron intake, number of check ups) | Baseline household survey (Section 3A, 3B 4, 10B) FGDs (FGD 1, Q15, 23-24) KIIs with health workers (KII 8, Q4) | 4: Baseline evaluation |
| What parenting skills and practices are commonly used by beneficiary women to protect children’s well-being? What are the parenting roles by gender?* | Adjusted question for IE: Does NICHE impact the parenting practices of children and beneficiary women? | Knowledge of parenting skills Attitudes towards child discipline Parent-child engagement activities Methods and practices applied to parenting by gender and relationship to child Availability of sources of parenting advice | Baseline household survey (Section 11, 12) FESs (FES 1) FGDs (FGD 1, 20-27) KIIs with key stakeholders(KII 1, Q26) | 4: Baseline evaluation |
| Evaluation criteria: Efficiency |  |  |  |  |
| How is the funding flow for the program arranged and what are the bottlenecks which exist? How can these be resolved?* | Both in formative and impact evaluation | Perceived bottlenecks by funders and national stakeholders Perceived solutions by funders and national stakeholders | KIIs with key stakeholders (KII 3, Q8, Q13, Q18; KII 7) Document review | 1: Review of NICHE |
| Do relationships between the various levels of the program, county-national across the ministries effectively and in line with program goals and results areas?* | Both in formative and impact evaluation | Extent of clearly defined roles and responsibilities. Communication between the various actors Perceived challenges, (i.e. competition on time/resources) | KIIs with key stakeholders (KII 1, Q2; KII 2, Q4, Q5; KII 5, Q15-17) Document review | 1: Review of NICHE |
| a. Are the relevant NICHE activities implemented in the most efficient way compared to alternatives?* - b. What are potentially expected costs to roll out the nutrition counselling? And child protection components? What could be the cost minimization strategies which could be utilized?* | Both in formative and impact evaluation | Perceived efficiency of implementation by key stakeholders Extent that alternative implementation strategies are considered Expected cost to roll out nutrition counselling, child protection components | KII s with key stakeholders (KII 2, Q15, Q16; KII 5, Q19, Q20; KII 6, Q23, Q24) Document review/review of cost markers | 1: Review of NICHE (presented with costing markers in baseline report) |

# Methodology

In this section we outline our evaluation design, including the detailed methods and processes we will follow, how we will collect and analyse data and triangulate using multiple sources. Figure 4 gives an overview of the qualitative and quantitative approaches that will be used to answer the evaluation questions, as discussed above. The combination of the document review, formative KIIs with UNICEF staff and other key stakeholders, a rapid qualitative assessment (e.g., interviews with health care workers, FGDs with beneficiary women, focused ethnographic studies and social mapping), and a quantitative baseline evaluation makes our approach truly mixed methods and formative.

Formative KIIs will influence the development of the M&E framework and the refinement of the qualitative and quantitative instruments. Further, the qualitative and quantitative approaches complement each other. For instance, the rapid qualitative assessment captures beneficiaries’ knowledge of nutrition and feeding practices, while the household survey measures baseline values of food insecurity, number and types of meals. The combined approach is an iterative process in which the findings of one component are used as inputs to other components. The multiple components allow for regular feedback on the performance of NICHE II in terms of its relevance, coherence and sustainability. The methodology described below is organized according to the research activities under each of the four evaluation components. The preliminary results of each evaluation component will be shared in presentations with UNICEF KCO, the ERG and possible other partners to seek feedback and validation of the findings. This continuous stakeholder engagement is an important part of the dissemination strategy (see section on dissemination plan) and is also included as an essential activity in the workplan.

Figure 4. Overview of the Evaluation Approach

## Component 1 & 2: Review of the NICHE II program and Refinement of the Theory of Change

The assessment of Component 1 and 2 of the evaluation, the review of the NICHE II and the refinement of the Theory of Change, consists of three activities; namely (1) document review, (2) formative KIIs and (3) assessment of the ToC. The KIIs are conducted with national and Kitui level stakeholder to collect formative information about the NICHE pilot and NICHE II inception phase. While the assessment of the ToC contributes exclusively to the second evaluation component, both the document review and the formative KIIs contribute to the review of the design and plans for NICHE II (Component 1) and the refinement of the ToC (Component 2).

Document review. AIR is currently conducting a document review of existing evidence and data to gain a high-level contextual understanding of the nutrition and social and child protection situation in Kenya – specifically in the five counties of interest – and how the NICHE II fits into that context. Overall, the document review helps answer key evaluation questions (i.e., on relevance, coherence and sustainability) covering Components 1 and 2 review of the NICHE II program and refinement of the ToC. It also serves as input to the primary quantitative and qualitative data collection. Throughout the process, we follow best practices for document reviews by keeping detailed and well-organised records of searches, the documents collected, the results of screening and review, the rationale for the inclusion or exclusion of documents, and so on. We will outline our findings in the formative evaluation report, together with consultation notes from the key stakeholder interviews.

We are analysing relevant NICHE project documents, existing reports, annual reviews, government policy and planning papers (see Table 2 for a preliminary list of materials). For example, the team is reviewing GoK reports to understand government processes and objectives, and strategies for, for example, nutrition or child protection. Reviewing NICHE II program documents, such as the operational manual, plans for the SBCC strategy and parenting component, and the NICHE pilot documents (i.e. the evaluation reports), helps reveal the current challenges and considerations of successfully implementing a social protection and nutrition program and identify lessons learned from the pilot. Similarly, we are reviewing UNICEF programmatic documents and government policy documents to identify the nutrition and social and child protection priorities and to determine whether NICHE II is aligned with those. Through this review, we investigate the congruity with government goals, government efforts already underway and non-government efforts underway.

Table 2. Document review Sources

| Type of document | Title |  |
| --- | --- | --- |
| Program document | UNICEF (2020). Nutrition Improvements through Cash and Health Education (NICHE) Program First Annual Report |
| Program document | Government of Kenya (2021). Operations Manual - Nutrition Improvements through Cash and Health Education (NICHE) |
| Program document | Ministry of Labour and Social Protection (2020). Enhancing Systems to Improve Harmonization for Sustainable Coordination of Safety Nets in Kenya – Inception Report for the NICHE Management |
| Program document | UNICEF (2020). Technical Assistance for the Expansion and Implementation of Nutrition Improvements Cash and Health Education (NICHE) in Five Counties of Kenya – Inception Report for the Government of Kenya |
| Program document | UNICEF (2018). GoK-UNICEF Kenya Country Program 2018–2022; Nutrition Program Strategy |
| Program document | CHASP (2021). Activity Report – START-UP Registration of Beneficiaries for NICHE Scale-Up in the 5 Counties of Kilifi, Kitui, Marasbit, Turkana and West Pokot. |
| Program document | Kimetrica (2018). Final Report: Evaluation of NICHE in the First 1,000 Days of a Child’s Life in Kitui and Machakos Counties, Kenya |
| Program document | Kimetrica (2016). Researching the Outcome and Impact of the Nutritional Improvements through Cash and Health Education (NICHE) Program on the First 1,000 Days of Life in Kitui County – Kenya – Inception Report |
| Program document | ‘NICHE SBCC Strategy’ (presentation, 2021) |
| Program document | UNICEF (2021). ‘NICHE Progress Update – 9th – March 2021’ (presentation) |
| Program document | UNICEF (2021). ‘Child Protection Initiative – Nutrition Improvements through Cash and Health Education (NICHE) in Kilifi County’ (presentation) |
| Background document | UNICEF (2018). Situation Analysis of Children and Women in Kenya |
| Background document | KNBS & UNICEF (2017). Child Poverty in Kenya, a multidimensional approach. |
| Background document | Ministry of Health (2016). Baby Friendly Community Initiative – Implementation Guidelines |
| Background document | ICS. ‘Monitoring Parenting Programs’ (presentation) |
| Background document | Other documents – TBD |

In addition to looking at the program documentation, AIR is collecting and analysing an array of peer-reviewed research. The review of the peer-reviewed literature will be used to refine the pathways in the ToC. We will develop search strings designed to return studies that include thematic, population, technical, programmatic and geographic terms relevant to social protection interventions in low-resource contexts, with a focus on those in Kenya. For example, we will focus on lessons learned from other cash transfer programs designed for pregnant women and mothers of young children (see, e.g., de Groot et al., 2020) and other nutrition and health education interventions (e.g., the First 1,000 Most Critical Days Program in Zambia). The literature review will substantiate the logical framework and generate insights related to integrated social protection in Kenya.

Findings from government and stakeholder documents as well as studies will be an essential part of the formative research components and inform further refinement of the ToC, results framework and data collection tools, if necessary. The document review will answer KEQs on relevance, coherence, sustainability and efficiency, and focuses in particular on KEQ 1 to 18 and KEQ 26-28.

Formative Key Informant Interviews. A qualitative approach, such as using formative KII, is useful as it allows researchers to investigate the how of program implementation because of its exploratory and discursive nature. Our approach will help us illuminate strengths and challenges associated with implementing NICHE II as well as understand the experiences of key stakeholders with the NICHE pilot. In the following paragraphs, we discuss the key informant interviews during Component 1 and the associated sampling frame.

During the formative phase and Component 1, we will conduct key stakeholder interviews at the national and county level with a specific focus on Kitui County, which will contribute to the review of the proposed NICHE II program (Component 1) and the refinement of program design and ToC (Component 2). The evaluation team will conduct a total of 36 formative KIIs. The key informants will include people who possess expert knowledge about existing nutrition and social and child protection strategies and about the NICHE pilot and NICHE II programs. In general, one-on-one interviews with key informants are an ideal forum for engaging with people who possess expert knowledge about a program or a related topic. For example, a key informant might provide valuable insights from a service provider’s perspective about how a program interacts with other services. At the national level, we will conduct KIIs with UNICEF staff in the nutrition and social and child protection sectors; key ministry officials from the MoH, the DCS in the MLSP, the MD&ASAL, NDMA and Ministry of Agriculture; and key partners such as funders and other UN agencies. At the county level we will interview county representatives of the Ministry of Health and Sanitation, the county nutrition coordinator and the coordinator form DCS. KIIs at the national and county level will identify and distil the key lessons learned during the NICHE pilot and the NICHE II inception phase to help refine the NICHE II program design and ToC. Further, these KIIs will explore issues of program relevance, coherence and sustainability as well as the extent to which equity, gender equality and human rights have been considered in the program design and implementation. Findings from these KIIs will be triangulated with findings from the document review and incorporated into the formative evaluation report.

National-level KIIs with UNICEF staff, GoK officials and partners will examine the alignment of the NICHE II program with relevant policy priorities and guidance (KEQs 1, 5, 8 and 13 in Table 1) as well as the extent to which the principles of gender equality and progressive universalism were incorporated into the program (KEQs 1, 2, 6, 7 and 9). These interviews will also help explain the program’s relevance to the Kenyan national context and its strategies for sustainability (KEQs 13, 17–18). KIIs with relevant government officials and implementing partners in Kitui County (location of the NICHE pilot) will deepen our analysis of the lessons learned from the NICHE pilot (KEQ 3) and provide information on existing programming in NICHE counties and potential opportunities for leveraging or strengthening existing GoK programs in these areas (KEQs 11–12). Although there is an existing evaluation of the NICHE pilot in Kitui County, key informants such as county-level officials and implementing partners were not included in the study. These informants may have important insights when it comes to refining the program design and implementation and developing strategies to ensure sustainability for NICHE II (see Table 3).

Table 3. Proposed KIIs at National Level and in Kitui County

| Respondent type | Respondent detail | KIIs | Total |  |
| --- | --- | --- | --- | --- |
| National level |  |  |  |  |
| UNICEF Kenya | Nutrition | 2 | 6 KIIs |  |
|  | Social policy | 2 |  |  |
|  | Child protection | 2 |  |  |
| Government of Kenya (National level) | Ministry of Health - Division Head, Division of Nutrition - NICHE program focal person, Division of Nutrition - Community Health Strategy | 3 | 7 KIIs |  |
|  | Ministry of Labour and Social Protection – Department of Children Services | 2 |  |  |
|  | Ministry of Devolution of Arid and Semi-Arid Lands | 1 |  |  |
|  | National Drought Management Authority | 1 |  |  |
| Partners | Funders - Foreign Commonwealth & Development Office - World Bank | 2 | 3 KIIs |  |
|  | Other UN agencies - World Food Organization | 1 |  |  |
| County level - All Counties |  |  |  |  |
| Government of Kenya | County Ministry of Health and Sanitation | 5 |  | 15 KIIs |
|  | County Nutrition Coordinator Officer | 5 |  |  |
|  | Ministry of Labour and Social Protection, Coordinator from Department of Children Services | 5 |  |  |
| County level – Kitui only |  |  |  |  |
| Government of Kenya | Ministry of Agriculture | 1 | 5 KIIs |  |
|  | National Drought Management Authority | 1 |  |  |
| Implementing partner | World Vision Concern Worldwide Action Against Hunger | 3 |  |  |
| Total number of KIIs at national level and county level |  |  |  | 36 KIIs |

Our national expert consultant Emily Mbelenga will verify the instruments for contextual accuracy and appropriateness, and she will help conduct key stakeholder interviews in the formative phase.

Assessment of the ToC. As last part of the formative evaluation, AIR will conduct an evaluability assessment to understand how well the ToC captures key outcomes and how well the existing infrastructure is suited to measure those outcomes. The goal of this assessment is to better understand whether the program design is accurately reflected in the logical framework, and whether the framework is comprehensive and clear about how progress toward program objectives is expected and can be assessed. Comprehensive evaluability assessments examine the plausibility, utility and feasibility of impact evaluation (Peersman et al., 2015). In this part of the evaluation, we will concentrate on its plausibility and utility. We will focus on questions such as: Is it plausible to expect impact, and how are we able to observe this? And how would the impact evaluation be used? The feasibility of measuring impact will be addressed in the development of the M&E framework and the primary data collection components of the baseline evaluation, which are further described later.

During our assessment of the ToC, we will evaluate the validity and comprehensiveness of the logical framework by using the results from the document review. The program manual, reports and updates will be used to examine whether the currently stated activities in the ToC are still accurate. We will also identify which of the linkages in the framework are most critical to observe whether the intervention objectives will be reached. Lessons learned from the NICHE pilot and other comparable projects will be used to strengthen the assumptions, risk factors and mitigating factors. Background documentation on other social protection and nutrition programs will also be used to refine risk and mitigation factors. The information from peer-reviewed studies will be used to examine the proposed pathways and the expected timing of results.

We will compare the indicators in the ToC with the indicators in the results framework to ensure that the indicators in the ToC are measurable, consistent and clearly defined. It is crucial that a ToC covers all program activities, the intermediate changes caused by the program and the ultimate impacts the program is intended to have. The first step toward ensuring that stakeholders will be able to determine whether the program achieved its goals is to define the metrics against which the program should be evaluated.

To summarize, the assessment of the ToC will take a holistic view of the program and key outcomes to identify targeted approaches to improving the present evaluation. The goal of this part of the evaluation will be to understand the high-level functioning of an integrated nutrition and social and child protection program and how it operates in the Kenyan context. Further, we will ensure that there exists a viable strategy for assessing the program on an ongoing basis.

## Component 3: Development of the M&E framework

As part of component 3, the development of the M&E framework, we describe our approach to the refinement of the existing M&E framework and plan through a thorough assessment of the results framework and a consultative process, and the collection of cost markers. The objective of this part of the evaluation is to develop a comprehensive and sustainable framework, which can be used for continuous monitoring of the NICHE II.

M&E framework and plan. The M&E framework builds directly off the preliminary results framework, incorporating the changes proposed in the ToC and suggestions made by key informants during the first round of interviews. The preliminary results framework is prepared by UNICEF KCO during the NICHE II inception phase and the outcome of internal consultations between staff from various sections and field officers.

The objective of the development of the M&E framework (component 3) is to refine the existing framework and will consist of two components – assessment of the existing framework and existing M&E systems, and a consultative process to inquire whether further changes are needed. First, we will systematically assess the existing results framework and monitoring strategy. The NICHE Management Information System (MIS) will form a critical component of the M&E. The MIS will support program management and planning, and it will promote financial and social accountability by collecting data on registration and program exit, targeting, payments, grievances and case management. The NICHE MIS builds on existing M&E systems, such as the Monitoring Evaluation, Accountability and Learning (MEAL) processes in the social protection sector (housed at the MLSP), the MIS of the nutrition sector (housed at the MoH) and the MIS of the child protection sector (at the MLSP for Kilifi). The consolidation of the various existing systems within the NICHE MIS are critical to the well-functioning of the system, and therefore to reliable information to inform future program decisions. The consolidated system will collect and analyse data in a reliable and recurring manner that allows for periodic analysis of implementation progress and changes in output variables. We will assess the proposed indicators that the NICHE MIS or other existing MIS are going to collect to understand how they contribute to the results framework and overall evaluability of NICHE II. We will also examine whether data collection tools for the specific indicators are developed and whether there is a clear plan for implementation to understand the feasibility of (on-time) future evaluation. Lastly, we assess the integration of the various systems, especially with regards to expected frequency and flow of data collection. In this component of the M&E framework assessment, we will also identify indicators in the results framework that are currently not included in the MIS planning. We will assess the proposed tools and mode of data collection (e.g., ad hoc data collection, program reports, evaluation) and examine whether they contribute to a reliable and sustainable monitoring system.

The second component of the M&E framework development is a consultative process with the MIS group and other key stakeholders who have used the existing NICHE M&E framework. As we understood from our internal meeting on the M&E framework during the inception phase, there is limited documentation on the experiences with M&E during the NICHE pilot and implementation of NICHE II so far. With the consultations we will seek to understand the lessons learned from the existing framework and determine whether these are adequately incorporated in the new plans. The consultative process will help verify the findings from the existing framework assessment and will be used as an input to create a comprehensive narrative for the M&E plan.

Collecting cost markers. AIR will work with UNICEF and the implementing partners to gather information on resources used for the intervention to create an exhaustive list of resources and associated costs. We will divide these costs by type (staffing, materials, etc.) and occurrence frequency (recurring or upfront). Using this information, AIR will create a cost database that contains basic descriptive information and information that allows analysis of the patterns of variation of resources – for example, by funder, geography or scale. The cost markers available at the current phase of the NICHE II program implementation will provide a benchmark for further analysis. In this evaluation, the focus will be on constructing a cost database, which can be used in more depth in follow-up studies. However, in the baseline assessment report we will use this information to give initial insights into the use and distribution of resources between counties. Depending on the comprehensiveness of the data, the costs markers can also be used to estimate the (planned) costs of the intervention for the average beneficiary.

As for the types of costs collected, the focus will be on the costs of upgrading a traditional cash transfer program to an integrated social protection program that includes nutrition and child protection counselling. Because we are fundamentally studying the integrated nature of social protection programs, we will focus on costs that UNICEF and its funding partners incur above those they would have incurred without incorporating the additional services.

## Component 4: Baseline evaluation

The baseline evaluation consists of qualitative and quantitative approaches, such that together the results provide with a comprehensive overview of individual and household level well-being, nutrition status and knowledge, and food and parenting practices at the point of the NICHE II implementation. This baseline can be used to identify current needs and challenges of the beneficiary population and will be essential for future impact evaluations.

Qualitative Approach in Component 4

We propose a qualitative approach that includes a highly participatory Rapid Qualitative Assessment (RQA), in addition to the formative key stakeholder interviews proposed in Component 1. The RQA includes KIIs with health service providers and local government officials, focus group discussions (FGDs) with beneficiaries, a social mapping exercise with the FGD participant and focused ethnographic studies (FES). These will take place in two additional counties where NICHE II is being implemented to generate qualitative data at the county and village levels.

RQA is a qualitative participatory method and is suited for formative evaluations for the following reasons:

- Implementation of program activities requires detailed descriptions of what happens and how people respond to the program.

People’s experiences typically vary in important ways, and hence it is critical to capture diverse respondents’ experiences and perceptions of their experiences and, more importantly, for these experiences to be captured in their own words.

The process of any program implementation is fluid and dynamic, so it cannot be fairly summarized on a single rating scale at one point in time (Patton, 2012, p. 195).

Additionally, these methods enable researchers to explore formal activities and anticipated outcomes as well as informal patterns and unanticipated interactions (Patton, 2012). Qualitative data give researchers the flexibility to explore unforeseen areas of interest to understand where elements of program implementation may have affected program effectiveness. Rapid assessment approaches such as the RQA are intensive team-based qualitative inquiries using triangulation and iterative data analysis to develop a preliminary understanding of a situation from an insider’s perspective (Beebe, 2001). The purpose of the RQA is to quickly obtain in-depth information about the context of program implementation areas from a variety of actors, including county-level government officials, implementers and beneficiaries; this information can then be used to inform the design and M&E framework for the program. The RQA will include three qualitative methods: KIIs with county-level government officials and village-level health or community workers in selected villages and highly participatory FGDs and FESs with program beneficiaries. The RQA will focus on government officials’ and implementers’ observations regarding the need for the program as well as beneficiaries’ experiences with nutrition challenges, health behaviours and parenting.

Throughout the qualitative approach during the baseline phase, we will employ participatory methods such as social mapping and card sorting to ensure that the collection of data through FGDs and FESs is beneficiary driven, engaging and sensitive to the context. We will use these qualitative methods to examine the relevance, coherence and sustainability of the NICHE II program.

The RQA will contribute to the quantitative baseline analysis by providing in-depth information about beneficiaries’ experiences with nutrition challenges, health behaviours and parenting. These insights can help explain the cultural drivers and reasons behind observed or reported feeding, health and parenting practices from the quantitative data (proposed KEQs 19-25 in Table 1). In addition, RQA data can be compared with subsequent qualitative data collection to shed light on how beneficiaries’ experiences may have changed during the program as well as identify potential challenges and barriers to program uptake. Findings from the RQA will be triangulated with findings from the quantitative baseline evaluation and will be incorporated into the baseline assessment report.

RQA sampling. We selected two out of the five program counties for the RQA. Because Kitui County beneficiaries were already interviewed for the pilot study, we suggest excluding this county from the RQA. AIR suggests selecting Kilifi as one of the counties, as it is the only program area to have the child protection component. The second county for the RQA is Turkana. Turkana is selected as one of the two case studies, since it represents one of the more remote and arid areas with main pastoral communities. The final selection of the two counties was the result of dialogue with UNICEF colleagues across the various sectors and key government stakeholders. In each selected county, we will select four villages for qualitative data collection (total of eight villages). Potential selection criteria for villages include proximity to urban areas, levels of existing nutrition and social and child protection programming and functioning of community platforms such as the BFCI.

Key informant interviews. We will conduct a total of 12 KIIs as part of the RQA at the county and village levels. In each county, we will conduct two KIIs with government officials such as the county ministry of health and sanitation and a county-level representative of the Department of Children Services at the Ministry of Labour and Social Protection (total of four KIIs). In addition, in each sub-county we will conduct two KIIs with Community Health Volunteers (CHVs) who are trained to conduct the nutrition counselling and home visits as part of the NICHE II program (total of 16 KIIs). KIIs with county-level government officials will help us understand the nutrition and social and child protection landscape in program areas as well as existing programming and services and perceptions of local needs (KEQ 19, 22, 24). In addition, KIIs with CHVs will enable us to establish a baseline of service providers’ knowledge and skills in nutrition and hygiene (KEQ 21).

Focus group discussions. We propose a total of eight FGDs with beneficiaries of NICHE II in selected villages as part of the RQA. Beneficiary FGDs will include pregnant women and mothers of children under 2 years old. Focus group research involves guiding a diverse group of participants through a discussion on a particular topic. The method is well suited to obtaining diverse perspectives on issues and offers the possibility of observing intergroup dynamics and norms during the discussion (Morgan, 1996). Generally, FGDs include anywhere from five to eight participants, and participants are guided through various discussion topics by a trained facilitator. Empirical research shows that three to six focus groups are sufficient to reveal 90 per cent of the relevant themes (Guest et al., 2016). The focus group format will enable us to understand the experiences of many beneficiaries in a short period of time, as the beneficiaries will be in a group environment with their peers and their interactions can be observed. Beneficiary FGDs will provide information about beneficiaries’ experiences with nutrition challenges, health behaviours and parenting (proposed KEQs 22-25), which will provide an in-depth complement to quantitative baseline data on caregivers’ knowledge of and skills in nutrition, hygiene and parenting practices as well as identify potential barriers to program uptake.

Social mapping. As part of the RQA, we propose conducting an additional participatory social mapping exercise with beneficiaries in four selected FGDs (two per county). Social mapping (Mikkelsen, 2005, pp. 107–109) is a participatory tool designed to involve community members – the subjects of the research – in the research process, not simply as respondents but as active agents and stakeholders. We will use this approach to collect data on local understandings of poverty, well-being, vulnerability, access to resources and other programs under implementation. Social mapping will help contextualise FGD findings on nutrition, health behaviours and parenting within the broader experiences of poverty and vulnerability in program regions, providing further insight into beneficiaries’ resource constraints and potential barriers to program uptake.

Focused ethnographic studies. In addition, we propose conducting a total of 16 FESs in selected villages (in each village, we will conduct one FES with a pregnant woman and one with a mother of children under 2). The FES approach was developed by Gretel Pelto and colleagues as a tool for the World Health Organization to study acute respiratory illness in children. This model has been adapted and applied in various other research areas, such as formative research and process evaluations of infant and young child feeding interventions in Haiti (Menon et al., 2005). FESs involve interviews that are shorter and more tightly defined than the wide-ranging and open approaches typical of more traditional ethnographic research. In the context of this RQA, FESs will include structured interviews on the topics of appropriate diets for infants, children, pregnant women and young mothers; access to food; social and cultural drivers of child-feeding practices; the dietary practices and behaviours of pregnant women; and parenting practices (proposed KEQs 22, 25). Further, we will incorporate a card-sorting exercise to learn about these topics in a more participatory manner. Card sorting involves presenting participants with a series of topics or items and asking them to group these items into categories. We will present participants with images of locally available foods and ask them to build nutritious meals for young children and pregnant women to learn about their perceptions of nutritious foods and meals.

FESs and card-sorting exercises will contribute to the baseline analysis by providing context for the cultural drivers of nutrition behaviour and parenting practices in program areas as well as identifying potential constraints and barriers to uptake of the program. While group interviews such as FGDs will provide information on general nutrition, health and parenting practices among beneficiaries, the FES individual interviews will allow us to explore more sensitive topics such as household decision-making, gender roles, resource constraints and child discipline practices.

AIR will lead the development of qualitative instruments and enumerator training in collaboration with Dalberg. Dalberg will then lead the qualitative data collection training under supervision by and constant communication with AIR. During the baseline phase, Dalberg will collect data at the county and village levels under supervision from both AIR and our national expert consultant, Emily Mbelenga.

See Table 4 for a complete list of sampling and qualitative methods for the RQA.

Table 4. RQA Methods and Sampling

| Sample sites |  |  |  |  |  | Government officials, frontline workers |  | Beneficiaries |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | KIIs |  | FGDs |  | FESs |  |  |
| County |  | Village | Urban |  | Rural | Sub county Govt officials | Community Health Volunteers (CHVs) | Pregnant women or mothers of children under 2 | Social mapping component | Pregnant women | Mothers of children under 2 |  |
| Kilifi | Ganze | Village 1 |  | X |  | 2 | 2 | 1 | 2 | 1 | 1 | 20 |
|  |  | Village 2 |  |  | X |  |  | 1 |  | 1 | 1 |  |
|  | Kaloleni | Village 3 |  | X |  |  | 2 | 1 |  | 1 | 1 |  |
|  |  | Village 4 |  |  | X |  |  | 1 |  | 1 | 1 |  |
| Turkana | Turkana Central | Village 1 |  | X |  | 2 | 2 | 1 | 2 | 1 | 1 | 20 |
|  |  | Village 2 |  |  | X |  |  | 1 |  | 1 | 1 |  |
|  | Turkana South | Village 3 |  | X |  |  | 2 | 1 |  | 1 | 1 |  |
|  |  | Village 4 |  |  | X |  |  | 1 |  | 1 | 1 |  |
|  | Totals: |  |  |  |  | 4 | 8 | 8 | 4 | 8 | 8 | 40 |

Equitable and effective sampling approach. AIR recognises that following best practices for human subjects research with vulnerable populations is essential, especially because a significant portion of our sample consists of vulnerable people, including mothers with young food-insecure children. (See Annex B for more detailed information on research ethics and strategies AIR will use to adhere to ethical guidelines and ensure equitable participation.) We will use purposive sampling to identify pregnant women and mothers with children under 2 years of age and other vulnerable beneficiaries for this evaluation to better understand their needs and the extent to which the NICHE II program is able to consider them in program design and implementation. Further, to ensure there is equitable input on the needs, perceptions and experiences that will inform program relevance and implementation, we will also ensure that recruitment of respondents will be gender balanced, such as collecting data from an equal number of male and female health and community health workers as well as county-level representatives from Ministries. To sample pregnant women, lactating women and mothers with children under 2 years of age, we will adopt a multistage approach to ensure that we identify, recruit and sample women in an ethical, appropriate and sensitive manner. AIR and Dalberg staff members will ensure that enumerators are trained to adhere to local cultural norms and customs when engaging with communities. This approach will ensure that our research does not harm the participants or to the surrounding community. AIR and all enumerators will also adopt research strategies that have proven effective for working with vulnerable populations (see Annex B), and we will also ensure that there is a gender-sensitive, rights-based research approach training for enumerators (see Annex B for more detailed information). For general ethical principles and our process of obtaining ethical clearance for the evaluation is described below in the ‘Ethical principles’ sub-section.

Enumerator training. All interviews, FGDs and FESs will be conducted by enumerators recruited and overseen by our partner, Dalberg. Enumerators will have experience conducting interviews and facilitating FGDs and FESs on similar types of projects. AIR will conduct training to inform enumerators about the evaluation, background information on the NICHE II, the key objectives and the research questions; will introduce the protocols; and will emphasize data security, consent and confidentiality. Further, Dalberg enumerators will be carefully trained by AIR and will have procedures in place for adverse events when speaking about sensitive topics and on how to avoid and mitigate personal judgements. Training for enumerators will include information on how to discuss and share information about services to participants, if or when it is needed, and what resources are available in the community, such as nutrition counselling for women and child protection counselling for caregivers. Given the sensitive nature of some topic areas, enumerator training will also include information about how to take care of one’s own mental health and how to opt out of an interview or a focus group should the enumerator not feel comfortable at any time. AIR will work with Dalberg to ensure that enumerators are aware of point contacts to refer to from both organizations when they are in the field.

Data collection. When collecting data, enumerators will be trained to be extremely cautious when handling sensitive information. Study materials will be designed to minimize the risk of harm or trauma to participants. We will receive informed consent from all participants regarding their participation in discussions with us. As well, all participants will be made aware that they may opt to not answer a question or stop participating should they not feel comfortable at any time, without having to explain why. Female enumerators will facilitate female FGDs with children, female caregivers and female beneficiaries.

Recording, transcription and translation. All interviews will be digitally recorded and transcribed. Before recording, all participants will be asked to give their consent to be audio-recorded in a language that they understand, worded at an appropriate level for their educational background. Interviews and focus group discussions conducted in local languages will be transcribed in English prior to analysis of all documents in NVivo. The evaluation team will carefully review all transcripts to ensure the completeness and clarity of the English translations. If needed, the research team will consult the audio recordings to verify content and the accuracy of the translations in the transcripts.

Analysis. The research team will code and analyse all data from KIIs, FGDs and FESs using the NVivo qualitative software program. The evaluation team will create a preliminary coding structure based on the research questions, interview and focus group protocols, and memos of ideas that emerge during data collection. This coding outline will be used to organize and subsequently analyse the information gathered through KIIs, FGDs and FESs. The outline will be a living document and may be modified as new themes and findings emerge during data analysis. A list of definitions for the codes will accompany the outline so that coders categorize data using the same standards. After inputting the raw data into NVivo, coders will select a sample of interviews to double code to ensure interrater reliability. The team will then input the data into the thematic structure. During this process of data reduction, researchers will characterize the prevalence of responses, examine differences among groups and identify key findings and themes related to the research questions.

Quantitative Approach in Component 4

The quantitative methodology consists of a quasi-experimental design which compares household registered for the NICHE II program in the five counties that are currently selected with households that are similar but reside just outside the registration areas. We will conduct a household survey among the NICHE treatment group and comparison group to establish baseline values of key nutrition, parenting and other well-being outcomes.

Quantitative household survey methodology. To perform the baseline analysis (Component 4), we will exploit primary quantitative data to understand key household and child outcomes at the beginning of the program. These results will provide baseline markers for follow-up analyses of the program, such as at the end of the program and at periodic points throughout. The quantitative baseline evaluation seeks to contribute to answering KEQs 9 and 19 to 25 under the effectiveness and impact evaluation criteria. Within the quantitative survey, we will include questions on topics such as feeding practices, nutrition and food security challenges, health-seeking behaviour and preventative ante-natal care, education, early childhood development and child development. The topics are guided by the indicators in the results framework and will be further refined if needed after the formative research phase. The indicators for each of these topics will provide us with baseline values that will allow us to understand the effectiveness of the program at the end or during program implementation. In addition, we will also include the measurement of height and weight for the child between 0 and 24 months (focused on the NICHE index child). Even though the results framework focuses on nutrition process rather than outcome indicators, we will include anthropometric measures to allow for a separate analysis of these variables over time. See Annex D for a draft of the household survey.

We will conduct a baseline survey using a quasi-experimental design called geographical regression discontinuity design (RDD) to identify NICHE treatment households and comparison households with one of the NSNP cash transfers in (near) neighbouring counties that are not yet selected for NICHE II. We selected a quasi-experimental design, as opposed to an experimental design based on randomised enrolment in the NICHE program, to not disrupt the current registration process and plans for implementation. Currently NICHE II beneficiaries are registered in Kilifi (Ganze and Kaloleni), Kitui (Kitui South and Mwingi North), Marsabit (Moyale and Saku), Turkana (Turkana Central and Turkana South) and West Pokot (Kacheliba and Kapenguria). We selected comparison sub-counties outside these registration areas through a consultative process with local UNICEF colleagues and our data collection partner and with inputs from the ERG. See Table 6 for the full list of NICHE treatment sub-counties with selected comparison areas. Using geographic RDD as identification method rests on the assumption that households directly on each side of the border are on average similar in terms of e.g. types of livelihood, environment, access to markets and social services, wealth. We therefore expect that these households would respond similarly to the NICHE cash top-up as the treatment households, if the top-up was decided by chance rather than registration.

We will not select any of the remaining sub-counties in the five NICHE counties, because there are plans to continue with on-demand registration in those areas as soon as capacity allows. Similarly, potentially eligible households in the selected sub-counties that are not yet registered are not included either because of the risk of spillover effects and because they might become registered over the course of the impact evaluation.

Table 5. NICHE Treatment and Assigned Comparison Areas

| NICHE treatment areas |  | Comparison areas |  |
| --- | --- | --- | --- |
| County | Sub-county | County | Sub-counties |
| Kilifi | Ganze | Taita Taveta | Voi |
|  | Kaloleni | Kwale | Kinango |
| Kitui | Kitui South | Makueni | Kibwezi West or East |
|  | Mwingi North | Tharaka Nithi | Tharaka |
| Marsabit | Moyale | Isiolo county | Isiolo North |
|  | Saku | Isiolo county | Isiolo North |
| Turkana | Turkana Central | Samburu | Samburu North |
|  | Turkana South | Samburu | Samburu North |
| West Pokot | Kacheliba | Trans Nzoia | Endebess |
|  | Kapenguria | Elgeyo Marakwet | Marakwet East |

Our methodology is based on a longitudinal cohort design. The cohort consists of households that are part of one of the NSNP cash transfer programs and had a pregnant woman or a child under 15 months at the time of registration. For future evaluation rounds, we recommend using a cohort with the same characteristics. Using a cohort rather than a panel in which the same individual is followed over time has, in this case, three major advantages. First, cohort studies are less affected by the timing of the impact evaluation and are more flexible in case the follow-up evaluation needs to be postponed. For example, with a panel sample, the entire sample of currently registered households will have stopped receiving the NICHE II transfer after 24 months (depending on the child’s age at registration the household will have ‘aged out’ of the NICHE program for periods between 0 and 15 months). Determining the impact of the program will be more difficult after households stop receiving the transfer. Second, using a cohort rather than a panel reduces concerns regarding sample attrition due to households moving to other areas. Third, for this evaluation we will use some age-specific indicators on early childhood development, nutrition and feeding practices. Using the same cohort allows us to compare the same indicators rather than risking measurement errors because of necessary age adjustments. For instance, complementary feeding guidelines differ by age, and indicators would therefore differ for an individual over time. Panel data studies are commonly perceived as more rigorous because they reduce unobserved bias by using the same sample. However, given that this program is still at the formative stage and some uncertainty exists about the timing of the implementation and follow-up evaluation, the three advantages of the cohort design outweigh the possible added precision from a panel study.

We describe our sampling approach, as well as the data collection process and estimation strategy, in more detail in the following section.

Sampling. We will use a sample of households that is representative of the population benefiting from NICHE II and compare these with households that are fulfilling the NICHE eligibility criteria but are in areas where the registration has not taken place yet. For the treatment group, we will use the NICHE registration records to identify households; for the comparison group, we will select households with comparable characteristics that are registered in one of the four cash transfer programs that are currently part of the NSNP. Within each sub-county we select villages based on their proximity to the sub-county border. Within the selected villages, we will randomly select households for the sample. With regards to the comparison group, our data collection partner will further verify that the selected household has a pregnant woman or a child under the age of 24 months in the household, similar as the NICHE households. Using the existing registration of cash transfer beneficiaries will also facilitate contacting households and reduce logistical challenges.

To implement this strategy, we propose surveying 500 households in across the five treatment counties (with about 50 households per sub-county) and 500 households in the comparison areas, with a total sample of 1,000 households. We based our power calculations on results from the NICHE pilot evaluation. We used the results on exclusive breastfeeding (72 per cent of NICHE beneficiaries and 59 per cent of the comparison group) and minimum acceptable diet (64 per cent for the treatment group; 20 per cent for comparison group) (Kimetrica, 2018). Assuming the generally accepted standard of 80 per cent power, our power calculations suggest a minimum sample size of 770 households in order to observe results of the same magnitude as the 13 percentage points observed for exclusive breastfeeding. When we lower the expected impact to 10 percentage points the minimum sample size necessary to observe these changes is 1,132 respondents. Using the impact results from minimum acceptable diet, we would need a minimum of only 206 respondents. For this evaluation we propose a sample of 1,000 households to be able to capture smaller impacts.	 

Following the geographical RDD argumentation, the treatment and comparison areas are similar except for the NICHE registration. For that reason, we consider the treatment sub-county and the bordering comparison sub-county as one area. We do not use county clusters, but we will compare households from each border areas in the statistical analysis (i.e., formally, we will control for the fixed effects of each border included in the analysis).

We will first identify 500 households for respectively the treatment and comparison areas to contact and then identify another 50 (10 percent) households to serve as reserves in case we are unable to locate some of the first 1,000 households. This careful process of selecting households will provide us with the best chance of having an evaluation sample that reflects the characteristics of the broader population of households that will benefit from NICHE II.

Data collection. In each of the 10 treatment-comparison groups, we will collect household- and child-level data from 100 respondents. Dalberg will lead all data collection efforts. AIR will be engaged to oversee the process and ensure the team collects the best data possible. The supervisory team will assist in training enumerators on survey questions, sampling strategies and research ethics. AIR will make certain that all enumerators participating in fieldwork are prepared to adhere to all research protocols and processes, thus ensuring accurate and ethical data collection. Our ethical guidelines for data collection are described in more detail in Annex B. Prior to starting data collection we will also request ethical clearance, this process is described below in the section on ‘Ethical principles’.

We propose to use in-person surveys with pregnant women and mothers of children under 
24 months old who benefit from NSNP transfers. Specific questions that will be included in these surveys are based on the ToC and the results framework. These questions will allow us to understand the characteristics and situation of beneficiaries of the program. We will ask about health behaviours, feeding practices and parenting in all counties. To ensure we can examine differential situations by gender of the child, we will collect disaggregated survey data by gender and consider gender implications when designing interview protocols.

Data collection will take place by electronic means to ensure the timeliness and accuracy of the data. AIR, in collaboration with the M&E nutrition consultant, will refine the proposed survey in Annex D based on the findings of the formative research. AIR will provide the survey to Dalberg, which will then convert the survey document into a carefully coded electronic format using Survey CTO. Electronic data collection provides two main benefits. First, electronic survey forms can build in quality control checks to ensure that all responses are correct (e.g., by preventing impossible answers or skipped responses). Second, the data are available in near real time so that our team will be able to check their quality on an ongoing basis and provide worthwhile feedback to enumerators. Dalberg will recruit experienced enumerators who are already familiar with electronic data collection techniques, but AIR will incorporate trainings on electronic data collection into the preparation for the fieldwork.

Recognizing that the COVID-19 pandemic may pose a challenge to data collection because in-person contact can increase risks of infection, AIR will comply with Centers for Disease Control and Prevention and local government guidelines to protect the health and safety of all individuals involved in the project. We will adjust data collection activities if needed – for example, by using telephone-based surveys to limit in-person interactions. Please see the section Mitigating Risks Related to COVID-19 for more details on AIR’s strategy for ensuring the safety of all informants, particularly children and pregnant women, during the COVID-19 pandemic, as well as its strategies for reaching a broad population even when using telephone-based surveys. Regardless of the collection method, AIR will protect the confidentiality and privacy of all data collected and will adhere to strict procedures for data handling and security. All transmitted files will be digitalized, encrypted, password protected and accessible only to approved members of the research team.

Regardless of the method used to conduct the surveys, we will work closely with Dalberg’s team and Ms. Emily Mbelenga to design survey protocols that are gender, culture and context appropriate. Gender influences how people use cash transfers and interact with their children. For instance, women are more likely to be in charge of feeding their children, and feeding practices may differ between boys and girls. There are also gendered power dynamics within families or communities that may prevent mothers or girls from participating in the evaluation, feeling comfortable answering our survey questions or providing honest answers. To adequately survey a broad population in a non-harmful manner, we will make certain that the gender of the enumerator matches that of the respondent, and enumerators will strive to ensure that respondents are in a safe space when responding to the survey.

Data analysis. AIR will provide a descriptive analysis at the beginning of the program that answers the evaluation questions on relevance and coherence proposed in Table 2. We will analyse data and provide summary statistics on key outcomes. These summary statistics will present the average value of important measures of well-being as well as the distributions of these outcomes when appropriate. This type of analysis will help us understand what outcome levels are typical for the evaluation population and how widely those levels vary. It will include frequency counts, proportions and confidence intervals at the county and sub-county levels, where possible. We will further disaggregate the data by sex, age, ethnicity and disability to determine if there are any discrepancies in their situation.

The descriptive analysis will describe beneficiary well-being across a wide range of household outcomes related to nutrition and health behaviours. This broad analysis will be important because a social protection program can address many dimensions of well-being. For example, we will design survey instruments that cover feeding practices, knowledge about feeding, food security, immunization uptake, access to services, health and other issues.

We will incorporate gender sensitivity into our evaluation by conducting a gender-focused data analysis. In other words, data will be disaggregated by gender and any other important identifying characteristics that relate to gender inequality in the region. These subgroup analyses will ensure that nuanced impacts are observed (e.g., impacts that are observed only for a subpopulation or that are substantially larger for a subpopulation than for the overall sample).

The geographical RDD will enable the future evaluators to employ a difference-in-differences estimation strategy in which the NICHE beneficiaries (treatment) and comparison households will be compared at baseline and at follow-up. The combination of the differences over time and the differences between the two groups will provide an insight into program impacts over time.

## Limitations and Mitigation Strategies

Although we prepared a research design that is relatively flexible and we have anticipated possible risks to the analysis, the following are limitations of the evaluation:

Because of COVID-19, there might be some restrictions and delays for program implementation. Specifically, there might be delays in the rollout of the program beyond the currently selected sub-counties or delays or limitations to the provision of nutrition and parenting services. Because this is a formative evaluation with only a baseline, the uncertainty of delays or programmatic changes are difficult to anticipate. 	
Mitigation strategy: Especially with regards to the quantitative baseline evaluation, we have designed an approach that is less sensitive to the timing of implementation or follow-up evaluations.

Although randomized evaluations are often seen as the gold standard for impact evaluation, in this case we considered a quasi-experimental design. We understand that the government’s priority is to get those in need covered by the program, and we, therefore, did not want to use a design that would require eligible population to be randomized into beneficiary and non-beneficiary populations.  	
Mitigation strategy: We developed a quasi-experimental approach for this evaluation. as more ethical while still being able to rigorously assess program effects in the future.

Our primary qualitative data sample includes two counties. This sample is not representative, meaning that the results are not wholly generalizable on its own, as they would be in the quantitative evaluation. 	
Mitigation strategy: We anticipate that our sample will reach the saturation of data needed to identify lessons learned and inform strategy development. In addition, our evaluation design is such that the qualitative approach complements the quantitative approach and provides depth and further understanding to the findings.

There is a possibility of spillover effects of the NICHE II program to non-beneficiaries within the same community, since some of the nutrition and parenting components will be open to all community members. We anticipate mostly positive spillover effects, meaning non-beneficiaries benefiting from the NICHE II implementation in their area. For the impact analysis we expect that the spillover effects have limited influence on the estimations of the treatment effects, because we do not think the spillover effects will reach the sub-counties from which we will select our comparison group. However, positive spillovers may lead to an underestimation of the overall impact of NICHE II on the community if many non-registered households benefit from the complementary NICHE II services. 	
Mitigation strategy: We think that the risk is mitigated due the limited expected effect, however we do recommend to incorporate the possibility in the discussion of future impact evaluation results.

## Quality Assurance and Ethical Principles

AIR supports its project teams by implementing several strategies to ensure success. These include (a) frequent internal status meetings to identify potential technical, cost and scheduling problems; (b) monthly expense reporting to track variances from planned expenditures; (c) senior AIR staff review of all project deliverables before submission to ensure adherence to quality standards; and (d) proactive communication with each team leader to enhance the successful completion of these cooperative efforts. In this section, we provide information about our processes for ensuring the security of project data (see the Ethical Principles section).

Quality assurance

Study implementation. The team lead has the ultimate responsibility for ensuring that all activities and deliverables are completed on time and are of the highest quality. The team lead will contact UNICEF KCO and other key stakeholders immediately if a potential problem might jeopardise quality. Although we do not anticipate such problems, any potential variation from the work plan will be thoroughly discussed with the technical reference group using a problem-solving approach. The team will determine how the issue will be resolved to maintain UNICEF’s and AIR’s high standards.

Financial management and cost control. AIR has assigned an experienced finance associate to the project. This associate will conduct annual project audits to ensure proper tracking and accounting of all expenses. In addition, the finance associate will be responsible for working with the project manager to project expenditures and track monthly spending. The finance associate also will conduct a detailed review of the monthly financial reports that are submitted by the project manager. AIR has developed procedures and protocols to prevent the misuse of project funds, and our organisation periodically conducts ad hoc audits to ensure project adherence to protocols.

Project QA reviews. Through AIR’s project review system, each project undergoes a thorough, bimonthly review with a senior-level project reviewer. During the project review, the team lead and reviewer will evaluate the project performance on key metrics, focusing on financial health, contractual requirements, subcontractor management, client communication, and quality control and assurance.

Data collection. The fourth level of QA involves the collection of high-quality, accurate data. This includes minimizing researcher bias, minimizing social desirability bias and employing high-quality, well-trained facilitators. AIR will be actively involved in overseeing and managing local partners’ selection of facilitators for this project to ensure that they are qualified and capable of performing to the highest standards. In addition, prior to commencing data collection, AIR will conduct comprehensive interactive trainings with in-country data collection researchers from Dalberg. These trainings will provide an overview of the project and train researchers and enumerators on the use of evaluation data collection materials. During these trainings we will cover gender-sensitive and human rights–based approaches to research, and we will make sure that the field team fully understands and is ready to follow ethical procedures including informed consent. Since it is highly unlikely that the quantitative and qualitative lead will be able to travel internationally for data collection, they will frequently interact with the field team using video calls and group messaging.

QA of deliverables. The research team assigned an independent quality reviewer with research and evaluation expertise to serve as the QA reviewer on each of its projects. Dr. Seidenfeld serves as the project’s QA reviewer ensuring the overall quality and rigour of the research design and analysis. Dr. Seidenfeld is Vice President of the International Development Division at AIR and has more than 15 years of experience designing, managing and implementing mixed-methods evaluations in diverse low-income countries, making him well positioned to critically evaluate the proposed quantitative and qualitative data collection and analysis plans during both the inception and analysis phases. In addition to internal organizational QA processes, the team leaders and the research team will work closely with UNICEF to ensure that all relevant stakeholders are actively involved in quality control processes.

Ethical principles

AIR aligns our ethical approach with the guidelines articulated in ‘UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis’ (April 2015) and UNEG evaluation principles. Based on our understanding of these guidelines and standards, we address key aspects related to research ethics, namely, duty of care, ethical clearance, data security.

#### Duty of care: Should the research take place?

At every phase of the research process (i.e., review, design, data collection, analysis and dissemination), AIR and its research partners will adhere to the strictest ethical guidelines to ‘do no harm’ in trying to ensure that beneficiary women’s voices are represented in the research findings and that their rights upheld. As articulated in the ‘UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection, and Analysis’, AIR respects the rights of vulnerable and marginalized groups such as marginalized households receiving cash transfers to participate and be represented in research- and evidence-generating activities. In Annex B we set out in detail our strategies to ensure active and equitable participation of diverse groups of beneficiaries.

Given the current circumstances of the global pandemic, we also describe our protocols to mitigate the risks to COVID-19. Despite the inherent risks associated with conducting research on vulnerable households with pregnant women or mothers with young children during the COVID-19 global pandemic, AIR firmly believes that the benefits of the proposed program evaluation ultimately outweigh the potential risks, provided that the stringent mitigation measures outlined in Annex B are fully adhered to by all research participants for the duration of the assignment. However, AIR will consult with UNICEF, appropriate IRBs (described in the section below) and other relevant stakeholders to determine whether the risks to participants and data collectors allow in-person data collection or, if unacceptably high, remote data collection activities (such as telephone-based surveys and interviews).

#### Research Ethics

##### AIR IRB review. All team leads at AIR must register new projects with AIR’s IRB (IRB00000436), which assesses the project’s compliance with standards of conduct and the protection of the rights of human research subjects. AIR requires annual ethics training for AIR staff and has an ethics officer who is responsible for establishing appropriate ethical and legal standards and overseeing compliance with laws, regulations and AIR’s personnel manual. All AIR staff, subcontractors and consultants involved in the collection of data from human research participants must adhere strictly to the requirements of AIR’s IRB. The IRB must pre-approve all research activities and protocols involving human subjects as well as an information security plan to protect the confidentiality of data collected from research participants.

All participants will be asked for their informed consent/assent to engage in activities that are specific to the research components of the project. Participants will be asked to give their consent/assent in a language they understand, worded at an appropriate level for their age and educational background. All individuals and organizations that collect data on behalf of AIR are required to sign our Participant Protection Agreement to ensure that they are aware of the requirements for protecting human subjects in research. AIR’s IRB follows the standards set forth in the American Evaluation Association guidelines and by the Joint Committee on Standards for Educational Evaluation. Three general principles define these standards: (a) Researchers will conduct research legally and ethically, taking into account the welfare of those involved in the evaluation as well as that of the public; (b) researchers will conduct research in a competent and efficient fashion that will lead to reliable and accurate results; and (c) researchers will design research and report the results in a manner that is useful to and appropriate for the intended audience. Clear guidelines exist regarding the expectations with which local data collectors must comply (e.g., how to document informed consent, how to store and restrict access to physical files and electronic data files, and how to treat identifiable information). 	

In-country ethical clearance. AIR will comply with all in-country requirements for ethics review and approval for all research activities. AIR will obtain a research permit from the National Commission for Science, Technology and Innovation (NACOSTI) for this study. In addition, we will request ethical clearance with the African Medical and Research Foundation (AMREF) for the relevant components in this study, which involve research with children (i.e., anthropometric measurements) and any components on child health and parenting, which are considered sensitive. Dalberg Research, on behalf of the AIR team, will submit the proposal for the study including the tools and questionnaires for an expedited review to the AMREF to ensure that the data collection process can continue smoothly.

##### Compliance with United Nations ethical standards. AIR follows the United Nations Evaluation Group’s (UNEG) Code of Conduct, which requires both a conflict- and gender-sensitive approach to research; adherence to the ‘do no harm’ principle; and transparency, confidentiality, accuracy, accountability and reliability, among other key principles (UNEG, 2008). Specifically, with regard to the protection of vulnerable individuals and communities, AIR respects and adheres to the United Nations Declaration of Human Rights, the United Nations Refugee Convention, the Convention on the Rights of the Child and the Convention on the Elimination of All Forms of Discrimination against Women as well as other human rights conventions and national legal codes that respect local customs and cultural traditions, religious beliefs and practices, personal interaction, gender roles, disability, age and ethnicity (UNEG, 2008).

##### Ensuring data security. AIR follows a series of steps to ensure that all data collected in the field are secure and do not risk loss of confidentiality. Before commencing a new project, the research team must submit a data governance plan that will guide data security throughout the study. The data governance plan must be approved before any data collection or analysis can begin. Once we have an approved data governance plan, we then ensure that all team members are fully trained in AIR’s established data security protocols. When transmitting files digitally, we encrypt and password protect all data files. During the data analysis phase, we restrict access to the data to the approved members of the research team.

# Evaluation work plan

The evaluation work plan has four main phases corresponding with the four components of this evaluation: (1) inception, (2) formative evaluation, (3) M&E framework and (4) baseline evaluation. The four phases are closely linked, and activities in each of the phases contribute directly to the processes and activities in consecutive phases. The phases are described in more detail below and Table 6 provides timeline for the expected activities. The timeline for the evaluation is 12 months, which started on 1 April 2021 and has an expected end date 31 March 2022. The activities in the work plan are being carried out by the AIR evaluation team. The roles and responsibilities of the team members are described in more detail Annex E. The responsibilities for each phase are also included in the description below.

## Phase 1: Inception (April-July 2021)

AIR had a project kick-off meeting with UNICEF on 30 March 2021 and has had weekly meetings with the UNICEF KCO team since the start of the project to further discuss details on the implementation and methodology. For instance, the AIR team and UNICEF held thematic meetings on the NICHE II registration process, the quantitative baseline methodology and the child protection component to learn about the status of the program in more detail and to discuss the options for the evaluation design prior to including these in the inception report. The inception report is, therefore, a combination of the research design described in the evaluation proposal and the results of the consultative process with the UNICEF KCO team. In agreement with the UNICEF KCO, we have postponed the delivery of the inception report to the beginning of May to ensure that all the planned consultative meetings could occur beforehand.

At the end of the inception phase we will hold a highly participatory virtual inception presentations to refine and potentially reprioritize evaluation questions, and discuss the evaluation design and methodology. During the workshop, we will solicit inputs from the primary end users of the evaluation, including UNICEF KCO, the Evaluation Reference Group (ERG) and possibly implementing partners and the following GoK institutions: MLSP, MoH, MD&ASAL and CoG.

The objectives of the inception workshop are:

- To agree on final research questions to guide the formative evaluation,

To ensure engagement and buy-in of key stakeholders from the start of the evaluation, and

To inform qualitative and quantitative sampling and instrument development.

During the workshop, we will present preliminary findings from the desk review and ToC assessment, including any glaring gaps in data availability, and will validate our sampling and identify potential missing respondents. Additionally, the workshop will enable us to deepen our understanding of the relationships among different actors engaged in the NICHE II program.The inception phase will be led by the Team lead, Juan Bonilla in coordination with the project manager Marlous de Milliano.

## Phase 2: Formative evaluation (July- December 2021)

Phase 2 of the formative evaluation consists of document review, refining the ToC and key informant interviews at the regional and national levels. The document review started in April, and the results will be used to refine the ToC and is led by the project manager. The KIIs are the second main inputs to the possible suggestions for adjustments to the ToC and NICHE II program design. The training for the interviewers and the KIIs is planned for mid- to end-May because IRB approval and the NACOSTI research permit will need to be obtained beforehand. The qualitative data collection will be led by the qualitative lead Hannah Ring. The formative research report, which will contain the findings on the lessons learned from the NICHE I, the suggestions for the NICHE II program design and refinement of the ToC. In agreement with UNICEF KCO, the team decided to prioritise the data collection of the baseline assessment due to the implementation of NICHE activities, the formative evaluation data will therefore only be analysed in depth after the data collection has finished. The formative evaluation report will therefore be submitted in December. The formative research report will be coordinated by the project manager.

After the first draft of the formative evaluation report is delivered the AIR team will present the preliminary results to the ERG and possible other key partners for their inputs and validation. The draft report will also go through the formal review process soliciting feedback from UNICEF KCO and the UNICEF ESARO. The AIR team will incorporate the inputs and feedback in the final version of the report.

## Phase 3: M&E framework (October-December 2021)

The timing of Phase 3 will overlap with Phase 2 because some of the activities such as the review of the existing results framework can be conducted simultaneously with the activities in Phase 2. In addition, the consultative process for M&E as well as the refinement of the M&E framework benefit directly from the momentum of the discussions regarding the changes to the ToC and the KIIs planned for Phase 2. The M&E framework and narrative will, therefore, be submitted shortly after the approval of the formative evaluation report. Our expert consultant Ms. Tamsin Walters will lead this activity. The results will be presented to the ERG as well as the NICHE MIS team for their feedback and validation.

## Phase 4: Baseline evaluation (August-March 2021)

Phase 4 consists of primary data collection for the RQA and quantitative household survey, data analysis, the baseline assessment report and preparation of other key findings dissemination materials. Because components of the baseline evaluation are subject to approval by AMREF, the data collection will only start after ethical clearance has been obtained (see the ‘ethical principles’ section for more details on the ethical clearance procedure). AIR will request an expedited procedure to make sure that Phase 4 can start as planned. We plan for the qualitative and quantitative data collection to start in September. The qualitative component will be led by the qualitative lead Hannah Ring, and the quantitative component by the quantitative lead Marlous de Milliano. The team lead, Juan Bonilla is responsible for the overall baseline evaluation. After the data collection and analysis, the baseline report will be presented to UNICEF KCO, the ERG, government partners and key stakeholders.

Table 6. Project Tasks and Timeline

| Phase and activity | 2021 |  |  |  |  |  |  |  |  | 2022 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar |
| Phase 1 (inception report) |  |  |  |  |  |  |  |  |  |  |  |  |
| Refining evaluation methodology | ● |  |  |  |  |  |  |  |  |  |  |  |
| Developing relevant data collection tools, including questionnaire and interview guides | ● |  |  |  |  |  |  |  |  |  |  |  |
| Applying for IRB approval | ● | ● |  |  |  |  |  |  |  |  |  |  |
| Deliverable 1a: Inception report |  | ● | ● |  |  |  |  |  |  |  |  |  |
| Deliverable 1b: Inception workshop |  |  | ● |  |  |  |  |  |  |  |  |  |
| Refining quantitative tools |  |  |  | ● | ● |  |  |  |  |  |  |  |
| Refining qualitative tools for KIIs |  |  |  | ● | ● |  |  |  |  |  |  |  |
| Applying for AMREF clearance with finalized tools, and obtaining NACOSTI permit |  |  |  |  | ● | ● |  |  |  |  |  |  |
| Phase 2 (formative evaluation report, including key stakeholder interviews) |  |  |  |  |  |  |  |  |  |  |  |  |
| Document review |  | ● | ● |  |  | ● | ● |  |  |  |  |  |
| Refining ToC |  |  |  |  |  | ● | ● |  |  |  |  |  |
| Training interviewers |  |  |  |  | ● |  |  |  |  |  |  |  |
| Conducting interviews with key regional and national informants* |  |  |  |  |  | ● | ● |  |  |  |  |  |
| Coding and analysis |  |  |  |  |  |  | ● | ● |  |  |  |  |
| Deliverable 2a: Draft formative evaluation report |  |  |  |  |  |  |  |  | ● |  |  |  |
| Deliverable 2b: Final formative evaluation report |  |  |  |  |  |  |  |  |  | ● |  |  |
| Phase 3 (M&E framework) |  |  |  |  |  |  |  |  |  |  |  |  |
| Reviewing and refining M&E framework |  |  |  |  |  |  | ● | ● |  |  |  |  |
| Consultations on the M&E framework |  |  |  |  |  |  |  | ● |  |  |  |  |
| Refining qualitative tools for RQA |  |  |  |  |  |  |  | ● |  |  |  |  |
| Refining quantitative tools |  |  |  |  |  |  |  | ● |  |  |  |  |
| Deliverable 3: M&E framework and narrative |  |  |  |  |  |  |  |  | ● |  |  |  |
| Phase 4 (baseline evaluation) |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruiting enumerators and interviewers |  |  |  |  |  | ● |  |  |  |  |  |  |
| Training and orienting survey enumerators |  |  |  |  |  | ● |  |  |  |  |  |  |
| Training interviewers |  |  |  |  | ● |  |  |  |  |  |  |  |
| Conducting data collection for RQA* |  |  |  |  |  | ● | ● |  |  |  |  |  |
| Coding and analysis |  |  |  |  |  |  |  | ● | ● |  |  |  |
| Survey pre-testing and finalization of tools |  |  |  |  |  | ● |  |  |  |  |  |  |
| Administrating surveys* |  |  |  |  |  | ● | ● |  |  |  |  |  |
| Data entry, cleaning and analysis |  |  |  |  |  |  | ● |  |  |  |  |  |
| Report writing |  |  |  |  |  |  |  | ● | ● |  |  |  |
| Deliverable 4a: Draft baseline assessment report |  |  |  |  |  |  |  |  |  | ● |  |  |
| Deliverable 4b: Final summary presentation |  |  |  |  |  |  |  |  |  | ● |  |  |
| Deliverable 4c: Final baseline assessment report |  |  |  |  |  |  |  |  |  |  | ● |  |
| Deliverable 5a: Policy briefs summarizing key findings |  |  |  |  |  |  |  |  |  |  |  | ● |
| Deliverable 5b: Other dissemination products |  |  |  |  |  |  |  |  |  |  |  | ● |

* The timing of all primary data collection is subject to ethical clearance and IRB approval.

# Dissemination Plan

Targeted and effective dissemination of information is critical at all phases of a research study and ensuring that all stakeholders have access to and understand the research results is essential to maximize transparency and ensure the utility of the evaluation. Targeted and effective dissemination of information is particularly important for this project, as UNICEF and the government stakeholders will use the results to strengthen responses to the NICHE II program and to potentially scale up the program to more districts. Thus, AIR is committed to generating meaningful, evidence-based policy dialogue and creating a framework to guide the implementation of the program throughout its life cycle. Next, we describe the approaches we will use to disseminate findings.

## Regular stakeholder engagement

AIR will maintain engagement with UNICEF KCO and other key stakeholders involved in the implementation of NICHE II, such as the Government of Kenya to collaboratively discuss the implications of the inception phase and draw on recommendations and processes to improve the program design at the key stakeholder workshop and presentations of deliverables. AIR will planregular stakeholder engagement through online presentations of the preliminary findings after each evaluation components to solicit feedback and validation of the findings. These dissemination meetings are developed to effectively and collaboratively engage with stakeholders on ways to foster uptake of newly collected data and gathered insights to improve the design and reach of NICHE II. Further, AIR will confer with UNICEF and key stakeholders throughout the evaluation to ensure that the program continues to be implemented in a way that will effectively support the target populations and lead to long-term improvements in their human development.

## Dissemination workshops with stakeholders

AIR will work closely with UNICEF Kenya to determine the style and outline of the dissemination deliverables, such as policy briefs and (online) presentations of findings. The evaluation results will be disseminated to senior county management teams, the national level government for MLSP, MoH, CoG, MD and ASAL. Below, we provide some illustrative examples.

- Formative evaluation report and baseline assessment report. The two key deliverables of this evaluation are the formative evaluation report and the baseline assessment report. These serve as comprehensive documents for presenting the findings of the various mixed-methods components of our evaluation. The formative evaluation report will concentrate on Components 1 and 2, including review of the proposed NICHE II program and refinement of the ToC. The baseline assessment report will focus on Components 4, which concern the baseline findings. Both reports are technical in nature, providing detailed information on methods, data collection and findings. The purpose is to provide UNICEF staff, implementers, key stakeholders and future evaluators with in-depth knowledge of the NICHE II program and initial findings on nutrition and social and child protection.

Evaluation and policy briefs. AIR uses evaluation and policy briefs with accessible language to communicate findings to governments and other relevant bodies. AIR’s Policy Center (which can be found here) assists with the creation of these briefs to ensure that they are forward thinking, action oriented and audience appropriate. For this project, AIR will develop three evaluation briefs (in English) summarizing the key findings from the formative evaluation and presenting key elements of the baseline evaluation through visual summaries for a broader, non-technical audience. The briefs will be targeted at specific audiences. For example, one might be for a general audience, one for the national government and one for local governments. We will adapt the language and focus of the findings for each of the target audiences to make the final product as helpful to the user as possible. This can be, for example, to strengthen advocacy, accountability or general understanding of the program. We may also use FGD data and photos collected (with consent) from the field study, as these may be particularly instructive when developing videos, providing a visual context.

Workshops, webinars and conferences. To achieve maximum policy impact, AIR hosts and attends workshops, webinars and conferences to share results. When we organize an event, we work with our evaluation partners to invite a broad spectrum of stakeholders, including government agencies and ministries, community organizations, scholars and donor agencies. In 2018, for example, AIR and UNICEF Zambia convened donors, service providers, researchers and policymakers for an interactive seminar on early childhood development research. During this conference, AIR shared the results of a formative evaluation on traditional parenting practices throughout Zambia and used the session to brainstorm more meaningful early childhood programming. AIR will consult with UNICEF Kenya to identify appropriate strategic venues at which to present the results from this evaluation with the Evaluation Reference Group, funders and implementers of NICHE as well as back to communities through existing platforms (e.g., chief baraazas). For these dissemination events, AIR will develop a PowerPoint presentation (in English) to share findings. The presentation will be created such that it is accessible to a broad audience. Given the current international travel restrictions, the presentations are expected to be conducted online or in a hybrid format.

Social media. AIR has an active social media presence – including on LinkedIn, Twitter and Facebook – and uses these online platforms to share the results of its studies, spark conversation about results and reach a global audience. If UNICEF KCO is in agreement, AIR will use its numerous social media outlets to communicate the findings from this evaluation to a broad audience.

# References

Bastagli, F., Hagen-Zanker, J., Harman, L., Barca, V., Sturge, G., Schmidt, T., & Pellerano, L. (2016). Cash transfers: What does the evidence say – A rigorous review of program impact and the role of design and implementation features. London: ODI. Retrieved from https://assets.publishing.service.gov.uk/media/57bafa91ed915d1259000002/Cash_transfers_what_does_the_evidence_say_Full_Report.pdf

Beebe, J. (2001). Rapid assessment process: An introduction. Walnut Creek, CA: Altamira Press.

Bonilla, J., Zarzur, R. C., Handa, S., Nowlin, C., Peterman, A., Ring, H. (2017). Cash for women’s empowerment? A mixed-methods evaluation of the government of Zambia’s child grant program. World Development, 95, 55–72.

CHASP (2021). Activity Report – START-UP Registration of Beneficiaries for NICHE Scale-Up in the 5 Counties of Kilifi, Kitui, Marasbit, Turkana and West Pokot.

Cohen, J., Rothschild, C., Golub, G., Omondi, G., Kruk, M., & McConnell, M. (2017). Measuring the impact of cash transfers and behavioral ‘nudges’ on maternity care In Nairobi, Kenya. Health Affairs, 36, 1956–1964.

Government of Kenya (2021). Operations Manual - Nutrition Improvements through Cash and Health Education (NICHE).

de Groot, R., Handa, S., Ragno, L. P., Spadafora, T., & Ghana LEAP1000 Evaluation Team. (2020). Child malnutrition, consumption growth, maternal care and price shocks: New evidence from northern Ghana. Development Studies Research, 7(1), 18–30.

DFID [Department for International Development]. (2011). Cash transfers literature review. London: Author. Retrieved from https://www.calpnetwork.org/wp-content/uploads/2020/01/cash-transfers-literature-review.pdf

Global Nutrition Report. (n.d.). Kenya nutrition profile. Retrieved from https://globalnutritionreport.org/resources/nutrition-profiles/africa/eastern-africa/kenya/#profile

Guest, G., Namey, E., & McKenna, K. (2016). How many focus groups are enough? Building an evidence base for nonprobability sample sizes. Field Methods, 29(1), 3–22.

Kenya CT-OVC Evaluation Team. (2012). The impact of Kenya’s Cash Transfer for Orphans and Vulnerable Children on human capital. Journal of Development Effectiveness, 4(1), 38–49.

Kenya SMART (2019). Kenya SMART survey summaries 2008 – 2019. July 2019.

KFSSG [Kenya Food Security Steering Group]. (2019). The 2019 long rains season assessment report. Nairobi, Kenya: Author. Retrieved from https://reliefweb.int/sites/reliefweb.int/files/resources/2019%20LRA%20National%20Report.pdf

Kimetrica (2018). Final Report: Evaluation of NICHE in the First 1,000 Days of a Child’s Life in Kitui and Machakos Counties, Kenya.

KNBS [Kenya National Bureau of Statistics]. (2014). Kenya demographic and health survey. Nairobi, Kenya: Author. Retrieved from https://dhsprogram.com/pubs/pdf/fr308/fr308.pdf

KNBS [Kenya National Bureau of Statistics] et al. (2015). Kenya Demographic and Health Survey 2014-2015. Retrieved from https://dhsprogram.com/pubs/pdf/fr308/fr308.pdf

KNBS [Kenya National Bureau of Statistics]  & UNICEF (2017). Child Poverty in Kenya, a multidimensional approach. Retrieved from https://www.unicef.org/esa/sites/unicef.org.esa/files/2018-09/UNICEF-Kenya-2017-Child-Poverty.pdf

Kopper, S., & Sautmann, A. Best practices for conducting phone surveys. Retrieved from https://www.povertyactionlab.org/blog/3-20-20/ best-practices-conducting-phone-surveys

MacAuslan, I., & Schofield, L. (2011). Evaluation of concern Kenya’s Korogocho emergency and food security cash transfer initiative. Oxford, UK: Oxford Policy Management.

Menon, P., Ruel, M. T., Loechl, C., & Pelto, G. (2005). From research to program design: Use of formative research in Haiti to develop a behavior change communication program to prevent malnutrition. Food Nutrition Bulletin, 26(2), 241–242. Available from: PM:16060227.

Merttens, F., Hurrell, A., Marzi, M., Attah, R., & Farhat, M. (2013). Kenya Safety Net Program monitoring and evaluation component: Quantitative impact evaluation final report. Oxford, UK: Oxford Policy Management. Retrieved from http://www.hsnp.or.ke/filedownload.php?download_file=hsnp_impact_quantitative_evaluation_report2009_2013.pdf

Mikkelsen, B. (2005). Methods for development work and research: A new guide for practitioners. New Delhi: Sage Publications India.

Morgan, D. L. (1996). Focus groups. Annual Review of Sociology, 22, 129–152. Retrieved from http://www.annualreviews.org/doi/abs/10.1146/annurev.soc.22.1.129

Oakley, A., Strange, V., Bonell, C., Allen, E., Stephenson, J., & RIPPLE Study Team. (2006). Process evaluation in randomised controlled trials of complex interventions. BMJ, 332(7538), 413–416. doi:10.1136/bmj.332.7538.413

OECD [Organisation for Economic Co-operation and Development]. (2019). Better criteria for better evaluation. Paris, France: Author. Retrieved from www.oecd.org/dac/evaluation/revised-evaluation-criteria-dec-2019.pdf

Patton, M. Q. (2012). Essentials of utilization-focused evaluation. Thousand Oaks, CA: SAGE.

Peersman, G., Guijt, I., & Pasanen, T. (2015). Evaluability assessment for impact evaluation. Methods Lab publication. London: ODI. Retrieved from www.odi.org/publications/9442-evaluability-assessment-impactevaluation-guidance-checklists-and-decision-support

Peterman, A., Palermo, T. M., Handa, S., Seidenfeld, D., & Zambia Child Grant Program Evaluation Team. (2018). List randomization for soliciting experience of intimate partner violence: application to the evaluation of Zambia's unconditional child grant program. Health Economics, 27(3), 622–628.

Rychetnik, L., Frommer, M., Hawe, P., & Shiell, A. (2002). Criteria for evaluating evidence on public health interventions. Journal of Epidemiology and Community Health, 56(2), 119–127. Retrieved from https://doi.org/10.1136/jech.56.2.119

UNEG. (2008). UNEG code of conduct for evaluation in the UN system. New York, NY: United Nations Evaluation Group.

UNICEF. (2017). Contributing towards the nutritional wellbeing of deprived children and women in Kenya: Second annual progress report. New York, NY: Author.

UNICEF. (2018). Situation Analysis of Children and Women in Kenya 2017. UNICEF, Nairobi, Kenya. Retrieved from https://www.unicef.org/kenya/media/136/file/SITAN-report-2017-pdf.pdf

UNICEF. (2019a). Country office annual report 2019: Kenya. New York, NY: Author. Retrieved from https://www.unicef.org/about/annualreport/files/Kenya-2019-COAR(1).pdf

UNICEF. (2019b). Levels and trends in child mortality: Report 2019. New York, NY: Author. Retrieved from https://www.unicef.org/media/60561/file/UN-IGME-child-mortality-report-2019.pdf

USAID. (2018). Kenya nutrition profile. Washington, DC: Author. Retrieved from https://www.usaid.gov/sites/default/files/documents/1864/Kenya-Nutrition-Profile-Mar2018-508.pdf

UNICEF (2020). Nutrition Improvements through Cash and Health Education (NICHE) Program First Annual Report.

World Bank. (2021). The World Bank in Kenya. Washington, DC: Author. Retrieved from https://www.worldbank.org/en/country/kenya/overview

# ANNEXES

# Annex A – Theory of Change

| NICHE Theory of Change |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact | Most vulnerable children in intervention areas have improved well-being in the areas of nutrition, social protection, and child protection |  |  |  |  |  |  |  |  |  |  |
| Outcome | Primary caregivers demonstrate improved nutrition, cash expenditure, and positive parenting practices |  |  |  |  | Improved functionality of community and institutional systems to deliver integrated nutrition, cash transfer, and protection services at county and national level |  |  |  |  |  |
| Output | Households have improved knowledge and skills on nutrition and hygiene | Households have improved access to feedback and referral mechanisms | Households have improved access to cash and knowledge on cash expenditure practices | Households have improved knowledge and skills in positive parenting/non-violent discipline and responsive care |  | Health workers and BWC have improved knowledge and skills on nutrition and hygiene | Improved delivery mechanisms for integrated nutrition and protection services | Target counties have improved beneficiary identification and cash transfer system | Target counties have improved community based child protection mechanisms | Evidence generation (including MIS, evaluations, capacity assessments, CBA) informs NICHE program implementation | Improved national and county level advocacy and coordination for NICHE |
| Inputs | Integrated nutrition counseling for cash transfer recipients | Establishment of referral and feedback mechanisms | Integrated nutrition counseling for cash transfer recipients | Parenting education for parents/caregivers with young children, foster care children, and children with protection concerns |  | Capacity development of Health Workers and Beneficiary Welfare Committees | Support for CHS establishment/ implementation | Establishment of registration/ cash transfer system for NICHE Beneficiaries | Operationalize evidence-based positive parenting education and promotion of family based care options | Development and implementation of monitoring and evaluation systems | Conduct advocacy forums and strengthen coordination mechanisms at national and county level |
|  |  |  | Establishment of registration/ cash transfer system for NICHE Beneficiaries | Operationalize evidence-based positive parenting education and promotion of family based care options |  |  |  |  |  |  |  |
| Activities | 4.1.2 CHVs conduct targeted home visits | 4.1.1 NICHE Beneficiary awareness creation and linkage to CHVs | 2.1.1/2.2.1 Training of relevant stakeholders (DCS, CHMT, etc.) in initial/on-demand NICHE registration | 5.1.2 Support the training of parents group fostering children without parental care and conduct regular follow up with these |  | 3.1.3 Training of CHEWs on BFCI | 4.1.1 NICHE Beneficiary awareness creation and linkage to CHVs | 2.1.1/2.2.1 Training of relevant stakeholders (DCS, CHMT, etc.) in initial/on-demand NICHE registration | 5.1.1 Formation, training and functioning of community based child protection mechanisms | 6.1.1 Develop and test MIS prototype | 1.2.1 County level NICHE sensitization and launch in select counties |
|  | 4.1.3 CHEWs provide mentorship and supportive supervision | 4.1.5 Conducting for bi-monthly Community Mother Support Groups (CMSG) | 2.1.2/2.2.2 Securing QA on initial registration process/on-demand registration of new and exited beneficiaries | 5.1.3 Support parenting sessions to prevent violence and trigger response mechanisms |  | 3.1.4 Operating and Contracting costs for training of Community Health Volunteers (CHVs) on BFCI | 4.1.4 Facilitation of bi-monthly CHVs meetings | 2.1.2/2.2.2 Planning, monitoring, and QA for counties to conduct initial/on-demand registration of all eligible NICHE beneficiaries |  | 6.1.2 Support the training of NICHE Information System users | 1.2.2 Officers supporting coordination, implementation and QA of NICHE at county level |
|  | 4.1.7 Development and airing of Radio Campaigns | 4.1.6 Bi-monthly baby friendly gatherings in place and held every two months |  |  |  | 3.1.5 Joint supportive supervision of BFCI nutrition counselling conducted by counties | 4.1.8 Sub-county supportive supervision visits conducted | 6.2.1 Operating and contracting costs for CHMT, DCS, NDMA, DSD at county level conduct routine program monitoring and quality assurance | Strengthen community based child protection mechanisms | 6.1.3/6.1.4 Roll out of NICHE information systems and data collection five target NICHE counties | 3.1.1 County/Sub-County HMT sensitization on BFCI |
|  | Support for CHS implementation at county level | 3.1.2 Formative research and adaptation of BFCI tools |  |  |  | 4.1.4 Facilitation of bi-monthly CHVs meetings | Support for CHS implementation at county level | 6.2.2 Contracting for regular quality assurance activities in line with UNICEF standards to enhance efficiency and prevent fraud |  | 6.2.3/6.3.1/6.3.2 Conduct capacity assessment/ baseline assessment/ cost efficiency analysis | Advocacy for CHS/ integrated programs |
| Assumptions | Functioning community health care system (community units) |  |  |  |  |  |  |  |  |  |  |
| Risks | Recurring droughts and limited access to food, COVID-19 |  |  |  |  |  |  |  |  |  |  |
| Mitigation measures | Linking NICHE to other existing food systems interventions |  |  |  |  |  |  |  |  |  |  |

# Annex B – Ethics Approach

Strategies to ensure active and equitable participation of diverse groups

Use of informed consent for participants. Participants will be asked to give their consent in a language that they understand, worded at an appropriate level for their age and educational background.

All of the protocols include a stopping point before the start of the interview questions, to gain assent for participation and permission to audio-record. The consent language includes (a) a concise and focused presentation of the key information that is most likely to assist a prospective participant in understanding the reasons that one might or might not want to participate in the research; (b) a statement that the study involves research, an explanation of the purposes of the research and the expected duration of participation, and a description of what will happen if children participate; (c) a description of any reasonably foreseeable risks or discomforts to the participant; (d) a description of any benefits to the participant or others that may reasonably be expected from the research; (e) a statement describing the extent, if any, to which confidentiality of records identifying the participant will be maintained; (f) an explanation of whom to contact for answers to pertinent questions about the research and research participants’ rights; and (g) a statement that participation is voluntary, that refusal to participate will involve no penalty or loss of benefits to which the participant is otherwise entitled, and that the participant may discontinue participation at any time without penalty.

We have also included introductory language for all the KII, FES and FGD protocols to explain the purpose of the evaluation, what the participants will be asked to do, and to what extent we will protect the privacy of their responses. We also explicitly ask participants for verbal agreement to take part in the KII/FES/FGD and to be audio-recorded. (We do not ask for written consent, as it is not required, and obtaining written consent would provide identifying links between participants and data that would not have existed otherwise, placing their privacy at greater risk.) Also, given the nature of the questions we will ask women, we will train enumerators to watch carefully for any signs that participants such as women beneficiaries are becoming distressed discussing certain issues, and will identify a point of contact at each community (such as a community leader) who can be informed and follow up if there are any concerns that a participant experienced any distress.

Catering to Needs of Participants. In order to ensure that there is comfort between the participant and interviewer, local enumerators from Dalberg who speak the local language will conduct the interviews at the village and county levels. Further, enumerators will conduct interviews and focus group discussions at a common space that is both safe and accessible for participants. AIR will put great care into its messaging of the research and will request local buy-in, which means meeting local male and female community leaders before focus group discussions and asking for their permission. Local buy-in is imperative to address any concerns and possible tensions that could arise during the research process. In addition, we will carefully consider the space and time during which interviews would be conducted to ensure that respondents are able to participate fully, with limited burden and feel at ease. For example, participants are not expected to travel to the capital and enumerators will find a common space near the participants’ residence (with the help of county level program implementation stakeholders) and where participants’ can share their responses and be assured that their responses will be confidential. This strategy will ensure that participants are not faced with barriers such as care-giving responsibilities, or mobility restrictions.

Risks Versus Benefits. The evaluation activities do not impose any risks to participants beyond what they would encounter in daily life. The greatest risk to participants is potential embarrassment or other consequences should any identifiable information that they provide become public knowledge. We will take steps to minimise this risk by (a) training enumerators in the protection of data, (b) setting ground rules at the beginning of FGDs regarding the sharing of information by participants, (c) following the data protection procedures we described earlier, (d) taking care not to include any information in evaluation reports that could directly identify study participants, and (e) notifying participants during the informed consent process of any risks that they could be identified indirectly based on their position (for example, there may only be one health worker in a village).

Inclusion and Equality. At the village and county level, we expect the sample to reflect the population being targeted by the program. When holding FGDs with women, we will have separate private groups for women, to help participants feel comfortable speaking freely about their experiences.

Gender-Sensitive, Rights-Based Research Approach Training for Enumerators. Recruiting and effectively training data collectors in gender-sensitive and rights-based approaches is also central to AIR’s strategy. AIR’s training for local data collectors from Dalberg will cover several approaches for more gender-sensitive, rights-based researchers, such as using enumerators of the same gender as the respondents, allowing for verbal as opposed to written consent, effectively eliciting responses from respondents who may not normally be asked for their opinions, and avoiding over-reliance on community gatekeepers for sampling. We find that these strategies are more beneficial for capturing responses from individuals whose voices are traditionally excluded from evaluations.

Trust in Enumerators. Taking measures to foster trust between respondents and enumerators is vital for successful evaluations, particularly in contexts where trust in outsiders is low. Reliance on data collectors who are familiar with the context can increase trust in enumerators. One solution is to rely on the local data collection capacity that are familiar with the context. Similarly, we will rely on local enumerators from Dalberg who are familiar with the context of the counties to collect village and county level data.

Sensitive Questions. To obtain reliable information about sensitive topics, it is important to provide additional support to participants who find the topics traumatic, and to rely on enumerators who are familiar with the context of the respondents. To obtain reliable information from women, for example, we will rely on enumerators of the same gender, and give respondents a private space in which to speak with the enumerators.

Mitigating Anger, Fear and Distress among Participants. Concerns regarding anger, fear and distress among research participants, which may be incited due to sensitive topics will be addressed by AIR and Dalberg through guidelines in four key areas as provided the U.S. National Institute of Mental Health (NIMH): (1) the decisional capacity of potential participants, (2) the vulnerability of research subjects, (3) the risks and benefits of research participation and (4) informed consent (NIMH, 2015). All team members will be trained to recognize emotional distress and have necessary tools to make appropriate referrals to child protection services, health care professionals, and other trauma- and violence-prevention related organizations in the communities visited.

Access to the Most Disadvantaged and Powerless Respondents. Ensuring that research does not account for just the perspectives of the gatekeepers of any one community but finds ways to adapt tools to access those more marginalized and disenfranchised from the political or social elites – women and girls, and individuals with disabilities or lower levels of education – is imperative. For this purpose, we will collaborate with a local consultant, Emily Mbelenga, and train local enumerators from Dalberg, who understand the different contexts in Kenya. During data collection, we will also work with Dalberg to select enumerators who are from the same county region, thus helping to facilitate local buy-in and/or permission for data collection by community leaders in the villages. We will ensure that the enumerators speak the local dialect, respect cultural norms, and that female enumerators interview women. Enumerators who speak the local mother-tongue languages are critical for barrier-free research and to reduce any misunderstandings.

Mitigating risks related to COVID-19

Due to the potential risks posed by the COVID-19 pandemic, AIR has prepared a robust mitigation strategy to ensure the safety of data enumerators and informants and to minimize the risk of unintentionally spreading the virus. This strategy includes three main pillars: (a) continuous monitoring, (b) minimizing travel and in-person contact, and (c) implementing robust protection protocols for primary data collection. At the time of writing the inception report, in-person data collection is allowed following appropriate guidelines. We assume this will be possible for the duration of the evaluation, however, through continuous monitoring and a flexible approach we seek to anticipate any changes if needed.

Continuous monitoring

Although the number of daily confirmed cases has been decreasing in Kenya, there is wide variation across and within counties in the region. Moreover, AIR recognizes that the COVID-19 pandemic is a dynamic and volatile event that can rapidly change the public health trajectory of a country or locale at any given time. AIR therefore commits to working closely with its local partner, Dalberg Research, to continuously monitor the public health context of the region and in particular of the five target county areas that are the focus of the proposed baseline data collection. For the duration of the assignment, AIR will convene at least biweekly contact with Dalberg’s team leaders and other team partners to discuss COVID-19–related health concerns that might pose a risk to ongoing research activities. If a surge in new cases does occur in a setting in which we have active personnel or research, we will immediately cease all activities and assess the situation in consultation with UNICEF. AIR will consult with in-house public health experts or other reputable specialists to determine if and when research activities can continue. Alternatively, we will redesign our study to adjust our methodological approach, if necessary and feasible.

Minimizing travel and in-person contact

One motivation for AIR to partner with Dalberg is that they are based and active in Kenya, which minimizes the need for the research team to travel to collect data. Minimizing travel reduces COVID-19’s risk to the research project in two key ways. First, it limits data enumerators’ potential exposure to public spaces and to heavily populated transportation hubs (e.g., airports and buses stations). Second, in the event that air travel between countries becomes restricted, data collection can resume by leveraging Dalberg’s in-country assets. In addition, their local presence will allow AIR to have accurate and up-to-date information on local circumstances.

Since it is unlikely that AIR staff will be able to travel internationally within the time frame of the study, we will provide remote training to data enumerators as well as support and oversight for Dalberg during data collection. AIR team members will remotely join training sessions via widely available online platforms such as Skype, Zoom and Microsoft Teams. Moreover, during data collection, we will establish WhatsApp groups with all supervisors to ensure rapid communication among the team. Relatedly, we propose to use the biweekly check-in calls to help data enumerators overcome any potential obstacles, ensure adherence to the timeline, and address feedback and quality concerns from AIR’s end as they arise. Even if the AIR team must supervise and oversee data collection remotely, we will still be able to conduct regular quality control checks on the quantitative data, as we will have access to the SurveyCTO platform, allowing us to download the data in real time as it is collected in the field.

Our proposed research design is flexible to minimize in-person contact if needed. For example, for the qualitative data collection, we can conduct KIIs by telephone in case needed or preferred. AIR will work with Dalberg to coordinate the use of telephone and video-conferencing technology, where appropriate and feasible. However, we are planning to conduct village-level data collection in person if possible, because mobile phone coverage may not be sufficient among our potential respondents in selected counties. To minimize the risk of COVID-19 transmission in FGDs, we will adhere to hygiene and safety measures, as explained in the following sections. Further, FGDs can be replaced by in-depth interviews with a similar number of respondents if the risk of COVID-19 transmission is deemed overly high in study areas. In the event that in-country travel is restricted due to COVID-19, we will conduct FESs and in-depth interviews (in place of FGDs) via telephone, granted that there is enough access to telephones among our targeted population to reach our desired sample, and granted that telephone contact information is available for this population.

For our proposed quantitative methods, telephone surveys will be conducted in the event that in-country travel is restricted due to COVID-19. Telephone surveys apply primarily to populations who own telephones, which inherently biases the sample of families that we could reach. Access to mobile telephones has increased significantly. However, a high level of coverage has not been reached by all counties targeted in the study, and differences arise within counties (e.g., lower income households and women are less likely to have access to a telephone and adequate connectivity). This may lead us to underestimate more marginalized households and households in communities with more limited infrastructure.

To deal with this issue, we propose two strategies: (a) We can oversample more marginalized villages with lower telephone ownership or (b) we can use focal points in communities, such as local leaders and people at the cash transfer distribution points, to extend mobile telephone access to a broader population. Under the latter approach, we would work with local leaders or other focal points in each village to increase survey participation. This method ensures greater mobile telephone access, as well as a reduction in selection bias, by ensuring that participation extends beyond families with consistent mobile telephone access. However, use of the mobile telephone of a local leader (or another focal point) may increase desirability bias in responses, reduce privacy and raise additional confidentiality concerns. AIR is prepared to assist with the implementation of telephone-based data collection in the event that in-country travel is restricted due to COVID-19.

For both KIIs and surveys, we will select best practices for conducting telephone-based data collection to reduce non-response and ensure completion of data collection activities. For instance, informed consent will be obtained verbally at the beginning of the interview, surveys and protocols will be kept short and simple to reduce the length of the call and to reduce fatigue, interviewers will be trained to recognize signs of discomfort during interviews, and teams will send text messages to inform the respondent of an upcoming call to reduce non-response (Kopper & Sautmann, 2020). We will also suggest careful analysis of survey completion to track the quality of telephone-based data collection. Including the duration of the survey in the consent script could help to avoid instances where the respondent runs out of time or telephone battery power. All preventative measures and approaches will continue as long as there is any threat of COVID-19 resurgence.

Implementing robust protection protocols for primary data collection:

Despite the myriad risks involved in conducting research during the COVID-19 pandemic, AIR believes that there are benefits to collecting primary data in person rather than remotely. The benefits may include improved access to quality data, stronger response rates from research participants and the opportunity to observe relevant community circumstances. If UNICEF, AIR and the other research team members agree that the benefits of in-person data collection outweigh the potential risks in some or all of the research settings, AIR will develop and implement a robust protection and safety protocol that will be adhered to by all field staff for the duration of the primary data collection phase. This protocol may include the following elements:

Staff from AIR and Dalberg will follow the latest WHO and national health ministry guidelines on adopting preventative measures to combat the potential spread of COVID-19. For example, during in-person data collection, all field staff will be required to wash their hands regularly, wear personal protective equipment (PPE) such as face coverings at all times, and maintain social distance. If local partners do not have access to PPE or hand-washing facilities, AIR will supply the necessary materials for both data enumerators and study participants.

Preferably two and no more than three people will be allowed to be present during survey and key informant interviews (e.g., the interviewer and the respondent and a child if no other caretaker is available).

FGDs will be limited in size and will follow local regulations. Appropriate distance will be maintained between enumerators and participants, and necessary protective materials will be supplied, as described above.

Informed consent will be delivered verbally to avoid an exchange of writing materials between the interviewer and the respondent.

Any data collection activity or enumerator training will be conducted outdoors if needed, as evidence suggests that the risk of spreading COVID-19 is larger indoors than outdoors.

If all of the agreed-upon safety and protection protocols cannot be observed for any reason, in-person data collection will not be permitted to continue. Dalberg supervisors will be primarily responsible for monitoring and enforcing these protocols.

# Annex C – Qualitative Protocols

### FORMATIVE EVALUATION: PART 1 OF DATA COLLECTION

#### Key Informant Interview (KII 1)– UNICEF Kenya (conducted in English)

Time: 45- 60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with staff from UNICEF Kenya under these sectors:

Nutrition Sector

Social Policy Sector

Child Protection Sector

Introduction & Background

I would like to begin our conversation with a few questions related to your position.

Please state your name and position at UNICEF. How long have you held this position?

Relevance

Now I would like to ask about your thoughts on the relevance of the NICHE II programme

How do the objectives of the NICHE II program fit into UNICEF Kenya’s country programme and strategic plan? Note to data collector: Probe for sector-specific policies/priorities based on respondent’s background and as it relates to social protection, nutrition, and child protection sectors.

a. What about UNICEF’s regional and global objectives in social protection, nutrition, and child protection?

b. And the Kenyan Government’s priorities in social protection, nutrition, and child protection?

c. Does the NICHE II program align with donor priorities in Kenya? Please explain

Were you involved in the design of the NICHE I pilot or NICHE II program? If so, could you tell me how gender equality and human rights were considered in the design of the program?

In thinking about the design and inception phase/implementation of NICHE II, does the program consider the needs, roles, and responsibilities of each gender? Please explain.

How are NICHE II program resources targeted towards women and/or other marginalized individuals? Please explain.

How has the targeting and registration process for NICHE II been effective in identifying and registering eligible households? Has this varied by county? Please explain.

How does the program provide support needed to overcome gender biases that may mitigate benefits from the program? Please explain.

What about the local context (and specific challenges related to social protection, nutrition, and child protection)? How were local conditions and needs considered during the design and inception phase of the NICHE II program?

Was the program adapted at all during the inception phase? Please explain

We talked a little about this at first, but could you tell me more about the specific nutrition, social protection, and child protection challenges in the Arid and Semi-Arid Lands (ASAL) counties? How does it vary by county?

Do you think there is widespread understanding of appropriate feeding practices for pregnant women, lactating women, and young children in ASAL counties? Are community healthy volunteers (CHVs) typically well informed about appropriate feeding practices? Please explain.

Are you aware of any widespread parenting practices/beliefs that might pose child protection concerns? Please explain.

Do community-based child protection mechanisms exist in ASAL counties? Does it vary by county/community? Please explain.

What were the main lessons learned from the NICHE I pilot?

Were any of these lessons learned incorporated into the design of NICHE II? Please explain.

At the core of UNICEF’s policy and framework for humanitarian action, there are the CCCs or the Core Commitment for Children. The CCCs promote equality, transparency, responsibility and a results-oriented approach to enable predictable and timely humanitarian action. The CCCs are guided by the United Nation’s Convention on the Rights of the Child (CRC), an international agreement on childhood. To what extent does the NICHE II programme align with the guidelines outlined by the CCC? Please describe.

Are health workers and child protection officers in Kilifi County trained together to provide the integrated nutrition and protection services?

If yes, what types of trainings are available?

Probe for types of trainings:

Community-based advocacy trainings?

Capacity development trainings for Community Health Volunteers, Community Health Workers and Child Protection Officers?

A ToT model?

Positive parenting education training?

Training on promotion of family based care?

If yes, what are the main content areas of the trainings?

If no, how is the integrated aspects of the services from the NICHE II program being implemented?

What types of delivery mechanism are in place to provide integrated nutrition and protections services?

Probe: Establishment of integrated registration system?

Coherence

Can you tell me about other social protection/nutrition/child protection interventions in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties?

Instructions to Data Collector: Limit the question to Social protection interventions if interviewee is a social protection section staff; Limit the question to Nutrition interventions if the interviewee is nutrition section staff; Limit the question to Child protection interventions (which is only carried out in Kilifi county) if interviewee is a child protection section staff.

Probe for intervention type, program name, duration, funder, etc.

Are there complementary programs active in NICHE II counties? Please explain.

Is the NICHE II program leveraging any synergies with other programs? Please describe.

How could the NICHE II program better coordinate with other programs to maximize resources and benefits to vulnerable households?

Does the implementation of the NICHE II programme cause conflicts or competition for time/resources from other programmes? If yes, how so?

During the inception phase for NICHE II, have there been any lessons learned about coordination? Have these varied by county? Please explain.

In thinking about Government of Kenya programs specifically, how could NICHE II better coordinate or strengthen existing government programs in the area of food security, resilience, cash transfer, child protection, and/or nutrition?

Does government collaboration differ by county? If yes, how so?

For health workers and community health workers in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties, what are the main challenges they face in supporting pregnant and lactating women and young children?

Do community health workers in these counties typically have knowledge of appropriate child feeding practices and optimal nutrition practices for pregnant and lactating women ? Please explain.

Probe for challenges in specific areas.

Child Feeding practices

Nutrition for pregnant and lactating women

Common health issues

Community health care system

Food insecurity measures

Hygiene practices

Nutrition

In Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties, what are the main challenges faced by child protection/social protection officers within the social protection landscape?

Probe for challenges in specific areas

protection from violence

abuse

sexual exploitation

neglect

Gender based violence (GBV)

What other programs or services are available to women to support improved nutrition practices? And to promote positive parenting approaches? During the NICHE II inception phase, how have UNICEF and other key stakeholders coordinated with these programs/services?

Sustainability

Does UNICEF have a strategy through NICHE II to ensure that social and child protection and nutrition capacities are developed at both the national and county levels? Please explain.

How (if at all) does the implementation approach for NICHE II foster self-reliance on the part of the Kenyan Government?

Does NICHE II support the Kenyan Government in establishing national processes (strategic plans, policy development, the development of guidelines, information and monitoring systems)? Please explain.

Are you aware of any non-monetary efforts/strategies in place to sustain the NICHE II programme? Probe: Strategies such as incorporating activities of NICHE II into other existing programmes or policies?

Does UNICEF have plans in place to ensure that NICHE implementation is sustained beyond the three-year implementation period without UNICEF’s technical assistance support? Please explain.

Conclusion

What lessons have you learned about implementing the NICHE II programme during the inception phase?

Have interventions under the NICHE II programme been adapted to the COVID-19 crisis? If yes, how?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?

Is there anything else you’d like to tell me about the NICHE II program?

Those are all of my questions. Is there anything else that you would like to add to our conversation? Do you have any questions for me?

Thank you so much for your time and sharing your thoughts.

#### Key Informant Interview (KII 2) – National level Government Stakeholders (conducted in English)

Time: ~45 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents by and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with national-level staff from concerned ministries including:

Ministry of Health (2 Divisions: Nutrition and Community Health Strategy)

Ministry of Labour and Social Protection – Department of Children Services

Ministry of Devolution of Arid and Semi-Arid Lands

National Drought Management Authority

Introduction & Background

I would like to begin our conversation with a few questions related to your position.

Please tell me a bit about your background and responsibilities in your current position at MoH/MoLSP/MoDA & SAL/NDMA.

Note to Data Collector:

Ministry of Health (2 Divisions: Nutrition and Community Health Strategy) = MoH

Ministry of Labour and Social Protection – Department of Children Services = MoLSP

Ministry of Devolution of Arid and Semi-Arid Lands = MoDA & SAL

National Drought Management Authority = NDMA

How long have you held this position?

Could you briefly describe your role and responsibilities with regards to the NICHE II programme?

In your view, what are the biggest poverty-related challenges in Kenya?

[Note to Enumerator, probe for specific challenges based on Ministry/Government Body] Probe: What are the challenges related to social protection, nutrition, and child protection?

Relevance

Now I would like to ask about your thoughts on the relevance of the NICHE II programme

How does the NICHE II programme fit into the MoH/MoLSP/MoDA & SAL/NDMA’s nutrition, social policy and child protection priorities?

Can you tell me a little about [MoH (Nutrition and Community Health Strategy) /MoLSP/MoDA & SAL/NDMA] priorities at the national level in relation to the NICHE II programme?

To what extent do you think the NICHE II fits well with the priorities?

At the national level, what are the main objectives your government body/ministry is hoping to achieve through the NICHE II programme?

What are the main strategic priorities?

From your perspective, did the context/landscape of Arid and Semi-Arid Lands (ASAL) counties of Kitui, West Pokot, Turkana, Marsabit, and Kilifi factor into the design and implementation of NICHE II?

If yes, how so?

What data or information sources have you used to help you make program design/targeting decisions concerning the context, especially the context of nutrition and social/child protection)?

From your perspective, did the contextual social protection, child protection and nutrition challenges present in Arid and Semi-Arid Lands (ASAL) counties in Kenya factor into the design and implementation of NICHE II?

If yes, how so?

At the national level, what are the greatest contextual social and child protection and nutrition challenges that vulnerable households are facing in the country?

Probe: How was the contextual challenges taken into account in the implementation of the NICHE II programme?

Probe: How was the contextual challenges taken into account in assessing the strategic priorities of the NICHE II programme?

What were the main lessons learned from the NICHE I Pilot programme?

Were any of the lessons learned incorporated into the design of NICHE II? Please explain.

What type of monitoring information from the NICHE I pilot was useful to enable you to assess how well the programme was implemented and whether it was reaching the right people? Did you feel that you were receiving all the information you needed or was anything missing?

Probe: Were NICHE II components adapted to meet the needs of different groups, such as mothers of children under 2 years, pregnant women? Please explain.

How were concerns for human rights and gender equality, factored into the design of the NICHE II programme?

To what extent, does the NICHE II programme take into account different roles and responsibilities of men and women?

To what extent, does the NICHE II programme take into account different needs of men and women?

To what extent, does the NICHE II programme help support overcoming gender biases that may mitigate benefits from the program? Please explain.

Do linkages (coordination structures) exist between the nutrition, social policy and child protection sectors of the government at the national level?

[If linkages] What do those linkages look like? And when and how were they established?

Are there any shared information systems or how do you share information between the sectors?

[If linkages] Do you think the current linkages are adequate to meet the needs of the target population of the NICHE II programme? Why do you think that?

[If no linkages] Have there been and plans or attempts to create these linkages?

To what extent were issues of gender, equity, and the rights of people who are marginalized such as with disabilities or different ethnicities considered in the design of the programme? What about in the implementation of the programme?

Probe for specific actions taken to ensure equitable participation.

Gender

Equity

Rights of people who are marginalized

How are you monitoring this? Is there any particular data/monitoring information that helps you track whether the programme is ensuring equitable access and implementation?

How are the integrated aspects of both the nutrition and child protection services through the cash transfer system being implemented?

Are health workers and child protection officers trained together to provide the integrated nutrition and protection services?

If yes, what types of trainings are available?

Probe for types of trainings:

Community-based advocacy trainings?

Capacity development trainings for Community Health Volunteers, Community Health Workers and Child Protection Officers?

A ToT model?

Positive parenting education training?

Training on promotion of family based care?

If yes, what are the main content areas of the trainings?

If no, how is the integrated aspects of the services from the NICHE II program being implemented?

What types of delivery mechanism are in place to provide integrated nutrition and protections services? (For example, do beneficiaries receive both services from nutrition and social protection?)

Probe: Establishment of integrated registration system?

Coherence

At the national level, what are the other initiatives and programmes in the areas of nutrition and social and child protection that your government body/ministry is supporting? Limit question to nutrition for Ministry of Health, limit the question to social and child protection for Ministry of Labour and Social Protection

At the national level, thinking about all the other initiatives and programmes implemented– which aim to meet challenges of nutrition, social policy and child protection, how well does the NICHE II programme fit with these other initiatives? Limit question to nutrition for Ministry of Health, limit the question to social and child protection for Ministry of Labour and Social Protection

How does your government body/Ministry leverage the NICHE II programme with other programmes to maximize resources and benefits to vulnerable households?

Does the implementation of the NICHE II programme cause conflicts or competition for time/resources from other programmes? If yes, how so?

During the inception phase for NICHE II, what (if any) lessons have you learned about coordination with other sectors/programs?

How could the NICHE II program better coordinate with other programs to maximize resources and benefits to vulnerable households?

Probe: How are these programmes sharing data/monitoring systems, if they are?

At the national level, what are the other initiatives and programmes in the areas of food security, resilience, cash transfer, child protection and nutrition that your government body/ministry is supporting?

How could NICHE II better coordinate or strengthen existing government programs in the area of food security, resilience, cash transfer, child protection, and/or nutrition?

Sustainability

And finally, I would like to ask you about the sustainability of the NICHE II Programme in general.

To what extent is the NICHE II programme sustainable in the long run?

How long do you think it will continue, and with what level of support from UNICEF and donors?

What types and levels of support (financial and otherwise) do you think the government and its ministries (MoH, MoLSP/MoDA & SAL/NDMA) would need to provide to ensure sustainability?

Are you aware of any non-monetary efforts/strategies in place to sustain the NICHE II programme?

Probe: Strategies such as incorporating activities of NICHE II into other existing programmes or policies?

To what extent is your Ministry working on guidelines/policies/plans to ensure that the NICHE II program can continue or ensure sustainability?

Probe: To what extent do the plans and strategies foster the GoK’s self -reliance concept?

If UNICEF Kenya funding and TA support were to end in three years, what do you think would happen to the NICHE II programme?

What would be needed to sustain it?

Which aspects of the NICHE II programme do you think will be most difficult to sustain? Why?

Which aspects of the NICHE II programme do you think will be easiest to sustain? Why?

Conclusion

What lessons have you learned about implementing the NICHE II programme?

Has the monitoring system been adequate and generated timely and useful information? 
a. Is there any particular information that you would like to have which is missing from the monitoring system?

Do you have any recommendations for how to improve the NICHE II programme? Please describe.

Have interventions under the NICHE II programme adapted to the COVID-19 crisis? If yes, how?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?

Is there anything else you’d like to tell me about the NICHE II programme or your experience as a key stakeholder of the program?

Those are all of my questions. Is there anything else that you would like to add to our conversation? Do you have any questions for me?

Thank you so much for your time and sharing your thoughts.

#### Key Informant Interview (KII 3)– Funders (FCDO & WB) (conducted in English)

Time: 45- 60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with staff from funders:

Foreign Commonwealth & Development Office (FCDO)

World Bank

Background Information on WB’s role for Data Collector:

World Bank’s role is in financial partnership for KSEIP; they are key informants on availability of government funding for NICHE (since WB’s funding is meant to be complementary to GoK’s as well as conditional to some milestones by GoK), funding operational challenges, sustainability given funding arrangements.

WB is least informed on specific county deprivations in nutrition, social and child protection, gender, human rights issues e.t.c.

FCDO’s involvement/role in NICHE is different from the WB’s, the Bank being the main financial partner. FCDO supports the Hunger Safety Net Program (HSNP).

Introduction & Background

I would like to begin our conversation with a few questions related to your position.

Please state your name and position at [World Bank/FCDO]. How long have you held this position?

How does your organization support the NICHE II program?

In your view, what are the biggest poverty-related challenges in Kenya?

Probe for challenges related to social protection, nutrition, and child protection.

Relevance & Coherence

For World Bank Respondent only. Skip Questions 4 – 10 when interviewing FCDO stakeholder.

What is the World Bank’s vision for NICHE and KSEIP?

Please describe the World Bank’s current vision/goals ten years from now for NICHE and KSEIP.

Do you see this above vision being realized currently in how NICHE II is being implemented?

Do you think the NICHE II program aligns with the World Bank’s priorities in social protection, nutrition, and child protection?

Does the NICHE II program align with other donor/private sector priorities in Kenya? Please explain.

What are the key strengths in the implementation arrangements for NICHE II within KSEIP?

Are there any challenges? If yes, what are the challenges and what are the possible solutions?

The Bank is a critical financial partner to the government for the program, what is working well with the funding arrangements? The setup of NICHE is such that the operational costs of NICHE are to be funded by GoK for GoK personnel, because NICHE is part of KSEIP.

What are the challenges in the current funding set-up for the NICHE II program and in the current funding flow mechanism for the NICHE II program?

How can these challenges be addressed?

The World Bank supports the Government of Kenya substantially through other programs aimed at addressing similar nutrition, child and social protection deprivations as Million Garden Initiative. How could synergies between NICHE and these programs be strengthened?

Apart from the Million Garden Initiative, are there other programs the World Bank is supporting and how could these leverage on NICHE?

What other programs does the World Bank support in the areas of nutrition-sensitive agriculture, early child development?

What are the opportunities in these programs that can be synergized with NICHE?

For FCDO Respondent only. Skip Questions 11-14 when interviewing World Bank stakeholder.

What is the FCDO’s vision for NICHE and the Hunger Safety Net Program under the National Safety Net programs?

Please describe the FCDO’s current vision/goals ten years from now.

Do you see this above vision being realized currently in how NICHE II is being implemented?

What are the key strengths in the implementation arrangements for NICHE II?

Are there any challenges? If yes, what are the challenges and what are the possible solutions?

The FCDO has been a critical development partner for the government for Nutrition as well as the Hunger Safety Net program, what is working well with the funding arrangements?

What are the challenges in the current funding set-up for the NICHE II program and the Hunger Safety Net Program?

How can these challenges be addressed?

Are there other programs in the area of Nutrition apart from NICHE which the FCDO is currently supporting or will be supporting in the near future?

What are the opportunities in these programs that can be synergized with NICHE II?

For both World Bank and FCO Respondent.

Are you aware of any lessons learned from the NICHE I pilot?

Were any of these lessons learned incorporated into the funding mechanism for NICHE II? Please explain.

Do you consider that the NICHE I pilot was adequately funded and the data from NICHE pilot provided appropriate information to guide the funding mechanism for  NICHE II?

Are you aware of other social protection/nutrition/child protection interventions in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties, either funded/implemented by your organization? Probe for intervention type, program name, duration, funder, etc.

Are you aware of other complementary programs being funded by your organisation that are active in NICHE II counties? Please explain.

Sustainability

To what extent do you think the NICHE II programme is sustainable in without UNICEF Kenya’s TA?

How long do you think it will continue, and with what level of support from UNICEF would be needed to ensure sustainability?

What types and levels of support do you think the government and its ministries (MoH, MoLSP/MoDA & SAL/NDMA) would need to provide to ensure sustainability?

To what extent is the World Bank/FCDO working on guidelines/policies/plans/ funding mechanisms to ensure that the NICHE II program can continue or ensure sustainability?

Are you aware of any non-monetary efforts/strategies in place to sustain the NICHE II programme?

Probe: Strategies such as incorporating activities of NICHE II into other existing programmes or policies?

Probe: To what extent do the plans and strategies foster the GoK’s self -reliance concept?

Probe: How do you think the implementation approach for NICHE II is helping to foster self-reliance on the part of the Kenyan Government? Why or why not?

If World Bank’s /FCDO’s funding support were to end in three years, what do you think would happen to the NICHE II programme?

What would be needed to sustain it?

Which aspects of the NICHE II programme do you think will be most difficult to sustain? Why?

Which aspects of the NICHE II programme do you think will be easiest to sustain? Why?

Conclusion

Is there anything else you’d like to tell me about the NICHE II program?

Have funding strategies for these interventions under the NICHE II programme changed due to the COVID-19 crisis?

If yes, how?

If no, how is the program meeting the changing funding needs due to COVID? For example, recurring or prolonged operational costs due to COVID?

Thank respondent for his/her time and conclude the interview.

#### Key Informant Interview (KII 4) – UN Organizations (WFP) (conducted in English)

Time: 45- 60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with staff from other agencies:

World Food Program

Introduction & Background

Please state your name and position at WFP. How long have you held this position?

Could you briefly describe your role and responsibilities with regards to the NICHE II programme?

In your view, what are the biggest poverty-related challenges in Kenya? Probe for challenges related to social protection, nutrition, and child protection.

Relevance

How does the NICHE II programme fit into the WFP’s nutrition, social policy and child protection priorities?

Can you tell me a little about WFP’s priorities at the national level in relation to the NICHE II programme?

How is WFP involved in KSEIP and the overall NSNP?

How can NICHE II synergize with other programs? Especially other KSEIP components?

How can the NICHE II information system be improved?

At the national level, what are the main objectives the WFP is hoping to achieve through the NICHE II programme?

What are the main strategic priorities?

How does the NICHE II align with WFP’s country programme and strategic plan? Probe for sector-specific policies/priorities related to social protection, nutrition, and child protection.

What about WFP’s regional and global objectives in social protection, nutrition, and child protection?

And the Kenyan Government’s priorities in social protection, nutrition, and child protection?

From your perspective, is the NICHE II program appropriate for the local context (and specific challenges related to social protection, nutrition, and child protection) in the Arid and Semi-Arid Lands (ASAL) counties?

Coherence

Can you tell me about other social protection/nutrition/child protection interventions in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties, either funded/implemented by WFP? Probe for intervention type, program name, duration, funder, etc.

Are there complementary programs active in NICHE II counties? Please explain.

How could the NICHE II program enhance coordination with other programs/KSEIP components to maximize resources and benefits to vulnerable households?

In thinking about Government of Kenya programs specifically, how could WFP and its support for the NICHE II better coordinate or strengthen existing government programs in the area of food security, resilience, cash transfer, child protection, and/or nutrition?

For health workers and community health workers in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties, what are the main challenges they face in supporting pregnant and lactating women and young children?

Do community health volunteers in these counties typically have knowledge of appropriate child feeding practices? Please explain.

Probe for challenges in specific areas.

Child Feeding practices

Nutrition for pregnant and lactating women

Common health issues

Food insecurity measures

Hygiene practices

Perceptions of local nutrition challenges

What other programs or services are available to women to support improved nutrition practices? And to promote positive parenting approaches?

Sustainability

What is WFP’s role in ensuring sustainability of the KSIEP components and the NICHE II program?

Do you think the implementation approach for NICHE II is helping to foster self-reliance on the part of the Kenyan Government? Why or why not?

Does NICHE II support the Kenyan Government in establishing national processes (strategic plans, policy development, the development of guidelines)? Please explain.

Are you aware of any non-monetary efforts/strategies in place to sustain the NICHE II programme? Probe: Strategies such as incorporating activities of NICHE II into other existing programmes or policies?

Conclusion

Is there anything else you’d like to tell me about the NICHE II program?

To your knowledge, have interventions under the NICHE II programme been adapted to the COVID-19 crisis? If yes, how?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?

Thank respondent for his/her time and conclude the interview.

#### Key Informant Interview (KII 5) – County-Level Government Stakeholders (Kitui, Kilifi, West Pokot, Turkana, Marsabit) (conducted in English)

Time: 45-60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents by and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with county-level staff from concerned ministries including:

County Ministry of Health and Sanitation (MoHS, County)

County Nutrition Coordinator Officer (NCO, County)

Coordinator from Department of children services , Ministry of Labour and Social Protection (CDCS, County)

Introduction & Background

I would like to begin our conversation with a few questions related to your position.

Please tell me a bit about your background and responsibilities in your current position at (MoHS, County/NCO, County/ CDCS, County).

How long have you held this position?

Could you briefly describe your role and responsibilities with regards to the NICHE II programme?

Relevance

Now I would like to ask about your thoughts on the relevance of the NICHE II programme

How does the NICHE II programme fit into the MoHS, County/NCO, County/ CDCS, County’s nutrition, social policy and child protection priorities?

Can you tell me a little about your Ministry’s priorities at the county level in relation to the NICHE II programme?

To what extent do you think the NICHE II fits well with the priorities?

At the county level, what are the main objectives your ministry is hoping to achieve through the NICHE II programme?

Are there different strategic priorities in your county versus the other four counties?

If yes, what are the main strategic priorities for your county?

From your perspective, did the overall context (poverty rates, geography, demographics, etc) of your county (Kitui, Kilifi, West Pokot, Turkana, Marsabit) factor into the design and implementation of NICHE II?

If yes, how so?

Was a needs assessment conducted? If so, what did it reveal?

What are the greatest needs among vulnerable households in the counties?

[Probe specific respondent to relevant sector] From your perspective, did the contextual social and child protection and nutrition challenges present in your county (Kitui, Kilifi, West Pokot, Turkana, Marsabit) factor into the design and implementation of NICHE II?

If yes, how so?

At the county level, what are the greatest contextual social and child protection and nutrition challenges that vulnerable households are facing in your county?

Probe: How was the contextual challenges taken into account in the implementation of the NICHE II programme?

Probe: How was the contextual challenges taken into account in assessing the strategic priorities of the NICHE II programme?

From your perspective, did the findings and lessons from the NICHE Pilot programme factor into the design and implementation of the NICHE II programme thus far – for instance identification of beneficiaries in both NICHE I and NICHE II?

If yes, how so?

What were the main findings and lessons from the NICHE Pilot programme?

What monitoring data did you collect during the NICHE pilot and how did this influence NICHE II?

Was the monitoring system an add-on, specific to the pilot or did you use existing channels and data that was readily available through established systems?

Can you see ways to improve streamlining of data collection and analysis for monitoring NICHE II?

Were NICHE II components adapted to meet the needs of different groups, such as mothers of children under 2 years, pregnant women, etc.? Please explain.

How were concerns for human rights and gender equality, factored into the design of the NICHE II programme?

To what extent, does the NICHE II programme take into account different roles and responsibilities of men and women?

Probe: What are the main roles and responsibilities of men and women in these counties?

To what extent, does the NICHE II programme take into account different needs of men and women?

To what extent, does the NICHE II programme help support overcoming gender biases?

[For County Nutrition Coordinator and County Coordinator from Department of children services] How can issues of supportive lifestyle and care be addressed in NICHE II? For example, issues of supportive life-style and care include: birth spacing, maternal workload, status of women in household decision making, availability of safe water and sanitation

Do linkages (coordination structures) exist between the nutrition, social policy and child protection sectors of the government at the county level?

[If linkages] What do those linkages look like? And when and how were they established?

[If linkages] What are the strengths in the current in the multi-sectoral coordination set-up in NICHE program?

[If linkages] How is coordination at the county level organized?

How could it better fit in into the existing coordination structures in the county?

[If linkages] Are there any joint information systems or opportunities for joint review of monitoring information?

[If linkages] Do you think the current linkages are adequate to meet the needs of the target population of the NICHE II programme? Why do you think that?

Are there areas regarding multi-sectoral-coordination set-up of NICHE, which could be enhanced?

How could linkages be improved in relation to programme monitoring and use of the information generated?

[If no linkages] Have there been and plans or attempts to create these linkages?

[If no linkages] Are there plans in place for capacity building for better coordination?

What are the strengths in the current NICHE II program design and implementation (service delivery) approach of NICHE II program?

Are there any challenges? If yes, what are the challenges and what are the possible solutions?

Are there areas regarding NICHE II program design and implementation (service delivery) approach-  which could be enhanced?

How is funding of NICHE activities arranged at your county level?

Is there involvement of all sectors, or this is done by one sector?

How is planning of NICHE activities done at the county level?

Is there involvement of all sectors? Or this is done by one sector?

[For County Ministry of Health only] Your county ministry signed the MoU on NICHE with National Ministry of Labour and Social Protection, and National Ministry of Health and the National Drought Management Authority. Can you describe what the county leadership experience with NICHE implementation has been like so far?

How are the integrated aspects of both the nutrition and child protection services through the cash transfer system being implemented?

Are health workers and child protection officers trained together to provide the integrated nutrition and protection services?

If yes, what types of trainings are available?

Probe for types of trainings:

Community-based advocacy trainings?

Capacity development trainings for Community Health Volunteers, Community Health Workers and Child Protection Officers?

A ToT model?

Positive parenting education training?

Training on promotion of family based care?

If yes, what are the main content areas of the trainings?

If no, how is the integrated aspects of the services from the NICHE II program being implemented?

What types of delivery mechanism are in place to provide integrated nutrition and protections services?

Probe: Establishment of integrated registration system?

Are there any plans in NICHE II to address issues of gender, equity, and the rights of people who are marginalized such as with disabilities or different ethnicities considered in the design of the programme? What about in the implementation of the programme?

Probe for specific actions taken to ensure equitable participation.

Gender

Equity

Rights of people who are marginalized

How is your engagement and access to services monitored?

Coherence

At the county level, what are the other initiatives and programmes in the areas of nutrition and social and child protection that your county ministry is supporting?

At the county level, thinking about all the other initiatives and programmes implemented– which aim to meet challenges of nutrition, social policy and child protection, how well does the NICHE II programme fit with these other initiatives?

How does your county ministry leverage the NICHE II programme with other programmes to maximize resources and benefits to vulnerable households?

Does the implementation of the NICHE II programme cause conflicts or competition for time/resources from other programmes?

How could the NICHE II program better coordinate with other programs to maximize resources and benefits to vulnerable households? Please provide examples of other programs.

In terms of monitoring, are there streamlined data collection systems or joint repositories for data collection and analysis? If so, please describe.

At the county level, what are the other initiatives and programmes in the areas of agriculture, food security, resilience, cash transfer, child protection and nutrition that your county ministry is supporting?

What are the opportunities in these initiatives or programs to integrate with NICHE II?

Does NICHE II rely on existing structures/mechanisms in your county? If yes, which ones? Please explain.

Sustainability

And finally, I would like to ask you about the sustainability of the NICHE Programme in general.

If UNICEF Kenya technical assistance and funding were to end in three years, what do you think would happen to the NICHE II programme?

What would be needed to sustain it at the county level?

What types and levels of support do you think your county ministry would need to provide to ensure sustainability?

Which aspects of the NICHE II programme do you think will be most difficult to sustain? Why?

Which aspects of the NICHE II programme do you think will be easiest to sustain? Why?

The World Bank is funding the NICHE II program to a large extent. If World Bank funding were to end, would the county be able to allocate financial resources to ensure that program service delivery could carry on beyond its funded period?

If yes, to what extent? For how long?

[For County Ministry of Health only] The NICHE II program is heavily reliant on Community Health Volunteers. What is the county’s legal position on CHVs?

Does the county have any plans to enact a bill on CHVs? If yes, when and what does the bill entail?

What is the county’s stand on renumeration of CHVs?

Are you aware of any non-monetary efforts/strategies in place to sustain the NICHE II programme?

Probe: Strategies such as incorporating activities of NICHE II into other existing programmes or policies?

At the county level, to what extent is your county Ministry working on guidelines/policies/plans to ensure that the NICHE II program can continue or ensure sustainability?

How well is the monitoring system incorporated into established monitoring systems and are there any aspects that are unsustainable in the long run?

At the county level, to what extent are some of the NICHE activities included in the county budgets? If not, are there any plans to look into this?

Conclusion

What lessons have you learned about implementing the NICHE II programme?

Do you have any recommendations for how to improve the NICHE II programme? Please describe.

Have interventions under the NICHE II programme adapted to the COVID-19 crisis? If yes, how?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?

Is there anything else you would like to tell me about the NICHE II programme or your experience as a key stakeholder of the programme?

Those are all of my questions. Is there anything else that you would like to add to our conversation? Do you have any questions for me?

Thank you so much for your time and sharing your thoughts.

#### Key Informant Interview (KII 6) – Kitui County Implementing Partners (conducted in English)

Time: 45-60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents by and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with county-level staff from implementing partners of the NICHE II programme:

Three NGOs providing nutrition counselling:

World Vision

Concern Worldwide

Action Against Hunger

Introduction & Background

I would like to begin our conversation with a few questions related to your position.

Please tell me a bit about your background and responsibilities in your current position at: World Vision

Concern Worldwide

Action Against Hunger

How long have you held this position?

Could you briefly describe your role and responsibilities to support the implementation of the NICHE II programme in Kitui?

To which Ministries does your organisation provide Technical Assistance (TA) regarding [Nutrition Counselling, Child Protection Strategy, SOCIAL BEHAVIOUR COMMUNICATION CHANGE (SBCC) strategy] as they relate to NICHE II?

Probe: How is your organisation involved in supporting NICHE II program?

Relevance

Now I would like to ask about your thoughts on the relevance of the NICHE II programme

In your view, what are the biggest poverty-related challenges in Kitui County, Kenya?

Probe: What are the challenges related to social protection, nutrition, and child protection?

From your perspective, did the context of Kitui County factor into the activities your organisation will conduct/is conducting to support the implementation of NICHE II programme? Probe: Specifically, in relation to the areas of nutrition, social policy and child protection?

If yes, how so?

From your perspective, did findings and lessons learned from the NICHE I Pilot programme in Kitui county influence how you’re supporting the implementation of NICHE II programme?

If yes, how so?

Probe: Was the implementation of NICHE II components adapted to meet the needs of different groups, such as mothers of children under 2 years, pregnant women? Please explain.

What kinds of human and material resources are needed to support the implementation the NICHE II programme?

Probe: Did your organisation receive any technical assistance from UNICEF or another organisation to support the implementation of NICHE II?

If yes, what type and from whom?

To what extent do you think there buy-in from the Ministry/Government (county/national) entities on the implementation of the NICHE II programme?

Were there any variations in terms of how receptive the county ministries (health, department of child services, nutrition sector) were to the activities related to the implementation of the NICHE II program? Please describe.

What do you think are the barriers to buy -in? Please describe.

What do you think are the facilitators to buy -in? Please describe.

What are the strengths in the current support your organisation is providing for the implementation approach of NICHE in service delivery?

Are there any challenges? If yes, what are the challenges and what are the possible solutions?

Are there areas regarding NICHE II program implementation (service delivery) approach-  which could be enhanced?

How are the integrated aspects of both the nutrition and child protection services through the cash transfer system being implemented in Kitui county by your organisation? [Skip if organisation is not involved in cash transfer system]

Are health workers and child protection officers trained together to provide the integrated nutrition and protection services?

If yes, what types of trainings are available?

Probe for types of trainings:

Community-based advocacy trainings?

Capacity development trainings for Community Health Volunteers, Community Health Workers and Child Protection Officers?

A ToT model?

Positive parenting education training?

Training on promotion of family based care?

If yes, what are the main content areas of the trainings?

If no, how is the integrated aspects of the services from the NICHE II program being implemented?

What types of delivery mechanism are in place to provide integrated nutrition and protections services?

Probe: Establishment of integrated registration system?

To what extent are issues of gender, equity, and the rights of people who are marginalized such as with disabilities or different ethnicities considered in the implementation of the NICHE II programme by your organisation? Probe for specific actions taken to ensure equitable participation.

Gender

Equity

Rights of people who are marginalized

How do you monitor engagement of these groups in the programme and assess whether they are accessing the services equitably?

From your perspective, in communities where the NICHE II programme is being delivered, is it meeting nutrition, social policy and child protection needs?

If yes, how so?

Which data do you use to monitor this?

If no, why not? Please describe.

Coherence

At the county level, are there other initiatives or programmes in the areas of nutrition and social and child protection that your organisation is supporting? Please describe.

What are the opportunities in these initiatives or programs to integrate with NICHE II?

At the county level, thinking about all the other initiatives and programmes implemented to meet challenges of nutrition, social policy and child protection, how well does the NICHE II programme fit with these other initiatives?

Does your organisation leverage (or plan to leverage) of its support of the NICHE II programme with other similar/complementary programmes to maximize resources? If yes, how so?

Are monitoring and information systems aligned across programmes? If not, could this be improved?

Do the above activities to support the planned implementation of the NICHE II programme cause conflicts or competition for time/resources from other programmes in your organisation? Please explain.

At the county level, what are the other initiatives and programmes in the areas of food security, resilience, cash transfer, child protection and nutrition that your organisation is supporting?

How difficult or easy is it to collaborate with ministries at the county level? Please describe.

Sustainability

And finally, I would like to ask you about the sustainability of the NICHE Programme in general.

In your perspective, to what extent do you think the NICHE II programme is sustainable in the long run?

How long do you think it will continue, and with what level of support from UNICEF Kenya and donors?

Given that health sector within the GoK is decentralized and budgeting for health activities is undertaken at the county level, to what extent are some of the NICHE activities included in the county health ministry budgets?

Can the existing level of M&E of the programme be sustained? If you think this would be challenging, which are the critical components of the system that you think should be prioritized? If these are not already integrated into government systems, how can they be integrated?

Are you aware of any non-monetary efforts/strategies in place to sustain the implementation of the NICHE II programme?

Probe: Are there strategies that your organisation has incorporated or has plans to incorporate activities of NICHE II into other existing programmes or policies?

If UNICEF Kenya funding and TA support were to end, what do you think would happen to the implementation of the NICHE II programme?

What would be needed for your organisation to sustain it?

Probe: Would you need funding/TA support/partnership

Which aspects of the implementation of the NICHE II programme do you think will be most difficult to sustain? Why?

Probe: What are the main barriers to keeping the NICHE II programme running?

Which aspects of the implementation of the NICHE II programme do you think will be easiest to sustain over the long term? Why?

Probe: What might help make it possible to continue delivering the NICHE II programme?

Conclusion

What lessons have you learned about supporting the planned implementation of the NICHE II programme?

Do you have any recommendations for how to improve the design and implementation of the NICHE II programme? Please describe.

Have activities to support the (planned) implementation of the NICHE II programme adapted to the COVID-19 crisis? If yes, how?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?

Is there anything else you’d like to tell me about the NICHE II programme or your experience as a key implementer of the programme?

Those are all of my questions. Is there anything else that you would like to add to our conversation? Do you have any questions for me?

Thank you so much for your time and sharing your thoughts.

### RQA: PART 2 OF DATA COLLECTION

#### Key Informant Interview (KII 7) – Sub County_Level Government Stakeholders (conducted in English)

Time: 45-60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents by and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with county-level staff from concerned ministries including:

Sub-County Coordinator for Dept. of Child Services (Sub-County DCS)

Sub-County Nutrition Coordinator Officer, Ministry of Health (Sub County NCO)

Introduction & Background

I would like to begin our conversation with a few questions related to your position.

Please tell me a bit about your background and responsibilities in your current position at as Sub-County level Nutrition Coordinator Officer, Ministry of Health (Sub County NCO) and Sub-County Coordinator for Dept. of Child Services (Sub-County DCS)

How long have you held this position?

Could you briefly describe your role and responsibilities with regards to the NICHE II programme?

In your view, what are the biggest poverty-related challenges in Kilifi and TURKANA counties?

[To ask Sub-County level Nutrition Coordinator Officer] [Ask only Kilifi sub counties to representative from Kilifi and about Turkana counties to representative from Turkana] Can you describe the nutrition and health landscape or challenges in the sub counties of Ganze and Kaloleni in Kilifi / Turkana Central and Turkana South in Turkana? Probe for specific areas.

Child Feeding practices

Nutrition for pregnant and lactating women

Common health issues

Food insecurity measures

Perceptions of local nutrition challenges

Do you think the landscape or challenges differ based on whether it is an urban and rural village? If so, please describe.

[To ask Sub-County Coordinator for Dept. of Child Services] [Ask only Kilifi sub counties as to representative from Kilifi and about Turkana counties to representative from Turkana] Can you describe the social and child protection landscape or challenges in Kilifi and Turkana sub-counties? Probe for specific area, especially for Kilifi county.

Protection from violence

abuse

sexual exploitation

neglect

Gender based violence (GBV)

Do you think the landscape or challenges differ based on whether it is an urban and rural village? If so, please describe.

Relevance

Now I would like to ask about your thoughts on the relevance of the NICHE II programme

[To ask Sub-County level Nutrition Coordinator Officer] How does the Intensive Nutrition Counselling and the Baby Friendly Initiative (BFCI) components of the MoH’s community health strategy fit into the sub-county level MoH’s nutrition priorities?

How does the BFCI components integrate with the NICHE II program?

To what extent do you think the Nutrition SOCIAL BEHAVIOUR COMMUNICATION CHANGE (SBCC) component of NICHE II fits well with the priorities of the sub-county level ministry?

[To ask Sub-County Coordinator for Dept. of Child Services] How does the counselling on child protection components of the NICHE II programme fit into the Dept. of Child Services’ social and child protection priorities in Kilifi sub-counties?

To what extent do you think the Child Protection SOCIAL BEHAVIOUR COMMUNICATION CHANGE (SBCC) component of NICHE II fits well with the priorities of the sub-county level Ministry?

[To ask Sub-County level Nutrition Coordinator Officer] We understand that the BFCI component is a  community-initiative to improve Infant and Young Child Feeding (IYCF) practices, and is used to promote breastfeeding, complementary feeding, maternal nutrition, water, sanitation, and hygiene (WASH); and early childhood development (ECD).

To what extent do you think these activities are relevant to the needs of the community?

Are there other community/village needs that are not being met by the current NICHE II programme? If so, what are they? Please describe.

Probe: What other services and opportunities are available to women to improve nutrition practices for their household?

[To ask Sub-County Coordinator for Dept. of Child Services] We understand that the counselling component on child protection (which is only implemented in the Kilifi county) and the Child Protection SOCIAL BEHAVIOUR COMMUNICATION CHANGE (SBCC) element are being implemented to protect children from violence, abuse, exploitation and neglect. To what extent do you think these activities are relevant to the needs of the community and children in the community?

Are there other needs that are not being met by the current NICHE II programme? If so, what are they? Please describe.

Probe: Protection from sexual exploitation and violence against children

Questions pertaining to implementation (which may be at beginning stages; questions may be on recommendations for implementation:

What are the existing community platforms (chamas) in the communities within your sub -counties in Kilifi and Turkana?

What are the types of operations?

How can these be utilized for NICHE implementation?

Are there platforms which bring together communities and health care providers to engage in dialogue? And platforms for the community to provide feedback?

Probe: Are there any health facility committees in existence? If yes, what are they and are they functional?

What are the informal and formal social protection systems present in your sub-counties?

Thinking about your sub-counties that you represent, are there food markets?

If yes, do the communities across the villages have access to these food markets?

i. If yes, what types of foods do community members purchase?

Who are the community gate keepers (village elders, leader of households)?

How can they be best engaged in NICHE II and its implementation?

To what extent were issues of gender, equity, and the rights of people who are marginalized such as with disabilities or different ethnicities considered in the design and implementation of NICHE II in order to meet the needs of the local community? Probe for specific actions taken to ensure equitable participation.

Gender

Equity

Rights of people who are marginalized

Rights of people with disabilities

To what extent, does the NICHE II programme take into account different roles and responsibilities of men and women in the local community?

To what extent, does the NICHE II programme take into account different needs of men and women in the local community?

To what extent, does the NICHE II programme take into account different needs of and girls and boys in the local community?

To what extent, does the NICHE II programme help support overcoming gender biases?

We understand that at the national level, there are coordination structures between the NICHE II programme components (between parenting component, cash transfer and nutrition counselling). At the sub- county levels, do these linkages/ coordination structures exist between the nutrition, social policy and child protection sectors?

[If yes] What do those linkages look like? And when and how were they established?

[If yes] What are the strengths in the current linkages/coordination structure of NICHE program in your sub- county?

[If yes] How is coordination at the sub- county level organized?

How could it better fit in into the existing coordination structures in the sub -county or county?

[If yes] Do you think the current linkages are adequate to meet the needs of the community and their challenges with regards to nutrition, and child protection? Why do you think that?

Are there areas regarding these linkages/coordination structures of NICHE, which could be enhanced?

[If no] Have there been and plans or attempts to create these linkages?

[If no] Are there plans in place for capacity building for better coordination?

What type of monitoring information is shared and discussed between the different components/sectors? How do you share information?

What are the strengths in the current NICHE II program design and implementation (service delivery) approach of NICHE II program?

Are there any challenges? If yes, what are the challenges and what are the possible solutions?

Are there areas of NICHE II program design and implementation (service delivery) which could be enhanced?

How is funding of NICHE activities arranged at your SUB county level?

Is there involvement of all sectors, or this is done by one sector?

How is planning of NICHE activities done at the sub- county level?

Is there involvement of all sectors? Or this is done by one sector?

How are the integrated aspects of both the nutrition and child protection services through the cash transfer system being implemented?

Are health workers and child protection officers trained together to provide the integrated nutrition and protection services?

If yes, what types of trainings are available?

Probe for types of trainings:

Community-based advocacy trainings?

Capacity development trainings for Community Health Volunteers, Community Health Workers and Child Protection Officers?

A ToT model?

Positive parenting education training?

Training on promotion of family based care?

If yes, what are the main content areas of the trainings?

If no, how is the integrated aspects of the services from the NICHE II program being implemented?

What types of delivery mechanism are in place to provide integrated nutrition and protections services?

Probe: Establishment of integrated registration system?

Coherence

At the village/county level, what are the other initiatives and programmes in the areas of [nutrition/Health] and [social and child protection] that your ministry is supporting?

What other services and opportunities are available to women to improve nutrition practices for their household?

Probe: Are there are other components of the NICHE II programme that is being implemented to meet nutrition challenges? Please describe.

What other services and opportunities are available to caregivers to improve child protection practices for their household?

Probe: Are there are other components of the NICHE II programme that is being implemented to meet social and child protection challenges, such as protection from violence, abuse, exploitation and neglect? Please describe.

Thinking about the other initiatives and programmes in the areas of [nutrition/Health] and [social and child protection] that your Ministry is supporting,

How does your Ministry leverage the NICHE II programme with these other programmes or initiatives to maximize resources?

Are there shared information/monitoring systems across programmes/initiatives? Is there scope for improving alignment of existing systems?

Does the implementation of the NICHE II programme cause conflicts or competition for time/resources from other programmes?

At the village/county level, what are the other initiatives and programmes in the areas of food security, resilience, cash transfer that ministry is supporting?

How could NICHE II better coordinate or strengthen existing government programs in the area of food security, resilience, cash transfer, child protection, and/or nutrition?

Sustainability

And finally, I would like to ask you about the sustainability of the NICHE Programme in general.

To what extent is the NICHE II programme sustainable in the long run at the village level?

How long do you think it will continue, and with what level of support from UNICEF and donors?

Are you aware of any non-monetary efforts/strategies in place to sustain the NICHE II programme?

Probe: Strategies such as incorporating activities of NICHE II into other existing programmes or policies?

If UNICEF Kenya funding and TA support were to end in three years, what do you think would happen to the NICHE II programme?

What would be needed to sustain it at the village/county level?

Which aspects of the NICHE II programme do you think will be most difficult to sustain? Why?

Which aspects of the NICHE II programme do you think will be easiest to sustain? Why?

Probe: Do you think it will be possible to continue collecting the same level of monitoring information? If not, which do you think are the critical indicators/data that need to continue being collected? Which information is most useful for you and helps you determine appropriateness and effectiveness of the programme?

Conclusion

What lessons have you learned about implementing the NICHE II programme?

Do you have any recommendations for how to improve the NICHE II programme? Please describe.

Have interventions under the NICHE II programme adapted to the COVID-19 crisis? If yes, how?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?

Is there anything else you’d like to tell me about the NICHE II programme or your experience as a key stakeholder of the programme?

Those are all of my questions. Is there anything else that you would like to add to our conversation? Do you have any questions for me?

Thank you so much for your time and sharing your thoughts.

#### Key Informant Interview (KII 8) Village level Community Health Volunteers  (CHVs) (conducted in Swahili)

Time: 45- 60 minutes

Instructions Prior to Beginning the Interview: Please introduce yourself to the respondents and collect consent as provided below.

Collect Informed Consent Form and Obtain Participant’s Consent prior to conducting interview.

Respondent Types: Please use this protocol for interviews with:

Community Health Volunteers

KII Participant Verbal Consent Form

Hello.  My name is __________________ from Dalberg Research/American Institutes for Research. We are conducting a study of the Nutrition Improvements through Cash and Health Education (NICHE) II program. The purpose of this discussion is to obtain more in-depth information about your experience with or knowledge of the NICHE program. The answers provided will help UNICEF Kenya and its partners and where NICHE II services can be improved to better support families.

Halo. Jina langu ni __________________ kutoka Utafiti wa Dalberg / Taasisi za Utafiti za Amerika. Tunafanya utafiti wa Maboresho ya Lishe kupitia mpango wa Fedha na masomo ya Afya (NICHE) II. Kusudi la majadiliano haya ni kupata habari za kina zaidi juu ya uzoefu wako na au ujuzi wa programu ya NICHE. Majibu yaliyotolewa yatasaidia UNICEF Kenya na washirika wake na ambapo huduma za NICHE II zinaweza kuboreshwa ili kusaidia familia bora.

Your name will be kept private and separate from the evaluation. Only AIR and researchers working with AIR will have access to your name and the details of your results, and this will only be used for follow-up and directly related research purposes. All information that is collected in this study will be treated confidentially. While aggregated results will be made available, no individuals will be identified in any report of the results of the study. There is minimal risk involved in the assessment. You also do not have to answer any questions you do not want to answer. Everything you say will be kept confidential. You may indicate at any time if you do not want to be quoted.

Jina lako litahifadhiwa kibinafsi na tofauti na tathmini. AIR ​​tu na watafiti wanaofanya kazi na HEWA ndio watapata jina lako na maelezo ya matokeo yako, na hii itatumika tu kwa ufuatiliaji na malengo ya utafiti yanayohusiana moja kwa moja. Habari yote ambayo imekusanywa katika utafiti huu itashughulikiwa kwa siri. Wakati matokeo ya jumla yatapatikana, hakuna watu watakaotambuliwa katika ripoti yoyote ya matokeo ya utafiti. Kuna hatari ndogo inayohusika katika tathmini. Pia sio lazima ujibu maswali yoyote ambayo hutaki kujibu. Kila kitu unachosema kitahifadhiwa kwa siri. Unaweza kuonyesha wakati wowote ikiwa hautaki kunukuliwa.

Participation in this discussion is voluntary, and any individual may withdraw at any time. Today’s session may take up to 1 hour of your time. For reference and to clarify notes, we would like to record the session. You may request that we stop recording at any point during the interview. The recording will be saved on a secure computer network, and no one outside of our research team will have access to the recording. If you would like us to turn off the recorder at any point, you may say so.

Kushiriki katika mjadala huu ni kwa hiari, na mtu yeyote anaweza kujitoa wakati wowote. Kipindi cha leo kinaweza kuchukua hadi saa 1 ya wakati wako. Kwa kumbukumbu na kufafanua maelezo, tungependa kurekodi kikao. Unaweza kuomba tuache kurekodi wakati wowote wakati wa mahojiano. Kurekodi kutahifadhiwa kwenye mtandao salama wa kompyuta, na hakuna mtu yeyote nje ya timu yetu ya utafiti atakayeweza kurekodi. Ikiwa ungependa tuzime kinasa sauti wakati wowote, unaweza kusema hivyo.

Do you agree to participate in this interview?

Je! Unakubali kushiriki katika mahojiano haya?

Signature of Enumerator: _______________________________ Date: ________________

Enumerator: Sign above to witness the verbal consent of the participant. Keep one copy for the PIs records and leave the second copy with the participant.

Saini ya Mwandishi: _______________________________ Tarehe: ________________

Mtumiaji: Saini hapo juu kushuhudia idhini ya mdomo ya mshiriki. Weka nakala moja kwa kumbukumbu za PIs na acha nakala ya pili na mshiriki.

This research is funded by UNICEF Kenya (the Sponsors). This means that the research team is being paid by the Sponsors for doing the study. If you have questions about this study, you may contact TURKANA at Dalberg Research. If you have questions about your rights, you may reach out to the TURKANA LOCAL CONTACT or the American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

Utafiti huu unafadhiliwa na UNICEF Kenya (Wadhamini). Hii inamaanisha kuwa timu ya utafiti inalipwa na Wadhamini kwa kufanya utafiti. Ikiwa una maswali juu ya utafiti huu, unaweza kuwasiliana na TURKANA katika Utafiti wa Dalberg. Ikiwa una maswali juu ya haki zako, unaweza kuwasiliana na MAWASILIANO YA MTAA wa TURKANA au Taasisi za Amerika za Bodi ya Ukaguzi wa Taasisi za Utafiti (Simu: + 1 2024035542).

Introduction & Background

I would like to begin our conversation with a few questions related to your position. Ningependa kuanza mazungumzo yetu na maswali machache yanayohusiana na msimamo wako

Please tell me a bit about your background and responsibilities in your current position.

Tafadhali niambie kidogo juu ya historia yako na majukumu yako katika nafasi yako ya sasa.

How long have you held this position?  Umeshikilia nafasi hii kwa muda gani?

Could you briefly describe your role and responsibilities with regards to the NICHE II programme?  Je! Unaweza kuelezea kwa kifupi jukumu na majukumu yako kwa mpango wa NICHE II?

Probe: Are you associated with the Intensive Nutrition Counselling and the Baby Friendly Initiative (BFCI) components?  Ulizia: Je! Unahusishwa na Ushauri Nasaha wa Lishe na Vipengele vya Mpango wa Urafiki wa Watoto (BFCI)?

Probe: Are you associated with counselling on child protection component? Ulizia: Je! Unahusishwa na ushauri juu ya sehemu ya ulinzi wa watoto?

What are your reporting responsibilities: what information do you have to collect and record? How do you report and to who? What is the frequency of that reporting? Je! Majukumu yako ya kuripoti ni yapi: una habari gani ya kukusanya na kurekodi? Je! Unaripotije na kwa nani? Je! Ni mzunguko gani wa ripoti hiyo?

Do you receive feedback after you have submitted your reports? Je! unapokea maoni/majibu baada ya kuwasilisha ripoti zako?

In your view, what are the biggest poverty-related challenges in Kilifi and TURKANA sub-counties or within your local communities?? Kwa maoni yako, ni changamoto zipi kubwa zinazohusiana na umasikini katika kaunti za Kilifi na TURKANA?

Can you describe the nutrition and health landscape or challenges in Kilifi and TURKANA sub-counties or within your local communities? Probe for specific areas. Je! Unaweza kuelezea mazingira ya lishe na afya au changamoto katika kaunti za Kilifi na TURKANA? Ulizia kuhusu.

Feeding practices            Njia za kulisha

Common health issues     Maswala ya kawaida ya kiafya

Food insecurity measures     Hatua za uhaba wa chakula

Hygiene practices                 Kujizoesha usafi

Perceptions of local nutrition challenges       Mitazamo ya changamoto za lishe

Do you think the landscape or challenges differ based on whether it is an urban and rural village? If so, please describe.  Je! Unafikiri mandhari au changamoto zinatofautiana kulingana na ikiwa ni kijiji cha mijini na vijijini? Ikiwa ndivyo, tafadhali eleza.

Can you describe the social protection landscape or challenges in Kilifi and TURKANA counties? Probe for specific areas Je! Unaweza kuelezea mazingira ya kinga ya jamii au changamoto katika kaunti za Kilifi na TURKANA ? Ulizia kuhusu

protection from violence      kinga dhidi ya vurugu

abuse                                     unyanyasaji

sexual exploitation               unyanyasaji wa kijinsia

neglect                                  kupuuzwa

Gender based violence (GBV) Ukatili wa kijinsia

Do you think the landscape or challenges differ based on whether it is an urban and rural village? If so, please describe.  Je! Unafikiri mandhari au changamoto zinatofautiana kulingana na ikiwa ni kijiji cha mijini na vijijini? Ikiwa ndivyo, tafadhali eleza.

Relevance

Now I would like to ask about your thoughts on the relevance of the NICHE II programme

Sasa ningependa kuuliza maoni yako juu ya umuhimu wa mpango wa NICHE II

We understand that the BFCI component is a community-initiative to improve Infant and Young Child Feeding (IYCF) practices, and is used to promote breastfeeding, complementary feeding, maternal nutrition, water, sanitation, and hygiene (WASH); and early childhood development (ECD).  Tunaelewa kuwa sehemu ya BFCI ni mpango wa jamii wa kuboresha mazoea ya Kulisha watoto wachanga na watoto wachanga (IYCF), na hutumiwa kukuza unyonyeshaji, lishe ya ziada, lishe ya mama, maji, usafi wa mazingira, na usafi (WASH); na ukuaji wa watoto wa mapema (ECD).

To what extent do you think these activities are relevant to the needs of the community? Je! Unafikiri shughuli hizi zinahusiana kwa kiwango gani na mahitaji ya jamii?

Are there other community/village needs that are not being met by the current NICHE II programme? If so, what are they? Please describe.  Je! Kuna mahitaji mengine ya jamii / kijiji ambayo hayajafikiwa na mpango wa sasa wa NICHE II? Ikiwa ni hivyo, ni nini? Tafadhali eleza.

Probe: What other services and opportunities are available to women to improve nutrition practices for their household?  Ulizia: Je! Ni huduma gani zingine na fursa zinapatikana kwa wanawake kuboresha mazoea ya lishe kwa kaya zao?

We understand that the counselling component on child protection (which is only implemented in the Kilifi county) and the Child Protection SOCIAL BEHAVIOUR COMMUNICATION CHANGE (SBCC) element are being implemented to protect children from violence, abuse, exploitation, and neglect. To what extent do you think these activities are relevant to the needs of the community and children in the community?  Tunaelewa kuwa sehemu ya ushauri juu ya ulinzi wa watoto (ambayo inatekelezwa tu katika kaunti ya Kilifi) na kipengele cha Ulinzi wa Mtoto SOCIAL BEHAVIOUR COMMUNICATION CHANGE (SBCC) kinatekelezwa kulinda watoto dhidi ya unyanyasaji, unyanyasaji, unyonyaji na kutelekezwa. Je! Unafikiri shughuli hizi zinahusiana kwa kiwango gani na mahitaji ya jamii na watoto katika jamii?

Are there other needs that are not being met by the current NICHE II programme? If so, what are they? Please describe.  Je! Kuna mahitaji mengine ambayo hayajafikiwa na mpango wa sasa wa NICHE II? Ikiwa ni hivyo, ni nini? Tafadhali eleza.

Probe: Protection from sexual exploitation and violence against children Ulizia: Ulinzi kutoka kwa unyonyaji wa kijinsia na ukatili dhidi ya watoto

How are the integrated aspects of both the nutrition and child protection services through the cash transfer system being implemented?  Je! Ni vipi vipengele vilivyojumuishwa vya huduma za lishe na ulinzi wa watoto kupitia mfumo wa uhamishaji wa fedha unatekelezwa?

Are health workers and child protection officers trained together to provide the integrated nutrition and protection services? Je! Wafanyikazi wa afya na maafisa wa ulinzi wa watoto wamefundishwa pamoja ili kutoa huduma za lishe na ulinzi zilizojumuishwa?

If yes, what types of trainings are available?  Ikiwa ndio, ni aina gani za mafunzo zinapatikana?

Probe for types of trainings: Ulizia kuhusu aina za mafunzo

Community-based advocacy trainings? Mafunzo ya kitetezi ya jamii

Capacity development trainings for Community Health Volunteers, Community Health Workers and Child Protection Officers Mafunzo ya kuwawezesha wahudumu wa afya wa jamii, wahudumu wa afya na ma afisa wa kutoa huduma ya ulinzi wa watoto

A ToT model mfumo wa kuwafunza waalimu wa waalimu

Positive parenting education training? Masomo juu ya mbinu bora za malezi

Training on promotion of family-based care. Mafunzo kuhusiana na matunzo ya familia

If yes, what are the main content areas of the trainings?  Iwapo ndio, ni zipi mada zinazogusiwa kwenye mafunzo haya?

If no, how is the integrated aspects of the services from the NICHE II program being implemented?   Ikiwa hapana, ni vipi vipengele vilivyojumuishwa vya huduma kutoka kwa mpango wa NICHE II unatekelezwa?

What types of delivery mechanism are in place to provide integrated nutrition and protections services? Ni aina gani za utaratibu wa kujifungua uliopo ili kutoa huduma za lishe na ulinzi jumuishi?

Probe: Establishment of integrated registration system?  Ulizia: Uanzishwaji wa mfumo jumuishi wa usajili

Coherence

Did you receive any training from the government or another agency with regards to nutrition/child protection counselling and home visits? Je! Ulipata mafunzo yoyote kutoka kwa serikali au wakala mwingine kuhusu lishe / ushauri wa ulinzi wa watoto na ziara za nyumbani?

If yes, can you describe the trainings briefly?  Ikiwa ndio, unaweza kuelezea mafunzo kwa muda mfupi?

If yes, how relevant or adequate do you think the trainings were?  Ikiwa ndio, unafikiri mafunzo yalikuwa muhimu au ya kutosha?

Do you have any recommendations?  Una mapendekezo yoyote?

Probe for trainings on different types of topics/activities:  uliza juu  ya mafunzo aina za mada / shughuli:

Optimal hygiene     Usafi bora

Health seeking        Kutafuta afya

Feeding practices for young children as well as pregnant and lactating women          Mila ya kulisha watoto wadogo na pia wajawazito na wanaonyonyesha

community-based counselling       ushauri wa kijamii

ways to support mother-to-mother support groups and other community groups                                         Njia za kusaidia vikundi vya msaada kutoka kwa mama hadi mama na vikundi vingine vya jamii.

To what extent do you think the activities you have been trained to provide to the community members take into account the issues of gender, equity, and the rights of people who are marginalized such as with disabilities or different ethnicities? Probe for specific areas  Je! Unafikiria shughuli ambazo umepewa mafunzo kwa wanajamii huzingatia maswala ya jinsia, usawa, na haki za watu waliotengwa kama vile walemavu au makabila tofauti? Ulizia mambo yafuatayo

Gender		Jinsia

Equity		Usawa

Rights of people who are marginalized such as older people      Haki za watu ambao wametengwa kama vile wazee

Rights of people with disabilities 		Haki za walemavu

To what extent, does the training and NICHE II programme take into account different roles and responsibilities of men and women in the local community?  Je! Kwa kiwango gani, mafunzo na mpango wa NICHE II huzingatia majukumu na majukumu tofauti ya wanaume na wanawake katika jamii ya eneo hilo?

To what extent, does the training and NICHE II programme take into account different needs of men and women in the local community?  Je! Kwa kiwango gani, mafunzo na mpango wa NICHE II huzingatia mahitaji tofauti ya wanaume na wanawake katika jamii ya eneo hilo?

To what extent, does the training and NICHE II programme take into account different needs of and girls and boys in the local community?  Je! Kwa kiwango gani, mafunzo na mpango wa NICHE II huzingatia mahitaji tofauti ya wasichana na wavulana katika jamii ya eneo hilo?

At the village/county level, what are the other initiatives and opportunities available to households to meet their nutrition/health/food security and social and child protection needs?   Katika kiwango cha kijiji / kata, ni mipango gani na fursa zingine zinazopatikana kwa kaya ili kukidhi lishe yao / afya / usalama wa chakula na mahitaji ya kijamii na ulinzi wa watoto?

What other services and opportunities are available to women to improve nutrition practices for their household?  Je! Ni huduma gani zingine na fursa zinazopatikana kwa wanawake kuboresha mazoea ya lishe kwa kaya zao?

What other services and opportunities are available to caregivers to improve child protection practices for their household? Je! Ni huduma gani zingine na fursa zinazopatikana kwa wanawake kuboresha mazoea ya lishe kwa kaya zao?

Does the implementation of these activities from the NICHE II programme cause conflicts or competition for time/resources from other initiatives you are also disseminating to community members?  Je! Utekelezaji wa shughuli hizi kutoka kwa mpango wa NICHE II unasababisha mizozo au ushindani kwa wakati / rasilimali kutoka kwa mipango mingine unayosambaza pia kwa wanajamii?

If community members have feedback on the delivery of nutrition services, how do they provide feedback and suggestions?  Ikiwa wanajamii wana maoni juu ya utoaji wa huduma za lishe, wanatoaje maoni na maoni?

Probe: Is there a feedback mechanism or a platform where the community provides feedback?  Ulizia: Je! Kuna utaratibu wa maoni au jukwaa ambalo jamii hutoa maoni?

Sustainability

And finally, I would like to ask you about the sustainability of the NICHE Programme in general.

Na mwishowe, ningependa kukuuliza juu ya uendelevu wa Mpango wa NICHE kwa ujumla.

To what extent do you think these activities which you are disseminating to community members through the NICHE II programme – is sustainable in the long run at the village level? Je! Unafikiria shughuli hizi unazosambaza kwa wanajamii kupitia mpango wa NICHE II - ni endelevu kwa muda mrefu katika ngazi ya kijiji?

How long do you think it will continue, and with what level of support from UNICEF and/or government?  Unafikiri itaendelea kwa muda gani, na kwa kiwango gani cha msaada kutoka UNICEF na / au serikali?

Are you aware of any non-monetary efforts/strategies in place to sustain the activities? Je! Unafahamu juhudi / mikakati yoyote isiyokuwa ya kifedha iliyopo kuendeleza shughuli?

Probe: Strategies such as incorporating activities of NICHE II into other existing community-based programmes? Ulizia: Mikakati kama vile kuingiza shughuli za NICHE II katika programu zingine zilizopo za jamii?

If support from UNICEF Kenya and the government were to end, what do you think would happen to the activities?  Ikiwa msaada kutoka UNICEF Kenya na serikali zingekamilika, unafikiri ni nini kitatokea kwa shughuli hizo?

What would be needed to sustain it at the village/county level?  Ni nini kitakachohitajika kuidumisha katika kiwango cha kijiji / kata?

Which aspects of the activities do you think will be most difficult to sustain? Why? Je! Ni mambo yapi ya shughuli unafikiri yatakuwa magumu zaidi kutekeleza? Kwa nini?

Which aspects of the activities do you think will be easiest to sustain? Why? Je! Ni mambo yapi ya shughuli unafikiri yatakuwa rahisi kutekelezwa? Kwa nini?

Conclusion

Do you have any recommendations on how to improve the activities to meet the needs of the community? Please describe. Je! Una mapendekezo yoyote juu ya jinsi ya kuboresha shughuli ili kukidhi mahitaji ya jamii? Tafadhali eleza.

Have interventions under the NICHE II programme been adapted to the COVID-19 crisis? If yes, how?  Je! Hatua kati ya mpango wa NICHE II zimebadilishwa kuwa mgogoro wa COVID-19? Ikiwa ndio, vipi?

Probe: Did the interventions or activities change as a result of COVID-19? If yes, how?  Ulizia: Je! Hatua au shughuli zilibadilika kama matokeo ya COVID-19? Ikiwa ndio, vipi?

Is there anything else you’d like to tell me about the NICHE II programme or your experience in providing home visits/ counselling services?  Je! Kuna kitu kingine chochote ungependa kuniambia juu ya mpango wa NICHE II au uzoefu wako katika kutoa huduma za kutembelea nyumbani / ushauri?

Those are all of my questions. Is there anything else that you would like to add to our conversation? Do you have any questions for me? Hayo yote ni maswali yangu. Je! Kuna kitu kingine chochote ambacho ungependa kuongeza kwenye mazungumzo yetu? Je! Una maswali yoyote kwangu?

Thank you so much for your time and sharing your thoughts. Asante sana kwa muda wako na kushiriki maoni yako.

#### Focused Ethnographic Study [FES 1]: Pregnant Women/Mothers of Children Under 2 (conducted in Swahili)

Participant Verbal Consent Form

Thank you for coming. My name is ____________________ and my colleague is _____________________. We are working with a team of researchers from Dalberg in Nairobi. We are working on a project looking at child feeding practices. We are doing this to help understand the views of the people about child feeding and how it is done here. These views will be included in a report and the information will be used to help improve nutrition programs in the future.

Asante kwa kuja. Jina langu ni ____________________ na mwenzangu ni _____________________. Tunafanya kazi na timu ya watafiti kutoka Dalberg huko Nairobi. Tunafanya kazi kwenye mradi unaoangalia mazoea ya kulisha watoto. Tunafanya hivi kusaidia kuelewa maoni ya watu juu ya kulisha watoto na jinsi inafanywa hapa. Maoni haya yatajumuishwa katika ripoti na habari hiyo itatumika kusaidia kuboresha programu za lishe katika siku zijazo.

We would like to ask your views on a range of questions and will be having similar discussions with other people in this community and in other parts of Kenya.

Tungependa kuuliza maoni yako juu ya maswali anuwai na tutakuwa na mazungumzo kama hayo na watu wengine katika jamii hii na katika maeneo mengine ya Kenya.

The answers and information you give will be completely confidential. We will explain what people in this community and others think in a report, but we will not mention any names. We will be recording this discussion because we want to be sure that we note what you say correctly. But no one else will listen to this tape except me and my colleague here. Your personal contributions and views will not be shared with anyone else in a way that can identify you.

Majibu na habari unayotoa itakuwa siri kabisa. Tutaelezea nini watu katika jamii hii na wengine wanafikiria katika ripoti, lakini hatutaja majina yoyote. Tutarekodi mjadala huu kwa sababu tunataka kuhakikisha kuwa tunaona kile unachosema kwa usahihi. Lakini hakuna mtu mwingine atakayesikiza mkanda huu isipokuwa mimi na mwenzangu hapa. Michango yako ya kibinafsi na maoni hayatashirikiwa na mtu mwingine yeyote kwa njia inayoweza kukutambulisha.

We are very interested in hearing different viewpoints. There are no right and wrong answers. We are just interested in what you really think.

Tunavutiwa sana kusikia maoni tofauti. Hakuna majibu sahihi na mabaya. Tunavutiwa tu na kile unafikiria kweli.

I will be asking the questions and my colleague will be writing down your answers. The discussion will take about 1 hour to complete, and we will have some refreshments later. Do you have anything you want to ask me, or can we start?

Nitakuwa nauliza maswali na mwenzangu atakuwa akiandika majibu yako. Majadiliano yatachukua saa 1 kukamilika, na tutapata viburudisho baadaye. Je! Una chochote unachotaka kuniuliza, au tunaweza kuanza?

Signature of Enumerator_______________________________ Date________________

Saini ya Mwhesabu ___________________ Tarehe________________

Enumerator: Sign above to witness the verbal consent of the participants. Keep one copy for the PI’s records and leave copies with the participants if requested.

Hesabu: Saini hapo juu kushuhudia idhini ya maneno ya washiriki. Weka nakala moja kwa kumbukumbu za PI na uwaachie washiriki nakala ikiwa itaombwa.

This research is funded by UNICEF Kenya (the Sponsors). This means that the research team is being paid by the Sponsors for doing the study. If you have questions about this study, you may contact TURKANA at Dalberg Research. If you have questions about your rights you may reach out to the TURKANA LOCAL CONTACT or the American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

Utafiti huu unafadhiliwa na UNICEF Kenya (Wadhamini). Hii inamaanisha kuwa timu ya utafiti inalipwa na Wadhamini kwa kufanya utafiti. Ikiwa una maswali juu ya utafiti huu, unaweza kuwasiliana na TURKANA katika Utafiti wa Dalberg. Ikiwa una maswali juu ya haki zako unaweza kuwasiliana na MAWASILIANO YA MTAA wa TURKANA au Taasisi za Amerika za Bodi ya Ukaguzi wa Taasisi ya Utafiti (Simu: + 1 2024035542).

Introductions & Food Card Activity

Let us start by introducing ourselves: can you tell me a little about your family? Wacha tuanze kwa kujitambulisha: unaweza kuniambia kidogo juu ya familia yako?

Before I ask you some questions, we are going to play a game: I’m going to place these cards with pictures of different foods on them and ask you to ‘build’ two nutritious meals for a child older than 5 months and one nutritious meal for a pregnant woman. Each meal should be made up of three cards of your choice and we’ll have a short discussion after each meal is ‘built’.

Kabla sijakuuliza maswali, tutacheza mchezo: Nitaweka kadi hizi zilizo na picha za vyakula tofauti juu yao na nitakuuliza "utengeneze" milo miwili yenye lishe kwa mtoto aliyezidi miezi 5 na mlo mmoja wenye lishe kwa mwanamke mjamzito. Kila mlo unapaswa kuwa na kadi tatu za chaguo lako na tutakuwa na majadiliano mafupi baada ya kila mlo 'kujengwa'.

Instructions to enumerator:

Note the cards chosen on the grid below.

Initiate a discussion about the reasons for their choices, noting these down on the grid below. In the discussion, ask how many meals should ideally be fed to the child, and to a pregnant woman.

Remove the cards used from the deck.

Ask the respondent to ‘build’ another meal, until two child meals and one pregnant woman’s meal have been completed.

Response grid, food card grouping activity:

| Child Meal 1Mlo wa Mtoto 1 (child between 5 - 12 months) mtoto alie na umri zaid ya miezi mitano) |  |  |
| --- | --- | --- |
| First food Mlo wa kwanza | Second food mlo wa pili | Third food Mlo wa tatu |
| Discussion, including ideal number of meals Majadiliano, idadi bora ya milo |  |  |
| Child Meal 2 Mlo wa mtoto 2 (child between 12 – 24 months) Mtoto alie na umri Zaidi ya miezi mitano ) |  |  |
| First food Mlo wa kwanza | Second food Mlo wa pili | Third food Mlo wa tatu |
| Discussion Majadiliano |  |  |
| Meal for Pregnant Woman Mlo kwa mwanamke mja mzito |  |  |
| First food Mlo wa kwanza | Second food Mlo wa pili | Third food Mlo wa tatu |
| Discussion, including ideal number of meals Majadiliano, idadi iliyo bora ya milo |  |  |

Access, Knowledge & Decisions about Food

How difficult or easy is it to obtain food for your family? Mention foods that were chosen in the food card activity. Je! Ni kwaugumu gani au urahisi gani kupata chakula kwa familia yako? Sema vyakula ambavyo vilichaguliwa katika shughuli ya kadi ya chakula.

Where do these foods come from? Chakula hiki hupatikana kutoka wapi?

Are they already in the house or in the garden? Tayari viko hapa nyumbani ama kwenye bustani?

Do they come from far away?  Je, vinatoka sehemu iliyoko mbali?

Were they bought in a market or shop? Je, vilinunuliwa sokoni ama dukani?

What quantities are you able to obtain? Are these enough? Ni kiasi gani unaweza kukipata? Ni viwango vya kutosha?

What challenges (if any) do you face getting food for yourself and your children? Mention specific foods from food card activity.Je! Unapata changamoto gani (kama ipo) kupata chakula chako na cha watoto wako? Sema vyakula maalum kutoka kwa shughuli ya kadi ya chakula.

Are these foods expensive? Je, vyakula hivi ni ghali?

Are there other obstacles to getting food (probe for seasonal differences in food availability, climate, irrigation, distance to market, etc.)? Je, zipo changamoto zengine katika kukipata chakula (ulizia tafauti katika upatikanaji wa chakula kwa misimu tofauti, hali ya hewa, unyunyizaji wa maji, umbali wa soko nk)

What other challenges do you face getting food for your family? Unazipata changamoto gani Zaidi katika kupata chakula kwa familia yako?

Who makes decisions about what foods your family eats? Nani anaefanya maamuzi kuhusu chakula munachokula kwa familia yako?

Who makes decisions about breastfeeding? If a child is 0-5 months, is s/he being exclusively breastfed? Who makes that decision? Nani anaefanya maamuzi ya kunyonyesha? Iwapo mtoto ako na umri wa miezi kati ya 0-5, ananyonyeshwa maziwa ya mama pekee? Nani anaefanya maamuzi haya?

Who makes decisions about foods eaten by the baby? Nani anaefanya maamuzi kuhusu chakula kinacholishwa mtoto?

Are there particular foods which should be eaten by pregnant women? Why? Je, vipo vyakula maaulumu wanavyostahiki kula wanawake wajawazito? Kwa nini?

Are there particular foods which should not be eaten by pregnant women? Why? Je, vipo vyakula maaulumu wasivyostahiki kula wanawake wajawazito? Kwa nini?

Who makes decisions about foods eaten by pregnant women? Nani anaefanya maamuzi kuhusu chakula kinacholiwa na wanawake wajawazito?

How are other decisions made in the home? For example, are decisions made by men/your husbands? Are decisions made by older people? Are decisions made by consensus? Je, maamuzi yanafanyika vipi kwako nyumbani? Kwa mfano, maamuzi yanafanywa na wanaume/ mume wako? Maamuzi yanafanywa na wazee/ wenye umri wa kukuzidi? Maamuzi yanafanyika kwa Pamoja?

Who are the main decision-makers in the household? Ni kina nani wenye kutoa maamuzi Zaidi kwako nyumbani?

How do you respond to the opinions of (a) older people, (b) men (c) women, (d) younger people? Unayachukulia vipi maoni ya (a) wazee (b) wanaume (c) Wanawake (d) watu uliyowapita kwa umri

Who do you get nutrition and child feeding information from? What about information on foods for pregnant women? Probe for members of their households, other community members, a clinic or community health worker, an NGO, radio, etc. Unapata Habari kuhusu virutubisha na jinsi ya kumlisha mtoto kutoka wa nani? Na Habari kuhusu vyakula vya wanawake wajawazito? Ulizia watu wa familia, wanajamii, muhudumu wa afya katika kituo cha afya ama muhudumu wa kijamii, shirika lisilo la kiserikali, radio na kadhalika

Are there people you can ask questions about nutrition and child feeding? Who? Where? Please explain. Je, wapo watu unaoweza kuwaulizia kuhusu virutubisha na chakula kwa Watoto? Ni nani? Wapi? Tafadhali elezea

Are there other kinds of support you need (apart from money) to take care of your children? Please explain. Je, kuna usaidizi aina yeyote ingine ungependa kupata (kando na pesa) ili kuwaangalia watoto wako? Tafadhali elezea

Do local leaders or respected people ever offer advice on food and nutrition issues? Potential probe: for example, do religious leaders have opinions about what kinds of foods should be eaten or what kinds of roles people should play in their homes?. Je viongozi wa jamii ama waheshimiwa hutoa ushauri wowote kuhusu chakula na masuala ya virutubisho? Unaweza kuulizia: kwa mfano, je viongozi wa kidini wanatoa ushauri wowote kuhusu vyakula vinavyostahiki kuliwa ama watu wanafaa kua na majukumu gani nyumbani kwao?

Time Use

On a typical day, could you tell me how you usually pass your day, from the time you wake up to the time you go to bed? Katika siku ya kawaida, unaweza nijulisha jinsi unavyo pitisha siku yako, kutoka wakati unaamka hadi wakati wa kwenda kulala?

Of the activities which you have mentioned to me, which activity takes most of your time in a given day?  Kati ya shughuli ambazo umenitajia, ni shughuli gani inayochukua muda wako mwingi katika siku zako?

Following this activity, what is the second most time-consuming activity? Ni shughuli gani ya pili inayochukua muda wako mwingi?

And your third most time-consuming activity? Na ni ipi shughuli ya tatu inayochukua muda wako mwingi?

Of the activities which you mentioned, which one takes the least amount of time from you?  Katika shughuli ulizozitaja, ni shughuli ipi inayochukua muda wako mfupi Zaidi?

Apart from this, which other activity takes less time? Kando na shughuli uliyoitaja, ni shughuli ipi ingine inayochukua muda mfupi?

Thinking of your daily routine, when do you obtain food? In the morning/afternoon/evening? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe upata chakula wakati gani? Asubuhi/ mchana/jioni?  Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

Do you do this every day? Je, wewe hufanya hivi kila siku?

If no, when do you do it? Iwapo la, ni wakati gani unafanya hivi?

Do you get help in obtaining food? If yes, from whom? Je,unapata msaada wowote katika kukipata chakula? Iwapo ndio, wewe hupata msaada kutoka kwa nani?

Thinking of your daily routine, when do you obtain water? In the morning/afternoon/evening? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe hupata maji wakati gani? Asubuhi/ mchana/ jioni?  Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

Do you this every day? If yes, how many times a day? Je, wewe hufanya hivi kila siku? Iwapo ndio, ni mara ngapi kwa siku?

If no, when do you do it? Iwapo la, ni wakati gani wewe hivi kila siku?

Do you get help in obtaining water? If yes, from whom? Je, wewe hupata usaidizi wowote katika kuyapata maji? Iwapo ndio, usaidizi huo wewe huupata kutoka kwa nani?

Where is the nearest source of water? Chanzo cha maji kilichoko karibu kiko wapi?

Do you have to do anything to the water to make it safe to drink? Je, ni lazima uyafanyie maji hayo chochote ili yaweze kua salama kwa kunywa?  Probe: Boil water, add purifiers? Ulizia: kuchemsha, kuongezea visafisho

Thinking of your daily routine, when do you obtain cooking fuel? In the morning/afternoon/evening? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe hupata nishati ya kupikia wakati gani? Asubuhi/ mchana/ jioni? Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

Do you this every day? If yes, how many times a day? Je, wewe hufanya hivi kila siku? Iwapo ndio, ni mara ngapi kwa siku?

If no, when do you do it? Iwapo la, ni wakati gani wewe hivi kila siku?

Do you get help in obtaining cooking fuel? If yes, from whom? Je, wewe hupata usaidizi wowote katika kupata nishati ya kupikia? Iwapo ndio, usaidizi huo wewe huupata kutoka kwa nani?

What kind of fuel is used to cook? Unatumia nishati aina gani kwa kupikia?

Where is the fuel obtained? Nishati hii hupatikana wapi?

Thinking of your daily routine, when do you prepare/cook food and wash utensils? In the morning/afternoon/evening/ for every meal? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe hutayarisha/ hupika chakula na kuosha vyombo wakati gani? Asubuhi/ mchana/ jioni?  Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

How many hours each day do you spend on food preparation (including washing of food or utensils) and cooking? Je, wewe hutumia masaa mangapi kwa siku katika kutayarisha (Pamoja na kuosha chakula na vyombo) na kupika?

When do you feed your children? Breastfeeding? Feeding solid foods? Wewe huwalisha Watoto wakati gani? Kuwanyonyesha? Kuwapatia vyakula?

Probe: Whenever they want/when I have time/ during usual mealtimes, morning & night, etc. ulizia: wanapohitaji kulishwa/ ninapo pata wakati/ muda wakawaida wa kula/ asubuhi na usiku

Probe for number of hours if respondent can read and count and can provide estimate of hour Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa. . How many hours each day do you spend feeding your children? Je, wewe hutumia masaa mangapi kila siku kuwalisha Watoto wako?

Breastfeeding? Kuwanyonyesha?

Feeding solid foods? Kuwalisha vyakula?

Parenting

Who is primarily responsible for raising children in your family? (Probe: mothers, fathers, siblings, grandmothers, neighbors, other caregivers). Nani mwenye jukumu la msingi katika kulea Watoto katika kaya yako? (ulizia: wamama, mababa, ndugu, nyanya, majirani, walezi wengine)

Who helps this person with raising children? (Probe: mothers, fathers, siblings, grandmothers, neighbors, other caregivers). Nani anaemsaidia mtu huyu katika kulea Watoto? (ulizia: wamama, mababa, ndugu, nyanya, majirani, walezi wengine)

What do you do when you see your child falling ill? Kwa kawaida, wewe hufanya nini unapomuona mtoto wako amekua mgonjwa?

When do you take your child to seek help? (Probe: Do you go to a traditional healer, use traditional medicine, or take them for prayers?) (As in duration/intensity of illness) Ni wakati gani humpeleka mtoto kupata usaidizi? (ulizia: je unaenda kumuona daktari wa kienyeji ama unampeleka kwa maombi?) (urefu/ makali ya maradhi)

Where does your child receive general health services? Mtoto hupata huduma za kawaida za afya kutoka wapi?

How often would you take your child/children to the clinic? What services do they receive at the clinic? Probe for growth monitoring, etc. Uko na uzoefu gani wa kumpeleka mtoto/ Watoto wako kwenye zahanati? Unapata huduma gani kutoka hapo kwenye zahanati? Ulizia kufuatilia ukuaji wa mtoto na kadhalika

Has your child received any vaccinations? If yes, which ones? If no, why not? Mtoto wako amepata chanjo zozote? Iwapo ndio, ni chanjo zipi? Iwapo la, kwanini hajapata?

Do you recall a recent time when you disciplined your child? Please describe how and why you disciplined them. Probe for age of child. Unakumbuka wakito wowote hivi karibuni ulipo mtia adabu mtoto wako? Tafadhali elezea ulimtia adabu vipi na kwanini? Ulizia umri wa mtoto

How do other members of your household/family discipline your children? Je, wanakaya wenzako wanawatia vipi adabu Watoto wako?

How should parents discipline children when they are young (0-3)? And when they are a bit older (4-8)?  Je, wazazi wanafaa kuwatia adabu vipi Watoto wakiwa wadogo (0-3?) na wanapokua wakubwa (4-8)?

Does this change from boys to girls? Je, jambo hili linatafautiana kwa Watoto wakiume na wakike?

Do you care for any children that you did not give birth to? Please explain. Je, unawatunza Watoto wowote ambao wewe sio mzazi wao? Tafadhali elezea

Thank respondent for their time and conclude the discussion. Mshukuru muhojiwa na umalizie majadiliano

#### Focus Group Discussion [FGD 1]– Pregnant Women/Mothers of Children Under 2 (conducted in Swahili)

Participant Verbal Consent Form

Thank you all for coming. My name is ____________________ and my colleague is _____________________. We are working with a team of researchers from Dalberg in Nairobi. We are working on a project looking at child feeding practices. We are doing this to help understand the views of the people about child feeding and how it is done here. These views will be included in a report and the information will be used to help improve nutrition programs in the future.

Asanteni nyote kwa kuja. Jina langu ni ____________________ na mwenzangu ni _____________________. Tunafanya kazi na timu ya watafiti kutoka Dalberg huko Nairobi. Tunafanya kazi kwenye mradi ukiangalia mazoea ya kulisha watoto. Tunafanya hivyo kusaidia kuelewa maoni ya watu juu ya kulisha watoto na jinsi inafanywa hapa. Maoni haya yatajumuishwa katika ripoti na habari hiyo itatumika kusaidia kuboresha programu za lishe katika siku zijazo.

We would like to ask your views on a range of questions and will be having similar discussions with other people in this community and in other parts of Kenya.

Tungependa kuuliza maoni yako juu ya maswali anuwai na tutakuwa na mazungumzo kama hayo na watu wengine katika jamii hii na katika maeneo mengine ya Kenya.

The answers and information you give will be completely confidential. We will explain what people in this community and others think in a report, but we will not mention any names. We will be recording this discussion because we want to be sure that we note what you say correctly. But no one else will listen to this tape except me and my colleague here. Your personal contributions and views will not be shared with anyone else in a way that can identify you.

Majibu na habari unayotoa itakuwa siri kabisa. Tutaelezea nini watu katika jamii hii na wengine wanafikiria katika ripoti lakini hatutataja majina yoyote. Tutarekodi mjadala huu kwa sababu tunataka kuhakikisha kuwa tunaona kile unachosema kwa usahihi. Lakini hakuna mtu mwingine atakayesikiza mkanda huu isipokuwa mimi na mwenzangu hapa. Michango yako ya kibinafsi na maoni hayatashirikiwa na mtu mwingine yeyote kwa njia inayoweza kukutambulisha.

We are very interested in hearing different viewpoints. There are no right and wrong answers. We are just interested in what you really think. It is very important that you speak one at a time, as otherwise we will not be able to hear or understand you.

Tunavutiwa sana kusikia maoni tofauti. Hakuna majibu sahihi na mabaya. Tunavutiwa tu na kile unafikiria kweli. Ni muhimu sana uzungumze moja kwa wakati, kwani vinginevyo hatutaweza kukusikia au kukuelewa.

I will be asking the questions and my colleague will be writing down your answers. The discussion will take about 2 hours to complete and we will have some refreshments later. Do you have anything you want to ask me, or can we start?

Nitakuwa nauliza maswali na mwenzangu atakuwa akiandika majibu yako. Majadiliano yatachukua kama masaa 2 kukamilisha na tutapata viburudisho baadaye. Je! Una chochote unachotaka kuniuliza, au tunaweza kuanza?

Signature of Enumerator_______________________________ Date________________

Saini ya Mwandikishaji_______________________________ Tarehe________________

Enumerator: Sign above to witness the verbal consent of the participants. Keep one copy for the PI’s records and leave copies with the participants if requested.

Hesabu: Saini hapo juu kushuhudia idhini ya mdomo ya washiriki. Weka nakala moja kwa rekodi za PI na uwaachie washiriki nakala ikiwa itaombwa.

This research is funded by UNICEF Kenya (the Sponsors). This means that the research team is being paid by the Sponsors for doing the study. If you have questions about this study, you may contact TURKANA at Dalberg Research. If you have questions about your rights you may reach out to the TURKANA LOCAL CONTACT or the American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

Utafiti huu unafadhiliwa na UNICEF Kenya (Wadhamini). Hii inamaanisha kuwa timu ya utafiti inalipwa na Wadhamini kwa kufanya utafiti. Ikiwa una maswali juu ya utafiti huu, unaweza kuwasiliana na TURKANA katika Utafiti wa Dalberg. Ikiwa una maswali juu ya haki zako unaweza kuwasiliana na MAWASILIANO YA MTAA wa TURKANA au Taasisi za Amerika za Bodi ya Ukaguzi wa Taasisi ya Utafiti (Simu: + 1 2024035542).

Introductions & Food Card Activity

Let us start by introducing ourselves: can we first go round and quickly introduce ourselves to each other?

Wacha tuanze kwa kujitambulisha: tunaweza kwanza kuzunguka na kujitambulisha kwa haraka kwa kila mmoja?

Before I ask you all some questions, we are going to play a game: I’m going to place these cards with pictures of different foods on them and ask you to ‘build’ two nutritious meals for a child older than 5 months and one nutritious meal for a pregnant woman. Each meal should be made up of three cards chosen by the group, following a discussion, and after each meal is ‘built’.Kabla sijakuuliza maswali kadhaa, tutacheza mchezo: Nitaweka kadi hizi zilizo na picha za vyakula tofauti juu yao na nitakuuliza "ujenge" milo miwili yenye lishe kwa mtoto aliyezidi miezi 5. na mlo mmoja wenye lishe kwa mwanamke mjamzito. Kila mlo unapaswa kuwa na kadi tatu zilizochaguliwa na kikundi, kufuatia majadiliano, na baada ya kila mlo 'kujengwa'.

Instructions to enumerator:

Note the cards chosen on the grid below.

Initiate a discussion about the reasons for their choices, noting these down on the grid below. In the discussion, ask how many meals should ideally be fed to the child, and to a pregnant woman.

Remove the cards used from the deck.

Ask the group to ‘build’ another meal, until two child meals and one pregnant woman’s meal have been completed.

Response grid, food card grouping activity:

| Child Meal 1 Mlo wa mtoto 1 (child between 5 -12) mtoto alie na umri wa miezi Zaidi ya mitano) |  |  |
| --- | --- | --- |
| First food Mlo wa kwanza | Second food Mlo wa pili | Third food Mlo wa tatu |
| Discussion, including ideal number of meals Majadiliano, idadi bora ya chakula |  |  |
| Child Meal 2 Mlo wa mtoto 2 (child between 12 – 24 months) Mtoto alie na umri chini ya miezi mitano) |  |  |
| First food Mlo wa kwanza | Second food Mlo wa pili | Third food Mlo wa tatu |
| Discussion Majadiliano |  |  |
| Meal for Pregnant Woman Chakula kwa wanawake wajawazito |  |  |
| First food Mlo wa kwanza | Second food Mlo wa pili | Third food Mlo wa tatu |
| Discussion, including ideal number of meals Majadiliano; idadi bora ya chakula |  |  |

Access, Knowledge & Decisions about Food

How difficult or easy is it to obtain food for your family? Mention foods that were chosen in the food card activity. Je! Ni kwaugumu gani au urahisi gani kupata chakula kwa familia yako? Sema vyakula ambavyo vilichaguliwa katika shughuli ya kadi ya chakula.

Where do these foods come from? Chakula hiki hupatikana kutoka wapi?

Are they already in the house or in the garden? Tayari viko hapa nyumbani ama kwenye bustani?

Do they come from far away?  Je, vinatoka sehemu iliyoko mbali?

Were they bought in a market or shop? Je, vilinunuliwa sokoni ama dukani?

What quantities are you able to obtain? Are these enough? Ni kiasi gani unaweza kukipata? Ni viwango vya kutosha?

What challenges (if any) do you face getting food for yourself and your children? Mention specific foods from food card activity.Je! Unapata changamoto gani (kama ipo) kupata chakula chako na cha watoto wako? Sema vyakula maalum kutoka kwa shughuli ya kadi ya chakula.

Are these foods affordable? Je, vyakula hivi ni ghali?

Are there other obstacles to getting food (probe for seasonal differences in food availability, climate, irrigation, distance to market, etc.)? Je, zipo changamoto zengine katika kukipata chakula (ulizia tafauti katika upatikanaji wa chakula kwa misimu tofauti, hali ya hewa, unyunyizaji wa maji, umbali wa soko nk)

What other challenges do you face getting food for your family? Unazipata changamoto gani Zaidi katika kupata chakula kwa familia yako?

Who makes decisions about what foods your family eats? Nani anaefanya maamuzi kuhusu chakula munachokula kwa familia yako?

Who makes decisions about breastfeeding? If a child is 0-5 months, is s/he being exclusively breastfed? Who makes that decision? Nani anaefanya maamuzi ya kunyonyesha? Iwapo mtoto ako na umri wa miezi kati ya 0-5, ananyonyeshwa maziwa ya mama pekee? Nani anaefanya maamuzi haya?

Who makes decisions about foods eaten by the baby? Nani anaefanya maamuzi kuhusu chakula kinacholishwa mtoto?

Are there particular foods which should be eaten by pregnant women? Why? Je, vipo vyakula maaulumu wanavyostahiki kula wanawake wajawazito? Kwa nini?

Are there particular foods which should not be eaten by pregnant women? Why? Je, vipo vyakula maaulumu wasivyostahiki kula wanawake wajawazito? Kwa nini?

Who makes decisions about foods eaten by pregnant women? Nani anaefanya maamuzi kuhusu chakula kinacholiwa na wanawake wajawazito?

How are other “general decisions” made in your community? For example, are decisions made by men/your husbands? Are decisions made by older people? Are decisions made by consensus? Je, maamuzi yanafanyika vipi kwako nyumbani? Kwa mfano, maamuzi yanafanywa na wanaume/ mume wako? Maamuzi yanafanywa na wazee/ wenye umri wa kukuzidi? Maamuzi yanafanyika kwa Pamoja?

Who are the main decision-makers in the household? Ni kina nani wenye kutoa maamuzi Zaidi kwako nyumbani?

How do you respond to the opinions of (a) older people, (b) men (c) women, (d) younger people? Unayachukulia vipi maoni ya (a) wazee (b) wanaume (c) Wanawake (d) watu uliyowapita kwa umri

Who do you get nutrition and child feeding information from? What about information on foods for pregnant women? Probe for members of their households, other community members, a clinic or community health worker, an NGO, radio, etc. Unapata Habari kuhusu virutubisha na jinsi ya kumlisha mtoto kutoka wa nani? Na Habari kuhusu vyakula vya wanawake wajawazito? Ulizia watu wa familia, wanajamii, muhudumu wa afya katika kituo cha afya ama muhudumu wa kijamii, shirika lisilo la kiserikali, radio na kadhalika

Are there people you can ask questions about nutrition and child feeding? Who? Where? Please explain. Je, wapo watu unaoweza kuwaulizia kuhusu virutubisha na chakula kwa Watoto? Ni nani? Wapi? Tafadhali elezea

Are there other kinds of support you need (apart from money) to take care of your children? Please explain. Je, kuna usaidizi aina yeyote ingine ungependa kupata (kando na pesa) ili kuwaangalia watoto wako? Tafadhali elezea

Do local leaders or respected people ever offer advice on food and nutrition issues? Potential probe: for example, do religious leaders have opinions about what kinds of foods should be eaten or what kinds of roles people should play in their homes? Je viongozi wa jamii ama waheshimiwa hutoa ushauri wowote kuhusu chakula na masuala ya virutubisho? Unaweza kuulizia: kwa mfano, je viongozi wa kidini wanatoa ushauri wowote kuhusu vyakula vinavyostahiki kuliwa ama watu wanafaa kua na majukumu gani nyumbani kwao?

Access, Knowledge & Decisions about Pregnancy and Breastfeeding

In your community and culture, what is considered a healthy pregnancy? Ukizingatia jamii yako na tamaduni zake, ni nini kinachochukuliwa kuwa ujauzito mzuri/ wenye afya?

In your community, what kind of information do you receive about pregnancy, breastfeeding and complementary feeding? Katika jamii yako, munapata Habari aina gani kuhusu ujauzito, kunyonyesha na ulishaji wa Zaidi kwa Watoto?

Are there any “do’s and don’ts” during pregnancy? And while breastfeeding? If yes, please describe. Je, yapo mambo yanayo ruhusika ama yasiyo ruhusika kufanyika wakati wa ujauzito? Na wakati wa kunyonyesha? Iwapo ndio, tafadhali elezea.

Probe: Is a pregnant woman or breastfeeding expected to eat or avoid certain types of foods? If yes, which ones? Ulizia: je, vipo vyakula ambavyo mwanamke mjamzito au anaenyonyesha ana stahiki kuvila au kutokula? Iwapo ndio, elezea ni vyakula gani?

Probe: What is appropriate work/chores for a pregnant or breastfeeding woman? Ulizia: ni kazi zipi zinazoweza kufanywa na wanawake wajawazito au wanaonyonyesha?

Probe: Do women in this community receive information on child spacing and family planning?  Ulizia: je, wanawake wa jamii hii hupata Habari yoyote kuhusu upangaji wa uzazi na jinsi ya kupangilia Watoto?

If yes, what types of information? Iwapo ndio, ni Habari aina gani?

Time Use

On a typical day, could you tell me how you usually pass your day, from the time you wake up to the time you go to bed? Katika siku ya kawaida, unaweza nijulisha jinsi unavyo pitisha siku yako, kutoka wakati unaamka hadi wakati wa kwenda kulala?

Of the activities which you have mentioned to me, which activity takes most of your time in a given day?  Kati ya shughuli ambazo umenitajia, ni shughuli gani inayochukua muda wako mwingi katika siku zako?

Following this activity, what is the second most time-consuming activity? Ni shughuli gani ya pili inayochukua muda wako mwingi?

And your third most time-consuming activity? Na ni ipi shughuli ya tatu inayochukua muda wako mwingi?

Of the activities which you mentioned, which one takes the least amount of time from you?  Katika shughuli ulizozitaja, ni shughuli ipi inayochukua muda wako mfupi Zaidi?

Apart from this, which other activity takes less time? Kando na shughuli uliyoitaja, ni shughuli ipi ingine inayochukua muda mfupi?

Thinking of your daily routine, when do you eat food? In the morning/afternoon/evening? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe upata chakula wakati gani? Asubuhi/ mchana/jioni?  Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

a. Do you do this every day? Je, wewe hufanya hivi kila siku?

b.If no, when do you do it? Iwapo la, ni wakati gani unafanya hivi?

Do you get help in obtaining food? If yes, from whom? Je,unapata msaada wowote katika kukipata chakula? Iwapo ndio, wewe hupata msaada kutoka kwa nani?

Thinking of your daily routine, when do you obtain water? In the morning/afternoon/evening? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe hupata maji wakati gani? Asubuhi/ mchana/ jioni?  Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

a.Do you this every day? If yes, how many times a day? Je, wewe hufanya hivi kila siku? Iwapo ndio, ni mara ngapi kwa siku?

b.If no, when do you do it? Iwapo la, ni wakati gani wewe hivi kila siku?

c. Do you get help in obtaining water? If yes, from whom? Je, wewe hupata usaidizi wowote katika kuyapata maji? Iwapo ndio, usaidizi huo wewe huupata kutoka kwa nani?

d.Where is the nearest source of water? Chanzo cha maji kilichoko karibu kiko wapi?

e.Do you have to do anything to the water to make it safe to drink? Je, ni lazima uyafanyie maji hayo chochote ili yaweze kua salama kwa kunywa?  Probe: Boil water, add chlorine? Ulizia: kuchemsha, kuongezea chlorine

Thinking of your daily routine, when do you obtain cooking fuel? (Probe: irewood, charcoal, kerosene/ paraffin, coconut husks/ remains, LPG, cowdung). In the morning/afternoon/evening? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe hupata nishati ya kupikia wakati gani? Asubuhi/ mchana/ jioni? Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

a.Do you this every day? If yes, how many times a day? Je, wewe hufanya hivi kila siku? Iwapo ndio, ni mara ngapi kwa siku?

b.If no, when do you do it? Iwapo la, ni wakati gani wewe hivi kila siku?

c. Do you get help in obtaining cooking fuel? If yes, from whom? Je, wewe hupata usaidizi wowote katika kupata nishati ya kupikia? Iwapo ndio, usaidizi huo wewe huupata kutoka kwa nani?

d.What kind of fuel is used to cook? Unatumia nishati aina gani kwa kupikia?

e.Where is the fuel obtained? Nishati hii hupatikana wapi?

Thinking of your daily routine, when do you prepare/cook food and wash utensils? In the morning/afternoon/evening/ for every meal? Ukifikiria mpangilio wa shughuli zako za kila siku, wewe hutayarisha/ hupika chakula na kuosha vyombo wakati gani? Asubuhi/ mchana/ jioni?  Probe for number of hours if respondent can read and count and can provide estimate of hours. Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa.

a.How many hours each day do you spend on food preparation (including washing of food or utensils) and cooking? Je, wewe hutumia masaa mangapi kwa siku katika kutayarisha (Pamoja na kuosha chakula na vyombo) na kupika?

When do you feed your children? Breastfeeding? Feeding solid foods? Wewe huwalisha Watoto wakati gani? Kuwanyonyesha? Kuwapatia vyakula?

a.Probe: Whenever they want/when I have time/ during usual mealtimes, morning & night, etc. ulizia: wanapohitaji kulishwa/ ninapo pata wakati/ muda wakawaida wa kula/ asubuhi na usiku

Probe for number of hours if respondent can read and count and can provide estimate of hour Ulizia kuhusu idadi ya masaa iwapo mhojiwa anaweza kusoma na kuhesabu na anaweza kukisia idadi ya masaa. . How many hours each day do you spend feeding your children? Je, wewe hutumia masaa mangapi kila siku kuwalisha Watoto wako?

Breastfeeding? Kuwanyonyesha?

Feeding solid foods? Kuwalisha vyakula?

Parenting

Who is primarily responsible for raising children in your family? (Probe: mothers, fathers, siblings, grandmothers, neighbors, other caregivers). Nani mwenye jukumu la msingi katika kulea Watoto katika kaya yako? (ulizia: wamama, mababa, ndugu, nyanya, majirani, walezi wengine)

Who helps this person with raising children? (Probe: mothers, fathers, siblings, grandmothers, neighbors, other caregivers). Nani anaemsaidia mtu huyu katika kulea Watoto? (ulizia: wamama, mababa, ndugu, nyanya, majirani, walezi wengine)

Do you care for any children that you did not give birth to? Please explain. Je, unawalea Watoto ambao haukuwazaa wewe mwenyewe? Tafadhali elezea.

What do you do when you see your child falling ill? Kwa kawaida, wewe hufanya nini unapomuona mtoto wako amekua mgonjwa?

a.  When do you take your child to seek help? (Probe: Do you go to a traditional healer, use traditional medicine, or take them for prayers?) (As in duration/intensity of illness) Ni wakati gani humpeleka mtoto kupata usaidizi? (ulizia: je unaenda kumuona daktari wa kienyeji ama unampeleka kwa maombi?) (urefu/ makali ya maradhi)

Where does your child receive general health services? Mtoto hupata huduma za kawaida       za afya kutoka wapi?

a.How often would you take your child/children to the clinic? What services do they receive at the clinic? Probe for growth monitoring, etc. Uko na uzoefu gani wa kumpeleka mtoto/ Watoto wako kwenye zahanati? Unapata huduma gani kutoka hapo kwenye zahanati? Ulizia kufuatilia ukuaji wa mtoto na kadhalika

Has your child received any vaccinations? If yes, which ones? If no, why not? Je, Watoto wako wamepata chanjo zozote? Iwapo ndio, wamepata chanjo zipi? Iwapo la, kwanini hawajapata chanjo?

Do you recall a recent time when you disciplined your child? Please describe how and why you disciplined them. Probe for age of child. Je, unakumbuka hivi karibuni ulipomuadhibu mtoto? Tafadhali elezea ulimuadhibu vipi na kwa nini. Ulizia umri wa mtoto

How do other members of your household/family discipline your children? Je, wanawaadhibu vipi Watoto wako watu wengine wa kaya yako/ familia yako?

How should parents discipline children when they are young (0-3)? And when they are a bit older (4-8)?  Wazazi wanapaswa kuwaadhibu vipi Watoto wanapokua wadogo (0-3)? Na wanapo pata kimo kidogo (4-8)?

Does this change from boys to girls? Je, hii inatofautiana kati ya Watoto wa kiume na wakike?

Who is responsible for orphans in this community?  Nani anaewajibika kuwatunza mayatima katika jamii hii? 
a. Who takes care of the orphaned child?  Nani haswa anayemtunza mtoto yatima  (Probe: siblings, grandmothers, neighbors, other caregivers) (ulizia: ndugu, bibi/nyanya, majirani, walezi wengine)
b. How does the community perceive orphaned children? Je, jamii hii inamtazamo gani kwa Watoto mayatima?

How is care for a child with disability look like in this community? Je, utunzaji wa Watoto walemavu unaonekana vipi katika jamii hii? 
a. Who takes care of the child with disability? Ni nani anayemtunza mtoto mwenye ulemavu  (Probe: mothers, fathers, siblings, grandmothers, neighbors, other caregivers) ( ulizia: mama, baba, ndugu, bibi/nyanya, majirani, walezi wengine)
b. How does the community perceive children with disabilities? Je, jamii hii inamtazamo gani kwa Watoto walemavu?

In your community, what are the traditional methods to engage a child or stimulate a child for social cues and growth?  Katika jamii yako, ni zipi njia za tamaduni za kumshirikisha mtoto au kumfunza namna ya kujumuika na wenzako na katika kumkuza mtoto?

Social Mapping Activity (**to be completed in 4 of the 8 FGDs only)

About the Social Mapping activity: Social mapping is a participatory tool which is designed to involve community members—the subjects of research—in the research process, not simply as respondents but as active contributors. We will use this approach to collect data on local understandings of poverty, wellbeing, vulnerability, access to resources, and other programs under implementation.

Kuhusu shughuli ya Ramani ya Jamii: Ramani ya jamii ni zana shirikishi ambayo imeundwa kushirikisha wanajamii - masomo ya utafiti - katika mchakato wa utafiti, sio tu kama wahojiwa lakini kama wachangiaji hai. Tutatumia njia hii kukusanya data juu ya uelewa wa wenyeji wa umaskini, ustawi, mazingira magumu, upatikanaji wa rasilimali, na mipango mingine inayotekelezwa.

Method: The SM is carried out as a two-stage process. In the first stage, the participants define and create the map, drawing it out on a large piece of paper (you have been provided with materials used for this stage). In the second stage, the map is analyzed through discussion. Careful notes will need to be taken during this stage to ensure that this discussion is accurately captured: without proper notes, the map will not be useful.

Njia: SM inafanywa kama mchakato wa hatua mbili. Katika hatua ya kwanza, washiriki hufafanua na kuunda ramani, wakichora kwenye karatasi kubwa (umepewa vifaa vilivyotumika kwa hatua hii). Katika hatua ya pili, ramani inachambuliwa kupitia majadiliano. Vidokezo vya uangalifu vitahitajika kuchukuliwa wakati wa hatua hii ili kuhakikisha kuwa majadiliano haya yamenaswa kwa usahihi: bila maelezo sahihi, ramani haitakuwa na faida.

Stage One: drawing the map

First of all, define the boundaries of the map: ask the participants to decide, through discussion, what area their map will cover. In this research, maps should ideally cover villages, but you should emphasize that it is important to include even outlying homes where possible within the boundaries.

Hatua ya Kwanza: kuchora ramani

Kwanza kabisa, fafanua mipaka ya ramani: waulize washiriki waamue, kupitia majadiliano, ni eneo gani ramani yao itafunika. Katika utafiti huu, ramani zinapaswa kufunika vijiji, lakini unapaswa kusisitiza kwamba ni muhimu kujumuisha hata nyumba za nje wakati inawezekana ndani ya mipaka.

Now ask some of the participants to draw the map. They should make sure that they include the following features:

Houses or family compounds

Roads and paths

Waterways (creeks or rivers: note whether used for drinking or washing)

Wells (note whether used for drinking or washing)

Fields

Schools

Clinics

Churches

Markets, shops, or businesses

Community organizations

Other public spaces and buildings

Any other features which are determined by the group to be important.

When the map is finished, please ensure that consensus has been reached about its completion. Does everyone in the group feel that it is done?

Sasa waombe washiriki kuchora ramani. Wanapaswa kuhakikisha kuwa wanajumuisha huduma zifuatazo:

• Nyumba au misombo ya familia

• Barabara na njia

• Njia za maji (vijito au mito: kumbuka ikiwa hutumiwa kwa kunywa au kuosha)

• Visima (kumbuka ikiwa hutumiwa kunywa au kuosha

• Mashamba

• Shule

• Kliniki

• Makanisa

• Masoko, maduka, au biashara

• Mashirika ya jamii

• Sehemu nyingine za umma na majengo

• Sifa zingine zozote ambazo zimedhamiriwa na kikundi kuwa muhimu.

Wakati ramani imekamilika, tafadhali hakikisha kwamba makubaliano yamefikiwa juu ya kukamilika kwake. Je! Kila mtu katika kikundi anahisi kuwa imefanywa?

Stage Two: discussion and analysis

Now that the basic map has been completed, the next stage is to facilitate a discussion around a series of topics, using the interaction with the map as a way of structuring the conversation. For example, you could begin by asking about leaders and people of respect and power in the community. Where are their houses? Are their houses bigger than other houses? Who are the powerful people in the community and why? Make notes next to each of their houses and use different colored pens to help.

Hatua ya Pili: majadiliano na uchambuzi

Sasa kwa kuwa ramani ya kimsingi imekamilika, hatua inayofuata ni kuwezesha majadiliano karibu na safu ya mada, kwa kutumia mwingiliano na ramani kama njia ya kuandaa mazungumzo. Kwa mfano, unaweza kuanza kwa kuuliza juu ya viongozi na watu wa heshima na nguvu katika jamii. Nyumba zao ziko wapi? Je! Nyumba zao ni kubwa kuliko nyumba zingine? Je! Ni watu gani wenye nguvu katika jamii na kwa nini? Andika maelezo karibu na kila nyumba yao na utumie kalamu zenye rangi tofauti kusaidia.

Now, you can discuss wealth. Are there people in the community who have more wealth (money, land, livestock, businesses, other resources) than others? Again, make notes next to these houses, using different symbols and colors (you will need to create a key box at the bottom of the map to indicate what colors and symbols mean). What are the main wealth categories in the community (very poor, poor, less poor, not poor, well-off etc.) and how are they defined? Discuss and again make notes on the map. Discuss any patterns which are visible. Are poorer people’s houses in one area, for example? Have things changed over time?

Sasa, unaweza kujadili utajiri. Je! Kuna watu katika jamii ambao wana utajiri zaidi (pesa, ardhi, mifugo, biashara, rasilimali nyingine) kuliko wengine? Tena, andika maandishi karibu na nyumba hizi, ukitumia alama na rangi tofauti (utahitaji kuunda kisanduku muhimu chini ya ramani ili kuonyesha rangi na alama zina maana gani). Je! Ni aina gani kuu za utajiri katika jamii (masikini sana, masikini, duni sana, sio masikini, tajiri n.k. Jadili na andika tena kwenye ramani. Jadili mifumo yoyote inayoonekana. Je! Nyumba za watu masikini katika eneo moja, kwa mfano? Je! Mambo yamebadilika kwa muda?

When you have done this, you can start talking about resources. What are the most important resources in the community? Mark these on the map. Does everyone have the same access to them? If some houses have greater access (to water for example), mark this on the map.

Now please discuss programs, either from the Government or from NGOs, CBOs or FBOs. What programs exist in the community and what do they do? Which houses participate? Are there some people who hold special positions in community programs? Again, make sure you mark all this information on the map so that it can be understood later.

Unapofanya hivi, unaweza kuanza kuzungumza juu ya rasilimali. Je! Ni rasilimali gani muhimu zaidi katika jamii? Tia alama hizi kwenye ramani. Je! Kila mtu ana ufikiaji sawa kwao? Ikiwa nyumba zingine zina ufikiaji mkubwa (kwa mfano maji), weka alama kwenye ramani.

Sasa tafadhali jadili programu, ama kutoka kwa Serikali au kutoka kwa NGOs, CBOs au FBOs. Je! Kuna programu gani katika jamii na zinafanya nini? Ni nyumba zipi zinashiriki? Je! Kuna watu wengine ambao wanashikilia nyadhifa maalum katika mipango ya jamii? Tena, hakikisha uweke alama habari hii yote kwenye ramani ili iweze kueleweka baadaye.

To wrap up the Social Mapping activity, please ask the group to tell you whether there is anything else they would like to include on the map, and why. Now thank everyone for their time and contributions and end the session.

Kufunga shughuli ya Ramani ya Jamii, tafadhali uliza kikundi kukuambia ikiwa kuna kitu kingine chochote ambacho wangependa kujumuisha kwenye ramani, na kwanini. Sasa asante kila mtu kwa wakati na michango yake na maliza kikao.

Thank respondents for their time and conclude the discussion. Washukuru wahojiwa kwa muda wao na umalizie majadiliano

# Annex D – Quantitative Survey Tools

KENYA - NICHE II EVALUATION

BASELINE SURVEY

HOUSEHOLD INSTRUMENT/ DODOSO LA KAYA

Julai 2021

Draft for Training/ Nakala kwa ajili ya mafundisho

- Order of modules is illustrative and can be programmed in CAPI  in different sequence

#### SECTION 0. COVERSHEET / META DATA: KENYA NICHE II - BASELINE SURVEY

| No | Question | Response | No | Question | Response |
| --- | --- | --- | --- | --- | --- |
| 1 | Date of interview Tarehe ya mahojiano [CAPI pre-fill] | ¦___¦___¦ - ¦___¦___¦ - ¦___¦___¦ | 7 | Sub county / Kaunti ndogo | [CAPI pre-fill] |
| 2 | Time start Mda wa kuanza mahojiano (MM:HH) [CAPI pre-fill] | ¦___¦___¦ : ¦___¦___¦ 24-hour clock | 8 | Locality/Community / Eneo/ jamii | [CAPI pre-fill] |
| 3 | Name of supervisor / code Jina la //Namba msimamizi | [CAPI pre-fill] | 9 | Household code / Nambari ya kaya | [CAPI pre-fill] |
| 4 | Name of enumerator / code Jina la //Namba mhojaji | [CAPI pre-fill] | 10 | Name of caregiver and index child / Jina la mlezi na mtoto mlengwa | [CAPI pre-fill] |
| 5 | Region / Mkoa | [CAPI pre-fill] | 11 | Is the household available to be interviewed? / Kaya inapatikana kwa ajili ya mahojiano? | 1 = Yes Ndio 2 = No >> End of interview (Section 00) Apana >> Mwisho wa mahojiano (sehemu ya 00) |
| 6 | County / Kaunti | [CAPI pre-fill] | 12 | Is the target child available at the time of the interview? / Mtoto mlengwa anapatikana wakati wa mahojiano? | 1 = Yes Ndio 2 = No, child is temporarily away/ Apana, mtoto hayupo kwa mda huu 3 = No, child has died / Apana mtoto alifariki |

#### SECTION 00: END OF INTERVIEW/ MWISHO WA MAHOJIANO

| No | Question | Response | No | Question | Response |
| --- | --- | --- | --- | --- | --- |
| 1 | Response status / Matokeo ya mahojiano | 1 = Complete interview Dodoso limekamilika 2 = Partially complete Dodoso limekamilika nusu 3 = Non-contact (location unknown) Haipatikani (kaya haijulikani ilipo) 4 = Refusal Amekataa 5 = Other (specify:Nyingine (ainisha)_________________________) | 4a | Latitude | N ¦___¦¦___¦¦___¦.¦___¦¦___¦¦___¦¦___¦¦___¦ |
|  |  |  | 4b | Longitude | E ¦___¦¦___¦¦___¦.¦___¦¦___¦¦___¦¦___¦¦___¦ |
|  |  |  | 5 | Who was the main respondent of the questionnaire? Nani alikuwa mhojiwa mkuu katika dodoso hili? | [CAPI pre-fill] |
| 2 | Overall Comments/ Observations (If refused, or partially complete, give reasons for refusal; If moved, and within the study districts, give details on contact / location information) / Maoni ya jumla/Mtazamo ((kama alikataa, au limekamilika nusus, toa sababu za kukataliwa: Kama alihama ila yupo katika wilaya za mahojiano peana njia za jinsi ya kumtafuta/alikohamia |  | 6 | Contact number | ¦___¦¦___¦¦___¦¦___¦¦___¦¦___¦¦___¦¦___¦¦___¦ |

#### SECTION 0A. INFORMED CONSENT (CAREGIVER & HOUSEHOLD) RIDHAA YA KUHOJIWA (MLEZI & KAYA)

The informed consent is administered to all main respondents (primary female caregivers of the index child aged up to 24 months or other adult respondent). In the case the primary female respondent is a legal minor (<18 years), the informed consent is administered to her legal guardian and she is administered the assent form. In the case no female caregiver is available, or another member of the household is expected to be the primary respondent for household-level modules, the informed consent is also administered to this member.

Makubaliano haya ya kuhojiwa yatanfwa kwa wahojiwa wakuu wote (mlezi mkuu wa kike wa mtoto mlengwa aliye na umri usiozidi miezi 24 au mhojiwa mwingine ambaye ni mtu mzima). Endapo mhojiwa ni mlezi wa kike aliyekubalika kuhojiwa kisheria (< chini ya miaka 18), makubaliano ya kuhojiwa yatafanywa na msimamizi wake ila yeye atafanya makubaliano ya kukubali kuhojiwa. Endapo hamna mlezi wa kike anapatikana kwa ajili ya mahojiano na kuna mtu mwingine katika kaya atakayeshiriki mahojiano kwa ajili ya maswali yanayohusu kaya, makubaliano haya yatanywa na huyo mhojiwa.

[ENUMERATOR: READ SCRIPT BELOW]/ MHOJAJI SOMA MAELEZO YAFUATAYO

Hello.  My name is __________________ from Dalberg Research, based in Nairobi. In collaboration with the American Institutes for Research, we are conducting a study to understand the living conditions of vulnerable families with young children in this area. Because you have a young child aged up to 24 months, you have qualified for this survey and we would like you, the primary caregiver of [name of the index child] to answer questions about your health, education, economic situation of your household and questions specifically about your children, including [name of the index child]. We would also like to measure the height and weight of [name of the index child].

Habari. Jina langu ni __________________ natokea Dalberg Resaerch, iliyopo Nairobi. Kwa ushirikiano na AIR, tunafanya utafiti ili kuelewa hali ya maisha ya familia zenye watoto wachanga katikla eneo hili. Kwa kuwa una mtoto mchanga mwenye umri chini ya miezi 24 unavigezo vya kushiriki katika utafiti huu, na tungependa wewe kama mlezi mkuu wa [jina la mtoto mlengwa] kujibu maswali kuhusu afya yako, elimu, hali ya uchumi ya kaya yako na maswali mengine kuhusu watoto wako, akiwepo [jina la mtoto mlengwa]. Tungependa pia kupima urefu na uzito wa mwanao [jina la mtoto mlengwa].

The answers provided will help the Department of Children Services, UNICEF Kenya Country Office and the Government of Kenya to understand the living conditions and needs of families like your own. The information will be used to improve services in your district. Approximately 1,000 families are participating in this study in Kitui, Kilifi, Marsabit, Turkana and West Pokot counties.

Majibu yatakayotolewa yatasaidia idara ya watoto, UNICEF Kenya, Ofisi ya County na serikali ya Kenya kuelewa hali ya maisha ya familia na mahitaji ya familia kama hii yako. Taarifa hizi zitaboresha jinsi huduma zinavyotolewa katika wilaya yako. Takriban familia 1,000 zitashiriki katika utafiti huu katika kaunti za Kitui, kilifi, Marsabit, Turkana na West Pokot.

I want to be clear that there is no direct benefit to your household for participating in the survey. If you do not agree to take part in the study, it will not change any services or benefits that your household or any of its members receives now, or may receive in the future. If you agree to participate, you can stop at any time without penalty and without giving me an explanation. You may feel uncomfortable answering some of the questions I may ask you. Please know that you do not have to answer any question you do not want to answer. Simply tell me when you do not want to answer a specific question and I will move to the next. We will not share your answers with anyone in your household or your community. Only the researchers leading this study will have access to the personal details of participants. Your name will be kept separately from your answers in a private, secure location.

Nataka niwe wazi kwamba hakuna faida ya moja kwa moja kwa kaya yako kwa kushiriki katika utafiti huu. Usipokubali kushiriki katika utafiti huu, haitaadhiri huduma au manufaa yoyote ambayo kaya yako au mwanakaya yeyote anapokea kwa sasa, au ambazo anaweza akapokea siku za mbele. Ukikubali kushirikia pia unaweza ukasitisha mahojiano mda wowote ukipenda bila adhabu yoyote  na bila kutoa maelezo. Ukiskia hauko huru kujibu maswali yoyote ambayo nitakuuliza tafadhali elewa kwamba sio lazima kujibu swali lolote ambalo hutaki: unaweza kuniambia swali ambalo hutaki kuibu na nitaendelea na linalofuata. Hatutatoa taarifa zako kwa mtu yeyote katika kaya au jamii. Ni watafiti wanaoongoza utafiti huu tu wataweza kupata taarifa za wahojiwa. Majina na majibu yako yatawekwa tofauti katika sehemu salama.

The questions may take up to 1.5 hours of your time. We will leave a card with information about the study and with telephone numbers in case you would like to know more or you have questions even after our visit. Also, after the interview we may offer you information or a direct referral to services, for example health or other social action services, which could help you in the future. In the case we believe you, or any of the children in your household, are in immediate harm or danger, we are mandated by law to directly refer you to these services.

Mahojiano yanaweza kuchukua hadi lisaa na nusu yam da wako. Tutakuachia kadi yenye taarifa za utafiti huu na pia namba za simu endapo ungetaka kujua Zaidi au utakuwa na maswali hata baada ya sisi kuondoka. Pia, baada ya mahojiano tunaweza kukupa taarifa au huduma za moja kwa moja, mfano afya au huduma za kijamii ambazo zitakusaidia siku za baadaye. Endapo tukiamini kuwa wewe, au watotot katika kaya yako wapo katika hali ya hadhara, tunaruhusiwa kisheria kukuelekeza katika huduma hizo

Finally, due to the coronavirus pandemic, we are taking precautions to protect you and your household, including offering you a mask to wear during the interview - if you wish - and standing two meters apart during the course of the interview. We want to emphasize that there is a risk of contracting the coronavirus in Kenya, and it is spread through face-to-face air droplets. By wearing masks and maintaining distance we will be minimizing the risk of transmission during an interview. If you have any concerns about this or the risk the interview may poise, I’m happy to give you more information.

La mwisho, kwa sababu ya janga la Corona, tunachukua hadhari kukukinga wewe na familia yako, ikiwepo kukupa wewe barakoa ya kuvaa wakati wa mahojiano –kama ukipenda- na kusimama umbali wa mita mbili. Tungependa pia kusisitiza kwamba hadhari ya kuupata ugonjwa huu Kenya ni mdogo, lakini unaenezwa kwa njia ya vitone vya mate kutoka mtu mmoja kwenda mwingine, jambo ambalo linawezekana wakati wa mahojiano. Kama ungependa kujua Zaidi kuhusu madhara, ya mahojiano ninaweza kukupa taarifa Zaidi.

Do you agree to participate, including weighing and measuring your child 0-24 months old? Je unakubalikushiriki, ikiwepo kupima mtoto wako wa umri wa miezi 0-24?

Signature of Enumerator/ Sahihi ya mhojaji ________________________________	Date/ Tarehe ________________

Enumerator: Sign above to witness the verbal consent of the participant. Keep one copy for the PIs records and leave the second copy with the participant.

Mhojaji: Weka sahihi hapo juu kama shahidi wa makubaliano. Weka nakala moja kwa ajili ya mtafiti mkuu na umwachie nakala nyingine mhojiwa.

Who is sponsoring this study? Nani anafadhili utafiti huu?

This research is funded by UNICEF Kenya (the Sponsors). This means that the research team is being paid by the Sponsors for doing the study. If you have questions about this study, you may contact [add name Dalberg Field manager] (Tel: + [add phone]) from Dalberg Research. If you have questions about your rights you may reach out to the AMREF (Tel: +254 20 6994000; 0795746777)  or the American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

Utafiti huu unafadhiliwa na UNICEF Kenya (wafadhili). Hii ina maana watafiti wanalipwa na mfadhili kwa kufanya utafiti huu. Kama una maswali kuhusu utafiti unaweza kuwasikliana na [Ongeza jina la meneja wa Field na namba ya simu] kutoka Dalberg Research. Kama una maswali kuhusu haki zako kama mshiriki unaweza kuwasiliana na AMREF (Tel: +254 20 6994000; 0795746777) au American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

#### SECTION 0B. INFORMED ASSENT (CAREGIVER & HOUSEHOLD, LEGAL MINORS) SECTION 0B. RIDHAA YA KUSHIRIKI (MLEZI NA KAYA, WATOTO WADOGO KWA MJIBU WA SHERIA)

The assent is administered to all female caregivers who are legal minors (<18 years), while the informed consent is administered to her legal guardian.

Makubaliano haya yanafanywa kwa walezi wote wa kike ambao wapo chini ya miaka 18, ilihali Makubaliano ya kuhojiwa ni ya msimamizi wa mlezi.

[ENUMERATOR: READ SCRIPT BELOW]

Hello.  My name is __________________ from Dalberg Research, based in Nairobi. In collaboration with the American Institutes for Research, we are conducting a study to understand the living conditions of vulnerable families with young children in this area. Because you have a young child aged up to 24 months, you have qualified for this survey and we would like you, the primary caregiver of [name of the index child] to answer questions about your health, education, economic situation of your household and questions specifically about your children, including [name of the index child]. We would also like to measure the height and weight of [name of the index child].

Habari. Jina langu ni __________________ natokea Dalberg Resaerch, iliyopo Nairobi. Kwa ushirikiano na AIR, tunafanya utafiti ili kuelewa hali ya maisha ya familia zenye watoto wachanga katikla eneo hili. Kwa kuwa una mtoto mchanga mwenye umri chini ya miezi 24 unavigezo vya kushiriki katika utafiti huu, na tungependa wewe kama mlezi mkuu wa [jina la mtoto mlengwa] kujibu maswali kuhusu afya yako, elimu, hali ya uchumi ya kaya yako na maswali mengine kuhusu watoto wako, akiwepo [jina la mtoto mlengwa]. Tungependa pia kupima urefu na uzito wa mwanao [jina la mtoto mlengwa].

The answers provided will help the Department of Children Services, UNICEF Kenya Country Office and the Government of Kenya to understand the living conditions and needs of families like your own. The information will be used to improve services in your district. Approximately 1,000 families are participating in this study in Kitui, Kilifi, Marsabit, Turkana and West Pokot counties.

Majibu yatakayotolewa yatasaidia idara ya watoto, UNICEF Kenya, Ofisi ya County na serikali ya Kenya kuelewa hali ya maisha ya familia na mahitaji ya familia kama hii yako. Taarifa hizi zitaboresha jinsi huduma zinavyotolewa katika wilaya yako. Takriban familia 1,000 zitashiriki katika utafiti huu katika kaunti za Kitui, kilifi, Marsabit, Turkana na West Pokot.

I want to be clear that there is no direct benefit to your household for participating in the survey. If you do not agree to take part in the study, it will not change any services or benefits that your household or any of its members receives now, or may receive in the future. If you agree to participate, you can stop at any time without penalty and without giving me an explanation. You may feel uncomfortable answering some of the questions I may ask you. Please know that you do not have to answer any question you do not want to answer. Simply tell me when you do not want to answer a specific question and I will move to the next. We will not share your answers with anyone in your household or your community. Only the researchers leading this study will have access to the personal details of participants. Your name will be kept separately from your answers in a private, secure location.

Nataka niwe wazi kwamba hakuna faida ya moja kwa moja kwa kaya yako kwa kushiriki katika utafiti huu. Usipokubali kushiriki katika utafiti huu, haitaadhiri huduma au manufaa yoyote ambayo kaya yako au mwanakaya yeyote anapokea kwa sasa, au ambazo anaweza akapokea siku za mbele. Ukikubali kushirikia pia unaweza ukasitisha mahojiano mda wowote ukipenda bila adhabu yoyote  na bila kutoa maelezo. Ukiskia hauko huru kujibu maswali yoyote ambayo nitakuuliza tafadhali elewa kwamba sio lazima kujibu swali lolote ambalo hutaki: unaweza kuniambia swali ambalo hutaki kuibu na nitaendelea na linalofuata. Hatutatoa taarifa zako kwa mtu yeyote katika kaya au jamii. Ni watafiti wanaoongoza utafiti huu tu wataweza kupata taarifa za wahojiwa. Majina na majibu yako yatawekwa tofauti katika sehemu salama.

The questions may take up to 1.5 hours of your time. We will leave a card with information about the study and with telephone numbers in case you would like to know more or you have questions even after our visit. Also, after the interview we may offer you information or a direct referral to services, for example health or other social action services, which could help you in the future. In the case we believe you, or any of the children in your household, are in immediate harm or danger, we are mandated by law to directly refer you to these services.

Mahojiano yanaweza kuchukua hadi lisaa na nusu yam da wako. Tutakuachia kadi yenye taarifa za utafiti huu na pia namba za simu endapo ungetaka kujua Zaidi au utakuwa na maswali hata baada ya sisi kuondoka. Pia, baada ya mahojiano tunaweza kukupa taarifa au huduma za moja kwa moja, mfano afya au huduma za kijamii ambazo zitakusaidia siku za baadaye. Endapo tukiamini kuwa wewe, au watotot katika kaya yako wapo katika hali ya hadhara, tunaruhusiwa kisheria kukuelekeza katika huduma hizo

Finally, due to the coronavirus pandemic, we are taking precautions to protect you and your household, including offering you a mask to wear during the interview - if you wish - and standing two meters apart during the course of the interview. We want to emphasize that there is a risk of contracting the coronavirus in Kenya, and it is spread through face-to-face air droplets. By wearing masks and maintaining distance we will be minimizing the risk of transmission during an interview.  If you have any concerns about this or the risk the interview may poise, I’m happy to give you more information.

La mwisho, kwa sababu ya janga la Corona, tunachukua hadhari kukukinga wewe na familia yako, ikiwepo kukupa wewe barakoa ya kuvaa wakati wa mahojiano –kama ukipenda- na kusimama umbali wa mita mbili. Tungependa pia kusisitiza kwamba hadhari ya kuupata ugonjwa huu Kenya ni mdogo, lakini unaenezwa kwa njia ya vitone vya mate kutoka mtu mmoja kwenda mwingine, jambo ambalo linawezekana wakati wa mahojiano. Kama ungependa kujua Zaidi kuhusu madhara, ya mahojiano ninaweza kukupa taarifa Zaidi.

Signature of Enumerator/ Sahihi ya mhojaji ________________________________	Date/ Tarehe ________________

Enumerator: Sign above to witness the verbal consent of the participant. Keep one copy for the PIs records and leave the second copy with the participant.

Mhojaji: Weka sahihi hapo juu kama shahidi wa makubaliano. Weka nakala moja kwa ajili ya mtafiti mkuu na umwachie nakala nyingine mhojiwa.

Who is sponsoring this study? Nani anafadhili utafiti huu?

This research is funded by UNICEF Kenya (the Sponsors). This means that the research team is being paid by the Sponsors for doing the study. If you have questions about this study, you may contact [add name Dalberg Field manager] (Tel: + [add phone]) from Dalberg Research. If you have questions about your rights you may reach out to AMREF (Tel: +254 20 6994000; 0795746777) or the American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

Utafiti huu unafadhiliwa na UNICEF Kenya (wafadhili). Hii ina maana watafiti wanalipwa na mfadhili kwa kufanya utafiti huu. Kama una maswali kuhusu utafiti unaweza kuwasikliana na [Ongeza jina la meneja wa Field na namba ya simu] kutoka Dalberg Research. Kama una maswali kuhusu haki zako kama mshiriki unaweza kuwasiliana na AMREF (Tel: +254 20 6994000; 0795746777) au American Institutes for Research Institutional Review Board (Tel: +1 2024035542).

#### SECTION 1: HOUSEHOLD ROSTER / ORODHA YA WANAKAYA

Instruction: For this section, we would like to know about each person who use this household as their main place of residence and are part of the household. By part of the household, I mean do they still live here and eat from the same pot or share economic resources. People who are usually here, but who are temporarily away, at a hospital or at boarding school still count as household members if they plan to return. Please include any children who are fostered into the household and any servants (houseboy or housegirl)./Kwa kipengele hiki, tungependa kujua kuhusu kila mmoja ambaye anatumia kaya hiina hapa ndio makazi yake ya siku zote. Kuwa mmoja wa kaya hiinamaanisha bado wanaishi hapa na kula hapa ama kutumia raslimali za hii kaya.Watu ambao huishi hapa lakini kwa muda huwa nje ya kaya katika hospitali ama shule za kulala bado wanachukuliwa kuwa watu wa kaya hiiiwapo wanapanga kurudi kuishi kwa hii boma.Tafadhali jumuisha watoto ambao hulelewa apa japokuwa si wa kuzaliwa hapa ama wafanyakazi wa hii kaya.

| 1 |  | 2 |  | 3 |  | 4 |  |  | 5 |  |  |  |  | 8 |  |  | 9 |  | 10 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | ONLY FOR MEMBERS AGE 10 AND OLDER/KWA WATU WALIO NA MIAKA KUMI NA ZAIDI PEKE YAO |  |  |  |  |  | 11 |  |
| ID/KITAMBULISHO |  | Name of the member/Jina la Mwanakaya Put household head first in list./Anzia na jina la mkuu wa kaya/boma Then list all household members in decreasing order of age (approximate)/Kisha fuatiliza majina ya wanakaya wengine katika kaya hiiukianza na wenye umri mkubwa kwenda kwa wenye umri mdogo. CHECK that no babies or small children have been omitted/Hakikisha hakuna watoto wadogo walioachwa nyuma / hawajaandikishwa |  | Sex/Jinsia 1 = Male/Mme 2 = Female/ Mke |  | What is [NAME’S] relationship with the head?/Uhusiano wa [JINA] na mkuu wa kaya/ boma 1 = Head/Mkuu wa kaya 2 = Spouse/Mwenza 3 Son/Daughter/ mtoto/ mwanae 4 = Grandchild/Mjukuu 5 = Parent/Parent-in-law/ Mzazi/Mzazi Mkwe 6 = Son/Daughter-in-law/ Mshika mwana 7 = Other relative/Ndugu mwingine 8 =Adopted/Mtoto wa kambo 9= Foster 10= Kaffala 11= Step child 12 = House help/Kijakazi 13 = Non-relative/Hatuhusiani |  |  | How old is [NAME] now?/ Record exact age in completed years for all members. For those under 36 months, also record the number of months since the last birthday (use child health book or birth certificate if available.)/Andika umri kamili kwa miaka iliyoitimizwa kwa kila mmoja katika kaya.Kwa waliyo chini ya miezi thelathini na sita,andika nambari ya miezi waliyonayo tangu mara ya mwisho ya siku ya kuzaliwa (tumia cheti cha kuzaliwa ama kitabu cha matibabu kama kipo) |  |  |  |  | What is [NAME’S] present marital status?/ Gani hali ya [JINA] ya ndoa kwa sasa? 1 = Married or living together, monogamous/Niko kwenye ndoa,tunaishi pamoja,mke moja 2 = Married or cohabiting, polygamous/Katika ndoa au kuishi pamoja wake wengi 3 = Divorced or separated/Tumetalakiana au tumetengana 4 = Widowed/Mjane au Mgame 5 = Never married or cohabited/ Sijawai kuwa katika ndoa ama kuishi na mchumba If 3 – 5 >> next member |  |  | Does [NAME’S] spouse or partner live in this household?/ Je mke/mwenza wa [JINA] huishi katika hii kaya? 1 = Yes/ Ndio 2 = No/ Apana (>> next member)/ >> mwanakaya anayefuata |  | 7 COPY THE I.D. CODE OF THE SPOUSE (IF MORE THAN ONE SPOUSE, THE FIRST ONE) | How long [NAME’S] has been living in the household? (Answer if question 4 is answered by 8=adopted, 9=Foster, 10 Kaffala, 11=stepchild., 12=househelp, 13=non-relative) |  |
|  |  |  |  |  |  |  |  |  | AGE IN YEARS/ UMRI KWA MIAKA |  | IF <36 MONTHS: MONTHS SINCE LAST BDAY/ ENDAPO CHINI YA MIEZI THELATHINI NA SITA:NI MIEZI MINGAPI TANGU SHEREHE YA MWISHO YA SIKU YA KUZALIWA |  |  |  |  |  |  |  |  | In Months…… |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 |  | 2 |  | 3 |  | 4 | 5 |  | 6 |  | 7 | 8 |  | 9 | 10 |  | 11 |  |  |
|  | MEMBERS AGE 0 – 19 YEARS/ WANAKAYA WA UMRI WA MIAKA KATI YA SUFURI NA KUMI NA TISA |  |  |  |  |  |  |  |  |  |  |  | MEMBERS AGE 0-5/ WANAKAYA WA UMRI KATI YA SUFURI NA MIAKA MITANO |  |  |  |  |  |  |  |
| ID | Is the biological mother of [NAME] alive?/ Mama mzazi wa [JINA] yuko hai? WRITE ID =YES, MOTHER LIVES IN HOUSEHOLD/ ANDIKA KITAMBULISHO=NDIO, MAMA MZAZI HUISHI KATIKA KAYA HII 88=YES, BUT MOTHER NOT IN HOUSEHOLD/ 88 =NDIO, ILA MAMA HAYUPO KWA KAYA 99=NO, MOTHER IS DEAD/ 99 = APANA, MAMA ALIFARIKI 77=DON’T KNOW/ 77 = SIJUI |  | Does [NAME] have biological siblings from the same mother (living in or out of the household)?/Je [JINA] ana kaka au dada wa mamake mzazi (wanaoishi hapa au nje ya kaya) 1=YES/ 1= NDIO 2=NO/ 2=APANA 9=DON’T KNOW/ 9=SIJUI |  | How many biological siblings are younger than [NAME]? /Je [JINA] ana kaka na dada wangapi wa mamake mzazi walio chini yake kiumri? [Enter number, if none = 0] [Andika idadi, kama hakuna weka 0] |  | Is the biological father of [NAME] alive?/ Babake mzazi wa [JINA] yuko hai? WRITE ID =YES, FATHER LIVES IN HOUSEHOLD 88=YES, BUT FATHER NOT IN HOUSEHOLD 88 =NDIO, ILA BABA HAYUPO KWA KAYA 99=NO, FATHER IS DEAD 99 = APANA, BABA ALIFARIKI 77=DON’T KNOW 77 = SIJUI | Does [NAME] have a pair of shoes or sandals?/ Je [JINA] ana viatu au ndala zozote? 1=YES/ 1= NDIO 2=NO/ 2=APANA 9=DON’T KNOW/ 9=SIJUI |  | Does [NAME] have at least 2 sets of clothes?/ Je [JINA] ana nguo angalau seti mbili? 1=YES/ 1= NDIO 2=NO/ 2=APANA 9=DON’T KNOW/ 9=SIJUI |  | Does [NAME] have a blanket?// Je [JINA] ana blanketi? 1=YES/ 1= NDIO 2=NO/ 2=APANA 9=DON’T KNOW/ 9=SIJUI | Does [NAME] have a birth certificate? / Je [JINA] ana cheti cha kuzaliwa? If yes, may I see it?/Kama ndio naomba nikione 1=Yes, seen/ 1=Ndio nimeona 2=Yes, not seen/ 2=Ndio, sijaona 3=No/ 3=Apana |  | Has [NAME]’s birth been registered?/Cheti cha kuzaliwa cha [JINA] kimesajiliwa? 1=YES/ 1= NDIO 2=NO/ 2=APANA 9=DON’T KNOW/ 9=SIJUI | When was [NAME]’s birth registered? Je kuzaliwa kwa [JINA] kilisajiliwa lini? 1=Within 90 days from birth/ 1=Ndani ya siku tisini kutoka siku ya kuzaliwa 2=Between 3 months and 1 year since birth/ 2=Kati ya miezi mitatu na mwaka mmoja tangu kuzaliwa 3=After 1 year since birth/ 3= Mwaka mmoja baada ya siku ya kuzaliwa (>>NEXT SECTION) SEHEMU INAYOFUATA |  | What is the main reason why [NAME]’s birth is not registered? Kwanini kuzaliwa kwa [JINA] hakukusajiliwa? 1=Costs too much/ 1=Hugharimu pesa nyingi 2=Must travel too far/ 2=Hubidi kusafiri mbali sana 3=Did not know it should be registered/ 3=Sikujua kunafaa kusajiliwa 4=Did not find it important/ 4=Sikuona umuhimu wa kusajili 5=Do not know where to register/ 5=Sijui kwa kusajili 6=Other (specify)/ 6=Sababu nyingine (eleza) 9=Don’t know/ 9=Sijui |  |  |
| 01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#### SECTION 2: EDUCATION OF ALL HOUSEHOLD MEMBERS AGED 3 YEARS OR OLDER/ ELIMU YA WANAKAYA WOTE WALIO NA UMRI WA MIAKA 3 NA KUENDELEA

|  | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MEMBERS AGED 3 OR OLDER/WATU WALIO NA MIAKA MITATU AMA ZAIDI |  |  |  |  |  |  |  |  |  |  |  |  |
| ID | Can [NAME] read and write in any language?/[JINA] ana uwezo wa kusoma na kuandika kwa lugha yoyote? 1=Swahili 1=Swahili 2= English 2=Kiingereza 3=Other 3=Nyingine 4=None 4=Hakuna | Has [NAME] ever attended school?/[JINA] amewahi kwenda shuleni? 1=Yes >>Q4 1=Ndio >>Q4 2=No 2=Apana | What was the main reason [NAME] never attended school?/ Ni sababu gani haswa ilifanya [JINA] kutoenda shuleni? [SEE CODES BELOW] >>NEXT PERSON [ANGALIA MAJIBU HAPO CHINI] >> SEHEMU INAYOFUATA | What is the highest level [NAME] completed? [SEE CODES BELOW]/ Ni kiwango gani cha juu cha elimu [JINA] alimaliza? |  | Is [NAME] currently attending school?/[JINA] huenda shuleni kwa sasa? 1=Yes >> Q7 1=Ndio >>Q7 2=No 2=Apana | Why is [NAME] not currently in school?/ Kwa nini [JINA] haendi shuleni kwa sasa? [SEE CODES BELOW] >> Next Person [ANGALIA MAJIBU HAPO CHINI] >>Q9a | Which grade is [NAME] attending?/[JINA] anasoma darasa/daraja, ama kidato kipi? [SEE CODES BELOW] [ANGALIA MAJIBU HAPO CHINI] | In the last full week of school, how many days did [NAME] attend the full day? Kwa wiki nzima ya masomo iliyopita ni siku ngapi [JINA] alihudhuria siku nzima? [0-5 days exclude weeks with no school] [Siku 0-5 Usiulize kuhusu wiki zisizo za shule] | In the last 12 months, how much have you spent for [NAME] on the following items:/ Kwa muda wa miezi 12 iliyopita,ni pesa ngapi umetumia na [JINA] kwa vitu vifuatavyo: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Enrollment fees (In Ksh)/ Karo ya kuingia shule (pesa za Kenya) | School books and other school supplies (In Ksh)/ Vitabu vya shule na vitu vingine vya shule | School uniform or sports clothes (In Ksh)/ Nguo za shule ama za michezo shuleni | School transportation (In Ksh)/ Nauli ya shule |
| Codes for Q4: 1.No formal education 2.Primary education incomplete 3.Primary education complete 4.Secondary education, incomplete 5.Secondary education, complete 6.Some secondary vocational training / some certificate 7.Diploma Incomplete 8.Diploma Complete 9.College/University incomplete 10.Complete university Degree 11.post-graduate university degree 12.Other 13.DK/Refused to answer |  |  |  |  | Codes for Q7: Pre-primary 1 ….01 Pre-primary 2……02 Lower primary Grade 1 ………..03 Grade 2 …………04 Grade 3 …………05 Upper primary Grade 4 …………06 Grade 5…………07 Grade 6…………08 Lower primary Grade 7…………09 Grade 8…………10 Grade 9…………11 Senior school Grade 10…………12 Grade 11…………13 Grade 12…………14 |  |  | Codes for Q3 & Q6: Too young/ Mdogo sana 1 Already attained the level they wanted/ Alifikisha kiwango alichokua anataka 2 Required for work or care activities including on farm or household/ Anatakikana kwenye kazi au kutunza ikiwepo kazi ya shambani.. 3 Not interested in school/ Hataki shule 4 Too expensive to go to school/ Ni ghali sana kwenda shule 5 School too distant/ Shule iko mbali 6 Not appropriate for female children to go to school (culture)/ Sio vizuri kwa wasichana kwenda shule (kwa tamaduni zetu) 7 Schooling believed not to increase income/ Inaaminika kwenda shule hakuongezi kipato 8 Could learn everything useful at home/ Anaweza kujifunza mambo yote muhimu hapa nyumbani 9 |  |  | Too sickly to attend/ Ni mgonjwa sana hawezi kwenda 10 No places available in local school/ Hakuna nafasi katika shule ya hapa karibu 11 No school of appropriate religion Available/ Hakuna shule inayofaa ya dini inapatikana 12 Not safe/ Sio salama 13 Got pregnant or married/ Alipata mimba au aliolewa 14 Due to COVID-19/ Kutokana na Covid-19 (Corona) ………...……………………….15 Child has disability / learning limitation/ Ana ulemavu/ kutoweza kusoma ………….…16 Other reason (specify)/ Nyingine (elezea) 17 |  |  |

#### SECTION 3A: HEALTH OF ALL HOUSEHOLD MEMBERS/AFYA YA WATU WOTE WA KAYA

|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Has [NAME] been sick or injured during the last 4 weeks?/ [JINA] amekuwa mgonjwa ama kupata jeraha kwa wiki mbili zilizopita? 1=Yes, sick/ injured/Ndio amekuwa mgonjwa ama amepata jeraha 2=No/Apana>>Q8 9=Don’t know/Sijui>>Q8 | During the last 4 weeks, did [NAME] have to stop the usual activities because of this condition?/Kwa muda wa wiki mbili zilizopita, [JINA] aliachana na kazi zake za kawaida kwa sababu ya hali hio? 0=No/Apana IF YES: PUT NUMBER OF DAYS/ (1 – 14)/ KAMA NDIO WEKA IDADI YA SIKU (1-14) | During the last 4 weeks has [NAME] consulted a health practitioner, visited a health facility or consulted a traditional healer for this injury/illness?/Kwa muda wa wiki mbili zilizopita [JINA] amemwona mhudumu wa afya, kutembelea hospitali ama mganga wa kienyeji kwa sababu ya ugonjwa huu /jeraha 1=YES /NDIO(>>Q6) 2=NO/APANA | If no, what was the main reason not to?/ Iwapo apana,sababu gani haswa ilifanya akose? 1=Lack of money/ too expensive/ 1=Kukosa pesa/malipo ni ghali mno 2=Too far/ 2=ni mbali sana 3=Do not believe in medicine/ 3=Sina//Hana imani na dawa 4=Lack of health professionals/ 4=Kukosekana kwa wataalamu wa afya 5=Poor quality/services/ 5=Huduma duni/ hafifu 6=Did not require medical assistance/not severe enough/ 6=Hakuhitaji matibabu/ haukua mkubwa 7=Due to COVID-19/ 7=Kwa sababu ya Corona 8=Other, specify/ 8=Sababu nyingine (elezea) >>Q8 | On the most recent visit whom did [NAME] consult?/ Kwa matibabu ya hivi punde [JINA] alimtembelea nani? 01=Doctor/Daktari 02=Dentist/Daktari wa meno 03=Nurse/Nesi 04=Medical assistant/Msaidizi wa huduma ya afya 05=Midwife/ Mkunga 06=Pharmacist/Farmacia 07=Drug/chemical seller/Muuza dawa 08=Community Health Worker/Mhudumu wa afya wa kijiji (APE) 09=Traditional Healer/Mganga wa kienyeji 10=Trained TBA 11=Untrained TBA 12=Spiritualist 13=Other (specify)/Mwingine,(eleza) 98=DK/SIJUI [Mark all that apply] | Where did the consultation take place?/Huduma ilifanyika wapi? 1=Public facility/Kituo cha umma 2=Private Facility/Kituo cha kibinafsi 3=Pharmacy/Duka la dawa 4=APE house 5=Traditional Healer/Kwa mganga wa kienyeji 6=Drug store/Chumba cha dawa 7=Drug seller/Kwa muuzaji wa dawa 8= Other (Specify)/Kwingineko(eleza) 9=DK/Sijui [Mark all that apply] | How much in total was spent on [NAME]’s medication and consultation in the last 4 weeks?/ Ni hela ngapi kwa jumla zilitumika na [JINA] kugharamia matibabu na huduma kwa wiki mbili zilizopita? [Include both cash and in kind] [GIVE AMOUNT IN Ksh] [ENTER ‘00’ IF NONE] | During the last 4 weeks did [NAME] buy any medicine or medical supplies?/ Kwa muda wa wiki mbili zilizopita [JINA] ameweza kununua dawa zozote ama bidhaa zinazohusiana na matibabu? [OTHER THAN ALREADY INCLUDED IN Q7!] TOFAUTI NA ZILIZOANDIKWA KWENYE Q7!] 1=YES/ NDIO 2=NO APANA (>>Q10) | How much in total was spent on [NAME]’s medicine or medical supplies in the last 4 weeks?/ Ni hela ngapi zilizotumika na [JINA] kwa dawa na bidhaa zingine za matibabu kwa wiki mbili zilizopita? [GIVE AMOUNT IN Ksh] | Does [NAME] have any disability that limits his/her full participation in life activities: such as seeing, hearing, walking, remembering, self-care or communicating? / Je,[JINA] ana ulemavu wowote ambao humzuia kutekeleza kikamilifu kazi katika maisha:kama vile kuona,kusikia,kutembea,kukumbuka,kujitunza ama kuwasiliana? 1=YES/NDIO 2=NO/LA (>> Q12) | What type of disability does [NAME] have?/ Ni ulemavu wa aina gani [JINA] anao? 1=Blind/Kipofu 2=Deaf/Mute/Kiziwi 3=Mental Deficiency/Akili punguani 4=Paralyzed/Kupooza 5=Stunted or amputated arm/Kukatwa mkono ama usiokua 6=Stunted or amputated leg/Kukatwa mguu ama mguu usiokua 7=Other, specify/Sababu nyingine (eleza) [Record up to 3 disabilities] |  |  | Did [NAME] sleep under a mosquito net last night?/ Je, [JINA] alilala ndani ya neti ya mbu usiku uliopita 1= Yes, untreated/Ndio,isiyotibiwa 2= Yes, treated/Ndio,iliyotibiwa 3= No/Apana 9= DK/Sijui |
|  |  |  |  |  |  |  |  |  |  |  | 1st | 2nd | 3rd |  |

#### SECTION 3B: FERTILITY & REPRODUCTIVE HEALTH OF WOMEN 10 – 49 YEARS OLD/UWEZO WA KUPATA MTOTO NA AFYA YA WANAWAKE WENYE UMRI WA MIAKA 10 – 49

|  | 1 | 2 | 3 | 4 | 5 |  | 6a |  | 6b | 6c | 6d | 6e | 7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ASK FOR ALL BETWEEN 10-49 YEARS/ULIZA KWA WOTE WALIO KATI YA KUMI NA AROBAINI NA TISA |  |  |  |  |  |  |  |  |  |  |  |
| ID | Is [NAME] pregnant now or has [NAME] been pregnant in the last 24 months?/ Je, [JINA] ni mjamzito kwa sasa ama [JINA] amekuwa na ujauzito ndani ya miezi ishirini na minne iliyopita? 1=YES/NDIO 2=NO/APANA (>>Q8) 9=DK/SIJUI (>>Q8) | Did [NAME] see anyone for antenatal care during this / last pregnancy?/ [JINA] alimwona yeyote kwa afya ya mtoto kwa muda huu wa ujauzito/mara ya mwisho ya ujauzito? 1=YES/ /NDIO(>>Q4) 2=NO/APANA | What is the main reason [NAME] didn’t go for antenatal care?/ Ni kwa sababu gani [JINA] hakweda kwa huduma ya afya ya mtoto? [SEE CODES BELOW] | Whom did [NAME] see?/ Ni nani [JINA] aliye enda kuona? [SEE CODES BELOW: MARK ALL THAT APPLY] | How many times did [NAME] receive antenatal care during this / last pregnancy?/ Ni mara ngapi [JINA] alipata huduma ya afya ya mtoto na mama wakati huu wa ujauzito/ujauzito wa mwisho uliopita? [number] 98= DK/SIJUI |  | During any of your antenatal care was any of the following done at least once?/Katika kipindi cha huduma ya afya ya mama mjamzito,kuna lolote kati ya mambo haya alilofanyiwa angalau mara moja?: |  |  |  |  |  | Who attended the birth of this / last pregnancy? Nani alihudumia kujifungua kwa mimba hii/ujauzito uliopita? [SEE CODES BELOW, MARK ALL THAT APPLY] 8 = Have not yet given birth/ Bado sijajifungua 9 = Lost baby / still birth/ Nilimpoteza mtoto/mtoto alifariki |
|  |  |  |  |  |  |  | Were you weighed?/ Ulipimwa uzito wa mwili? 1=YES/NDIO 2=NO/APANA | Was your blood pressure measured?/ Ulipimwa damu kudhibiti sinikizo? 1=YES/NDIO 2=NO/APANA |  | Was your Hemoglobin level measured?/ Je kiwango chako cha haemoglobin kilipimwa? | Did you receive IFA (Iron and folic acid) tablets?/Uliweza kupata tembe au dawa ya maji ya IFA (madini ya iron na Folic)? 1=YES/NDIO 2=NO/APANA | During the whole pregnancy, for how many days did you take the IFAs tablets or syrup? [number of days] Kwa kipindi chote cha uja uzito, ni siku ngapi ulitumia tembe au dawa ya IFA (madini ya iron na Folic)? [Idadi ya siku] |  |
| Codes for Q3 Economic reasons/ Shida za kiuchumi……………… 01 No health care available/ Hakuna huduma za afya…………… 02 Health care too far/ Huduma za afya ziko mbali sana…………… 03 Not necessary/ Sio muhimu .......................................... 04 Health personnel not friendly/ Wahudumu wa afya sio wastaarabu 05 Long waits at facilities/ KMda mrefu wa kusubiri katika kituo….. 06 Prefers community midwives/ Kupendelea wakunga wa hapa kijijini.. 07 Due to COVID-19/ Kutokana na Covid-19 (Corona) ……………….08 Other, specify Nyingine (elezea) …………………………….. 09 |  |  |  |  |  | Codes for Q7 Doctor/ Daktari 01 Nurse/ Nesi/Mhudumu 02 Auxiliary midwife/ Mkunga 03 Traditional birth attendant/ Mhudumu wa kienyeji… 04 Community health worker/ Mhudumu wa afya ya jamii 05 Midwife/ Mkunga 06 Other, specify/ Nyingine (eleza) 07 |  |  |  |  |  |  |  |

|  | 8 | 9 | 10 | 11a | 11b |  | 12 | 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ASK FOR ALL BETWEEN 10-49 YEARS |  |  |  |  |  |  |  |
| ID | Has [NAME] ever given birth?/ [JINA] amewahi kujifungua mtoto? 1=YES/NDIO 2=NO/APANA >> NEXT WOMAN | In total, how many children has [NAME] given birth to who were born alive?/ Kwa jumla,ni watoto wangapi ambao [JINA] amewahi kupata wakiwa hai? | How many children has [NAME] has given birth to who were born alive, but do not live in this household?/ Ni watoto wangapi ambao [JINA] amewapata wakiwa hai lakini hawaishi kwa hii kaya? [number] If 0 >> Q13 | How many of these are children (under 18 years old)?/ Ni wangapi kati ya hawa ambao bado ni watoto (wana umri wa miaka chini ya 18)? [number] If 0 >> Q13 | Where are these children now (mark for each)?/ Hawa watoto wako wapi kwa sasa? (sahihisha kwa kila mmoja) [SEE CODES BELOW] |  | What is the primary reason the children are not living with you (mark for each)?/ Ni kwa sababu gani haswa hawa watoto hawaishi na wewe? (sahihisha kwa kila moja) [SEE CODES BELOW] | Has [NAME] ever given birth to a child who was born alive but later died?/ [JINA] amewahi kujifungua mtoto aliye hai lakini baadaye akafariki? [IF NO, PROBE: I mean, to a child who ever breathed or cried or showed other signs of life – even if he or she lived only a few minutes or hours?] [KAMA APANA DADISI: Namaanisha kwa mtoto ambaye alipumua, au alilia au kuonyesha dalili za kuwa hai hata kama aliishi tu dakika/ masaa chache] [Enter total number, 0 if none] |
| Codes for Q11b Extended family/ Kwa wanafamilia wengine ………01 Host Centre/ Kituo cha watoto 02 Host Family/ Katika familia ya kufikia 03 Guardian/ Kwa mtunzaji/ msimamizi 04 Lives independently alone or with own family/ Anajikasha peke yake au ana familia yake binafsi ………………………05 Lives independently on street or outside/ Anajikalisha kwenye mitaa au uko nje tu 06 Other, specify/ Nyingine (eleza) 07 DK/ SIJUI………………………….09 |  |  |  |  |  | Codes for Q12 Economic reasons/Sababu za kiuchumi 01 Education reasons/ Sababu za kielimu02 Health reasons/ Sababu za kiafya 03 Conflict/violence/ Mzozo au fujo 04 They have own family/ Ana familia yake 05 Other, specify Nyingine (eleza) 06 |  |  |

#### SECTION 3B: FERTILITY & REPRODUCTIVE HEALTH OF WOMEN 10 – 49 YEARS OLD (continued)

#### SECTION 4: HOUSING CONDITIONS /HALI YA KAYA

This section taken directly from the IOF 2015 with additions from MICS 6.

|  | Question | Answers | Skip |
| --- | --- | --- | --- |
| 1 | What is the main source of drinking water used by members of this household?/Ni kipi chanjo kikuu cha maji yanayotumika katika kaya hii? | Water piped inside the house/ Maji ya mfereji ndani ya nyumba ……………………………… 1 Water piped to the yard/Maji ya mfereji kwa kaya 2 Water piped to neighbour’s house/ Maji ya mfereji kutoka kwa jirani 3 Fountain water/ Maji ya kisima 4 Water hole/ Maji ya kisima cha kuchimbwa chini 5 Well water with manual pump/ Maji ya kisima cha bomba ya kutumia mikono 6 Protected well water without pump/ Kisima kilichojengewa ukuta bila bomba ya kupiga maji 7 Water from protected spring/ Maji ya chemichemi iliolindwa kwa kujengewa ukuta 8 Water from unprotected spring/ Maji ya chemichemi isiyojengewa ukuta 9 Water from the cistern (or mobile tank or truck)/ Maji yanayosafirishwa (na lori ama tenki 10 Unprotected water from hollow/ Maji yasiyo kingwa ya kisima 11 River, lagoon, or lake water/ Maji ya mto,kando ya ziwa ama ya ziwa 12 Rainwater/ Maji ya mvua 13 Bottled water/ Maji ya chupa 14 Other (specify)/ Kwingineko (eleza ……………15 | >>Q4 |
| 2 | Where is the water source located?/ Chanjo hicho cha maji kiko wapi? | In own dwelling/ Katika nyumba yangu….……1 In own yard/plot/ Katika makaazi/ ploti………..2 Elsewhere/ Kwingine ….……………………….3 |  |
| 3 | How long does it take to go there, get water and come back? / Inachukua mda gani kufika katika chanjo hicho na kurudi hapa nyumbani? | Minutes / Dakika……………………………… 999= Don’t know/ Sijui |  |
| 4 | Treats water in any way to make it safe to drink?/Hutibu maji kwa njia yoyote kuifanya iwe safi ya kunywa? | 1= Yes/Ndio 2= No/Hapana 9= Don’t know/Sijui | If 2-9 >> Q5 |
| 5 | What do you usually do to make the water safe to drink/Huwa wafanya nini kuyafanya maji kuwa safi ya kunywa? [Mark all that apply] | Boiling 1 (Kuchemsha) Add bleach/Chlorine 2 (Kuongeza Chlorine/bleach) Filter with a cloth 3 (Chunga na kitambaa) Use water filter (ceramic, sand, compost) 4 (Hutumia kichungi cha maji ) Solar disinfection 5 (Huanika maji kwa jua kuondoa bacteria) Let it stand and settle 6 (Huacha maji kukaa na kutulia) Other (specify) 8 (Jinsi nyingine (eleza) |  |
| 6 | Now I would like to talk about handwashing. When do you wash your hands?/Sasa ningependa kuongelea kuhusu unawaji mikono.Ni lini huwa unanawa mikono? [MULTIPLE RESPONSE POSSIBLE. DO NOT READ THE CHOICES BUT PROBE AND MARK ALL THAT APPLY] YES/NDIO= 1 NO/HAPANA= 2 | Before food preparation 1 (Kabla ya kutayarisha chakula) Before eating 2 (Kabla ya kula) Before feeding children 3 (Kabla ya kulisha watoto) After defecation 4 (Baada ya haja kubwa) After cleaning baby’s bottom 5 (Baada ya kuosha mtoto pande ya nyuma) Other (specify) 6 (Nyingige (eleza) |  |
| 7 | [Enumerator: Observe presence of water at the place for handwashing, verify by checking the tap/pump, or basin, bucket water container or similar objects for presence of water] [Mhoji: Kagua kama kuna maji sehemu ya kunawa, hakiki kwa kuangalia bomba/pampu, au karai au ndoo] | Water is available/ Maji yapo 1 Water is not available/ Maji hayapo 2 |  |
| 8 | Is there soap or detergent, or ash/mud/sand present at the place for handwashing or in the house?/ Kuna sabuni ama matope/jivu/mchanga pahali ya kunawia mikono ama kwa nyumba? [Mark all that apply] | Bar or liquid soap/ (Sabuni ya kipande ama ya maji) …………………………………………… 1 Detergent (powder/liquid/paste) (Sabuni ya unga/maji) 2 Ash/Mud/Sand(Jivu/matope/mchanga) 3 None/ (Hakuna) 4 |  |
| 9 | What kind of health facility is in your area that is commonly used by members of this household?/Ni aina gani ya kituo xha afya kiko eneo hili ambaxho wanatumika mara nyingi watu katika kaya hii? | Dispensary/Zahanati 1 Health Centre/ Kituo cha afya 3 Sub county hospital/ Hospitali ya kaunti ndogo 4 County hospital/ Hospitali ya kaunti 5 Referral hospital/ Hospitali ya rufaa 6 Other (specify)/ Nyingine (eleza) 15 |  |
| 10 | Where is the health facility located?/ Kituo hicho cha afya kiko wapi? | Just near my home/ Karibu na nyumbani….……1 Far from home/ Mbali na nyumbani ………..2 |  |
| 11 | How long does it take to go there and come back? / Inachukua mda gani kufika kituo hicho na kurudi hapa nyumbani? | Minutes / Dakika……………………………… 999= Don’t know/ Sijui |  |
| 12 | What kind of toilet facility do members of your household usually use?/ Ni choo cha aina gani kinatumiwa na wanakaya wa kaya hii? If the response is "Latrine”, ask to see it. Endapo jibu ni “Choo” uombe kukiona If not possible to determine ask permission to observe the facility/ Kama hawezi kuelezea aina ya choo omba ruhusa ya kukiona | Toilet connected to septic tank 1 (Choo kilichounganishwa na tenki la taka ) Improved latrine 2 (Choo kilichoboreshwa) Improved traditional latrine 3 (Choo cha zamani kilichoboreshwa) Not improved latrine 4 (Choo kisichoboreshwa) There is no latrine 5 (Hamna choo) |  |
| 13 | What is the main source of energy or fuel that the family uses to cook?/ Ni kipi chanzo kikuu cha umeme au nguvu/moto wa kupikia kwa familia hii? | Electricity 1 (Nguvu za umeme) Gas 2 (Gesi) Oil/Paraffin/Kerosene 3 (Mafuta taa) Charcoal 4 (Makaa) Mineral coal 5 (Makaa ya kuchimbwa ardhini) Firewood 6 (Kuni) Animal faeces 7 (Mafi ya wanyama) Other (specify) 8 Kwingineko (eleza) |  |
| 14 | What is the main source of energy or fuel that the household uses for lighting?/ Ni kipi chanzo kikuu kaya hii hutumia kuwasha mwangaza/kumulika? | Electricity 1 (Umeme) Generator 2 (Jenereta) Solar panel 3 (Sola) Gas 4 (Gesi) Oil/Paraffin 5 (Mafuta taa) Kerosene 6 (Mafuta ya taa) Candle 7 (Msumaa) Batteries 8 Batteries 9 Firewood 10 (Kuni) Other (specify) 11 Nyingine(eleza) |  |
| 15 | Who owns the house where the household lives?/ Nani anamiliki nyumba ambayo familia huishi? | The family 1 (Familia) Rented 2 (Kukodishwa) Assigned 3 (Ya kupewa) | >>Q14 >>Q15 |
| 16 | If it is rented, what is the monthly rent?/ Kama imekondishwa, malipo ya mwezi ni hela ngapi? | Value Ksh/ Dhamani kwa KShs | >>Q16 |
| 17 | If it is your own, what is the monthly value that you would charge for rent?/ Kama ni yako, ungekodisha hela ngapi kwa mwezi? | Value Ksh/ Dhamani kwa KShs |  |
| 18 | If it is assigned, what is the monthly amount that you would pay in rent?/ Kama ni ya kupewa, Ungekuwa umekodi ungelipa hela ngapi kwa mwezi? | Value Ksh/ Dhamani kwa KShs | >>Q16 |
| 19 | How many rooms does this house have (including the living room)?/ Hii nyumba ina vyumba vidogo vingapi?(ikiwemo sebule) |  |  |
| 20 | Of these rooms, how many do you use for sleeping?/ Kati ya hivi vyumba, ni ngapi zinatumika kulala? |  |  |
| 21 | What is the primary material used in the roof? Ni bidhaa gani iliyotumika kwa wingi kuezeka? | Concrete slab 1 Roof tile 2 Lusalite sheets 3 Zinc sheets/ Mabati 4 Grass/stem/palm trees/ Nyasi/Makuti 5 Other (specify)/ Nyingine (eleza) 6 |  |
| 22 | What is the primary material used for the walls?/ Ni bidhaa gani imetumika kutengeneza kuta? | Adobe/adobe blocks 1 Cement blockHiis/ Matofali ya cimiti 2 Brick blocks/ Matofali ya udongo 3 Old sticks/ Miti/ vijiti vizee 4 Wood/zinc/ Mbao 5 Bamboo/cane/palm trees/ Milanzi/Miwa/Minazi 6 Other (specify)/ Nyingine (eleza) 7 |  |
| 23 | What is the primary material used in the construction of the floor?/ Ni bidhaa gani imetumika kutengeneza sakafu? | Clay /Udongo wa ufinyanzi 1 Wooden flooring (rudimentary)/ Sakafu ya mbao 2 Adobe 3 Wooden tiles/pieces (parquet)/ Vigae vya mbao 4 Wooden flooring (sealed) Sakafu ya mbao (iliozibwa) 5 Brick, marble or stones? Mawe/Marble 6 Cement/ Simiti…………………………………………..7 Other (specify)/ Nyingine (eleza) 8 |  |
| 24 | In the last 12 months, have members of this household used a computer or the internet (regardless of where they used it) or mobile money (Mpesa)?/ Kwa miezi kumi na miwili iliyopita,watu wa kaya hiiwamewahi kutumia kompyuta/tarakilishi ama mtandao (haijalishi waliko tumia) ama kutuma au kupokea pesa kwa mtandao (Mpesa)? [enter IDs of members who use each service]/ [Ingiza kitambulisho cha kila mmoja aliyetumia huduma] | A. Computer/Tarakilishi B. Internet/Mtandao C. Mobile money/ Pesa kwa simu |  |

#### SECTION 5: FOOD SECURITY (FAO Global Food Insecurity Experience Scale, FIES)/USALAMA WA CHAKULA (SECTION 5: FOOD SECURITY (FAO Global Food Insecurity Experience Scale, FIES)/ USALAMA WA CHAKULA (Kwa kipimo cha uzoefu wa ukosefu wa chakula duniani cha FAO, FIES)

|  | Question | Answers | Skip |
| --- | --- | --- | --- |
| 1a | When did you receive the last cash transfer from the Inua Jammi and NICHE program? | ………….……………………………..Weeks ago |  |
| 1 | How many meals excluding snacks would you normally have in a day before you had received the last cash from the Inua Jammi? Mnakula milo mingapi kwa siku bila kuhesabu vitafunio vidogo (chakula kisicho rasmi)? | One/ (Mlo mmoja) 1 Two/ (Milo miwili) 2 Three/ (Milo mitatu) 3 More than three/ (Milo zaidi ya mitatu) 4 |  |
| 2 | In thelast month before you had received the last cash from the Inua Jammi , did you or others in your household worry about not having enough food to eat because of a lack of money or other resources? Kwa wiki nne zilizopita, wewe ama wengine kwenye kaya hii mmewahai kuhofia kukosa chakula cha kutosha cha kula kwa sababu ya kukosa pesa ama raslimali zingine? | Yes/ Ndio 1 No/ Apana 2 |  |
| 2b. | Compared to before the last payment of Inue Jammi/NICHE how are your worries about having enough food right now? | More worried…………………….1 The same…………………………2 Less worried……………………...3 |  |
| 3 | In the last month before you received the last cash from the Inua Jammi , were you or any household member not able to eat healthy and nutritious food because of lack of money or other resources? Kwa wiki nne zilizopita wewe ama yeyote katika kaya hii mmemewahi kushindwa kula chakula chenye afya na madini yanayofaa kwa kukosa hela ama raslimali zingine? | Yes/ Ndio 1 No/ Apana 2 |  |
| 4 | In the last month before you received the last cash from the Inua Jammi , did you or any household member have only a few kinds of foods because of a lack of money or other resources? Kwa wiki nne zilizopita wewe ama mtu yeyote katika kaya hii mmekuwa mkipata vyakula aina chache kwa kukosa pesa ama raslimali zinginezo? | Yes/ Ndio 1 No/ Apana 2 |  |
| 5 | In the last month before you received the last cash from the Inua Jammi , was there a time when you or others in your household had to skip a meal because there was not enough money or other resources to get food? Kwa wiki nne zilizopita,kuna wakati ambapo wewe ama watu wengine kwa kaya hii iliwabidi mkose kula mlo kwa sababu hakukuwa na hela za kutosha ama raslimali zinginezo ili kupata chakula? | Yes/ Ndio 1 No/ Apana 2 |  |
| 7 | In the last month before you received the last cash from the Inua Jammi , was there a time when your household ran out of food because of a lack of money or other resource? Kwa wiki nne zilizopita kuna wakati kaya yako ilikosa chakula kwa sababu ya kukosa hela ama raslimali nyingine? | Yes/ Ndio 1 No/ Apana 2 |  |
| 8 | In the last month before you received the last cash from the Inua Jammi was there a time when you or others in your household were hungry but did not eat because there was not enough money or other resources for food? Kwa wiki nne zilizopita kuna wakati wewe ama wengine kwa kaya yenu mlikuwa na njaa lakini mkakosa kula kwa kukosa pesa ama raslimali zingine za chakula? | Yes/ Ndio 1 No/ Apana 2 |  |
| 9 | In last month before you received the last cash from the Inua Jammi , was there a time when you or others in your household went without eating for a whole day because of a lack of money or other resources? Kwa wiki nne zilizopita kuna wakati wewe ama wengine kwa kaya hii mlikosa kula kwa siku yote nzima kwa kukosa pesa ama raslimali zingine? | Yes/ Ndio 1 No/ Apana 2 |  |
| 10 | Compared to before you received the last cash from the Inua Jammi how has the food that your eating per day changed? | Eating more food or eating more preferred food (higher quality)………………………………1 Eating the same food as before………………2 Eating less food or less preferred food (less quality) …. ………………………………………..3 |  |

#### SECTION 6A: FOOD CONSUMED/CHAKULA KILICHOLIWA

| Have you or members of your household consumed (Eaten)…[FOOD ITEM] … during the past week? Je wewe ama watu wengine wa kaya hii mmewahi kula (AINA YA CHAKULA) kwa wiki iliyopita? Ask QUESTION 1. If coded ‘1’ then go to Q2-Q5 for same item, then go to next item. |  |  | How much of this food did your household CONSUME during the last week (7 days) - including food that was purchased, and food produced or grown by your household or received as a payment or a gift? Ni kiasi gani cha hii chakula kaya yako ilitumia kwa siku saba zilizopita (wiki moja)-kikiwepo chakula kilichonunuliwa,mlicholima ama kilichopokelewa kama malipo ama zawadi? |  | What was the total value of that food consumed? /Dhamani ya hicho chakula kilicholiwa ni shilingi ngapi? | What was the main source of this food? Aina hii ya chakula ilitoka wapi? Purchased/Kununuliwa; 1; Gift/aid from relatives/ Zawadi kutoka kwa ndugu; 5. Home produced/ Kilitoka hapa nyumbani; 2; Gift/aid from neighbours/ Zawadi kutoka kwa majirani; 6. Gathered/ /Kiliokotwa/kuzolewa; 3; Gift/aid from organisation (NGO, religious, govt)/ Zawadi kutoka kwa mashirika (NGO, ya kidini, ya serikali); 7. Payment in kind/ Kulipiwa kwa njia isiyo ya pesa; 4; Not applicable/ Haihusiki; 9. |
| --- | --- | --- | --- | --- | --- | --- |
| Unit table 1 Debe; 1 gorogoro; 1 mkebe; 1 small glass / cup Glasi au Kikombe kidogo; 1 mokoroff (tin of tomato paste); 1 teaspoon/ Kijiko kidogo; 1 tablespoon/ Kijiko kikubwa. =18kg; = 2.25kg; =250g; =200g/200ml; =70g; =5ml; = 10ml. | Unit codes. Kilogramme Gramme Litre Millilitre; Kg gr li ml; Number Debe Gorogoro Mkebe; nu de go mk. LAST 1 WEEK/JUMA MOJA LILILOPITA |  |  |  |
| Item [If ‘1’ in Q1 go to Q2-Q5 for same item then go to next item.] | Item code | 1=Yes 2=No | Quantity (Kiwango) | Unit (circle most applicable) (Kipimo) | Ksh (Kiwango cha pesa) | Main Source (Kilikotoka) |
|  |  | 1 | 2 | 3 | 4 | 5 |
| Maize – grain/ (Mahindi) | 01 |  |  | kg / gr / de / go / mk |  |  |
| Maize – flour/ (Unga wa mahindi) | 02 |  |  | kg / gr / de / go / mk |  |  |
| Rice / (Mchele) | 03 |  |  | kg / gr / de / go / mk |  |  |
| Other grains (wheat, sorghum, millet, other types) /(ngano,mpunga,mawele,aina zingine) | 04 |  |  | kg / gr / de / go / mk |  |  |
| Bread/ Mkate | 05 |  |  | kg / gr |  |  |
| Potatoes (Irish)/Viazi | 06 |  |  | kg / gr / de / go / mk |  |  |
| Sweet potatoes, cassava, arrow roots, yams, cooking banana/Viazi vitamu,mihogo, ndizi ya kupika, | 07 |  |  | kg / gr / de / go / mk |  |  |
| Beans/Maharagwe | 08 |  |  | kg / gr / de / go / mk |  |  |
| Other pulses/nuts (peas, grams, groundnuts)/ Kunde, ndengu, njugu karanga | 09 |  |  | kg / gr / de / go / mk |  |  |
| Eggs/Mayai | 10 |  |  | Number |  |  |
| Fresh fish/Samaki freshi | 11 |  |  | Number/ kg |  |  |
| Dried/smoked fish/Samaki wa kukaushwa | 12 |  |  | Number/ kg |  |  |
| Beef/Nyama ya ng,ombe | 13 |  |  | kg / gr / de / go / mk |  |  |
| Chicken/Kuku | 14 |  |  | kg / gr / de / go / mk/nu |  |  |
| Other meat (goat meat, mutton, pork, etc)/Nyama ya mbuzi,nyama ya kondoo,nyama ya nguruwe | 15 |  |  |  |  |  |
| Sukuma wiki (kales)/ Sukuma wiki | 16 |  |  |  |  |  |
| Other vegetables (tomatoes, cabbage, lettuce, onions etc) or sardines/omena/Aina zingine za mboga; Nyanya,mboga,vitunguu,managu | 17 |  |  |  |  |  |
| Milk – cow /Maziwa ya ng’ombe | 18 |  |  | li / ml |  |  |
| Milk – goat /Maziwa ya mbuzi | 19 |  |  | li / ml |  |  |
| Milk – camel /Maziwa ya ngamia | 20 |  |  | li / ml |  |  |
| Bananas (ripe)/Ndizi (zilizoiva) | 21 |  |  | Number |  |  |
| Other fruits (mangoes, avocados, oranges, pawpaws, etc.)/Matunda mengineo (Maembe, parachichi, paipai na kadhalika) | 22 |  |  |  |  |  |
| Cooking fat/Mafuta ya kupika | 23 |  |  | kg / gr |  |  |
| Other cooking oils/Aina zingine za mafuta ya kupikia | 24 |  |  | li / ml |  |  |
| Sugars (white/brown, sugarcane, etc.) [1 teaspoon=5gm & 1 tablespoon=10gm]/Sukari (nyeupe,miwa) | 25 |  |  | kg / gr |  |  |
| Spices (salt and others, etc.)/Viongeza radha (chumvi na vinginevyo) | 26 |  |  |  |  |  |
| Tea leaves / tea bags [1 teaspoon=2g]/Majani chai/majani ya mfuko | 27 |  |  | kg / gr |  |  |
| Coffee and other non-alcoholic drinks/Kahawa na vinywaji vingine visivyo vya kulevya | 28 |  |  |  |  |  |
| Alcoholic beverages (beer, wines, spirits, home-brew)/Vinywaji vya kulevya (pombe,pombe kali,pombe ya kutengeneza nyumbani) | 29 |  |  |  |  |  |
| Meals eaten out/Malazi yaliyoliwa | 30 |  |  |  |  |  |
| Other ready made foods (biscuits/mandazi/cakes/pasta/baby foods)/Chakula tayari kinginecho (mandazi/keki/pasta/chakula cha watoto) | 31 |  |  |  |  |  |

| #### SECTION 6B: FOOD CONSUMED BEFORE THE LAST PAYMENT OF THE INUA JAMMI/CHAKULA KILICHOLIWA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Did you or members of your household consumed (Eaten)…[FOOD ITEM] … in a typical week before your last payment of the Inua Jammi. Je wewe ama watu wengine wa kaya hii mmewahi kula (AINA YA CHAKULA) kwa wiki iliyopita? Ask QUESTION 1. If coded ‘1’ then go to Q2-Q5 for same item, then go to next item. |  |  | How much of this food did your household CONSUME during a typical week before your last payment of the Inua Jammi - including food that was purchased, and food produced or grown by your household or received as a payment or a gift? Ni kiasi gani cha hii chakula kaya yako ilitumia kwa siku saba zilizopita (wiki moja)-kikiwepo chakula kilichonunuliwa,mlicholima ama kilichopokelewa kama malipo ama zawadi? |  | What was the total value of that food consumed? /Dhamani ya hicho chakula kilicholiwa ni shilingi ngapi? |
| Unit table 1 Debe; 1 gorogoro; 1 mkebe; 1 small glass / cup Glasi au Kikombe kidogo; 1 mokoroff (tin of tomato paste); 1 teaspoon/ Kijiko kidogo; 1 tablespoon/ Kijiko kikubwa. =18kg; = 2.25kg; =250g; =200g/200ml; =70g; =5ml; = 10ml. | Unit codes. Kilogramme Gramme Litre Millilitre; Kg gr li ml; Number Debe Gorogoro Mkebe; nu de go mk. LAST 1 WEEK/JUMA MOJA LILILOPITA |  |
| Item [If ‘1’ in Q1 go to Q2-Q5 for same item then go to next item.] | Item code | 1=Yes 2=No | Quantity (Kiwango) | Unit (circle most applicable) (Kipimo) | Ksh (Kiwango cha pesa) |
|  |  | 1 | 2 | 3 | 4 |
| Maize – grain/ (Mahindi) | 01 |  |  | kg / gr / de / go / mk |  |
| Maize – flour/ (Unga wa mahindi) | 02 |  |  | kg / gr / de / go / mk |  |
| Rice / (Mchele) | 03 |  |  | kg / gr / de / go / mk |  |
| Other grains (wheat, sorghum, millet, other types) /(ngano,mpunga,mawele,aina zingine) | 04 |  |  | kg / gr / de / go / mk |  |
| Bread/ Mkate | 05 |  |  | kg / gr |  |
| Potatoes (Irish)/Viazi | 06 |  |  | kg / gr / de / go / mk |  |
| Sweet potatoes, cassava, arrow roots, yams, cooking banana/Viazi vitamu,mihogo, ndizi ya kupika, | 07 |  |  | kg / gr / de / go / mk |  |
| Beans/Maharagwe | 08 |  |  | kg / gr / de / go / mk |  |
| Other pulses/nuts (peas, grams, groundnuts)/ Kunde, ndengu, njugu karanga | 09 |  |  | kg / gr / de / go / mk |  |
| Eggs/Mayai | 10 |  |  | Number |  |
| Fresh fish/Samaki freshi | 11 |  |  | Number/ kg |  |
| Dried/smoked fish/Samaki wa kukaushwa | 12 |  |  | Number/ kg |  |
| Beef/Nyama ya ng,ombe | 13 |  |  | kg / gr / de / go / mk |  |
| Chicken/Kuku | 14 |  |  | kg / gr / de / go / mk/nu |  |
| Other meat (goat meat, mutton, pork, etc)/Nyama ya mbuzi,nyama ya kondoo,nyama ya nguruwe | 15 |  |  |  |  |
| Sukuma wiki (kales)/ Sukuma wiki | 16 |  |  |  |  |
| Other vegetables (tomatoes, cabbage, lettuce, onions etc) or sardines/omena/Aina zingine za mboga; Nyanya,mboga,vitunguu,managu | 17 |  |  |  |  |
| Milk – cow /Maziwa ya ng’ombe | 18 |  |  | li / ml |  |
| Milk – goat /Maziwa ya mbuzi | 19 |  |  |  |  |
| Milk – camel /Maziwa ya ngamia | 20 |  |  |  |  |
| Bananas (ripe)/Ndizi (zilizoiva) | 21 |  |  | Number |  |
| Other fruits (mangoes, avocados, oranges, pawpaws, etc.)/Matunda mengineo (Maembe, parachichi, paipai na kadhalika) | 22 |  |  |  |  |
| Cooking fat/Mafuta ya kupika | 23 |  |  | kg / gr |  |
| Other cooking oils/Aina zingine za mafuta ya kupikia | 24 |  |  | li / ml |  |
| Sugars (white/brown, sugarcane, etc.) [1 teaspoon=5gm & 1 tablespoon=10gm]/Sukari (nyeupe,miwa) | 25 |  |  | kg / gr |  |
| Spices (salt and others, etc.)/Viongeza radha (chumvi na vinginevyo) | 26 |  |  |  |  |
| Tea leaves / tea bags [1 teaspoon=2g]/Majani chai/majani ya mfuko | 27 |  |  | kg / gr |  |
| Coffee and other non-alcoholic drinks/Kahawa na vinywaji vingine visivyo vya kulevya | 28 |  |  |  |  |
| Alcoholic beverages (beer, wines, spirits, home-brew)/Vinywaji vya kulevya (pombe,pombe kali,pombe ya kutengeneza nyumbani) | 29 |  |  |  |  |
| Meals eaten out/Malazi yaliyoliwa | 30 |  |  |  |  |
| Other ready made foods (biscuits/mandazi/cakes/pasta/baby foods)/Chakula tayari kinginecho (mandazi/keki/pasta/chakula cha watoto) | 31 |  |  |  |  |

#### SECTION 7: NON-FOOD CONSUMED (Last 1 and Last 3 Months)/BIDHAA VILIVYOTUMIWA VISIVYO VYAKULA (Mwezi mmoja na miezi mitatu iliyopita)

| What is the total value of all [ITEM] purchased, produced at home and received as gifts during the reference period [last one month or last 3 months]? Nini dhamani ya (BIDHAA) iliyonunuliwa,tengenezwa nyumbani na kupokewa kama zawadi kwa muda uliotajwa (mwezi mmoja uliopita au miezi mitatu iliyopita) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Items LAST ONE MONTH before your last payment of the Inua Jammi /BIDHAA MWEZI MMOJA ULIOPITA | Item Code | Ksh | Items LAST 3 MONTHS before your last payment of the Inua Jammi | Item Code | Ksh |
| Tobacco (cigarettes, tobacco) and miraa/Tumbako (Sigara, tumbaku) na miraa/mirungi | 01 |  | Men’s clothing/Nguo za kiume | 19 |  |
| Paraffin/kerosene/Mafuta ya taa | 02 |  | Women’s clothing/Nguo za kike | 20 |  |
| Water (for drinking and other household consumption/ use)/Maji (ya kunywa na matumizi mengine nyumbani) | 03 |  | Children’s clothing NOT INCLUDING school uniforms/Nguo za watoto isipokuwa sare za shule | 21 |  |
| Charcoal, firewood (including gathered)/ Makaa,Kuni (zikiwemo za kukusanya) | 04 |  | Material for clothes, and tailoring/Kitambaa cha nguo na kusonesha | 22 |  |
| Other utilities (electricity, gas)/Stima,gesi | 05 |  | Footwear (including repair costs)/Viatu (ukijumuisha gharama ya kutengenezesha) | 23 |  |
| Toilet soap (washing powder, laundry soap, detergents)/ Sabuni ya kuosha/chooni (ya unga, kipande, ya maji) | 06 |  | Recreation (toys, cinema, photography, records etc)Vitu za watoto za kucheza,senema,picha,rekodi na kadhalika | 24 |  |
| Other toiletries (shampoo, toothpaste, hair cream, etc)/ Aina zingine za bidhaa za bafuni (shampoo, Mafuta ya nywele,dawa ya meno | 07 |  | Personal articles (umbrella, watch, lighter, belts, etc)/Vitu vya kibinafsi (mwavuli,saa,vyombo vya kutoa mwangaza,mishipi na kadhalika) | 25 |  |
| Other cleaning expenses, equipment (brushes, shoe polish, etc) Vitu vingine vya kusafisha na bidhaa (breshi ya kufua, rangi ya viatu n.k.) | 08 | ` | Medical Expenditure (both inside and outside health facilities) – categories listed below:/Gharama ya matibabu (ndani na nje ya kituo cha afya) |  |  |
| Matches, candles/Viberiti, Misumaa | 09 |  | - Medicines and medical supplies (e.g. bandages etc) excluding AIDS drugs/ Dawa na bidhaa zinazoambatana na dawa (kama vile bendeji na kadhalika) | 26 |  |
| Batteries, bulbs/Betri na globu | 10 |  | - Transport to and from health facilities/Nauli ya kwenda na kutoka kituo cha afya | 27 |  |
| Bus fares, matatu, taxis/ Nauli ya basi,matatu,texi | 11 |  | - Consultation & treatment fees including gifts/Malipo ya kumuona muhudumu wa afya na malipo ya matibabu na zawadi ulizotoa | 28 |  |
| Other transport expenses (bicycle, car repair, petrol etc) excluding transport to and from school or health facilities/Matumizi mengine ya nauli (Basikeli, kutengeneza gari,petroli) isipokuwa usafiri wa kuelekea na kutoka shuleni ama kituo cha afya. | 12 |  | - Laboratory & diagnostic test fees/Malipo ya mahabara na vipimo | 29 |  |
| Hair cut and other personal services/Kunyoa na gharama zahuduma za kibinafsi | 13 |  | - Visits to traditional healers/Kutembelea waganga wa kienyeji | 30 |  |
| Books, notebooks, newspapers, stationary, etc (not for school)/Vitabu, vitabu vya kunakili mambo ya kibinafsi,gazeti, kalamu n.k (vizivyo vya shule) | 14 |  | - Hospitalisation fees including food (“bed bill”)/Malipo ya kulazwa hospitalini ikiwemo bili ya chakula na kitanda | 31 |  |
| Communications (phone calls -- fixed and mobile, airtime, post office expenses, etc.)/Mawasiliano (kupiga simu- ya nyumbani na ya mkono,kadi ya simu,matumizi njia ya posta) | 15 |  | - Other health expenditure excluding AIDS drugs/Matumizi mengine ya kiafya yasiyohusu dawa za kupunguza makali ya UKIMWI | 32 |  |
| TKK (“to cooperate”) Kitu kidogo/Hongo/rushwa | 16 |  | - AIDS drugs/Dawa za kupunguza makali ya ukimwi | 18 |  |
| Rent, including utilities if paid together as a lump sum/ Kodi ya nyumba/Kodi na matumizi mengine yanayoambatana na kodi endapo ulipwa kwa pamoja | 17 |  |  |  |  |

| NON-FOOD CONSUMED (Last 12 Months)/BIDHAA ZISIZO VYAKULA VILIVYOTUMIKA (Kwa miezi 12 iliyopita) |  |  |
| --- | --- | --- |
| What is the total value of all [ITEM] purchased, produced at home and received as gifts during the last 12 months before your last payment of the Inua Jammi? Nini dhamani kamili ya (BIDHAA) ulionunua,uliotengeneza hapa nyumbani na ulizopokea kama zawadi kwa muda wa miezi kumi na miwili iliyopita? |  |  |
| Items LAST 12 MONTH /Bidhaa miezi kumi na miwili iliyoweza kupita | Item Code | Ksh |
| Textiles (blanket, bedsheet, towels, mosquito netting, etc., not for clothes)/Nguo/Vitambaa (blanketi, shuka za kitandani, taulo, neti ya mbu,…na kadhalika wala sio za nguo za kuvaa | 33 |  |
| Kitchen equipment (cutlery, pots, plates, jiku, small equipment – kettle and sufuria)/Vyombo vya jikoni (vyombo vya kukatia, vyungu, sahani, jiko, vyombo vidogo-birika na sufuria) | 34 |  |
| Lanterns, lamps, torches/Taa ya mkono, taa ya kutia presha, tochi | 35 |  |
| Education Expenditure (Primary, Secondary and Nursery) (categories listed below)/Gharama ya masomo (Shule ya msingi,Shule ya upili na chekechea) (orodha zipo hapa chini) |  |  |
| - Tuition fees, registration fees, exam fees & other fees either paid or owed/ Karo ya shule, karo ya kujisajiri, karo ya mtihani na karo zinginezo zilizolipwa ama bado hazijalipwa | 36 |  |
| - Private tuition Mafundisho ya nyumbani | 37 |  |
| - Transport to and from school Nauli ya kwenda na kutoka shuleni | 38 |  |
| - Uniforms including school shoes Sare za shule zikiwepo viatu | 39 |  |
| - School supplies including textbooks Bidhaa za shule zikiwepo vitabu vya kusoma | 40 |  |
| - Food (school lunch, breakfast, snacks) Chakula (chakula cha mchana shuleni, vitafunio n.k.) | 41 |  |

#### SECTION 8: SHOCKS AND COPING MECHANISMS / MISUKOSUKO NA MBINU ZA KUIKABILI

|  |  | 1 | 2 | 2A |
| --- | --- | --- | --- | --- |
| SHOCK ID |  | During the last 12 months, was your household affected negatively by any of the following [SHOCK]? Kwa miezi 12 iliyopita, kaya yako imeadhiliwa vibaya na chochota kwa hizi zifuatazo? [Msukosuko] Yes/ Ndio=1 No/ Apana=2 (>>NEXT SHOCK) MSUKOSUKO UNAOFUATA | What did your household do in response to [SHOCK] to try to regain your former welfare level? Kaya yako ilifanya nini kukabiliana na [Msukosuko] kujaribu kurudi katika hali ya kawaida? NOTE THE TWO MOST IMPORTANT COPING STRATEGIES FOR THE SHOCK. IF SHOCK HAPPENED MORE THAN ONCE DURING THE LAST 12 MONTHS, ASK ABOUT THE MOST RECENT INCIDENT. IF ONLY ONE STRATEGY, MARK ‘00’ FOR SECOND. NAKILI MBINU MBILI AMBAZO ZILIKUA ZA MUHIMU SANA. KAMA TUKIO LILIFANYIKA ZAIDI YA MARA MBILI KWA MIEZI 12 ILIYOPITA, ULIZA KUHUSU LILE LA HIVI KARIBUNI. KAMA WALITUMIA MBINU MOJA TU, ANDIKA 00 KWA MBINU YA PILI Use coping strategy codes |  |
|  |  |  | Most important coping strategy/ Mbinu muhimu Zaidi ya kuhimili | Second most important coping strategy/ Mbinu ya pili muhimu ya kuhimili |
| 101 | Drought/irregular rains/ Ukame/ Mvua zisizo za kutegemea |  |  |  |
| 102 | Floods/Landslides/ Mafuriko/ maporomoko ya ardhi |  |  |  |
| 103 | Winds/Cyclones/ Vimbunga/upepo mkali |  |  |  |
| 104 | Unusually high level of crop/livestock pests or disease/ Mfumuko mkubwa wa wadudu na magonjwa ya mimea na mifugo |  |  |  |
| 105 | Crop/harvest destroyed (ex. Fire)/ Mimea/mazao kuharibiwa (mfano moto) |  |  |  |
| 106 | Livestock died / Mifugo walifariki |  |  |  |
| 107 | Unusually low prices for agricultural output/ Bei za chini sana kwa mazao ya kilimo |  |  |  |
| 108 | Unusually high costs of food or agricultural inputs/ Bei za juu sana za chakula na pembejeo za kilimo |  |  |  |
| 109 | End of regular assistance/aid remittances from outside household/ Kukatizwa kwa msaada wa mara kwa mara unaotoka nje ya kaya |  |  |  |
| 110 | Serious illness or accident of household member(s)/ Ugonjwa mkubwa au ajali ya (m)wana kaya |  |  |  |
| 111 | Birth in the household/ Mtoto kuzaliwa katika kaya |  |  |  |
| 112 | Death of household income earner/ Kufa kwa mwanakaya anayeleta pesa kwenye kaya |  |  |  |
| 113 | Break-up of household (divorce/separation/death/migration)/ Kuvunjika kwa kaya (kutengana/kuachana/kifo/kuhama) |  |  |  |
| 114 | Payment of labolo (brideprice)/ Kulipa mahari |  |  |  |
| 115 | Theft of money/valuables/assets/agricultural output/ Kuibiwa kwa pesa/ vitu vya thamani/ vifaa/ mazao |  |  |  |
| 116 | High education costs/ Gharama kubwa ya elimu |  |  |  |
| 117 | House destroyed (for example, burning, flood, winds)/ Nyumba kuharibiwa (mfano kuchomeka, mafuriko, upepo) |  |  |  |
| 118 | Conflict in the community/ Mzozo katika kijiji |  |  |  |
| 119 | COVID-19 / COVID-19 |  |  |  |
| COPING STRATEGY ID: Relied on own savings/ Tulitegemea akiba yetu 1 Received unconditional help from relatives/friends / Tulipokea msaada wa bure kutoka kwa ndugu na marafiki 2 Received unconditional help from government/ Tulipokea msaada wa bure kutoka kwa serikali 3 Received unconditional help from NGO/religious institution/ Tulipokea msaada wa bure kutoka NGO/ shirika la dini 4 Changed eating patterns (relied on less expensive or less preferred food options, reduced the proportion or number of meals per day, or household members skipped days of easting, increased consumption of wild foods, members eating away from home, etc.)/ Tulibadilisha vile tulikua tunakula (tulianza kulala chakula cha bei rahisi, chakula kisichopendwa sana, tukapunguza milo, kuruka siku bila kula, tukaanza kula vyakula vya porini, wanakaya kula nje ya kaya 5 Reduced adult consumption for children to eat/ Tulipunguza ulaji wa watu wazima ili watoto wakule 6 Household members took on more employment/ Wanakaya walianza kufanya kazi zaidi 7 Adult household members who were previously not working had to find work/ Wanakaya watu wazima ambao walikua hawafanyi kazi ilibidi watafute kazi 8 Household members migrated / Wanakaya walihama 9 Reduced expenditures on health and/or education/ Tulipunguza matumizi ya afya na/au elimu 10 |  |  | Obtained credit/took loan / Tulichukua mkopo…..………………………………… 11 Sold agricultural or durable assets, land/building, crop stock, livestock or others/ Tuliuza mazao au vifaa, ardhi/nyumba, mifugo na vingine 12 Intensified (more days, longer hours) fishing/farming/ Tulizidisha (siku nyingi, mda mrefu) kuvua samaki/kilimo 13 Sent children to live elsewhere / Tuliwatuma watotot wakaishi kwingine 14 Engaged in spiritual efforts – prayer, sacrifices, diviner consultation/ Tulifanya juhudi za kiroho – maombi, zaka, kuomba ushauri wa watu wa kiroho 15 Cash transfer payment or other benefit from other social protection program / Tulipokea pesa za msaada/malipo au manufaa ya miradi ya kukinga jamii 16 Planted trees or built conservation structures / Tulipanda miti au kujenga sehemuza hifadhi 17 Children sent to paid work/ Watoto kutumwa kufanya kazi za kulipwa 18 Children worked more at home or family farm/enterprise (unpaid)/ Watoto walifanya kazi Zaidi hapa nyumbani/shambani/biashara ya nyumbani 19 Girl child married off (received labola)/Tulimuozesha mtoto wa kike ili tupate mahari 20 Other (specify)/ Nyingine (eleza) 21 None/ Hakuna 99 |  |

#### SECTION 9: EXPERIENCE WITH OTHER PROGRAMS/ UZOEFU NA MIRADI MINGINE

|  |  | 1 | 2 | 3 |
| --- | --- | --- | --- | --- |
|  | Name of Program or Service/ Jina la mradi au huduma | In the last 12 months, has any member of your household received money or goods, including food, clothing, livestock or medicines, or benefited for instance receiving information/education from any of the following types of programs? Kwa miezi 12 iliyopita, kuna mtu yeyote katika kaya hii amepokea pesa, bidhaa, ikiwepo chakula, nguo, mifugo au dawa, au amefaidika kwa mfano kwa kupata taarifa/mafunzo kutoka kwa mojawapo ya miradi ifuatayo? 1=YES/ NDIO 2=NO>> APANA Next Program/ Q4 | Who was providing this support or offering this service?/ Nani alikuwa anatoa msaada au huduma hio? 1 = Government program/ Mradi wa serikali 2 = NGO or church program/ Mradi wa NGO au kanisa 9 = DK/ SIJUI | What is the total value of assistance received from this program in the last 12 months? Dhamani ya msaada huo wote ni kama shilingi ngapi, kwa miezi 12 iliyopita? [Convert in-kind assistance to KSH] [BADILISHA MSAADA WA HALI KWENYE PESA za kenya] >>Next Program |
| 01 | Food assistance program (in-kind)/ Msaada wa chakula (usio wa pesa) |  |  |  |
| 02 | School feeding programs |  |  |  |
| 03 | Public works programs/ Mradi wa kazi za umma |  |  |  |
| 04 | Farmer or agricultural support program (including livestock or input subsidy)/ Mradi wa kusaidia wakulima au kilimo (ikiwepo mifugo au pembejeo) |  |  |  |
| 05 | Other programs/services for income generation including entrepreneurship or micro-credit, small business training/ Miradi mingine/ huduma za kuleta mapato au kujiendeleza kibiashara au mikopo midogo/ mafunzo ya biashara ndogo ndogo |  |  |  |
| 06 | Community health campaign or health program/ Hamasisho au Mradi wa jamii wa afya |  |  |  |
| 7 | Water or sanitation program/ Mradi wa maji au usafi |  |  |  |
| 8 | Social Welfare or psychosocial support program/ Mradi wa masilahi ya jamii au ushauri wa kisaikolojia |  |  |  |
| 9 | Education or school support program, including literacy programs/ Mradi wa msaada wa elimu, ikiwepo miradi ya mafunzo |  |  |  |
| 10 | Youth services or activities Humuma za wanarika |  |  |  |
| 11 | Any other program, specify Mradi mwingine (eleza) |  |  |  |

| 4 | In the last 12 months, has any member of your household received money or goods, including food, clothing, livestock or medicines from individual people (friends, family, others) who are not part of your household? Kwa miezi 12 iliyopita, kuna mtu yeyote katika kaya hii amepokea pesa, bidhaa, ikiwepo chakula, nguo, mifugo au dawa, au amefaidika kutoka kwa watu binafsi (marafiki, familia, wengine) ambao sio watu wa kaya hii? | 1=YES / NDIO 2-NO / APANA >> Next Section |  |
| --- | --- | --- | --- |
| 5 | What is the total value of assistance received from all these non-household members in the last 12 months? Dhamani ya msaada huo wote kutoka kwa watu hao ambao sio wa kaya hiii, ni kama shilingi ngapi, kwa miezi 12 iliyopita? | [Convert in-kind assistance to Ksh] [BADILISHA MSAADA WA HALI KWENYE PESA za kenya] |  |

#### SECTION 10A: MATERNAL AND NEWBORN HEALTH and FEEDING/ AFYA YA MAMA NA MTOTO MCHANGA

These questions need to be asked to the mother or main caregiver for the index child (0-24 months), or any other new primary female caregiver. Questions are about index child [Check child ID and Name; CAPI: pre-fill child ID].  Maswali haya yanatakiwa kuulizwa kwa mama au mlezi mkuu wa mtoto mlengwa (umri wa miezi 0-24), au mlezi mwingine mgeni wa kike. Maswali haya ni kuhusu mtoto mlengwa [angalia utambulisho wa mtoto na jina lake: CAPI: pre-fill child ID]

|  | Question | Answers | Skip |
| --- | --- | --- | --- |
| 1 | Did you ever breastfeed (NAME)?/ Uliwahi kumnyonyesha [JINA] hata kidogo? | Yes/ Ndio 1 No/ Hapana 2 | >> Q7 |
| 2 | How long after birth did you first put (NAME) to the breast?/ Ni mda gani baada ya kuzaliwa ulimnyonyesha [JINA] kwa mara ya kwanza? | Immediately/ Hapo hapo……………………………….00 Hours/ Baada ya masaa [ ] ………………. 1 [ ] Days/ Baada ya siku [ ] …………………… 2 [ ] |  |
| 3 | In the first 2 days after delivery, was (NAME) given anything other than breast milk to eat or drink – anything at all like, water, infant formula, etc. / Kwa siku za kwanza 2 baada ya kuzaliwa, je [JINA] alipewa chochote tofauti na maziwa ya mama cha kukula au kunywa – chochote tu kama vile maji, formula ya watoto n.k. | Yes/ Ndio 1 No/ Hapana 2 |  |
| 4 | Are you still breastfeeding (NAME)?/ Bado unamnyonyesha [JINA]? | Yes/ Ndio 1 No/ Hapana 2 | >> Q6 |
| 5 | At what age did you stop breast-feeding (NAME)?/ Uliacha kumnyonyesha [JINA] akiwa na umri gani? [Record age in completed months]/ [Nakili umri katika miezi aliyokamilisha] | Months………………………….[ ]/ Miezi …………………. |  |
| 6 | Has [NAME] been breastfeed yesterday during the day or the night?/ Je [JINA] alinyonyeshwa jana mda wa mchana au usiku? [Indicate as “Yes” any child who is breastfed by a woman other than the mother, or who are given breastmilk by another woman from a spoon, a cup, a bottle]/ Nakili ndio kwa motto yeyote ambaye alinyonyeshwa na mama mwingine asiye mama yake, au aliyepewa maziwa na mama mwingine kwa kijiko, kikombe au chupa | 1=Yes / Ndio 2= No/ Hapana 9= Don’t know / Sijui |  |
| 7 | How many times yesterday during the day or night [NAME] consumed .../ Ni mara ngapi jana mchana au usiku [JINA] alitumia? [Times]/ [Mara] | Water/ Maji………………………………………………………………………………………A Infant formula?/Maziwa maalum yaliyotengenezwa ya watoto ……….B Canned milk powder?/ Maziwa ya unga ya mkebe……………………………C Fresh cow’s milk?/ Maziwa freshi ya ngombe ………………………………….D Fresh goat’s milk?/ Maziwa freshi ya mbuzi……………………………………..E Fresh camel’s milk?/ Maziwa freshi ya ngamia………………………………….F Yogurt?/ Yogati/maziwa ya mgando …………………………………………………G |  |
| 8 | At what age (in months) did you first give (NAME) water or other fluids besides breast milk?/ Ni katika umri gani (kwa miezi) ulimpa [JINA] maji au kinywaji kingine kando na maziwa ya kunyonya kwa mara ya kwanza? [00=LESS THAN ONE MONTH] [00=CHINI YA MWEZI MMOJA] [97=NOT YET] [97=BADO SIJAMPA] | Months………………………….[ ] |  |
| 9 | At what age (in months) did you first give (NAME) solid or semi-solid food?/ Ni katika umri gani (kwa miezi) ulimpa [JINA] chakula laini au kigumu kwa mara ya kwanza? [00=LESS THAN ONE MONTH] [00=CHINI YA MWEZI MMOJA] [97=NOT YET] [97=BADO SIJAMPA] | Months………………………….[ ] |  |
| 10 | How many times has [Name] been fed solid, semi-liquid or soft food yesterday?/ Ni mara ngapi [JINA] alipewa chakula laini au kigumu kwa jana? | Times………………………….[ ]/ Mara …… [ ] |  |
| Now we will talk about your eating behavior (of the female caregiver) during the last pregnancy |  |  |  |
| 11 | During this / last pregnancy did your eating habits change | Yes/ Ndio 1 No/ Hapana 2 | 2>> Next section 10A |
| 12 | In a typical day during the pregnancy, were you eating less amount or amount of food than you normally eat when not pregnant; | Less amount……………………………………...1 More amount……………………………………..2 Same amount… (eating habits change in different ways)…3 |  |
| 13 | In a typical day during the pregnancy were you eating less frequently or more frequently than you normally do? | Less frequent……………………………………...1 More frequent……………………………………..2 Same frequency… (eating habits change in different ways)…3 |  |
| 14 | In a typical day during the pregnancy were you eating less variety of foods or more variety of foods than you normally do? Here I do not mean amount of food but rather types of foods, like eating/drinking, many different types of foods like milk, ugali, meat, fruits, vegetables in a given day or just eating a few types of these | Less variety……………………………….……...1 More variety……………………………………..2 Same variety… (eating habits change in different ways)…3 |  |

SECTION 10A: MATERNAL AND NEWBORN HEALTH and FEEDING (CONTINUED)/ AFYA YA MAMA NA MTOTO MCHANGA (INAENDELEA)

| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Please, can you say all that [Name] ate yesterday, during the day or at night, whether at home or away from home? [Each time the respondent remembers and says the food consumed by the child, write the corresponding number in the corresponding food groups (lines below)] / Tafadhali unaweza kutaja vitu vyote ambavyo [JINA] alikula jana, mchan na usiku, aidha nyumbani au nje ya nyumbani? [kila wakati mhojiwa akikumbuka na kusema chakula kilicholiwa na mtoto, andika ni mara ngapi alikula hicho chakula 1=Yes Ndio 2= No Apana 9= Don’t know Sijui |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a. | b. | c. | d. | e. | f. | g. | h. | i. | j. | k. | l. | m. | n. | o. |
| Potatoes, cornmeal porridge, bread, rice, spaghetti, biscuits, or other food made from cereals? Viazi, uji wa mahindi, mkate, wali/mchele, spageti, biskuti au chakula kingine cha jamii ya mahindi | Pumpkin, carrot, or sweet potato, yellow or orange?/ Malenge, karoti, kiazi kitamu cha njano au rangi ya chungwa? | White potatoes, white yams, cassava, or any other tubers or potatoes? Viazi vyeupe, magimbi, mhogo au jamii nyingine ya viazi? | Any leafy greens (beans, cassava, leaves, kale, sweet potato leaves?/ Majani ya rangi ya kijani, (maharagwe, mhogo, sukuma wiki, majani ya viazi vitamu? | Ripe mango, ripe papaya, guava with red pulp or other food rich in vitamin A? Maembe, paipai, au mapera yaliyoiva ama kingine chenye vitamin A? | Any other fruit or vegetable (banana, apple, tomato, lemon, orange, tangerine, grapes, cabbage)? Tunda au mboga aina nyingine (ndizi, appale, limau, chungwa, chenza, au kabeji? | Liver, kidney, heart, or other organs? Nyama ya Maini, figo, roho au viungo vingine vya mwili? | Any other meat such as beef, pork, sheep, goat, or duck, or other game meat? Nyama nyingine kama ya ngombe, nguruwe, nyama ya mbuxi, kondoo, kuku, nyama ya wanyama pori na kadhalika? | Eggs? Mayai? | Fresh or dried fish or seafood? Samaki fresh au aliyekaushwa, au wa baharini? | Any food made with beans, peas, lentils, almonds, or seeds?/ Chakula chochote kilichtengenezwa na maharagwe, njugu, choroko, mlozi au mbegu zingine? | Cheese, yogurt, or other products made from milk? Jibini, yogati au kitu kilichotokana na maziwa? | Foods made with oil, peanuts, sesame or butter/margarine? Chakula kilichotokana na mafuta, njugu karanga, simsim au siagi? | Powdered micronutrients/supplementsVirutubisho vya unga unga? | Sugary juices, fruit juices, soft drinks, chocolate drinks, yogurt, or sugared tea or sugared coffee? Juisi za sukari, juisi za matunda, vinywaji vya chokoleti au chai au kahawa iliowekwa sukari? |

| 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Now I am going to ask you about you (mother of child/female caregiver). Did you eat any of these foods during the day yesterday? 1= Yes; 2= No/ Sasa nitakuuliza maswali kuhusu wewe mwenyewe (mamake mtoto au mlezi). Ulikula vyakula vyovyote kati ya hizi jana mchana wote? 1=Ndio; 2=Apana |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a. | b. | c. | d. | e. | f. | g. | h. | i. | j. | k. | l. | m. | n. | o. | p. | q. | r. | s. |  |
| Rice, corn, sorghum, millet, bread, pasta, potatoes, yams, green banana? Wali/mchele,mahindi, mtama, mawele, mkate, Viazi, spageti, magimbi, ndizi ya kupika? | Potato Reno, sweet potato, cassava? Viazi, viazi vitamu, mhogo? | Beans, peas, lentils, soybeans? Maharagwe, njugu, ndengu, soya? | Peanuts, almonds, sesame seeds, pumpkin seeds, cashew nuts? / Njugu karanga, mlozi, ufuta, mbegu za malenge, korosho? | Milk, cheese, yogurt or other dairy products, sour cream? Maziwa, jibini, yogati, au bidhaa nyingine ya maziwa? | Liver, kidneys, gizzards, heart?/ Nyama ya Maini, figo, firigisi/mbizi, roho? | Beef, pork, goat, rabbit, chicken, duck, bird, mouse, rat, wild game meat? Nyama ya ng’ombe, sungura, kuku, bata, ndege, panya, au ya wanyama pori? | Fresh or dried fish, shellfish or seafood (lobster, squid, octopus, oysters, crab)/ Samaki fresh au iliyokaushwa, samaki wa baharini (kamba kamba, pweza, kaa)? | Eggs of poultry or any other bird like duck or quail? Mayai ya kuku, bata, au ndege wengine? | Tsec (amaranth), watercress, sweet potato leaves, pumpkin leaf, cassava or bean leaves, okra, spinach? Mchicha, matembele/majani ya viazi vitamu, majani ya maboga, kisamvu/majani ya mhogo, spinachi? | Pumpkin, carrot, red chili, orange squash, sweet potato? Malenge, karoti, pilipili nyekundu, juisi ya machungwa, viazi vitamu? | Mango, papaya, passion fruit, peach?/ Maembe, paipai, matunda ya pasheni? | Cabbage, tomatoes, lettuce, eggplant, cucumber, green peppers, beets?/ Kabeji, nyanya, saladi, tango, pilipili ya kijani, beet? | Orange, apple, pear, grape, pineapple, wile berries, tangerine, watermelon, avocado, cocnut pulp? Chungwa, apple, peari, zabibu, nanasi, matunda ya kichakani, chenza, tikiti maji, parachichi, madafu? | Have you used oil, fat, or butter to cook? Umetumia mafuta, mafuta ya salad au siagi kipikia? | Sugary foods such as chocolates, sweets, cookies and biscuits, cakes, sweets or ice cream?/ Vyakula vya sukari sukari kama chokoleti, pipi/peremende, biskuti, keki au barafu? | Did you take tea leaves (black) or coffee without sugar just before or after food? Ulikunywa chai ya rangi/majani chai au kahawa nyeusi punde kabla au baada ya kula? | Have you used ingredients even if in small amounts to give flavour such as peppers, spices, herbs, fish powder, tomato paste, flavour bouillon, or seeds?/Umetumia viungo hata kidogo kuongeza ladha k.m pilipili, viungo, poda ya samaki ? | Did you drink sugary juices, fruit juices, soft drinks, chocolate drinks, yogurt, or sugared tea or sugared coffee? Umekunywa juisi za sukari, juisi za matunda, vinywaji vya chokoleti au chai au kahawa iliowekwa sukari? |  |

#### SECTION 10B: IMMUNIZATIONS & MEDICATION

These questions need to be asked to the mother or main caregiver for the index child (0-24 months) [CAPI: If child is dead, >> Section 11 Child Discipline]

Maswali haya yanatakiwa kuulizwa mama au mlezi wa mtoto mlengwa (mwenye umri wa miezi 0-24)

|  | 1 | 2 |  |  |  |  |  |  |  |  |  |  |  | 3 | 3b | 4 | 5 | 5b | 6 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID of child | Do you have a card where (name)’s vaccinations are written down? Una kadi ambayo huwa inaandikwa jinsi [JINA anavyopewa chanjo? (IF YES) may I see it please?/ (KAMA NDIO) Naweza kuiona tafadhali? 1=Yes, seen/ Ndio, nimeiona 2=Yes, not seen/ Ndio, sijaiona 3=No Apana | Check health card for vaccination history. If health card not available inquire from respondent. For PEN, OPV and Pneumococcal and Rotavirus vaccinations record number of times vaccination received. 1=YES; 2=NO; 9 = DK Angalia kadi kuona historia ya chanjo. Kama kadi ya afya haipo muulize mhojiwa kuhusu chanjo za PEN, OPV, Nimonia na Rotavirus na unakili ni mara ngapi alichanjwa. 1=NDIO 2=APANA 3=SIJUI |  |  |  |  |  |  |  |  |  |  |  | Has (NAME) received a Vitamin A dose within the last 12 months? Je [JINA] amepata matone ya Vitamin A ndani ya miezi 12 iliyopita? 1=YES/NDIO 2=NO APANA 9=DK SIJUI | If yes, how many times did (NAME) receive the Vitamin A dose? 98=DK Kama ndio, ni mara ngapi [JINA] alipata dozi ya vitamin A 98 = Sijui | Has [NAME] received deworming medication in the last 6 months? Je [JINA] amepata dawa za minyoo ndani ya miezi 6 iliyopita? 1=YES/NDIO 2=NO APANA 9=DK SIJUI | Has [NAME] had diarrhea in the last 2 weeks? Na je [JINA] amepata kuhara ndani ya wiki mbili zilizopita? 1=YES/NDIO 2=NO APANA 9=DK SIJUI | If yes, was (NAME) given ORS and Zinc supplement?/ Kama ndio, je [JINA] ali[ewa ORS na virutubisho vya Zinc? 1=YES/ Ndio 2=NO/ Hapana 9=DK/ Sijui | In the last months has [NAME] gone to a well-baby clinic or for a preventive health check-up or growth monitoring? Katika mwezi 1 uliyopita, [JINA] ameenda kliniki ya watoto, kuakaguliwa ili kuzuia magonjwa au kuangaliwa anavyokua? 1=YES/NDIO 2=NO APANA |
|  |  | BCG Vaccination against tuberculosis – that is, an injection in the arm or shoulder that usually causes a scar/ BCG Chanjo ya kuzuia TB/kifua kikuu – sindano inayodungwa mkononi au bega na huwa inaacha kovu | POLIO Vaccination drops in the mouth to protect him/her from getting polio POLIO Chanjo ya vitone mdomoni kumkinga na polio |  |  |  | PENTA/DPT-HepB-Hib An injection in the thigh or buttocks to prevent him/her from getting tetanus, whooping cough, or diphtheria PENTA/DPT-HepB-Hib Sindano inayodungwa kwenye matako kuzuia pepopunda, kifaduro au mkamba/diptheria |  |  | PNEUMO-COCCAL An injection usually given on the right upper thigh to prevent pneumonia? PNEUMO-COCCAL Sindano hudungwa paja la kulia kuzuia nimonia |  |  | MEASLES A shot in the arm at the age of 9 months or older to prevent him/her from getting measles SURUA/UKAMBI Sindano kwenye mkono kwa umri wa miazi 9 (tisa) kuzuia surua/ukambi |  |  |  |  |  |  |
|  |  |  | OPV0 | OPV1 | OPV2 | OPV3 | PEN1 | PEN2 | PEN3 | 1 | 2 | 3 |  |  |  |  |  |  |  |

#### SECTION 11: CHILD DEVELOPMENT

These questions need to be asked to the mother or main caregiver for the index child (0-24 months); Taken from PATH tool (MICS components)

Maswali haya yanatakiwa kuulizwa mama au mlezi wa mtoto mlengwa (mwenye umri wa miezi 0-24); yametolewa kwenya PATH (kitengo cha MICS)

|  | 1 |  |  |  |  |  |  |  | 2 |  | 3 | 4 | 5 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID of child | In the past 3 days, did you or any household member over 15 years of age engage in any of the following activities with [NAME]? Kwa siku 3 zilizopita, wewe au mtu mwingine kwenye kaya alifanya lolote kati ya yafuatayo na [JINA]? [RECORD ALL MENTIONED] [NAKILI YOTE YATAKAYOTAJWA] A=MOTHER (female primary caregiver)/ MAMA (mlezi mkuu wa kike) B=FATHER (male primary caregiver)/ BABA (mlezi mkuu wa kiume) X=OTHER MWINGINE Y=NO ONE HAMNA Z=DON’T KNOW SIJUI |  |  |  |  |  |  |  | When during the day do you normally play with [NAME] [ENUMERATOR, read these out one at a time and ask for a response]: Ni wakati gani wa mchana huwa una cheza na [JINA] {MHOJI: soma hizi moja moja alafu uliza jibu} Do you play with [NAME]. . . ? Huwa unacheza na [JINA] ... A = When bathing the child? Wakati unamuosha? B = When feeding the child?/ Wakati unamlisha? C = When changing the child? Wakati unambadilisha nguo? D = When doing chores? Wakati unafanya kazi? E = During work in the field?/ Wakati unafanya kazi nje ya nyumba? F = During free time? Wakati wa mapumziko? [Mark all that apply] [Andika majibu yote] |  | At what age can a child see? Mtoto huanza kuona akiwa na umri gani? [Months] | At what age can a child hear? Mtoto huanza kusikia akiwa na umri gani? [Months] | On how many days in the past week was [NAME]: Ni siku ngapi kwa wiki iliyopita [JINA]…. |  |
|  | a. With who did [child’s NAME] read books or looked at pictures? Kumsomea kitabu au kuangalia picha na [JINA]? | b. With who did [child’s NAME] tell stories? Kumhadidhia hadidhi [JINA]? | c. With who did [child’s NAME] sing songs including lullabies? Kumuimbia nyimbo [JINA] au kuimba pamoja maye [JINA] hata nyimbo za kulala? |  | d. With who did [child’s NAME] go for a walk outside the home, compound, yard or enclosure? Kumtembeza [JINA] nje ya hapa nyumbani/kaya? | e. With who did [child’s NAME] pplay? (ex. Peek-a-boo, clapping, hide and go-seek?) Kucheza na [JINA] (k.m kucgum, kupiga makofi, kujificha na kutafutana)? |  | f. With who did [child’s NAME]name, count or draw things? (ex. “It’s a dog”)/ kuita majina, kuhesabu au kuchora vitu na [JINA]? (k.m. ‘hii ni mbwa”) |  |  |  |  | A. Left alone for more than one hour? Aliwachwa peke yake kwa Zaidi ya lisaa limoja? | B. Left in the care of another child, that is, someone less than 10 years old for more than one hour? Aliwachwa atunzwe na mtoto, yaani, mtu ambaye ana umri chini ya miaka 10, kwa Zaidi ya lisaa? |
|  | A B X Y Z | A B X Y Z | A B X Y Z |  | A B X Y Z | A B X Y Z |  | A B X Y Z | A B C D E F |  |  |  |  |  |
|  | 6 |  |  | 7 |  |  | 8 |  |  |
| ID of child | How often do you have trouble soothing or calming [NAME] when he/she is crying or upset? Ni kwa uzoefu gani huwa unapata shida kumtuliza [JINA] wakati Analia au amekasirika? 1=Almost never Ni kama hakuna 2=Less than ½ the time/ Chini ya nusu ya mda 3=1/2 the time/ Nusu ya mda 4=More than ½ the time/ Zaidi ya nusu ya mda 5=Almost always/ Karibu kila wakati |  |  | During the average day, how often does your [NAME] get fussy and irritable? Kwa siku ya kawaida, ni mara ngapi [JINA] huwa analeta ugomvi/kukasirika? 1=Almost never/ Ni kama hakuna 2=Once or twice a day/ Mara moja au mbili kwa siku 3=Couple times in the morning and afternoon/evening/ Mara kadhaa mida ya subuhi na mchana/jioni 4=Several times a day/ Mara kadhaa kwa siku 5=Almost every hour/ Karibu kila lisaa |  |  | In general, compared to most toddler, how often does [NAME] cry and fuss? Kwa jumla, ukilinganisha na watoto wengine, ni mara ngapi [JINA] huwa anakasirika na kuleta ugomvi? 1=Almost never/ Ni kama hakuna 2=Less than average/ Chini ya kawaida 3=About average/ Ni kama kawaida 4=More than average/ Zaidi ya kawaida 5=Almost always/ Mara nyingi |  |  |

#### SECTION 12: CHILD DISCIPLINE

The respondent for this section should be the primary caregiver (woman) of the selected index child aged 0-24 months; Ask for each child 1 year – 14 years (inclusive) [MICS module]

Mhojiwa wa sehemu hii ni mlezi mkuu (wa kike) wa mtoto mlengwa (mwenye umri wa miezi 0-24). Uliza kwa kila mwenye umri wa miaka 1 hadi miaka 14 (hata aliyetimiza miaka 14)

|  | 2 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID of child | Adults use certain ways to teach children the right behaviour or to address a behaviour problem. I will read various methods that are used. Please tell me if you or any other adult in your household has used this method with (name) in the past four weeks. Watu wazima hutumia njia flani ili kuwafundisha watoto nidhamu njema au kusuluhisha tatizo la nidhamu. Nitasoma mbinu kadhaa ambazo hutumika. Tafadhali niambie kama wewe au mtu mwingine katika kaya ametumia mbinu hizi na [JINA] katika wiki nne zilizopita. 1=YES/ NDIO 2=NO/ APANA |  |  |  |  |  |  |  |  |  |
|  | A. Took away privileges, forbade something [NAME] liked or did not allow (him/her) to leave the house/ Kumnyima kitu anachokipenda [JINA] au kutomruhusu kutoka nje ya nyumba? | B. Explained why [NAME]’s behaviour was wrong/ Kumweleza [JINA] kwanini tabia yake sio nzuri? | C. Shook (him/ her)/ Kumtingiza [JINA]? | D. Shouted, yelled at or screamed at (him/her)/ Kumkemea, kumpigia kelele [JINA]? | E. Gave (him/ her) some-thing else to do/ Kumpa [JINA] kitu kingine cha kufanya? | F. Spanked, hit or slapped (him/her) on the bottom with bare hand/ Kumchapa, kumpiga kwa kutumia mkono au kofi ya matako [JINA]? | G. Hit (him/her) on the bottom or elsewhere on the body with something like a belt, hairbrush, stick or other hard object/ Kumpiga [JINA] kwenye makalio na kitu kingine kama vile mshipi, brashi au kiboko au kitu kigumu? | H. Called (him/ her) dumb, lazy or another name like that/ Kumuita majina kama vile mpumbavu, mlegevu au majina mengine? | I. Hit or slapped (him/ her) on the face, head or ears/ Kumpiga au kumzaba kofi kwenye uso, kichwani au masikioni? | J. Hit or slapped (him/ her) on the hand, arm, or leg/ Kumpiga au kumzaba kofi kwenye mkono au miguuni? |

After completing the questions for each child separately, ask the question below (only once per household!): Baada ya kumaliza maswali hayo kwa kila mtoto tofauti tofauti, uliza swali hili hapa (mara moja kwa kila kaya)

| 3 | Do you believe that in order to bring up, raise, or educate a child properly, the child needs to be physically punished?/ Je unaamini kwamba ili kumlea, kumkuza au kumfundisha mtoto vizuri, inabidi mtoto aewe adhabu ya kuchapwa/kimwili? | Yes Ndio 1 No Apana 2 Don’t know / No opinion/ Sijui/sina maoni 8 |
| --- | --- | --- |

| Section 12b: aTTITUDES TOWARD DOMESTIC VIOLENCE |  |  |
| --- | --- | --- |
| DV1. Sometimes a husband is annoyed or angered by things that his wife does. In your opinion, is a husband justified in hitting or beating his wife in the following situations: [A] If she goes out without telling him? [B] If she neglects the children? [C] If she argues with him? [D] If she refuses to have sex with him? [E] If she burns the food? | Yes No DK Goes out without telling 1 2 8 Neglects children 1 2 8 Argues with him 1 2 8 Refuses sex 1 2 8 Burns food 1 2 8 |  |

#### SECTION 13: NUTRITION & FEEDING KNOWLEDGE/ UFAHAMU WA LISHE NA KULISHA

Respondent for this section should be primary caregiver of the index child (0-24 months). DO NOT PROMPT OR PROVIDE ANSWERS, ALLOW RESPONDENT TO ANSWER AND THEN MARK ALL THAT APPLY

Mhojiwa wa sehemu hii ni mlezi mkuu (wa kike) wa mtoto mlengwa (mwenye umri wa miezi 0-24). USIMWONGOZE/USIMSOMEE MAJIBU, MUACHE AJIBU ALAFU ANDIKA MAJIBU YOTE YATAKAYOTAJWA.

|  | Question | Answers | Skip |
| --- | --- | --- | --- |
| 1 | How long after birth should a baby be first put to the breast? Ni mda gani baada ya kuzaliwa mtoto anafaa kunyonyeshwa? | Immediately/ within one hour/ Hapo hapo/ndani ya lisaa 1 Within one day/ Ndani ya siku moja …….. ……………..2 After one day/ Baada ya siku moja ………………….. 3 After more than one day/ Baada ya Zaidi ya siku moja 4 Baby should not be breastfed/ Mtoto hatakiwi kunyonya 5 Don’t know/ Sijui ……………………………………… 9 |  |
| 2 | Until what age should a baby by exclusively breastfed (only breastmilk, not even water?) Mtoto anatakiwa kunyonyeshwa maziwa ya mama pekee kwa mda gani baada ya kuzaliwa (maziwa pekee, bila hata maji? | Age in months:Umri kwa miezi ¦___¦___¦ Don’t know/ Sijui 99 |  |
| 3 | Why should a baby under 6 months be exclusively breastfed? Kwanini mtoto mchanga chini ya miezi 6 anatakiwa kunyonyeshwa pekee bila kupewa kitu kingine? [DO NOT READ RESPONSES; RECORD ALL MENTIONED] [USISOME MAJIBU; ANDIKA YOTE YATAKAYOTAJWA] | Protects baby from illness/disease/ Humlinda na magonjwaA Breast milk contains everything a baby needs for the first 6 months/ Maziwa ya titi yana kila kitu mtoto anahitaji hadi miezi 6…………………………………………………… B Helps baby grow better/ Husaidia mtoto kukua vyema C Mother less likely to get pregnant/ Mama ana uwezekano mdogo kupata mimba D Delays return of mother’s monthly bleeding/ Huchelewesha kurudi kwa hedhi ya mama E Breastmilk is clean, safe and convenient/ Maziwa ya titi ni safi, salama nay a urahisi F Breastmilk is free/affordable/ Maziwa ya titi na bure/ bila gharama G Reduces health care cost/ Hupunguza gharama za kiafya H Other/ Nyingine (eleza) X Don’t know/ Sijui Z |  |
| 4 | At what age should a baby first start to receive liquids (including water) other than breast milk? Ni katika umri gani mtoto anatakiwa kuanza kupewa vinywaji (yakiwepo maji) kando na maziwa ya mama? | Age in months: Umri kwa miezi ¦___¦___¦ Don’t know/ Sijui 99 |  |
| 5 | At what age should a baby first start to receive semi-solid foods (such as porridge) in addition to breast milk? Ni katika umri gani mtoto anatakiwa kuanza kupewa vyakula laini (kama vile uji) pamoja na maziwa ya mama? | Age in months: Umri kwa miezi ¦___¦___¦ Don’t know/ Sijui 99 |  |
| 6 | Can you list the food groups a child (6-23 months) is expected to eat in day?/ Unaweza kuniambia makundi ya vyakula ambayo motto (miezi 6-23) anatakiwa kula kwa siku? [DO NOT READ RESPONSES; RECORD ALL MENTIONED; MARK Other if they mention food groups that are not included in the official first 8]/ USIMSOMEE: ANDIKA ZOTE ZILIZOTAJWA; ANDIKA NYINGINE kama akitaja kundi linguine la chakula ambalo haliko kwenye hizo 8 rasmi] Note: concentrate on food groups/types and not on dishes or meals participants ate. E.g. grains and cereals rather than porridge. | Breast milk/ Maziwa na mama A Grains and cereals, roots, tubers and plantains/ Nafaka, mizizi, mimea B Pulses (beans, peas, lentils) nuts and seeds/ Maharagwe, njugu, choroko, karanga na mbegu C Dairy products (milk, infant formula, yogurt, cheese)/ Bidhaa za maziwa (maziwa, mazuwa ya kiwandani ya watoto, yogati , jibini D Flesh foods (meat, fish, poultry, organ meets)/ Chakula freshi (nyama, samaki, kuku, nyama za viungo E Eggs/ Mayai F Vitamin-A rich fruits and vegetables/ Matunda na mboga zenye wingi wa vitamin A G Other fruits and vegetables/ Aina zingine za mboga na matunda…………………………………….H Other/ Nyingine (Eleza)…………………………………X Don’t know/ Sijui Z |  |
| 7 | From the following 7 groups how many food groups are children expected to eat in a day? Group 1: Grains and cereals (e.g. oats for porridge), roots, tubers (e.g. potatoes) and plantains; Group 2: Pulses (e.g. beans, peas, lentils), nuts and seeds; Group 3: Dairy products (milk, formula, cheese, yogurt); Group 4: Meat and fish (incl. poultry and organ meat); Group 5: eggs; Group 6: Vitamin-A rich fruits and vegetables (green leafy vegetables, orange-fleshed sweet potatoes, carrots, pumpkin/squash, mango, papaya); Group 7: Other fruits and vegetables. Ni aina ngapi ya makundi ya vyakula ambayo motto anatakiwa kula kwa siku? Note: for this question you can mention the food groups and examples. | Number of groups:/ Idadi ya makundi ¦___¦___¦ |  |
| 8 | What can happen to children if they do not get enough different griups per day? Nini kitafanyikia watoto wakikosa makundi ya kutosha tofauti tofauti? [DO NOT READ RESPONSES; RECORD ALL MENTIONED] [USISOME MAJIBU; ANDIKA YOTE YATAKAYOTAJWA] | Impaired learning Kushindwa kujifundisha/kusoma A Impaired development/ Kutokukua vyema B Slow growth/lower height/ Kukua polepole/urefu mdogo C Low immunity/ Kinga duni/ndogo mwilini D Other/ Nyingine (eleza) X Don’t know/ Sijui Z |  |
| 9 | How many times a day should a 12-24 month old infant that is still breastfeeding eat? (meals and snacks) Ni mara ngapi kwa siku mtoto mchanga wa umri wa miezi 12-24 ambaye bado ananyonya anatakiwa kula? | Number/ Idadi ¦___¦___¦ Don’t know/ Sijui 99 |  |
| 10 | How many times a day should a 12-24 month-old infant (who is not breastfeeding) be given meals/snacks in a day? | Number/ Idadi ¦___¦___¦ Don’t know/ Sijui 99 |  |

#### SECTION 13B: WELFARE PERCEPTIONS

| 1 | Imagine six steps, where on the bottom, the first step, stand the poorest poorest people, and on the highest step, the sixth, stand the rich. On which step are you? | Today ¦___¦ Two months ago ¦___¦ |
| --- | --- | --- |

| 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- |
| Concerning your household’s food consumption over the past one month, which of the following is true? NOTE: ADEQUATE MEANS NO MORE NOR LESS THAN WHAT IS CONSIDERED TO BE THE MINIMUM CONSUMPTION NEEDS OF THE FAMILY 1=It was less than adequate for your family’s needs 2=It was just adequate for your family’s needs 3=It was more than adequate for your family’s needs 4=Not Applicable | Concerning your household’s housing, which of the following is true? NOTE: ADEQUATE MEANS NO MORE NOR LESS THAN WHAT IS CONSIDERED TO BE THE MINIMUM CONSUMPTION NEEDS OF THE FAMILY 1=It was less than adequate for your family’s needs 2=It was just adequate for your family’s needs 3=It was more than adequate for your family’s needs 4=Not Applicable | Concerning your household’s clothing, which of the following is true? NOTE: ADEQUATE MEANS NO MORE NOR LESS THAN WHAT IS CONSIDERED TO BE THE MINIMUM CONSUMPTION NEEDS OF THE FAMILY 1=It was less than adequate for your family’s needs 2=It was just adequate for your family’s needs 3=It was more than adequate for your family’s needs 4=Not Applicable | Concerning the health care your household gets, which of the following is true? NOTE: ADEQUATE MEANS NO MORE NOR LESS THAN WHAT IS CONSIDERED TO BE THE MINIMUM CONSUMPTION NEEDS OF THE FAMILY 1=It was less than adequate for your family’s needs 2=It was just adequate for your family’s needs 3=It was more than adequate for your family’s needs 4=Not Applicable | Concerning your children’s schooling, which of the following is true? NOTE: ADEQUATE MEANS NO MORE NOR LESS THAN WHAT IS CONSIDERED TO BE THE MINIMUM CONSUMPTION NEEDS OF THE FAMILY NOTE: SKIP IF NO CHILDREN 1=It was less than adequate for your family’s needs 2=It was just adequate for your family’s needs 3=It was more than adequate for your family’s needs 4=Not Applicable |

#### SECTION 14: OPERATIONAL PERFORMANCE/ UTENDAJI WA MRADI

| No. | Question | Answers | Skip |
| --- | --- | --- | --- |
| 0 | [CAPI] Note linenr of respondent |  |  |
| 1 | Are you aware of the NICHE program that is operating in this community? Je unaufahamu mradi wa NICHE unaoendelea katika eneo hili? [ENUMERATOR: If ‘NO’, explain what the NICHE program is to double-check respondent’s awareness.] [MHOJI: Kama “Apana” muelezee mhojiwa kuhusu mradi wa NICHE ili uhakiki tena ufahamu wa mhojiwa | Yes/ Ndio 1 No/ Apana 2 | Q8 |
| 2 | How did you know about the NICHE program? | Chief’s baraza…………………………………1 NICHE registration people……………………2 Through the Inua Jamii program……………...3 Community member………………………………..4 Other…………………………………………………5.. |  |
| 3 | What kind of services can you get from the NICHE program [Mark all that apply] | Top-up of cash transfer…………………………A Nutrition counselling…………………………...B Parenting and child protection counselling ……C Other (Specify)/ Nyingine (eleza) X Don’t know Sijui Z | >> Q4 >> Q6 |
| 4 | Do you know how much the top-up of the NICHE program is? | Amount in Ksh […] Don’t know ……99998 |  |
| 5 | How often will you receive the NICHE top-up? | One time……………………………………...1 Every month………………………………….2 Every two months……………………………3 Other…………………………………………99 Don’t know………………………………………..98 |  |
| 6 | Where is the nutrition counselling expected to be offered? | At home/ Nyumbani 1 At the health centre/clinic Katika kituo cha afya/kliniki 2 At the well-baby clinic/ Katika kliniki ya watoto 3 At a community gathering/ Katika mkutano wa kijiji4 Other (specify) Nyingine (eleza) 8 Don’t know………………………………………..9 |  |
| 7 | How many times is the nutrition counselling expected to be offered? | Weekly…………………………………………1 Every two weeks……………………………….2 Monthly ……………………………………….3 Other ………………………………………….9 Don’t know…………………………………….8 |  |
|  | We now want to ask questions about the cash transfer programs called Inua Jamii [For those who answered that they know NICHE, you can add that this includes NICHE] |  |  |
| 8 | Who do you think is eligible to receive a transfer from the Inua Jamii program? Unadhani ni nani anastahili kupokea pesa kutoka kwa mradi wa NICHE? [Mark all that apply] [Chagua zote zinazotajwa] | Pregnant women/ Wanawake waja wazito A Women with young children/ Wanawake wenye watoto wadogo B Women with children under 6 months old/ Wanawake wenye watoto wa umri chini ya miezi sita 6………………………………………………...C Individuals caring for many orphans/children/ Watu wanaowatunza yatima/ watoto wengi D Sick individuals/ Watu wagonjwa E Widowed individuals/ Wajane/Wagane F Individuals who are not able to work/ Watu ambao hawawezi kufanya kazi G Individuals with a disability/ Watu wenye ulemavu H Old individuals/ Wazee I Very poor individuals/ Watu maskini sana J Other (Specify)/ Nyingine (eleza) K Don’t know Sijui L |  |
| 9 | Do you think the selection process for the program is clear? Unadhani utaratibu wa kuchagua wanufaika wa mradi unaeleweka? | Yes, very clear / Ndio upo wazi kabisa 1 Yes, somewhat clear/ Ndio unaeleweka kiasi 2 Neutral/ Katikati 3 No, not so clear/ Apana, haueleweki vizuri 4 No, not clear at all/ Apana, haueleweki hata kidogo 5 |  |
| 10 | Do you know where to go if you have any questions regarding the Inua Jamii program or eligibility? | Yes Ndio 1 No Apana 2 |  |
| 11 | Have you or any other member of the household ever received payments or other services from the Inua Jamii program? Wewe au mtu mwingine kwenye kaya hii amewahi kupokea malipo au huduma zozote kutoka kwa mradi huo? | Yes Ndio 1 No Apana 2 | If 2 Next section |
| 12 | Can I see your program identification card? Naweza kuona kadi yako ya mradi huo? Enumerator: Copy ID of the individual/ Mhoji: Nakili kitambulisho cha mnufaika | XXXXXXXXXXXX [12 digits] 999999999999 = ID not available or illegible / Kitambulisho hakipo au hakisomeki |  |
| 13 | Are you or any other members of your household still participating in the program, and expecting to receive payments or other services from the program? Je wewe au mwanakaya mwingine badoo yupo kwenye mradi na anatarajia kupata malipo au huduma kutoka kwa mradi? | Yes Ndio 1 No Apana 2 | Q15 |
| 14 | If not, why not? Kama apana, kwanini? | No longer eligible/ Kwa sasa hakidhi 1 Beneficiary moved out of household/ Mnufaika alihama kutoka kwenye kaya 2 Missed the collection of consecutive payments/ Kukosa kupokea malipo ya awali yakifuatana 3 Voluntarily left the programme: didn’t need it / Kuamua kujitoa kwenye mradi: hakuuhitaji 4 Voluntarily left the programme: programme did not work properly/ Kuamua kujitoa kwenye mradi: mradi ulikua hauendelei vizuri 5 Voluntarily left the programme: too many Conditions/ Kuamua kujitoa kwenye mradi: masharti mengi sana 6 Enrolled in another cash transfer programme/ Alikuwa kwenye mradi mwingine wa kupokea pesa 7 Did not follow rules (conditions) Hakufuata sheria (masharti)…………………..8 Other, specify Nyingine (eleza) _________________________ 9 Don’t know/ Sijui 10 |  |
| 15 | How many eligible beneficiaries are there in this household? Kuna wanufaika wangapi wanaokidhi katika kaya hii? | One/ Mmoja 1 Two/ Wawili 2 Three/ Watatu 3 Four or more/ Wanne au zaidi 4 |  |
| 16 | When was the last time you received a payment? List month and year. Ni lini mara ya mwisho ulipokea malipo hayo? Nakili mwezi na mwaka | Month: Mwezi: ¦___¦___¦ Year: Mwaka ¦___¦___¦___¦___¦ |  |
| 17 | How much did you receive the last time? Ulipokea kiasi gani? | Amount received in Ksh Kiasi alichopokea Kshs Don’t know/remember/ Sijui/Sikumbuki 99999 |  |
| 18 | How much did you receive the time before last payment? | Amount received in Ksh Kiasi alichopokea Kshs Don’t know/remember/ Sijui/Sikumbuki 99999 |  |
| 19 | In total, how many payments have you received? Kwa jumla, umepokea malipo mara ngapi? | Number Idadi |  |
| 20 | How often do you receive the payments | Every month………………………………………1 Every two months…………………………………2 Every three months………………………………..3 More than three months in between payments……...4 Not at a regular time………………………………5 Don’t know………………………………………..98 |  |
| 21 | When do you expect the next payment? Ni lini unatarajia malipo mafuatatyo/mengine? | Number of months Idadi ya miezi Don’t know/ Sijui …..……………………………..98 Never/ Hakuna 99 |  |
| 22 | How long in the future do you expect to continue receiving this money? Ni kwa mda gani unatarajia kuendelea kupata malipo haya? | Number of months Idadi ya miezi Don’t know Sijui ……...…………………………..98 Longer/rest of my life/ Mda mrefu/maisha yangu yote 99 |  |
| 23 | For the last payment, how long did you need to travel to the Payment point to collect the payment and coming back? [Only travel time] Kwa malipo ya mwisho yaliyopita, ilibidi usafiri kwa mda gani ili kufika sehemu ulipolipiwa na kurudi (Kusafiri tu) [Always record both hours and minutes. E.g. 1,5 hours is 1 hour 30 minutes. 40 minutes is 0 hours and 40 minutes. 2 hours is 2 hours and 0 minutes] [Mda wote nakili kwa masaa na dakika, mfano masaa 1.5 ni lisaa moja na dakika 30, dakika 40 ni masaa 0 na dakika 40, masaa 2 ni masaa 2 na dakika 0] | Hours: Masaa ¦___¦___¦ Minutes: Dakika ¦___¦___¦ Don’t know/remember/ Sijui/Sikumbuki 99 |  |
| 24 | For the last payment, how much money did you spend on transportation to travel from your house to the payment point and back again? Kwa malipo ya hivi karibuni sana, ni kiasi gani cha pesa ulitumia kwa kusafiri kutoka nyumbani kwako kwenda ulipolipiwa na kurudi tena nyumbani? | Amount spent on transport in Ksh/ Kiasi cha pesa Ksh Don’t know/remember Sijui/Sikumbuki 999 |  |
| 25 | In general, who receives the Inua Jamii? | Respondent 1 Spouse 2 Respondent and spouse……………………………..3 Other adult family members 4 Respondent’s child or other child in the household 5 Other…………………………………………….98 |  |
| 26 | At any point before or after payment were you asked to give money/ gifts OR voluntarily gave money / gifts to anyone in order to receive payment? Wakati wowote kabla au baada ya malipo, uliwahi kuulizwa upeane pesa/zawadi au ukajitolea kupeana pesa/zawadi kwa mtu yeyote ili upokee malipo yako? | Asked to give and did so Niliulizwa na nikatoa 1 Asked to give and refused Niliulizwa na nikakataa 2 Voluntarily offered and person accepted the money/ gifts Nilijitolea nikatoa na mtu akachukua pesa/zawadi 3 Voluntarily offered but person refused to take money/ gifts Nilijitolea nikatoa lakini mtu akakataa akachukua pesa/zawadi 4 Don’t know/refused/ Sijui/ Alikataa kujibu 5 |  |
| 27 | In general, do you feel safe collecting the money from the payment point and taking it back home? Kwa ujumla, huwa unahisi uko salama kupokea malipo sehemu unapolipiwa na kurudi nayo nyumbani? | Yes, I feel safe/ Ndio, najihisi niko salama 1 No, I feel unsafe during transit/ Apana, nahisi siko salama wakati wa kusafiri 2 No, I feel unsafe at the payment point/ Apana, nahisi siko salama sehemu ninayopokea pesa 3 No, I feel unsafe at the payment point AND in transit home/ Apana, nahisi siko salama sehemu ninayopokea pesa na pia wakati wa kusafiri 4 |  |
| 28 | In this household, who generally decides how the payment from the program is used? Katika kaya hii, nani kwa ujumla anafanya maamuzi ya malipo yanayotoka kwa huo mradi yatakavyotumiwa? | Member ID: Kitambulisho cha mwanakaya ¦___¦___¦___¦ |  |
| 29 | In general, who does [NAME] consult with when deciding how to use the payment from the program? Kwa ujumla, [JINA] huwa anashaurianan na nani wakati wa maamuzi ya matumizi ya malipo kutoka kwa mradi? | Alone/ Pekee yake 1 Spouse/ Mwenza 2 In consultation with other adult family members/ Kwa kushauriana na wanakaya wengine watu wazima 3 In consultation with children/ Kwa kushauriana na watoto 4 In consultation with ALL family members/ Kwa kushaurianan na wanakaya wote 5 In consultation with someone else in the community/ Kwa kushauriana na mtu mwingine katika kijiji hiki6 |  |
| 30 | Has there every been any disagreements on how to spend the money? | Yes/ Ndio 1 No/ Apana 2 |  |
| 31 | Did you give any of the money to family, friends or others living outside your household as gifts or contributions for social causes? Je ulipeana baadhi ya hizo pesa kwa wanafamilia, marafiki au wengine nje ya kaya yako kama zawadi au mchango ya maswala mengine ya kijamii? | Yes/ Ndio 1 No/ Apana 2 |  |
| 32 | In general, what are the three main things that the payment from the program are used for. Kwa ujumla, ni mambo gani makuu matatu ambayo malipo hayo yanatumika kufanya? | Food and nutrition /Chakula na lishe A Formal government education (fees, textbooks, uniforms etc.)/ Elimu rasmi ya serikali (karo, vitabu, sare n.k) B Other education (nursery, other religious school)/ Elimu nyingine (chekechea, shule za kidini) C Health care/ Huduma za afya D Shelter / Accommodation / Rent/ Makazi/ sehemu ya kulala/Kodi ya nyumba E Clothing / Shoes (does not include school uniforms) Mavazi/ viatu (sio sare za shule) ………….. F Investment/small business/ Kuwekeza/ biashara ndogo G Formal social occasions such as weddings and funerals/ Matukio rasmi ya kijamii kama harusi, matanga H Savings/VSLA/ Akiba/VSLA I Water………………………………………………...J Transportation……………………………………….K Other spending, specify Matumizi mengine (eleza) _ L |  |
|  | NUTRITION COUNSELING COMPONENT | KITENGO CHA USHAURI WA LISHE |  |
| 33 | In the past month, i.e. since [cite the date 30 days ago] has anyone talked or sensitized you around nutrition for you or your child? Kwa mwezi mmoja uliyopita yaani, kuanzia [taja tarehe ya siku 30 zilizopita], kuna mtu yeyote amekueleza kuhusu lishe bora kwako na mtoto wako? | Yes Ndio 1 No Apana 2 | Next section |
| 34 | How many times did someone sensitize you around nutrition in the past month? Ni mara ngapi mtu yeyote amekushauri kuhusu lishe kwa mwezi mmoja uliyopita? | Once ? Mara moja 1 2-3 times / Mara 2-3 2 More than 3 times / Zaidi ya mara 3 3 |  |
| 35 | Who talked to you about nutrition? Please select all that apply. These should be people who talked to you about nutrition in the past month only Ni nani alikushauri kuhusu lishe? Chagua majibu yote. Wawe ni watu waliokushauri ndani ya mwezi mmoja uliyopita pekee? | A community worker/ Mfanyakazi wa jamii 1 A nurse or health care workers/ Nesi au mhudumu wa afya………………………………………….. 2 Someone from the district Mtu kutoka wizarani.. 3 Another government workers, such as a teacher/ Mfanya kazi mwingine wa serikali, kama mwalimu4 Other (specify)/ Nyingine (eleza) ,,,,,,,,,,,,,,,,,,,,, 5 |  |
| 36 | You said that a community worker/nurse or HCW/someone from the district/another government worker/Other came and talked to you in the past month. How long was that event? Umesema kwamba mhudumu wa jamii/nesi/mtu kutoka wilayani/mfanya kazi wa serikali au mtu mwingine alikuja na akakushauri kuhusu lishe kwa mwezi mmoja umepita. Shughuli hio ilichukua mda gani? (if the nutrition talk was part of a bigger event, for example under-5, just ask for how long did they talk about nutrition) (Endapo maongezi ya lishe ilikua sehemu ya shughuli nyingine kubwa, uliza tu waliongea kuhusu lishe kwa mda gani) | Talked about nutrition for less than 5 minutes/ Waliongea kuhusu lishe kwa mda chini ya dakika 5 1 5-15 minutes/ Dakika 5-15 2 15-30 minutes Dakika 15-30 3 More than 30 minutes Zaidi ya dakika 30 4 |  |
| 37 | Where was that? Ilikuwa ni wapi? Do NOT prompt the answers, let respondent answer freely and then tick appropriate answer/ Usimsomee, ngojea mhojiwa ajibu alafu uchague majibu atakayotaja | At the health centre/clinic Katika kituo cha afya/kliniki 1 At the well-baby clinic/ Katika kliniki ya watoto 2 At home/ Nyumbani 3 At a special event for this purpose/ kwa shughuli maalum ya lengo hilo 4 At a women’s agricultural group/ kwa kikundi cha kilimo cha wanawake 5 At a cooking demonstration/ Katika maonyesho ya upishi 6 Over the phone/text/ Kwenye simu/ujumbe wa simu 7 Other (specify)/ Nyingine (eleza) 8 |  |
|  | PARENTING COMPONENT (only in Kilifi and surrounding comparison areas)/ KITENGO CHA ULEZI (Kilifi tu na maeneo ya karibu ya kulinganisha) |  |  |
| 38 | In the past month, i.e. since [cite the date 30 days ago] has anyone talked or sensitized you around parenting and violence prevention for you or your child?/ Kwa mwezi mmoja uliyopita yaani, kuanzia [taja tarehe ya siku 30 zilizopita], kuna mtu yeyote amekueleza/kukushauri kuhusu malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako? | Yes/ Ndio 1 No / Apana 2 | Next section |
| 39 | How many times did someone sensitize you around parenting and violence prevention in the past month? Ni mara ngapi mtu yeyote amekueleza/kukushauri kuhusu malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako? | Once Mara moja 1 2-3 times / Mara 2-3 2 More than 3 times / Zaidi ya mara 3 3 |  |
| 40 | Who talked to you about parenting and violence prevention? Please select all that apply. These should be people who talked to you about parenting and violence prevention in the past month only/ Ni nani alikushauri kuhusu malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako? Chagua majibu yote. Wawe ni watu waliokushauri malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako ndani ya mwezi mmoja uliyopita pekee? | A community worker/ Mfanyakazi wa jamii 1 A nurse or health care workers/ Nesi au mhudumu wa afya………………………………………….. 2 Someone from the district Mtu kutoka wizarani.. 3 Another government workers, such as a teacher/ Mfanya kazi mwingine wa serikali, kama mwalimu4 Other (specify)/ Nyingine (eleza) ,,,,,,,,,,,,,,,,,,,,, 5 |  |
| 41 | You said that a community worker/nurse or HCW/someone from the district/another government worker/Other came and talked to you in the past month. How long was that event? Umesema kwamba mhudumu wa jamii/nesi/mtu kutoka wilayani/mfanya kazi wa serikali au mtu mwingine alikuja na akakushauri kwa mwezi mmoja umepita. Shughuli hio ilichukua mda gani? (if the parenting and violence prevention talk was part of a bigger event, for example under-5, just ask for how long did they talk about parenting and violence prevention) / (Endapo maongezi ya malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako ilikua sehemu ya shughuli nyingine kubwa, uliza tu waliongea kuhusu malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako kwa mda gani) | Talked about nutrition for less than 5 minutes/ Waliongea kuhusu malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako kwa mda chini ya dakika 5 1 5-15 minutes/ Dakika 5-15 2 15-30 minutes Dakika 15-30 3 More than 30 minutes Zaidi ya dakika 30 4 |  |
| 42 | Where was that? / Ilikuwa ni wapi? Do NOT prompt the answers, let respondent answer freely and then tick appropriate answer / Usimsomee, ngojea mhojiwa ajibu alafu uchague majibu atakayotaja | At the health centre/clinic Katika kituo cha afya/kliniki 1 At the well-baby clinic/ Katika kliniki ya watoto 2 At home (with a home-visit)/ Nyumbani (kutembelewa nyumbani) 3 At a special event for this purpose/ Katika hafla maalum kwa lengo hili 4 At a community gathering/ Katika mkutano wa kijiji5 Over the phone/text/ Kwenye simu/ujumbe wa simu 6 Other (specify) Nyingine (eleza) 8 |  |
| 43 | In the last 30 days, have you heard any messages on parenting or violence prevention on the radio/ Kwa siku 30 zilizopita, umesikia ujumbe wowote kuhusu malezi na jinsi ya kuzuia ukatili/fujo kwako na mtoto wako kwenye radio? | Yes / Ndio 1 No / Apana 2 |  |

#### SECTION 15: ANTHROPOMETRICS/ VIPIMO NA REKODI

MEASURE INDEX CHILD 0-24 months. Record weight and height, with minimal clothing. Also observe and record whether the child has oedema or not. MPIME MTOTO MLENGWA MIEZI 0-24. Nakili uzito na urefu, akiwa amevaa nguo chache iwezekanavyo. Pia angalia na unakili endapo mtoto ana Oedema au hana.

[INSTRUCTIONS: Two measurements of height and weight will be taken for each individual and if the difference is > 0.5 cm or 0.5 kg a third measurement should be taken to verify the first two measurements.]

[MAELEKEZO: Vipimo vya uzito na urefu vitafanywa mara mbili kwa kila mtoto na endapo tofauti kati yazo ni >centimita 0.5 au >kilo 0.5, kipimo cha tatu kitafanywa ili kubaini vipimo vya awali viwili.

|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MEMBER ID | Is [NAME] available to be measured? Je [JINA] anapatikana kwa ajili ya kupimwa? 1 = Yes/ Ndio 2 = No/ Apana >> Next section (Section 00) Sehemu inayofuata (Sehemu ya 00) | What is [NAME'S] day, month and year of birth? Je [JINA] alizaliwa siku, mwezi na mwaka gani? (DD / MM /YY) | What is the source of information on the individual’s birth date? Chanzo cha taarifa za kuzaliwa za mtoto zimetoka wapi? 1=Birth certificate/ Cheti cha kuzaliwa 2=Baptismal record/ Taarifa za ubatizo 3=Clinic card/ Kadi ya kliniki 4=Home record/ Rekodi za nyumbani 5=Determined using local calendar of events/ Kulinganisha na matukio ya kijijini 6=Mother/caregiver recall/ Kumbukumbu ya mama/mlezi 7=Recollection by other persons/ Kumbukumbu ya watu wengine 8=Other (specify)/ Nyingine (eleza) | Was [NAME] measured? Je [JINA] amepimwa? 1=YES, laying down/ Ndio akiwa amelazwa (>>Q5) 2=YES, Standing/ Ndio akiwa amesimama (>>Q5) 3=NO/ Apana | Why not? Kwanini hajapimwa? 1=Not home during survey period,/ Hakuwa nyumbani kipindi cha utafiti 2=Too ill,/ Mgonjwa sana 3=Handicapped or deformed,/ Ni mlemavu 4=Not willing,/ Hataki 5=Other (specify)/ Nyingine (eleza) (>> END) | Weight in kilograms Uzito kwa kilo [USE ONE DECIMAL PLACE] [ANDIKA HADI NUKTA MOJA TU] | Was [NAME] undressed to the minimum? Je [JINA] alivuliwa nguo inavyowezekana? 1=Yes/ Ndio 2=No, child could not be undressed fully/ Apana, mtoto asingeweza kutolewa nguo kabisa | Height in centimeters Urefu kwa centimeta [USE ONE DECIMAL PLACE] [ANDIKA HADI NUKTA MOJA TU] | MUAC Always measure the left arm and write the result in centimeters/ Wakati wote pima na uandike urefu wa mkono wa kushoto. [USE ONE DECIMAL PLACE] ANDIKA HADI NUKTA MOJA TU] Note: Do not round the values obtained Elezo: usiweke kwa ujumla | Check for oedema (children only) Angalia kama ana Oedema (Mtoto pekee) 1=Oedema present/ Oedema ipo 2=Oedema not present/ Oedema haipo 3=Unsure/ Hakuna uhakika 9=Not checked (specify reason)/ Hakuangaliwa (eleza sababu) | Did you refer [NAME] to the health facility? Ulimuelekeza [JINA] kwa kituo cha afya? 1=YES NDIO 2=NO/ APANA |
|  |  | ¦__¦__¦/¦__¦__¦/¦__¦__¦__¦__¦ |  |  |  | ¦___¦___¦___¦.¦___¦ |  | ¦___¦___¦___¦.¦___¦ | ¦___¦___.¦___¦ |  |  |

# Annex E – Team Composition and Responsibilities

The AIR team consists of highly qualified staff who will apply their content, methodological and project management expertise to this work. In this annex, we describe the team’s composition and articulate each key team member’s responsibilities. In constructing the team, our object was to ensure that we could provide UNICEF with a high level of content and methodological expertise deployed efficiently (see Figure E1).

Figure E1. Evaluation Team Composition

As our team leader, Dr. Juan Bonilla, has experience in designing and managing large-scale, policy-relevant social programmes, including programmes in social protection, agricultural development, maternal and child health and nutrition, and education policy. For this evaluation, he oversees the completion of all study activities and serves as the primary point of contact for UNICEF. Dr. Bonilla has ultimate responsibility for ensuring the quality and timeliness of the work. He will contact UNICEF KCO immediately if challenges arise that could jeopardize the quality or timeliness of any required output. He has 13 days for this evaluation.

Our nutrition planning and research expert, Emiliana Mbelenga, based in Nairobi, has extensive experience working with international organizations, including UNICEF, FAO, FCDO on nutrition-related projects. Ms. Mbelenga has a deep understanding of the country, and work/research experience in various counties including Kitui county which is one of the focus areas for the formative research component. She contributes to the review of the NICHE II program design, will conduct key informant interviews during the formative research component and will contribute to the development of the formative evaluation report. She will work directly with the AIR evaluation team and contributes 10 days to the evaluation.

Our nutrition monitoring and evaluation expert, Tamsin Walters, has extensive experience in strategic evaluation, country contextual analysis and development of national nutrition policies and plans to support scaling up of nutrition programmes in over 30 countries. Ms. Walters leads Component 3 focusing on the refinement of indicators and tools on nutrition and feeding practices for the M&E framework. She will also support the team in interpreting the baseline results. She contributes 10 days to the evaluation.

Our qualitative lead, Hannah Ring, is working and has worked on several cash transfer evaluations across Africa and the Middle East. As the qualitative lead, she is responsible for leading the development of the qualitative data collection tools, ensuring alignment with the research questions, overseeing the Dalberg Research team through qualitative data collection, and supervising the work of the qualitative research associate. She has 29 days on this project.

Dr. Marlous de Milliano, the quantitative lead and project manager, has contributed to the data collection and analysis of various cash transfer programmes. Dr. de Milliano is responsible for the design and implementation of the quantitative primary data collection and the analysis and reporting of these data. She will also oversee the work of Dalberg during the quantitative data collection and supervise the quantitative research associate. As project manager she is also responsible for the team’s internal coordination of tasks related to this evaluation. She has 35 days on this evaluation.

Dr. David Seidenfeld serves as the quality assurance reviewer. In this role, he will enlist his deep understanding of social protection programmes and research methodologies to review all deliverables and research outputs developed by the team to ensure the highest level of quality. Dr. Seidenfeld is Senior Vice President at AIR and leads AIR’s International Development Division. He has 2 days on the evaluation.

AIR’s core team of experts is supported by an experienced quantitative research associate and an experienced qualitative research associate, who assist the leads in all stages of the assessment. Working under the supervision of the senior AIR staff members, the research associates are responsible for supporting project coordination, conducting quality checks on the qualitative and quantitative data, data analysis and synthesis of data. The research associates have between 30 and 32 days on the project. Finally, we draw upon AIR’s professional finance and contracts staff, publications staff and information technology specialists as needed.

The majority of the AIR team is based in the United States for the duration of the study, collaborating with the Dalberg Research team via calls, video conferencing and WhatsApp messaging. The evaluation team at Dalberg Research will provide its expertise in study design, instrument translation and validation, participant recruitment, data collection, reporting and dissemination. Dalberg is responsible for coordinating all data collection efforts, traveling throughout the country where possible.

# Annex F – Terms of Reference

TERMS OF REFERENCE (TOR) FOR INSTITUTIONAL CONTRACTORS-RFP 9161003 -2020

| PART I |  |  |
| --- | --- | --- |
| Purpose of Assignment | Evaluation of the Nutritional Improvements through Cash and Health Education (NICHE) II program |  |
| Location of Assignment | Home-based (due to COVID-19 global pandemic) and in program sites in Kitui, Kilifi, West Pokot, Turkana and Marsabit counties |  |
| Duration of contract | 5 months |  |
| Start date | From: 1st October 2020 |  |
| Reporting to: | Chief Nutrition (Immediate Supervisor: Nutrition Specialist/NICHE technical committee for Impact Evaluation) |  |

1.0 Background

1.1 Social protection context

In Kenya, social protection is entrenched in primarily three ways, through: the National Safety Net Program providing cash transfer programs to the most vulnerable; the National Social Security Fund which provides social security protection to formal and informal workers in form of retirement packages; and the social health insurance implemented by the National Health Insurance Fund (NHIF). The Kenya Social Protection Policy was launched in 2011, being built on the government of Kenya’s commitment to reducing poverty, as articulated in Kenya Vision 2030. The Policy further commits the government of Kenya to reducing vulnerabilities of the population to economic, social, and natural shocks and stresses through both cash-oriented programs and complementary services like nutrition and child protection. It aims at increasing access to such social welfare services by vulnerable groups.

1.2 National Safety Net Program

The Kenya National Safety Net Program (NSNP) was established in September 2013 and is constituted by four cash transfer programs: the Cash Transfer for Orphans and Vulnerable Children (CT-OVC), Older Persons Cash Transfers (OP-CT), Cash Transfers for People with Severe Disabilities (PWSD - CT) and the Hunger Safety Net Program (HSNP). The overall aim of the NSNP has been to improve the welfare and alleviate poverty and vulnerabilities of the most vulnerable households. In this regard, extremely poor households which have an orphan/vulnerable child or older person of above 65 years or a person with a severe disability are targeted and receive a bi-monthly sum of 4,000 Kenyan shillings. Beneficiaries of the HNSP receive a bi-monthly sum of 5,400 Kenyan shillings. Although the NSNP cash transfers have made a profound difference in the lives of its beneficiaries, there is still a need to for this set of service to move beyond cash transfers to include complementary services which would fosters resilience and improve well-being. The GoK in collaboration the World Bank, and the United Kingdom’s Department for International Development (DFID) has recently designed the Kenya Social and Economic Inclusion Project (KSEIP) which seeks to move beyond cash transfers by promoting social and economic inclusion of the poor by providing a variety of complementary services to the NSNP beneficiaries. The KSEIP will be undertaken from 2019 to 2023 and will comprise of three components as below:

- Component 1: Enhancing institutional capacity and social protection delivery systems, particularly the coverage and functionality of the Social Registry, as well as continuing to improve the efficiency of other delivery mechanisms;

- Component 2: Investing in the scale-up of the existing nutrition-sensitive safety net, and testing customized economic inclusion models as a complement to the regular cash transfers to improve human capital and the self-sufficiency of poor and vulnerable households;

- Component 3: Improving the shock responsiveness of the safety net system by expanding its coverage and strengthening financing arrangements for enhancing households’ resilience and providing timely support to cope with recurrent climate-induced droughts.

The 1st and 3rd component of KSEIP are exclusively being implemented by the GoK and are outside the scope of UNICEF’s support. The second component, which comprises of integrating nutrition and social as well as child protection, will constitute the Nutrition Improvements through Cash and Health Education (NICHE II) program.

UNICEF’s Strategies and County Program Outcomes

The UNICEF Global Social Protection Program Framework advocates for human rights based i.e. child-sensitive Social protection which also underlies the NICHE approach where households with young children are targeted. On the other hand, UNICEF’s Global Strategy for Nutrition aims at reducing stunting. In addition, UNICEF Programming Guidance “Improving young children’s diets during the complementary feeding period” and the “Actions Framework to improve the diets of young children in Eastern and Southern Africa Region” focused on systems approaches to tackle a key determinant of child undernutrition and specifically highlights the respective and complementary roles of the education, food, water, sanitation and hygiene, health and nutrition, and social protection system. The last two systems are at the center of the implementation or NICHE in the five counties in Kenya. The Kenyan Nutrition Action Plan; which articulates the priorities for the Kenyan government on Nutrition, identifies reduction of stunting as its main goal. In tandem with this, NICHE aims at addressing the determinants of stunting by securing optimal feeding practices through both SBCC and provision of extra household cash.

In Kenya, stunting, wasting and being underweight were estimated at 26%, 4% and 11% among children under five years of age in 2014. The brunt of the burden of malnutrition is borne by the arid and semi-arid (ASAL) counties. Interventions which purport to increase household’s food purchasing power are thus deemed as more fitting; additional to high impact nutritional interventions like promotion of breastfeeding and child protection.

Little is known about the magnitude of sub-optimal parenting skills in the Kenyan context, even though it is appreciated from proxy indicators that this is a significant social welfare and public health problem. Nevertheless, it is estimated that 79% of boys and 76% of girls experience physical, sexual and/or emotional violence before the age of 18 in Kenya.

The NICHE program contributes to three outcomes of 2018-2022 Government of Kenya and UNICEF Kenya Country Office joint Program:

Outcome 4 (Social inclusion): An increased number of children from the poorest & most vulnerable households benefit from shock-responsive & integrated social protection interventions, as well as from child-specific policies and more specifically Output 4.1: Social service demand is strengthened through modelling of evidence-based linkages between social protection and social/economic sectors (including health, nutrition, protection, energy, and HIV) in select counties.

Outcome 1 (Reduced Mortality & Stunting): Increased proportions of vulnerable children, pregnant and lactating women, including adolescent girls, have equitable access to and use quality WASH, Nutrition, Health, and HIV/AIDS services to reduce their risk of mortality, preventable diseases, stunting and other forms of malnutrition, and improve their birth outcomes. Specifically, this consultancy will contribute to Activity 1.1.2: Development of strategic partnerships and linkages to increase nutrition sensitivity of existing social protection programs for household resilience.

Outcome 3: By 2022, Children and adolescents are increasingly protected from exposure to HIV and AIDS, violence, abuse, exploitation, harmful cultural practices, and benefit from increased access to prevention, care, treatment, support, justice and other services needed to ensure their physical, mental and social well-being

Output 3.1. By 2022, Children, parents, caregivers, and communities in target counties, urban informal settlements and refugee settings have knowledge and adopt desirable practices to prevent and respond to HIV/AIDS, violence, abuse and exploitation of girls and boys, and have improved service seeking behaviors

Additional background information pertaining to the program context has been provided as an Annex (Annex 1).

1.3 The NICHE I pilot

The design and scale up of the NICHE II package of interventions is informed by findings from an initial pilot (NICHE I) which was delivered through a Randomized Controlled Trial in Kitui from January 2017 to June 2018. In this regard the NICHE I beneficiaries were limited to only CT-OVC beneficiaries who received the additional cash top and nutrition counselling (intervention arm of the RCT) and were compared against similarly eligible CT-OVC beneficiaries who did not receive the extra cash-top up & nutrition counselling. The trial proved that the combined package of the cash-top up and nutritional counselling delivered additional to a cash transfer program improved young children’s feeding practices and quality of mothers’ diets though not stunting. The trial did not examine the effect yielded from the various components of the NICHE intervention i.e. whether quality of feeding of women and children can be improved through only adding the nutrition counselling by itself without the extra cash-top up.  The trial did not address implementational related questions, for instance whether the implementation of NICHE at a large scale, where the intensity of the counselling component is moderated, can still yield a positive impact on the nutrition of young children and mothers and improve the delivery of more integrated services of social protection, health and nutrition.

2.0 Program Overview

2.1 Program Overview of NICHE II

NICHE II will be implemented by GoK through UNICEF’s technical support. The program will be implemented in five counties (Kitui, Kilifi, Marsabit, Turkana, West pokot).

As part of NICHE II,  an additional cash top-up of 500 shillings will be offered to NSNP beneficiary households which have a child under two years or a pregnant or lactating woman (i.e. beneficiary households of the four cash transfer programs i.e. CT-OVC, OP-CT, PWSD-CD, HSNP). The households receiving the cash-top up will also be offered intensive nutrition counselling (and child protection counselling in Kilifi) by utilizing the community health strategy platform and Baby Friendly Initiative approach (BFCI).

In order to secure protection of children within NSNP beneficiary households and surrounding communities from violence, abuse, exploitation and neglect, child protection education will be included in the program in one of the five counties, in Kilifi as a pilot for integrating child protection SBCC with nutrition SBCC. Due to limited resources the rest of the four counties will only execute the nutrition component of the SBCC. During the first 3 years of the NICHE II program, UNICEF will provide technical support for the implementation of the program. In the last two years of the program, the program will be implemented without UNICEF support. The key stakeholders in the NICHE II Program are the Ministry of Labor and Social Protection, the Ministry of Health, Ministry of Devolution and Arid and Semi-Arid Lands (MD&ASAL), Council of Governors (COG) and UNICEF.

The nutrition and child protection counselling in NICHE will be delivered through operationalizing the Baby-friendly Community Initiative (BFCI). The BFCI is a global initiative which packages standardized-evidenced based complementary community-based interventions aimed at improving infant and young child feeding practices as well as mothers’ dietary adequacy. In Kenya, the BFCI is adopted by the Ministry of Health as the approach for delivery of community-based nutrition services to secure optimal nutrition for young children and mothers. However, the BFCI platform has not been rolled out to scale in most counties. As part of the NICHE interventions, BFCI will be scaled up in the counties where NICHE will be implemented.

When the BFCI package is implemented to scale it entails: i) awareness raising to key decision and policy makers on optimal feeding and hygiene practices for children and mothers ii) training of health workers and community volunteers on promotion of optimal hygiene, health seeking, and feeding practices for young children as well as pregnant and lactating women iii) mentorship of community volunteers in providing community based counselling iv) formulation and support of community-based structures (mother-to-mother support groups, community groups) for peer support on optimal practices as well as community engagement in the provision of nutrition services v) establishment and support of feedback mechanisms and platforms where the community provides feedback on delivery of nutrition services within the health facilities. Thus, in the NICHE counties, BFCI is envisioned to improve nutritional and hygiene related behaviors of caregivers, create community platforms where the community engages and empowers itself to promote optimal nutritional practices. It is important to note for the planning of the NICHE the evaluation, that while as the home-based nutrition counselling that will be offered will be limited to NICHE beneficiary households, the nutrition promotion through the community structures to be established will serve the communities at large.

2.2 NICHE II Objectives and Theory of Change

A detailed illustration of the NICHE II program Theory of Change has provided as an Annex. At the impact level the program envisions improving well-being of women and children in the areas of nutrition, social and child protection. This will be achieved through two main outcomes a) improved behavioral practices of caregivers and b) improved functionality of both community and institutional systems to deliver integrated nutrition, social and child protection services.

The key behaviors to promoted, through NICHE II are further detailed below (i.e. key NICHE SBCC practices):

Health seeking behavior

  - Early and continuous antenatal care utilization

  - Skilled birth attended deliveries

  - Growth monitoring utilization

  - Immunization and Vitamin A uptake

Feeding practices

  - Intake of iron supplements

  - Diverse diet for pregnant or lactating women

  - Early initiation of breastfeeding

  - Exclusive breastfeeding

  - Initiation of complementary feeding at 6 months

  - Diverse diet for complementary feeding

  - Frequent feeding of complementary feeding

  - Household hygiene

  - Inclusion of Iron rich foods

  - Use of micronutrient powders and use of fortified foods

Positive parenting (in Kilifi County only)

  - Positive parenting

Financial literacy

  - Financial literacy

The program implementation objectives will be to:

- Establish a functional NICHE coordination system in place at national and county levels

- Strengthen the NICHE registration system embedded in the National Safety Net Programme

- Strengthen community Health Strategy in the five NICHE counties strengthened to deliver high impact nutrition interventions and child protection-related Interventions for cash transfer beneficiaries

- Ensure that households receiving cash transfers provided with nutrition counselling to improve the nutritional status of pregnant and lactating women and children under two years of age

- Ensure that households receiving cash transfers are provided with skills to enable foster care of children without parental/appropriate care as well as general parenting skills to improve protection of children

- Establish a functional NICHE monitoring and quality assurance systems in place at national and county levels.

2.3 Target Beneficiaries and geographical locations

The NICHE program has a target to reach 41,583 households in a total of three years in all the five counties where it will be implemented, Kitui, West Pokot, Turkana, Marsabit and Kilifi. NICHE beneficiaries will be NSNP households with a pregnant or a child under 24 months.

2.4 Program timeline and budget

NICHE II is expected to cover 23, 000 beneficiary households (i.e. basing on the criteria of households which will be selected among those under the NSNP cash transfer) in the three years at a budget of USD 12,900,000.

The program started on 21st November 2019. The first four months of the program (November 2019 to March 2020) served as the inception phase for NICHE, with significant strides made in program planning, design, and coordination. The main activities in the preparatory phase were to:

- conduct consultative and validation workshops at national and county level for development of the NICHE Operational Manual (OM), implementation plan, and workplans

- develop the initial drafts of the NICHE OM, implementation plan, and workplans, informed by feedback and priorities of GoK at national and county levels,

- conduct national and county level NICHE sensitization,

- conduct NICHE planning and review meetings, and

- support NICHE coordination, implementation, and quality assurance at county level.

Based on the above activities, county and national Year One workplans and costed county budgets, as well as governance structures and OM priorities were realized through consultative processes with national and county stakeholders. Overall, NICHE is leveraging upon the existing social protection, child protection, and community health platforms and operational processes, with program elements contextualized by county.

An evaluation is being planned to be undertaken before the end of the inception phase. This ToRs is to be read in combination with the envisioned summative evaluation objectives for NICHE II as well as The Draft Theory of Change and Results Framework for NICHE II.

3.0 Objectives, Purpose & Expected Results

3.1 Purpose

The purpose of the formative evaluation is to conduct an evidence-based, highly consultative and participative analytical reflection on the NICHE II program. Formative evaluations, conducted during program development or at early stages of implementation, aim at improving the design with a view to improve performance. This includes looking at what has been learned so far during NICHE I and the inception phase for NICHE II, as well as structuring and framing the building blocks of the NICHE II program so that it may be systematically monitored and evaluated.

The evidence to be derived from the formative evaluation will also inform the GoK (specifically the National Social Protection Unit, under Ministry of Labor and Social Protection) and its collaborating partners on their deliberations on the future of KSEIP beyond its lifespan. It is in line with UNICEF KCO, specifically nutrition, social policy, and child protection sections and management as outlined in the UNICEF Kenya 2018-2022 Country Program Document on improving programming through multi-sectoral program integration. Currently program integration is a prioritized implementation approach for Kenya Country Office. Furthermore, improved maternal and infant dietary practices and ultimately reduction of stunting is one of the key outcomes in UNICEF’s global nutrition strategy. Thus, it is also expected that the evidence will contribute to guiding UNICEF’s overall operationalization of its global nutrition strategy.

3.2 Objectives of the Evaluation

- To identify and document key lessons learned, good practices and innovations from the NICHE pilot as well as the completed  NICHE II Inception Phase, with a particular eye to gender, equity and child rights, that can inform and support NICHE II implementation

- To refine NICHE II program design and Theory of Change

- To improve monitoring and evaluation processes and systems for the implementation of the NICHE II program and its future evaluability

- Establish a baseline against which NICHE II’s impact can be summatively evaluated

3.3 The components of the evaluation

The evaluation will have four components: the review of the proposed NICHE II program, informed by key lessons learned from the NICHE I pilot and the NICHE II inception phase; the refinement of the programme design and theory of change (TOC); the development of an M&E framework for NICHE II; and a baseline study for NICHE II’s M&E framework. The review, design refinement and the M&E Framework are the core components of the formative evaluation.

Component 1 – Review of the proposed NICHE II program

The review will assess the relevance, coherence and sustainability criteria and the analysis will be structured around the key evaluation questions. It will also look at what worked and what did not work under NICHE I, what has been learned so far during NICHE II’s inception phase, and identify potential enabling and hindering factors to the achievement of NICHE II’s anticipated outcomes. An evaluation matrix that provides the analytical framework of this review against the evaluation criteria and key evaluation questions will be developed by the evaluator during the evaluation’s inception phase. The results of the review will be a main input to refining the program design and theory of change (component 2), which will in turn shape the M&E Framework of the NICHE II program (component 3).

Component 2 – Refinement of the program design and TOC

This component will provide a set of forward-looking and actionable recommendations to strengthen programmatic strategies in the design of the NICHE II Program, taking into consideration the results for the review (component 1) and an assessment of the program’s theory of change. The draft Theory of Change for NICHE is included in Annex 3 of the TOR.

Based upon the agreed adjustments to the program design, the evaluators will work with program stakeholders to further refine the theory of change, placing a particular emphasis on making assumptions explicit and its results measurable. The revised theory of change shall encompass both the diagrammatic model as well as the narrative description, featuring assumptions (internal and external) and drivers.

Component 3 – Development of the M&E Framework

This component, the development of an M&E Framework of the NICHE II program, is at the core of the formative evaluation. The elements of the evaluative framework will be the theory of change (component 2), a results framework (see draft results framework in Annex 4 of the TOR) and a monitoring and evaluation plan for the entirety of the NICHE II program. Developing the M&E Framework will also involve an analysis of what is considered desirable and feasible by NICHE II stakeholders in light of the evidence gathered through the formative evaluation’s review (component 1).

Component 4 – The Baseline Study

Conducting a baseline study based on the developed M&E Framework for the NICHE II program, one of the two main outputs of the formative evaluation, will enable the program’s impact to be appropriately evaluated (i.e. the current baseline assessment will inform an impact evaluation at the end of the program). Additionally, collect baseline cost-effective analyses markers that will later facilitate a cost-effective study at the end of the program. The baseline study is the first step in the implementation of the M&E Framework, as it provides relevant data on target indicators at the onset of the intervention which allows for measuring change. The design of the baseline study will be undertaken as part of the M&E Framework (component 3), so that its conduct is with the view of providing a basis from which the program’s impact will be appropriately evaluated at the end of the program.

3.4 Scope of the evaluation

The scope of this formative evaluation will be the NICHE II program. Hence the ToRs encompasses program design and implementation of the NICHE program, Geographically the evaluation will be confined to the five counties (West Pokot, Kitui, Kilifi, Marsabit and Turkana) where NICHE will be implemented as well as the National GoK as well as UNICEF KCO. The programmatic scope of the evaluation will be aligned with the program implementation design, e.g. all the program components (Social Protection, Nutrition and Child Protection in Kilifi).

While the principal focus of this formative evaluation will be on the second phase of the program, NICHE II, from November 2019 till the present period, it will also look at what worked and what did not work under NICHE I insofar as it illuminates issues in the current program.  For example, the extent to which NICHE II has been informed by key lessons learned from the NICHE I pilot.

The evaluation will engage all key stakeholders of NICHE II (Ministries of Labor, Social Protection, Ministry of Devolution and ASAL, Council of Governors, and the Ministry of Health and UNICEF).

4.0 Description of the Assignment

Human rights and Gender equality Perspective

The ToR for the evaluation will be guided by the right to social security, which is articulated in Article 22 of the Universal Declaration of Human Rights and in Article 9 of the International Covenant on Economic, Social and Cultural Rights (ICESCR). Additionally, the convention of rights of a child will guide the ToR in its purpose and execution. Methodological approaches which are non-discriminatory towards women in the study setting will be utilized, as well aggregation of data by gender in the analysis.

5.0 Key Evaluation Questions

The evaluation (i.e. formative evaluation) part of this exercise will specifically address the following UNEG criteria for evaluations – relevance, coherence and sustainability, as outlined in the questions below. The criteria on effectiveness and efficiency will not be addressed as they are not relevant at this stage of the evaluation.:

| Criteria | Evaluation Question |
| --- | --- |
| Relevance | - How is the NICHE II Theory of Change and Results Framework aligned to the nutrition, social and child protection situation in Kenya? And to what extent does it integrate gender equality and human rights? - Have the lessons learned from NICHE I pilot been reflected in NICHE II’s design? - Has the social- and child-protection and nutrition challenges and landscape in counties as well as national level been sufficiently taken into account to justify the implementation approach and strategic priorities of NICHE II? - How well is the NICHE II aligned to nutrition, social policy and child protection priorities of: MLSP and MoH, UNICEF global and regional offices, and key donors? - To what extent is the NICHE II implementation approach supportive of gender transformation at beneficiary household level and takes into account, different roles and responsibilities, needs of each gender and supporting to overcome gender biases? - In what ways can the NICHE II interventions embrace a rights-based approach at different program stages (design, implementation, impact measurement)? - How is the NICHE program aligned to key sources of normative guidance such as Core Commitments for Children (CCCs) in development and humanitarian situations? - To what extent has the allocation and use of NICHE II resources for targeted groups taken into account the need to prioritize women and individuals/groups who are marginalized and/or discriminated against? |
| Coherence | - What are existing interventions in the area of nutrition, social and child protection in the NICHE counties and how can NICHE II’s implementation approach leverage on these to maximize resources ? - How could the NICHE II’s implementation approach be designed in such a way that it strengthens existing GoK programs in the area of food security, resilience, and cash transfer, child protection and nutrition systems strengthening? |
| Sustainability | - Does the NICHE II have strategies in place to ensure that social- and child-protection and nutrition capacities will be developed at both national and county levels in the three years of the NICHE implementation and sustained without UNICEF’s TA’s support? - To what extent does the implementation approach of NICHE II foster GoK’s self-reliance in the context of devolution? - To what extent will NICHE II support national processes such as strategic plans, policy development, development of guidelines as proxies of supporting sustainable efforts? |

6.0 Methodology

The evaluation methodology will adhere to the United Nations Evaluation Group (UNEG) Norms & Standards. The detailed evaluation design will be developed by the external evaluators to be contracted to conduct the evaluation during the inception phase, in close consultation with the UNICEF Kenya Country Office evaluation manager and programme section, and key evaluation stakeholders. The design should specify how data collection and analysis methods integrate gender considerations throughout the evaluation process, including to the extent possible, inclusion of girls and boys, women and men, as well as a range of programme stakeholders.

6.1 Inception phase

The evaluation process will start with an inception phase which will involve review of program documents and relevant literature. As part of the inception phase, the evaluation team will conduct an assessment to ascertain the available information, assess the reliability of disaggregated data, identify data constraints, and determine the data collection needs and methods. An inception report will be produced which will set out the scope, design and the method including the data sources and tool to be used. A detailed methodology including an evaluation matrix, data analysis plan, data collection instruments, and field work plans will be finalized.

The design of the evaluation will reflect program implementation format whereby the Child Protection component of the evaluation will only be assessed in Kilifi county while Social Protection and Nutrition program component will be assessed in all five targeted counties (Kilifi, Turkana, West Pokot, Marsabit, Kitui).

6.2 Overall methodology approach

The evaluation will utilize a mixed method design that is utilization-focused integrating both quantitative and qualitative data collection tools to complement each other. The mixed methods will utilize both secondary data and primary data sources like key informant interviews. Data collection and analysis methods should integrate gender considerations throughout the evaluation process, including to the extent possible, inclusion of girls and boys, women and men, as well as a range of program stakeholders. Evaluation data should be disaggregated by sex, ethnicity, age, disability, etc.

6.3 Data sources

Existing data sources which could be used in the formative evaluation include the Kenya Demographic Health Surveys, KAP Survey, and SMART Surveys, GoK and/or UNICEF program documents. NICHE I evaluation report will also be included in the data sources.

Based on the draft NICHE II Theory of Change for (Annex3), the Logical Framework (Annex 4), and other existing data sources, an evaluability assessment would be undertaken to clarify logic and coherence of the NICHE II. The evaluability assessment should also assess reliability of disaggregated data.

6.4 Analysis Strategies

The analysis strategy will be developed in detail based on the detailed methodology to be developed during the inception phase. In addition, the evaluation should review the coherence of the NICHE II to existing policies and strategies. Findings should be triangulated through qualitative data collection, including key informant interviews with UNICEF, GoK, key donors, private sector partners, other UN agencies (WFP, FAO, WHO, etc), and implementing partners. It is also proposed that the evaluation findings are informed by other UNICEF’s on-going evaluations and reviews within the sectors relevant to NICHE II.

The proposed methodology approach should consider ethics human rights-based approaches, child- based rights and will be gender sensitive. These considerations will be made in all steps of the evaluation, from design, data collection as well as data analysis conforming to the UNEG norms and standards and ethical guidance.

A note on the baseline study

The outline of the methodological and analytical framework for the baseline study (component

4) will be determined by the indicators and evaluation plan in the M&E Framework developed in component 3. Some preliminary methodological considerations on aspects of the study include the use of surveys, qualitative investigations, and comparison groups, but the complete details of the baseline study will not be developed until the work on the M&E Framework (component 3) begins. The methodology for the baseline assessment is also expected to incorporate collecting baseline markers for a follow-up cost-effective analyses of the program.

6.5 Limitations

The present Covid-10 pandemic situation poses a challenge for data collection and consultations utilizing traditional methods. As such, innovative means/approaches will need to be developed by the consulting firm in terms of data collection methods and tools including (but not limited to) use of remote and online technologies; so that the evaluation exercise can still be completed on time. There could be a risk that at the time of the baseline some beneficiaries will already have been sensitized about the upcoming NICHE intervention activities posing a risk for bias.

7.0 Ethical considerations

At the core of the ethical principles to be followed during the evaluation is to ensure doing no harm to children, parents or other participants in the evaluation. The evaluation team will be expected to apply for seek ethical clearance. Additionally, the following general ethical considerations should apply in the methodology:

- Participation in the interview should be voluntary and based on informed consent. Prior to conducting any interviews/discussion written and/or oral consent must be obtained from all respondents, after the purpose of the study has first been explained to respondents in a language of their understanding.

- In the case of child participants, consent is to be sought from either the parents or guardians prior to selecting for any interviews – where such consent is not deemed to be contrary to the best interests of the child.

- Participants/respondents will be informed of their right not to answer any questions they are not comfortable with and to terminate the interview at any time they deem fit.

- Confidentiality and anonymity regarding the data collected from the participants must be ensured through the following means: safeguards to ensure confidentiality during data processing and reporting which means not making or implying precise references to study participants or statements made by any participants.

8.0 Deliverables, timelines and payment schedule

8.1 Key Tasks, Expected Deliverables, and Timeline

The evaluation is anticipated to begin in August 2020 with the inception phase and take 16 weeks over a span of 5 months to complete. The key tasks for the consulting firm will be as described in the table below:

| Outputs/ Deliverables | Estimated number of days | Estimated Due Date | Payment Schedule |
| --- | --- | --- | --- |
| Approved inception report including the following | 15 days | 15th August 2020 | 10 % of payment |
| - Literature review of all relevant program documents, reports and consultations notes from inception workshop (virtual) |  |  |  |
| - Detailed evidence-based and validated/approved methodology for all the components of the evaluation exercise - a) Review of the proposed NICHE II program; b) Refinement of the program designing and ToC; c) Development of the M&E Framework; and d) Baseline study |  |  |  |
| - Developed relevant data collection tools including questionnaire and interview guides |  |  |  |
| - Approved research protocols cleared from ethical board if applicable (including data collection tools) |  |  |  |
| - Modified and finalized workplan |  |  |  |
| Approved formative evaluation report including | 30 days | 30th August 2020 | 30 % of payment |
| - Executive summary which can inform decision making and includes all necessary elements (background, purpose, objectives, methodology, key findings, key conclusion, key recommendations) |  |  |  |
| - Main report based on UNICEF Evaluation Report standards and the GEROS Quality Assessment System; comprising 40 – 60 pages |  |  |  |
| - Draft reports preceding the main report and notes of the feedback received in the validation process of the draft report into main report |  |  |  |
| M&E Framework | 7 days | 30th August 2020 | 10% of payment |
| - M&E Framework that includes - Theory of Change - Logical/Results Framework and - Monitoring and evaluation plans |  |  |  |
| - Feedback reports from consultations with UNICEF KCO Program staff from Nutrition, Social Policy and Child Protection sections as well as GOK staff from National Social Protection Unit, Ministry of Health and County teams (for the 5 counties). |  |  |  |
| Final Approved Baseline Assessment Report | 60 days | 31st October 2020 | 40% of payment |
| - All data collected – raw and cleaned data and documentation submitted to UNICEF |  |  |  |
| - Draft baseline report including feedback notes from validation process |  |  |  |
| - Final approved baseline report within 40 – 50 pages |  |  |  |
| Dissemination plan of both formative evaluation and baseline assessment reports | 40 days | 31st November 2020 | 10% of payment |
| - Manuscript for publications of the key findings of the evaluation; basing on UNICEF’s guidance (based on UNICEF’s leadership and guidance as: https://www.unicef-irc.org/files/upload/documents/UNICEF-External-Publishing.pdf and as well as policy briefs |  |  |  |
| - Policy briefs summarizing key findings |  |  |  |
| - Presentation and graphics of the reports |  |  |  |

Project Management

The Chief of PME Section of UNICEF Kenya will manage the evaluation. The chief of PME will provide guidance as and when required for technical issues related to the evaluation through the KCO Research, Evaluation and Monitoring Group. Additionally, all the three sections involved will contribute towards the technical oversight of the evaluation through the UNICEF KCO internal NICHE technical working group. Furthermore, an Evaluation Reference Group will be formed comprising of members from UNICEF KCO, relevant GoK ministries and representatives of implementing partners. While the ERG’s responsibilities will be described in the ERG terms of reference, it has an advisory capacity whose primary role is to review evaluation milestones (terms of reference, inception report, draft evaluation report, M&E framework, draft baseline report) and to provide comments. The ERG Secretariat will maintain a written record, as part of an audit trail, of all ERG comments, which the evaluation team is expected to respond to in writing (agree – actions taken; disagree – justification). The group will include experts from UNICEF Regional Office.

8.1 Stages of the Quality Assurance for the Evaluation Process

The following stages of quality assurance  in the evaluation process are envisioned. which will be undertaken through Review seminars/meeting with the Evaluation Reference Group:

- Review Formative evaluation inception plan– An outline of the expected methodology, timelines and road map of all the components of the evaluation developed by the consultant will be reviewed by the reference group.

- Review finalized methodology and tools prior to data collection:  The finalized data collection tools and methodology will be reviewed by the reference group prior to data collection

- Review of the ormative evaluation report review– This will include the review and validatation of the formative evaluation report http://www.uneval.org/search/index.jsp?q=ETHICAL+GUIDELINES

- Review of the Monitoring and Evaluation framework – This will include Review of the drafted Theory of Change and Results Framework

- Baseline assessment report review – Review of the baseline report

- Dissemination plan – Review the dissemination for the evaluation and baseline reports

8.2 Advocacy and Dissemination

The results of the Evaluation will be disseminated for advocacy purposes to senior county management teams, the national level government for MLSP, MoH, CoG, MD&ASAL. This will be done through both policy briefs as well as seminars specifically for this purpose (KSEIP Steering Committee, CSG, Child Protection, Social Protection and Nutrition technical coordination for/at national and county level, etc.). In addition, results will also be disseminated back to communities through existing platforms e.g. chief baraazas etc.

Evaluation process and methods

The evaluation procedure will focus on both technical and financial suitability. The weights of 70% and 30% shall be applied for technical and financial compliance respectively.

Only firms scoring at least 70% of the maximum score during technical evaluation will be considered for financial evaluation.

TECHNICAL EVALUATION (70%)

The details of the evaluation weighting are provided below:

| ITEM | TECHNICAL EVALUATION CRITERIA | MAX OBTAINABLE POINTS |
| --- | --- | --- |
| 1 1.1 1.2 | Overall Response Relevant evaluation capabilities and quality of evaluation outputs Overall Response e.g. the understanding of the assignment by the proposer and the alignment of the proposal submitted with the ToR -Evidence of in-depth knowledge of the key issues and concepts underpinning this evaluation (integrated social protection, child protection and nutrition programme) and demonstrated thorough understanding of the ToR and deliverables, with explanation of a fully tailored and innovative approach for this evaluation Completeness of response Overall concord between TOR/needs and proposal -Credible overall approach to the evaluation and its four components, detailing use of quantitative and qualitative methods | 5 |
| 2 2.1 2.2 2.3 2.4 2.5 | Company and Key Personnel Team composition and networks to deliver results Range and depth of organizational experience with similar projects -Skills and capacity of the lead consultant and key implementing staff members to deliver an effective evaluation programme including expertise of evaluation methodologies and evaluation synthesis Team leader: over 10 years’ experience in programmatic evaluations • Strong leadership and coordination skills • Strong report writing skills • Relevant academic qualification (MSc to Ph.D.) Other team members: Experience and skills mix or nutrition programming and programmatic evaluations - over 8 years’ experience in programmatic evaluation - over 8 years’ nutrition programming in developing countries - a minimum of relevant first degree relevant experience in report writing -Experience in Theory of Change and M&E Framework development - Expertise in conducting quantitative analysis as well as qualitative synthesis and baseline, impact evaluations Client references -Institutional expertise, knowledge and experience in programmatic evaluations in social protection, nutrition and child protection | 50 |
| 3 | Proposed Methodology and Approach Suitable methodology for responding to the programmerequirements Project management, monitoring and quality assurance processes including use of innovative approaches and compatibility with UNICEF -Quality of proposed implementation plan, i.e how the bidder will undertake each task -Quality of the proposed approach and methodology -Evidence of use of integrated and multidisciplinary evaluation approaches and methods including details of qualititative and quantitative methods eg data collection approaches (eg sampling), data analysis plan. -Risk assessment - recognition of the risks/peripheral problems and methods to prevent and manage risks/peripheral problems during the course of the evaluation/research. -Work plan showing, project implementation plan in line with the project | 15 |
| TOTAL TECHNICAL SCORE |  | 70 |
| TOTAL FINANCIAL SCORE |  | 30 |
| SUMMARY OF TECHNICAL & FINANCIAL SCORE |  | 100 |
| Minimum points required in technical evaluation to qualify financial evaluation |  | 49 (70%) |

Content of technical proposal

In order to ensure a relevant evaluation of proposals, technical proposals from institutions are expected to include, at a minimum:

- Introductory note

- Company profile and legal status. Submission of financial information (such as recent set of audited financial statements) would be welcome

- List of similar projects delivered, including detailed description of achievements/outcomes

- Client references

- Proposed timeline/workplan

- Proposed work approach in the context of COVID-19 demonstrating the possibility to undertake most stages of the evaluation within the current limitations of COVID-19

- Proposed methodology for all the four components of the assignment. The proposal for the baseline assessment should include baseline markers for the cost-effective analysis. Proposals which will include the methodology approach for the anticipated End line Impact evaluation & cost-effective analyses will have an added advantage given the demonstration of how the methodology being proposed for the Baseline will facilitate and accommodate an impact evaluation at the end. The envisioned impact evaluation details at the end of the program are provide as an annex.

- Proposed budget – i.e. a budget for undertaking the formative evaluation including the baseline assessment

- Team of consultants proposed to carry out the assignment, including their CVs with qualifications and expertise in similar projects relating to social protection, nutrition and child protection.

- Proposals should also include how gender equality, children and human rights will be considered in the evaluation

- The consultants will require to clearly identify any potential ethical issues and approaches, as well as identify the processes for seeking ethical review and oversight of the evaluation process in their proposal

- The consultants require to clearly identify any potential conflicts of interest related to the proposal

Evaluation team: - key skills and competences

The consulting firm will preferably be based at either a university, or a research organization, or an evaluation firm; and should adequately demonstrate the availability of high caliber expert/s in the evaluation of large-scale social protection, nutrition and child health and child protection programs in developing countries. The consultant team should have skills (knowledge) in social cash transfers, nutrition, child protection and research.

Key skills required of the lead consultant include:

- Masters (required) or Advanced Degree (Ph.D. desirable) in either social science, public health nutrition, nutrition epidemiology, monitoring and evaluation, statistics, public health or demography, economics, sociology.

- At least 10 years of progressively responsible professional work experience at national and international levels in conceptualizing, designing and implementing evaluations and/or research of large-scale social protection, child health nutrition-related and child protection programs in developing countries, including experience with both quantitative and qualitative research methods

- Relevant experience in Theory of Change and Monitoring and Evaluation Frameworks development

- Relevant experience in social protection, nutrition and child protection programming

- Strong or proven (at least 5 to 8 years) experience with social protection, child health nutrition and child protection programs in low and middle-income countries

- Proven publication record, preferably in peer reviewed journals

- Demonstrated ability to produce high quality evaluation and/or analytical research reports

- Familiarity with UNICEF’s work on social protection and cash plus

- Familiarity with Kenyan context

- Excellent spoken and written fluency in English

- Proficiency in various MS Office applications (Excel, Word and PowerPoint) and statistical package such as STATA, R, SPSS or SAS.

- Knowledge and experience in working with gender issues child and human rights based approaches is critical

Key skills of the research team members:

- Post-graduate qualification or current registration for post-graduate study in social policies, public health, nutrition, child protection, monitoring and evaluation, epidemiology, statistics, or demography, Strongly Desired

- Familiarity with UNICEF’s work and/or Kenya

- Excellent spoken and written fluency in English

- Proficiency in various MS Office applications (Excel, Word and PowerPoint) and with statistical package such as, STATA, R, SPSS or SAS.

All applicants both domestic (to Kenya) and international, matching the eligibility criteria are welcome; Teams are encouraged to gender balanced and culturally diverse while making use of national capacity.

FINANCIAL EVALUATION (30%)

Only those financial proposals for bidders which have been technically accepted according to the above criteria will be opened. The Financial proposal will be weighted based on the clarity and appropriateness.

The price should be broken down for each component of the proposed work. The total amount of points allocated for the price component is 30. The maximum number of points will be allotted to the lowest price proposal that is opened and compared among those invited firms/institutions which obtain the threshold points in the evaluation of the technical component. All other price proposals will receive points in inverse proportion to the lowest price; e.g.:

Max. Score for price proposal * Price of lowest priced proposal

Score for price proposal X =         ---------------------------------------------------------------------------

Price of proposal X

The Contract shall be awarded to a bidder obtaining the highest combined technical and financial scores. Proposals not complying with the terms and conditions contained in this ToR, including the provision of all required information, may result in the Proposal being deemed non-responsive and therefore not considered further.

Conditions

- As per UNICEF policy, payment is made against approved deliverables. No advance payment is allowed unless in exceptional circumstances against bank guarantee, subject to a maximum of 30 per cent of the total contract value in cases where advance purchases, for example for supplies or travel, may be necessary.

- The institution selected will be governed by and subject to UNICEF’s General Terms and Conditions for individual contracts.

- Performance will be evaluated considering quality of deliverables, consultation with stakeholders, timeliness of deliverables of and comprehensiveness of work as defined in the terms of reference.

- The institution may not publish or disseminate Reports, data collection tools, collected data or any other documents produced from this consultancy without the express permission of and acknowledgement of UNICEF.

- The consultants will be required to clearly identify any potential ethical issues and approaches, as well as the processes for ethical review and oversight of the evaluation process in their proposal

Administrative issues

- Whenever possible, the bidder is requested to provide an all-inclusive cost in the financial proposal.  Bidder should factor in all cost implications for the required service/assignment

- If travel becomes feasible during  the course of the assignment: i) travel cost shall be calculated based on economy class travel, regardless of the length of travel and ii) costs for accommodation, meals and incidentals shall not exceed applicable daily subsistence allowance (DSA) rates, as promulgated by the International Civil Service Commission (ICSC)

- Unexpected travels shall also be treated as above.

ANNEXES

Annex 1: Program Concept – Additional Information

1.1 Nutrition situation

Kenya like the rest of the sub-Saharan African region experiences pandemic rates of both acute and chronic malnutrition. Stunting, wasting and being underweight were estimated at 26%, 4% and 11% among children under five years of age in 2014. The blunt of the burden of malnutrition is borne by the arid and semi-arid lands (ASAL). The ASAL accounts for 86% of the cases of children with acute malnutrition1. Levels of stunting are equally disproportionately high in the ASAL region, being as high as 54% in some of the ASAL counties1. Given that malnutrition is the major risk factor for early childhood deaths, accounting for nearly half of all childhood deaths; addressing malnutrition and its underlying causes in the ASAL is an urgent need.  The harsh climate which characterizes the ASAL limits the window of opportunity of intervening through mainstream agri-based food security approaches. Interventions which purport to increase household’s food purchasing power are thus deemed as more fitting; additional to high impact nutritional interventions like promotion of breastfeeding and child protection.

1.2 Child Protection Situation

There’s a growing realization on the benefits of positive parenting (additional to avoidance of neglect and abuse) on the overall physical growth and cognitive development of the child. In this regard, the most critical period, is from pregnancy to age 3, where the brain grows faster than at any other age.  To optimize this peak of brain development, children require a safe, secure and loving environment, additional to the right nutrition and stimulation from their parents or caregivers. This is a window of opportunity to lay a foundation of health and wellbeing whose benefits last a lifetime – and carry into the next generation. For every $1 spent on early childhood development interventions, the return on investment can be as high as $13. Early childhood development is also key to upholding the right of every child to survive and thrive.

Little is known about the magnitude of sub-optimal parenting skills in the Kenyan context, even though it is appreciated from proxy indicators that this is a significant social welfare and public health problem. Nevertheless, it is estimated that 79 per cent of boys and 76 per cent of girls experience physical, sexual and/or emotional violence before the age of 18 in Kenya. More specifically 73 per cent of boys and 66 per cent of girls experience physical violence before the age while 32 per cent of girls and 18 per cent of boys had experienced sexual violence, as reported in VACS 2010.  Approximately 3.6 million Kenyan children are orphans or otherwise classified as vulnerable. There are programs for keeping these children in extended families or foster families, such as cash transfer for orphan and vulnerable children.

1.3 Program Implementation

The cash top up under NICHE will be provided by the State Department of Children Services through their regular NSNP and HSNP cash transfer programs. NICHE eligible beneficiaries (households who are under the ordinary cash transfer programs but have either a child under two, a pregnant or lactating woman) will further be provided with intensive nutrition counseling at community and household level and in one county (Kilifi) they will additionally be provided with child protection education.

1.4 The Baby Friendly Community Initiative

The nutrition counselling in NICHE will be delivered through operationalizing the Baby-friendly Community Initiative (BFCI). The BFCI is a global initiative which packages standardized-evidenced based complementary community-based interventions aimed at improving infant and young child feeding practices as well as mothers’ dietary adequacy. In Kenya, the BFCI is adopted by the Ministry of Health as the approach for delivery of community-based nutrition services to secure optimal nutrition for young children and mothers. However, the BFCI platform has not been rolled out to scale in most counties. As part of the NICHE interventions, BFCI will be scaled up in the counties where NICHE will be implemented.

When the BFCI package is implemented to scale it entails: i) awareness raising to key decision and policy makers on optimal feeding and hygiene practices for children and mothers ii) training of health workers and community volunteers on promotion of optimal hygiene, health seeking, and feeding practices for young children as well as pregnant and lactating women iii) mentorship of community volunteers in providing community based counselling iv) formulation and support of community-based structures (mother-to-mother support groups, community groups) for peer support on optimal practices as well as community engagement in the provision of nutrition services v) establishment and support of feedback mechanisms and platforms where the community provides feedback on delivery of nutrition services within the health facilities. Thus, in the NICHE counties, BFCI is envisioned to improve nutritional and hygiene related behaviors of caregivers, create community platforms where the community engages and empowers itself to promote optimal nutritional practices. It is important to note for the planning of the NICHE evaluation, that while as the home-based nutrition counselling that will be offered will be limited to NICHE beneficiary households, the nutrition promotion through the community structures to be established will serve the communities at large.  In summary the key behaviors to promoted through the BFCI platform will include the following:

1.5 Child Protection Education

In regard to child protection, beneficiary households and communities will be provided with parenting education with child protection awareness sessions focusing on understanding child development, improving communication and interactions between caregivers and children and most importantly avoiding harsh and violent disciplines. Parenting education will also aim to involve fathers and male caregivers to address violence at home including intimate partner violence (IPV) and gender-based violence (GBV) at home which has a significant impact on child wellbeing. It will also promote male engagement in child-rearing and encourage gender equity in parenting daughters and sons. Parenting education and community awareness sessions will also highlight the importance of family-based care for children through prevention of family separation as well as promotion of family based alternative care for children separated from their parents (such as kinship care, foster care, guardianship and adoption).

1.6 Program Objectives & Expected Results

NICHE implementation is expected to achieve results on the following objectives:

1-Community health in the five NICHE counties strengthened to deliver High Impact Nutrition Interventions for beneficiaries in the five counties

2-Households of beneficiaries are provided with nutrition counselling to improve the nutritional status to improve the nutrition status of pregnant and lactating women and children under two years in the five counties

3- Households of beneficiaries are provided with skills for foster care of children without parental care and parenting skills in Kilifi counties

4-Secure a functional coordination system (multi-sectoral) at county and national level

5-Registration of beneficiaries in NICHE strengthened and embedded in the national safety net program

6-Functional NICHE monitoring and quality assurance system in place at national and county level

Annex 3: NICHE Theory of Change

Annex 4: Logical Framework

Annex 4 Cont/..Logical Framework

For further information, please contact: Nutrition Section, UNICEF Kenya

United Nations Children’s Fund

UN Complex Gigiri, Block Q Upper Level

P. O. Box 44145 – 00100 Nairobi

© United Nations Children’s Fund (UNICEF) May 2021

For further information, please contact: Nutrition Section, UNICEF Kenya

United Nations Children’s Fund

UN Complex Gigiri, Block Q Upper Level

P. O. Box 44145 – 00100 Nairobi

© United Nations Children’s Fund (UNICEF) May 2021

https://www.unicef.org/about/execboard/files/2018-PL4-Kenya-CPD-ODS-EN.pdf

It contributes in particular to the evaluation of Output 1.1 in the Country Program Document, which aims to ‘In 10 or more disadvantaged counties, communities increasingly have improved service-seeking behaviour and adopt desirable practices on sanitation and water use, young child feeding and parenting, maternity and prevention of child disease and HIV/AIDS’. The NICHE II implementation and evaluation covers 5 of the most disadvantaged counties and focuses on young child feeding and parenting.

The numbering of evaluation questions differs from the ToR, we added additional questions during the inception and formative research stage. Questions which were not in the ToR are marked with an asterix.

The Impact evaluation questions are the key Evaluation Questions to measure the impact of the NICHE program. These questions cannot be answered at baseline, but for each of the impact evaluation questions we are collecting the indicators at baseline to ensure they can be answered in the future in any follow-up evaluation rounds.

Numbers behind the data tools are illustrative to the number of the possible questions within the tools in Annex C in Inception Report.

Even though the eligibility qualifies children up to 24 months old, the registration in the five counties included only children up to 15 months to allow for a minimum of 9 months in the program. Since the registration was finalized in April 2021, the children will be older during data collection.

NICHE II is implemented in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties.

NICHE II is implemented in Kitui, West Pokot, Turkana, Marsabit, and Kilifi counties.

2019 UNICEF Global Social Protection; https://www.unicef.org/reports/global-social-protection-programme-framework-2019

2017 UNICEF Global Nutrition Strategy https://www.unicef.org/supply/files/0940_Sustainable_Development_Goals_and_UNICEFs_Nutrition_Strategy.pdf

United Nations Children’s Fund (UNICEF). Improving Young Children’s Diets During the Complementary Feeding Period. UNICEF Programming Guidance. New York: UNICEF, 2020.  (accessible here).

Action Frameworks to improve the diets of young children (6-23 months) in Eastern and Southern Africa Region (accessible here).

Kenya Demographic Health Surveys 2014

Details of the pilot can be obtained from the Evaluation Report of the NICHE Pilot

https://www.unicef.org/about/execboard/files/2018-PL4-Kenya-CPD-ODS-EN.pdf

https://www.un.org/en/universal-declaration-human-rights/

https://www.ohchr.org/en/professionalinterest/pages/cescr.aspx

https://www.ohchr.org/en/professionalinterest/pages/crc.aspx

http://www.unevaluation.org/document/detail/1914

Ethical considerations have been further outlined in section 6.0 of the ToR

Outline of Main report: Including but not limited to the following sections/ segments:

- A title page with key basic information and a Table of contents, List of acronyms

- Description of the object of the evaluation

- Report Requirements

- Evaluation Purpose, Objectives and Scope

- Evaluation Methodology

- Findings

- Conclusion and Lessons learned

- Recommendations (based on the evidence generated and conclusions, and developed in consultation with relevant stakeholders)

- Gender and Human Rights including Child Rights (illustrating the extent to which the implementation of the object, as well as process incorporates a gender equality perspective and human right- based approach, including child rights)

- Annexes: Including but not limited to ToRs; List of persons interviewed; and sites visited; List of documents consulted, More details on methodology, such as data collection instruments, Evaluation matrix - Results framework, Ethical clearance, Evaluators biodata and/or justification of team composition, Results framework, Ethical clearance, Evaluators biodata and/or justification of team composition

Kenya Demographic Health Surveys 2014