Summative Evaluation of the Economic Community of West African States (ECOWAS) Nutrition Fora (2004 – 2019)

Final Report

Consultancy services provided to

The United Nations Children Fund (UNICEF)

West and Central Africa Office (WCARO), Dakar – Senegal

March 18, 2020

Evaluation of the Economic Community of West African States (ECOWAS) Nutrition Fora

The Evaluation Team

Serge Eric Yakeu (CE), Team Leader

Laura Golakeh, National Consultant (Liberia)

# Acknowledgements

The evaluation of the Nutrition Forum of the Economic Community of West African States (ECOWAS) namely “ECOWAS Nutrition Forum” was carried out by Serge Eric Yakeu (Credentialed Evaluator, Team Leader) and Laura Golakeh (National Consultant). The authors of this evaluation report would like to acknowledge and express their thankfulness to all the UNICEF’s staff members involved in the Regional and Country Office in Senegal, Burkina Faso, Cote d’Ivoire, Guinea-Bissau, Liberia and Nigeria. They cooperated with great enthusiasm throughout the process, especially during the fieldwork in the selected countries, allowing us to collect all the information required for this evaluation.

We are also grateful for the support provided by Michele Tarsilla (PhD), Regional Evaluation Advisor and his team for this work. He has played a key role as Manager in this evaluation. We sincerely appreciate his cooperation and all the time spent coordinating and collecting the required documentation/information, providing appropriate references to strengthen the whole evaluation process, arranging an intense and successful fieldwork agenda, assisting with field travel schedules, and finally, coordinating the process of reviewing draft versions and providing feedback on both the Inception and final evaluation reports. The same remarks go to Noel Zagre (PhD), Regional Nutrition Advisor at the WCARO office in Senegal.

We also feel that it is important to mention the impressive cooperation of the heads of both the Nutrition and Evaluation sections of the UNICEF’s Country Office in the visited countries. We appreciate the time they spent on the evaluation process and their generosity in sharing with us the knowledge and experience to get this mission completed.

We express our gratitude to William Kofi Bosu (PhD), Professional Officer Non-Epidemic Diseases and Neglected Tropical Diseases (NTDs), and Keita Namoudou (PhD), Professional Officer, Primary Health Care and Non-Communicable Diseases (NCDs) of the West African Health Organisation (WAHO) based in Bobo Dioulasso (Burkina Faso), for the guidance and multiple support received throughout the start-up, data collection and production of this evaluation report. Their comments, suggestions, and availability for the facilitation of scoping meetings, the provision of the Forum documents and other data sources to the evaluators, were very helpful in the success of this evaluation.

Finally, we would like to thank all of the ECOWAS government officials, institutional partners and Civil Society Organizations (CSO) for their availability to the interviews conducted during the data collection phase. Despite the restrictive appointment schedule, they were available to meet with the Consultants.

Serge Eric Yakeu (CE), Team Leader

Laura Golakeh, National Consultant

The information contained in this report does not necessarily reflect the views and position of UNICEF WCARO. The responsibility for the opinions expressed as well as the errors of fact or judgment remains that of the Consultants.

# Table of Contents

Acknowledgements	iii

Table of Contents	iv

List of tables, figures and annexes	v

List of acronyms	vi

Executive summary	viii

1.	Introduction	1

1.1.	Evaluation context	1

1.2.	Nutritional status of West-Africa	5

1.3.	Evaluation Object	8

2.	Evaluation purpose, objectives and scope	11

2.1.	Purpose and use of the Evaluation	11

2.2.	Objectives and scope of the evaluation	12

3.	Evaluation methodology	13

3.1.	Evaluation criteria	13

3.2.	Evaluation questions	13

3.3.	Approach and principles to the evaluation	14

3.4.	Data collection and sources	15

3.5.	Synthesis of findings, debriefings and reporting	17

3.6.	Human rights, Equity, Ethical and gender consideration	17

3.7.	Limitations	18

4.	Findings and preliminary conclusions	19

4.1.	Relevance	19

4.2.	Effectiveness	25

4.3.	Efficiency	32

4.4.	Sustainability and ownership	35

4.5.	Gender, human rights and equity	38

Final Conclusions	40

Recommendations	42

Lessons learned	44

Annexes	45

# List of tables, figures and annexes

List of Tables and figures

Table 1: List of past editions of the forum with their corresponding themes and Lead Partners	9

Table 2: Evaluation users and uses of the evaluation	11

Table 3: Key Evaluation questions	13

Table 4: Distribution of key informants met by category of stakeholders	17

Table 5: Key priorities of the 2018-2025 ECOWAS Strategic Plan	20

Table 6: Classification of ECOWAS countries by availability of nutrition plan, results monitoring framework and nutrition budget.	25

Table 7: Distribution of Funding and sources for 2015 – 2019 Foras	32

Table 8: Strategic and operational recommendations	42

Figures

Figure 1: Child and adolescent nutrition status in West Africa (aged 5-19)	6

Figure 2: Adult nutrition status in West Africa	6

Annexes

Annex 1: Evaluation Terms of References (ToRs)	45

Annex 2: Evaluation Matrix	57

Annex 3: List of Documents reviewed	60

Annex 4: Data collection tools	62

Annex 5: List of key informants met	67

Annex 6: Synthesis of the Objectives of and Recommendations from the ECOWAS’ Nutrition Fora of 2008 - 2019	69

Annex 7: Field work plan	73

Annex 8: Evaluators’ biodata	74

# List of acronyms

ACF		: Action Against Hunger

ACRWC 	: African Charter on the Rights and Welfare of the Child

AfDB 		: African Development Bank

AMLD		: Alliance for Leadership Migration and Development

ANS		: African Nutrition Society

AUC		: African Union Commission

BI		: Biodiversity International

CAADP 	: Comprehensive Africa Agriculture Programme

CDC 		: Center for Disease Control

CEDAW 	: Convention on the Elimination of All Forms of Discrimination Against Women

CILSS 		: Permanent Interstate Committee on Drought Control in the Sahel

CORAF 	: West and Central African Council for Agricultural Research and Development

CRC 		: Convention on the Rights of the Child

CRS		: Catholic Relief Services

CSO 		: Civil Society Organizations

ECOWAS 	: Economic Community of West African States

ECREEE 	: ECOWAS Regional Centre for Renewable Energy and Energy Efficiency

ECSA-HC 	: Eastern Central and Southern Africa Health Community

ERERA 		: ECOWAS Regional Electricity Regulatory Authority

EU		: European Union

FANUS 	: Federation of African Nutrition Societies

FAO 		: Food and Agriculture Organisation

GIABA 	: Inter-governmental Action Group against Money Laundary and Terrorist Financing in West Africa

GII 		: Gender Inequality Indices

GNR 		: Global Nutrition Report

HKI		: Helen Keller International

IBFN		: International Baby-Food Network

ICCPR 		: International Covenant on Civil and Political Rights

IFPRI 		: International Food Policy Research Institute

IUNS 		: International Union of Nutrition Sciences

MSF		: « Medecins Sans Frontièrs »

NCDs 		: Non-Communicable Diseases

NGO		: Non-Governmental Organisation

NTDs 		: Neglected Tropical Diseases

OECD/DAC 	: Organisation for Economic Co-operation and Development's Development Assistance   Committee

PPDU 		: ECOWAS Infrastructure Projects Preparation and Development Unit

SDGs 		: Sustainable Development Goals

SUN		: Scaling Up Nutrition

ToRs 		: Terms of Reference

UHC 		: Universal Health Coverage

UNEG 		: United Nations Evaluation Guidelines

UNICEF 	: The United Nations Children Fund

USAID 		: United States Agency for International Development

WAMA 	: West African Monetary Agency

WFP 		: World Food Programme

WAHO 	: West African Health Organisation

WCARO 	: West and Central Africa Regional Office

WHO 		: World Health Organisation

# Executive summary

This document represents the evaluation report commissioned by the UNICEF-WCARO on the request of the West African Health Organisation (WAHO). The evaluation was conducted between November 2019 and January 2020.

Evaluation object

The Economic Community of West African States’ (ECOWAS) Nutrition Forum brings together the major stakeholders in nutrition to review nutrition policies and practices, progress in the reduction of malnutrition and diet-related diseases and innovative practices in the region. It also provides ECOWAS Member States and Partners with an opportunity to brainstorm on nutrition challenges, develop a common vision of the nutrition profile of the sub-region, identify financing mechanisms, share experiences, review the implementation level of past Forum recommendations, and provide a technical update to participants on topical malnutrition issues.

The forum was created in 1996 and has been managed biennially by WAHO since 2001. WAHO was created by the Heads of States and Governments of ECOWAS through a Protocol A/P2/7/87 signed in Abuja on 9 July 1987, as a specialized institution in charge of health issues. Its headquarters is located in Bobo-Dioulasso in Burkina Faso.

Purpose, Objectives and scopes of the Evaluation

The evaluation had a double purpose: accountability and learning. Its main objective was to provide evidence on the extent to which the Forum contributed to the nutrition discourse in the ECOWAS region and generate recommendations that will help to adapt the strategy of the Forum to the emerging needs. The specific objectives were the following:

- Assess the relevance, effectiveness, efficiency and sustainability of the ECOWAS fora organized since 2004;

- Assess the extent to which the forum has achieved the expected results, especially in terms of process, planning, stakeholder engagement pre-forum, stakeholder participation, methodology, and final recommendations;

- Draw lessons learned about what has worked and has not worked in respect of the ECOWAS Nutrition Forum including unexpected outcomes (positive and negative);

- Document the Fora costs and sources of funding;

- Identify gaps and make specific actionable recommendations to the expected evaluation users.

All the 15 ECOWAS Member countries form the geographical scope of the evaluation. Language distribution within the region was used to select a sample of five countries for field visits in Liberia, Burkina Faso, Nigeria, Cote d’Ivoire and Guinea-Bissau. The chronological scope covered the ECOWAS nutrition Forum organised between 2004 and 2019. Thematic scope is formed by the Forum’s perspectives. for the adoption of adequate policies and strategies at regional and national levels as well as the quality of nutrition programming and workforce at national and lower levels, the mid-term reviews and its organisation and to roles and responsibilities of different stakeholders.

The expected users of the evaluation are ECOWAS, WAHO, Member States, Technical and financial partners including UNICEF, and in-country partners.

Evaluation Methodology

The evaluation applied the Bellwether methodology which determines where an issue is positioned in the policy agenda framework, how lawmakers and other influential persons such as officials are thinking and talking about it, and how likely they are to act on it. It involved a qualitative approach consisting of both individual and/or group interviews and quantitative approach with the exploitation of existing quantitative data from literature review of the forum’s reports.

The evaluation was carried out in three phases: the inception; data collection; and analysis and reporting phases. In the inception phase, preliminary interviews in Monrovia, review of key documentation and development of data collection and evaluation tools were done. Document review involved the review and analysis of existing documents. The data collection phase, involving field visits in four countries namely Burkina Faso, Cote d’Ivoire, Guinea-Bissau and Nigeria, was carried out from mid-December 2019 to mid-January 2020. Key informants were purposively selected and interviewed using interview guides.  Interviews were conducted through face-to-face interviews, via emails, and mostly via Skype/phone/Whatsapp calls.  Forty-two key informants from Member States (28.5%), WAHO (12%), Partners (45.2%), NGO/CSO (12%), and Parliamentarians (2.3%) were interviewed. In the analysis and reporting phase, the evaluation applied content analysis to data collected from various documents, a standard criteria analysis of Relevance, Effectiveness, Efficiency, Sustainability and Ownership, Gender, Human rights and Equity. Triangulation was used to assure the credibility and validity of findings, and conclusions. The reporting step was preceded by participatory debriefing meetings after field data collection in each country with the reference group to review findings and determine priorities and formulate realistic and useful recommendations.

Main Findings and Conclusions

The evaluation team found that the Forum is relevant in enabling ECOWAS Member States to address the priorities related to evolving needs of the nutrition and health sector in West Africa. The forum objectives are aligned to ECOWAS Regional Nutrition Strategic Plan and National priorities. It provides networking opportunities to stakeholders to share regional and national experiences on nutrition development. Furthermore, the Forum is complementary with other high-level events and platforms such as the Federation of African Nutrition Societies (FANUS), the Scaling Up Nutrition (SUN) Movement of the United Nations, and the Regional Centre of Excellence Against Hunger and Malnutrition (CERFAM). Finally, the forum has been found relevant to address issues related to governance and planning mechanisms, which is helpful to position Member States in the implementation of the Sustainable Development Goals (SDGs).

The forum was very effective in addressing its objectives with emphasis on the advocacy for adequate nutrition policies, action plans and fundraising mechanisms. It therefore offers a regional space to boost the nutrition issues which is almost unique. The evaluation team found that the forum has contributed to number of unintended effects such as positioning of nutrition in the development policies of Member States, the adoption of national legislations and regulations to foster the implementation of nutrition action plans and provided opportunities to ECOWAS countries to work towards regional/global nutrition goals. However, it was less successful in addressing the multisectoral coordination of nutrition interventions in the region.

The evaluation team could not properly assess the forum’s efficiency due to non-consistency of financial information and sources most of which were not available from 2004 - 2013. Financial information of the past three forums (2015 – 2019) reveals that forum’s financial sources come largely from WAHO (55%). In addition, WAHO funds the mid-term reviews entirely. Most of times, partners money is used to support for example per diems (WHO in 2015), or communication and meals (FAO in 2017), and/or facilitation fees and sponsorship of forum delegates (UNICEF in 2019). Other contributors include WFP, USAID, AfDB, World Bank, and African Union Commission. The evaluation found that there are wide disparities in the financial contributions between forums given the fact that some partners fund their participation directly. The coordination mechanism is being managed by WAHO with less synergy with other existing platforms such as the SUN Movement which could enhance the forum’s efficiency given that each of these platforms has a comparative advantage to deal with nutrition challenges in West Africa. In addition, the evaluation team found the forum’s timeline for session’ debates were too short to enable Member States to generate evidence-based follow up on forum’s recommendations.

The forum’s ownership by Member States is good. The forum’s results can be sustained by stakeholders whose capacities have been enhanced through networking opportunities. Member States always show greatest engagement for networking and nutrition knowledge sharing, but their leadership in coordinating nutrition multisectoral approach remains weak with absence of accountability. It was noted that most country priorities are focused on child nutrition and on early child development rather than on adolescent nutrition. Number of countries are affected by contextual factors such as humanitarian crisis in Burkina Faso, Niger and Mali which might have affected negatively their financial participation to WAHO activities.

Gender, human rights and equity principles have been addressed during technical discussions. In fact, nutrition is closely linked with human rights’ defense, particularly those of vulnerable groups such as adolescent boys and girls, vulnerable women such as those with newborns, women of reproductive age, and people with disabilities. The forum’s participation is gendered, with participation of both men and women, and discussions always cover the opinions and needs of the different groups (men, women, boys and girls) and particularly the most vulnerable. Barriers for boys and girls are covered by the forum’s discussions and recommendations.

Recommendations

- Strategic recommendations (SR)

SR1: The forum should advocate for increased leadership, fundraising and accountability of the Member States by:

- Share the dashboards of countries who committed to provide financial contribution to WAHO during the Ministerial Council. This could activate the accountability line of Member States; and influence their willingness to continuously funding WAHO action plans.

- Share Scorecards on results for countries to see where they are relative to others.

- Involve high-level officials (Presidency) to further boost the interest on the nutrition (inviting States to own the forum by planning budget for the participation of their delegates).

- Update Member States on progress made towards implementing forum recommendations with more focus on country-led initiatives to enhance their accountability.

SR2: The Forum should increase advocacy efforts for the review of the nutrition curricula in the region and framework of nutrition indicators in the region by:

- Mainstream health and nutrition package at all level including trainings at school, vocational training centers as well as at the university levels, with the aim of strengthening the capacity of both future generation of nutrition specialists and those vulnerable recipient groups in remote and very remote locations.

- Unify framework of member countries: E.g. Management of nutrition indicators into programmatic information systems (DHIS2) and surveys, opportunity for countries to harmonize needs and adapt national actions.

SR3: WAHO should always push for a Multisectoral coordination of nutrition at each forum by:

- Jointly combine multisectoral sectors such as the WASH, nutrition, health, agriculture, education and social protection sectors in forum’s debates.

- Continuously involve country’s multisectoral platform such as National Council of Nutrition who assure the multisectoral coordination of nutrition at country level

- Work closely with CERFAM to share its achieved research findings on pathways to eradicating malnutrition.

SR4: WAHO should continuously work for a strong collaboration with the Scaling Up Nutrition Movement (SUN)

- This could be benefit for advocacy on country fundraising as the SUN is institutionally attached to High-level political spheres such as Vice-Presidency and/or Presidency level in each of the ECOWAS countries.

- WAHO will therefore improve the image of the SUN given its advanced technical expertise in health and nutrition in the region.

- SUN Movement Focal Point could be the actor who can call the Ministry of health to provide follow up on forum recommendations (SUN discusses with Heads of State, and therefore it is very influential).

- Operational recommendations (OP)

OP1: WAHO should adequate for preparation, review of the forum length and content to achieve more value for money

- More focus should be placed on online meeting to be better prepared ahead before going to forum with the aim of assessing what was not done well, and why.

- Forum’s duration should be reviewed from 2 to 3 years basis to allow more times to Member States and other stakeholders to complete improvement on nutrition priorities and better address the forum’s recommendations

- Need to have technical papers on key subjects such as adolescent health and nutrition and invite people who have data to come and present findings on relevant nutrition related research topics which could be useful to address what is missing.

OP2: WAHO should assure a follow up of forum’s recommendations at country level rather by

- Monitor WAHO’s Focal Point roles and responsibilities in managing the follow up of forum’s recommendations.

Lessons learned

- Having a networking platform such as the ECOWAS Nutrition Forum can positively influence Member States involved in the adoption of nutrition or other sectorial policies, action plans as well as the legislations for their implementation. By gathering Member States during each edition of the Forum, good practices from more advanced countries provide a learning opportunity to less advanced countries to adopt appropriate measures in dealing with nutrition issues.

- By offering equal opportunities to all stakeholders mostly to the Member States to work towards the solutions for nutrition concern, the forum was very helpful to gather common efforts towards measures for fundraising and partnership development within the ECOWAS region. It has an advantage of preventing duplication of nutrition interventions including funding.

- By aligning its objectives to those of ECOWAS Regional Nutrition Strategic Plans and National Priorities, the forum makes a difference and always attract the participation of relevant stakeholders such as technical and financial partners, High-level officials from ECOWAS and Member States.

- As a multisectoral platform, the success of the ECOWAS’ Nutrition Forum requires the participation of diverse individuals and organisations’ profile such as health, nutrition, education, Wash, agriculture and social protection. Participants always belong to most of these basic development sectors. Therefore, participation is inclusive of public and private sectors, NGOs, CSOs, technical and financial partners.

- The nutrition forum bridges Member States on a unique concern which is the fight against malnutrition in West Africa. It therefore calls them to combine efforts by supporting the design and implementation of both national and regional nutrition strategic policies and action plan.

## Introduction

### Evaluation context

#### Governance structure of the ECOWAS

- With his Headquarters (HQ) in Nigeria, the Economic Community of West African States, also known as ECOWAS, is a regional political and economic union of fifteen African countries;. Collectively, these countries comprise an area of 5,114,162 km², with an estimated population of over 349 million in 2015. Life expectancy at birth of 57 years, a total fertility rate of 5 children per woman, an annual rate of population growth of 2.7% and an urbanization rate of 44%. The health situation is fraught with high morbidity and mortality rates, some endemo-epidemic diseases such as meningitis, measles, malaria, emergence and resurgence of other diseases as well as food and nutritional insecurity. The performance of the region’s health system is hindered by many constraints ranging from governance issues, inadequate funding, lack of qualified and motivated staff and the short supply of medical products, to poor cooperation between Member States in the control and containment of cross-border epidemics.

- ECOWAS is made up of institutions and specialised agencies. The institutions comprise: The Authority of Heads of States and Government, The Commission, The Community Parliament, The Community Court of Justice, Council of Ministers, Specialised Technical Committees as well as the ECOWAS Bank for Investment and Development (EBID). Specialised agencies include: i) West African Health Organisation (WAHO); ii) West African Monetary Agency (WAMA); iii) Inter-governmental Action Group against Money Laundary and Terrorist Financing in West Africa (GIABA); iv) ECOWAS Gender and Development Centre; v) ECOWAS Youth and Sports Development Centre; vi) ECOWAS Water Resources Coordination Centre; vii) West African Power Pool; viii) ECOWAS Regional Centre for Renewable Energy and Energy Efficiency (ECREEE); ix) ECOWAS Regional Electricity Regulatory Authority (ERERA); x) ECOWAS Infrastructure Projects Preparation and Development Unit (PPDU) as well as ECOWAS Brown Card Scheme.

- The ECOWAS Commission is the engine room of all ECOWAS programmes, projects and activities. It was transformed from an Executive Secretariat to a Commission in 2007. The Commission is in a better position to support ECOWAS member states to build their capacities for programme implementation, and to oversee the economic integration of the ECOWAS.

- All ECOWAS countries have ratified the main international treaties relevant for the right to food, including the International Covenant on Economic, Social and Cultural Rights (ICESCR); the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW); the Convention on the Rights of the Child (CRC); and the International Covenant on Civil and Political Rights (ICCPR). Cape Verde is the only country that has ratified (as of June 2014) the Optional Protocol to the ICESCR, which means that individuals or groups can lodge a complaint with the Committee on Economic, Social and Cultural Rights alleging a violation of any ESC right, including the right to food.

- Most ECOWAS countries have approved the main regional legal instruments that directly or indirectly refer to the right to food: The African Charter on Human and People’s Rights (1981); the African Charter on the Rights and Welfare of the Child (ACRWC) (1999); and the Protocol to the African Charter on the Rights of Women in Africa (2003). At the West African level, the Charter for Food Crisis Prevention and Management in the Sahel and West Africa (2012) is a comprehensive document that provides a clear set of responsibilities and recommendations across sectors, making some references to the right to food in its considerations, principles and tools. The existence of the ECOWAS also offers opportunities to align regional strategies and policies to tackle these challenges in the region collectively.

- States in West Africa have been some of the most unstable countries in the region. Factors triggering political reforms differ from country to country, but they are also similarities in many aspects. For example, in Ghana, many reforms have taken place mainly with the aim of improving governance while other reforms are constitutional in nature. In Togo and Guinea Bissau, the reforms can mostly be linked to crisis. In Togo for instance, the 1991 text of the constitution included reforms supported by dialogues and political agreements which was “indicative of a permanent lack of confidence between political actors”.

- The “Doing business report (2015)” reveals that a key institutional feature of the ECOWAS construct is the existence of sophisticated formal rules in the form of protocols, strategies and institutional arrangements. These rules describe the power of the ECOWAS Commission, ECOWAS Parliament and the ECOWAS Community Court of Justice. As a result, ECOWAS became the first region to grant observer status to CSO including business associations at its meetings. In 1996, ECOWAS established the Forum of Associations Recognized by ECOWAS to engage in more structured forms of dialogue with stakeholders and democratize the process of regional integration. In terms of implementation and institutionalization, ECOWAS has limited space for autonomous action. It obliges the Commission to follow a more ad-hoc path by looking for concrete windows of opportunities to push forward regional agendas in close alliance with states that are willing to do so.

- There is also limited track record in implementing regional decisions. Torres Carmen and Van Seters (2016) affirmed that ECOWAS scores low on criterion for conditioning factors for compliance: legal, institutional coherence, demand for regional integration and leadership; for reasons such as limited institutions with supranationalism, incomplete contracts, limited trade and industry relations and weak leadership among others. ECOWAS has sought to strengthen the roles of regional ministries by setting up new ECOWAS offices in member states. For instance, the establishment of the ECOWAS Community Court of Justice in 1991 to interpret ECOWAS treaties and hear issues brought by Member States and institutions on community laws as well as in recent times the widening of its scope to hear cases of human rights violation.

- Despite these successes in West African countries, some gaps still exist. At the ECOWAS retreat in Senegal in 2018, ECOWAS Member States recommended key actions to sustain these gains. Some of these recommendations include building knowledge and exchange ideas on sensitive and challenging issues associated with political reforms, reconstructing the political system by redefining the relations between the government, political parties and societies as well as building capacities of institutions responsible for regulating and monitoring governance.

#### Socioeconomic context

- Although West African countries have experienced huge agricultural transformations, their domestic market is today more than 300 million consumers and projected to be half a billion in the next decade. This constitutes a major development stake in the region over the medium and long term. The main constraints to intra-regional trade include regulatory environment for doing business, inadequate transport links, cost of transport service and limited access to finance. Additionally, road network in the region remains inefficient and poorly linked and cross-border corridors are still subject to roadblocks and request for bribes. Other constraints to intra-regional trade include high prevalence of trade barriers as well as high levels of informal trade. However, it is important to note that ECOWAS have developed different trade policy frameworks to improve coordination and increase trade integration between members states. For example, the ECOWAS Trade Liberalization Scheme developed by ECOWAS leaders is the main framework for developing the region into a free trade area.

- In recent years ECOWAS strengthened its policy framework and committed to accelerate the implementation of policy measures and investments in the areas of agricultural development and food security. For example, ECOWAS adopted the protocol on free movement of persons by eliminating visa requirements for citizens from the region and establishing biometric passport in 13 out of 15 countries. The region ranks low regarding all human development indicators. ECOWAS countries are classified in the low Human Development category and 60 percent of the population is estimated to live on less than one dollar a day.

- The same report affirmed that ECOWAS, though not a wealthy region, is the only region that has been able to put in place since 2000 a self-financing mechanisms to collect 0,5% levy on the value of goods imported into the region to be collected by member states and paid into a dedicated ECOWAS account. This creates policy space for ECOWAS and provides some legitimacy to its institutions.

- From 2000 onwards, ECOWAS increased its profile in promoting a regional approach to agriculture and food security by developing the Comprehensive Africa Agriculture Development Program. The ECOWAS Commission has also acted as convener of multi-actor dialogue processes as well developed a wide range of policy initiatives and at the same time committing significant resources to support the effective domestication of continental and regional agricultural and food security agendas. ECOWAS own contribution to ECOWAS Agriculture Policy exceeds the Maputo ratio which amounts for 15 percent of its budget. The main regional policy on mainstreaming gender in agriculture makes an explicit reference to the participation of women in regional agricultural policies and related institutional development plans. In 2012, Ghana hosted a four day ECOWAS regional workshop to examine the roles of women in the search for food security in West Africa to determine what intervention ECOWAS could put in place to address the challenges regarding gender disparities in the agricultural sector and ensure food security.

- In June 2015, ECOWAS and core partners launched the Alliance for Climate Smart Agriculture which includes gender issues as one of the 4 priority area of work. Moreover, ECOWAS has an early warning system in the ECOWAS Commission. The region is the first to finalize the Regional Agricultural Investment Plan in 2010. To facilitate its implementation, a Regional Agency for Food and Agriculture and a Regional Fund for Agriculture and Food were set up. These agricultural policies have been somewhat useful in supporting nutrition challenges in the region.

#### About the WAHO

- WAHO is a specialized public health institution of the ECOWAS, created by Protocol A/P2/7/87 of 9 July 1987 signed in Abuja by the Heads of States and Governments. Its Headquarters is located at Bobo-Dioulasso in Burkina Faso. Article III of the Protocol establishing WAHO stipulates that “the objective of the West African Health Organisation shall be the attainment of the highest possible standard and protection of health of the peoples in the sub-region through the harmonisation of the policies of the Member States, pooling of resources, and cooperation with one another and with others for a collective and strategic combat against the health problems of the sub-region". Thus, by its founding protocol, the WAHO is entrusted with a political mandate to ensure coordination of regional health interventions within the ECOWAS region.  The overall objective of WAHO is, together with the other Community Institutions, to contribute to the attainment of the ideal of the creation of an Economic Union of West Africa, in accordance with Article 3 of the Revised ECOWAS Treaty. Specifically, the main objectives of WAHO are those described in its founding protocol.

- As part of the overall vision to move from ECOWAS Community of States to Community of People in 2020, WAHO’s vision is to be recognized by the Member States and the International Community as a proactive instrument of regional health integration that enables high-impact and cost-effective interventions and programmes. The WAHO’s decision making bodies comprise: i) The Authority of Heads of State and Government of ECOWAS, the Supreme Decision-making Body; ii) The Council of ECOWAS Ministers, made up of the Ministers of Regional Integration, Finance and Planning - the Body which takes decisions for the approval of the authority; and iii) The Assembly of Health Ministers, which brings together the fifteen Ministers of Health, the body responsible for health issues at the technical level. It also has one Focal Point in each of the 15 ECOWAS countries.

- WAHO priority programs are health information and research for health, disease control, epidemics and other health emergencies, health promotion, medicines, vaccines and other health products, traditional medicine, maternal, neonatal, child, adolescent, youth and older people’s health, health infrastructure and equipment, strengthened governance of the health system, human resources for health, technical assistance to member states, technical and financial partnerships and harmonization of policies and building WAHO’s institutional capacity.

### Nutritional status of West-Africa

- According to the World Bank, the West Africa has a population of about 372 million and 17 % are children under five years of age (CU5). Over one third of these – 19 million CU5 – are stunted, while the prevalence of CU5 wasting, stunting and overweight is 8.1 %, 2.4% and 29.9 % respectively (Global Nutrition Report-GNR 2018). Overweight and obesity also affect the adult population, with 14 % and 37 % of women affected, respectively (GNR 2017) . Nearly half of women of reproductive age (49 %) have anaemia and 47 % of children aged 6-59 months have vitamin A deficiency.

- According to UNICEF, there has been some progress towards achieving global nutrition targets in the West Africa Sub-region. As at 2018, eight countries in the sub-region were on course to meet the global target for infant exclusive breastfeeding, seven for under-five overweight, four countries for under-five stunting, and one for under-five wasting. However, not a single country in the subregion is on course to meet the targets for anaemia in women of reproductive age, low birth weight, male diabetes, female diabetes, male obesity, and female obesity. Seven countries in the subregion have insufficient data to comprehensively assess their progress towards these global targets. Similarly, the region experiences a malnutrition burden among its population aged 5-19 years (Figure 1).

# Figure 1: Child and adolescent nutrition status in West Africa (aged 5-19)

Underweight by gender

Obesity by gender

Source: UNICEF, Division of Data Research and Policy (2019). Global UNICEF Databases: Infant and Young Child.

- As shown on figure 1 above, the average prevalence of underweight in under-fives is 22% for girls and 34% for boys in 2016 - the lowest compared to other subregions in Africa. The prevalence of stunting in under-fives is 29.2%, this is greater than the global average of 21.9%.

- The Western Africa subregion's prevalence of wasting in under-fives of 8.1% is also greater than the global average of 7.3%. Some 30.8% of infants under 6 months in the Western Africa subregion are exclusively breastfed, while the subregion's average low birth weight prevalence of 15.2% is greater than the global average of 14.6%.

- The Western Africa region's adult population also face a malnutrition burden. An average of 49.3% of women of reproductive age have anaemia, and 6.7% of adult men have diabetes, compared to 6.2% of women. Meanwhile, 13% of women and 4.4% of men have obesity (Figure 2).

# Figure 2: Adult nutrition status in West Africa

Diabetes by gender

Obesity by gender

Source: UNICEF, Division of Data Research and Policy (2019). Global UNICEF Databases: Infant and Young Child

- Even though, West African countries are unique in context, challenges faced are similar from country to country. First of all, it is widely known that poverty is closely associated with malnutrition. The 2018 extreme poverty estimates from the World Bank revealed that Africa is lagging the rest of the world. Sub-Saharan Africa is the only region in the world where the overall number of extremely poor people is increasing rather than decreasing, according to the World Bank's Poverty and Shared Prosperity report. High food prices lead poor households to cut down on other expenses, such as health, education or housing which further undermines nutrition. As attempt to this situation, the ECOWAS countries have been very open to international markets, relying on cheap food imports for their staple food supply. This political and economic strategy temporarily improved the vulnerable population’s food security situation. However, it hampered the development of the agricultural sector and long-term FNS.

- Moreover, the ECOWAS regions is highly impacted by the climate change.  Up to 250 million people are expected to be affected by water stress, and food production. Climate change is expected to make natural disasters more frequent and intense. The most vulnerable people will - as usual - suffer earliest and most. Poor families with chronically malnourished children are the first to suffer in both man-made and natural disasters. Women play key roles in achieving food nutrition security. However, they face numerous obstacles in access to production assets and services. These obstacles increase their vulnerability and that of their families to food insecurity, and also considerably reduce their contribution to overall agricultural production. Gender inequality is very high in the region. The Gender Inequality Indices (GII) are among the highest in the world.

- Furthermore, the same source affirms that the financial capacity of West African countries is very limited. Programs mostly rely on international aid and are thus dependent on the ups and downs of development partners. Budget delivery is still low, and an important percentage is dedicated to operating expenses. Although international partners are increasingly aligning their initiatives with regional policies and programs, responding to ECOWAS interests and needs, still requires organizations and governments to run parallel to regional and national processes, with a diversity of investments responding to external interests.

- In this context, number of ECOWAS countries have made progress towards the fight against malnutrition. For example, Burkina Faso has taken great strides to address malnutrition in the country, including concerted efforts to strengthen nutrition governance. Since 2015, the UN Network, through its intensive arm –REACH– has worked closely with the SUN Government Focal Point and other authorities to employ a participatory approach that has mobilized multiple sectors whose work supports nutrition outcomes. Today, roughly eight ministries (Agriculture, Education, Health, Local Governance, National and Women’s Solidarity, Research, Social Protection, Trade and WASH) are engaged to fight malnutrition in full force. Burkina Faso is in many ways a success story. Not only has it reached several nutrition governance milestones, it has reduced child stunting from 35 % in 2010 (Demographic and Health Survey) to 21% in 2017 (National Nutrition Survey) .

- Liberia developed a National Nutrition Policy in 2008, to ensure adequate nutritional intake and utilization for all people living in Liberia, especially the most vulnerable to ensure health and well-being for sustainable economic growth and development.

- Nigeria’s National Strategic Plan of Action for Nutrition (2014-2019) promotes the delivery of effective interventions that will ensure adequate nutrition to all Nigerians, especially vulnerable groups; enhances capacity to deliver effective and appropriate nutrition interventions; contributes to the control of diet related noncommunicable diseases; promotes and strengthen research, monitoring and evaluation; promotes and facilitate community participation for nutrition interventions and promotes and strengthen nutrition coordination and collaboration.

- Sierra Leone has developed a number of policies and designed programs and strategies including the Free Health Care Initiative, The Sustainable Agricultural Development Program, the Sierra national Food and Nutrition Security Policy was developed with an overall goal to contribute to the improved health, social and economic well-being of all the people in Sierra Leone, especially women, children and other nutritionally vulnerable groups.

### Evaluation Object

- The ECOWAS’ Nutrition Forum is a regional platform that brings together the major stakeholders in nutrition to review nutrition policies and practices, progress in the reduction of malnutrition and diet-related diseases and innovative practices in the region. These fora also provide ECOWAS Member States and Partners with an opportunity to brainstorm on nutrition challenges, develop a common vision of the nutrition profile of the sub-region, identify financing mechanisms, review the implementation level of past Forum recommendations, and provide a technical update to participants on topical malnutrition issues.

- The ECOWAS Nutrition Forum has been organised since 1996 and its management led by WAHO since 2001. It was hosted annually from 1996-2004 in Senegal (1996, 1997), Cote d’Ivoire (1998), Niger (1999), Mali (2000), Ghana (2001), Gambia (2002), Guinea (2003) and Benin (2004). From 2006-2019, the forum was hosted biennially in Cape Verde (2006), Sierra Leone (2008), Cote d’Ivoire (2010), Burkina Faso (2012), Togo (2015), Guinea-Bissau (2017) and Liberia (2019).

- Its specific objectives are aligned with the forum’s theme and so differ between fora. However, they have been geared towards providing a platform to: i) Share experience and review nutrition interventions and programs implemented at country level; (ii) Develop a regional profile of nutrition and identify adequate resources needed from African institutions and partners to support the implementation of activities; (iii) Provide a technical update focusing on a crucial and relevant topics such as “Food and Nutrition Security” in the sub-region; (iv) Review the recommendations from previous forum; (v) Develop action plans aiming at improving the nutritional situation; (vi) Carry out a technical updates in the area of planning and funding multisectoral nutrition and food programmes in the ECOWAS region to identify strategies and actions aiming to improve the efficiency of the implementation of nutrition programmes.

- The list of stakeholders attending the nutrition forums includes: i) Member States from the fifteen ECOWAS countries ii) Parliamentarians from the ECOWAS Parliament and the Parliamentarian Network on Nutrition for West and Central Africa; iii) African and West African Economic or Technical Institutions including African Union Commission, NEPAD ECOWAS Commission, UEMOA, Permanent Interstate Committee on Drought Control in the Sahel (CILSS), Eastern Central and Southern Africa Health Community (ECSA-HC); iv) Partners such UN agencies, SUN Movement Global Secretariat and International Non-Governmental Organizations (NGOs), v) Financial partners such as World Bank, African Development Bank (AfDB), European Union and USAID; vi) Farmer groups, NGOs and CSOs such ROPPA, Network of West African CSOs on the SUN Movement Platform vii) private sector industry such as the UEMOA-AIFO involved in food fortification viii) Regional Professional Associations such as African Nutrition Society (ANS), Federation of African Nutrition Societies (FANUS); ix) Research Institutions such as West and Central African Council for Agricultural Research and Development (CORAF), International Union of Nutrition Sciences (IUNS), International Food Policy Research Institute (IFPRI) and the Centers for Disease Control (CDC). Local delegates from the host country are drawn from multiple sectors including education, health, nutrition, social protection and agriculture.

To date, sixteenth edition of the forum were organised on a rotative basis from one country to another. The sixteenth edition of the forum was hosted by Liberia in Monrovia from 18-20 November 2019. For each forum, there is a Lead Technical Partner and a sometimes a Facilitator. Table 1 resumes list of past fora, their corresponding themes and Lead Partners and annex 5 presents the objectives and recommendations of the ECOWAS Nutrition Fora from the 2008 edition onwards for which information was available.

# Table 1: List of past editions of the forum with their corresponding themes and Lead Partners

| Year | Meeting | Location | Theme | Lead Partner |
| --- | --- | --- | --- | --- |
| 2003 | 8th Forum | Conakry, Guinea | Micronutrient deficiencies: the way forward | MI |
| 20-24 /9/2004 | 9th Forum | Cotonou, Benin | Nutrition and HIV | SARA USAID |
| 18-22 /9/2006 | 10th Forum | Mindelo, Cape Verde | Nutrition and chronic diseases as part of the double burden of malnutrition morbidity | SCN |
| 22-26 /9/2008 | 11th Forum | Freetown, Sierra Leone | Food and nutrition security in West Africa: opportunities and challenges | FAO |
| Sep-10 | 12th edition | Grand Bassam, Côte d’Ivoire | "Financing and Planning Nutrition Programmes in ECOWAS Member States" | UNICEF, World Bank |
| 5 – 9 /11/2012 | 13th | Ouaga, Burkina Faso (replaced Guinea Bissau) | "Roles of local authorities, communities, the civil society and private sector in scaling up nutrition interventions" | MI |
| Oct-15 | 14th | Lome, Togo (replaced Liberia) | Nutrition and the MDGs in ECOWAS Member States: progress, challenges and prospects | UNICEF |
| 24-27 /10/2017 | 15th | Bissau, Guinea Bissau | Nutrition surveillance: towards improved planning and evidence-based decision making on food and nutrition security in West Africa |  |
| 18-20 /11/2019 | 16th | Monrovia, Liberia | Adolescent nutrition: institutionalizing sustainable actions for improved outcomes in West Africa | UNICEF |

Source: Document review.

## Evaluation purpose, objectives and scope

### Purpose and use of the Evaluation

#### Purpose of the evaluation

- As per the Terms of Reference (ToRs) available in annex 1, this evaluation of the ECOWAS Nutrition Forum has been jointly commissioned by the WAHO and the UNICEF (WCARO). The Forum was previously evaluated in 2003 following a recommendation at the 6th annual meeting of the then ECOWAS Nutrition Network (September 2001, Accra). The process through which the regional network was formed and is operating were documented.

- This evaluation also aims to highlight the network’s major milestones and accomplishments and assessed any direct or indirect impact on nutrition policy and programming, human capacity building and institutional strengthening in the region and beyond.

- The current evaluation will provide evidence on the extent to which the Forum has contributed to the nutrition discourse in the ECOWAS region. The findings will not only inform the Forum implementation strategy in the years to come, but also shed light on some potential corrective actions that could be explored further in the future. More specifically, this evaluation generates recommendations that will help to adapt the strategy of the Forum to the emerging needs. Therefore, it is formative and summative in nature, looking at the relevance and effectiveness of the Forum. The evaluation provides constructive learning deliverables with evidence-based recommendations supported by management responses that generate improvements, inform stakeholders involved about the contribution of the Forum, and improve understanding of its business model.

#### Use of the evaluation

- The main expected Users of the evaluation are ECOWAS, WAHO, UNICEF and other Technical and financial partners, Member States and in-country partners and other participants of the Forum. The envisaged uses of the evaluation are briefly described by users in table 2.

# Table 2: Evaluation users and uses of the evaluation

| Evaluation users | Evaluation uses |
| --- | --- |
| ECOWAS | Better adapt the forum design and activities to address emerging issues and needs in the sector of nutrition as well as improve accountability and tracking of recommendations implementations in countries. |
| Technical and financial partners (including UNICEF Regional Office for West and Central Africa) | Tailor their contributions to the Forum so as to make them more effective and efficient during the next Forum editions; Put into practice the lessons learned into the organization of other nutritional regional coordination events/fora which is expected to be coordinated in the region and sub-region. |
| Member States | Enhance the effectiveness of the coordination with each other Diversify the modalities of participation to the event Make their participation more results-oriented in the future |
| In-country partners and other participants of the Forum | Enhance a better alignment of their respective initiatives, especially in the areas which the Nutrition Forum focuses on from time to time. |

### Objectives and scope of the evaluation

    - Objectives of the evaluation

- This evaluation aimed to achieve the following specific objectives:

- Assess the relevance, effectiveness, efficiency and sustainability of the ECOWAS fora organized since 2004;

- Assess the extent to which the organization of the forum has been conducive to meet its organizers’ and participants’ expectations, especially in terms of process, planning, stakeholder engagement pre-forum, stakeholder participation, methodology, and final recommendations;

- Document the Fora costs and sources of funding;

- Identify gaps and make specific actionable recommendations to the expected evaluation users (Table 2).

- Draw lessons learned about what has worked and has not worked in respect of the ECOWAS Nutrition Forum including unexpected outcomes (positive and negative);

    - Scope of work

- In terms of thematic scope, the evaluation assessed the ECOWAS Nutrition Forum from several perspectives. Specifically, it assessed the influence of the Forum on the adoption of adequate policies and strategies at regional and national levels as well as the quality of nutrition programming and workforce at national and lower levels. Secondly, it examined the Forum from a process perspective in respect to its organisation and to roles and responsibilities of different stakeholders. The evaluation covered also the mid-term reviews and their contribution to the results of the ECOWAS Nutrition Forum.

- In terms of geographical scope, this evaluation covered the contributions provided to the Forum by all the 15 ECOWAS Member countries and the benefits derived from the forum. A strong rationale such as language distribution within the region was used to select a sample of five countries for field visits namely Liberia, Burkina Faso, Nigeria, Cote d’Ivoire and Guinea-Bissau.

- The chronological scope covered the ECOWAS nutrition Forum organised between 2004 and 2019.

## Evaluation methodology

### Evaluation criteria

- The evaluation was structured around four evaluation criteria of the Organisation for Economic Co-operation and Development's Development Assistance Committee (OECD/DAC): Relevance, Effectiveness, Efficiency, Sustainability, and an additional criterion on Gender, Equity and Human Rights was also included. Due to the lack of baseline and the challenge of measuring the direct link (attribution) between the Forum and the different changes observed in countries’ nutrition profile in the region, the impact criterion was not selected.

### Evaluation questions

- Table 3 summarises the key evaluation questions for each evaluation criterion. They were revised and organised in the evaluation matrix per data sources, data collection and data analysis methods (Annex 2).

# Table 3: Key Evaluation questions

| Evaluation criteria | Evaluation questions |
| --- | --- |
| - Relevance | 1.1. To what extent has the Forum addressed the evolving needs of the nutrition sector / key stakeholders in the West Africa region over the years, in terms of coordination and mobilization of stakeholders? |
|  | 1.2. To what extent are the Forum objectives aligned with those spelled out in the ECOWAS regional nutrition strategies and policies? |
|  | 1.3. To what extent has the Forum’s design been conducive to achieving the intended objectives? |
|  | 1.4. How complementary is the ECOWAS Nutrition Forum with other high-level events and platforms? |
|  | 1.5. To what extent do the various stakeholders (Member states representatives, partners, academics, etc.) perceive their voices, values, concerns are taken into account before, during or after the Forum? |
| - Effectiveness | 2.1. To what extent and through which mechanisms has the ECOWAS Nutrition Forum contributed to its intended outcomes (improving nutrition programming and policies in the region)? |
|  | 2.2. What are the factors (internal and external to ECOWAS) that contributed the most to the attainment of the Forum’s objectives? |
|  | 2.3. What have been the major constraints (internal and external to ECOWAS) in influencing nutrition policies and programming in the region? How can these be addressed in the future? |
|  | 2.4. What have been the Forum’s unintended effects (positive or negative), if any? |
|  | 2.5. To what extent and how are the reports of the Nutrition Forum disseminated? How could this be improved? |
|  | 2.6. What could be done to better and more consistently track the ECOWAS Nutrition Forum outcomes and the uptake of the recommendations in the future? |
| - Efficiency | 3.1. To what extent were financial resources, human resources and supplies: i) Sufficient (quantity)? Ii) adequate (quality)? Iii) used/deployed in a timely manner? |
|  | 3.2. What are the Forum’s different sources of funding? |
|  | 3.3. Are there other alternative strategies that could be put in place to achieve the same level of results but at a lesser cost? What measures could be implemented to increase the value for money of the ECOWAS Nutrition Forum? |
|  | 3.4. Are the process and criteria used to identify the length and content of the Forum appropriate? How could the Forum design and implementation be changed in order to achieve more value for money? |
| - Sustainability and ownership | 4.1. To what extent and in what ways were the capacities of the government, civil society, NGOs, etc. enhanced in order to sustain the Forum’s results? |
|  | 4.2. What has been the level of stakeholder engagement in the Forum’s organization (both financial and technical contributions)? |
|  | 4.3. To what extent are the ECOWAS Nutrition Forum and related events included in national or partner event calendar planning? |
| - Gender and human rights | 5.1. To what extent are Gender, Human rights and Equity principles considered in relevant technical discussions and recommendations provided by the ECOWAS Nutrition? |
|  | 5.2. To what extent are the opinions and needs of different groups (men, women, boys and girls), and particularly the most vulnerable, taken into consideration when deciding and acting upon the ECOWAS Forum recommendations? |
|  | 5.3. To what extent did the discussion held during the Forum cover the barriers to services for boys and girls? |

### Approach and principles to the evaluation

- The evaluation was based on the United Nations Evaluation Guidelines (UNEG) norms and Standards for evaluations. It was guided by the UNEG’s ethical guidelines and principles for evaluation such as ethical and meeting standards, being appreciative, rigorous, inclusive and culturally sensitive.

- The policy influencing approach proposed by Coffman (2007) was adopted to guide this evaluation. The model on which this approach is based differentiates between two different modalities to influence policies: the “Inside track modalities”, which feature close collaboration with decision-makers, versus “Outside track modalities” that seek to influence change through pressure and confrontation. Given the wide range of stakeholders, country contexts and cultural behaviors associated with the thematic topic of “Nutrition”, this approach was complemented with a participatory process in all stages of this evaluation.

- As the nature of the ECOWAS’ Nutrition forum and its agenda are always organised around advocacy and policy change strategies, the “Bellwether methodology” was considered to complement the policy influence approach. Bellwethers are knowledgeable and innovative thought leaders whose opinions about policy issues carry substantial weight and predictive value. This methodology determines where an issue is positioned in the policy agenda queue, how lawmakers and other influential persons such as officials are thinking and talking about it, and how likely they are to act on it. Therefore, it allows to provide both summative data about the Nutrition forum advocacy strategy's success to date and formative data for shaping its future. Bellwether data indicate where an issue stands on the policy agenda and how effectively advocates, have leveraged their access to increase an issue's visibility and sense of urgency.

- Field data collection was preceded by an inception meeting in Monrovia (Liberia) to discuss evaluation logistics such as access to information, contact information for those to be interviewed or surveyed. The aim was for the evaluation team to become more knowledgeable about the scope of work and to obtain a good understanding of the type of information that was already available. Preliminary interviews were conducted during the 16th edition of the Nutrition forum in Monrovia to gain a better understanding of the theory behind the scope of work and how the evaluation will be used.

- The evaluation was mostly based on a qualitative performance assessment. To this end, the purposive sampling method proposed by De Vaus (2001) was used to consider key informants and beneficiaries to be interviewed. Participant groups included: i) ECOWAS/WAHO; ii) Member States’ representatives; iii) Technical and financial partners; iv) Non-States actors’ partners or In-country partners including Non-Governmental Organisations (NGOs) and Civil Society Organisations (CSO). They were selected based on a range of criteria such as country membership to ECOWAS, geographic diversity, partisan representation, and cross-sector experience with the nutrition theme in the 15 countries. Sampling was focused on those who are familiar with the nutrition forum and activities to support implementation. Therefore, sampling was not limited only to those with adequate knowledge and experience of the forum. But selected key informants should be part of the five categories of forum’s participants with at least knowledge of the nutrition forum.

- Using mixed methods consisting of both qualitative (Individual and/or group interviews) and quantitative (exploitation of existing quantitative data in documents) methods, the data collection and analysis were based on the evaluation matrix attached in annex 2.

### Data collection and sources

The data was collected through document review, key informant interviews and during country visits.

#### Document review

- Systematic sampling was applied to the selection of fora’s reports and country documents. During the document review, data were obtained from existing reports and published articles to help identify information to complement the evaluation questions. The main sources of information covered by the review were: i) Reports of previous Fora from 2008 to 2019; ii) Previous evaluation reports including mid-term review of previous fora; iii) Member states’ reports on follow-up of recommendations; iv) Previous conference resolutions/recommendations; v) Strategic plan (s) of the ECOWAS Nutrition forum, and regional nutrition strategy for West Africa; vi) Existing policy and grant briefs; vii) Reports and documents published and unpublished (from various sources including the Client and its partners); viii) Other documents retrieved online. The detailed list of consulted documents is presented in Annex 3.

#### Key Informant Interviews

- Using semi-structured questionnaires (see Annex 4), key informant interviews were conducted in face-to-face and by e-mail, but mostly via skype/phone/Whatsapp calls with available stakeholders including ECOWAS member State Officials, WAHO staffs, NGOs and CSOs, and partners. Informed consent was obtained prior to each interview. Triangulation was used to consider multiple types of evidence to answer each evaluation question. A focus was paid to the forum’s performance towards its primary objectives with tracking evidence and measured its influence on participants’ attitudes for further fora. The list of persons to be interviewed was suggested during the inception phase and compiled by ECOWAS’ team.

- In total, 42 key informants from Member States (58% of male and 42% of female), WAHO (only male), partners (53% of male and 47% of female), NGO/CSO (40% of male and 60% of female), and Parliamentarians (only a male) were interviewed by the consultants (table 4).

- Among the 42 key stakeholders met, 32 (76%) had participated in at least one edition of the forum. The evaluation found that, among those who had participated in at least one Nutrition forum, 12 (38%) had participated in one edition, 10 (31%) in 2-4 editions, 6 (19%) in 4-6 editions and 4 (13%) had in more than six editions. Twenty-two (69%) of those who participated in the nutrition forum did not attend more than 4 editions.

#### Country visits

- In addition to Liberia which was used for the inception phase, four countries were selected for field visits, namely Burkina Faso, Guinea Bissau, Cote d’Ivoire and Nigeria. Country visits were carried out during a period of three weeks, from 16-23 November 2019 in Liberia, 15-21 December 2019 in Nigeria and Guinea-Bissau, and 4-11 January 2020 in Cote d’Ivoire and Burkina Faso. During each country visit, key informant interviews were completed, and a structured checklist was used to identify any available outcomes named as part of the contribution of the Nutrition forum support such as existing nutrition policy, food security and nutrition framework, existing intervention funded to cover nutrition policy or framework.

- Sampling criteria to identify the countries to be visited included : i) language inclusion to cover at least one French (Cote d’Ivoire), one English (Nigeria) and one Lusophone (Guinea Bissau) speaking country; ii) Host of the next 17th Nutrition Forum (Nigeria in 2021), and iii) Headquarters of the ECOWAS/WAHO for debriefing meeting (Burkina Faso).

# Table 4: Distribution of key informants met by category of stakeholders

| Categories | Member States |  | WAHO |  | Partners |  | NGO/CSO |  | Parliamentarians |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |
| Number of persons interviewed | 7 | 5 | 5 | 0 | 10 | 9 | 2 | 3 | 1 | 0 | 25 | 17 |
| N | 12 |  | 5 |  | 19 |  | 5 |  | 1 |  | 42 |  |
| Percentage | 58.3 | 41.7 | 100 | 0 | 52.6 | 47.4 | 40 | 60 | 100 | 0 | 59.5 | 40.5 |
| Total | 28.5 |  | 12 |  | 45.2 |  | 12 |  | 2.3 |  | 100% |  |

Legend: M = Male 	F = Female

### Synthesis of findings, debriefings and reporting

- Content analysis was applied to data collected from various documentary sources. For the credibility and validity of findings and conclusions, data were triangulated by sources (documents and key informants) and methods (by cross-comparing the information obtained from each method such as desk review, key informant interviews and field visits) to determine the extent to which they converge or diverge. Convergence allowed more confidence in the findings. Divergence of data was explored to determine why it has occurred and what the implications are. Moreover, the evaluation cross-compared the results obtained through different data sources.

- Reporting was divided into four components: i) Preparing a preliminary summary of findings; ii) Participatory debriefing meetings after field data collection in each country to review findings and determine priorities and formulate realistic and useful recommendations; iii) Draft evaluation report with analysed data including inputs provided during the participatory debriefings; iv) Review the findings, conclusions and most importantly recommendations with WAHO and UNICEF.

### Human rights, Equity, Ethical and gender consideration

- The issues of "Human rights, ethics, gender and equity" were taken into account throughout the evaluation process. Firstly, the evaluation team was composed of men and women. The evaluation consultant team included one man and a woman, and the evaluation reference team at UNICEF level was made up of women and men.

- Furthermore, in the analysis of the context of the evaluation, the indicators and findings were analysed taking gender into account. Information are disaggregated by sex. Gender, equity and human rights issues were also taken into account in the evaluation questions. These questions were clearly defined in the qualitative data collection tools (Annex 4), thus making it possible to grasp the appreciation of the actors on the taking into account of these questions in the design, implementation and monitoring of forum’s recommendations.

- However, it was not possible to respect the gender balance in the selection of institutional actors interviewed, since there were more male leaders. Both men and women were interviewed. The rights of the interviewees were taken into account through the consent notes available on each data collection tools (Annex 4).

### Limitations

- The evaluation of the ECOWAS’ Nutrition Forum as an advocacy platform was very challenging. Number of limitations might have compromised the quality of this evaluation. For each limitation the evaluation team developed a mitigation strategy as presented below.

- First of all, most interviews were performed at distance (Skype/Whatsapp/phone, e-mail) rather than in face-to-face. In such situation, number of biases were observed in the responses provided by key informants. Other limitations were associated with information collected from key informants who did not attend either past Fora from the inception edition in 1996 till the reform which happened in 2004 to move from annual to biennial edition term, or at least 2 successive editions. This information might be not relevant. Efforts were made to identify key informants who are more knowledgeable about the forum through Skype or WhatsApp and/or email communication. In addition, the evaluation applied triangulation of data sources to obtain most valid and reliable information.

- Secondly, reports of previous fora from 2004 to 2008 were not available. Fora’s documents provided little information about the Forum’s outcomes and the ECOWAS political and socioeconomic context. Efforts were made to look for information from other sources such as Internet. The focus was on expected outcomes over which the forum had control such as country’s commitment on forum’s recommendations (rather than high-level impacts). Furthermore, financial information and sources of the forum’s money were not available. Therefore, the evaluation could not properly assess the forum’s efficiency. The first key question of the efficiency criterion was canceled.

- Thirdly, there was insufficient time for field missions in the four selected countries to thoroughly evaluate the normative aspect of the forum. The evaluation looked for ways to save time and resources, such as paying more attention on desk review.

- Other challenges were linked to policy influence work rather than being specific to an approach to policy influence on the forum itself. Conceptually, it was very difficult to determine the links between policy influencing activities and outputs, and any change in policy and/or from nutrition actors (attitude in influencing policy at country level). As this is a policy evaluation, there was no baseline associated to this evaluation.

## Findings and preliminary conclusions

- The Findings are organised around the evaluation criteria and key evaluation questions.

### Relevance

### How the Nutrition Forum has addressed evolving needs of the nutrition sector in terms of coordination and mobilisation of stakeholders

- The themes that are addressed during the forums were identified by the participants who are focal points of the countries based on the nutrition issues common to the ECOWAS member countries. Participants were identified by each country in accordance with the profiles required for the forum. The central themes and sub-themes that made up the menu of discussions in the various editions of the forum, correspond to issues related to the nutrition context in the region. They are also related to key nutrition priorities and concerns of stakeholders. These include child and adolescent nutrition challenges, education and training around access to adequate and balanced diet, the need for mainstreaming of nutrition into foundational learning including in the training curricula for health professional schools, knowledge sharing and networking on nutrition concerns globally.

- All key informants stressed that the forum brought in more stakeholders like the small-scale farmers (both women and men), Heads of state, parliamentarians, youth, nutrition specialists, to deliberate the nutrition issues which is very important to everybody and make sure that no one is left out. During the forum, many new initiatives in nutrition are gathered and shared with Member States. The objective is to reduce the gap in meeting nutrition targets. Key nutrition indicators discussed include: i) Child nutrition challenges such as the prevalence aneamia, ii) the prevalence of low birth weight, iii) the prevalence of overweight and obesity among children under 5 years, iv) prevalence of diabetes among adults aged 20 to 79, v) prevalence of pregnancy in adolescent girls, and vi) prevalence of exclusive breastfeeding in the region.

- Document analysis of past forum reports as well as country national nutrition policies affirmed that the forum is built on the global agenda for the sub-region. While providing the nutrition background to participants, the forum is an opportunity for stakeholders to agree on specific actions to remedy the current nutrition challenges which include: i) more support and capacity building of CSO, nutrition focal points of Member States, parliamentarians, and other actors such as media; ii) need for long-term leadership and accountability at all levels; iii) further improvement of governance mechanisms such as multisectoral platforms, multi-stakeholder participation, Scaling Up Nutrition team, as well as significant increase of financial investment in nutrition; iv) need to strengthen monitoring through a common results framework for all actors.

### Alignment of Forum objectives with those of ECOWAS regional nutrition strategies

- Document analysis as well as discussions with country nutrition focal points corroborate that the forum objectives are aligned with the current 2018-2025 ECOWAS regional nutrition strategy (which emphasises governance, knowledge management and capacity building as priorities) as well as with past regional nutrition strategies and policies. For example, the 2018-2025 ECOWAS strategy aims to achieve the following key priorities (Table 5).

# Table 5: Key priorities of the 2018-2025 ECOWAS Strategic Plan

| Priority Areas | Description |
| --- | --- |
| Governance | Leadership support to ensure multisectoral coordination on nutrition; support for a multi-sectoral joint planning in the country in a context where various ministries or departments operate in silos; promotion of coordinated implementation of nutrition-specific and nutrition-sensitive activities; and ensure more effectiveness of functional mechanism for monitoring and evaluation at all levels. |
| Knowledge management | coordination of nutrition research at the intra and intersectoral level to ensure synergy in terms of availability of researchers’ expertise; sharing research and funding opportunities; more inter-country collaboration for the implementation of research activities; ensure a prompt and comprehensive information on nutrition by collecting and sharing existing data; information monitoring and sharing good practices |
| Capacity building | provide training on nutrition; provide more efforts to ensure food and nutrition security; and enhance scale-up of high-impact interventions on nutrition |
| Resources | Resource mobilization for food and nutrition security: from internal and external sources of both technical and financial opportunities |

- Documents review revealed that the instituted practice in which time is dedicated on the forum’s agenda for Member States to collectively discuss and agree on the theme of the next forum is commendable.  This ensured that the forum objectives were defined in line with the ECOWAS Member States’ nutrition strategies and policies. In 2008 for example, the forum gathered ECOWAS participants to share experiences and review nutrition interventions and programs implemented at country level, to develop a regional profile of nutrition and identify adequate resources needed from African institutions and partners to support the implementation of activities, to provide a technical update focusing on a crucial and relevant topic which was food and nutrition security in the sub-region (Annex 6).

- Furthermore, further forum’s themes and objectives were selected by Member States to be aligned to ECOWAS nutrition challenges. For example, the forum gathered nutrition actors respectively in: i) 2010 to look at planning and funding of multisectoral nutrition programmes in ECOWAS Region; ii) 2012 to question the roles of local communities, civil society and the private sector in Scaling Up Nutrition interventions; iii) 2017 to look at nutrition surveillance-towards improved planning and evidence-based decision making on food and nutrition security in West-Africa; or iv) 2019 to look at “Adolescent nutrition: institutionalizing sustainable actions for improved outcomes in West Africa” (Annex 6). Therefore, these fora provide ECOWAS Member States and Partners with an opportunity to brainstorm on regional nutrition challenges, develop a common vision of the nutrition profile of the sub-region, identify financing mechanisms, and review the implementation level of past Forum recommendations.

### Conduciveness of Forum design to achieving intended objectives

- The forum is designed to support ECOWAS efforts towards gathering all actors in sharing good practices and country nutrition improvements with the aim of influencing the implementation of regional and national nutrition priorities such as to review the status of ongoing regional nutritional initiatives, analyse the structure, relevance and limitations of the different nutrition surveillance systems in the region or explore how the value of routine and programme data in nutrition decision-making could be improved. In doing so, forum objectives vary from one forum to another as described in the previous section.

- The forum has been organised every two-years since the 2004 edition. It is preceded by a mid-term review of the previous Forum with the aim of reviewing the level of implementation of the recommendations of the Forum, update current on essential nutrition actions and to reflect on the organization of the next Nutrition Forum. The mid-term review also provides an opportunity to assess the level of implementation of recommendations by countries, WAHO and partners; to reflect on the experiences, challenges, lessons learned in implementing the recommendations and how these help the region to position itself to implement the sustainable development agenda; to review progress on selected regional nutritional initiatives; to build capacity on essential nutrition actions in the region, and to finalise the theme and expectations of the upcoming forum.

“The Nutrition forum is a networking platform for sharing regional and national experiences and nutrition development strategies. It offers the opportunity to meet for networking between stakeholders. The themes that are addressed during the forums are identified by the participants who are focal points of the countries based on the problems common to the ECOWAS member countries.”

From a key Informant

Since 2015, the format of the forum changed from 5 to 3 days meetings. Forum objectives cover both technical and financial challenges facing the nutrition sector in the region. Presentations are organised around a number of themes and sub-themes during the first 2 days. For instance, nutrition issues discussed during forum include nutritional status and regional initiatives with the objectives of providing an overview of the nutritional status, providing technical update on key regional initiatives, sharing information on ongoing regional initiatives and agreement on capacity building priorities to improve intervention programmes. Furthermore, participants argue on the review of nutritional surveillance. This is an opportunity to update and motivate Member States on specific nutritional surveillance such as nutrition and micronutrient deficiency surveillance at the community level, the need for improving the quality of routine nutrition data for decision-making. This aims to update participants on the nutritional indicators and collection instruments used by nutrition officers, share country experiences in the system of collection, analysis and decision-making in nutrition.

- Governance and planning mechanisms have also been part of the forum debates. Participants have looked at how to improve the planning and governance of nutrition programmes at different levels through nutritional data and various approaches to obtaining good quality data; the interoperability and comparability between different nutrition survey systems to look at how to improve objective data comparability between the countries, and explored the mechanisms in place to collect data in terms of frequency and period of data collection. Moreover, attention has also been paid to monitoring accountability for national and regional commitments to food and nutrition security with the objectives of enhancing the understanding of the actions to be taken and coordination between public and private institutions, among others, and sharing experiences in nutrition advocacy.

- Finally, forum has updated Member States on how to track nutrition financing and highlighted the importance of monitoring nutrition allocations and expenditures for additional nutrition financing, budget transparency and better financing. The fora have been oriented towards the objectives set and the achievement of objectives has always been evaluated at the end of each forum.

### Potential complementary high-level events or platforms

- The ECOWAS Nutrition fora have addressed uniquely the nutrition concerns of the region. Being a crucible of exchange and sharing of experiences between participants from various backgrounds, the forum therefore bridges with other platforms. Key informants revealed that the forum is moving towards an inclusive framework for the materialization of the multisectoral approach to nutrition. The evaluation identified three other high-level events and physical regional institute which cover the nutrition and health concerns and are complementary to the ECOWAS Nutrition Forum. However, these platforms are not limited to West Africa, but are open and cover the African continent. These are: The Federation of African Nutrition Societies (FANUS), the Scaling Up Nutrition (SUN) of the United Nations, and the Regional Centre of Excellence Against Hunger and Malnutrition (CERFAM).

- FANUS, created in 2007, organizes an African-wide conference every four years. It gathers around 250+ delegates and experts with interests in nutrition. Its 3rd conference was held in Arusha (Tanzania) in 2019.  Experts from government, field practitioners and programme experts, academia, NGOs, research, International Union of Nutritional Sciences (IUNS), international NGOs and bilateral organizations, debate and analyze the challenges of improving nutrition in Africa. In order to address Africa’s nutrition challenges and meet national goals and targets, FANUS objectives are as follows:

- Empowerment: Empowerment of all actors, especially the most vulnerable population groups with a focus on families and employing food-based approaches.

- Nutrition Governance: Recognition that nutrition is a human right and yet there are challenges of governance for nutrition, the remit for which does not sit clearly in one sector.  Multi-sectorial approaches are essential but require proper leadership at the highest level of government to ensure efficiency and accountability.

- Systematic Capacity Building: cross-sectoral and at all levels including higher education institutions responsible for the training of the nutrition workforce and the commitment of adequate resources to support nutrition actions and programmes.

- Harmonization: nutrition activities and training and the raising of standards to ensure the right skills and competencies required for the workforce to make a significant contribution to achieving and sustaining the goals for nutrition in Africa. Recognition of local contexts, priorities and the need for stakeholder involvement to ensure standardization and competency-based curricula to meet employer and service needs.

- CERFAM was commissioned in March 2019, following a partnership between the World Food Programme (WFP) and the Government of Cote d’Ivoire.  It serves 18 countries in West and Central Africa. It is the third such center after those set up in China and Brazil. CERFAM focus is on research and advocacy to help achieve the goal of eradicating hunger in Africa by 2030 (SDG 2). It will notably allow information and knowledge sharing not only with African countries but also with all those in the world with conclusive experience in the fight against malnutrition. In partnership with the World Food Programme (WFP), its objectives include facilitate and mobilize expertise, promote hunger and nutrition solutions, including through innovative approaches and strengthen networks and community of practice by connecting national, regional and international actors. Therefore, the central primary objective will be to document, promote and share at both regional and national levels the good practices for the eradication of hunger and malnutrition in West and Central Africa. It will also provide technical assistance to mobilize resources for the adoption of good practices and innovative solutions.

- The SUN Movement is a unique movement founded on the principle that all people have the right to healthy food and good nutrition. It brings together officials from government, civil society, the United Nations, donors, the private sector and researchers who are all working to improve nutrition. As approach, SUN supports the equality of women. Governments are leading national efforts to scale up nutrition under the responsibility of a SUN focal point. The focal point brings people to work together around a multi-stakeholder platform (civil society, donors, private sector, governments, UN agencies). Therefore, the SUN relies on national leaders who embrace nutrition and are committed to finding lasting solutions to improve nutrition in their countries. Moreover, global stakeholder networks align resources and harmonize actions to support country efforts with the support and overall coordination provided by the SUN Movement Secretariat and the SUN Lead Group. In each country, the SUN Movement actors are brought together around 4 key processes and progress is reviewed every six weeks: i) Creation of political and operational platforms, with strong leadership and multi-stakeholder spaces where stakeholders come together to harmonize their activities and take joint responsibility for strengthening nutrition; ii) Integration of good practices into national policies for scaling up effective interventions; including the adoption of effective laws and policies; iii) Alignment of actions across sectors with adequate and well costed national plans, with a consensual result framework and mutual accountability; iv) Increase in resources and monitoring of implementation for coherent, harmonized, effective actions with maximum impact.

- At the 16th ECOWAS Nutrition Forum, there was opportunity to discuss the highlights of the SUN Movement Global Gathering held in Kathmandu, Nepal in November 2019 and the 4th FANUS conference in Kigali, Rwanda in August 2019. The collaboration is not limited to simple invitations.  We have collaborated with ANS, FANUS in the development of the regional nutrition strategy, developing a harmonized tertiary-level training curriculum for nutrition. Their complementary field of intervention could technically enhance the nutrition challenge in the region.

### Extent of stakeholder engagement before, during and after the Forum

- The forum is relevant to various stakeholders including Member States, partners, academic and CSO. They perceived their voices and concerns being considered mostly before and during the forum. The forum is touching/ relevant, and it has to be looked at from high level to the lowest level. The high level could consider and think of it when budgeting and making sure that staff are working / discussing it at different forum.

- Forum is seen as a one-off event as it is dynamic four months before and one month after. Most often, there are no follow up meetings after the forum. Before the forum, actors revise update on what has already been done and they share experience and country good practices during the forum.

- During the forum, resolutions and recommendations are always taken on the basis of discussions where all stakeholders and participants submit their concerns which are analyzed and taken into account whenever they are judged relevant. Non-state actors, CSO, private sector and academics do not consider themselves to be well valued in the forum process (before, during and after). For example, absence at the Monrovia forum of a panel including CSO in specific activities of the nutrition of adolescent girls was recorded. Efforts were made to improve the process with the meeting of partners during the 2017 Bissau forum.

Box 1: Preliminary conclusions – Relevance

REL1: The nutrition forum was found very relevant in addressing the evolving needs of the nutrition and health sectors, and of stakeholders mostly for Member States over the past two decades. This has been expressed through the adoption of national nutrition policy and national nutrition action plans in almost all the 15 countries. Key informants affirmed that the forum is the first and unique initiative in its nature to gather all stakeholders engaged in the nutrition sector such as sectoral ministries of the 15 member States, both technical and financial partners including UNICEF, WFP, NGOs and CSOs. (Par. 67, 68 and 69).

REL2: The forum was designed to and is achieving its intended objectives which are aligned to Member States’ nutrition policies and to the ECOWAS regional nutrition strategies and policies. This include the country nutrition policies, nutrition action plans, and 2018-2025 ECOWAS Regional nutrition strategy. Governance and planning mechanisms are also part of the forum debates. The mid-term review provides an opportunity to assess the level of implementation of recommendations by Member States, and to reflect on the experiences, challenges, and lessons learned. This is helpful to position Member States in the implementation of the Sustainable Development agenda. (Par. 71, 72, 74, 75, 76 and 77).

REL3: Moreover, the ECOWAS Nutrition forum is complementary with other high-level events and platforms such as the Federation of African Nutrition Societies (FANUS), the Scaling Up Nutrition (SUN) of the United Nations, and the Regional Centre of Excellence Against Hunger and Malnutrition (CERFAM). Finally, forum debates involve issues on governance and planning mechanisms. This is helpful to position Member States in the implementation of the Sustainable Development agenda. (Par. 78, 79, and 82).

REL4: The nutrition forum addresses the voices, values and concerns of various stakeholders including Member States, partners and CSO. During the forum, resolutions and recommendations are always taken on the basis of discussions where all stakeholders and participants submit their concerns which are analyzed and taken into account whenever they are judged relevant. (Par. 83, 84 and 85).

### Effectiveness

### Extent to which Forum has achieved its intended outcomes

- The forum has been a tool for lobbying, and it has been very influential. Participants are identified by each country in accordance with the profiles required. These different stakeholders are found at country level in national multi-stakeholder and multi-sectoral platforms, and at the global level in which efforts for dialogue, mobilization, concertation and coordination of nutrition are incurred.

- The Forum has pushed ECOWAS’ governments to adopt specific actions to overcome nutrition challenges such adoption of multi-sectoral nutrition plans and national legislations for its implementation. By gathering member States as well as other nutrition actors, it provides an opportunity to share good practice on advanced efforts/initiatives in the region. Most of ECOWAS countries adopted a national nutrition policy within the past 5-6 years. In 2015, almost all these countries (80%) have a national action plan or a result monitoring framework for nutrition and about 60% of them have a national budget for their nutrition plan as shown in table 6. However, the evaluation couldn’t identify specific evidence on the contribution of the forum towards the achievement of these substantial progress. Key informants affirmed that the forum plays a critical role in the achievement of these results.

# Table 6: Classification of ECOWAS countries by availability of nutrition plan, results monitoring framework and nutrition budget.

| Countries | Nutrition plan available | Results monitoring framework | Nutrition budget |
| --- | --- | --- | --- |
| Benin | Yes | Yes | Yes |
| Burkina Faso | Yes | Yes | No |
| Cape Verde | Yes | Yes | Yes |
| Cote d’Ivoire | Yes | Yes | Yes |
| Gambia | Yes | Yes | Yes |
| Ghana | Yes | Yes | No |
| Guinea | Yes | No | No |
| Guinea-Bissau | Yes | Yes | Yes |
| Liberia | Yes | No | No |
| Mali | Yes | Yes | Yes |
| Niger | Yes | Yes | Yes |
| Nigeria | Yes | Yes | No |
| Senegal | Yes | Yes | Yes |
| Sierra Leone | Yes | No | No |
| Togo | Yes | Yes | Yes |
| Total | 100% | 80% | 60% |

Source: Adapted from the 2015 Forum report.

“In Monrovia, learning on how to harmonise data was very appreciated. The forum is trying in various ways to address this challenge. It is a unique opportunity for key stakeholders to come together to brainstorm on country experiences. Countries like Nigeria are ahead, others are still on the back”

Key informant.

The mid-term review of the recommendations of past forum presents an opportunity for member States to call in-country meetings during which participants assess progress towards the achievement of nutrition targets. In this way, the forum has helped to review gaps for nutrition management with high level coordination mostly led by the directors of nutrition in some countries such as Burkina Faso and Cote d’Ivoire or led by Presidency or Vice-Presidency like in Nigeria where the National Council of nutrition is chaired by the Vice-President.

- Initially, the forum aimed to reinforce capacities of stakeholders, and share of countries experience (actual focus); learning from other country experiences to gain clarification on key concepts. The evaluation founds that the multi-sectoral aspect attached to the nutrition issue is less met by the forum to date, such as the combination of thematic sectors like education, health, agriculture, and nutrition-specific and nutrition sensitive, and development topics.

- The involvement of key partners such as UNICEF, WFP, WHO, FAO; donors such as African Development Bank (AfDB), World Bank (WB), USAID, African Union Commission (AUC); NGO and CSO such as West African Actions Against Hunger and Malnutrition (WAAAHM), CILSS, Helen Keller International (HKI), is very influential. Some participants expect that forum could advocate for nutrition to be part of the foundational learning of the education system starting at the school system to teach children, as they grow and learn, they will practice food habits and practice them. For example,  many adolescents are not in school, therefore while nutrition-specific actions are centered around schools (e.g. school canteen), they need to reach the maximum number of adolescents who are not in schools such as young girls who dropped-out, setting up proximity actions like “Teenagers clubs” to talk for example about early marriage and child marriage.

- The use of resolutions and especially recommendations by all member countries to redirect policies at the level of each country and monitoring the implementation of these recommendations are among other mechanisms by which the results of the forum have contributed to improve national programs and policies.

### Internal and external factors to ECOWAS that contributed the most to the attainment of the Forum’s objectives

- Internal factors that contributed the most to the attainment of the Forum’s objectives include participants’ commitment and motivation to tackle nutrition challenges. The commitment of all participants and their full participation in the forum are factors that most contributed to the achievement of the forum’s objectives. This commitment has been always made possible and the forum has never failed.

- Other internal factors include the availability of ECOWAS policies and legislation that deal with rules and regulations on nutrition issues such as the ongoing 2018-2025 ECOWAS regional strategy for nutrition, existing ECOWAS Nutrition forum Plan, the availability of national nutrition policies and action plans. In Nigeria for example, the National council for nutrition (now called National council for Nutrition and Childhood) previously led by the Prime Minister is now led by the Presidency chaired by the Vice-President.

- Capacity building is also part of internal factors which has contributed most to the attainment of forum objectives. Lot of capacities have been built which were helpful for the harmonisation and mobilisation of nutrition players or actors to work on nutrition issues. Trainings also consider the participation of CSO and parliamentarians.

- External factors include the involvement of traditional leaders for social mobilisation, academic research centers including universities, donors mostly for financial contribution. Collaboration with other high-level events such as the Scaling Up Nutrition (SUN) have been very useful mostly for lessons learned and knowledge sharing on actual nutrition indicators.

### Constraints to ECOWAS in influencing nutrition policies and programming in the region? How can these be addressed in the future

- Number of constraints have possibly impacted nutrition policies and programming in the region. For instance, stakeholders deplore the little follow-up of Forum recommendations (even by e-mail) after each forum. There is almost no meeting until the next edition of the forum apart of the mid-term review meeting which preceed the forum. The evaluation found that the local coordination entrusted to the WAHO Focal point has not happened as expected. In addition, participants believe that there is little discussion on the proofreading of curricula for the improvement of nutrition programming in the region. In fact, the duration of forum does not allow adequate times for capitalization on nutrition improvements and pending issues.

- Moreover, apart of the mid-term review meeting, which is entirely funded by WAHO, the evaluation team found that most of financial resources are derived from external donors or private sector. The commitment of Member States in terms of contribution (annual) is not fulfilled by a number of countries. Only some countries always respect their statutory contributions. However, the evaluation couldn’t find evidence of this internal constraint. There is no funding for monitoring recommendations of nutrition needs.

- Another challenge is linked to the profiles of participants of the forum particularly from the Member States. The selection of representatives is mostly political rather than by nutrition background and competencies. Nomination of staffs at country level brought in the forum most of times new participants who do not have knowledge and experience with existing and/or past nutrition interventions. The immediate consequence is the loss of forum memory from those who were involved before and are no longer working on the same position in their respective countries.

- Furthermore, discussion can be important to bring existing constraints on the table so that Member States can take the lead in managing for example adolescent nutrition challenges and get ECOWAS’ leaders to become interested about the issue. This could assure more ownership of forum recommendations and assessment of how each department ministry can better integrate forum recommendation in planning and financing. There are various opportunities at country level to insert forum recommendations into national planning and financing. For example, every 6 months in Burkina Faso, there is a ministry meeting namely National Committee for nutrition coordination led by the Ministry of Health. Items from the recommendations of ECOWAS forum can be inserted as part of the agenda of these government meetings for follow up.

- The low level of the implication of multi-sectoral coordination is another major challenge. WAHO is now working to push efforts in this way by advocating for more support though a multisectoral vision, the scaling up of nutrition-specific and nutrition-sensitive interventions. Further efforts should be placed to promote and strengthen planning, targeting and implementation of coordinated interventions across key sectors at country and regional levels such as health, agriculture, water, hygiene, sanitation, environment, early childhood development, education, economic growth and social protection. The past 2019 edition of the forum enabled participants to commit on the promotion of the multi-sectoral and multi-stakeholder approach to the fight against malnutrition in the organization of the Forum, with effective participation from nutrition stakeholders and nutrition contributing sectors, and, within the health sector, different subsectors (including sexual and reproductive health); and participation of SUN Focal Points. The agreed decision for more support for the development of a regional accountability mechanism for monitoring existing commitments to nutrition, monitoring the implementation of the regional strategic plan with a call for strong financial and political commitments, look very promising. However, this will need an active coordination from WAHO Focal Point in each country and a participation of the multi-sectoral committee which was found less dynamic due to lack of budget.

- Factors external to ECOWAS in influencing nutrition policies and programming in the region comprise impact of climate change and insecurity in the region. Climate change causes long-term droughts, and endemic diseases such as malaria. The UN Standing Committee reports that Climate change is a long-term challenge to nutrition that needs impending responses. The region is most adversely affected by climate change with millions of people expected to be affected by water stress, and food production being severely compromised if no strategy of adaptation is adopted.

- Moreover, some ECOWAS countries such as Mali, Burkina Faso, Niger, Nigeria face growing insecurity. The nature of violence has changed significantly in West Africa with every case of violence being reported. Many armed conflicts in West Africa have been intrastate conflicts, marked by large-scale conflicts which exposed governmental forces to jihadists’ armed groups. These grounded conflicts might significantly expose population to severe malnutrition and starvation in a short and medium terms.

### Forum’s unintended effects

- There are number of unintended effects which can be attributed to the nutrition forum. The forum succeeds to host influential key stakeholders such as representatives of ECOWAS Parliament, representatives of the Parliamentarian Network for Nutrition, representatives of ECOWAS Commission, and Regional Economic Communities. It has somehow and therefore contributed to better positioning of nutrition in the development policies of the countries, the adoption of national legislations and regulations to foster the implementation of nutrition action plans and provided opportunities to ECOWAS countries to work towards regional/global nutrition goals. The forum has been very influential to the creation and implementation of national nutrition policies in the region. In Nigeria for example, the nutrition policy makes provision of the national council commission given its strategy plan managed by the Ministry of the Budget and National planning, drawn from all relevant ministries, department and agencies that are nutrition related. They came together to adopt what is called the national multisectoral plan for nutrition.

- In addition, the forum helps to pushing the plan to be funded and budget line for nutrition-specific and nutrition-sensitive activities. However, most of activities depend on donor moneys but the forum keeps developing pressure on governments to own and fund the nutrition activities. It is obviously agreed by all stakeholders that if government engages its own funds, then there will be a ground ownership and sustainability on nutrition related achievements.

- WAHO strategic plan aims to support Member States to take actions on nutrition issues. It takes advantages to strengthening country national nutrition plan with the adoption of new concept such as adolescent nutrition, guidelines for national advocacy, fundraising through a specific network such as national committee in food and nutrition. In Burkina Faso and Nigeria, national nutrition committee brings in their individual resources with high level of coordination and they all agree to move according to the nutrition needs of the countries with the contribution of other partners such as UNICEF in the review of University curriculum.

- ECOWAS has prepared strategic document for the development of nutrition in the ECOWAS region such as the ongoing 2018-2025 Strategic Nutrition plan. It is important to note that the objectives of each forum derive from the different themes identified in connection with the strategic orientations from the ECOWAS nutrition forum strategic plan.

### Dissemination of the Nutrition Forum’s reports

- The reports of the nutrition forum are managed by WAHO office. More often, there is secretariat set out by WAHO during each forum. Documents are managed in two steps. Firstly, forum images and photos, presentations including case studies and good practices, deliberations and recommendations are shared immediately to all participants via emails or under a Dropbox link where all forum documents have been uploaded by the secretariat. Participants can have access to the Dropbox link and download forum files when needed.

- Secondly, the forum reports as well as forum mid-term reports are shared later upon drafted and made available to Member States. The reports of the forum are used to take stock of the meeting with decision-makers and hierarchical authorities. Each delegate can later share forum reports with their corresponding organisation upon return to their home-country. The evaluation does not find any challenge regarding the sharing of forum reports. Reports are shared to all relevant forum’s participants. However, internet connection could critically constraint access to these reports on Dropbox as internet is needed specially to download heavy files, videos and photos.

- However, a weak leadership of Member States which is characterised by the absence of accountability has been reported. This could also affect the effectiveness of sharing of forum reports.

### How to better and more consistently track the ECOWAS Nutrition Forum outcomes and the uptake of the recommendations in the future

- Key informants met are all unanimous on the fact that WAHO Focal Point are less dynamic. This is also due to the absence of an assigned budget and working plan for the monitoring of ECOWAS nutrition forum outcomes and update stakeholders on progress towards the implementation of forum recommendations. To date, the mid-term review remains the unique opportunity to track forum outcomes and progress made in each country towards nutrition issues.

- The evaluation identifies areas of improvement to better and more consistently track the ECOWAS nutrition forum outcomes and the update of the recommendations in the future. These include: i) Establishment of a semi-annual monitoring platform of the level of implementation of recommendations by a WAHO monitoring and evaluation unit which can be managed by its Focal point. To this aim, it will be necessary to adopt and strengthen a monitoring mechanism of the implementation of forum’s conclusions and recommendations. This should be transparent and inclusive of all national actors. Ii) The forum should also improve its contribution to the promotion of the multisectoral and multi-stakeholder approach to the fight against malnutrition in the region, with effective participation of the various nutrition sectors and stakeholders including the SUN movement.

- The analysis of WAHO staffing revealed a dominance of Health specialists (55%). To have the Forum as a technical multisectoral platform requires staffs from other sectors to join the team (e.g. Necessity to have a Child protection specialist, nutritionist specialist, Agroeconomics/agronomist).

- It is irrefutable that the forum helps countries to perceive the importance of the nutrition issues when combining their individual challenges. However, many countries have to understand its role with respect to the forum’s recommendations. There is also a need to review country reports on what they commit to as implementing commitment is sometimes not achieved. Involvement of other intersectoral ministries such agriculture, education, and social affairs should be useful.

Box 2: Preliminary conclusions – Effectiveness

EFF1: The forum effectively contributed to its intended outcomes aiming to improve nutrition programming and policies in the region. It calls key actors to consider the integration of nutrition indicators through capacity building sessions. The shared know-how has certainly impacted the adoption of political actions including legislations and regulation for nutrition and health. (Par 87, 88 and 89).

EFF2: Internal factors to the attainment of the forum’s objectives include country’s commitment and motivation to eradicate nutrition challenges, and capacity building through networking; whereas external factors are the involvement of traditional leaders, academic research centers including universities, donors mostly for financial contribution, collaboration with other high-level events such as the Scaling Up Nutrition (SUN). The major internal constraints in influencing nutrition policies and programming in the region include the lack of follow up of forum's recommendations, the limited timeline between two editions of the forum for the capitalisation of nutrition improvements and pending issues, and the absence of multisectoral coordination of nutrition. External constraints to ECOWAS in influencing nutrition policies and programming are impacts of climate change and growing insecurity in the region. (Par 90, 92, 94, 96, 98 and 99).

EFF3: By hosting influential key stakeholders such as representatives of ECOWAS Parliament, representatives of the Parliamentarian Network for Nutrition, representatives of ECOWAS Commission, and Regional Economic Communities, the forum has contributed to number of unintended effects such as better positioning of nutrition in the development policies of Member States, the adoption of national legislations and regulations to foster the implementation of nutrition action plans, and provided opportunities to ECOWAS countries to work towards regional/global nutrition goals. (Par 101, 103 and 104).

EFF4: The nutrition forum has been found effective in the dissemination of forum’s reports. Reports are shared with Member States and key partners (and then share with country offices). Member States always go back with recommendations to share with key local partners for implementation of nutrition action plans at country level. But weak leadership of Member States which is characterised by the absence of accountability has been reported. This could also affect the effectiveness of the dissemination of forum reports (Par 106 and 107).

EFF5: Number of alternative solutions could better and more consistently track the ECOWAS Nutrition forum outcomes and update of the recommendations such as the establishment of a semi-annual monitoring platform of the level of implementation of recommendations by a WAHO monitoring and evaluation unit which can be managed by its Liaison Officers. The forum could also improve its contribution to the promotion of the multisectoral and multi-stakeholder approach to the fight against malnutrition in the region, with effective participation of the various nutrition sectors and stakeholders including the SUN movement There is need to involve other intersectoral ministries such agriculture, education, and social affairs. This also requires having sector staffs at WAHO office. (Par 109, 110, 111 and 113).

### Efficiency

### Forum’s sources of funding

- Attempts were made to obtain as much information as possible on actual costs from 2004 to 2019, but financial information for the 2004 – 2013 editions was not available. Nonetheless, table 7 gives some idea of the overall pattern of cost and source of funding over the past three forums (2015 – 2019). These estimated costs were provided based on assumptions of ‘usual’ or ‘typical’ costs. Based on these figures, the majority of forum’s money come from WAHO (55%). However, partners predominantly funded the 2015 and 2019 editions with respectively 56% in Lome and 53% in Monrovia. Most of times, partners money is used to support for example per diems (WHO in 2015), or communication and meals (FAO in 2017), and/or facilitation fees and sponsorship of forum delegates (UNICEF in 2019). All mid-term reviews are fully funded by WAHO. For example, the Monrovia 2018 mid-term review of forum was entirely funded by WAHO with up to USD76,481.

# Table 7: Distribution of Funding and sources for 2015 – 2019 Foras

| Funding Source | Monrovia 2019 |  |  | Bissau 2017 |  |  | Lome 2015 |  |  | Summary Forums 2015 - 2019 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Amount (USD) | Per cent | Amount (USD) |  | Per cent | Amount (USD) |  | Per cent | Amount (USD) |  | Per cent |
| WAHO | 93,103 | 47.5 | 170,308 |  | 62.7 | 107,206 |  | 43.7 | 370,617 |  | 55.0 |
| Partners | 102,801 | 52.5 | 62,302 |  | 22.9 | 138,009 |  | 56.3 | 303,112 |  | 45.0 |
| Government | 0.0 | 0.0 | 38,873 |  | 14.3 | 0.0 |  | 0.0 | 38,873 |  | 5.8 |
| Total (USD) | 195,904 | 100.0 | 271,482 |  | 100.0 | 245,215 |  | 100.0 | 673,729 |  | 100.0 |

Source: WAHO.

- Other contributors include WFP, USAID, AfDB, World Bank, and African Union Commission. Unfortunately, WAHO does not have accurate information on the expenditures sponsored directly by all partners. WAHO affirms that there are wide disparities in the financial contributions between forums given the fact that some partners fund their participation. The evaluation couldn’t find information on travel costs which account for more than 30% of forum’s budget.

- Countries are not requested to fund their own participation in the forum. They are always supported by WAHO or Partners. Host country may contribute their own funds to support the forum organization. According to WAHO, Lome (2015) and Ouaga (2012) replaced the scheduled host countries at short notice and were unable to provide their own dedicated funds to support the Forum.

- Most times, UNICEF and WFP provide technical assistance for the preparation of the forum. Intrinsic capacity of states to operate WAHO is very weak. WAHO liaison Officers do not have formal funding mechanism to facilitate follow-up on recommendations. Moreover, various forum recommendations stopped working when the funding ended. For example, there is no continuity of initiatives like nutrition framework development that each country can adapt as well as the Salt project (to regulate salt iodization and set standards), because of lack of money.

### Alternative strategies to achieve the same level of results but at a lesser cost and measures to increase the value for money of the ECOWAS Nutrition Forum

- Number of alternative strategies could be helpful to deal with the foregoing challenge. Stakeholders believe that synergies of actions with other existing platforms such as the SUN and CERFAM could be helpful in achieving similar results at lower costs. Moreover, the partners remain committed to supporting the ECOWAS Member States in the quest for a solution to the challenge of malnutrition and the achievement of the Sustainable Development Goals (SDGs) by 2030. They emphasised the need to step up funding with support from all institutions and agencies, especially the World Bank, AfDB and UN Agencies.

- In the absence of specific fundraising mechanism for the forum, people met believe that attention should be paid on continued lobbing and advocacy for a multisectoral coordination mechanism to address jointly agricultural, nutrition, health and education needs.

- Key informants raised that Member States do not have sufficient time to assess improvement towards the nutrition indicators within a year. They advocate for a shift on the timeline between two editions of the forum from 2 to at least 3 years. Having only a year to measure updates on nutrition indicators is very limited. Member states may not have time to implement forum recommendations. These recommendations need to be planned, budgeted and adopted by sectoral ministries before their implementation. Moreover, data collection of nutrition indicators takes lot of times. The completion of surveys or nutrition studies on food security, food consumption, livelihood-based coping strategies requires many months and can take a year for large countries like Nigeria, Mali or Niger. Other stakeholders believe that a reduction of the number of presentations will allow more time for the presentation of country case studies and best practices.

### Alternatives to the Forum design and implementation in order to achieve more value for money

- Usually, forum’s theme and content are adopted during the preceded edition. It follows a participative process during which facilitators brainstormed participants on what they would like to cover in the next forum. During each forum, a moderator panel is set to facilitate all sessions. It is composed by representatives of 2 – 3 countries on a rotative basis and they chair the overall forum presentations and discussions. The forum duration moved from 5 to 3 days since its 14th edition held in 2015 in Togo. This was largely due to insufficient financial resource to cover more days. Most often, the forum agenda is organised as follows: i) Day One: Status of implementation of previous recommendations in different ECOWAS member countries, follow by technical update on food security and nutrition in West Africa (opportunities and challenges);  ii) Day Two: Countries’ experiences in food and nutrition, followed by Group work on priority actions for addressing food security and nutrition in ECOWAS member countries; and iii) Day Three:  Regional initiatives aimed at addressing the issue of food insecurity and malnutrition in the sub-region, Sector meetings of different forum actors (partners, country delegations and local delegation); and the elaboration and validation of the recommendations of the forum.

- While WAHO acknowledges the need for a multisectoral coordination of each forum, the content of forum deals less with joint multisectoral debates. A part of the 2010 edition held in Cote d’Ivoire which advocated for the planning and funding of multisectoral nutrition programmes in the ECOWAS region, other forum’s editions addressed different themes. The internal management tend to deviate nutrition objectives to mostly health sector, rather than integrating rural development factors which embrace agriculture to deal with food security which might support access to food of vulnerable groups.

- Key informants are unanimous about the fact that Forum content would be more relevant if it covered multisectoral themes in each edition. Even the national Committee for nutrition argues that someone with agricultural background is needed to deal with the engagement of sectoral ministries. Increasing investment in the nutrition sector requires that the forum is elevated to high level such as assembly of ministers or presidency like in Nigeria and Cote d’Ivoire which is very useful to hold country delegates to be accountable on forum’s recommendations.

- The evaluation team noted that collaboration between UNICEF and WAHO regarding the promotion of the nutrition forum is limited to the UNICEF regional office. Most UNICEF country offices are less knowledgeable about the forum and/or are less involved. The UNICEF regional office assists the forum technically with the organisation of conference thematic content, and financially by sponsoring selected country delegates depending to the availability of funds. This collaboration between WAHO and the nutrition section of UNICEF WCARO would have been extended at country level to enhance the quality of country presentations.

- Strong collaboration with partners like FANUS and SUN appears to be necessary. This could help budget tracking and in developing advocacy briefs to be used to confront and engage with leaders. SUN support could be useful to advocate for adopting stronger, evidence-based nutrition policies at global, regional, and country levels, pledging to increase financing for proven nutrition-specific and nutrition-sensitive interventions, and influence commitment to align and harmonize actions across sectors and stakeholders.

- In addition to a better preparation ahead before going to forum, key informants argue that more focus on online meeting to assess what was not done well, and why could lower the costs of nutrition forum. There is a need to have some technical papers on key subjects: on adolescent health and nutrition, people who have data should be invited to come and present what they have especially on the adolescent health and nutrition in terms of research data on this specific topics; which could be useful to address what is missing.

Box 3: Preliminary conclusions – Efficiency

EF1: Financial information of forum’s money from 2004-2013 was not available apart of the 2015, 2017 and 2019 editions. Based on the overall pattern of cost and source of funding over the past three forums (2015 – 2019), the forum’s financial resources come largely from WAHO (55%). Most of times, partners money is used to support for example per diems (WHO in 2015), or communication and meals (FAO in 2017), and/or facilitation fees and sponsorship of forum delegates (UNICEF in 2019). Other contributors include WFP, USAID, AfDB, World Bank, and African Union Commission. Unfortunately, WAHO does not have accurate information on the expenditures sponsored directly by all partners. WAHO affirms that there are wide disparities in the financial contributions between forums given the fact that some partners fund their participation. All mid-term reviews are fully funded by WAHO. (Par 114 and 115).

EF2: Alternative strategies in increase the value for money of the ECOWAS nutrition forum include the revision of the timeline between two editions of the forum from 2 to at least 3 years, more attention on continued lobbing and advocacy for a multisectoral coordination mechanism to address jointly agricultural, nutrition, health and education needs; fundraising mechanism; and more synergies of actions with other existing platforms such as the SUN and CERFAM (Par 117, 118 and 119).

EF3: In order to achieve more value for money, Forum content can be revised to always cover multisectoral themes commonly. More focus can be paid on online meeting to be better prepared ahead before going to forum with the aim of assessing what was not done well, and why. There is a need to have technical papers on key subjects such as adolescent health and nutrition, and people who have data should be invited to come and present findings on relevant nutrition related research topics which could be useful to address what is missing. Increase investment in the nutrition sector require that the forum needs to be elevated to high level such as assembly of ministers or presidency like in Nigeria and Cote d’Ivoire which is very useful to hold country delegates to be accountable on forum’s recommendations. (Par 120, 121, 122, 123, 124 and 125).

### Sustainability and ownership

### Extent and ways to which the capacities of stakeholders could be enhanced in order to sustain the Forum’s results

- The comparative advantage of nutrition forum is very high given its focus on capacity building and networking platform for stakeholders. It brought key persons on nutrition in their respective countries to brainstorm, share lessons and disseminate findings. These can sustain the forum recommendations at national level. Therefore, its impact is positive, which could facilitate the fundraising process. The forum brings a lot of partners, NGO and CSO from diverse sub-field of nutrition: has sensitised partners on how they can channel the activities, and why key support is needed for e.g. adolescent health and nutrition.

- From 1996 to date, the Forum provides capacity building opportunities to government, CSO and NGO representatives with the aim of sustaining their skills. Greatest attention was paid on networking among participants so as to create a learning environment for knowledge sharing and exchange of information. Participation of government officials was very high, and it was their responsibilities to select key nutrition focal points to attend the forum. Due to political influence, the profile of some country delegates was challenging. It is not sure whether those representing country are the good targets. Government change and internal nomination of staffs largely influence the follow up of forum recommendations as those knowledgeable about the forum have left or move to other positions.

The evaluation found that Member states do not yet own the capacity building aspect of the nutrition issues to continue provide trainings and promote careers progression. They need more nutrition training capacities to boost for example careers of extension workers, researchers and staffs. Training component and content could be translated in a digestible language with an evidence-based generation of information: pushing to have routine data collection at the health center (food and nutrition demonstration, etc).

“Capacity building through networking provides an added value to the ECOWAS Nutrition Forum. Most people affirmed that it is a unique opportunity to partner and liaise with other nutrition colleagues.”

it is expected that more advocacy emphasis on best practices from countries could be necessary. Their impacts on the implementation of selected national nutrition policies including their action plans could help other countries to make progress. In addition, more emphasis will be welcomed on programs that are sustainable with focus on teaching adolescent on appropriate food systems or how to cook their foods. E.g. Issues like women of reproductive age and breastfeeding women need more visits and assistance to address health and nutrition problems at the grassroot levels.

### Level of stakeholder engagement in the Forum’s organization

- The level of Member States’ engagement in the forum’s organisation remains very good.  Participation of Member States is always more than 50% of total participants (56% reached during the 14th edition held in Lomé-Togo). The average number of participants is 136.

- The level of engagement of stakeholders in the forum’s organisation either financially or technically is relatively appreciative. For instance, partners are relatively engaged both technically and financially. Key informants affirmed that the Bissau case was a good experience to valorise nutrition issues in West Africa. Whatever WAHO is able to fun entirely the forum’s mid-term review and provide more than 50% of forum’s expenses, the evaluation couldn’t verify the level of commitment of Member States to the forum in terms of respect of their statutory contribution which might negatively affect the participation of Member States. CSO’s participation is limited as they cannot afford the cost of attendance.

- The evaluation team found that sectoral ministries are fully engaged. These include mostly ministries of health and agriculture. Their efforts are limited by the insufficiency of financial support for local nutrition initiatives. Low country financial contribution doesn’t necessarily mean low engagement of member states. Most country priorities are focused on child nutrition and on early child development rather than on adolescent nutrition. Moreover, number of countries are affected by contextual factors such as humanitarian crisis like Burkina Faso, Niger and Mali. These growing challenges can greatly affect their engagement and financial contribution to WAHO.

### Extent to which the ECOWAS Nutrition Forum and related events are included in national or partner event calendar planning

- There are various ways to asses to adoption of the ECOWAS Nutrition Forum in national and partner event calendar planning. The first evidence of ownership is country financial engagement to nutrition related activities or to forum recommendations. If they can get in own money, therefore they will be able to decide where to invest and how to feel the gaps.

- Perception change on the nutrition issue includes the increase involvement of partners with both technical and financial supports. The forum provides more awareness to Member States on the need for existing national nutrition policy and action plan. But the appropriation is very weak without budget for activities. More often, country budget is for the operations. They are working on what exist rather than working on what doesn’t exist (research).

- Real change requires strong and long-term partnership with partners, NGOs and CSOs, to support country-led interventions. In some countries, nutrition country-led initiatives are very advanced such as in Nigeria where forum concern is considered in national event calendar planning. However, the ministry of budget and planning still has to coordinate all intervention. Partners adapt on what countries want to achieve and therefore, forum recommendations could be sustainable only if partner funding is used appropriately.

- Each ministry (health, nutrition, agriculture) has nutrition components with specific activities to be performing, but issue is when it comes to allocating money. Many countries such as Burkina Faso and Liberia have built capacities a lot, but implementation failed due to lack of money particularly for training assistance such coordination of extension services at the local areas. This needs champions at the highest level possible to advocate for budgetary allocation for nutrition such as first ladies and presidency. WAHO could reinforce its collaboration with existing nutrition platforms such as SUN movement and CERFAM for more advocacy on knowledge sharing on nutrition issues. A close collaboration between WAHO and these platforms will be helpful in avoiding duplication of roles and interventions.

Box 4: Preliminary conclusions – Sustainability and Ownership

ST1: The Forum provides capacity building opportunities to stakeholders during each edition as they commonly share country case studies, best practices, innovative achievements on nutrition issues, and brainstorm on desired recommendations. Attention was paid on networking among participants so as to create a learning environment for knowledge sharing and exchange of information. Participation of government officials was very high (above 50% all the time). This impacts the implementation of national nutrition policies as well as legislations for their action plans. (Par 126, 127 and 128).

ST2: The mid-term review meeting is entirely funded by WAHO. However, the forum has been always funded by shared sources. Technically, Member States always show greatest engagement for networking and nutrition knowledge sharing. Their participation is above 50% of all participants. But their capacity remains very weak due to weak leadership and absence of accountability. Most country priorities are focused on child nutrition, on early child development, or on the management of humanitarian crisis occurring in the region rather than on adolescent nutrition. (Par 129, 130 and 131).

ST3: The forum objectives are most often derived from national nutrition policies. However, follow up on recommendations are missing most of the time. The ownership is limited by lack of budget to support further nutrition events at country level. Therefore, country financial engagement remains very weak. (Par 132, 133 and 135).

### Gender, human rights and equity

### Extent to which Gender, Human rights and Equity principles are considered in relevant technical discussions and recommendations by the ECOWAS Nutrition Forum

- The review of forum’s reports and key informant interviews disclose a mixed gender profile of forum participants.  Most times, female participants prevail. Greater participation of women could lead to promoting greater gender equality, including increasing women’s control over Forum’s nutrition discussion and their ability to make decisions.

- Nutrition is considered as a fundamental human right for all children and adolescents in the ECOWAS Nutrition fora. All technical themes and subthemes of each forum consider gender and equity concerns, vulnerability assessment for mostly adolescent pregnant girls, poor women and child nutrition. For example, the 2019 edition of the forum held in Monrovia argue about current state of adolescent malnutrition and diet-related diseases, risk factors, consequences, co-morbidities and current response in the region; the evaluation of the current (nutrition-specific and nutrition-sensitive) policies, programmes, interventions and best practices to improve and sustain adolescent nutrition in the region; explore mechanisms for strengthening health systems and financing for adolescent nutrition. Many indicators can attest the inclusion of human rights and equity principles. Even by the theme of each forum and in every discussion, these concerns were mentioned. Addressing nutrition issues also means that participants are addressing the human rights (for vulnerable groups) and gender concern.

“Nutrition is a fundamental human right concern for all children and adolescents. It is gendered as it covers both boys and girls’ needs for better feeding capabilities.”

A key Informant

In the 2008 edition in Sierra Leone, the central theme “Food Security and Nutrition” was mostly focused on women empowerment. This was an opportunity for women's empowerment particularly in the context of food security and nutrition in West Africa. Gender equality and women's economic empowerment are a key prerequisite to ensuring the right to adequate food, achieving food security and improved nutrition for all, and ultimately for realizing the 2030 Agenda. Forum discussions greatly support the concern of vulnerable groups such as child nutrition with issues like breastfeeding for child nutrition (with focus being placed on children less than 5 years), adolescent health and nutrition for both boys and girls.

### Extent to which the opinions and needs of different groups (men, women, boys and girls), and particularly the most vulnerable, are taken into consideration when deciding and acting upon the ECOWAS Forum recommendations

- The opinions and needs of different groups (men, women, boys and girls) and particularly the most vulnerable are taken into consideration during forum debates and when deciding and acting upon the ECOWAS forum recommendations. Case studies and good practices shared by participants derived from national and regional initiatives which were made off sensitive topics such as child nutrition mostly for those under 5, adolescent health and nutrition for both girls and boys, people with handicap such as displaced population in countries affected by humanitarian crisis like Burkina Faso, Mali and Niger.

- Forum deliberations consider the opinions and needs of these targeted groups in forum recommendations. These can be viewed in some advocacy themes elaborated, agreed and debated during nutrition fora as follow: i) Institute social protection measures including conditional transfers, national health insurance to reduce barriers to access by out-of-school and indigent adolescents (for both girls and boys); ii) Increase priority of funding to adolescent health and nutrition programmes; iii) Provide platform for adolescents to express their needs and aspirations through the use of youth ambassadors and champions; iv) Institute appropriate programmes to reach and build the skills of out-of school, institutionalized and indigent adolescents; v) Support countries to integrate indicators on adolescent nutrition and health in national surveys (DHS, MICS, SMART), especially 10-14-year-olds; and vi) Re-affirm political will and mobilize resources from national and international institutions in order to accelerate the fight for the Food Security and for the control of Malnutrition.

### Extent to which the discussion held during the Forum cover the barriers to services for boys and girls

- In addition to the aforementioned findings, the forum shows greatest consideration for the barriers to services for boys and girls. Issues like child education (boys and girls) is gaining the overall discussion with the needs to protect the rights of vulnerable boys and girls within the ECOWAS region.

- Moreover, discussion themes expose for more consideration of the nutrition concern about adolescent boys and girls on the right platform. Participants agreed to see more commitments for example during presentations from the sensitisation and awareness received from previous fora. It is expected that a lot of improvement policies on the barriers to services for boys and girls from all countries will be always shared during nutrition forum. These could include more interventions on adolescent nutrition (reproduction health), focus on improving breastfeeding for adolescent girls and pregnant young women, complementary foods and feeding practices for adolescent boys and girls.

- Forum recommendations highlighted above show that the barriers to services for boys and girls are covered during the ECOWAS Nutrition forum.

Box 5: Preliminary conclusion – Gender, Human rights and equity

GHE 1: Gender, human rights and equity principles are considered relevant during technical discussions and they are part of forum recommendations. Participant of the forum are gendered with most times the dominance of women. The nutrition forum addresses the human rights of target groups which are children and adolescent boys and girls. (Par 136, 137 and 138).

GHE 2: The forum is always successful in addressing the opinions and needs of the different groups (men, women, boys and girls) and particularly the most vulnerable. The ECOWAS Nutrition Forum was even created to advocate for the needs of these target groups. Their needs are part of all deliberations and recommendations. (Par 139 and 140).

GHE 3: The forum always covers the barriers to services for boys and girls. Topics like girls-child and boys-child education, and adolescent nutrition are discussed during forum and participants agreed to see more commitments to protect the rights of boys and girls within the ECOWAS region. (Par 141, 142 and 143).

## Final Conclusions

- Based on the findings of the evaluation the evaluation team has developed the following conclusions.

Relevance

- The ECOWAS Nutrition Forum is highly relevant to enabling the ECOWAS Member States in addressing the priorities related to evolving needs of the nutrition and health sector in West Africa. While providing an opportunity to all the 15 Member States to adopt and validate country nutrition policies and action plans, the forum objectives are aligned to key priorities inserted in these nutrition policies. Furthermore, it is also aligned with the 2018-2025 ECOWAS Regional nutrition strategy. The forum is an opportunity for networking between stakeholders, sharing regional and national experiences and strategies which are part of both national and regional nutrition policies. The mid-term review which precedes the forum itself provides an opportunity to Member States to review forum recommendations. The evaluation team found that the Forum is complementary with other high-level events and platforms such as the Federation of African Nutrition Societies (FANUS), the Scaling Up Nutrition (SUN) of the United Nations, and the Regional Centre of Excellence Against Hunger and Malnutrition (CERFAM). The forum has been found relevant to address issues on governance and planning mechanisms, which is helpful to position the Member States in the implementation of the Sustainable Development Goals (SDGs). (REL1, 2 & 3))

Effectiveness

- The evaluation found that the forum was very effective in addressing its objectives. More emphasis has been paid on the advocacy for adequate nutrition policies, action plans and fundraising mechanisms. It therefore offers a regional space to boost the nutrition issues which is almost unique. It offers a great networking opportunity for all stakeholders engaged to share current trends and challenges to nutrition concern in the region. Gathering people who are knowledgeable, developing program which should be incorporated into nutrition program for governance and research has been well valued. Moreover, the forum is focused on learning by calling nutrition stakeholders to look at coordinated mechanism for nutrition research and knowledge sharing. The evaluation team found that the forum has contributed to number of unintended effects such as positioning of nutrition in the development policies of Member States, the adoption of national legislations and regulations to foster the implementation of nutrition action plans, and provided opportunities to ECOWAS countries to work towards regional/global nutrition goals. However, it was less successful in addressing the multisectoral coordination of nutrition interventions in the region. (EFF1 and EFF2)

- The effectiveness of the forum in achieving its objectives was facilitated by country’s commitment and motivation to overcome the nutrition challenges, and capacity building through networking. This was supported by external factors such as the involvement of academic research centers including universities, donors mostly for financial contribution, and collaboration with the SUN. However, the lack of follow up of forum's recommendations, the limited timeline between two editions and the absence of multisectoral coordination of nutrition were found as major internal constraints. The ongoing insecurity in some countries and climate change effects could negatively impact the implementation of nutrition policies and programming. (EFF2).

Efficiency

- Due to the absence of the forum’s financial reports from 2004-2019, the evaluation team couldn’t properly assess the forum’s efficiency. Nonetheless, financial information of the past three forums (2015 – 2019) reveals that forum’s financial sources come largely from WAHO (55%). Most of times, partners money is used to support for example per diems (WHO in 2015), or communication and meals (FAO in 2017), and/or facilitation fees and sponsorship of forum delegates (UNICEF in 2019). Other contributors include WFP, USAID, AfDB, World Bank, and African Union Commission. Unfortunately, accurate information on the expenditures sponsored directly by all partners are not available. The evaluation found that there are wide disparities in the financial contributions between forums given the fact that some partners fund their participation directly. However, it was confirmed that WAHO funds entirely the mid-term review meeting. The coordination mechanism is being managed by WAHO with less synergy with other existing platforms such as the SUN movement which could enhance the forum’s efficiency given that each of these platforms has a comparative advantage to deal with nutrition challenges in West Africa. The forum’s timeline was found limited to enable Member States to generate evidence-based follow up on forum recommendations. For example, the FANUS is a four-year nutrition event. Its timeline seems to be suitable to enable Member States to implement the event’s recommendations. (EF1, 2 and 3))

Sustainability and Ownership

- The forum is sustainable given the alignment of its objectives to national and regional policies. The forum’s ownership by Member States is relatively good. The capacities of stakeholders such as the government, CSO/ NGOs have been enhanced in order to sustain the Forum’s results with networking opportunities. Participation of key officials such as parliamentarians, ministries, vice-presidency and presidency representatives could continue support the implementation of existing legislations and regulations as well as the adoption of news legislations. Member States always show greatest engagement for networking and nutrition knowledge sharing. Number of countries are affected by contextual factors such as humanitarian crisis like Burkina Faso, Niger and Mali. This situation can negatively affect their financial participation to WAHO activities and therefore to the Nutrition Forum. (ST1 and 2)

Gender, Human rights and equity

- The forum has been successful in addressing gender, human rights and equity principles during technical discussions. Nutrition forum is all about human rights’ defense particularly for vulnerable targets such as adolescent boys and girls, women in social distress and those of reproductive age, and people with disabilities. The participation is gendered and female, and discussions always cover the opinions and needs of the different groups (men, women, boys and girls) and particularly the most vulnerable. Topics like girls-child and boys-child education, and adolescent nutrition were helpful to cover barriers for boys and girls. These needs are also covered by forum’s recommendations. (GHE 1, 2 and 3)

## Recommendations

- The recommendations presented in table 8 are based on findings and conclusions of the evaluation as well as on the active consultation with key stakeholders which were interviewed during the in-country visits. Each interview verified the perceptions of various stakeholders concerning the main recommendations in assisting the ECOWAS Nutrition forum to discourse their needs. These recommendations are addressed to WAHO as it was entrusted the management of the forum. It is expected that a validation meeting with the reference group of this evaluation will be organised to review these recommendations.

# Table 8: Strategic and operational recommendations

| No | Conclusions | Recommendations | Priority level |
| --- | --- | --- | --- |
| Strategic recommendations (SR) |  |  |  |
| SR1 | EF1, EF2 and EF3 ST1 and ST2 | The forum should advocate for increased leadership, fundraising and accountability of the Member States by. - Share the dashboardsof countries who committed to provide financial contribution to WAHO during the Ministerial Council. This could activate the accountability line of Member States, and influence their willingness to continuously funding WAHO action plans. - Share Scorecards on results for countries to see where they are relative to others. - Involve high-level officials (Presidency) to further boost the interest on the nutrition (inviting States to own the forum by planning budget for the participation of their delegates). - Update Member States on progress made towards implementing forum recommendations with more focus on country-led initiatives to enhance their accountability. | High |
| SR2 | REL1, REL2 & REL3, EFF1 and EFF2, ST1 and ST2 | The forum should increase advocacy efforts for the review of the nutrition curricula and the framework of nutrition indicators in the regions by. - Mainstream health and nutrition package at all level including trainings at school, vocational training centers as well as at the university levels, with the aim of strengthening the capacity of both future generation of nutrition specialists and those vulnerable recipient groups in remote and very remote locations. - Unify framework of member countries: E.g. Management of nutrition indicators into programmatic information systems (DHIS2) and surveys, opportunity for countries to harmonize needs and adapt national actions | High |
| SR3 | EFF1 and EFF2and EF1, EF2 and EF3 | WAHO should always push for a multisectoral coordination of nutrition at each forum by: - Jointly combine multisectoral sectors such as the WASH, nutrition, health, agriculture, education and social protection sectors in forum’s debates. - Continue involve country’s multisectoral platform such as National Council of Nutrition who assure the multisectoral coordination of nutrition at country level - Work closely with CERFAM to share its achieved research findings on pathways to eradicating malnutrition. | High |
| SR4 | EFF1 and EFF2, EF1, EF2 and EF3 | WAHO should continuously working for a strong collaboration with the Scaling Up Nutrition Movement (SUN): - This could be benefit for advocacy on country fundraising as the SUN is institutionally attached to High-level political spheres such as Vice-Presidency and/or Presidency level in each of the ECOWAS countries. - WAHO will therefore improve the image of the SUN given its advanced technical expertise in health and nutrition in the region. - SUN Movement Focal Point could be the actor who can influence the Ministry of health to provide follow up on forum recommendations (SUN discusses with Heads of State, and therefore it is very influential). | Medium |
| Operational recommendations (OP) |  |  |  |
| OP1 | EFF1 and EFF2 | WAHO should advocate for preparation, review of the forum length and content to achieve more value for money: - More focus should be placed on online meeting to be better prepared ahead before going to forum with the aim of assessing what was not done well, and why. - Forum’s duration should be reviewed from 2 to 3 years basis to allow more times to Member States and other stakeholders to complete improvement on nutrition priorities and better address the forum’s recommendations - Need to have technical papers on key subjects such as adolescent health and nutrition and invite people who have data to come and present findings on relevant nutrition related research topics which could be useful to address what is missing. | Medium |
| OP2 | EFF1 and EFF2, and ST1 and ST2 | WAHO should assure a follow up of forum’s recommendations at country level rather by: - Monitor WAHO’s Focal Point roles and responsibilities in managing the follow up of forum’s recommendations. | Medium |

## Lessons learned

Several lessons emerged from the evaluation findings amongst which the followings have been selected:

- Having a networking platform such as the ECOWAS Nutrition Forum can positively influence Member States involved in the adoption of nutrition or other sectorial policies, action plans as well as the legislations for their implementation. By gathering Member States during each edition of the Forum, good practices from more advanced countries provide a learning opportunity to less advanced countries to adopt appropriate measures to deal with nutrition issues.

- By offering equal opportunities to all stakeholders mostly to the Member States to work towards the solutions for nutrition concern, the forum was very helpful to gather common efforts towards measures for fundraising and partnership development within the ECOWAS region. It has an advantage of preventing duplication of nutrition interventions including funding.

- By aligning its objectives to those of ECOWAS Regional Nutrition Strategic Plans and National Priorities, the forum makes a difference and always attract the participation of relevant stakeholders such as technical and financial partners, High-level officials from ECOWAS and Member States.

- As a multisectoral platform, the success of the ECOWAS’ Nutrition Forum requires the participation of diverse individuals and organisations’ profile such as health, nutrition, education, Wash, agriculture and social protection. Participants always belong to most of these basic development sectors. Therefore, participation is inclusive of public and private sectors, NGOs, CSOs, technical and financial partners.

- The nutrition forum bridges Member States on a unique concern which is the fight against malnutrition in West Africa. It therefore calls them to combine efforts by supporting the design and implementation of both national and regional nutrition strategic policies and action plan.

## Annexes

### Annex 1: Evaluation Terms of References (ToRs)

TERMS OF REFERENCE

Summative/Formative Evaluation of the ECOWAS Nutrition Forum

Home + Travel to Liberia and Burkina Faso

| Section | Content |  |
| --- | --- | --- |
| Objectives | This evaluation will have two purposes: accountability and learning. This evaluation will provide both the members states and financial partners (vertical accountability) and the participants (horizontal accountability) and evidence on the extent to which the ECOWAS Nutrition Forum contributed to the nutrition discourse in the ECOWAS region. With respect to learning, this evaluation is expected not only to inform the Forum implementation strategy in the years to come but it will also shed light on some potential corrective actions that may want to be explored further in the future. More specifically, this evaluation is expected to generate recommendations that will help UNICEF, ECOWAS and their partners to adapt the Forum to the emerging needs. Table 1: Intended Users and Uses of the Evaluation Evaluation Users; Evaluation Uses. ECOWAS; Better adapt the forum design and activities to address emerging issues and needs in the sector of nutrition as well as improve accountability and tracking of recommendations implementations in countries.. Technical and financial partners (including UNICEF Regional Office for West and Central Africa); Tailor its contribution to the Forum so as to make it more effective and efficient during the next Forum editions Put into practice the lessons learned into the organization of other nutritional regional coordination events/fora which is expected to coordination in the region and sub-region. Member States; Enhance the effectiveness of the coordination with each other Diversity the modalities of contributing to the event Make their participation more results-oriented in the future. In-country partners and other participants of the Forum; Enhance a better alignment of their respective initiatives, especially in the areas which the Nutrition Forum focuses on from time to time.. The specific objectives of this evaluation are to: - Assess the relevance, effectiveness, efficiency and sustainability of the ECOWAS fora organized over the last 6 years. - Assess the extent to which the organization of the forum has been conducive to meet its organizers ’and participants’ expectations, especially in terms of process, planning, stakeholder engagement pre-forum, stakeholder participation, methodology, and final recommendations. - Draw lessons learned about what has worked and did not work in respect to the ECOWAS Nutrition Forum including unexpected outcomes (positive and negative). - Document the Fora costs and sources of funding. - Identify gaps and make specific actionable recommendations to the expected evaluation users (see table above) Strategic and operational recommendations are expected to provide guidance to the recipients on how to - Increase the efficiency and effectiveness of future fora; - Enhance ownership by all major stakeholders; and - Make future for a more responsive to the region’s nutrition and food security situation. |
| Background | Globally, undernutrition is the underlying cause of nearly half of the deaths in children under five years of age. Stunting, also called chronic undernutrition, deprives children of their intellectual potential and robs countries of human capital. Despite some progress made in the past decades, the undernutrition levels in the ECOWAS region remain among the highest in the world. The ECOWAS Nutrition Forum provides a regional platform for multiple stakeholders to analyze the nutrition-related problems in the sub-region, review progress in addressing undernutrition in all its forms and towards the attainment of international targets as well as share best practices. The Forum was previously evaluated in 2003 following a recommendation at the 6th annual meeting of the then ECOWAS Nutrition Network (September 2001, Accra). The evaluation sought to document the evolutionary process through which the regional network was formed and is operating. The evaluation also highlighted the network major milestones and accomplishments and assessed any direct or indirect impact on nutrition policy and programming, human capacity building and institutional strengthening in the region and beyond. Sixteen years after the first evaluation of the Forum and following the many changes that the Forum as well as nutrition policies and programming in the region underwent, the ECOWAS requested the support of UNICEF to finance, provide technical support and conduct the recruitment of the consultants for the evaluation. The Economic Community of West African States (ECOWAS) Nutrition Forum has become the flagship nutrition event in the Region in recent years. The Forum started in 1996 as the West Africa Nutrition Focal Points network based on recommendation by the Ministers of Health of 9 francophone West African countries. The aim was to provide a consultative platform for solving the nutrition problems in the region. In 1999, the network was extended to cover all ECOWAS Member States. After its establishment in 2000, the West African Health Organization (WAHO) started coordinating the Forum in 2001. Initially, the meeting frequency was annual but became biennial in 2004. The Forum lasts for 3 days. Typical attendees include technical high-level staff from the Ministries of Health, financial and technical partners (UN agencies, NGOs, etc.). These fora provide ECOWAS Member States and Partners with an opportunity to brainstorm on nutrition problems affecting the sub-region, share experiences and best practices on nutrition, develop a common vision of the nutrition profile of the sub-region, identify financing mechanisms, review the implementation level of past Forum recommendations, and provide a technical update to participants on topical issues. Financial support for this event comes from ECOWAS and nutrition partners (Donors, UN agencies and international NGOs). Thirteen ECOWAS Member States have hosted the Nutrition Forum since its inception, with Liberia and Nigeria being the only countries yet to host it. Typically, the Nutrition Forum is made up of Opening and Closing Ceremonies; Media briefing / Ad hoc interviews; Exhibition of nutrition achievements and products; Delegates’ group meetings, Social events (welcome cocktail, diner gala, tourist visits) and a Technical session. The technical update session comprises: - country presentations on nutrition sector developments (which includes also key points regarding the implementation of the recommendations and the action plan from the last Forum and countries’ experiences); - a review of nutrition initiatives in the region; and - technical presentations related to the conference theme. Panel discussions on different topics are also organized, as well as group work on topics of current relevance to nutrition in the region. There is also a formal anonymous participant appraisal of each Forum which aims to improve the organization of future fora. The last event, the 15th ECOWAS Nutrition Forum was held in Bissau, Guinea-Bissau in October 2017. As usual, a regional mid-term review meeting was organized to review progress in the implementation of recommendations of the preceding Forum by Member States, WAHO and Partners. The last mid-term review took place in November 2018 in Monrovia. The preliminary dates for the 16th ECOWAS Nutrition Forum to be held in Monrovia are the 12-14 November 2019. The objectives of the 2019 Nutrition Forum are defined as follows: - To update participants on the regional nutrition situation and current initiatives. - To review the current state of adolescent malnutrition and diet-related diseases, risk factors, consequences, co-morbidities and current response in the region. - To evaluate the current (nutrition-specific and nutrition-sensitive) policies, programmes, interventions and best practices to improve and sustain adolescent nutrition in the region. - To explore mechanisms for strengthening health systems and financing for adolescent nutrition. - To analyze existing surveillance systems and the needed information on adolescent nutrition in the region. |  |
| Scope of Work |  | Thematic Scope: The evaluation is expected to assess the ECOWAS Nutrition Forum from several perspectives. Specifically, it will assess the influence of the Forum on the adoption of adequate policies and strategies at regional and national levels as well as the quality of nutrition programming and workforce at national and lower levels. Secondly, it will examine the Forum from a process perspective in respect to its organisation and to roles and responsibilities of different stakeholders. Finally, the evaluation will provide information on the Forum funding arrangements. The evaluation is expected to cover also the mid-term reviews and their contribution to the results of the ECOWAS Nutrition Forum. Geographical Scope: The desk review conducted as part of this evaluation will cover the contributions provided to the Forum by all the 15 ECOWAS Member countries (available syntheses on national nutrition policies and strategies can be used for this purpose). The primary data collection (key informant interviews, surveys, etc.) should cover all the ECOWAS member States (and their respective participation/contribution to the Forum) to the extent possible. Field visit to up to 4 countries (among which Liberia, where the Forum is taking place in 2019 and Burkina Faso, to meet the organising WAHO team) will be arranged. The selection of the countries to visit will be based on strong rational (level of contribution to the Forum from countries for instance). Chronological Scope: The evaluation will cover the ECOWAS nutrition Forum organised between 2013 and 2019. The 16th ECOWAS Nutrition Forum that shall take place in November 2019 in Monrovia, Liberia, will particularly contribute to answering questions related to efficiency. For this purpose, the participation of the evaluator in the event will be necessary. Evaluation Criteria This evaluation will be guided by five criteria: four of the five OECD/DAC criteria (Relevance, Effectiveness, Efficiency, and Sustainability) and an additional Gender, Equity and Human Rights. The impact criterion was not selected due to the lack of a baseline and the challenge of measuring the direct link (attribution) between the Forum and the different changes observed in countries’ nutrition status in the region. Evaluation Questions (by criterion) I. Relevance - To what extent has the Forum addressed the evolving needs of the nutrition sector / key stakeholders in the West Africa region over the years, in terms of coordination and mobilization of stakeholders? - To what extent are the Forum objectives aligned with those spelled out in the ECOWAS regional nutrition strategies and policies? - To what extent was the Forum’s design conducive to achieving the intended objectives? - How complementary is the ECOWAS Nutrition Forum with other high-level events and platforms? - To what extent do the various stakeholders (Member states representatives, partners, academics, etc.) perceive their voices, values, concerns are taken into account before, during or after the Forum? II. Effectiveness - To what extent and through which mechanisms has the ECOWAS Nutrition Forum contributed to its intended outcomes (improving nutrition programming and policies in the region)? - What are the factors (internal and external to ECOWAS) that contributed the most to the attainment of the Forum’s objectives? - What have been the major constraints (internal and external to ECOWAS) in influencing nutrition policies and programming in the region? How can these be addressed in the future? - What have been the Forum’s unintended effects (positive or negative), if any? - To what extent and how are the reports of the Nutrition Forum disseminated? How could this be improved? - What could be done to better and more consistently track the ECOWAS Nutrition Forum outcomes and the up-take of the recommendations in the future? III. Efficiency - To what extent were financial resources, human resources and supplies: - sufficient (quantity)? - adequate (quality)? - used/deployed in a timely manner? - What are the Forum’s different sources of funding? - Are there other alternative strategies that could be put in place to achieve the same level of results but at a lesser cost? What measures could be implemented to increase the value for money of the ECOWAS Nutrition Forum? - Are the process and criteria used to identify the length and content of the Forum appropriate? How could the Forum design and implementation be changed in order to achieve more value for money? IV. Sustainability and Ownership - To what extent and in what ways were the capacities of the government, civil society, NGOs, etc. enhanced in order to sustain the Forum’s results? - What has been the level of stakeholder engagement in the Forum’s organization (both financial and technical contributions)? - To what extent are the ECOWAS Nutrition Forum and related events included in national or partner event calendar planning? V. Gender and human rights, equity - To what extent are Gender, Human rights and Equity principles considered in relevant technical discussions and recommendations provided by the ECOWAS Nutrition? - To what extent are the opinions and needs of different groups (men, women, boys and girls), and particularly the most vulnerable, taken into consideration when deciding and acting upon the ECOWAS Forum recommendations? - To what extent did the discussion held during the Forum cover the barriers to services for boys and girls? Evaluation Methodology The evaluation will be conducted using a participatory and inclusive approach to provide relevant answers to key evaluation questions. It will be based on mixed methods of data collection and analysis. Relevant data should be collected from the Forum participants and other stakeholders at national and regional level (government staff, UNICEF, other partners) and using secondary sources. The triangulation of data from the different sources will be performed to guide the elaboration of evaluation findings. The iterative process of dialogue with the main ECOWAS Nutrition Forum stakeholders that will be initiated during the evaluative process will allow to reconstitute the theory of change and perform a contribution analysis to address the effectiveness criteria questions. The ECOWAS Nutrition Forum is seen as a space for advocacy and policy influencing; the proposed methodology to evaluate it will take this into consideration and identify and adequate evaluation framework, based on specialized literature. The consultants are strongly encouraged to propose the use of innovative methodologies in their technical proposal. The suggested methodology could include elements of the Bellwether Methodology or approach described by Overseas Development Institute (2011) to monitor and evaluate policy influence. However, it will be the consultant to suggest a detailed evaluation design, including a methodology to address each evaluation question and the tools to be use, in his/her technical proposal (the design will be further refined in the inception report). The inception report will be subject to validation by a technical steering committee At least, the following data collection methods are expected to be part of the methodological design: - Secondary data will be collected through Desk review of reports and other documentation from the ECOWAS Nutrition Forums and Midterm Reviews, Country nutrition strategies and Policies (or documents providing regional summaries), published and grey literature on the ECOWAS Nutrition Forum and other similar events to inform the design and recommendations. - Primary data will be collected through: - Key informant interviews: a list of relevant persons, involved in the organization of the forum or participants, will be developed. - Participant survey - Direct observation The consultant is expected to propose additional suitable methods of data collection in accordance with the retained methodological framework. The data collection and analysis as well as the different deliverables produced as part of this assignment (inception report, final report) will be consistent with the international evaluation quality standards namely: the UNEG Checklist on Quality Evaluation Reports, the GEROS Quality Assessment Criteria, and the UNEG Guide on the Integration of Gender Equality and Human Rights in Evaluation. Shall the evaluation design include collecting data from children, relevant UNICEF ethical standards on research involving children must be adhered to. The evaluation exchange, volume XIII number I, spring 2007, p.29, Evaluating an Issue’s Position on the Policy Agenda: The Bellwether Methodology. ODI, background Note February 2011, A guide to monitoring and evaluating policy influence. http://www.unevaluation.org/document/detail/607 https://www.unicef.org/evaluation/files/GEROS_Methodology_v7.pdf http://www.uneval.org/document/detail/980 https://www.unicef-irc.org/research/ethical-research-and-children/ |
| Deliverables and Schedules |  | Schedule of Tasks, Deliverables, Duty-Station & Timeline The evaluation is planned for a period of 50 working days during the period from October 2019 to January 2020. This period includes the desk review, field work, elaboration of evaluation reports and policy briefs, as well as all required workshops. The Table 2 below presents the indicative work plan for the evaluation. Table 2: Preliminary Work Plan Evaluation phases and Tasks; Number of Days of Work; Deliverables. - Preparatory Phase. Documentary Review, preliminary interviews with key stakeholders, elaboration of the inception report, which includes a travel to Bobo Dioulasso, Burkina, to meet with the organizing team; 12 days; Draft Inception report. Integration of the Steering Committee comments into the Inception report and submission; 2 days; Approved inception report. - Data Collection and Field Phase. Field mission to 2 countries for primary data collection purposes before and/or after ECOWAS Nutrition Forum+ continuous review of secondary data sources; 12 days; Primary data. Initial analysis and debriefing on preliminary findings to evaluation Steering Committee (site where to hold the debriefing will need be determined); 3 days; Power Point Presentation (PPT). Participation to the 16th ECOWAS Nutrition Forum (November 2019) + data collection on site (observation, participant survey, and interviews if possible); 5 days; Primary data. - Data analysis, report writing, validation and dissemination. Data analysis and elaboration of draft evaluation report based on the Steering Committee inputs; 10 days; Draft report. Review of the draft report by the Steering Committee; 0 days (allow two weeks for the review); Reviewed draft report. Integration of comments and submission of final evaluation report; 3 days; Final report. Elaboration of evaluation policy briefs based on the final approved evaluation report, update of the PPT; 3 days; Policy briefs and finalised PPT. TOTAL; 50 days. Deliverables: - Inception report: The consultant will submit an inception report summarizing the initial documentary review and presenting a detailed methodology and plan for the evaluation. The inception report will be structured as follows: - Introduction presenting the object of the evaluation, its purpose, scope and objectives; - Preliminary results of the documentary review summarized in the evaluation context section; - Evaluation criteria and questions refined through the desk review and preliminary interviews; - Detailed description of the evaluation methodology, including relevant data collection methods that will allow answering evaluation questions and sampling strategy; - Evaluation matrix presenting for each evaluation criterion and each evaluation question planned data collection methods and data sources. - Methods of data analysis; - Limitations of the evaluation and section on ethics and ethical considerations - Work Plan - Annex: List of the main documents reviewed; Proposed data collection tools; Initial list of key informants. - PPT on preliminary findings during the debriefing with the Steering Committee. - Evaluation Report: - Draft evaluation report (more details provided below) integrating the stakeholders’ observations from the debriefing (this deliverable will be shared with the Steering Committee members for comments). - Full final evaluation reports integrating all comments provided by the Steering Committee members (max. 50 pages excluding annexes). Textbox 1: Evaluation Report Structure The full final report shall be structured as follows: - Table of Contents including List of Tables and List of Figures - Executive Summary (covering all main sections of the report: background, methodology and process, main findings and recommendations, lessons learnt) - Acknowledgements (all who supported the evaluation and provided strong cooperation and collaboration during the process) - List of abbreviations and acronyms - Introduction (object of the evaluation, evaluation purpose, objective, scope, indented uses and users) - Evaluation context - Methodology, including sampling strategy and data analysis methods - Key findings (by criterion – each individual question will need to be answered) + Preliminary Conclusions (to be placed in coloured boxes with explicit references to the number of the finding paragraph which they are based on) - Final conclusions - Lessons Learnt - Recommendations (strategic and operational, maximum 5 priority recommendations) - Annexes (ToRs; List of persons interviewed and sites visited; List of documents consulted; More details on methodology, such as data collection instruments, including details of their reliability and validity; Evaluators biodata and/or justification of team composition; Evaluation matrix; Results framework). - Policy brief (max. 5 pages). The policy brief will include the main findings of the evaluation. - Final version of the PowerPoint presentation: The Consultant will produce a final PowerPoint presentation of the main evaluation findings (based on the final evaluation report), it will be shared with the Steering Committee members and use for dissemination of the evaluation findings. - Raw data: All raw data and complete transcripts from primary data collection will be delivered to UNICEF. All original research instruments with their recorded field data, transcripts and where applicable copies of all excel files/databases used for data analysis will be delivered to UNICEF to validate the analyses. UNICEF shall be entitled to all property rights, including but not limited to patents, copyrights, trademarks, and materials that bear a direct relation to, or made in consequence of, the services provided. At the request of UNICEF, the consultant shall assist in securing such property rights and transferring them to UNICEF in compliance with the requirement as is applicable. The consultant will need to make sure that the draft report and final report will be consistent with the international evaluation quality standards namely: the UNEG Checklist on Quality Evaluation Reports, the GEROS Quality Assessment Criteria, and the UNEG Guide on the Integration of Gender Equality and Human Rights in Evaluation. Duty-Station The Consultant will be home-based with some travels to Bobo-Dioulasso, Burkina Faso (to meet the organizing team), to Monrovia (to participate into the Forum) and 2 other countries, to be proposed by the consultant, based on strong rational. This will be proposed by the Consultant in the offer and discussed and agreed between the UNICEF and the Consultant before the signature of the contract. |
| Timing |  | The total duration of the contract is 50 days over the period from October 15, 2019 to January 30, 2020. |
| Reporting Requirements |  | In line with the UNICEF Evaluation Policy, this evaluation will be managed by the Regional Office for West and Central Africa (WCARO) The Consultant will report to the WCARegional Evaluation Adviser. Governance of the evaluation The contractor will be supervised by the UNICEF WCAR Regional Evaluation Adviser. n. A Reference Group comprising of ECOWAS and UNICEF officers (including the UNICEF Regional Nutrition Advisor and to the WAHO Programme Officer Nutrition) will be set up to provide oversight to the Evaluation and provide comments to the different deliverables (inception, draft and final report). The Regional Evaluation Adviser based at the UNICEF Regional Office for West and Central Africa (WCARO) will also provide technical oversight over the entire evaluation process, including on the different evaluation products (inception report, draft and evaluation report). |
| Profile Requirements |  | - Consultant International (50 days) . Education The Consultant will need to possess an advanced University Degree (minimum Master’s degree) in Public Health, Social Policy Evaluation, Nutrition, or other related field. Experience and Key Competencies: The Consultant should have extensive experience and competencies which will include: - A minimum of eight years of experience in policy and programme evaluation and must have completed at least three high quality policy or programme evaluations in that period (a copy of an evaluation report, which the applicant has been a primary author of, will need to be submitted a part of the application); - Prior experience with the conduct of evaluation of regional/international events/fora and community of practices is desirable - Have a perfect command of quantitative and qualitative methods of research and evaluation methods based on equity, human rights and gender; - Have excellent oral and written communication skills in French and English as well as skills in facilitation of participatory processes; - Have preferably work experience in West Africa Knowledge and understanding of the political context and development, and nutrition issues including nutrition-specific and nutrition-sensitive interventions in the west African region, or related sub-region - Good time management skills, including the ability to work towards tight deadlines, multi-task and work with a high degree of independence - Demonstrated skills in the use of information technology - Very good knowledge of French and English |
| Administrative Issues |  | UNICEF accepts applications from individual contractors. All applications should contain the following documents: I. Technical Project Proposal (max 3 pages), which would include at least the following (applicants are strongly encouraged not to repeat the text from Terms of Reference but rather to demonstrate a critical understanding of it): - Understanding of the evaluation purpose - An adequate conceptual framework and evaluation methodology (to measure the Forum influence on regional nutrition strategies) - Consultant’s profile/portfolio - Proposed timeframes (hour/days) - Names and contact details of reference persons - List of past evaluation reports (if applicable) - Any other additional information to support the application (optional). - Should the international consultant know of a consultant that is also applying for the national consultant position, please indicate his/her name in the proposal - Financial Proposal: - Detailed budget breakdown (in US Dollars). This will include travel related costs. Applicants are strongly encouraged to email their technical and financial evaluation offers (proposals should be uploaded on the HR application website). Deadline for applications: 7th of October 2019. The consultant will be engaged under short-term individual contract, immediately after the completion of the contracting procedure, for an estimated period of 50 days over a period of 6 months. The exact number of days to be proposed by the contractor and discussed with and confirmed, including the specific deadlines, by UNICEF when signing the contract. The Terms of Reference is an integral part of the individual contract signed with the contractor. Amounts and terms of payment are subject for negotiations but should comply with the UN standards. A detailed budget breakdown (budget proposal) shall be submitted together with the technical project proposal. The payment schedule will be agreed and linked with the deliverable outputs, the detailed conditions will be agreed in the consultancy contract. UNICEF reserves the right to withhold all or a portion of payment if performance is unsatisfactory, if work/outputs: - is incomplete, - does not meet the quality standards of both UNICEF and its partner, - is not delivered or has failed to meet deadlines - (fees reduced due to late submission: 5 days – 10%, 15 days – 20%; 1 month – 50%; more than 1 month – payment withheld). The contract is expected to last for a duration of 50 days. - Duty station: home-based, with travel to the 4 countries. - Air tickets to and from home base using the most direct and economical routes will be covered by UNICEF - UNICEF does not provide or arrange health insurance coverage for the consultant. DSA will be paid during the field mission, as per the International Civil Service Commission |

### Annex 2: Evaluation Matrix

| Evaluation Questions | Data sources | Data collection methods | Data analysis | Sampling plan |
| --- | --- | --- | --- | --- |
| Relevance |  |  |  |  |
| To what extent has the Forum addressed the evolving needs of the nutrition sector / key stakeholders in the West Africa region over the years, in terms of coordination and mobilization of stakeholders? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| To what extent are the Forum objectives aligned with those spelled out in the ECOWAS regional nutrition strategies and policies? | Fora’s reports Key informants (ECOWAS) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| To what extent was the Forum’s design conducive to achieving the intended objectives? | Key informants (ECOWAS) Country documents | Key Informant Interviews Country Field visits | Triangulation | Purposive sampling |
| How complementary is the ECOWAS Nutrition Forum with other high-level events and platforms? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| To what extent do the various stakeholders (Member states representatives, partners, academics, etc.) perceive their voices, values, concerns are taken into account before, during or after the Forum? | Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Key Informant Interviews Country Field visits | Triangulation | Purposive sampling and Systematic sampling |
| Effectiveness |  |  |  |  |
| To what extent and through which mechanisms has the ECOWAS Nutrition Forum contributed to its intended outcomes (improving nutrition programming and policies in the region)? | Fora’s reports Key informants (ECOWAS) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| What are the factors (internal and external to ECOWAS) that contributed the most to the attainment of the Forum’s objectives? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| What have been the major constraints (internal and external to ECOWAS) in influencing nutrition policies and programming in the region? How can these be addressed in the future? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| What have been the Forum’s unintended effects (positive or negative), if any? | Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Key Informant Interviews Country Field visits | Triangulation | Purposive sampling and Systematic sampling |
| To what extent and how are the reports of the Nutrition Forum disseminated? How could this be improved? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| What could be done to better and more consistently track the ECOWAS Nutrition Forum outcomes and the uptake of the recommendations in the future? | Key informants (ECOWAS) Country documents | Key Informant Interviews Country Field visits | Triangulation | Purposive sampling and Systematic sampling |
| Efficiency |  |  |  |  |
| To what extent were financial resources, human resources and supplies: i) Sufficient (quantity)? Ii) adequate (quality)? Iii) used/deployed in a timely manner? | Fora’s reports Key informants (ECOWAS) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| What are the Forum’s different sources of funding? | Fora’s reports Key informants (ECOWAS) | Desk review Key Informant Interviews | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| Are there other alternative strategies that could be put in place to achieve the same level of results but at a lesser cost? What measures could be implemented to increase the value for money of the ECOWAS Nutrition Forum? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| Are the process and criteria used to identify the length and content of the Forum appropriate? How could the Forum design and implementation be changed in order to achieve more value for money? | Key informants (ECOWAS) | Key Informant Interviews | Triangulation | Purposive sampling |
| Sustainability and ownership |  |  |  |  |
| To what extent and in what ways were the capacities of the government, civil society, NGOs, etc. enhanced in order to sustain the Forum’s results? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| What has been the level of stakeholder engagement in the Forum’s organization (both financial and technical contributions)? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) | Desk review Key Informant Interviews | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| To what extent are the ECOWAS Nutrition Forum and related events included in national or partner event calendar planning? | Fora’s reports Key informants (ECOWAS) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| Gender and human rights |  |  |  |  |
| To what extent are Gender, Human rights and Equity principles considered in relevant technical discussions and recommendations provided by the ECOWAS Nutrition? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| To what extent are the opinions and needs of different groups (men, women, boys and girls), and particularly the most vulnerable, taken into consideration when deciding and acting upon the ECOWAS Forum recommendations? | Fora’s reports Key informants (ECOWAS, Partners, CSO/NGOs) Country documents | Desk review Key Informant Interviews Country Field visits | Content analysis Triangulation | Purposive sampling and Systematic sampling |
| To what extent did the discussion held during the Forum cover the barriers to services for boys and girls? | Key informants (ECOWAS, Partners, CSO/NGOs) | Desk review Key Informant Interviews | Triangulation | Purposive sampling |

### Annex 3: List of Documents reviewed

Bamfo N. 2013. The political and security challenges facing ECOWAS in the Twenty-first century: Testing the limits of an organisation’s reputation. Department of political science, Valdosta State University, USA.

Blair E. 2016. Harvard Family Research Project. Presidents and Fellows of Harvard College. https://archive.globalfrp.org/evaluation/the-evaluation-exchange/issue-archive/advocacy-and-policy-change/evaluating-an-issue-s-position-on-the-policy-agenda-the-bellwether-methodology (Access date: 20/11/2019)

Bossuyt J. 2016. Political economy of regional integration in Africa. ECOWAS report. www.ecdpm.org/peria/ecowas

Coffman, J. (2007). “Evaluation based on theories of policy process”. The evaluation exchange, vol.XIII, no. 1&2, Spring (www.hfrp.org/evaluation/the-evaluation-exchange/issuearchive/advocacy-and-policy-change/evaluation-based-ontheories-of-the-policy-process, Access date: 22/11/2019)

Cohen M., Tirado C., Aberman N-L., Thompson B, IFPRI-FAO publication. Impact of Climate Change and Bioenergy on Nutrition.: Rome. http://www.fao.org/docrep/010/ai799e/ai799e00.HTM FAO/WFP (2008). (Access date: February 8, 2020)

De Vaus D. 2001. Research Design in Social Research. Sage Publication, London (Ltd). 148p.

ECOWAS Newsletter. 2019. https://www.ecowas.int/ecowas-holds-retreat-to-improve-telecommunications-and-information-technology-in-the-region/ (Assessed date: 12/05/2019).

Engel J. and Jouanjean M.A. 2015. Political and economic constraints to the ECOWAS Regional Economic Integration process and opportunities for donor engagement. EPA PEAKS, London: ODI.

Issue Brief, May 2008. FOOD SECURITY IN WEST AFRICA: Lean season markets and hazards update - August 2008.  – joint paper FAO/WFP/CRS/CILSS/FEWSNET. Rome. FEWSNET (2008).

Joseph R. 1997. Democratization in Africa after 1989: Comparative and theoretical Perspectives. Comparative politics 29 (3): 363-411.

Keck, M. and Sikkink, K. (1998) Activists beyond borders: advocacy networks in international politics. Ithaca, NY: Cornell University Press.

Loada A. 2014/ The comprehensive Africa Agriculture Programme (CAADP) progress. Future Agriculture working paper 85. Brighton: Future Agricultures.

Regional Nutrition Strategic Plan for West Africa 2018-2025 (PP 27).

ODI, background Note February 2011, A guide to monitoring and evaluating policy influence.

Protocol on Democracy and Good governance: supplement to the protocol relating to the mechanism for conflict prevention, management, resolution, peacekeeping and security. 2001.

The evaluation exchange, volume XIII number I, spring 2007, p.29, Evaluating an Issue’s Position on the Policy Agenda: The Bellwether Methodology.

Torres C. and Van Seters J. 2016. Overview of trade and barriers to trade in West Africa: Insights political economy dynamics, with particular focus on agricultural and food trade. European Centre for Development Policy Management. Discussion paper No 195.

Tri-Council Policy Statement: Ethical conduct for research involving Humans, 1998 (updated in 2000 and 2002).

Regional Nutrition Strategic Plan for West Africa 2018-2025 (PP 27).

UNEG Norms and standards (2016): www.unevaluation.org/document/download/2601 (Access date : 20/11/2019)

UNICEF, Division of Data Research and Policy (2019). Global UNICEF Databases: Infant and Young Child

UNICEF 2017. UNICEF-Adapted UNEG Evaluation Reports Standards. Evaluation Office. June 2017.

WAHO. Regional Nutrition Strategic Plan for West Africa 2018 - 2025.

World Bank. 2015. Doing Business 2015: Going beyond efficiency. Regional profile 2015 of the Economic Community of West African States (ECOWAS). Washington DC, The World Bank.

Websites

https://scalingupnutrition.org/news/burkina-fasos-common-nutrition-narrative-outlines-the-measures-taken-by-un-agencies-to-improve-nutrition/. (Access date: February 7, 2020)

http://liberiamohsw.org/Policies%20&%20Plans/National%20Nutrition%20Policy.pdf (Access date: February 7, 2020)

http://www.fao.org/3/a-i4183e.pdf (Assessment on the Right to Food in the ECOWAS region) (Access date: February 8, 2020)

http://www.fao.org/3/a-i4183e.pdf (Access date: February 8, 2020)

Poverty and Shared Prosperity 2018 (https://www.worldbank.org/en/publication/poverty-and-shared-prosperity)

https://www.ennonline.net/nex/9/nutstrategywestafrica (Access date: February 06, 2020)

http://www.internationaldemocracywatch.org/attachments/350_ECOWAS%20Protocol%20on%20Democracy%20and%20Good%20Governance.pdf Accessed date: 12/07/2019

https://globalnutritionreport.org/resources/nutrition-profiles/ (Access date: 22/02/2020)

https://www.ecowas.int/about-ecowas/basic-information/ (Access date: 21/02/2020).

### Annex 4: Data collection tools

Evaluation of The Economic Community of West African States (ECOWAS) Nutrition Fora

Guide for key informant interviews

(ECOWAS & WAHO, List of KII to be added)

This guide has been developed to gather your consent for the evaluation of ECOWAS’ Nutrition Fora. Your answers will remain confidential and will be used only for learning to improve future ECOWAS’ Nutrition Fora

Date: ______________________	Name: ______________________________________________________

Position and organisation: ____________________________________________________________________

Relevance

- To what extent has the Forum addressed the evolving needs of the nutrition sector/key stakeholders in the West Africa region over the years, in terms of coordination and mobilisation of stakeholders (understanding of evolving needs of the forum, participation to forum)?

- To what extent are the forum objectives aligned with those spelled out in the ECOWAS regional nutrition strategies and policies?

- To what extent was the forum’s design conductive to achieving the intended objectives (Cc. objectives of the Forum)?

- How complementary is the ECOWAS nutrition forum with other high-level event and platforms in the region?

- To what extent do the various stakeholders (Member states representatives, partners, academics, etc) perceive their voices, values, concerns are taken into account before, during or after the forum?

Effectiveness

- To what extent and through which mechanisms has the ECOWAS Nutrition forum contributed to its intended outcomes (improving nutrition programming and policies in the region)?

- What are the factors (internal and external to ECOWAS) that contributed the most to the attainment of the forum objectives?

- What have been the major constraints (internal and external to EOCWAS) in influencing nutrition policies and programming in the region? How can these be addressed in the future?

- What have been the forum’s unintended effects (positive or negative), if any?

- To what extent and how are the reports of the nutrition forum disseminated? How could this be improved?

- What could be done to better and more consistently track the ECOWAS nutrition forum outcomes and the up-take of the recommendations in the future?

Efficiency

- To what extent were financial resources human resources and supplies:

- Sufficient (quantity)?

- Adequate (Quality)?

- Used/ deployed in a timely manner?

- What are the forum’s different sources of funding?

- Are there other alternative strategies that could be put in place to achieve the same level of results but at a lesser cost? What measure could be implemented to increase the value for money of the ECOWAS nutrition forum?

- Are the process and criteria used to identify the length and content of the forum appropriate? How could the forum design and implementation be changed in order to achieve more value for money?

Sustainability and Ownership

- To what extent and what ways were the capacities of the government, civil society, NGOs, etc enhanced in order to sustain the forum’s results?

- What has been the level of stakeholder engagement in the forum’s organisation (both financial and technical contribution)?

- To what extent are the ECOWAS nutrition forum and related events included in national or partner event calendar planning?

Gender and Human rights, equity

- To what extent are gender, human rights and equity principles considered in relevant technical discussions and recommendations provided by the ECOWAS nutrition?

- To what extent are the opinions and needs of different groups (men, women, boys and girls), and particularly the most vulnerable, taken into consideration when deciding and acting upon the ECOWAS forum recommendations?

- To what extent did the discussion held during the forum cover the barriers to services for boys and girls?

THANKS FOR YOUR PARTICIPATION!

Guide for key informant interviews

(Technical & Financial partners, List of KII to be added)

This guide has been developed to gather your consent for the evaluation of ECOWAS’ Nutrition Fora. Your answers will remain confidential and will be used only for learning to improve the ECOWAS’ Nutrition Fora

Date: ______________________	Name: ______________________________________________________

Position and Organisation: ____________________________________________________________________

Relevance

- To what extent has the Forum addressed the evolving needs of the nutrition sector/key stakeholders in the West Africa region over the years, in terms of coordination and mobilisation of stakeholders?

- How complementary is the ECOWAS nutrition forum with other high-level event and platforms?

- To what extent do the various stakeholders (Member states representatives, partners, academics, etc) perceive their voices, values, concerns are taken into account before, during or after the forum?

Effectiveness

- What are the factors (internal and external to ECOWAS) that contributed the most to the attainment of the forum objectives?

- To what extent and how are the reports of the nutrition forum disseminated? How could this be improved?

- What could be done to better and more consistently track the ECOWAS nutrition forum outcomes and the up-take of the recommendations in the future?

Efficiency

- What measure could be implemented to increase the value for money of the ECOWAS nutrition forum?

- Are the process and criteria used to identify the length and content of the forum appropriate?

Sustainability and Ownership

- To what extent and what ways were the capacities of the partners enhanced in order to sustain the forum’s results?

- What has been the level of stakeholder engagement in the forum’s organisation (both financial and technical contribution)?

Gender and Human rights, equity

- To what extent are gender, human rights and equity principles considered in relevant technical discussions and recommendations provided by the ECOWAS nutrition?

- To what extent did the discussion held during the forum cover the barriers to services for boys and girls?

THANKS FOR YOUR PARTICIPATION!

Guide for key informant interviews

(In-Country Partners including national and international NGOs, List of KII to be added)

This guide has been developed to gather your consent for the evaluation of ECOWAS’ Nutrition For a. Your answers will remain confidential and will be used only for learning to improve future ECOWAS’ Nutrition For a

Date: ______________________	Name: ______________________________________________________

Position and organisation: ____________________________________________________________________

Relevance

- To what extent has the Forum addressed the evolving needs of the nutrition sector/key stakeholders in the West Africa region over the years, in terms of coordination and mobilisation of stakeholders?

- How complementary is the ECOWAS nutrition forum with other high-level event and platforms?

- To what extent do the various stakeholders (Member states representatives, partners, academics, etc) perceive their voices, values, concerns are taken into account before, during or after the forum?

Effectiveness

- What are the factors (internal and external to ECOWAS) that contributed the most to the attainment of the forum objectives?

- What could be done to better and more consistently track the ECOWAS nutrition forum outcomes and the up-take of the recommendations in the future?

Efficiency

- What measure could be implemented to increase the value for money of the ECOWAS nutrition forum?

- Are the process and criteria used to identify the length and content of the forum appropriate? How could the forum design and implementation be changed in order to achieve more value for money?

Sustainability and Ownership

- To what extent and what ways were the capacities of the government, civil society, NGOs, etc enhanced in order to sustain the forum’s results?

- To what extent are the ECOWAS nutrition forum and related events included in national or partner event calendar planning?

Gender and Human rights, equity

- To what extent are gender, human rights and equity principles considered in relevant technical discussions and recommendations provided by the ECOWAS nutrition?

- To what extent did the discussion held during the forum cover the barriers to services for boys and girls?

THANKS FOR YOUR PARTICIPATION!

Structured Checklist for field visits

Date : ________________

Country : ______________ 					City : ____________________________

Ob1. Availability of a nutrition policy

- Yes 		2. No

Ob2. Exiting National Nutrition Action Plan

- Yes 		2. No

Ob3. Food security and/or nutrition framework

- Yes 		2. No

Ob4. Country-led financial policy for Nutrition issues

- Yes 		2. No

Ob5. Funded nutrition intervention

- Yes 		2. No

Ob6. Exiting Forum/Fora on Health and Nutrition

- Yes 		2. No

Ob7. Other observations (To be specified)

_________________________________________________________________________________

### Annex 5: List of key informants met

| No | Names | Positions | Organisations | Country |
| --- | --- | --- | --- | --- |
| Member States |  |  |  |  |
| 1 | Dr. Chris Osa. Isokpunwu | Director of Nutrition Division | Federal Ministry of Health Federal Secretariat Phase III | Nigeria |
| 2 | Dona Yvone Rezende Menezes | Former Director of Nutrition | Ministry of Health | Guinea-Bissau |
| 3 | Réné Oka Kouamé | Director and Coordinator of the National Nutrition Program | Vice-Presidency | Cote d’Ivoire |
| 4 | Constant Tra Bi | Acting Executive Secretary | National Council for Nutrition, Food and Early Childhood Development (CONNAPE) | Cote d’Ivoire |
| 5 | Kouamé Koffi | Monitoring and evaluation specialist | CONNAPE | Cote d’Ivoire |
| 6 | Faustin N'DRI | Chef du projet | National Multisectoral Platform for Information on Nutrition (PNMIN) | Cote d’Ivoire |
| 7 | Patricia Ngoran–Theckly Yoboue | Nutrition, Food and Early Childhood development Councelor | Vice-President Office | Cote d’Ivoire |
| 8 | Ella Compaoré | (SUN Focal Point), Technical Secretary for Food and Nutrition | Ministry of Health | Burkina Faso |
| 9 | Estelle BAMBARA | Director of Nutrition | Ministry of Health | Burkina Faso |
| 10 | Sonon Bodjrenou Felix | Chief Nutrition Services | Ministry of Health | Benin |
| 11 | Bentoe Zogley Tehoungue | Director of Reproductive Health | Ministry of Health | Liberia |
| 12 |  |  |  |  |
| WAHO |  |  |  |  |
| 12 | Paulo Djata, | Focal Point | WAHO | Guinea-Bissau |
| 13 | Kouakou Kouame Alphonse | Point Focal | WAHO | Cote d’Ivoire |
| 14 | Isaïe Medah | Focal Point & Director General of Public Health | WAHO | Burkina Faso |
| 15 | William Kofi Bosu | Professional Officer Non-Epidemic Diseases & NTDs | WAHO | Burkina Faso |
| 16 | Namoudou Keita | Professional Officer, Primary Health Care & NCDs | WAHO | Burkina Faso |
| Partners |  |  |  |  |
| 17 | Prof. Nnam | President | The African Union for Nutrition | Nigeria |
| 18 | Prof. Ene-obong | Lecturer | University of Nigeria, Calabar | Nigeria |
| 19 | Siméon Nanama, | Chief Nutrition Section | Ministry of Health | Nigeria |
| 20 | Robert Ndamobissi | Evaluation Manager, Office of the Representative | UNICEF | Nigeria |
| 21 | Beatrice Eluaka | Executive Secretary | Civil Society – Scaling Up Nutrition | Nigeria |
| 22 | Judith Kabore | Regional Lobbying Officer for ACF and Regional Coordinator for CSO | SUN CSN | Senegal |
| 23 | Pita CORREIA |  | WFP - Bissau | Guinea-Bissau |
| 24 | Noël Marie Zagre | Regional Advisor Nutrition | UNICEF | Senegal |
| 25 | Albert Ewodo Ekani | Chief Social Policy and Monitoring & Evaluation | UNICEF | Guinea-Bissau |
| 26 | Salvator Nibitanga | Chief Health & Nutrition | UNICEF | Guinea-Bissau |
| 27 | Iama Sanhá | Nutrition Officer | UNICEF | Guinea-Bissau |
| 28 | Isabel Garcia Almeida | National Focal Point | SUN | Guinea-Bissau |
| 29 | Denis Garnier | Chief Nutrition Section | UNICEF | Cote d’Ivoire |
| 30 | Soukeynatou Fall | Chief M&E Specialist | UNICEF | Cote d’Ivoire |
| 31 | Paulin Koffi | Nutrition Specialist | UNICEF | Cote d’Ivoire |
| 32 | Jean-Claude Mubalama | Head of Health and Nutrition Program | UNICEF | Cote d’Ivoire |
| 33 | Dowrot Bertine Ouaro Dabire | Nutrition Officer (Former Nutrition Director) | UNICEF | Burkina Faso |
| 34 | Seydou Ndiaye | National Coordinator | SUN - Senegal | Senegal |
| 35 | Mediatrice Toure Kiburente | Nutrition Specialist in charge of the Nutrition Program | UNICEF | Burkina Faso |
| 36 | Kenjiro Ban | Chief Official | IANA Secretariat | South Africa |
| NGO & CSO |  |  |  |  |
| 37 | Prof. Ngozi Nnam | President | FANUS - Nigeria | Nigeria |
| 38 | Lydia Sasu | Executive Director | Development Action Association (DAA) | Ghana |
| 39 | André Ouedraogo | Nutrition Expert | CILSS, Burkina Faso | Burkina Faso |
| 40 | Christelle Hure | Advocacy Officer | Action Against Hunger, | Senegal |
| 41 | Simon Sau | General Secretary | ROPPA – Farmers organisation | Ghana |
| Parliamentarians |  |  |  |  |
| 42 | Dissan Gnoumou | President | Network of Parliamentarians for Nutritional Security in West and Central Africa / National Assembly | Burkina Faso |

### Annex 6: Synthesis of the Objectives of and Recommendations from the ECOWAS’ Nutrition Fora of 2008 - 2019

| Items | Editions (Years) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008 | 2010 | 2012 | 2015 | 2017 | 2019 |
| Themes | “Food Security and Nutrition | Planning and Funding of Multisectoral nutrition programmes in ECOWAS Region | Role of local communities, civil society communities and the private sector in Scaling Up Nutrition interventions | Nutrition-related MDGs in West Africa: achievements, opportunities and way forward”. | Nutrition surveillance-Towards improved planning and evidence-based decision making on food and nutrition security in West-Africa | Adolescent nutrition: institutionalizing sustainable actions for improved outcomes in West Africa |
| Forum objectives | - Share experiences and review nutrition interventions and programs implemented at country level - Develop a regional profile of nutrition and identify adequate resources needed from African institutions and partners to support the implementation of activities. - Provide a technical update focusing on a crucial and relevant topic: “Food and Nutrition Security” in the sub-region. | - Share experiences and practices that contribute to improve the nutritional situation in ECOWAS countries - Review the recommendations from previous forums - Develop action plans aiming at improving the nutritional situation - Carry out a technical update for planning and funding multisectoral nutrition and food programmes to improve the efficiency of the implementation of programmes in the sub-region | - Take stock of the implementation of Bassam's recommendations and action plans to improve the nutritional situation. - Share the lessons learned from the implementation of the Paris-Accra principle on aid effectiveness and the application of the “Three-one” approach to nutrition. - Discuss lessons learned from the implementation of multilateral initiatives (SUN and REACH approach), International Health Partnership and the Global Health Initiative - Identify best practices and challenges related to the involvement of local and the private sector in national SUN programs - Develop country action plans to promote and strengthen the role of local communities, civil society and the private sector in SUN programs. - Create a consensus on the role and responsibilities of WAHO and its financial and technical partners in supporting the implementation of national action plans. | - To review progress in nutrition and food security within the region and in the implementation of the last Forum recommendations and action plan in the Member States - To update participants on the regional nutrition situation and current initiatives - To evaluate progress on the attainment of the major nutrition related MDGs - To reflect on the experiences, challenges, lessons learnt and remaining gaps and how these help the Region to position itself to implement the post-2015 sustainable development agenda - To identify evidence-based strategies for improving and harmonizing nutrition surveillance and information management in the region - To evaluate available mechanisms for coordinating multiple nutrition specific and sensitive initiatives in countries and at regional level - To formulate keys recommendations to accelerate the post-2015 agenda on nutrition | - Review the key points of the last Forum held in Lome in 2015 - Review the status of ongoing regional nutritional initiatives - Analyse the structure, relevance and limitations of the different nutrition surveillance systems in the region - Explore how the value of routine and programme data in nutrition decision-making could be improved - Appraise the mechanisms available to monitor food and nutrition security - Assess the interoperability and comparability between different nutrition survey systems - Review mechanisms for monitoring accountability on national and regional commitments related to food and nutrition security | - To update participants on the regional nutrition situation and current initiatives. - To review the current state of adolescent malnutrition and diet-related diseases, risk factors, consequences, co-morbidities and current response in the region. - To evaluate the current (nutrition-specific and nutrition-sensitive) policies, programmes, interventions and best practices to improve and sustain adolescent nutrition in the region. - To explore mechanisms for strengthening health systems and financing for adolescent nutrition. - To analyze existing surveillance systems and the needed information on adolescent nutrition in the region. |
| Format | 5 days | 5 days | 5 days | 4 days | 4 days | 3 days |
| Participants | - Officials: 49 from 13/15 member States - Host country delegates: 23 - WAHO’s Participants: 30 - Partners: 11 - NGO & CSO: 9 Total: 122 | - Officials: 70 from 15 member States - 8 WAHO’s participants - 18 Partners - NGO & CSO Total: 133 | - 81 Officials: 14/15 members states - 28 WAHO - 38 Partners - 18 NGO & CSO Total: 165 | - 76 Officials: from 15 Member States - 25 WAHO’s participants - 18 Partners - 17 NGO & CSO Total: 136 | - 31 Official from 15 Member States - 53 Host country - 7 WAHO’s - 31 Partners - 4 Parliamentarians - 9 NGO & CSO Total: 135 | - 58 Officials: from 13 member states - 20 Host country - 8 WAHO’s participants - 25 Partners - 7 Academic/Research - 2 Parliamentarians - 8 NGO & CSO Total: 128 |
| Budget |  |  |  |  |  |  |
| Recom-mendations | Member States - Re-affirm political will and mobilize resources from national and international institutions in order to accelerate the fight for the Food Security and for the control of Malnutrition. - Setting up or strengthen a National Coordination framework with the necessary resources in order to ensure inter sectoral collaboration and communication among the different actors at all levels. - Involve actors of other sector Civil Society and National Parliament for leadership and anchoring of nutrition at a higher level. - Promote systematic use of biodiversity for local and balanced diets. TO ECOWAS Parliament - Take the lead on advocacy to facilitate higher institutional anchorage for resource mobilization, for strengthening the legal and regularly framework, with a view to protect, improve food and nutrition situation within the ECOWAS region and at country level. | Member States - Reinforce multisectoral collaboration in the implementation of priority actions - Establishment/reinforcement existing networks among and within member states in order to facilitate experience and technical support sharing - Governments should be proactive in mobilizing resources for the nutrition programme | Member States - Renforcer la collaboration multisectorielle dans la mise en œuvre des actions Prioritaires ; - Etablir des réseaux ou renforcer ceux existants entre et dans les états membres afin de faciliter le partage d’expériences et l’appui technique - Développer un réflexe de pro activité dans la mobilisation de ressources pour les programmes de nutrition. | Member States: - - Incorporate nutrition indicators into the national health information systems - - Ensure institutional anchoring of nutrition at the highest possible decision-making body in order to achieve maximum efficiency - - Make the multisectoral platform on nutrition effective - - Increase the adequacy of domestic funding for nutrition - - Encourage empowerment, accountability and ownership in the preparation and implementation of nutrition programmes - - Train nutrition human resource in quantity and quality - - Establish a coherent mechanism for coordinating nutrition initiatives (SUN, REACH, AGIR, Zero Hunger Initiative, etc.) | Member States - Harmonise collection tools and methods for the assessment of global targets to be coordinated by WAHO in the ECOWAS region - Advocate for increased funding in accordance with the Abuja Declaration - Strengthen the capacities of actors for quality data collection - Incorporate sanitary and phytosanitary concerns into nutrition interventions • Enhance the training of data management professionals in countries | To partners Support countries with funding for adolescent health and nutrition Support countries to undertake costing of (existing) interventions for adolescents Support countries to integrate indicators on adolescent nutrition and health in national surveys (DHS, MICS, SMART), especially 10-14-year-olds Support countries in strengthening local technical capacity on data management Support countries to expand school feeding programs to include integrated adolescent health services. |
|  | To Partners - Develop frank and synergetic collaboration of partner institutions, in the first place in the agriculture and health sectors. - Support countries in a concerted manner - Build upon country experiences and initiatives. - Seize the opportunity of the present food crisis to place Food and Nutrition Security at center of development, taking into consideration gender and poverty dimensions, in order to accelerate the achievement of the Millennium Development Goals (MDGs). - Strengthen collaborations between the institutions of the United Nations System, and other partners in development within the SCN framework, in order to take advantage of global, regional, national and local opportunities aiming at strengthening collaboration among different sectors, in particular, in the agriculture and health sectors. - Promote operational research in order to make optimal use of biodiversity for food and nutrition security, with accompanying measures for small scale farmers and consumers education. - Create collaboration between the Human Development and Gender, and Agricultural, Environment and Water Resources Commissions of ECOWAS, in order to carry out, articulate, harmonize and strengthen interventions by including nutrition actions and biodiversity management. - Pursue reflection within the ECOWAS Commission on Agricultural production and the merging of bio-fuels, by incorporating nutritional considerations | WAHO and partners - Provide support (logistic, technical and financial) to countries for the implementation of priority actions identified by countries - Support activities to mobilisation resources for national nutrition programmes | OOAS et partenaires - Apporter un appui (logistique, technique et financier) aux pays pour la mise en œuvre des actions prioritaires identifiées, notamment en nutrition ; - Appuyer les activités de mobilisation de ressources pour les programmes nationaux de nutrition | WAHO and partners - Prepare an ECOWAS regional strategic plan on nutrition - Advocate for institutional anchoring of nutrition at the highest possible decision-making body in order to achieve maximum efficiency - Monitor the implementation of the Forum’s recommendations - Update the WAHO website on nutrition in order to foster experience sharing | WAHO and partners • Design monitoring and evaluation tools based on existing tools and a harmonised framework at the regional level to monitor commitments made by countries (scorecards); • Advocate for increased funding in accordance with the Abuja Declaration • Strengthen the capacities of institutions and countries to produce and utilize routine data of good quality. • Conduct an external appraisal of the ECOWAS forum to ascertain the impact of it in the countries | Member States - Increase priority to adolescent health and nutrition programmes - Provide platform for adolescents to express their needs and aspirations through the use of youth ambassadors and champions Institute appropriate programmes to reach and build the skills of out-of school, institutionalized and indigent adolescents - Organize regular engagements with First Ladies, politicians, opinion and religious leaders, NGOs - Institute social protection measures including conditional transfers, national health insurance to reduce barriers to access by out-of-school and indigent adolescents - Increase the financial investment of adolescent health and nutrition Advocate for strong engagement of policy makers to increase budgetary allocation to nutrition, and specifically for adolescent nutrition - Increase funds for adolescent health services through the identification of innovative funding mechanisms for nutrition including dedicated budget lines, leveraging funds from existing programmes, statutory levies, crowd funding and private sector participation - Improve the data availability, quality and use for decision-making in adolescent nutrition and health Define a core set of indicators based on data from various sources to monitor the health and nutrition of adolescents, - Integrate adolescent health and nutrition, including the 10-14-year age group into national HMIS - Develop national research agenda including longitudinal studies, systematic reviews, KAP, operational research on adolescent health and nutrition - Increase public awareness on the health and nutrition needs of adolescents Develop national communication (SBCC) plans on adolescent health and nutrition - Increase the organization of nutrition and health services for adolescents To establish or strengthen school health clinics providing adolescent-friendly services. |
|  | TO WAHO/ CILSS - Pursue integration of nutritional considerations within the food security information systems in collaboration with relevant institutions, particularly the UN System. - Harmonize analysis frameworks and tools for data collection and analysis, on food and nutrition security in order to facilitate appropriate decision making at local, national and regional levels. - Taking into consideration, the issue of climate change, in the formation and implementation of decisions in favor of food and nutrition security, and with special attention to Disaster Risk Management associated with the occurrence of extreme climatic disaster. - Better involvement of community-based organizations, civil society, training and research institutions in the resolution of nutrition related issues. |  |  | To Technical and Financial Partners - - Support countries for the improvement of the availability and quality of data on nutrition. - - Support countries for the mobilization of resources towards the actual implementation of programmes and commitments. |  | To WAHO and Regional Economic Communities Support countries to develop appropriate policies and programmes to mainstream adolescent health and nutrition into national public health agenda Increase the financial investment of adolescent health and nutrition Support the sharing of novel technologies including mobile applications between countries in the development of adolescent nutrition and health communication programmes Provide platform for regular exchange of best practices in improving adolescent health and nutrition outcomes |
| Venues | Freetown, Sierra Leone | Grand Bassam, Cote d’ Ivoire | Ouagadougou, Burkina Faso | Lomé, Togo | Bissau, Guinea Bissau | Monrovia, Liberia |

### Annex 7: Field work plan

Evaluation of the ECOWAS’ Nutrition Forum

Mission workplan

| Activities | Completed |
| --- | --- |
| Phase 1: Inception – Inception report (Delivery 1) |  |
| Initial meeting online and Preliminary document review (home-based, HB) | Nov. 17/19 |
| Workshop and preliminary interviews in Monrovia | Nov. 22/2019 |
| Draft inception report and submission for comments to the Client (HB) | Nov. 29/19 |
| Comments received from UNICEF and WAHO | Dec. 03/10 |
| Document review and online search for additional information (HB) | Dec. 10/19 |
| Review and submission of final inception report (HB) | Dec. 13/19 |
| Phase 2: Data collection & Analysis methods – Preliminary findings (Delivery 2) |  |
| Travel to Nigeria and Guinea Bissau | Dec. 14 - 15 /19 |
| Field mission in Nigeria and Guinea Bissau | Dec. 16 - 20/19 |
| Travel to Ivory Coast and Burkina Faso | Jan. 4 - 5/20 |
| Field mission to Cote d’Ivoire and Burkina Faso | Jan. 6 - 10/20 |
| Key Informant Interviews completed | Jan. 12/20 |
| Phase 3: Synthesis of findings and reporting – Draft evaluation report (Delivery 3) |  |
| Draft evaluation report | Jan. 20/20 |
| Comments received from WAHO and UNICEF | Jan. 22/20 |
| Submission of revised DRAFT evaluation to UNICEF and WAHO | Jan. 27/20 |
| New comments provided by UNICEF ECOWAS | Jan. 28/20 |
| Submission final report to UNICEF & WAHO (INTERNAL TO UNICEF) | Jan. 31/20 |
| Presentation of findings and conclusions to WAHO/UNICEF (virtually) | Feb. 05/20 |
| Compendium on the report with comments from UNICEF & WAHO | Feb. 10/20 |
| Final validation of the report | Feb. 15/20 |

### Annex 8: Evaluators’ biodata

Serge Eric Yakeu Djiam, Team Leader – International Consultant (CE)

Bilingual (French & English), Serge Eric is a Credentialed Evaluator (CE). His is the Chair of EvalIndigenous and Former President of the African Evaluation Association (AfrEA). His background covers mostly Education and Rural development, Evaluation Capacity development, Project design and Planning, Participatory Monitoring & Evaluation, Outcome mapping and Impact Assessment, Food Security, Livelihoods Management, Rural finance and Institutional Analysis, Agricultural economics research, Environmental economics, and Development evaluation. He spent the 15+ years conducting evaluations in Africa (21 countries), Europe (7), North America, Middle-East (2), and Asia (3), in various environments including cities, villagers, forests, savanna. He works with stakeholders at multiple levels including community-based organisations, donors/funders, governments, partners’ and UN agencies such UNICEF, ILO, UNIDO, UNDP, UNESCO, IFAD, FAO, UNWomen, and WFP.

Serge Eric led the design and implementation of over 120 country research worldwide and within complex and humanitarian environments either as individual or in team setting in various locations including very remote areas. Most work required very strong cultural sensitivity. With his ability to manage participatory approaches in addition to his knowledge and leadership skills, he adapts readily to different cultural environments. His has an excellent command of both qualitative and quantitative research methodologies and statistics, outstanding knowledge and experience of statistical analysis software such as SPSS, R, CESPRO, SNARP – SURVEY and other new technologies.

He is also a Visiting Professor with various universities such as Quebec University in Montreal (UQAM), the Faculty of Agriculture and Food Consumption of the United Arabs Emirates University, University of Constantine II in Algeria, and served as “Senior Lecturer” for the Institute of Environmental Sciences in Cameroon. Serge Eric is very active as adviser for youth empowerment and as a Mentor for EvalYouth Mentorship programme.

Furthermore, he is currently serving as international resource specialist to chair workshop/conferences, for scientific reviews with evaluation journals, research and evaluation networks worldwide. With colleagues from several international networks, he completed a project called “Evaluation that make a difference” under EvalPartners initiative (http://evaluationstories.wordpress.com/editorial-board-2/). His bilingual communication skills are outstanding with an excellent public speaking facility with various types of audience (academic, policymakers, funders, civil society actors, and grantees). He’s pretty talented and swift in the design and production of high-quality reports in English and French, which could bear both technical and policy-oriented styles. He is a Life Member of the International Development Evaluation Association (IDEAS), Member of the Canadian Evaluation Society (CES), AfrEA, Cameroon Development Evaluation Association (CaDEA), Canadian Association of International Development Professionals (CAIDP), and EvalIndigenous Network.

With regards to his qualification, Mr. Yakeu has an Engineer Diploma (M.Sc.) in Agricultural economics and Rural Sociology, a B.Sc. in Human Nutrition (Cameroon), an International M.Sc. in Rural development (Belgium), A Master Degree in Research Methodologies and Statistics (Wageningen, Netherlands), and A M.Sc. in Environmental Economics (Humboldt, Germany). He also has several international certificates in Participatory M&E and Results-Based Management (IFAD 2008 in Dakar, and CLEAR/WorldBank 2013 in Ouagadougou), in Equity-Focused Evaluation (Unicef 2012), in Planning and Development Evaluation (Canada, IPDET 2013), in Development Cooperation (Belgium 2011). He finally completed the Advanced Security In The Field (ASITF) and the Basic Security In The Field (BSITF II) Certificates of the United Nations Department of Safety and Security.

For more details, please looks at: https://www.linkedin.com/in/serge-eric-yakeu-djiam-1ab15140/

Laura Golakeh, National Consultant

Laura Golakeh is an education advocate and gender expert. She is the founder of an NGO based in Liberia providing reading and writing skills to underprivileged children and engaging policy makers on the importance of quality education in Liberia. The organization called Right to Read, promotes early grade reading among children and operates a mobile library. Ms. Golakeh is the Founder and Lead Consultant for Light Consultants, a consultancy firm in Liberia specialized in educational leadership, evaluation as well gender and development. Through her firm, Ms. Golakeh provided consultancies to many international organizations including UNICEF, UN Women where she worked as National Consultant to develop the Liberia National Action Plan on UNSCR 1325 and build the capacity of staff of the Ministry of Gender, other government agencies and civil society organizations to implement the action Plan. She also worked as Liberia Education Context Specialist for USAID on a mid-term evaluation of the Accelerated Quality Education Project and most recently as Gender Expert for the German Institute for Development. Laura currently provides consulting services to the World Bank country office in Liberia through it’s Social Protection and Jobs program. Laura has also worked in various program and media capacities at non-governmental organizations like the Wellesley Center for Women in Boston, Massachusetts and the Liberia Media Center.

Laura has over five years’ experience working both in the private sector (mentioned above) and the public sector, including the Executive Office of the President of Liberia at the Ministry of State and the Angie Brooks International Center at the Ministry of Foreign Affairs. At the Angie Brooks International Center, she worked as Communications Officer and worked closely with Executive Assistant to implement projects including the Women’s Situation Room as well UNITAR trainings.

Laura has a Master of Arts in Gender and Peacebuilding. She is a 2014 Mandela Washington Fellow, volunteer Country Director for EiC Corporation and a former member of the UN Women Civil Society Advisory Committee. Laura loves traveling, writing and mentoring young people.

ECOWAS countries are Benin, Burkina Faso, Cameroon, Cabo Verde, Côte d'Ivoire, Equatorial Guinea, The Gambia, Ghana, Guinea, Guinea-Bissau, Liberia, Mali, Mauritania, Niger, Nigeria, Senegal, Sierra Leone, and Togo.

https://www.ecowas.int/about-ecowas/basic-information/ (Access date: 21/02/2020).

Joseph R. 1997. Democratization in Africa after 1989: Comparative and theoretical Perspectives. Comparative politics 29 (3): 363-411.

World Bank. 2015. Doing Business 2015: Going beyond efficiency. Regional profile 2015 of the Economic Community of West African States (ECOWAS). Washington DC, The World Bank.

As per the Protocol on Democracy and Good governance: supplement to the protocol relating to the mechanism for conflict prevention, management, resolution, peacekeeping and security. 2001. http://www.internationaldemocracywatch.org/attachments/350_ECOWAS%20Protocol%20on%20Democracy%20and%20Good%20Governance.pdf Accessed date: 12/07/2019

ECOWAS Newsletter. 2019. https://www.ecowas.int/ecowas-holds-retreat-to-improve-telecommunications-and-information-technology-in-the-region/ (Assessed date: 12/05/2019).

Torres C. and Van Seters J. 2016. Overview of trade and barriers to trade in West Africa: Insights political economy dynamics, with particular focus on agricultural and food trade. European Centre for Development Policy Management. Discussion paper No 195.

Engel J. and Jouanjean M.A. 2015. Political and economic constraints to the ECOWAS Regional Economic Integration process and opportunities for donor engagement. EPA PEAKS, London: ODI.

Bossuyt J. 2016. Political economy of regional integration in Africa. ECOWAS report. www.ecdpm.org/peria/ecowas

Loada A. 2014/ The Comprehensive Africa Agriculture Programme (CAADP) progress. Future Agriculture working paper 85. Brighton: Future Agricultures.

WAHO. Regional Nutrition Strategic Plan for West Africa 2018 - 2025.

The WAHO specific objectives cover: i) Promote research into the major endemic diseases in the region and undertake activities aimed at controlling these diseases and their eradication; ii) Promote the training of medical specialists and of paramedical personnel and where necessary support the training of future medical graduates; iii) Collect and disseminate technical information, epidemiological and others related to health research and training in Member States; iv) Assist in the establishment of technical information Centres in Member States; v) Promote and harmonize the establishment of laboratories for the production of vaccines, medicines manufacturing and quality control in the region; vi) Encourage cooperation in the control and eradication of drug dependency and abuse in the region; vii) Promote exchange of personnel and health technologies among Member States; viii) Provide advice on all health-related aspects of development projects to Member States; ix) Support the strengthening of health services and infrastructures of Member States; x) Provide assistance to Member States to resolve health problems in the event of emergencies following natural disasters; xi) Collaborate with sub-regional, regional and international organizations to address health problems in the region; xii) Promote cooperation between scientists and professionals’ groups contributing to health development; and xiii) Propose conventions, agreements, regulations and recommendations on regional health issues and undertake tasks entrusted to the Organization in this regard.

Poverty and Shared Prosperity 2018 (https://www.worldbank.org/en/publication/poverty-and-shared-prosperity)

https://globalnutritionreport.org/resources/nutrition-profiles/ (Access date: 22/02/2020)

https://www.ennonline.net/nex/9/nutstrategywestafrica (Access date: February 06, 2020)

Issue Brief, May 2008: Rome. FEWSNET (2008). FOOD SECURITY IN WEST AFRICA: Lean season markets and hazards update - August 2008.  – joint paper FAO/WFP/CRS/CILSS/FEWSNET.

UNICEF, Division of Data Research and Policy (2019). Global UNICEF Global Databases: Infant and Young Child.

Based on population weighted means of 16 countries. https://globalnutritionreport.org/resources/nutrition-profiles/ (Access date: 22/02/2020).

http://www.fao.org/3/a-i4183e.pdf (Assessment on the Right to Food in the ECOWAS region) (Access date: February 8, 2020)

Impact of Climate Change and Bioenergy on Nutrition. Cohen M., Tirado C., Aberman N-L., Thompson B, IFPRI-FAO publication: Rome. http://www.fao.org/docrep/010/ai799e/ai799e00.HTM FAO/WFP (2008). (Access date: February 8, 2020)

http://www.fao.org/3/a-i4183e.pdf (Access date: February 8, 2020)

https://scalingupnutrition.org/news/burkina-fasos-common-nutrition-narrative-outlines-the-measures-taken-by-un-agencies-to-improve-nutrition/. (Access date: February 7, 2020)

http://liberiamohsw.org/Policies%20&%20Plans/National%20Nutrition%20Policy.pdf (Access date: February 7, 2020)

https://extranet.who.int/nutrition/gina/sites/default/files/NGA%202014%20NSPAN.pdf (Access date: February 7, 2020)

UN agencies involved include UNICEF/WCARO, World Food Programme (WFP), the Food and Agriculture Organisation (FAO), World Health organisation (WHO).

Strategic and operational recommendations are expected to provide guidance to the recipients on how to increase the efficiency and effectiveness of future fora; Enhance ownership by all major stakeholders; and make future for a more responsive to the region’s nutrition and food security situation.

To consider at least French, English and Lusophone speaking countries.

UNEG Norms and standards (2016): www.unevaluation.org/document/download/2601 (Access date : 20/11/2019).

Explicit consent has been obtained from all interviews, group meetings and survey participants.

By assessing challenges faced and uses them as learning opportunities, as well as focus on the best of what exists and aspirations for what is desired.

The evaluation was carried out under the control of the reference group which has been established in order to obtain critical input and feedback during key stages of the evaluation.

With honesty and collection of meaningful input at all stages of the evaluation while being culturally sensitive.

Coffman, J. (2007). “Evaluation based on theories of policy process”. The evaluation exchange, vol. XIII, no. 1&2, Spring (www.hfrp.org/evaluation/the-evaluation-exchange/issuearchive/advocacy-and-policy-change/evaluation-based-ontheories-of-the-policy-process, Access date: 22/11/2019).

The evaluation exchange, volume XIII number I, spring 2007, p.29, Evaluating an Issue’s Position on the Policy Agenda: The Bellwether Methodology.

Blair, E. 2016. Harvard Family Research Project. Presidents and Fellows of Harvard College. https://archive.globalfrp.org/evaluation/the-evaluation-exchange/issue-archive/advocacy-and-policy-change/evaluating-an-issue-s-position-on-the-policy-agenda-the-bellwether-methodology (Access date: 20/11/2019)

De Vaus D. 2001. Research Design in Social Research. Sage Publication, London (Ltd). 148p.

The list of people met is available in annex 5.

For child nutrition for example, WHO reports that while the prevalence of stunting decreased between 2000 and 2016, the absolute numbers of stunted children are in fact increasing in West Africa: from 50.4 million in 2000 to 58.5 million in 2016. Cf. WHO’s Africa Nutrition Report (2017).

As per the 2015 Annual report. Federation of African Nutrition Societies (FNAUS).

The SUN Movement enables countries to adopt a collaborative approach bringing together the stakeholders and resources necessary for the rapid scaling up of nutrition-specific interventions and the implementation of intersectoral strategies contributing to nutrition. The multi-stakeholder platform harmonizes and coordinates multisectoral actions across the sectors (health, education, agriculture, social protection, empowerment of women, development and poverty reduction).

Institutional memories of the forum met affirmed that Helen Keller International was the first financial partner of the forum in 1996 when it was made off of only 8 francophone countries.

These are WAHO liaison officers from Country’s Nutrition direction who serve as Technical Leads.

This committee is made off of UN Agencies, WAHO Focal point, CSO and religion group such as Caritas.

UN Standing Committee on Nutrition. Food and Nutrition Security in West-Africa: Opportunities and Challenges. No 38 early-2010 ISSN 1564 – 3743.

http://www.unevaluation.org/document/detail/607

https://www.unicef.org/evaluation/files/GEROS_Methodology_v7.pdf

http://www.uneval.org/document/detail/980