Terms of Reference

0

Institutional Consultancy to Conduct an Evaluation of UNICEF’s Public Finance for Children Technical Support to the Ministry of Social Welfare, Relief and Resettlement of the Government of Myanmar – Phase I, II and III

UNICEF Myanmar

- INTRODUCTION

UNICEF recognizes that the decisions governments make about how to fund social policies and services are critical to children and to equitable development overall. And that many of the obstacles to improving child outcomes can be directly traced to Public Financial Management (PFM) challenges. UNICEF’s work on Public Finance for Children (PF4C) tackles these PFM challenges, to achieve strategic results across all areas of programming.

In 2016, UNICEF Myanmar initiated a technical support project to the Ministry of Social Welfare, Relief and Resettlement (MSWRR) of the Government of Myanmar (GoM), with the objective to strengthen its PFM capacities, to support the implementation of policies for children, mothers and vulnerable groups. The technical support was provided by UNICEF in collaboration with the Oxford Policy Management (OPM). The first phase of the project was completed in early 2017, with a second phase from May 2017 to February 2018, then extended until April 2018; and a third phase from October 2018 throughout 2019.

UNICEF is commissioning an Evaluation of UNICEF’s Public Finance for Children Technical Support to MSWRR (Phase I, II and III), to draw lessons learnt and identify good practice for future programming, promote organisational accountability, and enhance learning and documentation. These Terms of Reference (ToR) set out the purpose and objectives, methodological options and operational modalities for an institutional contract of a team of two evaluation consultants (one international and one national). Findings and recommendations from this evaluation will inform the strategic direction of the UNICEF’s engagement in Public Finance for Children (PF4C) in Myanmar, during the 2018-2022 Country Programme. The evaluation is expected to start in January and to be completed by June 2020, for a total duration of approximately nine working weeks (45 days) spread over six months to build ownership and take up. It will be supervised by the UNICEF Evaluation Specialist, in collaboration with the Social Policy Specialist (Public Finance) and a focal point from MSWRR.

- BACKGROUND AND RATIONALE

UNICEF has been globally involved in PF4C advocacy and programming, to address key PFM bottlenecks and barriers to attain the rights of children. Within this broader approach, this project was designed with the intention to consolidate and coordinate the PFM strengthening initiatives in support of MSWRR, undertaken in the 2011-2017 Country Programme, in alignment with the PFM reforms undertaken by the GoM.

There are two elements that define the context for this project and its evaluation: first, the roll-out of PFM reforms; and second, the planned expansion of key social protection programmes, under the leadership of the Department of Social Welfare (DSW) of the MSWRR.

PFM reforms in Myanmar have started quite recently, as part of the broader agenda of the political and economic transition. A Public Expenditure and Financial Accountability (PEFA) assessment performed in 2012 provided a baseline to guide their development. The Modernization of PFM Project, undertaken by the Ministry of Planning and Finance (MoPF) with the support of the World Bank started in 2014. With that support, the Government produced its PFM Reform Strategy, which since then has guided policy making through the first wave of reforms (2014-2018). Some of the contextual weaknesses addressed in the reform strategy include:

- Improving tax collection, including from natural resources;

- Enhancing staff PFM capacities, to undertake effective planning, budget execution, and monitoring of policies and programmes;

- Strengthening policy-based planning and budgeting (e.g., Medium Term Fiscal Framework (MTFF), linking recurrent and capital budgets, costing), and evidence-based planning;

- Improving and securing the flow-of-funds, e.g., computerization of the manual system;

- Strengthening reporting on budget execution;

- Improving budget transparency and participatory processes; and

- Strengthening external oversight, e.g., through Parliament.

Since 2016, UNICEF has committed to contribute to the roll-out of the PFM reforms and in the 2018-2022 Country Programme Document (CPD) has significantly invested to have more capacities and resources to support the GoM. Within the MYWP 2018-2019, a key partnership with the Budget Department of the Ministry of Planning and Finance (MoPF) was initiated, to work on improved evidence, capacity and systems for equity sensitive planning, budgeting and implementation. Within this output, PF4C has worked to:

- Contribute to generate evidence and understanding on trends and issues related to PF4C, at national and subnational level;

- Provide technical and capacity support to MSWRR to strengthen PFM processes, in line with government reforms; and

- Support States and Regions authorities to undertake child and equity sensitive planning and budgeting practices.

UNICEF has been participating in key national fora on PFM coordination, including the (donors-only) PFM Working Group and the Macro-Economic Management Sector Coordination Group (MMSCG). It has strengthened its working relationships with key PFM actors, such as the IMF, WB, EU and DFID. During the development of the Myanmar Sustainable Development Plan (MSDP), UNICEF PF4C positioned itself in support of strategy 2.4, to strengthen PFM to support stability and the efficient allocation of public resources, in full coordination with DPs.

Although not a key PFM actor, UNICEF in Myanmar is uniquely positioned to support PFM strengthening for enhanced provision of essential services for children, adolescents and vulnerable groups. One area of work is in direct partnership with MoPF and involves evidence-generation on public expenditure in social sectors, including Child-focused Public Expenditure Measurement (C-PEM). A second line of work is bridging central PFM reforms with sector-specific PFM strengthening: while the first wave of reforms has focused on central PFM systems (e.g., creation of a Treasury, revenue forecasting, cash management) the second wave is expected to touch more upon central-local and central-sectorial systems and processes, such as budget preparation, electronic submissions, expenditure reporting. In this area, UNICEF can work in coordination with both MoPF and MSWRR.

The focus on the MSWRR emerged as the most strategic choice, as it was the Ministry with specific mandate on children, youth and other vulnerable groups of population, as well as on disaster risk management. MSWRR was expected to substantially scale up on the provision of social services, notably a Maternal and Child Cash Transfer (MCCTs) and a Child Allowance (CA). With this expectation, it was agreed to support MSWRR to strengthen its PFM processes, starting from the areas of strategic planning, aligning plans with budget, prioritization and budget preparation. In this respect, UNICEF also considered that MSWRR had not been supported by other Development Partners (DPs), unlike, for example, the WB for the Ministry of Education.

The provision of social services in Myanmar has been limited in the past. Education, health and social protection have historically received a tiny portion of Union budget funding, which was 4.9 per cent of total government allocations in 2011/12, and had grown until 12.3 per cent in 2016/17. Within social sectors, budget allocations had grown faster for education and health, and were still at a surprisingly low 0.09 per cent of total government’s allocations in 2016/17. Weak absorptive capacity had been mentioned as well as one of the reasons for maintaining low allocations. Thus, if UNICEF’s contribution could improve absorption, it would have been able to expand the activities and increase expenditure.

Social policy areas under MSWRR’s mandate have received significant contributions from DPs: the official ODA (grants) contributing to MSWRR’s 2016/17 budget allocations was 17 per cent. It is quite likely that more funds are invested in these areas, particularly at the level of service delivery, though remain off-budget.

When it comes to decentralization, on one hand a Law amending the Constitution in 2015 has attributed to local governments functional and revenue assignments, for few social policy areas, including children welfare. However, most of these changes remain yet to be operationalized. On the other hand, in terms of de-concentration, MSWRR’s organizational structure has relied on several layers – such as Union, State and Regions, Township – with different roles and responsibilities in the provision of social services.

With this background, and in consideration of the existing Regional Long-Term Agreement (EAPRO-LTA) with the Oxford Policy Management (OPM), UNICEF Myanmar decided to seek technical assistance to ensure support to strengthening PFM of MSWRR. Five project’s components were elaborated, to frame and create space to define more specific PFM initiatives, as well as providing an ideal sequencing during the implementation of the project:

- Component 1 – Awareness and buy-in;

- Component 2 – Planning;

- Component 3 – Budgeting;

- Component 4 – Reporting and accounting; and

- Component 5 – Evidence generation and advocacy

Specifically, the project’s objective was to strengthen MSWRR’s PFM systems, processes and capacities, in full alignment with MoPF reforms, and taking into consideration the sector’s specificities, and to empower the Ministry to implement its mandate for children and other vulnerable groups in Myanmar. The expected results of the project that will be assessed by this evaluation include:

- Output 1: Improved capacity to plan, budget, execute, report, monitor and evaluate, to reflect the needs of the most vulnerable; and

- Output 2: Improved use of budgetary and expenditure data, to allow evidence-based planning, budgeting and reporting.

The targeted ministries for the project are: MSWRR (Department of Social Welfare, Department of Disaster Management and Department of Rehabilitation, specifically admin and finance staff) and MoPF (Budget Department). Other key stakeholders include DPs, population and children of Myanmar. All activities are concentrated in the administrative capital of Myanmar, Nay-Pyi-Taw. The first phase of the project was completed in early 2017, with a second phase from May 2017 to February 2018, then extended until April 2018; and a third phase from October 2018 throughout 2019.

As the project is ending, hence an evaluation is required to take stock of what has been achieved and identify lessons, good practices and innovation to inform future programming in PFM.

- PURPOSE, OBJECTIVES AND SCOPE OF WORK

UNICEF is commissioning an evaluation to produce reliable, credible and useful evidence on the overall contribution of the technical assistance provided to strengthen PFM of MSWRR (summative), designed and rolled out in three consecutive phases. The evaluation, which is expected to be also learning-oriented in nature, will help identify lessons, good practices and innovations to inform the strategic direction of UNICEF’s support towards PF4C in Myanmar (formative).

The purpose of this evaluation is both summative and formative. On the one hand, the evaluation will contribute to determine the extent to which the technical assistance has contributed strengthening PFM systems and processes of MSWRR. The evaluation will consider the project’s approach, results framework, activities, time-frame, M&E, etc. over the entire duration of the project. To the extent possible, it will consider the linkages between PFM improvements and enhanced results in service delivery for children, mothers and vulnerable groups. On the other hand, the evaluation will help UNICEF explore ways to improve its support to PF4C in Myanmar. The evaluation will be used to inform the strategic direction of UNICEF’s support in the upcoming Multi-Year Work-Plan, within the 2018-2022 Country Programme. It will allow to identify lessons, good practices and innovations for scaling up the support provided to the Government.

The primary users of the evaluation include UNICEF Myanmar – notably Social Policy and Child Rights Monitoring, Education and Child Protection sections, – and the MSWRR (duty bearers). Secondary users include relevant line ministries of the GoM, DPs (World Bank, IMF, DFID), EAPRO, and UNICEF Headquarters. It will be shared with UNICEF’s Regional Office for East Asia and the Pacific (EAPRO) and other offices to foster learning on PFM.

The objectives of the evaluation include the following:

- Analyse the strategies used by UNICEF Myanmar and re-construct the theory of change behind the provision of technical assistance to strengthen PFM of MSWRR, to improve essential social services for children, mothers and other vulnerable groups;

- Assess the overall quality and value of the technical assistance, across the five PFM project’s components: (1) Awareness and buy-in, (2) Planning, (3) Budgeting, (4) Reporting and accounting, and (5) Evidence generation and advocacy;

- Examine the evolution of the project’s technical assistance, its likely impact and sustainability, both at the national as well as the sub-national level; and

- Draw lessons learned, identify good practices and innovations that can be applied to future interventions in the area of PF4C.

The technical assistance to strengthen PFM of MSWRR has been the main activities designed and implemented by UNICEF Myanmar to roll-out the PF4C initiative. It has certainly been the most complex, because of the highest customization to the Myanmar context and because it evolved over three phases, in the period of four years. In this period of time, the several developments that occurred both in the PFM country context and the PF4C framework (e.g., issuance of the PF4C Global Programme Framework) were considered in the design of activities. The evaluation will be forward-looking, in providing conclusions and recommendations on what needs to be adjusted in future PFM strengthening initiatives with line Ministries.

Data collection will be conducted mainly in Yangon and Naypyidaw, and possibly in Mandalay Region. This evaluation will not cover an analysis of the overall PF4C portfolio, and it will not include an assessment of MSWRR overall PFM capacities.

Evaluation evidence will be judged using modified Organisation for Economic Co-operation and Development’s Development Assistance Committee (OECD/DAC) criteria of relevance, effectiveness, efficiency, impact and sustainability, as well as equity, gender equality and human rights considerations.

Key evaluation questions (and sub-questions) include the following:

Relevance of the technical support provided to the priorities and policies of the MSWRR and the needs of children and women in Myanmar, including:

- Was the project able to target actual PFM weaknesses, as assessed by MSWRR itself?

- Were the activities and outputs of the five project’s components consistent with the overall goal and the attainment of its objectives? Were the activities and outputs of the project consistent with the intended impacts and effects?

- To what extent are the objectives of the project still valid in strengthening its PFM capacity for children, mothers and other vulnerable groups?

Effectiveness of the technical support in achieving its objectives, including:

- To what extent were the objectives of the technical support achieved or likely to be achieved through the five PFM project’s components?

- What were the major factors influencing the achievement or non-achievement of the objectives and the five PFM project’s components?

Efficiency of project outputs – both qualitative and quantitative – in relation to the inputs provided:

- Were PFM activities cost-effective?

- Were PFM objectives achieved on time?

- Was the project implemented in the most efficient way compared to alternatives?

Impact (positive and negative changes, intended or unintended) resulting from the technical support provided on socio-economic development indicators:

- What has happened as a result of the project? Has, for instance, the fiscal space for children improved?

- What real difference has made the technical support provided to PFM at the national and sub-national level, and in particular to mothers (and/or girls) and the most vulnerable children?

Sustainability of the benefits of technical support provided:

- To what extent did the benefits of the project continue at the end of Phase III?

- What were the major factors which influenced the achievement or non-achievement of sustainability of the project, both at the national and sub-national levels?

- EVALUATION APPROACH AND METHODOLOGY

Based on the objectives of the evaluation, this section indicates a possible approach, methods, and processes for the evaluation. Methodological rigor will be given significant consideration in the assessment of proposals. Hence bidders are invited to interrogate the approach and methodology proffered in the ToR and improve on it or propose an approach they deem more appropriate. In their proposal, bidder should clearly refer to triangulation, sampling plan and methodological limitations and mitigation measures. Bidders are encouraged to also demonstrate methodological expertise in evaluating initiatives related to PFM support.

It is expected that the evaluation will employ both a theory-based and a mixed-methods approach drawing on key background documents and the monitoring framework (established in December 2017) for guidance. The timing of the evaluation is such that it will take both a summative and formative approach, identify and assessing the quality and value of UNICEF’s support, as well as it likely impact and sustainability. The evaluation should consider throughout issues of equity, gender equality and human rights, in line with UNICEF’s Evaluation Policy (2018) and the United Nations Evaluation Group (UNEG) Norms and Standards (2016).

At minimum, the evaluation will draw on the following methods:

- Literature review of PFM, with a focus on technical support provided to governments in developing countries, particularly in the East Asia region;

- Desk review of background documents and other relevant data, including review and analysis of secondary quantitative data;

- Key Informant Interviews (KIIs) with MSWRR (DSW, DDM, DR) and MoPF (BD);

- Focus Group Discussions (FGDs) with relevant stakeholders at the national and sub-national level;

- Case studies of each project component;

- Cost-effectiveness analysis of the technical support provided; and

- Surveys.

Data collection and analysis should be human rights based and gender sensitive. The data collected should be disaggregated by age, gender, state, etc. where relevant and focus on PFM activities both at the national and sub-national level. Sampling of KIIs and FGDs should be done in consultation with UNICEF. Baseline data will be provided based on the project document. Additionally, secondary data sources can be used and they will be made available to the selected bidder through OneDrive.

Likewise, conventional ethical guidelines are to be followed during the evaluation. Specific reference is made to the UNEG Norms and Standards and Ethical Guidelines, as well as to the UNICEF’s Evaluation Policy, the UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluation, the UN SWAP Evaluation Performance Indicator, and the UNICEF Procedure for Ethical Standards in Research, Evaluation and Data Collection and Analysis and UNICEF’s Evaluation Reporting Standards.  Good practices not covered therein are also to be followed. Any sensitive issues or concerns should be raised with the Evaluation Manager as soon as they are identified.

- MANAGEMENT AND COORDINATION

5.1 EVALUATION MANAGEMENT

The evaluation will be conducted by an external Evaluation Team to be recruited by UNICEF Myanmar. The Evaluation Team will operate under the supervision of an Evaluation Specialist at UNICEF Myanmar that will act as Evaluation Manager and therefore be responsible for the day-to-day oversight and management of the evaluation and for the management of the evaluation budget. The Evaluation Manager will assure the quality and independence of the evaluation and guarantee its alignment with UNEG Norms and Standards and Ethical Guidelines and other relevant procedures, provide quality assurance checking that the evaluation findings and conclusions are relevant; and recommendations are implementable, and contribute to the dissemination of the evaluation findings and follow-up on the management response. She will work in collaboration with the Social Policy Specialist in the Social Policy and Child Rights Monitoring section and a focal point from the MSWRR. Together with the Evaluation Specialist, they will form an Evaluation Management Team. Additional quality assurance will be provided by the Regional Evaluation Adviser that will be a member of the Reference Group. The final report will also be approved by the Country Representative at UNICEF Myanmar.

A Reference Group will be established, bringing together representatives from MSWRR, UNICEF MCO SPCRM, UNICEF Headquarters, EAPRO Evaluation section and Social Policy sections and up to two external experts in PFM. The Reference Group  will have the following role: contribute to the preparation and design of the evaluation, including providing feedback and comments on the Inception Report and on the technical quality of the work of the consultants; provide comments and substantive feedback to ensure the quality – from a technical point of view – of the draft and final evaluation reports; assist in identifying internal and external stakeholders to be consulted during the evaluation process; participate in review meetings organized by the Evaluation Management Team and with the Evaluation Team as required; play a key role in learning and knowledge sharing from the evaluation results, contributing to disseminating the findings of the evaluation and follow-up on the implementation of the management response.

5.2 EVALUATION TEAM PROFILE

The evaluation will be conducted by engaging an institution. The proposed team consists of one (1) international senior-level consultant (Team Leader) to conduct the evaluation that will be supported by at least one (1) national consultant (Team Member/Technical Expert).

The Team Leader should bring the following competences:

- Having extensive evaluation experience (at least 15 years) with an excellent understanding of evaluation principles and methodologies, including capacity in an array of qualitative and quantitative evaluation methods, and UNEG Norms and Standards.

- Having extensive experience on PFM interventions – planning, implementing, managing or monitoring and evaluation.

- Holding an advanced university degree (Master or higher) in international development, public policy, public administration, development economics or similar, including sound knowledge of PFM and familiarity with the rights of children.

- Bringing a strong commitment to delivering timely and high-quality results, i.e., credible evaluations that are used for improving strategic decisions.

- Having in-depth knowledge of the UN’s human rights, gender equality and equity agendas.

- Having a strong team leadership and management track record, as well as excellent interpersonal and communication skills to help ensure that the evaluation is understood and used.

- Specific evaluation experience of PFM is strongly desired but is secondary to a strong mixed-method evaluation background, so long as the PFM expertise of the other team member (see below) is harnessed to ensure the team’s collective understanding of issues relating to PFM programming.

- Previous experience of working in an East Asian context is desirable, together with understanding of Myanmar context and cultural dynamics.

- The Team Leader must be committed and willing to work independently, with limited regular supervision; s/he must demonstrate adaptability and flexibility, client orientation, proven ethical practice, initiative, concern for accuracy and quality.

- S/he must have the ability to concisely and clearly express ideas and concepts in written and oral form as well as the ability to communicate with various stakeholders in English.

The Team Leader will be responsible for undertaking the evaluation from start to finish, for managing the evaluation, for the bulk of data collection, analysis and consultations, as well as for report drafting in English and communication of the evaluation results.

One (1) national Team Member/Technical Expert:

- Holding advanced university degrees (Master level) in international development, public policy, development economics or similar.

- Hands-on experience in collecting and analysing quantitative and qualitative data, but this is secondary to solid expertise in PFM interventions.

- Strong expertise in equity, gender equality and human rights-based approaches to evaluation and expertise in data presentation and visualisation.

- Be committed and willing to work in a complex environment and able to produce quality work under limited guidance and supervision.

- Having effective communication, advocacy and people skills and the ability to communicate with various stakeholders and to express concisely and clearly ideas and concepts in written and oral form.

- Excellent Myanmar and English communication and report writing skills.

The Team Member will play a key role in data collection, analysis and presentation, and preparation of the debriefings and will make significant contributions to the writing of the main evaluation report.

The Evaluation Team is expected to be gender and geographically balanced. Back-office support assisting the team with logistics and other administrative matters is also expected.  It is vital that the same individuals that develop the methodology for the RFPS will be involved in conducting the evaluation. In the review of the RFPS, while adequate consideration will be given to the technical methodology, significant weighting will be given to the quality, experience (CV’s and written samples of previous evaluations) and relevance of individuals who will be involved in the evaluation.

5.3 EVALUATION DELIVERABLES

Evaluation products expected for this exercise are:

- An Inception Report (in English), including a summary note in preparation for data collection (in both English and Myanmar);

- A summary of initial evaluation findings from primary data collection (in English), including a desk review analysis and a PowerPoint presentation to facilitate a stakeholder consultation exercise;

- A draft and final report (in English and Myanmar) that will be revised until approved (incl. a complete first draft to be reviewed by the Evaluation Management Team and UNICEF; a second draft to be reviewed by the Reference Group and Regional Evaluation Adviser within UNICEF EAPRO, and a penultimate draft);

- A PowerPoint presentation (in both English and Myanmar) to be used to share findings with the Reference Group in validation workshop and for use in subsequent dissemination events; and

- A four-page executive summary (in both English and Myanmar) that is distinct from the executive summary in the evaluation report and it is intended for a broader, non-technical and non-UNICEF audience. The executive summary should also be produced both in text and video versions (video and photo materials should be collected as part of the evaluation to enrich the evaluation dissemination).

Other interim products are:

- Minutes of key meetings with the Evaluation Management Team and the Reference Group;

- Copy of the data collected in the course of the evaluation; and

- Presentation materials for the meetings with the Evaluation Management Team and the Reference Group. These may include PowerPoint summaries of work progress and conclusions to that point.

Outlines and descriptions of each evaluation products are meant to be indicatives, and include:

- Inception Report: The Inception Report will be key in confirming a common understanding of what is to be evaluated, including additional insights into executing the evaluation. At this stage, evaluators will refine and confirm evaluation questions, confirm the scope of the evaluation, further improve on the methodology proposed in the ToR and their own evaluation proposal to improve its rigor, as well as develop and validate evaluation instruments. The report will include, among other elements: i) evaluation purpose and scope, confirmation of objectives of the evaluation; ii) evaluation criteria and questions; iii) evaluation methodology (i.e., sampling criteria), along with a description of data collection methods and data sources (incl. a rationale for their selection), draft data collection instruments, for example, questionnaires, with a data collection toolkit as an annex, an evaluation matrix that identifies descriptive and normative questions and criteria for evaluating evidence, data analysis methods and a data analysis plan, a discussion on how to enhance the reliability and validity of evaluation conclusions, the field visit approach, a description of the quality review process, a discussion on the limitations of the methodology and ethical considerations; iv) proposed structure of the final report; v) evaluation work plan and timeline, including a revised work and travel plan; vi) resources requirements (i.e., detailed budget allocations, tied to evaluation activities, work plan) deliverables; vii) annexes (i.e., organizing matrix for evaluation questions, data collection toolkit, data analysis framework); and vi) a summary of the evaluation (evaluation briefing note)  for external communication purposes. The Inception Report will be 15-20 pages in length (excluding annexes), or approximately 15,000 words, and will be presented at a formal meeting of the Reference Group.

- Initial evaluation findings report: This report will present the initial evaluation findings from primary data collection, comprising the desk-based document review and analysis of the technical support project. The report developed prior to the first drafts of the final report should be 10 pages, or about 8,000 words in length (excluding annexes, if any), and should be accompanied by a PowerPoint presentation that will be used in a validation workshop with key stakeholders.

- Final evaluation report: The report will not exceed 50 pages, or 25,000 words, excluding the executive summary and annexes; it will be produced both in text and video versions.

- PowerPoint presentation: Initially prepared and used by the Evaluation Team in their presentation to the Reference Group, a standalone PowerPoint will be submitted to the Evaluation Management Team as part of the evaluation deliverables.

- An evaluation briefing note, data and a four-page executive summary (with infographics) for external users will be submitted to the Evaluation Management Team as part of the evaluation deliverables.

- Reports will be prepared according to the UNICEF Style Guide and UNICEF Brand Toolkit (to be shared with the winning bidder) and UNICEF-Adapted UNEG Evaluation Reports Standards as per GEROS guidelines (referenced before). All deliverables must be in professional level standard English and they must be language-edited/proof-read by a native speaker.

- The first draft of the final report will be received by the Evaluation Management Team and UNICEF who will work with the team leader on necessary revisions. The second draft will be sent to the Reference Group for comments. The Evaluation Manager will consolidate all comments on a response matrix and request the Evaluation Team to indicate actions taken against each comment in the production of the penultimate draft.

Bidders are invited to reflect on each outline and effect the necessary modification to enhance their coverage and clarity. Having said so, products are expected to conform to the stipulated number of pages where that applies.

An estimated budget has been allocated for this evaluation. As reflected in Table 1, the evaluation has a timeline of six months from January to June 2020. Adequate effort should be allocated to the evaluation to ensure timely submission of all deliverables, approximately 9 weeks on the part of the Evaluation Team.

Table 1: Proposed evaluation timeline

| ACTIVITY | DELIVERABLE | TIME ESTIMATE | RESPONSIBLE PARTY |
| --- | --- | --- | --- |
| 1. INCEPTION, DOCUMENT REVIEW AND ANALYSIS |  | 3 weeks, concurrent (Jan-Feb 2020) |  |
| - Inception meeting by Skype with the Evaluation Specialist; Chief, Social Policy and Child Rights Monitoring; and Social Policy Specialist | Meeting minutes | Week 1 | Evaluation Team, Evaluation Management Team |
| - Inception visit (incl. initial data collection and desk review; development of evaluation matrix, methodology and work plan, data collection material, drafting of the Inception Report) | Draft Inception Report | Week 1 | Evaluation Team |
| - Present draft Inception Report to the Reference Group | PowerPoint presentation | Week 2 | Evaluation Team, Evaluation Management Team, Reference Group |
| - Receive Inception Report and feedback to Evaluation Team | Evaluation commenting matrix | Weeks 3-4 | Evaluation Manager, Reference Group |
| - Present Inception Report, confirm planning for field visit | Final Inception Report | Week 4 | Evaluation Team, Evaluation Management Team, Reference Group |
| 2. DATA COLLECTION AND INITIAL ANALYSIS |  | 3 weeks, consecutive (Mar 2020) |  |
| - Pilot data collection tools and conduct field-based data collection | - | Weeks 5-7 | Evaluation Team |
| - Prepare initial evaluation findings report and prepare presentation for validation workshop to validate data collection results | Initial evaluation findings report (incl. desk review), PowerPoint presentation, meeting minutes | Week 7 | Evaluation Team, Evaluation Manager, Reference Group |
| 3. ANALYSIS, REPORTING AND COMMUNICATION OF RESULTS |  | 3 weeks, concurrent (Apr-Jun 2020) |  |
| - Prepare and submit first draft of evaluation report | Draft report | Week 8 | Evaluation Team |
| - Receive first draft and feedback to Evaluation Team | Evaluation commenting matrix | Week 9 | Evaluation Manager |
| - Prepare and submit second draft of evaluation report | Draft report | Week 10 | Evaluation Team |
| - Receive second draft and feedback to Evaluation Team | Evaluation commenting matrix | Weeks 11-12 | Evaluation Manager, Reference Group |
| - Prepare and submit penultimate draft of evaluation report | Draft report | Week 12 | Evaluation Team |
| - Submit and present final report to Reference Group and prepare presentation and other materials | Final report, executive summary, PowerPoint presentation, meeting minutes | Week 12 | Evaluation Team, Evaluation Manager, Reference Group |

- PAYMENT SCHEDULE

Unless the proposers propose an alternative payment schedule, payments will be as follows:

- Approved Inception Report: 25% of the contractual amount;

- Approved initial evaluation findings report: 30% of the contractual amount;

- Approved final report: 30%; and

- Approved final presentation and other materials: 15%.

- APPLICATION PROCESS

Each proposal will be assessed first on its technical merits and subsequently on its price. In making the final decision, UNICEF considers both Technical and Financial Proposals. The Evaluation Team first reviews the Technical Proposals followed by review of the Financial Proposals of the technically compliant firms. The proposal obtaining the highest overall score after adding the scores for the Technical and Financial Proposals together, that offers the best value for money, will be recommended for award of the contract.

The Technical Proposal should include but not be limited to the following:

- Request for Proposals for Services Form (provided above).

- Presentation of the Bidding Institution or institutions if a consortium (maximum two institutions will be accepted as part of the consortium), including:

  - Name of the institution;

  - Date and country of registration/incorporation;

  - Summary of corporate structure and business areas;

  - Corporate directions and experience;

  - Location of offices or agents relevant to this proposal;

  - Number and type of employees;

  - In case of a consortium of institutions, the above listed elements shall be provided for each consortium members in addition to the signed consortium agreement; and

  - In case of a consortium, one only must be identified as the organization lead in dealing with UNICEF.

- Narrative Description of the Bidding Institution's Experience and Capacity in the following areas:

  - Evaluation of PFM interventions;

  - Summative and formative evaluation of PFM interventions, ideally implemented by government institutions;

  - Previous assignments in developing countries in general, and related to social inclusion programmes, preferably in East Asia; and

  - Previous and current assignments using UNEG Norms and Standards for evaluation.

- Relevant References of the proposer (past and on-going assignments) in the past five years. UNICEF may contact references persons for feedback on services provided by the proposers.

- Samples or Links to Samples of Previous Relevant Work listed as reference of the proposer (at least three), on which the proposed key personnel directly and actively contributed or authored.

- Methodology. It should minimize repeating what is stated in the ToR. There is no minimum or maximum length. If in doubt, ensure sufficient detail.

- Work Plan, which will include as a minimum requirement the following:

  - General work plan based on the one proposed in the ToR, with comments and proposed adjustments, if any; and

  - Detailed timetable by activity (it must be consistent with the general work plan and the financial proposal).

- Evaluation Team:

- Summary presentation of proposed experts;

- Description of support staff (number and profile of research and administrative assistants etc.);

- Level of effort of proposed experts by activity (it must be consistent with the financial proposal); and

- CV of each expert proposed to carry out the evaluation.

The Technical Proposal will be submitted in hard copy and electronic (PDF) format.

Please note that the duration of the assignment will be from January to June 2020, and it is foreseen that the Team Leader and the Team Member will devote roughly nine weeks of their time to the evaluation. The presence of a conflict of interest of any kind (e.g., having worked for or partnered with UNICEF on PFM in EAPRO on the design or implementation phase will automatically disqualify prospective candidates from consideration).

The Financial Proposal should include but not be limited to the following:

- Resource Costs: Daily rate multiplied by number of days of the experts involved in the evaluation.

- Conference or Workshop Costs (if any): Indicate nature and breakdown if possible.

- Travel Costs: All travel costs should be included as a lump sum fixed cost. For all travel costs, UNICEF will pay as per the lump sum fixed costs provided in the proposal. A breakdown of the lump sum travel costs should be provided in the financial proposal.

- Any Other Costs (if any): Indicate nature and breakdown.

- Recent Financial Audit Report: Report should have been carried out in the past two years and be certified by a reputable audit organization.

Bidders are required to estimate travel costs in the Financial Proposal. Please note that: i) travel costs shall be calculated based on economy class fare regardless of the length of travel; and ii) costs for accommodation, meals and incidentals.

The financial proposal must be fully separated from the technical proposal. The financial proposal will be submitted in hard copy. Costs will be formulated in US$ and free of all taxes.

- EVALUATION WEIGHTHING CRITERIA

The proposals will be evaluated against the two elements: technical and financial. The ratio between the technical and financial criteria depends on the relative importance of one component to the other. Cumulative Analysis will be used to evaluate and award proposals. The evaluation criteria associated with this ToR is split between technical and financial as follows:

- Weightage for Technical Proposal = 70%

- Weightage for Financial Proposal = 30%

- Total Score = 100%

a. Technical Proposal:

The Technical Proposal should address all aspects and criteria outlined in this Request for Proposal.

Table 2: Evaluation of Technical Proposal

| The Technical Proposals will be evaluated against the following: |  |  |
| --- | --- | --- |
| REF | CATEGORY | POINTS |
| 1 | Overall response: - Completeness of response - Overall concord between RFP requirements and proposal | 2 3 |
| 2 | Company/key personnel/Individual Consultant: - Range and depth of experience with similar projects - Samples of previous work - References - Key personnel: relevant experience and qualifications of the proposed team for the assignment | 8 5 5 14 |
| 3 | Proposed methodology and approach: - Detailed proposal with main tasks, including sound methodology to achieve key outputs - Proposal presents a realistic implementation timeline | 20 13 |
| Total Technical |  | 70 |
| Only proposals which receive a minimum of 60 points will be considered further. |  |  |

b. Financial Proposal

The total amount of points allocated for the price component is 30. The maximum number of points will be allotted to the lowest price proposal that is opened and compared among those invited firms/institutions which obtain the threshold points in the evaluation of the technical component.

All other price proposals will receive points in inverse proportion to the lowest price, e.g.,

Max. score for price proposal * Price of lowest priced proposal

Score for price proposal X =	       ------------------------------------------------------------------------------

Price of proposal X

UNICEF, PF4C Global Programme Framework, 12/2017.

A second PEFA assessment has started in January 2019

A second wave of reforms has started in 2019.

Elaborated from WB (2014), Modernization of Public Finance Management Project, Project Appraisal Document, Annex 2.

“Public Financial Management reform in social sector in Myanmar”, UNICEF PF4C Project Brief, draft 4_171115.

Sector’s PFM improvements and the relationship with service delivery are subject of increased attention and a growing volume of research, although the analyses is still largely relying on qualitative evaluations

The evaluation questions proposed herein are tentative and they can be revised after the inception mission to reflect the actual learning and accountability priorities.

The proposed methodology is just indicative and based on internal experience in conducting similar evaluations. The will be a need to develop a detailed design, analytical methods and tools during the inception phase based on additional literature review and in consultation with UNICEF Myanmar.

Please refer to: http://www.unicef.org/evaluation

See: https://www.unicef.org/supply/files/ATTACHMENT_IV-UNICEF_Procedure_for_Ethical_Standards.PDF

UNICEF has instituted the Global Evaluation Report Oversight System (GEROS), a system where final evaluation reports are quality assessed by an external company against UNICEF/UNEG Norms and Standards for evaluation reports. The Evaluation Team is expected to reflect on and conform to these standards as they write their report. The team may choose to share a self-assessment based on the GEROS with the Evaluation Manager.

Please note that the timing of the data collection may change depending on the possibility of carrying out KIIs and FGDs and other contextual factors.