Final Inception Report

Evaluation of the Inclusive Education Programme Model UNICEF is implementing in Public Schools

RFP#: 2020-9157988

Submitted to The United Nations Children’s Fund (UNICEF)

Final Inception Report

Evaluation of the Inclusive Education Programme Model UNICEF is implementing in Public Schools

RFP#: 2020-9157988

Submitted to The United Nations Children’s Fund (UNICEF)

Submitted by Edvise ME

on December 23rd, 2020

Submitted by Edvise ME

on December 23rd, 2020

# TABLE OF CONTENTS

TABLE OF CONTENTS	2

ACRONYMS	4

SECTION 1: INTRODUCTION	5

1.1	Purpose of the Study	5

1.2	Key Issues	6

SECTION 2: CONTEXT AND DESCRIPTION OF THE OBJECT OF THE EVALUATION	7

2.1	Global Context	7

2.2	Local Context	10

2.3	Object of the Evaluation	12

SECTION 3: PURPOSE, OBJECTIVES AND SCOPE OF THE EVALUATION	14

3.1	Purpose	14

3.2	Scope of the Evaluation	16

3.3	Divergence with ToR	17

SECTION 4: METHODOLOGY	19

4.1	Approach	19

4.2	Methods	19

SECTION 5: RISKS AND RISK MITIGATION	28

SECTION 6: LIMITATIONS OF THE EVALUATION	29

SECTION 7: ETHICAL CONSIDERATIONS	29

7.1	Informed Consent	30

7.2	Protocols	31

7.3	General Protocols	31

SECTION 8: MANAGEMENT OF THE EVALUATION	33

8.1	Composition and Role of the Team	33

8.2	Evaluation Timeline and Deliverables	35

SECTION 9: ANNEXES	36

9.1	Evaluation Matrix (Separately Attached)	36

9.2	Written protocol to ensure subject’s safety	36

9.3	Written protocol for protection of subjects’ identities	38

9.4	Written protocols for protection of data	40

9.5	Proposed Key Informant Interview Guides	41

9.6	Proposed Focus Group Discussion Guides	70

9.7	Proposed Classroom Observation Tool	107

9.8	Proposed School Tour Observation Tool	111

9.9	Proposed Teachers Survey	116

9.10	Translated Key Informant Interview Guides	122

9.11	Translated Focus Group Discussion Guides	150

9.12	Translated Classroom Observation Tool	188

9.13	Translated School Tour Observation Tool	193

9.14	Translated Teachers Survey	197

9.15	List of Reviewed Documents	204

9.16	Methodological note prepared for interviewers and facilitators - Ethical considerations[1]	206

# ACRONYMS

- CWD: Children with disabilities

- MoE: Ministry of Education

- CRPD: Convention on the Rights of Persons with Disabilities

- CRC: Convention on the Rights of the Child

- NGO: Non-governmental Organization

- SDG: Sustainable Development Goals

- FGD: Focus Group Discussion

- KII: Key Informant Interviews

# SECTION 1: INTRODUCTION

## Purpose of the Study

Since 2013/2014, UNICEF has worked through their implementing partner “Mercy Corps” on Inclusive Education programme, together aiming to enable children with mild to moderate disabilities to enrol and be retained in schools. The services offered include:

- Improving accessibility through the construction of ramps, refurbishing and equipping resource rooms;

- Teacher training, including resource room teachers, on the delivery of inclusive education services;

- Providing resources and material;

- Awareness raising for students, parents and the surrounding community on the importance of inclusive education and the integration of children with disabilities (CWDs) in schools;

- Rehabilitation sessions and assistive devices for children with disabilities (CWDs);

- Referrals and tracking.

UNICEF has been operating in 100 schools since 2014, and will hand over 30 inclusive schools to the Ministry of Education (MoE) based on the transition plan that was developed with the MoE.

UNICEF has commissioned Edvise ME to conduct an evaluation of the Inclusive Education Programme and generate knowledge on:

- the adequacy of the programme delivered in public schools (camps and communities),

- the efficacy of UNICEF support provided to the MoE at the central leve,l

- and how it aligns with the Inclusive Education National Strategy and global good practices.

The ultimate purpose of the evaluation is to inform future UNICEF, and possibly other donors and stakeholders, programmes on disability inclusive education in Jordan.

This deliverable, the Inception Report, is the first under this assignment. The purpose of this report is to provide the context in which the evaluation will be conducted as well as a comprehensive evaluation matrix (Annex 9.1) that delineates the planning and organization of the evaluation. In addition, the report provides a detailed description of the methodology and the work plan that the evaluation team intends to follow. Finally, the report includes all data collection tools, in both Arabic and English, that will be used as guides in conducting all of the field work. Once the report and its details are approved, the evaluation team will be prepared to organize all logistics with the MoE for the field work and commence data collection with the start of the second semester of this academic year.

## Key Issues

The evaluation team did not face any major issues while putting together the Inception Report. Some of the minor challenges that were faced were:

- Planning around the extensive uncertainty surrounding the  situation of schools reopening come February 2021. Due to the pandemic situation in Jordan, schools are currently closed and it is unclear whether they will reopen for the next semester. Hence the evaluation team had to consider multiple scenarios for conducting the field work. This Inception Report presents all potential scenarios so that the client is informed of the possible limitations of certain scenarios.

- Some of the Programme’s specific documents, especially the progress reports, are very concise and specific to a number of output level indicators. This required conducting several extensive discussions with the implementing partner and reviewing other supporting documents for the evaluation team to gain sufficient understanding of the programme and its components.

It is important to note that the above challenges were minor and were overcome.

# SECTION 2: CONTEXT AND DESCRIPTION OF THE OBJECT OF THE EVALUATION

## Global Context

Inclusive education is not a new concept. The term “inclusive education” was used for the first time in the Salamanca Statement to describe “schools for all” – places that celebrate differences and where learning and individual differences are supported. Inclusive education was described as a process, not a destination or a tangible target.

Overtime, the definition has changed but the core message remains the same. UNESCO defines inclusive education as “a process of addressing and responding to the diversity of needs of all learners through increasing participation in learning cultures and communities, and reducing exclusion within and from education. It involves changes and modifications in content, approaches, structures and strategies, with a common vision which covers all children of the appropriate age range and a conviction that it is the responsibility of the state to educate all children.”

From a practical standpoint, inclusive education is a transformative way of education that requires a systemic change and includes philosophy, strategies, activities, and processes to make the right to education for all a reality. Since 2015, and the promulgation of the Sustainable Development Goals, inclusive education became a means to achieve goal 4: “ensure inclusive and equitable quality education and promote lifelong opportunities for all” .

As promoted by the Convention on the Rights of persons with Disabilities (CRPD),     (signed and ratified by Jordan in 2007 and 2008, respectively), it requires the dual action of actively removing barriers to education for children with disabilities and creating “environments in general schools that are child-centred and include representation of the full spectrum of people found in society – not just persons with disabilities”.

Despite 25 years of research, inclusive education continues to be misunderstood and only partially promoted. Thus, in 2016, the CRPD Committee adopted the General Comment nº4 on Article 24 of the CRPD (CRPD GC4), aiming to clarify not only what is meant by inclusive education but also what are the responsibilities of signatory countries. Article 24 states that children with disabilities should not be discriminated against but also that they should be able to participate in the general education system and goes beyond to identify what signatory states should provide to ensure compliance with the Article.

General Comment nº4

According to the CRPD GC4 inclusive education is central to achieving high-quality education for all learners, must be realized at all levels (preschool, primary, secondary and tertiary education, vocational training and lifelong learning, extracurricular and social activities), for all students, including persons with disabilities, without discrimination and on an equal basis with others.

Inclusive education entails a transformation in culture, policy, and practice a commitment to removing barriers, and the strengthening of the capacity of the education system to reach out to all learners. It focuses on the full and effective participation, accessibility, attendance, and achievement of all students without discrimination. It is a process of systemic reform embodying changes and modifications in content, teaching methods, approaches, structures, and strategies. State parties must commit sufficient financial and human resources in order for that systemic reform to be possible and realized. In order for systematic reform to be possible and realized, state parties must commit sufficient financial and human resources.

Core Features of Inclusive Education are:

- A “whole systems” approach: all resources are invested in advancing inclusive education.

- A “whole educational environment” embedding the culture, policies, and practices.

- A “whole person” approach: recognition is given to the capacity of every person to learn, and high expectations are established for all learners. Inclusive education offers flexible curricula, teaching, and learning methods that are adapted to different strengths, requirements, and learning styles. The focus is on the learners’ capacities and aspirations, rather than on content when planning teaching activities.

- Supported teachers: all teachers and other staff receive the education and training needed for them to acquire the core values and competencies to work in  inclusive learning environments.

- Respect for and value of diversity: all members of the learning community are equally welcome and must be shown respect for diversity.

- A learning-friendly environment: inclusive learning environments are accessible environments where everyone feels safe, supported, stimulated, and able to express.

- Effective transitions: learners with disabilities receive support to ensure the effective transition from learning at school to vocational and tertiary education and, finally, to work (life-long focus).

- Recognition of partnerships: The relationship between the learning environment and the wider community must be recognized as a route towards inclusive societies.

- Monitoring: Including persons with disabilities.

The right to inclusive education is assured without discrimination and on the basis of equality of opportunity. Discrimination includes the right not to be segregated, and must be understood in the context of the duty to provide accessible learning environments and reasonable accommodation. Accessibility benefits groups of the population and is based on a set of standards that are implemented gradually. Reasonable accommodation relates to an individual and is complementary to the accessibility duty. Modes and means of teaching should be accessible and teaching should be conducted in accessible environments.

The exclusion of persons with disabilities from the general education system should be prohibited, including through any legislative or regulatory provisions that limit their inclusion on the basis of their impairment or the degree of that impairment. It must support the creation of opportunities to build on the unique strengths and talents of each individual with a disability.

The education system must comprise four interrelated features: availability, accessibility, acceptability and adaptability. Compulsory, quality, free and accessible primary education is an immediate obligation. States parties have a specific and continuing obligation to move as expeditiously and effectively as possible towards the full realization of article 24. This is not compatible with sustaining two systems of education.

- Must consider the child’s own views and individual identity, the preservation of the family, care, protection and safety of the child, any particular vulnerability, and the child’s right to health and education.

- Provide habilitation and rehabilitation services within the education system, at the earliest stage possible, be based on a multidisciplinary assessment of a student’s strengths and support maximum independence, autonomy, respect of dignity, full physical, mental, social and vocational ability and inclusion and participation in all aspects of life.

Current Trends towards Inclusive Education

The UNESCO Global Education Monitoring Report of 2020 (as well as several of its background papers) adopt and promote a view of inclusive education that is encompassing and aligned with the SDG Agenda and with the CRPD GC4. In addition, a new UNESCO website – PEER – provides comparable data across countries of  their progress in  inclusive education. The Profile on Jordan (here) offers a comprehensive view of inclusive education in Jordan across various criteria: definitions, school organization, laws and policies, governance, learning environments, teachers and support personnel, and monitoring and reporting.

## Local Context

Historical Background

As is the case with many countries, charitable societies namely Non-governmental Organizations (NGOs) were the first to open centers for persons with disabilities in Jordan. The first was established by the Holy Land Institute for the Deaf in 1965. Several other organizations followed suit and opened centers for the persons with intellectual disabilities, the persons with hearing impairments and persons with visual impairments.1, 2

The first government unit for special education was established in 1977 under the Department of Social Affairs in the Ministry of Labor. This unit was responsible for starting the first two governmental centers for persons with intellectual disabilities and for persons with hearing impairments. 1, 2

Two years later in 1979, the Department of Social Affairs separated from the Ministry of Labor and became its own entity, which is now the Ministry of Social Development. The special education unit within the Ministry was elevated to the level of a department responsible for licensing and supervising all services for persons with disabilities, provided by both governmental and non-governmental entities.1, 3

In regard to education, the Ministry of Education is responsible for providing all its school aged citizens with a free public education. This daunting task was exacerbated due to the political unrest of its neighbouring countries in the past 30 or more years and the influx of refugees to Jordan. This influx exacerbated the challenges, pertaining to access as well as quality, for the education sector, both public and private. Hence, inclusive education may have been pushed down the priority list, especially in light of the scarce financial resources and competing priorities.

During this 30-year period, the number of special centers for children with disabilities increased in both the private and public sectors. However, a large number of children with disabilities are not receiving educational programmes and services.

Having listed all the challenges, it is important to acknowledge that there has been a slow and gradual process for the MoE to move toward inclusive education. This is supported by some of the important milestones, at the international and national levels, that have impacted Jordan’s progress towards inclusive education.

International Level

Jordan signed and ratified several International agreements and conventions that impact the education of children with disabilities:

- The United Nations Convention on the Rights of the Child (CRC) signed in 1991, confirms that all children have the right to education and training. 7

- The Salamanca Statement and Framework for Action on Special Needs Education in 1994, which was an important catalyst for inclusive education internationally, reiterated the right of all children to quality education. It affirmed that all children with and without disabilities should receive education in regular schools.8

- The Convention on the Rights of Persons with Disabilities (CRPD) signed in 2008 added to the previous agreements that children with disabilities have the right to education in free compulsory primary and secondary education.

- The CRPD Article 24 General Comment #4 (Right to Inclusive Education) of 2016 that specifies what constitutes inclusive education and establishes the normative guidelines for signatory countries.

National Level

It has taken several years for inclusive education to become part of the policy framework in Jordan:

- As a result of the Conference for Educational Development in 1987, the Ministry of Education accepted the responsibility of educating children with hearing, visual, and physical disabilities which had been under the auspices of the Ministry of Social Development until then.

- In 1989, a provisional act for the Welfare of Disabled People was initiated but wasn’t ratified till 1993. It stipulated that all persons with disabilities have the right to receive health services, rehabilitation, and to work according to their abilities.

- In 2007, when the new law for the Welfare of Disabled People was ratified, the education of students with disabilities was mandated.  This law was instrumental in ensuring the Ministry of Education and the Ministry of Higher Education to become responsible for providing education to students with disabilities in inclusive settings.2

- Consequently, the Ministry of Education ventured to open 800 resource rooms for children with learning difficulties. They also opened 15 special classes for children with developmental delays and intellectual disabilities.

- In 2017, law 20 for the Rights of Persons with Disabilities confirmed the right for all to be educated, prohibited their exclusion from schools, and stipulated that educational policies, plans, and programs should include persons with disabilities.

- The 2018 Education Strategic Plan of the Ministry of Education reiterated the necessity to improve education for all students and in particular aimed at raising the enrolment rate for all students with disabilities.

It is the combined effect of Law 20 of 2017 and the Ministry’s Strategic plan of 2018 that prompted the Ministry of Education to work with the Higher Council for the Rights of People with Disabilities to develop the Ten-year Strategy for Inclusive Education. This Strategy was launched in January of 2020 and its implementation is expected to start in the school year of 2020-2021.

Statistics

Despite the above-mentioned key steps achieved by the MoE toward inclusive education, there remains major challenges to overcome and extensive work to be put in place. According to the Ministry of Education’s statistics for 2018/2019, 1,396,868 students were enrolled in schools. The number of students with disabilities enrolled in Ministry of Education schools were 21,859 and in Ministry of Social Development centers were 5,859. That is a total of 27,718 students with disabilities receiving some form of educational services, i.e. 1.9% of the total school population.7 The international percentage for students with disabilities is estimated to be about 10% of the total school population.4 This means that there are an estimated 110,000 students with disabilities that are not receiving any educational services.

## Object of the Evaluation

For the past 5 years, UNICEF has been working through its implementing partner Mercy Corps to implement an Inclusive Education Programme in public schools to ensure that children with disabilities have equal access to quality education.

The UNICEF intervention included:

- Improving the accessibility of schools through the construction of ramps as well as refurbishing and equipping Resource Rooms in some schools.

- Providing children with disabilities (CWDs) with rehabilitation sessions and assistive devices.

- Improving the quality of education available to children with disabilities, through building the capacities of teachers, including resource room teachers, on the delivery of inclusive education services, and deploying shadow teachers (assistant teachers) inside the schools.

- Developing a referral and tracking system for those children with disabilities who wish to return or enrol back into the system (either formally or informally).

- Conducting several awareness sessions for parents and the surrounding community on the importance of inclusive education and the inclusion of children with disabilities in school.

To date, UNICEF has been operating in 100 schools (20 schools in Azraq and Za’atari camps and 80 schools distributed across the Jordanian governorates). As a result, UNICEF has integrated around 4,700 children with mild to moderate disabilities into the system, trained 2,081 teachers, and raised awareness of 19,781 parents who have participated in their  awareness programs.

This year, UNICEF has started working with Mercy Corps and the MoE at handing over 37 schools to the MoE. Selection of schools were made according to:

- Evidence that these schools have the capacity to continue implementing the inclusive education programme with minimal support from MC’s specialists.

- Schools’ staff have received training on Inclusive Education.

- The school is operational and organized, including the resource room, to support the CWDs.

The programme involves different stakeholders on multiple levels:

- UNICEF program staff,

- the MoE  who is now working hand in hand with UNICEF to hand-over the selected inclusive schools,

- Mercy Corps who is the main implementer of this programme,

- Schools who are part of this programme to include teaching and non-teaching staff,

- Children with and without disabilities who are either enrolled or not in the education system,

- Parents, caregivers of children, and different community members who were reached through information events and advocacy initiatives.

According to the newly developed operational plan by the MoE , the programme is expected to continue until April 2023.  It aims to apply the Ten-year National Strategy for Inclusive Education pillars through its components. Having said that, the evaluation will help in assessing the programme activities, identify gaps, and potential areas for improvement to inform UNICEF future support.

# SECTION 3: PURPOSE, OBJECTIVES AND SCOPE OF THE EVALUATION

## Purpose

This evaluation, as commissioned by UNICEF and described in this Inception Report, is based on the United Nations principles of a human rights-based (HRB) approach to development. As required, it is “normatively based on the international human rights standards and operationally directed by promoting and protecting human rights” (UNICEF, 2016). In addition, it acknowledges that “a human rights-based approach to development and gender mainstreaming are complementary and mutually reinforcing”(UNICEF, 2016).

As mentioned in the ToR (p. 1), inclusion is at the core of UNICEF’s work, and is at the core of this evaluation: it aims to determine to what extent the work of UNICEF in education, in Jordan, is inclusive of girls and boys with disabilities, equitable in its implementation, and sustainable in the long run.

This evaluation is set on 3 HRB normative standards:

- Universal Declaration of Human Rights - Article 26: “Everyone has the right to education”;

- Convention on the Rights of the Child (CRC) - Article 28: “recognize the right of the child to education, and with a view to achieving this right progressively and on the basis of equal opportunity”;

- Convention on the Rights of Persons with Disabilities (CRPD) - Article 24: “the right of persons with disabilities to education. With a view to realizing this right without discrimination and on the basis of equal opportunity, States Parties shall ensure an inclusive education system at all levels and lifelong learning”. Also d CRPD General Comment #4 (paragraph 10): “Inclusive education is to be understood as: a fundamental human right of all learners (...), a principle that values the well-being of all students (...), a means of realizing other human rights (...), the result of which is a process of continuing and pro-active commitment to eliminate barriers impeding the right to education”.

In addition to the 3 HRB normative standards, this evaluation will be set upon the working motto of the CRPD and the disability movement “Nothing About Us Without Us” and includes, as main stakeholders, the rights-holders of the programme being evaluated. Thus, as described below, children with disabilities, their parents, caregivers, and extended families are the backbone of this evaluation and will provide essential information  for Goal 1 - Objective A (below). This evaluation will not be possible without the direct engagement  of the rights-holders.

As per the evaluation ToR (p.3), this formative evaluation’s higher-level purpose is to inform future UNICEF programmes on inclusive education in Jordan. The more specific purpose is to generate knowledge on:

- The adequacy of UNICEF's inclusive education programmes delivered by Mercy Corps in public schools in camps and host communities; The support UNICEF provided to the MoE at the central level and how it aligns to the Inclusive Education National Strategy as well as  to global good practices.

In addition, two  objectives for this evaluation have been set by UNICEF and those are:

- Assess the quality of the inclusive education package provided by UNICEF and delivered by Mercy Corps at the school level in camps and communities.

- Define how UNICEF can better support the MoE to operationalize and implement the Inclusive Education National Strategy in the coming three years.

The evaluation team proposes that four actions be associated to the Purpose and Objectives as follows:

| Purpose | Objectives | Actions |
| --- | --- | --- |
| 1. Generate knowledge on the adequacy of the UNICEF’s inclusive education programmes delivered by Mercy Corps in public schools in camps and host communities; | 1.1.Assess the quality and adequacy of the inclusive education programmes delivered by Mercy Corps in camps and communities; | 1.1.1. Understand how these services support access, and quality (specifically retention and promotion through grades); 1.1.2. Understand the extent to which the inclusive education programme reflects global good practice. |
| 2. Generate knowledge on the support UNICEF provided to the Ministry of Education at the central level and how it aligns to the Inclusive Education National Strategy and to global good practices. | 2.1. Gather recommendations as to how UNICEF can better support the Ministry of Education, in the implementation of the Inclusive Education National Strategy (3-year plan) 10 year plan | 2.1.1. Understand how the Ministry of Education benefitted from technical data and evidence generated through UNICEF’s inclusive education programme. 2.1.2. Understand how these services could be sustained by the government |

In order to fulfil the Purpose and Objectives of the evaluation, various stakeholders will be involved at the national level. The proposed methodology, as described in Section 4, demonstrates the inclusive nature of the evaluation where an extensive number of rights-holders and duty-bearers will be directly engaged and heard during the evaluation.

## Scope of the Evaluation

The evaluation’s scope aims to cover the following key elements:

- Access: which includes accessibility and the availability of  resources and materials, including assistive devices and services such as rehabilitation sessions and referrals.

- Quality: which includes the teacher training provided and the programme’s ability to enrol, retain and advance students.

- Demand: which includes the raising awareness efforts to elevate awareness of students, parents, and the community.

- System strengthening: which includes the support provided to the MoE toward sustainability and that entails the advocacy, data, and evidence generation efforts.

In order to fulfil the scope and answer the main evaluation questions, the evaluation team formulated questions based on OECD/DAC “Guidelines for Project and Programme Evaluations”. Thus, the criteria and associated questions are:

| Criteria | Evaluation Question |
| --- | --- |
| Relevance | - To what extent the inclusive education programme objectives respond to the Ministry of Education priorities and beneficiaries’ needs? |
| Effectiveness | - To what extent was the inclusive education programme inline with inclusive practices and effective in delivering results for children with disabilities? |
| Cost efficiency and effectiveness | - To what extent was the inclusive education programme cost effective? - What is the breakdown of costs per child with disability? |
| Impact Long-term | - To what extent did the inclusive education programme contribute to a positive long-term change for children in general and children with disabilities in particular, teachers and improved the current situation in terms of education, environment, social cohesion. - for all children, with and without disabilities, and teachers , as well as improve the current situation …... |
| Sustainability | - To what extent can the inclusive education model be replicated, expanded, and sustained? - To what extent has the upstream work (advocacy, technical assistance, generation and use of data and evidence) of UNICEF undertaken with the MoE contributed to the institutionalization of the programme? |
| Coverage | - Is the inclusive education programme targeting children with disabilities and the vulnerable populations in Jordan |

The above listed criteria and questions were parsed out , into sub-questions which then  formulated and guided the development of the data collection tools. The below matrix organizes the logic through which the evaluation will follow in order to gather data and generate sufficient knowledge that would answer the set questions and lead the evaluation team to suggest practical evidence-based recommendations to UNICEF and its partners, particularly Mercy Corps and the MoE.

The Matrix includes the following elements:

- Criteria and corresponding evaluation questions.

- Sub Questions under each evaluation question.

- Indicators for each evaluation question.

- Data sources for each evaluation question.

- Methods for each evaluation question.

## Divergence with ToR

There are two potential slight divergences between the ToR and the proposed methodology, which are both  related to the evaluation questions.

The first is related to the criteria “Cost efficiency and effectiveness”, and its associated evaluation question: “To what extent was the inclusive education programme cost effective?”. Since the project being evaluated has been implemented by Mercy Corps with a substantial - but not exclusive - financial contribution from UNICEF, the evaluation team finds it unlikely that a direct link between financial contribution and outcome can be clearly made.  Furthermore, the costs under the UNICEF funded programme might not be those that would be true for the MoE should the institution take over the interventions and their costs and therefore, it is difficult to inform the financial sustainability of the programme. Having said that, the evaluation team intends to:

- Explore the matter with representatives of the MoE to assess to what extent they believe the ministry has the capacity to take over the responsibility of the programme, what elements of the programme, and what is in place (budget, policies, technical capacity) to enable it do so

The second is related to the “Coverage” criterion and its associated evaluation question that attempts at finding confirmation the programme has reached vulnerable populations. The evaluation team recognizes the potential variation in definitions that could exist across different stakeholders of “vulnerable populations” and how broad the term may be and therefore, suggests the divergence and focus on the following:

- Explore with different partners (including UNICEF, Mercy Corps and MoE) of their definition of “vulnerable populations”

- Explore with different partners the criteria against which the intervention schools were selected. It is necessary to explore in detail the processes of the school selection criteria and the students' enrolments with the representatives of Mercy Corps as well as the MoE.

- Explore with the different partners if the selected schools actually fulfil the developed criteria.

# SECTION 4: METHODOLOGY

## Approach

The evaluation, according to the ToR, was envisioned to cover three main elements under Methodology, which are: Desk review, Focus Group Discussions (FGD) in a sample of 22 Field Directorates in Jordan (with caregivers, children and teachers), and Key informant Interviews (KII) with representatives of key stakeholders.

The evaluation team captured the above and went beyond by  organizing its overall approach in the following phases:

Phase 1: Desk and Literature Review - leading to the Inception Report (refer to Annex 9.15 for key documents and research results);
Phase 2: Field work/data collection which entails the FGDs, KIIs as well as a teacher’s survey.

Phase 3: Analysis - leading to the Draft Evaluation Report.

Phase 4: Presentation and Final Report.

## Methods

The evaluation team has partially completed Phase 1, which is concerned with completing the review of all relevant literature.  We say “partially” because the evaluation team believes the review of relevant documents will continue throughout the assignment as more documents are made available.

Thus, the review has substantially served in identifying critical issues emerging, and gaining information needed on the programme that assisted to fine-tune the data gathering tools and protocols.

A preliminary bibliography can be found in Annex 9.15, which will be expanded as applicable and as more documents are made available. A complete Desk Review will be presented in the Final Report.

This section of the report covers one of the most critical elements of the inception report; it outlines the specifics of the proposed methodology, which will be followed under Phase 2 of this evaluation.

### 4.2.1 Detailed Proposed Methodology

The proposed data collection methodology is three-pronged:

- Conducting KII’s with key representatives of concerned entities

- Conducting school visits during which  KII’s, FGD’s, school tours and classroom observations will be implemented.

- Teacher Survey which aims at gathering perceptions of a wider population of teachers who have been engaged in the programme, including resource room teachers . The survey will also target teachers who were provided with UNICEF training whether they still currently work at the targeted schools or not. Teachers will be chosen based on the availability of contact list provided by UNICEF and its implementing partner Mercy Corps. It includes shadow teachers and classroom teachers who were provided with capacity building courses, and who have worked during the five year evaluation period in the inclusive program.

This mixed approach methodology will assist the Edvise ME  evaluation team to identify, collect, and validate qualitative data from different stakeholders with valuable perspectives on the programme at a higher strategic/policy level as well as an operational level.

Data collection methodology considerations:

- In addition to  the Edvise ME team and data collection consultants, note takers will be present in each session to record and document the results.

- Both data collection consultants and note-takers will receive training on data collection methodologies and ethical guidelines prior to the start of fieldwork.

- Training of the data collection team and note-takers includes general fieldwork protocols such as; acceptable terminology which is used to address/ speak of people with disabilities, demeanour, physical appearance -the importance of dressing modestly and conservatively-, and cultural mores amongst others.

- Additional consultants -who will also receive the mentioned training- will be on stand-by to step-in if any member/s of the data collection team are unable to carry out their duties. Such arrangements are in-place to mitigate risk from illness or otherwise.

- Verbal consents will be gathered by the data collection team from participants to record the sessions for reference purposes.

- The data collection team will introduce all focus group discussions and interviews with a clear introduction of the purpose of the assessment, the external and neutral relationship of Edvise-ME and the importance of their honest participation and data sharing.

- The consulting team will phrase all questions in a neutral manner to encourage discussion without any implied ‘judgment’ or ‘stance’ on any topic through any facial expressions, body gestures, or tone of voice.

- The consulting team will gear the conversation from general questions to more specific questions as discussions are taking place. The consultant will facilitate the conversation to maintain focus but also allow some natural flow and divergence for a few minutes.

- The consulting team will try and include everyone in the conversation to ensure different perspectives are heard and the discussion is not dominated by one or a few.

- Questions will be standardized, to the extent possible, so that comparison is possible, and trends can be identified.

- The maximum number of participants in each focus group should not exceed 10 for adults, 10 for children, and between 6-7 in focus group discussions with children with disabilities.

- The ideal duration for a focus group is anywhere between 45 to 60 minutes.

- The consulting team will agree with UNICEF on confidentiality terms consistent with UNICEF's regulations and policies

- Facilitators are trained to neutrally and objectively ask questions and address ideas to ensure gathering accurate and unbiased responses.

- Adaptive tools will be used to better engage children with disabilities in the focus group discussions.

- The groups are separated by gender based on the targeted schools. Edvise-ME will target schools of  both genders.

- In ‘out of school’ children, the groups will be mixed and will be carried out at Makani Centers.

- All groups will be conducted in a safe and neutral environment.

The Adaptation of Edvise-ME’s methodologies due to the COVID-19 pandemic include, but are not restricted to, the following:

- All team members, consultants, and note takers will adhere to health and safety rules and regulations in accordance to the defence act number 11. It  states that all the necessary measures related to the COVID-19 pandemic will be implemented including social distancing, the wearing of masks and gloves. Edvise-ME will also provide sterilization gels for all members involved in fieldwork as well as participants.

Below is the detailed description of the methodology:

      - Key Informant Interviews:

The consulting team will conduct up to 8 key informant interviews (KIIs) with different stakeholders to ask about their informed opinions of:

- Inclusive education in Jordan.

- The UNICEF funded Inclusive Education Programme.

- Challenges and possibilities of sustainability, replicability, and expansion.

- What recommendations for future programming.

The KIIs  are broken down as follows::

- Two KIIs with representatives from UNICEF: particularly the Chief of Education, and the Disability Focal Point at UNICEF.

- One KII with the implementing Partner: particularly the current Mercy Corps programme manager and the previous Mercy Corps programme manager.

- Two KII with representatives at the Ministry of Education: at the central level such as the Managing Director of the Managing Directorate of General Education, Head of the Special Education Department, Representative from the Managing Directorate of Training and Supervision, Head of CWD Programmes, Head of Disability Section.

- One KII with a representative at the Higher Council for the Rights of Persons with Disabilities: more specifically a staff member who was engaged in the development of the National Inclusive Education Strategy.

- Two KII with representatives at the GIZ and FCDO who are involved in the development and/or implementation of the inclusive education programme.

Guiding questions for the KIIS have been prepared and can be found in Annex 9.5

      - School Visits

Edvise ME will have two data collection teams prepared to take on the field work; each team will be led by a senior consultant and one or two other data collectors to support as necessary with the data collection and note-taking. All data collectors will be trained by our senior consultants on the tools and required protocols for data collection.

The team's plan is to conduct a total of 10 school visits which will include the following:

- Focus group discussions/Interview: The evaluation team will conduct a total of 8 FGD’s and 1 KII in each of the 10 schools that will be visited as follows:

- (1) interview with the school principal, and supervisor (if applicable and possible)

- (1) FGD with teachers, resource room teacher, shadow teachers (as applicable),

- (1) FGD with parents and caregivers.*

- (3) FGD with children with disabilities: one with children aged between (6-9), one with children aged between (10-14), one with children aged (15-18). *

- (3) FGD with children without disabilities: one with children aged between (6-9), one with children aged between (10-14), one with children aged (15-18). *

* These groups include mixed genders and nationalities based on location.

The focus group discussions will gather data from the primary stakeholders of the programme. This data will provide the evaluation team with the stakeholders’  perceptions of the programme (from their perspective and point of view), what worked and what did not, what more is needed within the wider context of the possibilities and challenges pertaining to inclusive education in general but in Jordan in particular.

Note: Focus group discussions with children will be broken up into 3 groups to accommodate the three age groups and ensure age-appropriate participation, while avoiding the risk of silencing younger students.

FGD guiding questions have been prepared and can be found in Annex 9.6

- Classroom observations in each school will provide information related to teachers’ ability to deliver information for all students, relationships between students with each other, classroom available resources and facilities, and other information.

The evaluation team will conduct 10 classroom observations - 1 in each school visited - to gather information related to how teachers are delivering information to all students, their relationships with students, the relationships between students (with and without disabilities), and the teachers’ ability to engage students with disabilities and to detect disability as they have been trained to.

The evaluation team also suggests visiting the resource room, should there be one, to observe if the room is being utilized as a resource to provide support for teachers to work effectively with children with disabilities.

The classroom observation tool has been prepared and can be found in Annex 9.7.

School Tour: to assess school facilities and resources, and the extent to which they are accommodating of students with disabilities- in the classrooms as well as other school facilities.

The school tour tool has been prepared and can be found in Annex 9.8.

Schools’ Selection Criteria

Edvise ME will coordinate with the MoE to ensure the school selection takes into account the following factors to guarantee fair coverage and allow for comparability across certain variables:

- Regional coverage (including schools from the North, Middle and South regions)

- Gender (boy’s schools and girl’s schools)

- Period of engagement (among the 85 initial schools versus the 15 schools that more recently joined)

- Availability of shadow teachers VS. remote follow-up

- Type of assistive technology provided to schools

- The concentration and type of disabilities present in each school

- The availability of resource room

- Including at least one model school

- School with inclusive playgrounds (specific to the camps).

With regards to geographic location and regional coverage, following is a proposed initial distribution organized according to the schools’ density list that we received from the implementing partner, Mercy Corps, in each governorate.  The proposed distribution will be finalized based on feedback from UNICEF and the final list of specific schools will be set in collaboration with the MoE.

| Host Communities (8 Schools out of 80) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Central Region |  |  | Northern Region |  |  | Southern Region |  |  |
| Governorate | Total # of intervention schools | Selected Sample | Governorate | Total # of intervention schools | Selected Sample | Governorate | Total # of intervention schools | Selected Sample |
| Amman | 14 | 1 (F) | Irbid | 15 | 2 (F/M) | Karak | 4 | 2 (F/M) |
| Zarqa | 18 | 2 (F/M) | Mafraq | 8 | 1 (F) | Ma’an | 8 | 1 (F) |
| Madaba | 2 | 0 | Jarash | 3 | 0 | Tafileh | 3 | 0 |
| Balqa | 2 | 0 | Ajloun | 2 | 0 | Aqaba | 1 | 0 |
| Camps (2 schools out of 20) |  |  |  |  |  |  |  |  |
| Governorate |  |  | Total # of intervention schools |  |  | Selected Sample |  |  |
| Al Azraq Camp |  |  | 7 |  |  | 0 |  |  |
| Al Za’atari Camp |  |  | 13 |  |  | 2 |  |  |

*this is the initial distribution which may be revised based on the final fieldwork plan.

The teams will also plan to conduct, around every visited school, a total of:

(2) focus group discussions with out-of-school children.

- (1) FGD with children with disabilities aged (10-18).

- (1) FGD with children without disabilities aged (10-18).

Edvise ME plans to coordinate for those FGD’s with multiple parties including the schools themselves (since they would have access to drop-out or unenrolled children), the Makani Center (should there be one in the area) and/or other local community-based organizations that have good outreach within the community.

      - Teacher Survey:

A survey will be sent to all teachers who have been a part of the programme across all 100 schools and who have received training (both classroom teachers and resource room teachers). This will include teachers since the introduction of the program in 2014 based on the availability or their contact information and Edvise-ME’s ability to reach this segment. The survey aims at gathering data regarding demographics, certification, knowledge acquired through the life of the programme, what specific impairments they are familiar with, their beliefs as to children with disabilities right to education, etc. A full survey protocol has been developed and can be found in Annex 9.9.

The Teacher Survey will be administered through SurveyMonkey and the data analysis also generated by SurveyMonkey as well as Zoho. The data from the Teacher Survey will complement that which will be gathered in FGDs and classroom observations, and provide a wider spectrum of information, across the programme.

This method has been added to ensure the evaluation and the recommendations are based on a considerable number of respondents and the focus was on teachers for the evaluation team’s belief in the essential role teachers play in the classroom, and outside the classroom, toward achieving the objectives of inclusive education in Jordanian schools. It is imperative to collect substantial data on teachers’ perspectives of the assistance they have received to evaluate their adequacy and quality.

### 4.2.2 The Different Scenarios during the Second Semester

The above detailed methodology will be implemented should the public schools be open and operational.

However, with the high possibility of schools being shut down or partially closed during the second academic semester due to the pandemic, Edvise ME coordinated with the MoE on devising two scenarios.

Scenario 1 is complete school closure (staff and students alike are not present at schools) which will only be applicable should Jordan have a complete lockdown imposed

Scenario 2 is partial school closure where staff report to school while students learn from home- as is currently the case during the first academic semester).

Scenario 3 is a partial school closure where staff report to school with grades rotating or only providing face-to-face to Kindergarten till Grade 3.

Scenario 4 is if schools are completely open where both staff and students -of all grades- are present.

Specific questions were posed by the evaluation team to guide the discussion with the MoE for scenarios 1 and 2. The details are described in the below table:

| Scenarios | Questions | MoE Responses |
| --- | --- | --- |
| 1st scenario: In case of complete school closures | - Is it possible to conduct interviews with principals and teachers virtually? - Is it possible to conduct FGD’s with students and children virtually? | - The teachers and principals’ discussions can be conducted virtually keeping in mind the potential challenges with connectivity, engagement and responsiveness. - The children’s discussions cannot be done virtually, as many households do not have a stable internet connection or the needed devices. Also, it is also complicated to communicate efficiently and effectively with young children (generally) and specifically with children with disabilities. - The school tours and classroom observations obviously will not be possible. |
| 2nd scenario: In case of partial school closures (teaching staff are working from schools but students are not) | - Is there a possibility to gather the teaching staff and principals to conduct focus group discussions? - Is it possible to gather small groups of children and students (not exceeding a maximum of 8 students) to hold face-to-face focus group discussions? - Is it possible to conduct a tour around the selected schools? - Is it possible to conduct classroom observations? | - Focus Group discussions can be organized with the principals and teachers (maximum of 8 individuals per group) - MoE can provide special permission for the evaluation team to organize and conduct face-to-face FGD’s with students at the school premises (maximum of 8 students per group) - School tours can be done - Classroom observations will not be possible in this case. |

Despite the Ministry of Education’s recent announcements of their intention to open schools during the second academic semester, nothing is yet confirmed or certain.  The current thinking, in terms of plan of action, is as follows per scenario:

| Scenario | Plan of Action |
| --- | --- |
| Scenario 1 is complete school closure (staff and students alike are not present at schools) which will only be applicable should Jordan have a complete lockdown imposed | - Evaluation is put on hold till further notice |
| Scenario 2 is partial school closure where staff report to school while students learn from home- as is currently the case during the first academic semester). | - Evaluation is put on hold till further notice since classrooms observations are not possible |
| Scenario 3 is a partial school closure where staff report to school with grades rotating or only providing face-to-face to Kindergarten till Grade 3. | - Evaluation will proceed- however the start date of the field work will be revised to give schools (staff and students) time to adjust and settle into a comfortable routine |
| Scenario 4 is if schools are completely open where both staff and students -of all grades- are present. | - Evaluation will proceed- however the start date of the field work will be revised to give schools (staff and students) time to adjust and settle into a comfortable routine |

Edvise ME team will remain flexible and revisit these scenarios based on the announcements of the MoE early 2021.

Despite the uncertainty, the evaluation team devised a field work plan- included below is section 4.2.3.

The plan considers Scenarios 3 and 4 where schools are open and operational for both staff and students (even if it is only selected grades or on a rotational basis).

### 4.2.3 Proposed Workplan

| TASK ID | TASK TITLE | DATE | WEEK 2 (March) |  |  |  |  | WEEK 3 (March) |  |  |  |  | WEEK 4 (March) |  |  |  |  |  | WEEK 1 (April) |  |  |  |  |  | WEEK 2 (April) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S |  | M | T | W | T | S |  | M | T | W | T |
| 1 | Central Region Visits (A total of 4) | 2nd and 3rd weeks of March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | 1st visit | 14-15/Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | 2nd visit | 21-22/Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | 3rd visit | 28-29/Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 | 4th visit | 13-14/April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Southern Region Visits (A total of 2) | The 3rd week of Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | 1st visit | 30-31 / March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | 2nd visit | 6-7/April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Northern Region Visits (A total of 4) | The 4th week of Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | 1st visit | 4-5/April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | 2nd visit | 11-12/April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Camps Visits ( A total of 2) | end of Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | 1st visit | 16-17/Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 | 2nd visit | 23-24/Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Key Informant Interviews | Ongoing during the fieldwork phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*The above timeline is expected to stay the same whether the schools were up and running or partially closed, since an average of 5 focus group discussions are expected to take place each day, and even if some were cancelled due to the COVID-19 situation, some schools/visits might still require 2-day period

# SECTION 5: RISKS AND RISK MITIGATION

The evaluation team has identified a number of potential risks that could have an effect on the evaluation- with varying degrees and levels. The table below lists all identified risks, the entailed assumptions and the planned mitigation measures should the risk present itself during implementation.

| Segment/ Category | Risks and Assumptions | Risk Level | Risk Mitigation Measures |
| --- | --- | --- | --- |
| Ministry of Education (MoE) | Complete closure of schools due to Covid-19 restrictions or governmental lockdowns. | High | The evaluation team suggests the evaluation field work be postponed till the start of the 2021/ 2022 academic year (September 2021) |
|  | Partial closure of schools due to Covid-19 (only staff are at school and classroom observations are not possible) | Medium/High | The evaluation team suggests putting the evaluation on hold |
|  | A closure of one or more of the targeted schools due to cases in those schools | Medium | Pre-agreed upon substitute schools (in the same area) will be on stand-by. |
|  | Delays by the MoE or closure of the MoE due to Covid-19. | Medium | Planning will commence early January so that logistics are done by February |
| Fieldwork | Participants’ are a no-show, cancel last minute, or there are too few participants to conduct group. | Low | The evaluation team will work with MoE to ensure they over-recruit (around 2 participants) per group to ensure that a sufficient number of participants show-up for each group. Also, the proposed sample is substantially large to accommodate for such risks |
|  | Participants’ target profile does not match pre-set criteria | Low | The evaluation team gave sufficient time for field work in case sessions need to be rescheduled or repeated |
|  | ‘Makani’ Centers are inaccessible due to Covid-19 challenges. | Low | The evaluation team will coordinate through the schools or community-based organizations to reach out-of-school children |
| Evaluation Team | Possible illness of an Edvise-ME team member due to Covid-19 or otherwise | Low | Other moderators and facilitators will be trained and put on stand-by to assure that no delays occur in fieldwork. |

# SECTION 6: LIMITATIONS OF THE EVALUATION

As with most evaluations, there are limitations that could lead to incomplete understanding of the situation or inconsistency that would require further investigation.

Some of the identified limitations of this evaluation are:

| Limitation | Measures |
| --- | --- |
| The evaluation will be mostly based on qualitative work which always risks partiality and bias since it is mostly dependant on people’s perspectives and perceptions. | The evaluation team set a multi-pronged approach to have several sources of data that would allow for validation and triangulation. One of which is the teacher survey which is a quantitative tool. |
| The pandemic situation imposing limitations such as inability to conduct FGD’s with primary stakeholders, school tours and observations | The evaluation team has conducted all relevant conversations and devised multiple scenarios for consideration should the situation present challenges |
| The ability to fully and responsibly engage children with disabilities | The evaluation team includes members who have extensive experience with children with disabilities. Any data gathered by proxy (through the children’s companions- if applicable) will be duly analysed and flagged as “potentially subjective”. |

# SECTION 7: ETHICAL CONSIDERATIONS

This evaluation follows the social model of disability as enshrined in the Convention on the Rights of Persons with Disabilities and promoted by UNICEF. The social model promotes children with disabilities as fully capable and autonomous, on an equal standing with all other children, and deserving of the same consideration and rights as enshrined in the Convention on the Rights of the Child. Person-first terminology will be used by the evaluation team. When communication with persons - particularly children - with disabilities, the team will exercise common sense, sensitivity and age-appropriate interpersonal skills. These ethical considerations have been noted in the development of the methodology and will be carried throughout the entire evaluation.

Because children - both with and without disabilities - will be a part of the evaluation methodology, a comprehensive ethics review is needed to ensure their full protection and guarantee their well-being and their rights. The evaluation team will be applying the UNICEF Ethical Standards in Research, Evaluation and Data Collection and Analysis. This means that the methodology for this evaluation and the protocols for data collection will be reviewed by the Ethical Review Board (ERB) that will ensure all planned procedures and tools are in compliance with expectations with regards to subject protection, maximizes their safety, and ensures  informed consent is obtained and their participation is voluntary. Any and all revisions proposed by the ERB will be followed-through before the data collection process starts.

As long-standing professionals with extensive experience working with children and UNICEF procedures, the evaluation team will proceed according to the same UNICEF Ethical Standards in Research, Evaluation and Data Collection and Analysis. Basic Rules of Etiquette (7.3.1 below) have also been put in place to ensure ethical norms are followed, in particular with children and adolescents with disabilities.

Furthermore, taking into account the “do no harm” principle, this inception report provides various scenarios for the successful completion of the research that are responsive to the COVID-19 Pandemic safety norms in place at the time of field-work. While various scenarios are possible and will be discussed with UNICEF and the Ministry of Education, at no time it is envisioned that data collection with children and adolescents will take place unless and until FGs and classroom observations can safely take place.

In all cases (KIIs and FGDs) the purpose of the research will be disclosed clearly at the beginning of each session to ensure that children, parents and their caregivers understand:

- The purpose of the research.

- That their participation is voluntary and can be stopped at any time.

- That children or their caregivers should give consent to their participation.

- That data will be treated confidentially, and records of personal data will be anonymous.

- That anyone is entitled to request information related to the evaluation in whatever format is most adequate for them.

- That they can be provided with help, at any time, if they feel uncomfortable and wish to disclose personal or a traumatic experience

In addition, the below specific measures will be implemented/ put in place to ensure complete compliance with the ethical guidelines throughout conducting this evaluation.

## Informed Consent

All KIIs and FGDs participants will be asked to give verbal consent to their participation in the research. The Survey responders will be asked for consent in the survey form.

Children (under age 16) as well as their parents and caregivers will have to verbally give their consent to participate in the FGDs. Adolescents over age 16 can provide their own consent without needing parent permission.

Once consent has been given, children are expected to participate in the FGDs on their own, to ensure freedom of expression and avoid the influence of adults in their replies. The only exception to this is when “reasonable accommodation” is required to ensure participation (e.g. Sign Language interpreter).

## Protocols

The field teams will follow certain rules and protocols while collecting data to ensure compliance with UNICEF ethical guidelines and safe-guarding integrity, accountability, respect, and beneficence.

## General Protocols

- The consulting team/facilitators will begin any interview/ meeting or focus group session with a clear introduction of the purpose of the assessment, the external and neutral relationship of the contracted consulting firm, and the importance of their honest participation and data sharing.

- The protocol will lay down the basic expectations of the sessions specifically respect of others’ views and of all involved in the assessment.

- The consulting team will phrase all questions in a neutral manner to encourage discussion without any implied ‘judgment’ or ‘stance’ on any topic through any facial expressions, body gestures or tone of voice.

- The consulting team will gear the conversation from general questions to more specific questions as discussions are taking place. The consultant will facilitate the conversation to maintain focus but also allow some natural flow and divergence for a few minutes.

- The consulting team will try and include everyone in the conversation to ensure different perspectives are heard and the discussion is not dominated by one or a few.

- Questions will be standardized, to the extent possible, so that comparison is possible, and trends can be identified.

- The maximum number of participants in each focus group should not exceed 12 participants for adults, 10 participants for children, and maximum of 8 participants in focus group discussions with children with disabilities.

- The ideal duration for a focus group is anywhere between 45 to 60 minutes.

### 7.3.1 Specific Protocols

The following are some basic rules of etiquette to follow throughout the research particularly that the evaluation is covering inclusive education and an important part of the data that will be collected will be from children with disabilities:

- Ask before you act – when in doubt, ask a person with a disability how they would like to be addressed or how you should refer to their impairment or disability.

- Do not speak about a person with a disability as if they are not present, cannot hear you, or cannot understand you.

- In all cases, refer to people by their names – do not describe persons with disabilities as “the little blind girl” or “the man in crutches”.

- Do not talk to adults with disabilities as if they are children and cannot fully understand you or act on their own – even people with communication limitations can understand and take their own decisions.

- Speak from a position that is comfortable to anyone – if needed, sit down or crouch to be at eye level.

- Every person has the right to make their own decisions – if someone uses a wheelchair it may seem easier or faster to decide where/how to go on their behalf. But making decisions is a right and you should give the opportunity and time needed for independent decision-making.

- Do not think in terms of stereotypes, thinking that all persons with disabilities are tired, angry, frustrated, depressed, sick or vulnerable. Persons with disabilities are just people with their own individualities; do not attribute their behaviour to their disability.

- Treat Persons with Disabilities the way you would like to be treated  – respectfully and attentively, not with pity or paternalism.

In addition to the data collection protocols, this inception report also includes:

- Written protocol to ensure subject’s safety

- Written protocol for protection of subjects’ identities

- Written protocols for protection of data

7.3.2 Confidentiality

The consulting team will ensure all measures, in line with UNICEF regulations and policies, are taken to guarantee the confidentiality of all evaluation participants.

All evaluation team members, either in their employment contracts or consulting agreements, have signed on confidentiality terms pertaining to all elements of the assignments.

Hired field data collectors will be trained on all ethical guidelines and associated protocols and will also be required to sign on confidentiality terms.

# SECTION 8: MANAGEMENT OF THE EVALUATION

## Composition and Role of the Team

Below is the team structure to conduct the evaluation in addition to the roles and responsibilities under each position

| Team Member | Roles and Responsibilities |
| --- | --- |
| Project Manager Nour Abu Ragheb | - Ensure objectives are met within timeframe and scope outlined by UNICEF. - Provide guidance and direction to the project team. - Ensure that Edvise ME team who will be facilitating the Focus Group Discussions are consistent with the script and protocols across the three countries. - Review all project deliverables and provide quality input wherever needed. - Work with the project team leader and rest of the team in formulating solid recommendations based on findings. - Support with FGD’s plan and implementation - Conduct key informant interviews with the senior consultant. |
| Team Leader Hala Ibrahim | - Advise on all technical elements of the project to ensure all tools and elements are appropriate and relevant - Conduct focus group discussions with children with disabilities - Conduct school visits and classroom observations - Develop adaptive tools for children with disabilities in collaboration with other team members - Work on the deliverables and draft recommendations using field data. - Prepare all the needed tools/ questionnaires to effectively run discussions/ meetings |
| International Expert Paula Hunt | - Support in conducting secondary research on inclusive education in Jordan - Advise on international evidence and research on inclusive education. - Inform on international best practices and global experiences/ programs. - Support and provide quality input on the process of developing the data collection tools - Support in the analysis of the data gathered from the field in order to evaluate the outputs of the Inclusive Education Programme. - Participate in producing the evaluation report in collaboration with the project manager, team leader and consultant. |
| Senior Consultant Zain Al Hakim | - Lead on all field work to include training of facilitators and data collectors, as well as arrange for transportation and all other field logistical needs. - Conduct focus group discussions with different targeted groups - Conduct key informant interviews with key stakeholders - Participate in producing the evaluation document in collaboration with the project manager, team leader and international expert. |
| Data Collectors and Moderators | - Effectively manage the focus group discussions, through keeping participants focused, encourage everyone to speak up, enforce a respectful tone, manage the pace, and uncover hidden information and hence, generate productive and quality discussion. - Record all focus group discussions for analysis. |

Data Collectors and Moderators

Data Collectors and Moderators

Figure 1: Team Structure

## Evaluation Timeline and Deliverables

The below table illustrates the revised evaluation timeline based on the agreement with UNICEF that should school be open and operational, in which case the evaluation can proceed, the field work will be delayed by 2 or 3 weeks to give schools the chance to settle in. This will of course result in shifting all next steps as illustrated in the below table:

| TASK ID | TASK TITLE | RESPONSIBILITY | DELIVERABLES | DUE DATE |
| --- | --- | --- | --- | --- |
| 1 | Phase 1: Inception |  |  |  |
| 1.1 | Prepare and submit draft inception report | Edvise ME | - Final Inception Report | 12/02/20 |
| 1.2 | Review the inception report | UNICEF JCO and RO |  | 12/16/20 |
| 1.3 | Reflect comments and submit final inception report | Edvise ME |  | 12/23/20 |
| Exams: December 29th- January 18th / Winter break: January 19th- February 4th |  |  |  |  |
| 2 | Phase 2: Field Work |  |  |  |
| 2.1 | Conduct field work | Edvise ME | - (100 ) FGDs - (10) Interviews with school principals - (10) school tours - (10) classroom observations - (8-10) key informant interviews - Teachers survey findings | 03/14/21 to 04/18/21* |
| 3 | Phase 3: Produce Evaluation Report |  |  |  |
| 3.1 | Submit draft evaluation report | Edvise ME | - Evaluation Report - PowerPoint Presentation - Presenting key finding | 05/27/21 |
| 3.2 | Review the draft evaluation report | UNICEF JCO and RO |  | 06/18/21 |
| 3.3 | Reflect comments and submit final inception report | Edvise ME |  | 06/28/21 |
| 3.4 | Review of the final report and provide final approval* | UNICEF JCO and RO |  | 07/08/21 |
| 3.5 | Develop a PowerPoint Presentation | Edvise ME |  | 07/10/21 |
| 3.6 | Present key findings to the review group | Edvise ME |  | TBD |
| 4 | Translation |  |  |  |
| 4.1 | Submit the translated version of the report and presentation | Edvise ME | - Translated evaluation report and PowerPoint presentation | TBD |

*Should UNICEF obtain approvals from MoE on the data collection tools, a workplan was designed to start earlier than the suggested dates.

**Edvise ME will provide UNICEF with the translated version of the final report and presentation noting that the submission date shall be agreed upon in due course subject to the final word count/ number of pages

# SECTION 9: ANNEXES

## Evaluation Matrix (Separately Attached)

## Written protocol to ensure subject’s safety

- The researcher in direct contact with the children participating in the research is obligated to report to law enforcement agencies if he/she suspects or is made aware of a child who needs protection. Children must be made aware during the informed consent process about the researcher’s obligation to report certain incidents, and therefore break the confidentiality.

- This protocol is based on the assumption that children can be safely referred to social services, the police or to emergency services and that these are mandated and able to assess the risks and take all appropriate actions. In other words, we assume that the mere reporting will not exposed children to increased risks.

- The researcher will therefore have at every location where children are going to be interviewed or participate in the focus groups, the list, addresses and phone numbers of the nearest social services/emergency services and police.

- If a child gives signs that he/she is about to disclose past or current situations that are not addressed and still put the child at risk/ need of protection, the researcher will interrupt him/her immediately and warn about the potential need of breaching the confidentiality.

- If the child does not want to go further, the researcher will ask whether he/she feels OK and wants to continue or terminate the interview.

- If the child decides to terminate the interview, the researcher will allow enough time to the child to feel comfortable to leave the room and see his/her parents/caregivers or the social workers. The researcher closes the interview by thanking the child, reassuring him/her that this will not have any consequences on his/her wellbeing or care plan. The researcher also reconfirms that the information that he/she made available will be kept confidential and not shared with anyone.

- If the child does disclose past or current situations that are not addressed and still put the child at risk/in need of protection, the researcher will listen quietly, carefully and patiently without displaying shock or disbelief.  He/she will show acceptance of what is being said without judgement.

- He/she will not assume anything, nor speculate or jump to conclusions. He/she will not investigate, interrogate or decide if the child is telling the truth.

- He/she will let the child explain in his or her own words what happened and will not ask leading questions or open questions.

- He/she will tell the child again that that she must inform relevant people/groups but only those whose job it is to protect children.

- He/she will acknowledge how difficult it must have been to talk and to open up.

- He/she will make some very brief notes at the time and write them up in detail as soon as possible. She will record the date, time, place, words used by the child and how the child appeared to her. She will record statements and observable things, not her interpretations or assumptions.

- He/she will tell the child what she will do and check his/her general status and if he/she feels comfortable to go back home/to the centre etc. or if he/she wants to be accompanied to a safe place.

- He/she will refer the child to the appropriate services, taking into account whom the alleged perpetrators are (family members, social services, police officers or external people) and the urgency of the intervention. He/she will accompany the child to a safe place as requested/needed.

- The researcher will inform UNICEF that a report for a child at risk was made, indicating the date and to which authority.

Reporting Protocols

## Written protocol for protection of subjects’ identities

This research effort aims at evaluating the Inclusive Education Programme on behalf of UNICEF and Mercy Corps.

Assent: If you are willing to participate, please fill in the above questionnaire and consent sheet.

I confirm that I have read and understand the information sheet dated _________
[insert date] explaining the above research project and I have had the opportunity to ask questions about the project.

I understand that my participation is voluntary and that I am free to withdraw
at any time without giving any reason and without there being any negative
consequences. In addition, should I not wish to answer any particular question or questions, I am free to decline.

I understand that my responses will be kept strictly confidential with the 
exception of cases that might reveal that a specific child needs protection.
I give permission to the members of the research team to use the information that I will share with them provided that my responses are confidential. I understand that my name will not be linked with the research materials, and I will not be identified or identifiable in the report or reports that result from the research.

I understand that my participation will not take more than 4 hours of my time and those of the child I am responsible for, including the travel to the place of meeting with the researcher and the travel back.

I understand that my participation and those of the child I am responsible for could cause negative emotions to us because of the remembering of our experience.

I agree to take part in the above research project.

I agree the information about the age, the psychical and physical conditions of the child and the services provided to her/him/our family to be shared with the researcher provided that these details are confidential.

In my capacity of a parent/foster parent/legal guardian [underline the true] of ____________________________________ [insert the name and the family name  of the child] I agree she/he to take part in the above research project under the same conditions.

________________________	________________         ____________________

Name of Participant	Date	Signature

_________________________	________________         ____________________

Name of person taking consent	Date	Signature

To be signed and dated in presence of the participant

Copies:

Researcher’s contact details: [Name], [phone number].

Once this has been signed by all parties, the participant should receive a copy of the signed and dated participant consent form, the information sheet and any other written information provided to the participants. A copy of the signed and dated consent form should be placed in the project’s main records (e.g. a site file), which must be kept in a secure location.

OR, for a parent

Assent: If you are willing to participate, please fill in the above questionnaire and consent sheet.

| - I confirm that I have read and understand the information sheet dated _________ [insert date] explaining the above research project and I have had the opportunity to ask questions about the project. |  |
| --- | --- |
| - I understand that my participation is voluntary and that I am free to withdraw at any time without giving any reason and without there being any negative consequences. In addition, should I not wish to answer any particular question or questions, I am free to decline. |  |
| - I understand that the responses of my child will be kept strictly confidential with the exception of cases that might reveal that a specific child needs protection. I give permission to the members of the research team to use the information that my child will share with them provided that these responses are confidential. I understand that my name or that of my child will not be linked with the research materials, and no member of my family will be identified or identifiable in the report or reports that result from the research. |  |
| - I understand that the participation of my child will not take more than 4 hours of my time and those of the child I am responsible for. |  |
| - I understand that my participation and those of the child I am responsible for could cause negative emotions to us because of the remembering of our experience. |  |
| - I agree to take part in the above research project. |  |
| - I agree the information about the age, the psychical and physical conditions of the child and the services provided to her/him/our family [underline the true] to be shared with the researcher provided that these details are confidential. |  |
| - In my capacity of a parent/foster parent/legal guardian [underline the true] of ____________________________________ [insert the name and the family nam of the child] I agree she/he to take part in the above research project under the same conditions. |  |

________________________________________         ____________________

Name of Participant Date Signature

_________________________________________         ____________________

Name of person taking consent Date Signature

To be signed and dated in presence of the participant

Copies:

Researcher’s contact details: (Name), (phone number).

Once this has been signed by all parties, the participant should receive a copy of the signed and dated participant consent form, the information sheet and any other written information provided to the participants. A copy of the signed and dated consent form should be placed in the project’s main records (e.g. a site file), which must be kept in a secure location.

## Written protocols for protection of data

Edvise Me follows a strict policy of data protection and safe data storage.

Data of primary beneficiaries and service clients will be handled according to the procedures foreseen in the UNICEF ethical guidelines and WHO guidelines on research on violence referenced in the section on adherence to ethical procedures.

Researchers who have access to the identified data will be clearly identified and limited by access procedures to files storages. Research, evaluation and data collection processes that involve human subjects or entail analysis involving sensitive secondary data will be submitted to an internal clearing and data handling process, overseen by the team leader and supported by the project coordination. All direct identifiers to personal informant, particularly children, will either not be collected or removed and anonymised. Hard copies such as interview notes or audio tapes will be kept securely locked away and destroyed after the research process. Files – including computer files – that contain personal or identifiable data, such as names will be encrypted or password protected, and only accessed by agreed members of the team.

## Proposed Key Informant Interview Guides

### Ministry of Education Guide

Hello Mr/ Ms. [name]. I’m here today to discuss with you the UNICEF Inclusive Education Program.

There are no right or wrong answers, I’m seeking your opinion. Everything said in this discussion is confidential and will only be used for research purposes. Neither your identity nor your affiliation will be revealed. We will not disclose any statement attributable to your name. This session will be recorded, however, only members of the research teams have access to the recording. They will also be the only ones to view the full written transcripts.

Do you agree with these rules?

By agreeing to this statement and continuing this interview you are giving our team consent to utilize the information you provide us within the completion of the UNICEF Inclusive Education Programme Evaluation.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- What is your position at the Ministry of Education? (Probe for the head of the education department, special education department) and at the field directorate level (concerned staff such as supervisors)

  - What does your job entail?

  - How long have you worked here?

Introduction

Objective: Understanding the perceptions held towards the Inclusive Education Program from the viewpoint of representatives at the Ministry of Education.

- What role do you play, if any, in the inclusive education program?

- How do you perceive the success of the inclusive education programme?

  - What are the strengths and weaknesses of the programme?

- What are the main challenges faced by the schools in achieving the programme objectives?

- What are the main barriers facing children with disabilities to benefitting from the Inclusive Education programme?

- In 2014, what was the conceptional/policy foundational basis for the inclusive education programme vis-à-vis inclusive education?

- How has the conceptional/policy foundation of the UNICEF inclusive education programme changed between 2014-2019?

- to what extent is UNICEF's support between 2014-2019 reflected in the National Inclusive Education Strategy

- What are the areas in which the programme is conceptually/policy aligned with the National Inclusive Education Strategy (NIES)?

- What are the areas in which the UNICEF inclusive education programme is conceptually/policy divergent with the National Inclusive Education Strategy?

- What can be improved upon from the National Inclusive Education Strategy?

(probe for what is missing from the strategy)

- Would you say that the existing inclusive education programme gender-balanced in its hiring practices? how so?

  - Are girls and boys treated equally by the adults in the programme?

- Does the inclusive education programme include specific measures to tackle inequality? How so?

- Is the inclusive education programme conceptually based on human-rights?

- Do the inclusive education programme documents and language reflect a human-rights and child-centred approach?

- Do you know if the wider school community has been oriented on inclusion?                                                 (parents, caregivers and the wider community, other children...etc)

Transition and Sustainability

Objective: Understanding what MoE representatives think the transition of the inclusive education program will look like and whether he/she thinks the programme is sustainable and expandable.

- To what extent do you think the MoE has the sufficient capacity to take on tasks and lead the whole programme without UNICEF’s support?

(probe for: human resource, financial, technical capacities...etc)

- Do you think the transition from UNICEF to MoE will be smooth? What makes you say that?

- Do you think the inclusive education programme is a sustainable system? Why?

- From your perspective, how capable is the MoE of replicating, and scaling the program in Jordan? Why?

- Does the MoE have the technical capacity to continue running the inclusive education program? Why?

- What can hinder the MoE’s ability to replicate expand the inclusive education program to other schools? Why?

- Do you think the MoE has the budget to continue running the inclusive education program as it is being run now by UNICEF?

- What are the elements to take into consideration while expanding?

- Is the programme's handover plan sufficient toward sustainability envisioned in the national strategy?

- What needs to be put in place to ensure a smooth transition of the programme from UNICEF/Mercy Corps to the MoE?

- To what extent is UNICEF's advocacy work on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is UNICEF's technical assistance on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is UNICEF's generation and use of data on inclusive education and/or children with disabilities evident within the?

  - programme?

  - Ministry of Education policy development?

- When choosing a location for a school to participate in the programme, was an effort made to ensure characteristics associated with vulnerability (e.g. poverty), were taken into consideration?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### Higher Council for the Rights of People with Disabilities (HCD) Guide

Hello Mr/ Ms. [name]. I’m here today to discuss with you the UNICEF Inclusive Education Program.

There are no right or wrong answers, I’m seeking your opinion. Everything said in this discussion is confidential and will only be used for research purposes. Neither your identity nor your affiliation will be revealed. We will not disclose any statement attributable to your name. This session will be recorded, however, only members of the research teams have access to the recording. They will also be the only ones to view the full written transcripts.

Do you agree with these rules?

By agreeing to this statement and continuing this interview you are giving our team consent to utilize the information you provide us with in the completion of the UNICEF Inclusive Education Programme Evaluation.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- What is your position at the Higher Council for the Rights of Persons with Disabilities?

- What does your job entail?

- How long have you worked here?

Context and Background Awareness

Objective: Understanding their perceptions of the current educational system and its compatibility with persons with disability.

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

If not, what needs to happen for the educational system to accommodate children with disabilities?

- What would you say are the biggest challenges in the education of children with disabilities in Jordan? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

Assessing the Inclusive Education Program

Objective: Understanding the audience and their perceptions in regard to the Inclusive Education Program and their perceptions of it, in theory, and in practice.

- What would you say are the biggest challenges in the education of children with disabilities in Jordan? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

- What role, if any, do you play in the inclusive education programme?

- Were you involved in the strategy followed in designing the inclusive education programme in theory? If yes, what role did you have in it?

- In your opinion, was the inclusive education programme implemented according to plan/ strategy?

- To what extent does the Inclusive Education Program overlap with the National Inclusive Education Strategy?

- In your opinion, what are the areas in which the programme is conceptually/policy aligned with the National Inclusive Education Strategy (NIES)? how so?

- In what areas is it divergent with the National Inclusive Education Strategy? how so?

- What can be improved upon from the National Inclusive Education Strategy?

(probe for what is missing from the strategy)

- Would you say that the existing UNICEF inclusive education programme  gender-balanced in its hiring practices? How so?

  - Are girls and boys treated equally by the adults in the programme?

- Does the UNICEF inclusive education programme include specific measures to tackle inequality? please explain.

- Is the inclusive education programme conceptually based on human-rights? please explain.

- Would you say that the inclusive education programme documents and language reflect a human-rights and child-centered approach? please explain.

- How do you perceive the success of the UNICEF inclusive education programme? What makes you say that?

- What are the ‘areas of opportunity’ to enhance the programme in your opinion?

- Would you say that more children with disabilities have enrolled in the schools since the introduction of the inclusive education program in 2014? if not, why do you think that is?

Would you say that schools have retained more children with disabilities since the introduction of the inclusive education program in 2014?  if not, why do you think that is?

- Do you have figures that show there has been an increase between the enrolment and retention of children in schools between 2014 and 2019? if not, who would have these numbers?

- Is there a rehab portion of the inclusive education programme? If yes, what does that include?

- Is there a referral system at schools?

  - what does it look like?

  - why are the students referred?

  - where are they referred to?

Transition & Sustainability

Objective: Understanding the processes put in place that will guarantee a smooth and efficient transition of the inclusive education program to MoE while highlighting the elements deemed necessary for its sustainability and probable expansion.

- Do you think the MoE has the sufficient capacity to take on tasks and lead the whole programme without UNICEF support?

(probe for: human resource, financial, technical capacities...etc)

- What elements/ factors would make the inclusive education programme a sustainable system? why?

- Is the programme's handover plan sufficient toward the sustainability envisioned in the national strategy?

- What are the bottlenecks that could hinder this achievement?

- What needs to be put in place (at UNICEF) to ensure a smooth transition of the programme from UNICEF/Mercy Corps to the MoE?

- To what extent is UNICEF's advocacy work on inclusive education and/or children with disabilities evident within the:

- programme?

- Ministry of Education policy development?

- To what extent is UNICEF's technical assistance on inclusive education and/or children with disabilities evident within the:

- programme?

- Ministry of Education policy development?

- To what extent is UNICEF's generation and use of data on inclusive education and/or children with disabilities evident within the?

- programme?

- Ministry of Education policy development?

- Is there anything else you would like to add?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### UNICEF Guide

Hello Mr/ Ms. ____________I’m here today to discuss with you the UNICEF Inclusive Education Program.

There are no right or wrong answers, I’m seeking your opinion. Everything said in this discussion is confidential and will only be used for research purposes. Neither your identity nor your affiliation will be revealed. We will not disclose any statement attributable to your name. This session will be recorded, however, only members of the research teams have access to the recording. They will also be the only ones to view the full written transcripts.

Do you agree with these rules?

By agreeing to this statement and continuing this interview you are giving our team consent to utilize the information you provide us within the completion of the UNICEF Inclusive Education Programme Evaluation.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- What is your position at UNICEF?

- What does your job entail?

- How long have you worked here?

Context Background Awareness

Objective: Understanding what perceptions are held towards the current education system and its compatibility with children with disabilities.

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

If not, what needs to happen for the educational system to accommodate children with disabilities?

- What would you say are the biggest challenges in the education of children with disabilities in Jordan? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

A Self-Assessment of the Inclusive Education Program

Objective: Understanding the audience and their responsibilities.

- What role do you play in the inclusive education programme?

- How do you perceive the success of the inclusive education programme?

  - What are the strengths and weaknesses of the programme?

- What are the 'areas of opportunity' to enhance the programme in your opinion?

- What was the conceptional/policy foundational basis for the programme?

- Has the conceptional/policy foundation changed between 2014-2019? if so how?

- To what extent is UNICEF's support between 2014-2019 reflected in the National Inclusive Education Strategy?

- In your opinion, what are the areas in which the programme is conceptually/policy aligned with the National Inclusive Education Strategy (NIES)? how so?

- In what areas is it divergent with the National Inclusive Education Strategy?

how so?

- What can be improved upon from the National Inclusive Education Strategy?

(probe for what is missing from the strategy)

- Would you say that the existing UNICEF inclusive education programme gender-balanced in its hiring practices? How so?

  - Are girls and boys treated equally by the adults in the programme?

- Does the UNICEF inclusive education programme include specific measures to tackle inequality? please explain.

- Is the UNICEF inclusive education programme conceptually based on human-rights? please explain.

- Would you say that the inclusive education programme documents and language reflect a human-rights and child-cantered approach? please explain.

- Would you say that more children with disabilities have enrolled in the schools since the introduction of the inclusive education program in 2014?

- Would you say that schools have retained more children with disabilities since the introduction of the inclusive education program in 2014?

- Do you have figures that clearly state there has been an increase between the enrolment and retention of children in schools between 2014 and 2019?

- Do you know how many of the enrolled children have progressed between grades, between 2014 and 2019?

- Do you have figures that clearly state there has been an increase between the enrolment and retention of children in schools between 2014 and 2019?

- Do you know how many of the enrolled children have progressed between grades, between 2014 and 2019?

- Have you (or UNICEF) provided the schools with any materials or resources to aid them in the teaching of students with disabilities?

If no, why?

If yes:

What materials/ resources did you provide?

- Have you (or UNICEF) provided the schools with any assistive technology devices to aid them in the teaching of students with disabilities

- Is there a rehab program in the inclusive education programme? if yes, what does that include? (probe for included services)

- Is there a referral system at schools?

  - what does it look like?

  - why are the students referred?

  - where are they referred to?

Transition and Sustainability

Objective: Understanding the processes put in place that will guarantee a smooth and efficient transition of the inclusive education program to MoE while highlighting the elements deemed necessary for its sustainability and probable expansion.

- To what extent do you think the MoE has the sufficient capacity to take on tasks and lead the whole programme without UNICEF support?

(probe for: human resource, financial, technical capacities...etc)

- What needs to be put in place (at UNICEF) to ensure a smooth transition of the programme from UNICEF/Mercy Corps to the MoE?

- What elements/ factors would make the inclusive education programme a sustainable system? why?

- Is the programme's handover plan sufficient toward the sustainability envisioned in the national strategy?

- What are the bottlenecks that could hinder this achievement?

- What are the elements to take into consideration while expanding?

- To what extent is UNICEF’s advocacy work on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is UNICEF’s technical assistance on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is UNICEF’s generation and use of data on inclusive education and/or children with disabilities evident within the?

  - programme?

  - Ministry of Education policy development?

Efficiency, Effectiveness, and Coverage

Objective: Understanding cost calculations per student and the criteria taken into consideration when choosing a school to join the Inclusive Education Program

- Do you know the cost per student with disability in the inclusive education programme?

If yes,

  - How does it compare to students with disabilities in other programs?

  - How does the cost compare to other students with no disability in the same school?

- What does your cost evaluation take into account?

  - Operational overhead

  - Severity of disability or impartment

  - Logistical organization

  - Materials and resources needed

  - Rehab sessions

  - Cost of infrastructural changes made to school campus and classes

- How do you calculate the cost of each of the mentioned categories?

  - What other factors do you take into account when evaluating the cost per student?

- In your opinion, what defines ' vulnerable populations'? (probe for: refugee status, economic background, nationality…etc)

- What are the criteria that factor into the schools chosen to join the Inclusive Education Programme?

  - Percentage of vulnerable population

  - Location

  - Age of building/s

  - Number of students

  - Number of students with disability at school/ in area.

  - The presence/ or lack of a Makani center nearby.

- Currently, which camps do you have the Inclusive Education Programme in?

  - Why did you choose this camp in particular? (Probe for most vulnerable, reach, population size… etc)

- Is there anything else you would like to add?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### Mercy Corps Guide

Hello Mr/ Ms. [name]. I’m here today to discuss with you the UNICEF Inclusive Education Program.

There are no right or wrong answers, I’m seeking your opinion. Everything said in this discussion is confidential and will only be used for research purposes. Neither your identity nor your affiliation will be revealed. We will not disclose any statement attributable to your name. This session will be recorded, however, only members of the research teams have access to the recording. They will also be the only ones to view the full written transcripts.

Do you agree with these rules?

By agreeing to this statement and continuing this interview you are giving our team consent to utilize the information you provide us within the completion of the UNICEF Inclusive Education Programme Evaluation.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- What is your position at Mercy Corps?

- What does your job entail?

- How long have you worked here?

Context Background Awareness

Objective: Understanding perceptions on education in Jordan in general and particularly for children with disabilities.

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

If not, what needs to happen for the educational system to accommodate children with disabilities?

- What would you say are the biggest challenges in the education of children with disabilities in Jordan? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

A Self-Assessment of the Inclusive Education Program

Objective: Understanding the audience and their responsibilities.

- What role do you play in the inclusive education programme?

- How do you perceive the success of the inclusive education programme?

  - What are the strengths and weaknesses of the programme?

- What was the conceptional/policy foundational basis for the programme?

- Has the conceptional/policy foundation changed between 2014-2019? if so how?

- To what extent is UNICEF's support between 2014-2019 reflected in the National Inclusive Education Strategy?

- In your opinion, what are the areas in which the programme is conceptually/policy aligned with the National Inclusive Education Strategy (NIES)? how so?

- In what areas is it divergent with the National Inclusive Education Strategy? how so?

- What can be improved upon from the National Inclusive Education Strategy?

(probe for what is missing from the strategy)

- Would you say that the inclusive education programme documents explicitly provide a conceptual framework based on the :

  - Convention on the Rights of the Child (CRC) (particularly Article 28)?

  - Convention on the Rights of Persons with Disabilities (CRPD) (particularly Article 24)?

  - CRPD General Comment #4?

  - Sustainable Development Goal #4?

if not, why?

- Would you say that the existing inclusive education programme gender-balanced in its hiring practices? How so?

  - Are girls and boys treated equally by the adults in the programme?

- Does the UNICEF inclusive education programme include specific measures to tackle inequality? please explain.

- Is the inclusive education programme conceptually based on human-rights? please explain.

- Would you say that the inclusive education programme documents and language reflect a human-rights and child-centred approach? please explain.

- How do you perceive the success of the inclusive education programme? What makes you say that?

- What are the 'areas of opportunity' to enhance the programme in your opinion?

- Would you say that more children with disabilities have enrolled in the schools since the introduction of the inclusive education program in 2014?

- Would you say that schools have retained more children with disabilities since the introduction of the inclusive education program in 2014?

- Do you have figures that clearly state there has been an increase between the enrolment and retention of children in schools between 2014 and 2019?

- Do you know how many of the enrolled children have progressed between grades, between 2014 and 2019?

- Do you have figures that clearly state there has been an increase between the enrolment and retention of children in schools between 2014 and 2019?

- Do you know how many of the enrolled children have progressed between grades, between 2014 and 2019?

- Have you (or UNICEF) provided the schools with any materials or resources to aid them in the teaching of students with disabilities?

If no, why?

If yes:

What materials/ resources did you provide?

- Have you (or UNICEF) provided the schools with any assistive technology devices to aid them in the teaching of students with disabilities

- Is there a rehab program in the inclusive education programme? if yes, what does that include? (probe for included services)

- Is there a referral system at schools?

  - what does it look like?

  - why are the students referred?

  - where are they referred to?

Transition and Sustainability

Objective: Understanding what MoE representatives think the transition of the inclusive education program will look like and whether he/she thinks the programme is sustainable and expandable.

- To what extent do you think the MoE has the sufficient capacity to take on tasks and lead the whole programme without UNICEF support?

(probe for: human resource, financial, technical capacities...etc)

- What elements/ factors would make the inclusive education programme a sustainable system? why?

- Is the programme's handover plan sufficient toward the sustainability envisioned in the national strategy?

- Do you think it can be replicated and expanded all over Jordan? How?

- What are the bottlenecks that could hinder this achievement?

- What are the elements to take into consideration while expanding?

- what needs to be put in place to ensure a smooth transition of the programme from UNICEF/Mercy Corps to the MoE?

- To what extent is Mercy Corps's advocacy work on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is Mercy Corps's technical assistance on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is Mercy Corps's generation and use of data on inclusive education and/or children with disabilities evident within the?

  - programme?

  - Ministry of Education policy development?

- When choosing a location for a school to participate in the programme, was an effort made to ensure characteristics associated with vulnerability (e.g. poverty), were taken into consideration?

Efficiency, Effectiveness, and Coverage

Objective: Understanding cost calculations per student and the criteria taken into consideration when choosing a school to join the Inclusive Education Program

- Do you know the cost per student with disability in the inclusive education programme?

If yes,

  - How does it compare to students with disabilities in other programs?

  - How does the cost compare to other students with no disability in the same school?

- What does your cost evaluation take into account?

  - Operational overhead

  - Severity of disability or impartment

  - Logistical organization

  - Materials and resources needed

  - Rehab sessions

  - Cost of infrastructural changes made to school campus and classes

- How do you calculate the cost of each of the mentioned categories?

  - What other factors do you take into account when evaluating the cost per student?

- In your opinion, what defines ' vulnerable populations'? (probe for: refugee status, economic background, nationality…etc)

- What are the criteria that factor into the schools chosen to join the Inclusive Education Programme?

  - Percentage of vulnerable population

  - Location

  - Age of building/s

  - Number of students

  - Number of students with disability at school/ in area.

  - The presence/ or lack of a Makani center nearby.

- Currently, which camps do you have the Inclusive Education Programme in?

  - Why did you choose this camp in particular? (Probe for most vulnerable, reach, population size… etc)

- Is there anything else you would like to add?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### GIZ and FCDO Guide

Hello Mr/ Ms. [name]. I’m here today to discuss with you the UNICEF Inclusive Education Program.

There are no right or wrong answers, I’m seeking your opinion. Everything said in this discussion is confidential and will only be used for research purposes. Neither your identity nor your affiliation will be revealed. We will not disclose any statement attributable to your name. This session will be recorded, however, only members of the research teams have access to the recording. They will also be the only ones to view the full written transcripts.

Do you agree with these rules?

By agreeing to this statement and continuing this interview you are giving our team consent to utilize the information you provide us within the completion of the UNICEF Inclusive Education Programme Evaluation.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- What is your position at the GIZ/ FCDO?

- What does your job entail?

- How long have you worked here?

Context Background Awareness

Objective: Understanding perceptions on education in Jordan in general and particularly for children with disabilities.

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

- If not, what needs to happen for the educational system to accommodate children with disabilities?

- What would you say are the biggest challenges in the education of children with disabilities in Jordan? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

An Assessment of the Inclusive Education Program

Objective: Understanding the audience and their responsibilities.

- What role do you play, if any, in the inclusive education programme?

- In what capacity does GIZ /FCDO contribute to the inclusive

- How do you perceive the success of the inclusive education programme?

- What are the strengths and weaknesses of the programme?

- What was the conceptional/policy foundational basis for the programme?

- To what extent is UNICEF's support between 2014-2019 reflected in the National Inclusive Education Strategy?

- Would you say that the existing inclusive education programme is gender-balanced in its hiring practices? How so?

  - Are girls and boys treated equally by the adults in the programme?

- Does the inclusive education programme include specific measures to tackle inequality? please explain.

- Is the inclusive education programme conceptually based on human-rights? please explain.

- What are the 'areas of opportunity' to enhance the programme in your opinion?

Transition and Sustainability

Objective: Understanding what MoE representatives think the transition of the inclusive education program will look like and whether he/she thinks the programme is sustainable and expandable.

- To what extent do you think the MoE has the sufficient capacity to take on tasks and lead the whole programme without UNICEF support?

(probe for: human resource, financial, technical capacities...etc)

- Do you think the transition to the MoE will be smooth? What makes you say that?

- What elements/ factors would make the inclusive education programme a sustainable system? why?

- Is the programme's handover plan sufficient toward the sustainability envisioned in the national strategy?

- Do you think it can be replicated and expanded all over Jordan? How?

- What are the bottlenecks that could hinder this achievement?

- What are the elements to take into consideration while expanding?

- what needs to be put in place to ensure a smooth transition of the programme from UNICEF/Mercy Corps to the MoE?

- To what extent is Mercy Corps's advocacy work on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is Mercy Corps's technical assistance on inclusive education and/or children with disabilities evident within the:

  - programme?

  - Ministry of Education policy development?

- To what extent is Mercy Corps's generation and use of data on inclusive education and/or children with disabilities evident within the?

  - programme?

  - Ministry of Education policy development?

- When choosing a location for a school to participate in the programme, was an effort made to ensure characteristics associated with vulnerability (e.g. poverty), were taken into consideration?

Efficiency, Effectiveness, and Coverage

Objective: Understanding cost calculations per student and the criteria taken into consideration when choosing a school to join the Inclusive Education Program

- Do you know the cost per student with disability in the inclusive education programme?

If yes,

  - How does it compare to students with disabilities in other programs?

  - How does the cost compare to other students with no disability in the same school?

- What does your cost evaluation take into account?

  - Operational overhead

  - Severity of disability or impartment

  - Logistical organization

  - Materials and resources needed

  - Rehab sessions

  - Cost of infrastructural changes made to school campus and classes

- How do you calculate the cost of each of the mentioned categories?

  - What other factors do you take into account when evaluating the cost per student?

- In your opinion, what defines ' vulnerable populations'? (probe for: refugee status, economic background, nationality…etc)

- Is there anything else you would like to add?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### Principals Guide

Hello Mr/ Ms. [name]. I’m here today to discuss with you the UNICEF Inclusive Education Program.

There are no right or wrong answers, I’m seeking your opinion. Everything said in this discussion is confidential and will only be used for research purposes. Neither your identity nor your affiliation will be revealed. We will not disclose any statement attributable to your name. This session will be recorded, however, only members of the research teams have access to the recording. They will also be the only ones to view the full written transcripts.

Do you agree of these rules?

By agreeing to this statement and continuing this interview you are giving our team consent to utilize the information you provide us with in the completion of the UNICEF Inclusive Education Programme Evaluation.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- Which school are you a principal for (Probe for area)

- How many years have you been here principal?

Primary Questions:

- Do you have students with disabilities/ impairments at your school? If yes, which?

(Probe for: visual impairment, hearing and speech impairment, physical disability, intellectual disability, mental illness, autism spectrum disorder…etc)

- Is teaching CWD very different than teaching children with no disabilities? How so?

- Do the interventions differ between the different age groups? if yes, how?  (6-9) (10-14) (15-18)?

  - are they adapted to the different age groups? If so, how?

- Do the teachers receive any support or assistance in teaching children with disabilities?  If yes, who provides this support?

- What kind of supervision, if any, do the teachers receive while educating children with disabilities?

Accessibility to Education for CWD

Objective: To understand if the child has access to educational services and what materials and resources necessary for his/her education.

- What would you say are the biggest challenges in the education of children with disabilities? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments' needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

- Is the education system in Jordan suitable for children with disabilities? If yes, how?

If no, what needs to happen for the educational system to accommodate children with disabilities?

- Has there been any effort by the school to accommodate students with disabilities in the past? If yes, how?

(probe for: the addition of ramps, handicap parking, wider doors, even leveled flooring, accessible toilets, Braille signs, sign language translators…etc.)

- How long ago did the school make these infrastructural improvements?

- As far as you know, why did they make these improvements?

- Which entity, if any, funded these improvements?

(Probe for each improvement mentioned)

- Does the school provide any materials or resources to enable teachers in teaching students with disabilities?

- If yes:

- What kind of materials/ resources?

- Are they sufficient?

- What else is missing?

- Do you know what assistive technology devices for children with disabilities are?

Note to Moderator, Read this:

An assistive tech device is "any device, piece of equipment, or product system that is used to increase, maintain, or improve functional capabilities of a child with a disability."

If yes:

- Do you have any?

- Have you or the teachers received any training on using such devices? If yes, which?

- To what extent do they help?

- To what extent are the interventions (resources and assistive technologies made available and training provided) in line with the targeted disabilities?

- What else did the school do to facilitate the education of students with disabilities?

Teacher Training & Orientation

- Have school-wide trainings been delivered to the teachers?

- What are the main criteria used for eligibility for the teacher training program on children with disabilities?

- Was the training/s sufficient?

- To what extent is the teacher training model effective and sufficient in enabling teachers to support the retention and learning of children with disabilities?

- Do you think the training you received has impacted your skills and capacity in including and retaining children with disabilities?

- How many teachers have received training to teach children with disabilities?

If yes:

  - What are the main components of the training model?

  - How has the teacher training model changed between 2014 and 2019?

- Have the teachers received any post training support/mentoring? if yes, by whom?

- Were there policies at school that supported Inclusive Education before this program came along?

- Have the school students been oriented on the inclusion program?

- Has the wider school community (including parents) been oriented on inclusion?

The Inclusive Education Program

Objective: Understanding Principals’ awareness and perceptions towards the Inclusive Education Program

- When did the school join this program? (Probe for month and year)

- How long did it last? Is it still on-going?

(Probe if the school continues to operate the program or if the teacher perceives it to be over)

- What kind of interventions were implemented?

(Probe for tangible and intangible interventions)

- What do you think of the 'inclusive education' concept for all students, including children with disabilities?

- What are its strengths?

- What are areas of future opportunity and growth?

- Is it a realistic concept? Why?

(Probe for: predicted probability of success, acceptability of system etc.)

- Is it a necessary step to take in public schools? Why?

- Should 'inclusive education' be a mandate by law for schools?

If no, why not?

- if yes, should this be applied for public schools or private? why?

- In your opinion, does the inclusive education program meet the needs of children with disabilities in terms of enabling them to fully engage in the learning process (as with children without disability)?

If no, why?

If yes, how so?

- Do children with disabilities have access to fully developed, individualized, and up-to-date Individual Education Program (IEP)? if yes, how many children?

- How many of them progress successfully in the programme, as reported in their IEP?

- On average, how much time does a child with an IEP spend in a resource room, per day?

- Are children with disabilities more or less likely to participate in school learning activities than their peers without disabilities?

- In your opinion, to what extent are the teachers’ practices in the classroom aligned with the training they received?

- Do you receive any support to enable you in implementing practices on inclusion?

- Are the resource rooms used effectively and efficiently in alignment with the delivered training?

- Is the school doing anything to sustain these services? if yes what?

Synergy to Ministry of Education

- To what extent does the inclusive education programme reflect the gender, equity, and human rights-based approach?

- Does the programme include specific measures to tackle inequality?

- Is the programme conceptually based on human-rights?

- Do you think the programme documents and language reflect a human-rights and child-centred approach?

- In your opinion, to what extent is the Inclusive Education Program effective in delivering results for children with disabilities?

- To what extent is the Inclusive Education Program, and its interventions in the schools, responsive to the needs of the enrolled students with disabilities?

- To what extent were the objectives of the programme achieved effectively in terms of:

- Support of enrolment and retention of children in schools?

  - Do you think you have the capacity to impact enrolment and retention of children with disabilities? if yes, to what extent?

- Support children's learning and participation/ engagement in courses

- Change in attitudes of children, caregivers, and practices in schools.

- How many children were enrolled and retained in 2014?

Similarly, how many children were enrolled and retained in 2019?

- Are there any obstacles that hinder the achievement of the intended objective/s of the inclusive education programme? if yes, what?

- Do you know if or when in the future this program will be handed over to the Ministry of Education (MoE)?

if that has already happened:

- how was the handover?

- Did you face any issues since? if so, what are they?

- Do you have any concerns about this program being supervised by the MoE?

Rehab Sessions & Assistive Devices:

Objective: Evaluating the extent of knowledge teachers have on rehabilitation sessions and assistive devices.

- Does the school offer any rehabilitation sessions to children with disabilities?

If yes, where do they give these sessions? (Probe for: on-location vs off-site, dedicated room, assistive devices…etc)

- Do the teachers use any assistive devices inside the classrooms? If yes, what are they? (Probe for for model IE schools, i.e hearing loop, sensory room...etc)

- Do you have a referral system at school for children with disabilities?

If no, why?

If yes:

- What kind of referral system do you currently have at school?

- Has the referral system suffered any changes between 2014 and 2019?

if yes, please describe and explain what the differences are and why they were implemented

Raising Awareness towards Children With Disabilities

Objective: Understanding what effort (if any) has been put in shifting perceptions of students, and their parents, towards children with disabilities and the importance of an inclusive education system.

- Has there been an effort by the school to raise awareness towards disabilities and the importance of inclusive education?

If no:

- Do you wish they did? Why?

- Is it necessary they do? Why?

If yes:

- Was this effort funded by UNICEF?

- What did their awareness-raising campaign/ sessions look like?

(Probe for: lectures, meetings, brochures/ info sheets…etc)

- How many lectures/ meetings/ activities did they have on this topic?

- Do you feel like they were successful at raising awareness towards children with disabilities? Why?

- Were the efforts aimed at students or parents of students or both?

If both, how did the campaign efforts vary?

- If the program management has been handed over to the Ministry of Education:

- When did that happen?

- How did the process look like?

- Was the transition smooth?

- Has the program been affected since then? if yes, how so?

- Have your perceptions of the education of children with disabilities changed since 2014?

Secondary Questions:

Introduction

Objective: Understanding the responsibilities of principals, their qualifications, and their perceptions on teaching children with disabilities.

- What are the issues in the educational system in Jordan today?

Have you been able to overcome these difficulties?

If no, why not?

If yes, how?

- Do you have teachers in your school who are trained to teach children with disabilities?

If no, why not? (Probe for: lacking funding, lacking training courses, no need, lacking accessibility at the school, perceptions held towards children with disabilities…etc)

- Is there anything else you would like to add to this discussion?

We’ve now concluded our discussion for today. Thank you for coming to speak to us today. We appreciate your time.

## Proposed Focus Group Discussion Guides

### Parents & Caregivers

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for research purposes. Neither the identity nor the affiliation of the speaker(s), nor that of any other participant, may be revealed. We will not disclose any statement attributable to your name. The session will be recorded. However, only members of the research teams have access to the recordings. They will also be the only ones to view the full written transcripts. Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- Are you a parent or a caregiver?

- How old is the child you look after?

- What grade is your child in?

- Does the child have any disabilities? If yes, what kind?

(Probe for: visual impairment, hearing and speech impairment, physical disability, intellectual disability, mental illness, autism spectrum disorder…etc)

- How many years have you been the primary caretaker?

- Do you care for any other children?

If yes who?

- Do they have disabilities as well?

- Tell me about your normal day, what does it look like?

Introduction

Objective: Understanding the audience, their responsibilities, and their qualifications (for caregivers) to work with children with disabilities.

- When did you enroll the child?

(probe for before 2014 or after)

- Do you face any difficulties caring for the child/children with disabilities?

If yes, what  are these difficulties?

Have you overcome these difficulties? if yes, how?

- Do you help your child study?

If no, why not? (Probe for: lacking the skillset/ know-how to teach with children with disabilities, lacking accessibility to resources and materials, lacking the time…etc)

If yes, in what capacity do you help him/her study?

- Is raising a children with disabilities different than a child without disabilities?

If no, why not?

If yes, how is it different?

- What are the different modes of communication that you use with the various disabilities?

(probe for: the use of braille, sign language, props, visual and auditory stimulus… etc.)

Accessibility to Education

Objective: To understand if the child has access to educational services and what materials and resources necessary for his/her education.

- What would you say are the biggest challenges in the education of children with disabilities? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What is required to overcome these hurdles?

- Does the educational system in Jordan include/meet the needs of children with disabilities?

If yes, how?

If not, what needs to happen for the educational system to accommodate children with disabilities?

- What factors did you take into consideration when choosing the school?

(Probe for accessibility; ramps, handicap parking spaces, wide halls, accessible toilets, braille signs and materials, Braille signs, sign language translators…… etc.)

- Has there been any effort by the school to accommodate students with disabilities?

- Does your child have access to shadow teachers and/or one-on-one attention?

- In your opinion, are the teachers teaching your child equipped to do so? What made you say that?

- What else did the school do to facilitate the education of students with disabilities?

If yes, how?

(probe for: the addition of ramps, handicap parking, wider doors, even levelled flooring, handicap toilets… etc.)

- How long ago did the school make these infrastructural improvements?

  - As far as you know, why did they make these improvements?

  - Which entity, if any, funded these improvements?

(Probe for each improvement mentioned)

Awareness and Perceptions of the Inclusive Education Program

Objective: Understanding what systems and protocols, if any, do the schools have for children with disabilities.

- Do you know what the ‘inclusive education’ program is? If yes

- What do you know about it?

- What are its strengths and weaknesses?

- Is it a realistic concept? Why?

(Probe for: predicted probability of success, acceptability of system…etc.)

- Is it a necessary step to take in public schools? Why?

- Should ‘inclusive education’ be a mandate by law for schools?

If no, why not?

if yes, should this be applied for public schools or private? why

- When did your child’s school join the inclusive Education Program?

- How long has your child been enrolled in the Inclusive education program?

- How was your child’s experience being in this program?

- How did you initially hear about the program?

- Did the child benefit from the program? If yes, how so?

- If you had recommendations to the program, what would it be?

- Have you been oriented on inclusion? if yes:

  - What, if any, did you learn from these sessions/ activities?

  - Have they impacted you? if yes, how?

  - Did they change your perceptions towards CWD?

Individualized Education Program (IEP)

Objective: Understanding what systems and protocols, if any, do the schools have for children with disabilities.

- Do you know what an Individualized Education Program is?

if yes, please explain

- Does the child you care for have access to a fully developed, individualized, and up-to-date Individual Education Programs? if no, why?

- Do you know how much time a child with an IEP spends in a resource room, per day?

- Does the child participate in school learning activities like his/ her peers (without disabilities)?

- Do you attend any meetings on IEP? What do you discuss in such sessions?

Materials, Resources, & Assistive Devices:

Objective: Evaluating the extent of knowledge parents and caregivers have on resources and assistive devices used by teachers to aid their children in learning.

- Has the school provided any materials or resources to enable your child’s teacher in communicating with him/her?

If no:

- What materials/ resources do you wish the teachers had access to?

- Does not having these materials/ resources hinder your child from learning?

If yes:

- What materials/ resources did the school provide?

- Are they sufficient for the teacher to do his/her job properly?

- What else is missing?

- Are the resource rooms used effectively and efficiently in alignment with the delivered training?

  - have you seen them?

- Do you know what assistive devices for children with disabilities are?

If yes:

- To what extent do they help?

- Do you know if the school provides these devices to the child in class?

Note to Moderator: An assistive tech device is "any device, piece of equipment, or product system that is used to increase, maintain, or improve functional capabilities of a child with a disability."

- To what extent are the resources and assistive technologies made available to your child/ the child you care for in line with his/her disability?

- As far as you know, is the inclusive education program responsive to the needs of your child/ the child you care for? If yes, how so?

Rehab Sessions & Referral Systems

Objective: Evaluating the awareness of parents and caregivers on the rehab sessions and the referral system at school.

- As far as you know, does the school offer any rehab sessions to children with disabilities?

If yes:

- Where do they give these sessions? (Probe for: on-location vs. off-site, dedicated room, assistive devices…etc)

- Do you know who funds this rehab program? (Probe for UNICEF)

- How much do these sessions cost you?

- How many sessions does your child attend a month?

- Do you accompany your child to these rehabilitation sessions?

- Does the school have a referral system for children with disabilities?

- Have you been oriented on the existing referral mechanisms?

- What are the existing referral mechanisms for referring children with disabilities to school that you know of?

- Is the existing system effective in identifying and ensuring access to children with disabilities already in school?

- Has the referral system suffered changes between 2014 and 2019? Please describe and explain what the differences are and why they were implemented.

- Are you involved in identifying and/or referring children to the UNICEF inclusive education programme?

- Has your child complained due to lack of:

- Unavailability of resources?

- Biased treatment

- Lack of assistance

- Accessibility issues

Raising Awareness towards Children with Disabilities

Objective: Understanding what effort (if any) has been put in shifting perceptions of students, and their parents, towards children with disabilities and the importance of an inclusive education system.

- Has there been any effort by the school to raise awareness towards disabilities and the importance of inclusive education?

If no:

- Do you wish they did? Why?

- Is it necessary they do? Why?

If yes:

- What did their awareness-raising campaign look like?

(Probe for: lectures, meetings, brochures/ info sheets…etc)

- How many lectures/ meetings did they have on this topic?

- What was the content of this campaign?

- Do you feel like they were successful at raising awareness towards children with disabilities? Why?

- Were their efforts aimed at other students or parents and caregivers such as yourselves?

- To what extent has your opinion about children with disabilities changed since 2014?

- Is there anything else you would like to add to this discussion?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### Teachers and Supervisors

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for research purposes. Neither the identity nor the affiliation of the speaker(s), nor that of any other participant, may be revealed. We will not disclose any statement attributable to your name. The session will be recorded. However, only members of the research teams have access to the recordings. They will also be the only ones to view the full written transcripts. Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- Are you a teacher or supervisor?

- Are you a classroom teacher, shadow teacher, special ed teacher, or other?

- How many years have you been teaching?

- What subjects do you teach?

- Which grades do you teach?

- Do you enjoy teaching? Why?

Introduction

Objective: Understanding the audience, their responsibilities, and their qualifications to work with children with disabilities.

- What are the issues you face in teaching today?

Have you been able to overcome these difficulties?

If no, why not?

If yes, how?

- Are you trained to engage children with disabilities in the classroom?

If no, why not? (Probe for: lacking the skillset/ training to deal with children with disabilities, accessibility at the school, perceptions held towards children with disabilities…etc)

if yes, are you trained to do so individually or within a group in the classroom?

- Are you trained to teach students with disabilities in the resource room?

- Which disabilities/ impairments do you work with now or have worked with in the past?

(Probe for: visual impairment, hearing and speech impairment, physical disability, intellectual disability, mental illness, autism spectrum disorder…etc)

- Do the interventions differ between the different age groups? if yes, how?  (6-9) (10-14) (15-18)?

  - are they adapted to the different age groups? If so, how?

- Do you receive any support or assistance while teaching children with disabilities?

If yes, who provides this support?

What kind of supervision, if any, do you receive to aid you in the education of children with disabilities?

Accessibility to Education

Objective: To understand if the child has access to educational services and what materials and resources necessary for his/her education.

- In What would you say are the biggest challenges in the education of children with disabilities? Why?

(probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments' needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take to overcome these hurdles?

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

If no, what needs to happen for the educational system to accommodate children with disabilities?

- Has there been any effort by the school to accommodate students with disabilities? If yes, how?

(probe for: the addition of ramps, handicap parking, wider doors, even leveled flooring, accessible toilets, Braille signs, sign language translators…etc.)

- How long ago did the school make these infrastructural improvements?

- As far as you know, why did they make these improvements?

- Which entity, if any, funded these improvements?

(Probe for each improvement mentioned)

- Has the school provided any materials or resources to enable you in teaching students with disabilities?

If no:

- What materials/ resources do you need?

- Does not having these materials/ resources hinder you from doing your job properly? How?

- If yes:

- What materials/ resources did the school provide?

- Are they sufficient for you to do your job properly?

- What else are you missing?

- Do you know what assistive technology devices for children with disabilities are?

If yes:

- Have you used any?

- Have you received any training on using such devices? If yes, which?

- To what extent do they help?

- How many children with disabilities with an identified need for assistive technology (as per IEP) have access and use the Assistive product or technology?

Note to Moderator: An assistive tech device is "any device, piece of equipment, or product system that is used to increase, maintain, or improve functional capabilities of a child with a disability."

- To what extent are the interventions (resources and assistive technologies made available and training provided) in line with the targeted disabilities?

- What else did the school do to facilitate the education of students with disabilities?

- How do you see your role in integrating CWDs in schools and sustaining these services?

Teacher Training & Orientation

- Have school-wide trainings been delivered to the teachers?

- What are the main criteria used for eligibility for the teacher training program on children with disabilities?

- Are teachers required to have a teaching degree or have extensive experience working with children?

- Was the training/s sufficient?

- Have you received any training to teach children with disabilities?

  - What are the main components of the training model?

  - How has the teacher training model changed between 2014 and 2019?

- Were there policies at school that supported Inclusive Education before this program came along?

- To what extent is the teacher training model effective and sufficient in enabling teachers to support the retention and learning of children with disabilities?

- Do you think the training you received has impacted your skills and capacity in including and retaining children with disabilities?

- Have the school students been oriented on the inclusion program?

- Has the wider school community (including parents) been oriented on inclusion?

- Have you been able to pass the knowledge to your colleagues in the same school?

Awareness and Perceptions of the Inclusive Education Program

Objective: awareness of and perceptions held towards Inclusive Education Program

- When did the school join this program? (Probe for month and year)

  - How long did it last? Is it still on-going?

(Probe if the school continues to operate the program or if the teacher perceives it to be over)

- What kind of interventions were implemented?

(Probe for tangible and intangible interventions)

- What do you think of the 'inclusive education' concept for all students, including children with disabilities?

- Is it a realistic concept? Why?

(Probe for: predicted probability of success, acceptability of system etc.)

- Is it a necessary step to take in public schools? Why?

- Should 'inclusive education' be a mandate by law for schools?

If no, why not?

if yes, should this be applied for public schools or private? why?

- What are the strengths and weaknesses of the inclusive education programme in your opinion?

- In your opinion, does the inclusive education program meet the needs of children with disabilities in terms of enabling them to fully engage in the learning process (as with children without disability)?

If no, why?

If yes, how so?

- Do children with disabilities have access to fully developed, individualized, and up-to-date Individual Education Program (IEP)? if yes, how many children?

- How many of them progress successfully in the programme, as reported in their IEP?

- On average, how much time does a child with an IEP spend in a resource room, per day?

- Are children with disabilities more or less likely to participate in school learning activities than their peers without disabilities?

- In your opinion, to what extent are your practices in the classroom aligned with the training you received?

- Do you receive any support to enable you in implementing practices on inclusion?

- Are the resource rooms used effectively and efficiently in alignment with the delivered training?

Synergy to Ministry of Education

- In your opinion, to what extent is the Inclusive Education Program effective in delivering results for children with disabilities?

- To what extent is the Inclusive Education Program, and its interventions in the schools, responsive to the needs of the enrolled students with disabilities?

- To what extent were the objectives of the programme achieved effectively in terms of:

- Support of enrolment and retention of children in schools?

- Do you think you have the capacity to impact enrolment and retention of children with disabilities? if yes, to what extent?

- Support children's learning and participation/ engagement in courses

- Change in attitudes of children, caregivers, and practices in schools.

- Are there any obstacles that hinder the achievement of the intended objective/s of the inclusive education programme? if yes, what?

- Do you know if or when in the future this program will be handed over to the Ministry of Education (MoE)?

if that has already happened:

- How was the handover?

- Did you face any issues since? if so, what are they?

- Do you have any concerns about this program being supervised by the MoE?

Rehab Sessions & Assistive Devices:

Objective: Evaluating the extent of knowledge teachers have on rehab sessions and assistive devices.

- As far as you know, does the school offer any rehab sessions to children with disabilities?

If yes:

Where do they give these sessions? (Probe for: on-location vs off-site, dedicated room, assistive devices…etc)

- Do you have a referral system at school for children with disabilities?

If no, why?

If yes:

- What kind of referral system do you currently have at school?

- When was it established?

- Is the referral system effective in identifying and ensuring access to children with disabilities already in school?

- Why are these children referred?

- Where are the children referred to?

- Has the referral system suffered any changes between 2014 and 2019?

if yes, please describe and explain what the differences are and why they were implemented

Raising Awareness towards Children With Disabilities

Objective: Understanding what effort (if any) has been put in shifting perceptions of students, and their parents, towards children with disabilities and the importance of an inclusive education system.

- Has there been an effort by the school to raise awareness towards disabilities and the importance of inclusive education?

If no:

- Do you wish they did? Why?

- Is it necessary they do? Why?

If yes:

- Was this effort funded by UNICEF?

- What did their awareness-raising campaign look like?

(Probe for: lectures, meetings, brochures/ info sheets…etc)

- How many lectures/ meetings/activities did they have on this topic?

- Do you feel like they were successful at raising awareness towards children with disabilities? Why?

- Were the efforts aimed at students or parents of students or both?

If both, how did the campaign efforts vary?

Did you have a role in these lectures/meetings/activities?

- If the program management was handed over to the Ministry of Education?

if yes:

- When did that happen?

- How did the process look like?

- Was the transition smooth?

- Has the program been affected since then? if yes, how so?

- Have your perceptions of children with disabilities changed since 2014?

- Is there anything else you would like to add to this discussion?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### In School Children with Disabilities: Aged between (6-9)

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for this assessment. Your name will not be associated with the study, nor revealed. The session will be recorded. However, only members of the research teams have access to this research effort.

Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now

Warm-up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

  - How old are you?

  - What grade are you in?

  - Do you like school? Why?

  - What do you want to be when you grow up? (Probe for career path...etc)

Introduction

Objective: Understanding the students, their needs and wants with a focus on their education journey.

  - What kind of disability do you have?

(Probe for: visual impairment, speech and hearing impairment, mental disabilities, physical disabilities… etc).

  - Does it affect your studying? How?

  - Do you face any difficulties  learning?

  - What would you say are the problems in learning for children like you?

  - Which classes are your favorite? Why?

  - Which are your least favorite? Why?

  - Were you able to make friends at school?

If not, why do you think that is?

if yes:

- How do you feel they perceive your disability?

- Do any of them have disabilities as well?

  - Do you think your school does a good job of dealing with you and people with disabilities?

If no, why not? (Probe for accessibility, inexperience, lacking appropriate resources and materials… etc.)

If yes, why do you think this?

  - Do you like your teachers?

  - Do you think your teachers do a good job of teaching you and people with disabilities?

If no, why not? (Probe for lacking training, inexperience, lacking appropriate resources and materials… etc.)

If yes, why do you think this?

  - How do teachers in class deal with you?

- Do they treat you like they do any other student?

if yes, how do they treat you the same?

if no, how is the treatment different?

- Do they give you any special care/ attention?

- Do they provide you with assistance? if yes, what kind?

Awareness towards Inclusive Education Program

Objective: Assessing the students’ knowledge of the Inclusive Education Program and understanding their perceptions of it.

  - Do you know what the inclusive education program is?

If yes….it?

  - What do you think are the good things about it? Bad things?

  - Have you participated in any of the sensitization events?

  - Do these sessions help your parents better support you at home?

Physical Accessibility

Objective: Understand what improvements, if any, did the school make to the school building/s and campus to make it more accessible to students with disabilities.

  - Can you enter the building easily?

  - Can you move around the school easily? why?

(Probe for: ramp, wheelchair accessibility, accessible toilets, handicap parking, wide doorways and halls, Braille signs, sign language translators…etc.)

  - Has the school always been the case?

or was the school not accessible at some point? Please explain.

  - What other features do you wish your school had?

  - Let’s use our imagination for a bit…

  - What if you each had a magic wand, and you were to use this wand to make your school   the best version it can be. Can you all see it in your mind? Please describe it.

- What does it look like?

- What does your class look like?

- What do your desks in class look like?

- What do the facilities look like?

- How do the teachers deal with you?

- How do the other students treat you?

- Where is it located?

  - How different would your educational experience be if you had these features?

(Probe for: emotional and functional benefits …etc.)

Assistive Devices & Rehab Sessions

Objective:

  - Understanding what materials and resources schools’ invested in, if any, to help students with disabilities while highlighting further needs.

  - Evaluating schools’ rehab programs, if they exist, and understanding how they can be improved.

  - Do you have a resource/ special room at your school?

If yes?

  - What things (resources and materials) do you need to learn?

- Are they beneficial?

- Do they help you in understanding or studying?

- Do your peers in class need these items too or is it just you?

  - What things do you wish your school had to help you learn?

(Probe for: audio recorders, timers, reading guides, writing supports, calculators, organizers…etc.)

  - Does the school have any assistive items (devices) that help you in learning?

(Probe for: electronic worksheets, phonetic spelling software, talking calculators, variable, speed recorders…etc.)

  - Do you get special help or assistance from your teachers? If yes, do you benefit from this one-on-one attention? Why?

Rehab Sessions

  - Do you have any special sessions with other teachers or therapists that your other friends don't have?

If yes:

- Can you tell me what you do there?

- Why do you need these sessions?

- How often did you receive them? (weekly, monthly…etc)

- Do you like these sessions? Why?

  - Do you feel like your teachers know how to teach you like other students? Why?

- What makes him/her a ‘good teacher’?

- If he/she is not a good teacher, why is that?

Raising Awareness towards CWD

Objective: Understanding what effort, if any, has been put in shifting perceptions of students, and their parents, towards CWD and the importance of an inclusive education system.

  - Do you like going to school with other children without disabilities?

- If no, why? (Probe for: feeling different, being bullied, lacking accessibility…etc)

- If yes, why? (Probe: independence, mingling with other children, friends, school is fun…etc)

  - Do you wish you went to a school for children with disabilities only? Why?

We have now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### In School Children with Disabilities: Aged between (10-14) & (15-18)

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for this assessment. your name will not be associated with the study, nor revealed. The session will be recorded. However, only members of the research teams have access to this research effort.

Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

  - How old are you?

  - What grade are you in?

  - What school do you attend? (Probe for the location; camp vs host community)

  - Do you like school? Why?

  - Do you know what you want to do in the future? (Probe for university, work, living independently...etc)

Introduction

Objective: Understanding the students, their needs and wants with a focus on their education journey.

  - Do you have a disability?Does it affect your studying? How?

  - Do you face any difficulties learning?

If no, why?

If yes, how?

  - Did you overcome these challenges? if yes, how?

  - Which classes are your favourite? Why?

  - Which are difficult for you? Why?

  - Were you able to make friends at school?

If not, why do you think that is?

if yes:

- How do you feel they perceive your disability?

- Do any of them have disabilities as well?

- Do you think your school does a good job in dealing with you and people with you and people with your type of disability?

If no, why not? (Probe for accessibility, inexperience, lacking appropriate resources and materials… etc.)

If yes, why do you think this?

- Do you feel like your teachers are capable of teaching you/ people with your type of disability?

- Do you have Shadow teachers? If yes, to what extend do you benefit from the support provided by the Shadow teachers?

- To what extent does the one-on-one support provided in the Resource Room contribute to your progress in the inclusive education programme?

Accessibility to Education

Objective: Understanding what the educational experience looks like from the eyes of children with disabilities including difficulties and obstacles faced by this segment.

- What would you say are the biggest challenges in the education of children with disabilities in Jordan? Why?

(Probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take for public schools to overcome these obstacles?

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

If no, what needs to happen for the educational system to accommodate children with disabilities?

- Is the school building/ campus accessible to you? Please explain.

(Probe for: ramp, wheelchair accessibility, accessible toilets, handicap parking, wide doorways and halls, Braille signs, sign language translators…etc.)

- Has the school always been accessible to you? Please explain.

- What other infrastructural features do you wish your school had?

- How different would your educational experience be if you had these features?

(Probe for: emotional and functional benefits …etc.)

Rehab sessions & Assistive Devices

Objective:

- Understanding what materials and resources schools’ invested in, if any, to help students with disabilities while highlighting further needs.

- Evaluating schools’ rehab programs, if they exist, and understanding how they can be improved.

- What type of resources and materials do you need to learn?

- Does the school possess the resources and materials to cater to your needs and the needs of other students with disability?

- What resources and materials do you wish your school-owned to help you learn?

(Probe for: audio recorders, timers, reading guides, writing supports, calculators, organizers…etc.)

- Does the school possess any assistive devices that help you in learning?

(Probe for: electronic worksheets, phonetic spelling software, talking calculators, variable, speed recorders…etc.)

- How else can your learning experience be optimized?

- Have you attended any rehab sessions at school?

If no, do you wish your school offered rehab sessions and physiotherapy?

If yes:

- Why was it recommended you receive rehab sessions?

- Who decided you should receive rehab sessions? (Probe for: teachers, principals, specialized doctor, school doctor, parents… etc.)

- What kind of rehab sessions did you receive? (Probe for: speech therapy, physical therapy, occupational therapy, help with difficulties in learning any subject.… etc.)

- Did they cost you/ your family anything? If yes, how much?

- Where did you receive these sessions? (Probe for on-location, off-campus, at a public/ private clinic… etc)

- How often did you receive them? (weekly, monthly…etc)

- How long were the sessions?

- As far as you know, are your teachers certified to work with children with disabilities? If no, why do you think they are not certified?

If yes:

What kind of certification do they have?

- Which disabilities are they trained to engage with? (Probe for: visual impairment, hearing and speech impairment, physical disability, intellectual disability, mental illness, autism spectrum disorder…etc)

- Is there a referral system at school for students with disabilities?

If yes:

- Why are students referred?

- Where are the students referred to?

Awareness towards the Donor & the ‘Inclusive Education Programme’

- Do you know what an Individualized Education Program is?

If no: skip to next question

If yes:

- What do you think of the IEP? (Probe for strengths and weaknesses)

- As far as you know, does the school have any written system/ protocols on special education?

- When the school joined the ‘Inclusive Education Program? (Probe for month and year)

- How long did it last? Is it still on-going?

(Probe if the school continues to operate the program or if the teacher perceives it to be over)

- What kind of interventions were implemented?

(Probe for tangible and intangible interventions)

- Has the programme been affected by the Covid-19 pandemic? if yes, how so?

(Probe for delays, changes to the plan...etc)

- Do you have access to a fully developed and up-to-date “Individual Education Program (IEP)? If yes, what does that look like?

- On average, how much time do you spend on IEP and/or in the resource room, per day?

- In case you needed support in class, who do you reach out to? (Probe for classroom teacher, assistive teacher, others…etc.)

- In your opinion, does the inclusive education program meet  the needs of children with disabilities in terms of enabling them to fully engage in the learning process (as with children without disability)?

- If no, why?

- If yes, how so?

Raising Awareness towards Children with Disabilities

Objective: Understanding what effort, if any, has been put in shifting perceptions of students, and their parents, towards children with disabilities and the importance of an inclusive education system.

- What do you think of the ‘inclusive education’ concept for all students including children with disabilities?

Is it a realistic concept? Why?

(Probe for: predicted probability of success, acceptability of system…etc.)

- Is it a necessary step to take in public schools? Why?

- Has there been any effort by the school to raise awareness towards disabilities and the importance of inclusive education?

If no:

- Do you wish they did? Why?

- Is it necessary they do? Why?

If yes:

- What did their awareness-raising campaign look like?

(Probe for: lectures, meetings, brochures/ info sheets…etc)

- How many lectures/ meetings did they have on this topic?

- What was the content of this campaign?

- Do you feel like they were successful at raising awareness towards children with disabilities? Why?

- Were their efforts aimed at students in the school or parents of students?

- If both, how did the campaign efforts vary?

- Are you aware of any projects/ programmes by either UNICEF or Mercy Corps on inclusive education and enhancing public schools to make them friendly to children with disabilities?

If yes, what do you know about it?

- Is there anything else you would like to add to this discussion?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### In School Children without Disabilities: Aged between (6-9)

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for this assessment. your name will not be associated with the study, nor revealed. The session will be recorded. However, only members of the research teams have access to this research effort.

Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now.

Warm-up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

  - How old are you?

  - What grade are you in?

  - Do you like school? Why?

  - What do you want to be when you grow up? (Probe for career path...etc)

Introduction

Objective: Understanding the students, their needs and wants with a focus on their education journey.

- Which classes are your favourite? Why?

- Which are your least favourite? Why?

- Does having a classmate in class with disabilities affect you? how?

(Probe for: distractions, attention of teacher going towards children with disabilities… etc).

- Do you like/ dislike having classmates with disabilities in class with you? why?

- Are you friends with these classmates?

(Probe: do you play with them at school, do you see them outside school...etc.)

- How does having them in class make you feel?

- Do you like your teachers?

- Do any of your classmates require special care/ attention?

If yes, how does that make you feel?

- why do you think the teacher gives him/her special attention?

- does it take too much time from your class time?

- Do you get any special care or attention?

Physical Accessibility:

Objective: Understand what improvements, if any, did the school make to the school building/s and campus to make it more accessible to students with disabilities.

- Did your school make any changes to its building/s?

If yes, what kind of changes?

(Probe for: ramp, wheelchair accessibility, handicap toilets, handicap parking, wide doorways and halls, Braille signs, sign language translators…etc.)

- Do you know why your school made these improvements?

(Probe for the students’ understanding of accessibility for children with disabilities…etc.)

- What kind of improvements do you wish your school would make?

- Let’s use our imagination for a bit…

What if you each had a magic wand, and you were to use this wand to make your school the best version it can be. Can you all see it in your mind? Please describe it.

- What does it look like?

- What does your class look like?

- What do your desks in class look like?

- What do the facilities look like?

- What are the teachers like?

- Where is it located?

- How different is your current experience from the one just described?

- How different would your educational experience be if your school had all these improvements?

(Probe for: emotional and functional benefits …etc.)

Awareness towards inclusive Education Program

Objective: Assessing the students’ knowledge of the Inclusive Education Program and understanding their perceptions of it.

- Do you know what the inclusive education program is? What do you know about it?

If yes….it?

- What do you think are the good things about it? Bad things?

Educational Resources & Materials

Objective:

- Understanding what materials and resources schools’ invested in, if any, to help students with disabilities while highlighting further needs.

- Evaluating schools’ rehab programs, if they exist, and understanding how they can be improved.

- What materials  (or resources) do you need to learn?

- Does the school have these things (resources and materials) now?

- What things do you wish your school had to help you learn?

(Probe for: audio recorders, timers, reading guides, writing supports, calculators, organizers…etc.)

- How do you now feel about children with disabilities? why?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### In School Children without Disabilities: Aged between (10-14) & (15-18)

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for this assessment. your name will not be associated with the study, nor revealed. The session will be recorded. However, only members of the research teams have access to this research effort.

Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now.

Warm-up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

  - How old are you?

  - What grade are you in?

  - Do you like school? Why?

  - Do you know what you want to do in the future? (Probe for university, work, living independently...etc)

Introduction

Objective: Understanding the students, their needs and wants with a focus on their education journey.

- How do you feel about school? Why?

- Do you think education is important? Why?

- What is your opinion of your school?

What do you think of:

  - The schools building/ campus?

  - The facilities? (Probe for: courts, rooms, floors, bathrooms, water fountains…etc)

  - The classes? (Probe for: space size, modernity, desks, boards, ventilation system…etc)

  - The teachers? (Probe for: experience, capability, professionalism…etc)

  - The environment?

- Are there any students with disabilities in your class/school?

(Probe for: visual impairment, speech and hearing impairment, mental disabilities, physical disabilities… etc).

- Does having a classmate in class with disabilities affect you? how?

(Probe for: distractions, attention of teacher going towards children with disabilities… etc).

- Do you like/ dislike having classmates with disabilities in class with you?

Are you friends with these classmates?

(Probe: do you play with them at school, do you see them outside school...etc.)

- How does having them in class make you feel?

- Do teachers in class give students with disabilities any special care/ attention?

If yes, how does that make you feel?

  - Do you get any special care or attention?

- In your opinion, to what extent is your school successful at integrating students with disabilities? What makes you say this?

Physical Accessibility

Objective: Understand what improvements, if any, did the school make to the school building/s and campus to make it more accessible to students with disabilities.

- Did your school make any improvements to its building/s or campus?

If yes:

  - What kind of improvements have they made?

(Probe for: ramp, wheelchair accessibility, handicap toilets, handicap parking, wide doorways and halls, Braille signs, sign language translators…etc.)

  - Do you know why your school made these improvements?

(Probe for the students’ understanding of accessibility for children with disabilities…etc.)

  - What kind of improvements do you wish your school would make?

  - How different is your current experience from the one just described?

  - How different would your educational experience be if your school had all these improvement’s?

(Probe for: emotional and functional benefits …etc.)

If no:

- What kind of improvements do you wish they would make?

- What does the ideal school look like?

(Probe for facilities, classes, sports courts…etc)

Rehab sessions & Assistive Devices

Objective:

- Understanding what materials and resources schools have invested in, if any, to help students in general and students with disabilities in particular while highlighting further needs.

- Evaluating schools’ rehab programs, if they exist, and understanding how they can be improved.

- What type of resources and materials do you need to learn?

- Does the school possess these resources and materials?

- Do you know what resources/ materials students with disabilities need?

- What resources and materials do you wish your school owned to help you learn?

(Probe for: audio recorders, timers, reading guides, writing supports, calculators, organizers…etc.)

- Does the school possess any assistive devices that help you in learning?

(Probe for: electronic worksheets, phonetic spelling software, talking calculators, variable, speed recorders…etc.)

- As far as you know, what assistive devices do students with disabilities need?

- Do you know if your school offers any rehab sessions for students with disabilities?

- As far as you know, are your teachers certified to work with children with disabilities?

- If yes:

- What kind of certification do they have?

- Which disabilities are they trained to work with? (Probe for: visual impairment, hearing and speech impairment, physical disability, intellectual disability, mental illness, autism spectrum disorder…etc)

- Is there a referral system at school for students with disabilities?

If yes:

- Why are students referred?

- Where are the students referred to?

Raising Awareness towards Children with Disabilities

Objective: Understanding what effort, if any, has been put in shifting perceptions of students, and their parents, towards children with disabilities and the importance of an inclusive education system.

- Do you know what the ‘inclusive education’ program is ?

If yes,

- What do you think of the ‘inclusive education’ program  for all students including children with disabilities?

- What are its strengths and weaknesses?

- Is it a realistic concept? Why?

(Probe for: predicted probability of success, acceptability of system…etc.)

- Is it a necessary step to take in public schools? Why?

- Has there been any effort by the school to raise awareness towards disabilities and the importance of inclusive education?

If no:

- Do you wish they did? Why?

- Is it necessary they do? Why?

If yes:

- What did their awareness-raising campaign look like?

(Probe for: lectures, meetings, brochures/ info sheets…etc)

- How many lectures/ meetings did they have on this topic?

- What was the content of this campaign?

- Do you feel like they were successful at raising awareness towards children with disabilities? Why?

- Were their efforts aimed at students in the school or parents of students?

- If both, how did the campaign efforts vary?

- Are you aware of any projects/ programmes by either UNICEF or Mercy Corps on inclusive education and enhancing public schools to make them friendly to children with disabilities?

If yes, what do you know about it?

- Have your opinions about children with disabilities changed? how so?

- Is there anything else you would like to add to this discussion?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### Out of School Children without Disabilities: Aged between (10-18)

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for this assessment. Your name will not be associated with the study, nor revealed. The session will be recorded. However, only members of the research teams have access to this research effort.

Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- How old are you?

- How do you spend your time during the day?

- Do you currently receive any form of education?

If yes, what? (Probe for vocational training, home schooling…etc.)

- How does not attending school make you feel?

Primary Questions

Accessibility to education

For Dropout Students

Objective: Assessing awareness levels of any improvements made to schools as part of the inclusive education program.

- Do you know if the school you attended made any improvements to its building/s or campus in the past few years?

If yes:

  - What kind of improvements have they made?

(Probe for: ramp, wheelchair accessibility, handicap toilets, handicap parking, wide doorways and halls, Braille signs, sign language translators…etc.)

  - Do you know why your school made these improvements?

(Probe for the students’ understanding of accessibility for children with disabilities…etc.)

  - What kind of improvements do you wish your school would make?

  - How different was your experience from the one just described?

  - How different would your educational experience have been if your school had all these improvements?

(Probe for: emotional and functional benefits …etc.)

  - Would these improvements have encouraged you to stay in school? Why?

- As far as you know, is the education system and schools accessible to children with disabilities?

  - if yes, do you know of any children with disabilities that go to school?

  - Are the education system and public prepared to integrate children with disabilities?

The Ideal Educational Experience:

Objective: Understanding what the ideal school would look and feel like. The focus here is on the emotional and functional elements of a successful educational system.

- Let’s close our eyes and imagine we had the ability to design the ideal school.

Can you describe it to me? (unprompted)

Probe:

  - Where is it located?

  - What do the facilities look like?

(probe for sports courts, bathrooms/ restrooms, ...e.tc

  - What resources does the school have?

  - What do the classrooms look like? (probe for size, space, boards...etc)

- Now let’s imagine together your ideal class experience.

  - What are the teachers like? (Probe for: professional, attentive, patient, understanding, educated, trained…etc.)

  - What are classes like? (Probe for: length of class, distribution of students, interactive…etc.)

  - How many students are with you in class?

- Do you know what an ‘inclusive education program’ is? if yes please explain.

Note to Moderator: Inclusive education, as defined by UNICEF, is an effective way to give all the children a fair chance to go to school, learn, and develop the skills they need in life. Inclusive education means all the children (with and without disability) attend the same classes and in the same schools. It means real learning opportunities for groups who have traditionally been excluded. Inclusive systems value the unique contributions students of all backgrounds bring to the classroom and allow diverse groups to grow side by side, to the benefit of all.

- Now that you know what it means…

  - What do you think of this concept? (Probe for emotional and functional thoughts on the topic)

  - Is it a realistic one? Why?

  - Do you think it’ll be successful? Why?

  - Is it a necessary step to take in public schools? Why?

  - Should this concept be a mandate in all schools? Why?

Awareness towards Children with Disabilities

Objective: Understanding the awareness and perceptions held by participants towards disabilities and children with disabilities

- Do you know what the different type of impairments/ disabilities there are?

(Probe for: visual impairment, speech and hearing impairment, mental disabilities, physical disabilities… etc.)

- Do you know anyone with impairments/ disabilities?

if yes:

  - Does the community accept him/her?

  - Does society provide them with the opportunities and rights they deserve, etc?

- Have you seen or heard of any awareness campaigns on children with disabilities and the importance of inclusive education?

If yes:

  - Who funded this campaign?

  - What did the awareness campaign look like?

  - What was the message of this campaign?

  - Do you feel like the campaign was successful at raising awareness towards children with disabilities? Why?

  - What did you think of the campaign? (probe for likes and dislikes). Why?

- Are you aware of any projects/ programmes by either UNICEF or Mercy Corps on inclusive education and enhancing public schools to make them friendly to children with disabilities?

If yes, what do you know about it?

Secondary Questions:

Were you enrolled in school at some point?

If no, why?

(Probe for the lack of desire -either by child or parents-, lack of means, lack of awareness school is important…etc)

If yes:

- When did you drop out? (year & grade)

- Why did you drop out?

(Probe for: lack of interest, failing classes, to work/support family… etc).

- Whose decision was it that you drop out?

(Probe for: father, mother, it happened organically, personal decision, circumstances… etc).

- Which school were you enrolled in?

(Probe for name and location)

- What did you like about school? What did you dislike about it?

- Would you like to go back to school given the option? Why?

If yes, what stops you from doing so?

We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

### Out of School Children with Disabilities: Aged between (10-18)

Welcome to this discussion group. We are gathered here today to discuss your educational experience at school with a focus on students with disabilities.

I’d like everyone to participate, please don’t be shy. I only ask that we respect and listen to one another. There are no right or wrong answers. All sorts of opinions are welcome here, and honesty is appreciated.

Everything said in this discussion is confidential and will only be used for this assessment. your name will not be associated with the study, nor revealed. The session will be recorded. However, only members of the research teams have access to this research effort.

Having heard these conditions, please confirm accepting these conditions verbally. If you do not wish to do so, kindly let me know now.

Warm-Up Questions

To get to know you a little better, why don’t you tell me a little about yourself.

- How old are you?

- What do you normally do during the day?

- Do you work? if yes, what do you do?

- What kind of disability do you have?

(Probe for: visual impairment, speech and hearing impairment, mental disabilities, physical disabilities… etc).

- Does your ability hinder your education? If so, how?

- Does it affect your learning abilities? If yes, how?

Primary Questions:

- Were you enrolled in school at some point?

If no, why?

(due to disability, the lack of desire, lack of means, lack of awareness school is important…etc.)

If yes:

- When did you drop out? (year & grade)

- Why did you drop out?

(Probe for: disability, lack of interest, failing classes, to work/support family… etc).

- Whose decision was it that you drop out?

(Probe for: father, mother, it happened organically, personal decision, circumstances… etc).

- Was that school accessible to you? How?

- Would you like to go back to school given the opportunity? Why?

If yes, what stops you from doing so?

Accessibility to Education

For Dropout Students

Objective: Assessing awareness levels of any improvements made to schools as part of the inclusive education program.

- Do you know if the school you attended made any improvements to its building/s or campus in the past few years?

If yes:

- What kind of improvements have they made?

- (Probe for: ramp, wheelchair accessibility, handicap toilets, handicap parking, wide doorways and halls, Braille signs, sign language translators…etc.)

- Do you know why your school made these improvements?

(Probe for the students’ understanding of accessibility for CwD…etc.)

- Were the improvements sufficient to make the school accessible to you/ someone with your disability? If yes, please explain

If not, what kind of improvements do you wish your school would make?

- How different would your educational experience be if you had these features?

(Probe for: emotional and functional benefits …etc.)

- How different would your educational experience have been if the school was accessible to you?

(Probe for: emotional and functional benefits …etc.)

- Would these improvements have encouraged you to stay in school? Why?

- As far as you know, were the teachers in the school you attended certified to work with children with disabilities?

If no, why do you think they are not certified?

If yes:

- What kind of certification do they have?

- Which disabilities are they trained to work with? (Probe for: visual impairment, hearing and speech impairment, physical disability, intellectual disability, mental illness, autism spectrum disorder…etc.)

- Did you feel like your teachers are trained to teach you/ people with your type of disability?

If no, why not? (Probe for lacking training, inexperience, lacking suitable resources and materials… etc.)

If yes, why do you think this?

For All Children

- What would you say are the biggest hurdles in the education of children with disabilities in Jordan? Why?

(Probe for: perceptions held towards people with disabilities (by society and their families), the lack of awareness towards this segments’ needs, insufficient funding, shortage or absence of attention by the government/ Ministry of education

- What would it take for public schools to overcome these hurdles?

- Is the education system in Jordan suitable for children with disabilities?

If yes, how?

If no, what needs to happen for the educational system to accommodate children with disabilities?

Rehab sessions & Assistive Devices:

Objective:

- Understanding what materials and resources children with disabilities need for learning and whether the schools they went to had them.

- Understanding what rehab programs, do children with disabilities need and whether the schools they went to had any.

- Let’s assume you were to join a school tomorrow, what resources and materials do you wish the school possessed to help you learn?

(Probe for: audio recorders, timers, reading guides, writing supports, calculators, organizers…etc.)

- How else can your learning experience be optimized?

- Would you need rehab sessions? If yes, what kind?

- Do you know what assistive technology devices are?

- if yes, do you need any?

- what are they?

For Dropout Students Only

- Did the school you went to possess the resources and materials necessary to cater for someone with your disability? (including assistive devices)

(Probe for: electronic worksheets, phonetic spelling softwares, talking calculators, variable, speed recorders…etc.)

- Have you attended any rehab sessions at school?

If no, do you wish the school offered rehab sessions?

If yes:

- Why was it recommended you receive rehab sessions?

- Who decided you should receive rehab sessions? (Probe for: teachers, principals, specialized doctor, school doctor, parents… etc.)

- What kind of rehab sessions did you receive? (Probe for: speech therapy, physical therapy… etc.)

- Did they cost you/ your family anything? If yes, how much?

- Where did you receive these sessions? (Probe for on-location, off-campus, at a public/ private clinic… etc)

- How often did you receive them? (weekly, monthly…etc)

- How long were the sessions?

- Is there a referral system at school for students with disabilities?

If yes:

- What kind of referral system does the school have?

- Why are students referred?

- Where are the students referred to?

- Who tracks these cases?

Awareness towards CwD

Objective: Understanding the awareness and perceptions held by participants towards disabilities and CwD

- Do you know what the UNICEF Inclusive Education Program is?

If yes,

To what extent is the program, and its interventions at the Makani Centers, relevant to the needs of the out of school children with disabilities?

- Have you seen or heard of any awareness campaigns regarding CWD and the importance of inclusive education programs?

If yes:

- What did the awareness campaign look like?

- What was the message of this campaign?

- Do you feel like the campaign was successful at raising awareness towards CWD? Why?

- What did you think of the campaign? (probe for likes and dislikes). Why?

For Dropout Students

- Has there been any effort by the school you attended previously to raise awareness towards disabilities and the importance of inclusive education?

If no:

- Do you wish they did? Why?

- Is it necessary they do? Why?

If yes:

- Who funded this campaign?

- What did their awareness raising campaign look like?

- (Probe for: lectures, meetings, brochures/ info sheets…etc)

- What was the content of this campaign?

- Do you feel like they were successful at raising awareness towards CwD? Why?

- Were their efforts aimed at students in the school or parents of students?

- What did you think of the campaign? (probe for likes and dislikes). Why?

- Are you aware of any projects/ programmes by either UNICEF or Mercy Corps on inclusive education and enhancing public schools to make them friendly to children with disabilities?

If yes, what do you know about it?

- Is there anything else you would like to add to this discussion?

Secondary Questions:

- Do you think education is important? Why?

- Do you currently receive any form of education?

If yes, what? (Probe for vocational training, home-schooling…etc.)

- Who cares for you?

(Probe for legal guardians)

- To what extent do you require your caregivers’ assistance?

(Probe for: all the time, for basic day-to-day activities, during movement and mobility…etc)

The Ideal Educational Experience:

Objective: Understanding the needs and wants of children with disabilities and what the ideal education experience looks like from their point of view.

- Let’s close our eyes and imagine we had the ability to design the ideal school.

- Can you describe it to me? (unprompted)

Probe:

- Where is it located?

- What do the facilities look like?

- (probe for sports courts, bathrooms/ restrooms, ...e.tc

- What resources does the school have?

- What do the classrooms look like? (probe for size, space, boards...etc)

- Now let’s imagine together your ideal class experience.

- What are the teachers like? (Probe for: professional, attentive, patient, understanding, educated, trained…etc.)

- What are classes like? (Probe for: length of class, distribution of students, interactive…etc.)

- How many students are with you in class?

- Do you know what an ‘inclusive education program is’? if yes please explain.

Note to Moderator: Inclusive education, as defined by UNICEF, is an effective way to give all the children a fair chance to go to school, learn, and develop the skills they need in life. Inclusive education means all the children (with and without disability) attend the same classes and in the same schools. It means real learning opportunities for groups who have traditionally been excluded. Inclusive systems value the unique contributions students of all backgrounds bring to the classroom and allow diverse groups to grow side by side, to the benefit of all.

- Now that you know what it means, what do you think of this concept?

- Is it a realistic one? Why?

- (Probe for: predicted probability of success, acceptability by others…etc.)

- Do you think it’ll be successful? Why?

- Is it a necessary step to take in public schools? Why?

- Should this concept be a mandate in all schools? Why?

\We’ve now concluded our discussion for today.

Thank you for coming to speak to us today. We appreciate your time.

## Proposed Classroom Observation Tool

| Physical Environment Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Is the physical set up of the classroom conducive for all students to move easily? |  |  |  |
| - Is the physical set up of the classroom conducive for the child with disabilities to move easily? |  |  |  |
| - Is the child with disabilities’ seat placed in an appropriate place for his/her disability? |  |  |  |
| - Is the seat for the student with a wheelchair, walker, or crutches near the entrance of the classroom? |  |  |  |
| - Is the seat for a hearing impaired (not deaf) student or with communication disabilities near the teacher/front of the class? |  |  |  |
| - Is the seat for a visually impaired (not blind) student near a good source of light? |  |  |  |
| - Is the seat for a _____________ student in a suitable place according to his/her disability? |  |  |  |
| - Is the arrangement of the class the same such that a visually impaired student knows how to move in it? |  |  |  |
| - If changes are made, are measures taken to inform the student or to assist him/her when the change is made? |  |  |  |

General classroom practices (it may not be possible to observe all the following points in one session in one classroom, but maybe in several classes in the school. The cumulative observations of classes in one school will give feedback if these points are present in the school as a whole.)

| Positive Classroom Environment Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Is there a positive classroom atmosphere? |  |  |  |
| - Does the teacher comport him/herself that emanates leadership and kindness? |  |  |  |
| - Does the teacher encourage the students for their involvement in class activities? |  |  |  |
| - Does the teacher reward success taking into consideration students’ abilities? |  |  |  |
| - Are all students’ work displayed on bulletin boards or only what looks good? |  |  |  |
| - Are students encouraged to assist each other in the tasks given by the teacher? |  |  |  |
| - Does the teacher address the student with disabilities in the same tone as the other students are addressed? |  |  |  |
| - Does the teacher have high expectations for achievement for all the students? |  |  |  |
| - Does the teacher set expectations for the student with disabilities that are the best he can achieve or accepts whatever he can do? |  |  |  |

| Class Management Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Are there 5-7 classroom rules that are posted where all students can view them? |  |  |  |
| - Are these rules consistently enforced by the teacher? |  |  |  |
| - Is there a small number of students who don’t go by the rules? What does the teacher do in this situation? |  |  |  |
| - Does the class have routines to follow? |  |  |  |
| - when entering or leaving the classroom |  |  |  |
| - when transitioning from one activity to another |  |  |  |
| - when distributing papers or handing in papers |  |  |  |
| - when shifting from individual seating to small group seating |  |  |  |

| Behaviour Management Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Does the teacher consistently use positive consequences (social, tangible like stickers or tokens, activities) throughout the lesson for appropriate behaviour? |  |  |  |
| - for attentive behaviour |  |  |  |
| - for following rules of the class |  |  |  |
| - for work well done |  |  |  |
| - for good effort in working |  |  |  |
| - Is there a reinforcement system used for all the students in the class for either good behaviour, books read, tracking homework…? |  |  |  |
| - Does there seem to be a system for giving out negative consequences for inappropriate behaviours, work not done…. |  |  |  |
| - Does the teacher give second chances to misbehaviours that may occur during the lesson? |  |  |  |
| - Is there a system of managing the behaviour of one or few students who consistently misbehave or disrupt the class? |  |  |  |

| Organization of Lesson Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Does the lesson have a clear beginning? |  |  |  |
| - Does the lesson have a clear ending? |  |  |  |
| - Are the materials for that lesson prepared ahead of time? |  |  |  |
| - If adapted materials are needed for the children with disabilities, are they readily available? |  |  |  |
| - Are there clear and smooth transitions from one activity to another within the lesson? |  |  |  |
| - Are instructions clear and presented both orally and written on the board? |  |  |  |
| - Is the time of the lesson well managed? |  |  |  |

| Teaching Methods Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Does the teacher build on the previous experiences or previous learning of the students? |  |  |  |
| - Is the goal of the lesson clear to all? If applicable, does the teacher highlight how, what is going to be learned, is meaningful to the students’ everyday lives? |  |  |  |
| - Are the activities of the lesson directly related to the goal of the lesson? |  |  |  |
| - Does the teacher use a multi-sensory approach during instruction? |  |  |  |
| - Does the teacher use both individual work and active learning methods during the lessons? |  |  |  |
| - pairs |  |  |  |
| - small group work |  |  |  |
| - how does the teacher ensure that the students with children with disabilities understand the task at hand? |  |  |  |
| - Does the student receive support to do the task at hand? |  |  |  |
| - is the child with disabilities paired with another student who assists the student? |  |  |  |
| - does the child with disabilities receive support from a shadow teacher? |  |  |  |
| - Do the students receive feedback for both correct and incorrect answers? |  |  |  |
| - Are tasks adapted to the different levels of the students? |  |  |  |
| - Can students with disabilities present their work in different ways than the rest of the class? |  |  |  |
| - if the student can’t write, can s/he do the work orally, or typed on a tablet? |  |  |  |
| - if the student has difficulty in communicating, is s/he given alternate ways of answering questions or reciting lessons? |  |  |  |
| - Is the learning of the student with disabilities assessed in a way that suits their disability? if yes, how? |  |  |  |
| - Are basic adaptations to tasks made for all students including children with disabilities? |  |  |  |
| - is extra time to complete a task or assessment given? |  |  |  |
| - if a student needs a reader or writer for a task or assessment, is that available? |  |  |  |
| - Are difficulties in learning seen as stemming from the student or from the relationship between the teacher, student, and learning environment? |  |  |  |

## Proposed School Tour Observation Tool

| Physical Environment Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - Is the physical environment of the school (entrance/exit, hallways) set up in such a way that enables all students to move around freely, particularly for children with disabilities? |  |  |  |
| - If not, what supportive measures have been taken for children with disabilities to move around the school especially at times of congestion, such as coming to and leaving school, walking in hallways... circle appropriate answers: buddies for children with disabilities, monitors, school staff, others _________ |  |  |  |
| - When a new child with disabilities joins the school, is s/he given orientation for the school environment? Are areas where a child with disabilities needs assistance identified and type of assistance decided upon? |  |  |  |
| - Are playgrounds (or internal halls for breaks in winter) conducive for children with disabilities? If children with disabilities cannot participate in usual break time activities of students, have any alternative activities been put in place for them? |  |  |  |
| - Is the cafeteria conducive for children with disabilities to move around in it easily? |  |  |  |
| - If not, what supportive measures have been taken to assist them inside the cafeteria? circle appropriate answers: buddies for children with disabilities, monitors, school staff, others _________ |  |  |  |
| - If some children with disabilities have difficulty with money transactions, who assists them in buying? |  |  |  |

| Inclusive Practices Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| School Staff |  |  |  |
| - Was there a whole- school training program before the inclusion of children with disabilities? |  |  |  |
| - Did it include all staff such as administrative, non-teaching staff? |  |  |  |
| - What are main areas of training on inclusive practices offered to the teaching staff prior to the inclusion of children with disabilities? |  |  |  |
| - Was it for all teachers at the school or just those receiving children with disabilities in their classrooms? |  |  |  |
| - On what basis were teachers chosen to include children with disabilities in their classes? |  |  |  |
| - Has a process of including children with disabilities been a gradual one? |  |  |  |
| - What is the aim for how many children with disabilities will be included in the whole school? |  |  |  |
| - If number of children with disabilities per class, how many classes in the school? |  |  |  |
| - If percentage of children with disabilities for school, what is the total number of students and the percentage they are aiming for? |  |  |  |
| - Was the training of the staff a one-time thing or is there on-going training programs? |  |  |  |
| - If on-going, what additional training have they done, in particular for teachers? |  |  |  |
| - What difficulties have they encountered with non-teaching staff and teaching staff in including students with children with disabilities? |  |  |  |
| - What measures have been put in place by the administration to support teaching staff with their students with disabilities? |  |  |  |
| - Do they have a supervisor for the program? Or do they have a committee of several people who oversees the program? - What qualifications does the supervisor or members of the committee have? |  |  |  |
| - Do teachers collaborate to discuss and solve problems/difficulties they encounter? - Is this scheduled within their school program? |  |  |  |
| - How do teachers share their successes with other teaching staff? |  |  |  |
| - Does the school allocate time within the schedule for the teachers who have children with disabilities to prepare materials specifically for them? |  |  |  |

| Inclusive Practices Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| Students |  |  |  |
| - How were the students at the whole school prepared for including children with disabilities? |  |  |  |
| - Or was the preparation just for the students of the classes where children with disabilities were placed? |  |  |  |
| - What policies does the school have to deal with mistreating children with disabilities, such as teasing, isolating, labelling, bullying? |  |  |  |
| - Have students been involved in supporting children with disabilities in school: mobility within the school, cafeteria…? |  |  |  |
| - Does the school have extra-curricular activities? If yes, are children with disabilities included? |  |  |  |
| - If the extra-curricular activities are not suitable for the child with disabilities, has the school started other activities that the children with disabilities can participate in? |  |  |  |
| - Has the school organized activities with the intention of involving all students with and without disabilities with the aim of building an understanding and acceptance of each other? |  |  |  |
| - Give examples of these activities ------------------- |  |  |  |
| - Does the school show the achievements of all its students or just its high achievers? |  |  |  |
| - Does the school see inclusion as an obstacle for achieving high academic standing in the educational community? |  |  |  |
| - Does the school favor academic achievement over developing the potential of all its students? |  |  |  |
| - Does the school include children from different cultural, national, religious and socioeconomic backgrounds? |  |  |  |
| - If yes, does it see this as enriching its community or as problematic? |  |  |  |

NB: Questions 9 and 10  are more for city schools and may not be appropriate for schools in camps and rural areas.

| Inclusive Practices Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| Parents |  |  |  |
| - How were the parents of the school prepared for the inclusion of children with disabilities with their children? |  |  |  |
| - What difficulties did they have with parents after children with disabilities were included in their children’s classes? |  |  |  |
| - How were the parents of the children with disabilities prepared for including their children in mainstream schools? |  |  |  |
| - What concerns did they have prior to inclusion? After inclusion? |  |  |  |
| - How does the school support the parents of children with disabilities in and out of the school? |  |  |  |
| - Are parents of all students involved in the school or its activities? If yes, how? |  |  |  |
| - Are activities planned for parents of students with and without disabilities together so that they have the opportunity to get to know and understand each other? |  |  |  |

| Other Resources in the School Questions Resource Room | Yes | No | Comments |
| --- | --- | --- | --- |
| - Does the school have a resource room? |  |  |  |
| - What is the role of the resource room? |  |  |  |
| - as a source of support for teachers that have children with disabilities in their classroom? |  |  |  |
| - as a learning class for children with disabilities who are pulled out of the regular classroom? |  |  |  |
| - Both? |  |  |  |
| - What percentage of the children with disabilities need to be pulled out? |  |  |  |
| - What percentage of their study hours are they pulled out for? |  |  |  |
| - Is there a process for children with disabilities to gradually decrease their time in the resource room, depending on the children with disabilities abilities and gap with their peers? |  |  |  |

Shadow teachers

Based on the MC reports we have read so far, it is not clear what the shadow teachers’ role is. Our understanding of what a shadow teacher is seems to be different than the activities they are involved in the MC program.

The questions will be developed once we get a job description from MC or UNICEF.

| Evaluation of the Program from school’s Perspective Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| - As a school, how long have you been involved with MC/UNICEF’s project on inclusive education? |  |  |  |
| - In your opinion, what are the benefits that the whole school has acquired with this program? |  |  |  |
| - In your opinion, what are the drawbacks/difficulties that the school has experienced? |  |  |  |
| - what is required for you to overcome these difficulties? |  |  |  |
| - In order to move forward as a school, what do you need to sustain this program? |  |  |  |
| - Did you choose/volunteer to be in this program or were you chosen to do so? |  |  |  |
| - What new policies did you have to make after accepting children with disabilities? |  |  |  |

| Preparation for handover to MoE Questions | Yes | No | Comments |
| --- | --- | --- | --- |
| From the onset of your involvement with the MC/UNICEF inclusion program, you have known that the MoE will eventually be supervising your inclusion program. |  |  |  |
| - How many years has your school been involved with this program? |  |  |  |
| - When is the school expected to be handed over to MoE? |  |  |  |
| - Have any preparations been made for the handover? |  |  |  |
| - If yes, what are they? |  |  |  |
| - Have you met the people responsible for this project at MoE? |  |  |  |
| - What concerns, if any, do you have about the handover? |  |  |  |

## Proposed Teachers Survey

To be transferred to SurveyMonkey

- Are you a teacher, supervisor, or principal?

| - Teacher | - Principal |
| --- | --- |
| - Supervisor | - None (end survey) |

- Do you work in a public school?

| - Yes | - No (end survey) |
| --- | --- |

- If you are a teacher, which grade/s do you teach? (You may choose more than one answer)

| - 1st | - 2nd | - 3rd | - 4th | - 5th |
| --- | --- | --- | --- | --- |
| - 6th | - 7th | - 8th | - 9th | - 10th |

- if you are a teacher, are you a homeroom teacher?

| - Yes | - No |
| --- | --- |

- Name the school you work in.

[Open ended question]________________

- Which governorate is the school in?

| - Amman | - Irbid | - Mafraq | - Jerash |
| --- | --- | --- | --- |
| - Zarqa | - Balqa | - Ajloun | - Madaba |
| - Karak | - Tafileh | - Ma’an | - Aqaba |

- if you are a teacher, what subjects do you teach? (You may choose more than one)

| - Science | - Math | - Religious studies | - Arabic |
| --- | --- | --- | --- |
| - English | - Geography | - History | - PE |

Others (please specify): -----------

- Do you teach/ work with students with disabilities?

| - Yes | - No |
| --- | --- |

If yes,

  - Are you certified to work with CwD?

| - Yes | - No |
| --- | --- |

  - How long was your training?

| - 1-3 months | - 3-6 months | - 6-12 months |
| --- | --- | --- |
| - 12-24 months | - More than 24 months |  |

  - Where did you receive your training?

| - In Jordan | - Outside Jordan |
| --- | --- |

  - What entity/ board certified you?

[open ended]________________

  - Which impairments or disabilities are you trained to work with? (you may choose more than one)

| - visual impairment | - intellectual impairment |
| --- | --- |
| - hearing impairment | - mental impairment |
| - speech impairment | - autism spectrum disorder |
| - physical impairment | - other (please specify) |

  - Which of these impairments or disabilities do you work with now or have worked with in the past? (you may choose more than one)

| - visual impairment | - intellectual impairment |
| --- | --- |
| - hearing impairment | - mental impairment |
| - speech impairment | - autism spectrum disorder |
| - physical impairment | - other (please specify) |

  - Which CWD age segments do you/ did you teach? (you may choose more than one)

| - Below 6 | - 6-9 |
| --- | --- |
| - 10-14 | - 15-18 |

  - Do you know how to read Braille?

| - Yes | - No |
| --- | --- |

  - Do you know Sign Language?

| - Yes | - No |
| --- | --- |

  - Do you use assistive technology devices while teaching CWD?

| - Yes | - No |
| --- | --- |

IF yes

    - What kind of assistive tech have you used

| - Electronic Worksheets | - Phonetic Spelling Software |
| --- | --- |
| - Talking Calculators | - Variable Speed Recorders |
| - Videotaped Social Skills. | - Others [please specify]__________ |

  - Does your school offer any rehabilitation sessions for CwD?

| - Yes | - No |
| --- | --- |

IF yes

    - Where do they give these sessions

| - On-location | - Off-site |
| --- | --- |

  - Do you have a referral system at school for children with disabilities?

| - Yes | - No |
| --- | --- |

  - What would you say are the biggest hurdles in the education of children with disabilities? (you may choose more than one)

- Perceptions held towards disabilities by society - perceptions held towards disabilities by the child’s family - The lack of awareness towards the needs of CWD - The lack of means - Insufficient funding from governmental bodies - Shortage of attention by the government/ Ministry of education - Other [please specify]________

- Is the current education system in Jordan suitable for children with disabilities?

| - Yes | - No |
| --- | --- |

- Has there been any effort by the school you work in to accommodate students with disabilities?

| - Yes | - No |
| --- | --- |

IF Yes

  - What kind of improvements have they made? (you may choose more than one answer)

| - added ramps | - added handicap parking |
| --- | --- |
| - widened doors and hallway | - designated an area in class for CWD |
| - levelled flooring | - added accessible toilets |
| - added Braille signs | - provided sign language translators |
| - others [please specify] ___________ |  |

- Do you know what an ‘inclusive education’ concept is?

| - Yes | - No |
| --- | --- |

IF Yes

  - Has your school been chosen to run the inclusive education programme?

| - Yes | - No |
| --- | --- |

  - In your opinion, does the inclusive education program meet the needs of CWD in terms of enabling them to fully engage in the learning process (as with children without disability)?

| - Yes | - No |
| --- | --- |

- Do you believe that all children have the right to education?

| - Yes | - No |
| --- | --- |

- Do you believe that no child should be excluded based on diversity characteristics?

| - Yes | - No |
| --- | --- |

- Do you believe that the education system should be adapted to the learner rather than the learner to the system?

| - Yes | - No |
| --- | --- |

- Do you believe the Ministry of Education is doing all that can be done for children with disabilities?

| - Yes | - No |
| --- | --- |

- Do you believe that children with disabilities cannot learn?

| - Yes | - No |
| --- | --- |

- Has there been any effort by the school to raise awareness towards disabilities and the importance of inclusive education?

| - Yes | - No |
| --- | --- |

END OF SURVEY

## Translated Key Informant Interview Guides

### وزارة التربية والتعليم

مرحباً سيد/ سيدة ___________ . نحن هنا اليوم بصدد مناقشة برنامج اليونيسيف للتعليم الدامج مع حضرتكم.

يرجى العلم بأنه لا توجد هنالك إجابات صحيحة أو خاطئة، نحن نسعى للحصول على آرائكم ووجهات نظركم فقط. كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إليكم أو عائد لكم. سيتم تسجيل الجلسة، ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

هل توافق على هذه القواعد؟ من خلال قبول ما تم ذكره ومواصلة هذه المقابلة ، فإنك تمنح فريقنا موافقتك على استخدام المعلومات التي تقدمها لنا في إطار استكمال تقييم برنامج اليونيسيف للتعليم الدامج.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - ما هو مسماك الوظيفي/ منصبك في وزارة التربية والتعليم؟ (الاستفهام حول: رئيس قسم التربية والتعليم، قسم التربية الخاصة) وعلى المستوى اليداني للمديرية (الموظفين المعنين مثل المشرفين(.

  - ماذا يتطلب عملك؟

  - منذ متى وأنت تعمل هنا ؟

المقدمة

الهدف: فهم التصورات السائدة تجاه برنامج التعليم الدامج من وجهة نظر ممثلي وزارة التربية والتعليم.

- هو الدور الذي تقوم به )إن وجد( فيما يتعلق ببرنامج التعليم الدامج؟

  - كيف ترى أو تتصور نجاح برنامج التعليم الدامج؟

  - ما هي نقاط القوة والضعف في البرنامج؟

  - ما هي أهم التحديات التي تواجه المدارس في تحقيق أهداف البرنامج؟

- ما هي  أهم العقبات التي تعيق الأطفال ذوي الاحتياجات الخاصة من الاستفادة من برنامج التعليم الدامج؟

- في عام 2014 ، ما هي القاعدة التأسيسية للمفاهيم والسياسات ذات العلاقة ببرنامج التعليم الدامج مقابل التعليم الدامج ؟

- كيف تغير الأساس المفاهيمي/ السياسات لبرنامج اليونيسيف للتعليم الدامج بين 2014-2019؟

- إلى أي مدى ينعكس دعم اليونيسف بين 2014-2019 في الإستراتيجية الوطنية للتعليم الدامج

- ما هي المجالات التي يتماشى فيها البرنامج من الناحية المفاهيمية / السياسات مع استراتيجية التعليم الدامج الوطنية (NIES)؟

- ما هي المجالات التي لا يتماشى فيها أو يختلف فيها برنامج اليونيسيف للتعليم الدامج من الناحية المفاهيمية /السياسات عن الاستراتيجية الوطنية للتعليم الدامج ؟

- هل يمكنك القول بأن برنامج التعليم الدامج القائم يوازن بين الجنسين في ممارسات التوظيف الخاصة به؟ كيف ذلك؟

  - هل يتم معاملة الإناث والذكور بنفس الطريقة من قبل البالغين/الكبار في البرنامج ؟

- هل يتضمن البرنامج معايير/إجراءات  محددة لمعالجة عدم المساواة ؟

- هل يستند برنامج التعليم الدامج من الناحية المفاهيمية إلى حقوق الإنسان؟

- هل تعكس وثائق برنامج التعليم الدامج ولغته نهجاً يركز على حقوق الإنسان والطفل؟

- هل تعرف ما إذا كان المجتمع المدرسي الدامج موجهاً نحو الاندماج؟ (أولياء الأمور ، مقدمو الرعاية والمجتمع الدامج ، الأطفال الآخرون ... إلخ(

عملبة الانتقال/التسليم والاستدامة

الهدف: فهم ما يتصوره ممثلي وزارة التربية والتعليم حول عملية الانتقال/التسليم لبرنامج التعليم الدامج، وما إذا كانوا يعتقدون أن البرنامج مستدام وقابل للتوسع أم لا.

- إلى أي مدى تعتقد أن وزارة التربية والتعليم لديها القدرة الكافية لتولي المهام اللازمة وقيادة البرنامج بأكمله دون دعم من قبل اليونيسف؟ (الاستفهام حول: الموارد البشرية ، الموارد المالية ، القدرات الفنية... الخ)

- هل تعتقد أن عملية الانتقال/التسليم من اليونيسف إلى وزارة التربية والتعليم ستكون سلسة؟ ما الذي يجعلك تقول ذلك؟

- هل تعتقد أن برنامج التعليم الدامج هو نظام مستدام؟ لماذا ؟

- هل خطة الانتقال/التسليم المعدة للبرنامج كافية لتحقيق الاستدامة المنشودة في الاستراتيجية الوطنية؟

- من وجهة نظرك ، ما مدى قدرة وزارة التربية والتعليم على تكرار وتوسيع نطاق البرنامج في الأردن؟ لماذا ا؟

- هل تمتلك وزارة التربية والتعليم القدرة الفنية على الاستمرار في تشغيل برنامج التعليم الشامل؟ لماذا ا؟

- ما الذي يمكن أن يعيق قدرة وزارة التربية والتعليم على تكرار توسيع برنامج التعليم الشامل ليشمل مدارس أخرى؟ لماذا ا؟

- هل تعتقد أن وزارة التربية والتعليم لديها ميزانية لمواصلة تشغيل برنامج التعليم الشامل كما تديره اليونيسف الآن؟

- ما هي العناصر/المبادئ التي يجب أخذها بعين الاعتبار أثناء عملية التوسع/الانتشار ؟

- ما هي المتطلبات اللازمة لضمان الانتقال /التسليم السلس للبرنامج من اليونيسيف وميرسي كور إلى وزارة التربية والتعليم؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### المجلس الأعلى لحقوق الأشخاص ذوي الاعاقة

مرحباً سيد/ سيدة الاسم . نحن هنا اليوم بصدد مناقشة برنامج اليونيسيف للتعليم الدامج مع حضرتكم.

يرجى العلم بأنه لا توجد هنالك إجابات صحيحة أو خاطئة، نحن نسعى للحصول على آرائكم ووجهات نظركم فقط. كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إليكم أو عائد لكم. سيتم تسجيل الجلسة، ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

هل توافق على هذه القواعد؟ من خلال قبول ما تم ذكره ومواصلة هذه المقابلة ، فإنك تمنح فريقنا موافقتك على استخدام المعلومات التي تقدمها لنا في إطار استكمال تقييم برنامج اليونيسيف للتعليم الدامج.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - ما هو مسماك الوظيفي/ منصبك  في المجلس الأعلى لحقوق الأشخاص ذوي الإحتياجات الخاصة؟

  - ماذا يتطلب عملك ؟

  - منذ متى وانت تعمل هنا ؟

السياق والوعي بالخلفية/الوعي بالسياق والخلفية

الهدف: فهم التصورات السائدة تجاه البرنامج التعليمي القائم ومدى ملاءمته للأطفال من ذوي الاحتياجات الخاصة.

- هل نظام التعليم في الأردن يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، فكيف؟

إذا كانت الإجابة "لا"، ماذا يتطلب النظام التعليمي لاستيعاب وتلبية احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

- من وجهة نظرك، ماهي أكبر التحديات التي يواجهها الأطفال من ذوي الاحتياجات الخاصة فيما يتعلق بالتعليم في الاردن؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم.

  - ماذا يتطلب الأمر للتغلب على هذه العقبات؟

تقييم برنامج التعليم الدامج

الهدف: فهم الحاضرين وتصوراتهم فيما يتعلق ببرنامج التعليم الدامج وتصوراتهم له، من الناحية النظرية والعملية.

- ما هو الدور الذي تقوم به )إن وجد( فيما يتعلق ببرنامج التعليم الدامج؟

- هل شاركت في الاستراتيجية التي تم اتباعها في تصميم برنامج التعليم الدامج نظرياً؟  إذا كانت الإجابة "نعم"، فما الدور الذي قمت به؟

- برأيك، هل تم تنفيذ برنامج التعليم الدامج وفقاً للخطة / الاستراتيجية؟

- إلى أي مدى يتداخل/يتشابه برنامج التعليم الدامج مع الاستراتيجية الوطنية للتعليم؟

- برأيك، ما هي المجالات التي يتماشى فيها البرنامج من الناحية المفاهيمية / السياسات مع استراتيجية التعليم الدامج الوطنية (NIES)؟

ما هي المجالات التي لا يتماشى فيها أو يختلف فيها البرنامج عن الاستراتيجية الوطنية للتعليم الدامج ؟

- هل يمكنك القول بأن برنامج اليونيسيف القائم للتعليم الدامج يوازن بين الجنسين في ممارسات التوظيف الخاصة به؟ كيف ذلك؟

- هل يتم معاملة الإناث والذكور بنفس الطريقة من قبل البالغين/الكبار في البرنامج ؟

- هل يتضمن برنامج التعليم الدامج معايير/إجراءات محددة لمعالجة عدم المساواة؟يرجى التوضيح

- هل يستند برنامج التعليم الدامج من الناحية المفاهيمية إلى حقوق الإنسان؟ يرجى التوضيح

- هل تعكس وثائق برنامج التعليم الدامج ولغته نهجاً يركز على حقوق الإنسان والطفل؟  يرجى التوضيح

- كيف ترى أو تتصور نجاح برنامج التعليم الدامج؟ ماالذي يجعلك تقول ذلك؟

- ما هي " مجالات الفرص" المتاحة لتحسين البرنامج من وجهة نظرك؟

- هل يمكنك القول بأن المزيد من الأطفال من ذوي الاحتياجات الخاصة التحقوا بالمدارس منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل يمكنك القول بأن المدارس احتفظت بالمزيد من الأطفال من ذوي الاحتياجات الخاصة منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل لديك بيانات تظهر الزيادة في الالتحاق/التسجيل ومدى الاحتفاظ بالأطفال من ذوي الاحتياجات الخاصة في المدارس بين عامي 2014 و2019؟

- هل هناك جزء يتعلق بإعادة التأهيل في برنامج التعليم الدامج ؟ إذا كانت الإجابة "نعم" ، ماذا يشمل ذلك؟

- هل هنالك نظام إحالة في المدرسة؟

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم":

- كيف يبدو؟

- لماذا تتم إحالة الطلاب؟

- أين تتم إحالة الطلاب؟

عملبة الانتقال/التسليم والاستدامة

الهدف: فهم العمليات التي تم وضعها بهدف ضمان الانتقال /التسليم السلس والفعال لبرنامج التعليم الدامج إلى وزارة التربية والتعليم مع تسليط الضوء على العناصر التي تُعد ضرورية لاستدامته واحتمالية توسعته أي زيادة انتشاره.

- إلى أي مدى تعتقد أن وزارة التربية والتعليم لديها القدرة الكافية لتولي المهام اللازمة وقيادة البرنامج بأكمله دون دعم من قبل اليونيسف؟

(الاستفهام حول: الموارد البشرية ، الموارد المالية ، القدرات الفنية... الخ)

- اهي العوامل/ العناصر التي قد تجعل برنامج التعليم الدامج نظاماً مستداماً؟ لماذا؟

- هل خطة الانتقال/التسليم المعدة للبرنامج كافية لتحقيق الاستدامة المنشودة في الاستراتيجية الوطنية؟

- ما هي المعوقات التي قد تعيق هذا الإنجاز؟

ما هي المتطلبات اللازمة (من قبل اليونيسيف) لضمان الانتقال /التسليم السلس للبرنامج من اليونيسيف وميرسي كور إلى وزارة التربية والتعليم؟

- إلى أي مدى تتضح أعمال التأييد/المناصرة التي تقدمها اليونيسيف بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

- البرنامج؟

- تطوير سياسة وزارة التربية والتعليم؟

- إلى أي مدى تتضح المساعدة الفنية التي تقدمها اليونيسف بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

- البرنامج؟

- تطوير سياسة وزارة التربية والتعليم؟

- إلى أي مدى يتضح تكوين واستخدام اليونيسف للبيانات المتعلقة بالتعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة، ضمن؟

- البرنامج؟

- تطوير سياسة وزارة التربية والتعليم؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### منظمة الأمم المتحدة للطفولة (اليونيسيف)

مرحباً سيد/ سيدة ___________ . نحن هنا اليوم بصدد مناقشة برنامج اليونيسيف للتعليم الدامج مع حضرتكم.

يرجى العلم بأنه لا توجد هنالك إجابات صحيحة أو خاطئة، نحن نسعى للحصول على آرائكم ووجهات نظركم فقط. كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إليكم أو عائد لكم. سيتم تسجيل الجلسة، ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

هل توافق على هذه القواعد؟ من خلال قبول ما تم ذكره ومواصلة هذه المقابلة ، فإنك تمنح فريقنا موافقتك على استخدام المعلومات التي تقدمها لنا في إطار استكمال تقييم برنامج اليونيسيف للتعليم الدامج.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - ما هو مسماك الوظيفي/ منصبك في اليونيسيف؟

  - ماذا يتطلب عملك؟

  - منذ متى وأنت تعمل هنا ؟

السياق والوعي بالخلفية/الوعي بالسياق والخلفية

الهدف : فهم التصورات السائدة تجاه برنامج التعليم الدامج من وجهة نظر UNICEF

- هل نظام التعليم في الأردن مناسب للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم" كيف ذلك؟

إذا كانت الإجابة "لا"، ماذا يتطلب النظام التعليمي لاستيعاب وتلبية احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

- من وجهة نظرك، ماهي أكبر التحديات التي يواجهها الأطفال من ذوي الاحتياجات الخاصة فيما يتعلق بالتعليم في الاردن؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم

  - ماذا يتطلب الأمر للتغلب على هذه العقبات؟

تقييم ذاتي لبرنامج التعليم الدامح

الهدف: فهم الحاضرين ومسؤولياتهم

- ما هو الدور الذي تقوم به إن وجد)فيما يتعلق ببرنامج التعليم الدامج؟

- برأيك ما هي نقاط القوة والضعف في البرنامج؟

- ما هي القاعدة التأسيسية للمفاهيم/السياسات ذات العلاقة بالبرنامج؟

- هل تغير الأساس المفاهيمي/ السياسات بين 2014-2019 ؟ في حال تغيرت، فكيف ذلك؟

- إلى أي مدى انعكس دعم اليونيسف على الاستراتيجية الوطنية للتعليم الدامج بين 2014-2019  ؟

- برأيك، ما هي المجالات التي يتماشى فيها البرنامج من الناحية المفاهيمية / السياسات مع استراتيجية التعليم الدامج الوطنية ؟

  - ما هي المجالات التي لا يتماشى فيها أو يختلف فيها البرنامج عن الاستراتيجية الوطنية للتعليم الدامج ؟

- هل يمكنك القول بأن البرنامج القائم للتعليم الدامج يوازن بين الجنسين في ممارسات التوظيف الخاصة به؟ كيف ذلك؟

  - هل يتم معاملة الإناث والذكور بنفس الطريقة من قبل البالغين/الكبار في البرنامج ؟

- هل يتضمن برنامج اليونيسيف للتعليم الدامج معايير/إجراءات محددة لمعالجة عدم المساواة ؟ يرجى التوضيح

- هل يستند برنامج التعليم الدامج من الناحية المفاهيمية إلى حقوق الإنسان؟ يرجى التوضيح

- هل تعكس وثائق برنامج التعليم الدامج ولغته نهجاً يركز على حقوق الإنسان والطفل؟ يرجى التوضيح

- كيف ترى أو تتصور نجاح برنامج التعليم الدامج؟ ماالذي يجعلك تقول ذلك؟

- ما هي " مجالات الفرص" المتاحة لتحسين البرنامج من وجهة نظرك؟

- هل يمكنك القول بأن المزيد من الأطفال من ذوي الاحتياجات الخاصة التحقوا بالمدارس منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل يمكنك القول بأن المدارس احتفظت بالمزيد من الأطفال من ذوي الاحتياجات الخاصة منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل لديك بيانات تظهر بوضوح الزيادة في الالتحاق/التسجيل ومدى الاحتفاظ بالأطفال من ذوي الاحتياجات الخاصة في المدارس بين عامي 2014 و2019؟

- هل تعرف عدد الأطفال الملتحقين/المسجلين الذين تقدموا بالمراحل الدراسية/الصفوف بين عامي 2014 و 2019 ؟

- هل قمت ( أو اليونيسف) بتزويد المدارس بأي مواد أو موارد لمساعدتهم في تعليم الطلاب من ذوي الإحتياجات الخاصة؟

إذا كانت الإجابة"لا"، لماذا؟

إذا كانت الإجابة "نعم

  - ماهي الموارد/المواد التي قمتم بتزويدها؟

- هل قامت اليونيسيف) بتزويد المدارس بأي أجهزة تقنية مساعدة لمساعدتهم في تعليم الطلاب من ذوي الاحتياجات الخاصة؟

- هل يوجد برنامج إعادة تأهيل في برنامج التعليم الشامل؟ إذا كانت الإجابة نعم ، فماذا يشمل ذلك؟ (التحقيق في الخدمات المضمنة)

- هل هنالك نظام إحالة في المدرسة؟

- إذا كانت الإجابة "لا"، لماذا؟

- إذا كانت الإجابة "نعم":

  - كيف يبدو؟

  - لماذا تتم إحالة الطلاب؟

  - أين تتم إحالة الطلاب؟

عملبة الانتقال/التسليم والاستدامة

الهدف: فهم العمليات التي تم وضعها بهدف ضمان الانتقال /التسليم السلس والفعال لبرنامج التعليم الدامج إلى وزارة التربية والتعليم مع تسليط الضوء على العناصر التي تُعد ضرورية لاستدامته واحتمالية توسعته أي زيادة انتشاره

- إلى أي مدى تعتقد أن وزارة التربية والتعليم لديها القدرة الكافية لتولي المهام اللازمة وقيادة البرنامج بأكمله دون دعم من قبل اليونيسف؟

- ) الاستفهام حول: الموارد البشرية ، الموارد المالية ، القدرات الفنية... الخ)

- ماهي العوامل/ العناصر التي قد تجعل برنامج التعليم الدامج نظاماً مستداماً؟ لماذا؟

- هل خطة الانتقال/التسليم المعدة للبرنامج كافية لتحقيق الاستدامة المنشودة في الاستراتيجية الوطنية؟

- ما هي المعوقات التي قد تعيق هذا الإنجاز؟

- ما هي العناصر/المبادئ التي يجب أخذها بعين الاعتبار أثناء عملية التوسع/الانتشار الجغرافي؟

- ما هي المتطلبات اللازمة لضمان الانتقال /التسليم السلس للبرنامج من اليونيسيف وميرسي كور إلى وزارة التربية والتعليم؟

- إلى أي مدى تتضح أعمال التأييد/المناصرة التي تقدمها ميرسي كور بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- إلى أي مدى تتضح المساعدة الفنية التي تقدمها ميرسي كور بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- إلى أي مدى يتضح تكوين واستخدام ميرسي كور للبيانات المتعلقة بالتعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة، ضمن؟

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- عند اختيار موقع مدرسة للمشاركة في البرنامج، هل تم بذل جهود لضمان أخذ الخصائص القابلة للتأثر (مثل الفقر) بعين الاعتبار؟

تكلفة الطالب وإختيار المدارس

- هل تعرف التكلفة لكل طالب ذوي إعاقة في برنامج التعليم الشامل؟

- اذا نعم

  - كيف تقارن التكلفة بالطلاب ذوي الإعاقة في البرامج الأخرى؟

  - كيف تقارن التكلفة مع الطلاب الآخرين الذين ليس لديهم إعاقة في نفس المدرسة؟

- ما هي العوامل التي تأخذونها في عين الاعتبار عند حسابة التكلفة؟

  - النفقات التشغيلية

  - شدة العجز أو التجريد

  - التنظيم اللوجستي

  - المواد والموارد اللازمة

  - جلسات إعادة التأهيل

  - تكلفة تغييرات البنية التحتية التي تم إجراؤها على الحرم المدرسي والفصول الدراسية

- كيف تحسب تكلفة كل فئة من الفئات المذكورة؟

  - ما هي العوامل الأخرى التي تأخذها في الاعتبار عند تقييم التكلفة لكل طالب؟

- في رأيك ، ما الذي يحدد "الفئات السكانية الضعيفة"؟ (التحقيق في: وضع اللاجئ ، الخلفية الاقتصادية ، الجنسية ... إلخ)

- ما هي المعايير التي تدخل في الاعتبار المدارس المختارة للانضمام إلى برنامج التعليم الشامل؟

  - نسبة السكان المعرضين للخطر

  - موقعك

  - عمر المبنى / ق

  - عدد الطلاب

  - عدد الطلاب ذوي الإعاقة في المدرسة / في المنطقة

  - / أو عدم وجود مركز مكاني قريب وجود

- حاليًا ، ما المعسكرات التي يوجد بها برنامج التعليم الشامل؟

- لماذا اخترت هذا المعسكر بالذات؟ (تحقق من الفئات الأكثر ضعفًا ، والوصول ، وحجم السكان ... إلخ)

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### ميرسي كور

مرحباً سيد/ سيدة ___________ . نحن هنا اليوم بصدد مناقشة برنامج اليونيسيف للتعليم الدامج مع حضرتكم.

يرجى العلم بأنه لا توجد هنالك إجابات صحيحة أو خاطئة، نحن نسعى للحصول على آرائكم ووجهات نظركم فقط. كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إليكم أو عائد لكم. سيتم تسجيل الجلسة، ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

هل توافق على هذه القواعد؟ من خلال قبول ما تم ذكره ومواصلة هذه المقابلة ، فإنك تمنح فريقنا موافقتك على استخدام المعلومات التي تقدمها لنا في إطار استكمال تقييم برنامج اليونيسيف للتعليم الدامج.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - ما هو مسماك الوظيفي/ منصبك في منظمة ميرسي كور؟

  - ماذا يتطلب عملك؟

  - منذ متى وأنت تعمل هنا ؟

السياق والوعي بالخلفية/الوعي بالسياق والخلفية

الهدف : فهم التصورات السائدة تجاه برنامج التعليم الدامج من وجهة نظر MercyCorps

- هل نظام التعليم في الأردن مناسب للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم" كيف ذلك؟

إذا كانت الإجابة "لا"، ماذا يتطلب النظام التعليمي لاستيعاب وتلبية احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

- من وجهة نظرك، ماهي أكبر التحديات التي يواجهها الأطفال من ذوي الاحتياجات الخاصة فيما يتعلق بالتعليم في الاردن؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم

  - ماذا يتطلب الأمر للتغلب على هذه العقبات؟

تقييم ذاتي لبرنامج التعليم الدامح

الهدف: فهم الحاضرين ومسؤولياتهم

- ما هو الدور الذي تقوم به (إن وجد) فيما يتعلق ببرنامج التعليم الدامج؟

- برأيك ما هي نقاط القوة والضعف في البرنامج؟

- ما هي القاعدة التأسيسية للمفاهيم/السياسات ذات العلاقة بالبرنامج؟

- هل تغير الأساس المفاهيمي/ السياسات بين 2014-2019 ؟ في حال تغيرت، فكيف ذلك؟

- إلى أي مدى انعكس دعم اليونيسف على الاستراتيجية الوطنية للتعليم الدامج بين 2014-2019  ؟

- برأيك، ما هي المجالات التي يتماشى فيها البرنامج من الناحية المفاهيمية / السياسات مع استراتيجية التعليم الدامج الوطنية ؟

  - ما هي المجالات التي لا يتماشى فيها أو يختلف فيها البرنامج عن الاستراتيجية الوطنية للتعليم الدامج ؟

- هل يمكنك القول أن وثائق برنامج التعليم الدامج توفر إطاراً مفاهيمياً يستند إلى:

  - الاتفاقية الدولية لحقوق الطفل (خاصةً المادة 28)؟

  - اتفاقية حقوق الأشخاص ذوي الإعاقة (خاصةً المادة 24)؟

  - الملاحظات العامة على اتفاقية حقوق الأشخاص ذوي الإعاقة # 4؟

  - هدف التنمية المستدامة # 4 ؟

- هل يمكنك القول بأن البرنامج القائم للتعليم الدامج يوازن بين الجنسين في ممارسات التوظيف الخاصة به؟ كيف ذلك؟

  - هل يتم معاملة الإناث والذكور بنفس الطريقة من قبل البالغين/الكبار في البرنامج ؟

- هل يتضمن برنامج اليونيسيف للتعليم الدامج معايير/إجراءات محددة لمعالجة عدم المساواة ؟ يرجى التوضيح

- هل يستند برنامج التعليم الدامج من الناحية المفاهيمية إلى حقوق الإنسان؟ يرجى التوضيح

- هل تعكس وثائق برنامج التعليم الدامج ولغته نهجاً يركز على حقوق الإنسان والطفل؟ يرجى التوضيح

- كيف ترى أو تتصور نجاح برنامج التعليم الدامج؟ ماالذي يجعلك تقول ذلك؟

- ما هي " مجالات الفرص" المتاحة لتحسين البرنامج من وجهة نظرك؟

- هل يمكنك القول بأن المزيد من الأطفال من ذوي الاحتياجات الخاصة التحقوا بالمدارس منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل يمكنك القول بأن المدارس احتفظت بالمزيد من الأطفال من ذوي الاحتياجات الخاصة منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل لديك بيانات تظهر بوضوح الزيادة في الالتحاق/التسجيل ومدى الاحتفاظ بالأطفال من ذوي الاحتياجات الخاصة في المدارس بين عامي 2014 و2019؟

- هل تعرف عدد الأطفال الملتحقين/المسجلين الذين تقدموا بالمراحل الدراسية/الصفوف بين عامي 2014 و 2019 ؟

- هل قمت ( أو اليونيسف) بتزويد المدارس بأي مواد أو موارد لمساعدتهم في تعليم الطلاب من ذوي الإحتياجات الخاصة؟

إذا كانت الإجابة"لا"، لماذا؟

- إذا كانت الإجابة "نعم

  - ماهي الموارد/المواد التي قمتم بتزويدها؟

- هل قمت (أو اليونيسيف) بتزويد المدارس بأي أجهزة تقنية مساعدة لمساعدتهم في تعليم الطلاب من ذوي الاحتياجات الخاصة؟

- هل يوجد برنامج إعادة تأهيل في برنامج التعليم الشامل؟ إذا كانت الإجابة نعم ، فماذا يشمل ذلك؟ (التحقيق في الخدمات المضمنة)

- هل هنالك نظام إحالة في المدرسة؟

- إذا كانت الإجابة "لا"، لماذا؟

- إذا كانت الإجابة "نعم":

  - كيف يبدو؟

  - لماذا تتم إحالة الطلاب؟

  - أين تتم إحالة الطلاب؟

عملبة الانتقال/التسليم والاستدامة

الهدف: فهم العمليات التي تم وضعها بهدف ضمان الانتقال /التسليم السلس والفعال لبرنامج التعليم الدامج إلى وزارة التربية والتعليم مع تسليط الضوء على العناصر التي تُعد ضرورية لاستدامته واحتمالية توسعته أي زيادة انتشاره

- إلى أي مدى تعتقد أن وزارة التربية والتعليم لديها القدرة الكافية لتولي المهام اللازمة وقيادة البرنامج بأكمله دون دعم من قبل اليونيسف؟

- ) الاستفهام حول: الموارد البشرية ، الموارد المالية ، القدرات الفنية... الخ)

- ماهي العوامل/ العناصر التي قد تجعل برنامج التعليم الدامج نظاماً مستداماً؟ لماذا؟

- هل خطة الانتقال/التسليم المعدة للبرنامج كافية لتحقيق الاستدامة المنشودة في الاستراتيجية الوطنية؟

- هل تعتقد أنه يمكن تكرارها وتوسيعها/ زيادة مدى انتشارها بحيث تشمل جميع أنحاء المملكة؟ كيف؟

- ما هي المعوقات التي قد تعيق هذا الإنجاز؟

- ما هي العناصر/المبادئ التي يجب أخذها بعين الاعتبار أثناء عملية التوسع/الانتشار الجغرافي؟

- ما هي المتطلبات اللازمة لضمان الانتقال /التسليم السلس للبرنامج من اليونيسيف وميرسي كور إلى وزارة التربية والتعليم؟

- إلى أي مدى تتضح أعمال التأييد/المناصرة التي تقدمها ميرسي كور بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم

- إلى أي مدى تتضح المساعدة الفنية التي تقدمها ميرسي كور بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- إلى أي مدى يتضح تكوين واستخدام ميرسي كور للبيانات المتعلقة بالتعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة، ضمن؟

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- عند اختيار موقع مدرسة للمشاركة في البرنامج، هل تم بذل جهود لضمان أخذ الخصائص القابلة للتأثر (مثل الفقر) بعين الاعتبار؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### مدراء المدارس

مرحباً سيد/ سيدة ___________ . نحن هنا اليوم بصدد مناقشة برنامج اليونيسيف للتعليم الدامج مع حضرتكم.

يرجى العلم بأنه لا توجد هنالك إجابات صحيحة أو خاطئة، نحن نسعى للحصول على آرائكم ووجهات نظركم فقط. كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إليكم أو عائد لكم. سيتم تسجيل الجلسة، ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

هل توافق على هذه القواعد؟ من خلال قبول ما تم ذكره ومواصلة هذه المقابلة ، فإنك تمنح فريقنا موافقتك على استخدام المعلومات التي تقدمها لنا في إطار استكمال تقييم برنامج اليونيسيف للتعليم الدامج.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - أنت مدير أي مدرسة؟ (الاسم وال منطقة)

  - كم سنة وأنت مدير هذه المدرسة ؟

الأسئلة الرئيسية

المقدمة

الهدف: فهم مسؤولياتهم ومؤهلاتهم للتعامل مع الأطفال من ذوي الإحتياجات الخاصة

- ما هي الإعاقات التي تقوم بالتعامل معها حالياً أو قمت بالتعامل معها مسبقاً؟

(الاستفهام حول: ضعف البصر، ضعف النطق والسمع، الإعاقة الجسدية، الإعاقة الذهنية، المرض العقلي، اضطراب طيف التوحد...إلخ)

- هل دمج وإشراك الأطفال من ذوي الاحتياجات الخاصة يختلف عنه للأطفال الأصحاء؟

إذا كانت الإجابة "لا" ، فلما لا؟

إذا كانت الإجابة "نعم" ما هو وجه الاختلاف

- ? هل دمج وإشراك الأطفال من ذوي الاحتياجات الخاصة يختلف بين الأعمار التاليه 6-9,  10-14,  أو 15-18 سنة

- هل يتلقى المعلمين أي دعم أو مساعدة أثناء تعليم الأطفال ذوي الإعاقة؟

إذا كانت الإجابة بنعم ، فمن الذي يقدم هذا الدعم؟

- ما نوع الإشراف  الذي يتلقاه المعلمين لمساعدتهم في تعليم الأطفال ذوي الإعاقة؟

إمكانية الوصول إلى التعليم

الهدف: فهم التسهيلات التي قامت بها المدرسة بهدف تسيير الخدمات التربوية/التعليمية للأطفال من ذوي الاحتياجات الخاصة، بما في ذلك التعديلات على البنية التحتية لمبى أو مباني المدرسة إضافة إلى توفير المواد والمصادر/الموارد الضرورية لتعليمهم.

- بشكل عام، ما هي أكبر عوائق وتحديات تعليم ذوي الاحتياجات الخاصة ؟ لماذا؟

(الاستفسار حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم.

- ماذا يتطلب الأمر للتغلب على هذه العقبات؟

- هل نظام التعليم في الأردن يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف؟

إذا كانت الإجابة "لا"، فما الذي ينبغي أن يحدث للنظام التعليمي لاستيعاب ومراعاة الأطفال من ذوي الاحتياجات الخاصة؟

- هل هناك جهود مبذولة من قبل المدرسة لتلبية احتياجات الطلاب من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

  - منذ متى قامت المدرسة بتحسينات البنية التحتية؟

  - بناءً على معرفتك، لماذا قامت المدرسة بهذه التحسينات؟

  - من هي الجهة، (إن وجد)، الممولة لهذه التحسينات؟

(الاستجوب حول: التحسينات التي تم ذكرها)

- هل قدمت المدرسة أية مواد أو موارد/مصادر للمعلمين لتمكينهم من تعليم الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

  - ما هي المواد/المصادر التي تقدمها المدرسة؟

  - هل هي كافية ؟

  - ماذا ينقصهم أيضاً؟

- هل تعلم ما هي الأجهزة التقنية المساعدة للأطفال ذوي الاحتياجات الخاصة؟

ملاحظة لمنظم/منسق الجلسة: الأجهزة التكنولوجية المساعدة: هي " أي جهاز أو قطعة من المستلزمات/الأدوات أو نظام إنتاج يستخدم لزيادة أو الحفاظ على أو تحسين القدرات الوظيفية للطفل من ذوي الاحتياجات الخاصة."

إذا كانت الإجابة "نعم":

  - هل عندكم أي منها ؟

  - هل  تلقى المعلمين  تدريبات متخصصة باستخدام هذه الأجهزة؟ إذا كانت الإجابة، نعم، أي منها؟

  - إلى أي مدى تساعد هذه الأجهزة؟

- كم عدد الأطفال من ذوي الاحتياجات الخاصة ممن تم تحديد احتياجهم للأجهزة التقنية المساعدة (بناءً على البرنامج التربوي الفردي IEP ) الذين بإمكانهم الوصول إلى واستخدام المنتجات والتقنيات المساعدة؟

- إلى أي مدى يتم توفير الموارد والتقنيات المساعدة والتدريب المقدم بما يتماشى مع الإعاقات المستهدفة؟

- بماذا قامت المدرسة أيضاً لتسهيل عملية تعلم الأطفال من ذوي الاحتياجات الخاصة؟

تدريب المعلمين والتوجيهات

- هل تم تقديم تدريب على مستوى المدرسة للمعلمين؟

- ما هي المعايير الرئيسية المستخدمة في الأهلية لبرنامج تدريب المعلمين على الأطفال ذوي الإعاقة؟

هل يتعين على المعلمين الحصول على درجة علمية أو خبرة واسعة في العمل مع الأطفال؟

هل كان التدريب / التدريبات كافية؟

- هل تلقيت أي تدريب لتعليم الأطفال ذوي الإعاقة؟

اذا نعم

  - ما هي المكونات الرئيسية لنموذج التدريب؟

  - كيف تغير نموذج تدريب المعلمين بين عامي 2014 و 2019؟

- إلى أي مدى يكون نموذج تدريب المعلمين فعالاً وكافياً في تمكين المعلمين من دعم استبقاء وتعلم الأطفال ذوي الإعاقة؟

- هل تعتقد أن التدريب الذي تلقيته قد أثر على مهاراتك وقدرتك على تضمين الأطفال ذوي الإعاقة والاحتفاظ بهم؟

- هل كانت هناك سياسات في المدرسة تدعم التعليم الشامل قبل ظهور هذا البرنامج؟

- هل تم توجيه طلاب المدرسة نحو برنامج الدمج؟

- هل تم توجيه المجتمع المدرسي الأوسع بما في ذلك الآباء) نحو الإدماج؟

الوعي تجاه الجهة المانحة و برنامج التعليم الشامل

- متى التحقت المدرسة ببرنامج التعليم الشامل؟ (الاستفهام حول: شهر، سنة)

- كم من المدة قضت؟ وهل مازال مستمراً؟

(الاستفهام حول: إذا استمرت المدرسة في تشغيل البرنامج أم أن المعلمين يرون أنه لاداعي له أو مبالغ به)

- ما نوع التدخلات التي تم تطبيقها؟

(الاستفهام حول: التدخلات الملموسة والتدخلات غير الملموسة)

- ما رأيك في مفهوم "التعليم الشامل" لجميع الطلاب ، بما في ذلك الأطفال ذوي الإعاقة؟

  - ما هي نقاط قوتها؟

  - ما هي نقاط ضعفها

  - هل هو مفهوم واقعي؟ لماذا ا؟

  - التحقيق في: الاحتمال المتوقع للنجاح ، ومقبولية النظام ، إلخ

  - هل هي خطوة ضرورية في المدارس العامة؟ لماذا ا؟

  - هل يجب أن يكون "التعليم الشامل" أمرًا يفرضه القانون على المدارس؟

- هل الأطفال من ذوي الاحتياجات الخاصة مخولون ولديهم الإمكانية للوصول إلى البرنامج التربوي الفردي المطور بالكامل والمحدث (IEP)؟ إذا كانت الإجابة "نعم"، كم عدد الأطفال؟

- كم عدد الأطفال الذين أحرزوا تقدماً ناجحاً في البرنامج ، كما ورد في البرنامج التربوي الفردي  الخاص بهم ؟

- في المتوسط، كم ساعة يقضي الطفل في البرنامج التربوي الفردي بغرفة المصادر، في اليوم الواحد؟

- هل الأطفال من ذوي الاحتياجات الخاصة أكثر أو أقل احتمالية بالمشاركة في أنشطة التعلم المدرسية مقابل زملائهم (الأصحاء) ؟

- من وجهة نظرك، هل برنامج التعليم الشامل يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة من حيث تمكينهم من المشاركة الكاملة في عملية التعلم ( كما هو الحال مع الأطفال الذين الأصحاء )

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

- برأيك ، إلى أي مدى تتماشى/تتطابق ممارساتك في الغرفة الصفية مع التدريب الذي تلقيته؟

  - هل تتلقى أي مساعدة لتمكينك من تطبيق الممارسات المتعلقة بعملية الإدماج ؟

- هل غرفة المصادر تستخدم بفعالية وكفاءة بما يتماشى مع  التدريب المقدم ؟

التآزر مع وزارة التربية والتعليم

- إلى أي مدى يعكس برنامج التعليم الشامل نوع الجنس والعدالة والنهج القائم على حقوق الإنسان؟

  - هل يتضمن البرنامج معايير  محددة لمعالجة عدم المساواة ؟

  - هل  يستند البرنامج من الناحية المفاهيمية إلى حقوق الإنسان؟

  - هل تعتقد أن وثائق البرامج ولغته تعكس نهجاً يركز على حقوق الإنسان والطفل ؟

- ماذا تعرف عن استراتيجية التعليم الشامل الوطنية؟

  - إلى أي مدى يتماشى ويتوافق  برنامج التعليم الشامل مع الاستراتيجية الوطنية؟

  - إذا لم يتماشى/يتوافق  برنامج التعليم الشامل مع الاستراتيجية الوطنية ، فما هي الفجوات بينهم وكيف يمكن معالجتها؟

- إلى أي مدى يتماشى/يتوافق برنامج التعليم الشامل مع الممارسات العالمية (لجنة حقوق الطفل، اتفاقية حقوق الأشخاص ذوي الإعاقة...)؟

- من وجهة نظرك، إلى أي مدى قد يكون برنامج التعليم الشامل فعالاً في تحقيق نتائج للأطفال من ذوي الاحتياجات الخاصة؟

- إلى أي مدى يمكن القول بأن  أهداف البرنامج  قد تحققت بفعالية من حيث

  - دعم التحاق الأطفال والاحتفاظ بهم في المدارس؟

  - هل تعتقد أن لديك القدرة على التأثير على التحاق الأطفال من ذوي الاحتياجات الخاصة والاحتفاظ بهم في المدارس؟ إذا كانت الإجابة "نعم"، إلى أي مدى؟

  - دعم تعلم الأطفال ومشاركتهم / التزامهم في المقررات الدراسية

  - تغيير سلوك الأطفال ومقدمي الرعاية والممارسات في المدارس.

- هل هناك أية عقبات تحد من تحقيق الأهداف المعنية من برنامج التعليم الشامل؟

إذا كانت الإجابة نعم، فماذا؟

- كم عدد الأطفال الذين تم تسجيلهم والاحتفاظ بهم في عام 2014؟ و كم عدد الأطفال الذين تم تسجيلهم والاحتفاظ بهم في عام 2019؟

- هل تعتقد أن التدريب الذي تلقيته قد أثر على مهاراتك وقدرتك على تضمين الأطفال ذوي الإعاقة والاحتفاظ بهم؟

- إلى أي مدى يعد نموذج تدريب المعلمين فعال وكافٍ لتمكين المعلمين من الحفاظ على الطلاب من ذوي الاحتياجات الخاصة وتعليمهم ؟

- هل تعرف ما إذا كان سيتم تسليم هذا البرنامج في المستقبل إلى وزارة التربية والتعليم أو متى؟

- هل تم تسليم إدارة البرنامج إلى وزارة التربية والتعليم؟

إذا كانت الإجابة "نعم"

  - متى تم ذلك؟

  - كيف بدت العملية؟

  - هل كانت عملية النقل سهلة وميسرة؟

  - هل تأثر البرمانج منذ ذلك الحين؟ إذا كانت الإجابة "نعم"، كيف ذلك؟

- هل لديك أي مخاوف بشأن هذا البرنامج الذي تشرف عليه وزارة التربية والتعليم؟

جلسات إعادة التأهيل والأجهزة المساعدة:

الهدف:  تقييم مدى معرفتهم  بجلسات إعادة التأهيل والأجهزة المساعدة.

- بناءً على معرفتك، هل تقدم المدرسة  أي جلسات إعادة تأهيل للطلاب من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

  - أين يتم إعطاء هذه الجلسات؟ (الاستفسار حول: في الموقع (المدرسة) مقابل خارج الموقع (خارج المدرسة)، غرفة مخصصة، أجهزة مساعدة......الخ)

- هل لديك نظام إحالة للطلاب ذوي الاحتياجات الخاصة في المدرسة؟

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم":

- ما نوع نظام الإحالة المتواجد حالياً في المدرسة؟

- متى تم إنشاؤه ؟

- هل نظام الإحالة فعال في تحديد وضمان الوصول إلى الأطفال من ذوي الاحتياجات الخاصة المتواجدين في المدرسة؟

- لماذا تتم إحالة الطلاب؟

- أين تتم إحالة الطلاب؟

- هل عانى أو واجه نظام الإحالة من أي تغييرات بين عامي 2014 و 2019 ؟

إذا كانت الإجابة "نعم" ، يرجى وصف وشرح ما هي الاختلافات ولماذا تم تطبيقها.

زيادة الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الجهود المبذولة (إن وجدت) في نقل التصور السائد تجاه الأطفال من ذوي الاحتياجات الخاصة وأهمية وجود نظام التعليم الشامل.

- هل قامت المدرسة ببذل أي جهود لزيادة الوعي تجاه ذوي الاحتياجات الخاصة وأهمية التعليم الشامل؟

إذا كانت الإجابة "لا":

- هل تتمنى لو قاموا بذلك؟  لماذا؟

- هل من الضروري أن يقوموا بذلك؟ لماذا؟

إذا كانت الإجابة "نعم":

- كيف كانت/بدت الحملة التوعوية التي قامت بها؟

(الاستفسار حول: المحاضرات ، الاجتماعات ، الكتيبات/ أوراق المعلومات...إلخ)

- كم عدد المحاضرات/الاجتماعات التي تم عقدها حول هذا الموضوع؟

- ما هو محتوى الحملة؟

- هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

- هل كانت جهودهم موجهة إلى طلاب أخرين أو لأولياء الأمور ومقدمي الرعاية مثلكم؟

إذا تم تسليم إدارة البرنامج إلى وزارة التربية والتعليم:

متى حدث ذلك؟

كيف بدت العملية؟

هل كان الانتقال سلسًا؟

هل تأثر البرنامج منذ ذلك الحين؟ اذا نعم فكيف

إلى أي مدى تغيرت آرائكم حول الأطفال من ذوي الاحتياجات الخاصة منذ 2014؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

اسئلة ثانوية

- ما هي القضايا التي توجهونها اليوم في التدريس بشكل عام ؟

هل أنتم قادرون على التغلب/تجاوز هذه الصعوبات؟

إذا كانت الإجابة "لا"، لما لا؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

- هل لديكم معلمين مدربين على إدماج الأطفال من ذوي الاحتياجات الخاصة في الغرف الصفية؟

إذا كانت الإجابة "لا"" (الاستفهام حول: نقص المهارة/ التدريب اللازم للتعامل مع الأطفال من ذوي الاحتياجات الخاصة، سهولة الوصول في المدرسة، التصور السائد تجاه الأطفال من ذوي الاحتياجات الخاصة،......الخ)

لقد اختتمنا الآن مناقشتنا لهذا اليوم.

شكرًا لحضروركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### المؤسسة الألمانية للتعاون الدولي (GIZ), وزارة الخارجية وشؤون الكومنولث (FCDO)

مرحباً سيد/ سيدة ___________ . نحن هنا اليوم بصدد مناقشة برنامج اليونيسيف للتعليم الدامج مع حضرتكم.

يرجى العلم بأنه لا توجد هنالك إجابات صحيحة أو خاطئة، نحن نسعى للحصول على آرائكم ووجهات نظركم فقط. كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إليكم أو عائد لكم. سيتم تسجيل الجلسة، ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

هل توافق على هذه القواعد؟ من خلال قبول ما تم ذكره ومواصلة هذه المقابلة ، فإنك تمنح فريقنا موافقتك على استخدام المعلومات التي تقدمها لنا في إطار استكمال تقييم برنامج اليونيسيف للتعليم الدامج.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - ما هو مسماك الوظيفي/ منصبك في منظمة GIZ/ FCDO؟

  - ماذا يتطلب عملك؟

  - منذ متى وأنت تعمل هنا ؟

السياق والوعي بالخلفية/الوعي بالسياق والخلفية

الهدف : فهم التصورات السائدة تجاه برنامج التعليم الدامج من وجهة نظر GIZ/ FCDO

- هل نظام التعليم في الأردن مناسب للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم" كيف ذلك؟

إذا كانت الإجابة "لا"، ماذا يتطلب النظام التعليمي لاستيعاب وتلبية احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

- من وجهة نظرك، ما هي أكبر التحديات التي يواجهها الأطفال من ذوي الاحتياجات الخاصة فيما يتعلق بالتعليم في الاردن؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم

  - ماذا يتطلب الأمر للتغلب على هذه العقبات؟

تقييم ذاتي لبرنامج التعليم الدامج

الهدف: فهم الحاضرين ومسؤولياتهم

- ما هو الدور الذي تقوم به (إن وجد) فيما يتعلق ببرنامج التعليم الدامج؟

- برأيك ما هي نقاط القوة والضعف في البرنامج؟

- ما هي القاعدة التأسيسية للمفاهيم/السياسات ذات العلاقة بالبرنامج؟

- هل تغير الأساس المفاهيمي/ السياسات بين 2014-2019 ؟ في حال تغيرت، فكيف ذلك؟

- إلى أي مدى انعكس دعم اليونيسف على الاستراتيجية الوطنية للتعليم الدامج بين 2014-2019  ؟

- هل يمكنك القول بأن البرنامج القائم للتعليم الدامج يوازن بين الجنسين في ممارسات التوظيف الخاصة به؟ كيف ذلك؟

  - هل يتم معاملة الإناث والذكور بنفس الطريقة من قبل البالغين/الكبار في البرنامج ؟

- هل يتضمن برنامج اليونيسيف للتعليم الدامج معايير/إجراءات محددة لمعالجة عدم المساواة ؟ يرجى التوضيح

- هل يستند برنامج التعليم الدامج من الناحية المفاهيمية إلى حقوق الإنسان؟ يرجى التوضيح

- هل تعكس وثائق برنامج التعليم الدامج ولغته نهجاً يركز على حقوق الإنسان والطفل؟ يرجى التوضيح

- كيف ترى أو تتصور نجاح برنامج التعليم الدامج؟ ما الذي يجعلك تقول ذلك؟

- ما هي " مجالات الفرص" المتاحة لتحسين البرنامج من وجهة نظرك؟

- هل يمكنك القول بأن المزيد من الأطفال من ذوي الاحتياجات الخاصة التحقوا بالمدارس منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل يمكنك القول بأن المدارس احتفظت بالمزيد من الأطفال من ذوي الاحتياجات الخاصة منذ تطوير/إدخال برنامج التعليم الدامج في عام 2014؟

- هل لديك بيانات تظهر بوضوح الزيادة في الالتحاق/التسجيل ومدى الاحتفاظ بالأطفال من ذوي الاحتياجات الخاصة في المدارس بين عامي 2014 و2019؟

- هل تعرف عدد الأطفال الملتحقين/المسجلين الذين تقدموا بالمراحل الدراسية/الصفوف بين عامي 2014 و 2019 ؟

- هل قمت ( أو اليونيسف) بتزويد المدارس بأي مواد أو موارد لمساعدتهم في تعليم الطلاب من ذوي الإحتياجات الخاصة؟

إذا كانت الإجابة"لا"، لماذا؟

- إذا كانت الإجابة "نعم

  - ما هي الموارد/المواد التي قمتم بتزويدها؟

- هل قمت (أو اليونيسيف) بتزويد المدارس بأي أجهزة تقنية مساعدة لمساعدتهم في تعليم الطلاب من ذوي الاحتياجات الخاصة؟

- هل يوجد برنامج إعادة تأهيل في برنامج التعليم الشامل؟ إذا كانت الإجابة نعم ، فماذا يشمل ذلك؟ (التحقيق في الخدمات المضمنة)

- هل هنالك نظام إحالة في المدرسة؟

- إذا كانت الإجابة "لا"، لماذا؟

- إذا كانت الإجابة "نعم":

  - كيف يبدو؟

  - لماذا تتم إحالة الطلاب؟

  - أين تتم إحالة الطلاب؟

عملية الانتقال/التسليم والاستدامة

الهدف: فهم العمليات التي تم وضعها بهدف ضمان الانتقال /التسليم السلس والفعال لبرنامج التعليم الدامج إلى وزارة التربية والتعليم مع تسليط الضوء على العناصر التي تُعد ضرورية لاستدامته واحتمالية توسعته أي زيادة انتشاره

- إلى أي مدى تعتقد أن وزارة التربية والتعليم لديها القدرة الكافية لتولي المهام اللازمة وقيادة البرنامج بأكمله دون دعم من قبل اليونيسف؟

- ) الاستفهام حول: الموارد البشرية ، الموارد المالية ، القدرات الفنية... الخ)

- هل تعتقد أن عملية الانتقال/التسليم إلى وزارة التربية والتعليم ستكون سلسة؟ ما الذي يجعلك تقول ذلك؟

- ماهي العوامل/ العناصر التي قد تجعل برنامج التعليم الدامج نظاماً مستداماً؟ لماذا؟

- هل خطة الانتقال/التسليم المعدة للبرنامج كافية لتحقيق الاستدامة المنشودة في الاستراتيجية الوطنية؟

- هل تعتقد أنه يمكن تكرارها وتوسيعها/ زيادة مدى انتشارها بحيث تشمل جميع أنحاء المملكة؟ كيف؟

- ما هي المعوقات التي قد تعيق هذا الإنجاز؟

- ما هي العناصر/المبادئ التي يجب أخذها بعين الاعتبار أثناء عملية التوسع/الانتشار الجغرافي؟

- ما هي المتطلبات اللازمة لضمان الانتقال /التسليم السلس للبرنامج من اليونيسيف وميرسي كور إلى وزارة التربية والتعليم؟

- إلى أي مدى تتضح أعمال التأييد/المناصرة التي تقدمها ميرسي كور بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم

- إلى أي مدى تتضح المساعدة الفنية التي تقدمها ميرسي كور بشأن التعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة ضمن:

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- إلى أي مدى يتضح تكوين واستخدام ميرسي كور للبيانات المتعلقة بالتعليم الدامج و/أو الأطفال ذوي الاحتياجات الخاصة، ضمن؟

  - البرنامج؟

  - تطوير سياسة وزارة التربية والتعليم؟

- عند اختيار موقع مدرسة للمشاركة في البرنامج، هل تم بذل جهود لضمان أخذ الخصائص القابلة للتأثر (مثل الفقر) بعين الاعتبار؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم وللوقت الذي قضيتموه معنا اليوم.

## Translated Focus Group Discussion Guides

### أولياء الأمور ومقدمي الرعاية

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة،لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - هل أنت ولي أمر أو مقدم رعاية؟

ملاحظة لمنظم/ميسر الجلسة: إذا كانت الإجابة لا، يرجى استئذان المشارك بمغادرة المجموعة.

  - كم عمر الطفل الذي تعتني به؟

  - في أي صف  يدرس  طفلك؟

  - هل يعاني الطفل من أي إعاقة/عجز معين؟ إذا كانت الإجابة " نعم"، ما نوعها؟

(الاستفهام حول: ضعف البصر، ضعف النطق والسمع ، الإعاقة العقلية، الإعاقة الذهنية، المرض العقلي، اضطراب طيف التوحد...إلخ)

  - كم سنة قضيت وأنت مقدم الرعاية الرئيسي؟

  - هل تعتني بأي أطفال أخرين؟ إذا كانت الإجابة "نعم"، فمن هم؟

  - هل يعانون من عجز/إعاقة أيضاً؟

- أخبرني عن يومك الطبيعي/روتينك اليومي؟ كيف يبدو؟

المقدمة

الهدف: فهم المشاركين ومسؤولياتهم ومؤهلاتهم (مقدمي الرعاية) للتعامل مع الأطفال من ذوي الاحتياجات الخاصة

- متى قمت بتسجيل الطفل؟

(الاستفهام حول: قبل سنة 2014 أم بعد ذلك)

- هل تواجه أية صعوبات في العناية بالطفل أو الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، ما هي تلك الصعوبات؟

  - هل تغلبت/تجاوزت تلك الصعوبات؟ إذا كانت الإجابة "نعم" كيف تم ذلك؟

- هل تقوم بمساعدة طفلك  من ذوي الاحتياجات الخاصة على الدراسة؟

(الاستفهام حول:  عدم توفر المهارة /الدراية الفنية اللازمة لتعليم الأطفال من ذوي الاحتياجات الخاصة، الإفتقار إلى إمكانية الوصول للمصادر والمواد المطلوبة، قلة الوقت..... الخ)

- هل تربية الأطفال من ذوي الاحتياجات الخاصة تختلف عن تربية الأطفال الأصحاء؟

إذا كانت الإجابة "لا" ، فلما لا؟

إذا كانت الإجابة "نعم" ما هو وجه الاختلاف؟

- ماهي طرق الاتصال المختلفة التي تستخدمها في التعامل مع مختلف الحالات/ الإعاقات؟

(الاستفهام حول: استخدام بريل، لغة الإشارة، دعائم، المحفزات البصرية والسمعية.......الخ)

إمكانية الوصول إلى التعليم

الهدف: فهم ما إذا كان الطفل لدية الإمكانية للوصول إلى الخدمات التربوية/التعليمية وما هي المصادر والمواد اللازمة لمساعدته في تعليمه.

- بشكل عام، ماهي أكبر عوائق وتحديات تعليم ذوي الاحتياجات الخاصة ؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم.

- ماذا يتطلب الأمر للتغلب على هذه العقبات؟

- هل نظام التعليم في الأردن يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف؟

إذا كانت الإجابة "لا"، فما الذي ينبغي أن يحدث للنظام التعليمي لاستيعاب ومراعاة الأطفال من ذوي الاحتياجات الخاصة؟

- ما هي العوامل التي قمت بأخذها بعين الاعتبار عند اختيارك للمدرسة؟

(الاستفهام حول: سهولة/إمكانية الوصول، الأرصفة المعدة لذوي الاحتياجات الخاصة، مواقف لذوي الاحتياجات الخاصة، قاعات واسعة، دورات مياه لذوي الاحتياجات الخاصة، إشارات بريل، إشارات بريل والمواد ذات العلاقة، مترجمي لغة الإشارة  )

- هل هناك جهوذ مبذولة من قبل المدرسة لتلبية احتياجات الطلاب من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

  - منذ متى قامت المدرسة بتحسينات البنية التحتية؟

  - بناءً على معرفتك، لماذا قامت المدرسة بهذه التحسينات؟

- هل هناك معلم/ة مساعده في الصف؟  هل يعطى طفلك أي إهتمام خاص ؟

- برأيك ، هل المعلمون الذين يعلمون طفلك مجهزين للقيام بذلك؟ ما الذي جعلك تقول ذلك؟

- هل قامت المدرسة أيضاً لتسهيل عملية تعلم الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة نعم ، فكيف؟

الإستفهام حول: إضافة سلالم ، مواقف سيارات للمعاقين ، أبواب أوسع ، أرضيات مستوية ، مراحيض للمعاقين ... إلخ

- منذ متى أدخلت المدرسة تحسينات البنية التحتية هذه؟

- على حد علمك ، لماذا أجروا هذه التحسينات؟

- من الذي مول هذه التحسينات؟

التوعية والتصورات لبرنامج التعليم الشامل

الهدف: فهم الأنظمة والبروتوكولات ، إن وجدت ، التي تمتلكها المدارس للأطفال ذوي الإعاقة

- ماذا تعرف عن  برنامج يونيسف" التعليم الدامج" لكافة الطلاب بما فيهم الأطفال من ذوي الاحتياجات الخاصة؟

  - ما هي نقاط قوة وضعف البرنامج؟

(الاستفهام حول ـ: الاحتمالية المتوقعة للنجاح، تقبل الآخرين...الخ).

  - هل هو مفهوم واقعي؟  لماذا؟

  - هل هي خطوة ضرورية يجب اتخاذها في المدارس الحكومية؟ لماذا؟

  - هل ينبغي أن يكون هذا المفهوم إلزامي في جميع المدارس؟ لماذا؟

إذا كانت الإجابة "لا"، فلما لا؟

إذا كانت الإجابة "نعم"، هل يجب أن يطبق ذلك في المدراس الحكومية أم الخاصة؟ لماذا؟

- هل تم إرشادك وتوجيهك حول مفهوم " الإدماج"؟ يرجى الشرح

- ما هي مدة التحاق طفلك في برنامج التعليم الدامج؟

  - كيف كانت تجربة طفلك في هذا البرنامج؟

  - كيف سمعت/ي في البداية عن البرنامج؟

  - هل استفاد طفلك من البرنامج؟ إذا كانت الإجابة بنعم ، كيف كان ذلك؟

  - هل لديك أي توصيات لتحسن سير عمل البرنامج ؟

- هل تم توجيهك نحو الشمولية؟ يرجى توضيح

البرنامج التربوي الفردي (IEP)

الهدف: فهم ما إذا كان الطفل لدية الإمكانية للوصول إلى الخدمات التربوية/التعليمية وما هي المصادر والمواد اللازمة لمساعدته في تعليمه.

- هل تعلم ما هو البرنامج التربوي الفردي؟

إذا كانت الإجابة "نعم": يرجى الشرح

- هل الطفل الذي تتولى رعايته مخول للوصول إلى البرنامج التربوي الفردي المطور بالكامل والمحدث (IEP)؟

- في المتوسط، كم ساعة يقضي الطفل في البرنامج التربوي الفردي بغرفة المصادر، في اليوم الواحد؟

- هل يشارك الطفل في أنشطة التعلم المدرسية مثل زملائه (الأصحاء) ؟

- هل تحضر أية إجتماعات ذات علاقة بالبرنامج التربوي الفردي ((IEP؟ ما الذي يتم مناقشته في مثل هذه الجلسات؟

المواد ,الموارد ,والأجهزة المساعدة

الهدف: تقييم مدى معرفة الآباء ومقدمي الرعاية بالموارد والأجهزة المساعدة التي يستخدمها المعلمون لمساعدة أطفالهم في التعلم.

- هل قدمت المدرسة أية مواد أو موارد/مصادر لتمكين معلمي أطفالك من التواصل معهم؟

إذا كانت الإجابة "لا":

  - ما هي المواد/المصادر التي تتمنى لو أن المعلم بإمكانه الوصول لها؟

  - هل يعيق عدم توفر هذه المواد/المصادر تعلم الطفل ؟

إذا كانت الإجابة "نعم":

  - ما هي المواد/المصادر التي تقدمها المدرسة؟

  - هل هي كافية ليقوم المعلم بدوره بشكل صحيح؟

  - ماذا ينقصهم أيضاً؟

- هل تعلم ما هي الأجهزة المساعدة التي يحتاجها الطلاب ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

  - إلى أي مدى تساعد هذه الأجهزة؟

  - هل تعلم ما إذا كانت المدرسة تقدم هذه الأجهزة للأطفال في الغرف الصفية؟

ملاحظة لمنظم/ميسر الجلسة: الأجهزة التكنولوجية المساعدة: هو " أي جهاز أو قطعة من المستلزمات/الأدوات أو نظام إنتاج يستخدم لزيادة أو الحفاظ على أو تحسين القدرات الوظيفية للطفل من ذوي الاحتياجات الخاصة."

- إلى أي مدى يتم توفير الموارد والتقنيات المساعدة لطفلك بما يتماشى مع إعاقته / إحتياجاته؟

- هل يتم استخدام غرف الموارد بفعالية وكفاءة بما يتماشى مع التدريب المقدم؟

- هل رأيتهم؟

- بناءً على معرفتك، هل يستجيب برنامج التعليم الدامج لاحتياجات طفلك ؟ إذا كانت الإجابة بنعم ، فكيف يتم ذلك؟

هل تم إرشادك وتوجيهك حول آليات الإحالية الحالية الطلاب ذوي الإحتياجات الخاصة ؟

جلسات إعادة التأهيل/ نظم الإحالة

الهدف:  تقييم مدى معرفة أولياء الأمور ومقدمي الرعاية بجلسات إعادة التأهيل و نظم الإحالة.

- بناءً على معرفتك، هل تقدم المدرسة  أي جلسات إعادة تأهيل للطلاب من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

  - أين يتم إعطاء هذه الجلسات؟ (الاستفهام حول: في الموقع (المدرسة) مقابل خارج الموقع (خارج المدرسة)، غرفة مخصصة، أجهرة مساعدة......الخ)

- هل لديك علم بنظام إحالة للطلاب ذوي الاحتياجات الخاصة في المدرسة؟

- هل النظام الحالي فعال في تحديد وضمان الوصول إلى الأطفال ذوي الاحتياجات الخاصة الموجودين فعلياً في المدارس؟

- هل عانى نظام الإحالة من تغييرات في الفترة ما بين 2014 و 2019؟ يرجى شرح الاختلافات التي لحقت بالنظام وكيف تم تنفيذها.

- هل تشارك في عملية إحالة الأطفال إلى برنامج اليونيسف  للتعليم الدامج؟

- هل اشتكى طفلك بسبب:

- عدم توافر الموارد او الأوات التي قد تساعده في التعلم

- تحيز العلاج الى اطفال او احتياجات معينة

- نقص او عدم وجود المساعدة التي يحتاجها

- صعوبة الوصول للمدرسة او صعوبة غستخدام المرافق المدرسية

زيادة الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الجهود المبذولة (إن وجدت) في نقل التصور السائد عند الطلاب وأولياء الامور تجاه الأطفال من ذوي الاحتياجات الخاصة وأهمية وجود نظام التعليم الدامج.

- هل قامت المدرسة ببذل أي جهود لزيادة الوعي تجاه ذوي الاحتياجات الخاصة وأهمية التعليم الدامج؟

إذا كانت الإجابة "لا":

- هل تتمنى لو قاموا بذلك؟  لماذا؟

- هل من الضروري أن يقوموا بذلك؟ لماذا؟

إذا كانت الإجابة "نعم":

- كيف كانت/بدت الحملة التوعوية التي قامت بها؟

(الاستفهام حول: المحاضرات ، الاجتماعات ، الكتيبات/ أوراق المعلومات...إلخ)

- كم عدد المحاضرات/الاجتماعات التي تم عقدها حول هذا الموضوع؟

- ما هو محتوى الحملة؟

- هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

- هل كانت جهودهم موجهة إلى طلاب أخرين أو لأولياء الأمور ومقدمي الرعاية مثلكم؟

- إلى أي مدى تغيرت آرائكم حول الأطفال من ذوي الاحتياجات الخاصه منذ 2014؟

تكلفة الطالب وإختيار المدارس

- هل تعرف التكلفة لكل طالب ذوي إعاقة في برنامج التعليم الشامل؟

- اذا نعم

  - كيف تقارن التكلفة بالطلاب ذوي الإعاقة في البرامج الأخرى؟

  - كيف تقارن التكلفة مع الطلاب الآخرين الذين ليس لديهم إعاقة في نفس المدرسة؟

- ما هي العوامل التي تأخذونها في عين الاعتبار عند حسابة التكلفة؟

  - النفقات التشغيلية

  - شدة العجز أو التجريد

  - التنظيم اللوجستي

  - المواد والموارد اللازمة

  - جلسات إعادة التأهيل

  - تكلفة تغييرات البنية التحتية التي تم إجراؤها على الحرم المدرسي والفصول الدراسية

- كيف تحسب تكلفة كل فئة من الفئات المذكورة؟

  - ما هي العوامل الأخرى التي تأخذها في الاعتبار عند تقييم التكلفة لكل طالب؟

- في رأيك ، ما الذي يحدد "الفئات السكانية الضعيفة"؟ (التحقيق في: وضع اللاجئ ، الخلفية الاقتصادية ، الجنسية ... إلخ)

- ما هي المعايير التي تدخل في الاعتبار المدارس المختارة للانضمام إلى برنامج التعليم الشامل؟

  - نسبة السكان المعرضين للخطر

  - موقعك

  - عمر المبنى / ق

  - عدد الطلاب

  - عدد الطلاب ذوي الإعاقة في المدرسة / في المنطقة

  - / أو عدم وجود مركز مكاني قريب وجود

- حاليًا ، ما المعسكرات التي يوجد بها برنامج التعليم الشامل؟

- لماذا اخترت هذا المعسكر بالذات؟ (تحقق من الفئات الأكثر ضعفًا ، والوصول ، وحجم السكان ... إلخ)

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد اختتمنا الآن مناقشتنا لهذا اليوم.

شكرًا لحضروركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### المعلمين والمشرفين

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة،لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

- لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

  - هل أنت معلم أو  مشرف

  - هل أنت معلم مساعد أو معلم إحتياجات خاصة أو معلم صف أو غير ذلك؟

  - منذ متى وأنت تعمل في التدريس؟

  - ما هي المواد التي تقوم بتدريسها؟

  - ماهي الصفوف (المراحل الدراسية) التي تقوم بتدريسها؟

  - هل تستمتع بالتدريس؟ لماذا؟

المقدمة

الهدف: فهم المشاركين ومسؤولياتهم ومؤهلاتهم للتعامل مع الأطفال من ذوي الاحتياجات الخاصة

- ما هي القضايا التي تواجهها في التدريس هذه الأيام؟

هل أنت قادر على التغلب/تجاوز هذه الصعوبات؟

إذا كانت الإجابة "لا"، لما لا؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

- هل أنت مدرب على إدماج الأطفال من ذوي الاحتياجات الخاصة في الغرف الصفية؟

إذا كانت الإجابة "لا"، " الاستفهامحول: نقص المهارة/ التدريب اللازم للتعامل مع الأطفال من ذوي الاحتياجات الخاصة، سهولة الوصول في المدرسة، التصور السائد تجاه الأطفال من ذوي الاحتياجات الخاصة،......الخ)

إذا كانت الإجابة "نعم"، هل أنت مدرب على القيام  بذلكعلى شكل أفراد أو ضمن مجموعات في غرفة المصادر؟

هل أنت مدرب على تعليم أطفال ذو إحتياجات خاصة؟

- ما هي الإعاقات أو العاهات التي تقوم بالتعامل معها حالياً أو قمت بالتعامل معها مسبقاً؟

(الاستفهام حول: ضعف البصر، ضعف النطق والسمع، الإعاقة الجسدية، الإعاقة الذهنية، المرض العقلي، اضطراب طيف

التوحد...إلخ)

- هل دمج وإشراك الأطفال من ذوي الاحتياجات الخاصة يختلف عنه للأطفال الأصحاء؟

إذا كانت الإجابة "لا" ، فلما لا؟

إذا كانت الإجابة "نعم" ما هو وجه الاختلاف

- هل تعمل مع الأطفال ذوي الإعاقة 6-9, 10-14,  15- 18  سنة؟

- هل تتلقى أي دعم أو مساعدة أثناء تعليم الأطفال ذوي الإعاقة؟

إذا كانت الإجابة بنعم ، فمن الذي يقدم هذا الدعم؟

- ما نوع الإشراف ، إن وجد ، الذي تتلقاه لمساعدتك في تعليم الأطفال ذوي الإعاقة؟

إمكانية الوصول إلى التعليم

الهدف: فهم التسهيلات التي قامت بها المدرسة بهدف تسيير الخدمات التربوية/التعليمية للأطفال من ذوي الاحتياجات الخاصة، بما في ذلك التعديلات على البنية التحتية لمبى أو مباني المدرسة إضافة إلى توفير المواد والمصادر/الموارد الضرورية لتعليمهم.

- بشكل عام، ماهي أكبر عوائق وتحديات تعليم ذوي الاحتياجات الخاصة ؟ لماذا؟

(الاستفسار حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم.

- ماذا يتطلب الأمر للتغلب على هذه العقبات؟

- هل نظام التعليم في الأردن يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف؟

إذا كانت الإجابة "لا"، فما الذي ينبغي أن يحدث للنظام التعليمي لاستيعاب ومراعاة الأطفال من ذوي الاحتياجات الخاصة؟

- هل هناك جهوذ مبذولة من قبل المدرسة لتلبية احتياجات الطلاب من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

  - منذ متى قامت المدرسة بتحسينات البنية التحتية؟

  - بناءً على معرفتك، لماذا قامت المدرسة بهذه التحسينات؟

  - من هي الجهة، (إن وجد)، الممولة لهذه التحسينات؟

(الاستجوب حول: التحسينات التي تم ذكرها)

- هل قدمت المدرسة أية مواد أو موارد/مصادر لتمكينك من تعليم الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "لا":

  - ما هي المواد/المصادر التي تحتاجها؟

  - هل عدم توفر هذه المواد/المصادر يعيق قيامك بعملك بشكل صحيح ؟ كيف ذلك؟

إذا كانت الإجابة "نعم":

  - ما هي المواد/المصادر التي تقدمها المدرسة؟

  - هل هي كافية لقيامك بعملك بشكل صحيح؟

  - ماذا ينقصهم أيضاً؟

- هل تعلم ما هي الأجهزة التقنية المساعدة للأطفال ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

  - هل قمت باستخدام أي منها؟

  - هل تلقيت تدريبات مختصة باستخدام هذه الأجهزة؟ إذا كانت الإجابة، نعم، أي منها؟

  - إلى أي مدى تساعد هذه الأجهزة؟

ملاحظة لمنظم/منسق الجلسة: الأجهزة التكنولوجية المساعدة: هي " أي جهاز أو قطعة من المستلزمات/الأدوات أو نظام إنتاج يستخدم لزيادة أو الحفاظ على أو تحسين القدرات الوظيفية للطفل من ذوي الاحتياجات الخاصة."

- كم عدد الأطفال من ذوي الاحتياجات الخاصة ممن تم تحديد احتياجهم للأجهزة التقنية المساعدة (بناءً على البرنامج التربوي الفردي IEP ) الذين بإمكانهم الوصول إلى واستخدام المنتجات والتقنيات المساعدة؟

- إلى أي مدى يتم توفير الموارد والتقنيات المساعدة والتدريب المقدم بما يتماشى مع الإعاقات المستهدفة؟

- بماذا قامت المدرسة أيضاً لتسهيل عملية تعلم الأطفال من ذوي الاحتياجات الخاصة؟

تدريب المعلمين والتوجيهات

- هل تم تقديم تدريب على مستوى المدرسة للمعلمين؟

- ما هي المعايير الرئيسية المستخدمة في الأهلية لبرنامج تدريب المعلمين على الأطفال ذوي الإعاقة؟

  - هل يتعين على المعلمين الحصول على درجة علمية أو خبرة واسعة في العمل مع الأطفال؟

  - هل كان التدريب / التدريبات كافية؟

- هل تلقيت أي تدريب لتعليم الأطفال ذوي الإعاقة؟

اذا نعم

ما هي المكونات الرئيسية لنموذج التدريب؟

كيف تغير نموذج تدريب المعلمين بين عامي 2014 و 2019؟

- هل تم توجيه طلاب المدرسة نحو برنامج الدمج؟

- هل تم توجيه المجتمع المدرسي الأوسع بما في ذلك الآباء) نحو الإدماج؟

- إلى أي مدى يعتبر نموذج تدريب المعلمين فعالاً وكافياً في تمكين المعلمين من دعم استبقاء وتعلم الأطفال ذوي الإعاقة؟

- هل تعتقد أن التدريب الذي تلقيته قد أثر على مهاراتك وقدرتك على تضمين الأطفال ذوي الإعاقة والاحتفاظ بهم؟

- إلى أي مدى يعد نموذج تدريب المعلمين فعال وكافٍ لتمكين المعلمين من الحفاظ على الطلاب من ذوي الاحتياجات الخاصة وتعليمهم ؟

- هل كانت هناك سياسات في المدرسة تدعم التعليم الشامل قبل ظهور هذا البرنامج؟

الوعي تجاه الجهة المانحة و برنامج التعليم الشامل

- متى التحقت المدرسة ببرنامج التعليم الشامل؟ (الاستفهام حول: شهر، سنة)

- كم من المدة قضت؟ وهل مازال مستمراً؟

(الاستفهام حول: إذا استمرت المدرسة في تشغيل البرنامج أم أن المعلمين يرون أنه لاداعي له أو مبالغ به)

- مانوع التدخلات التي تم تطبيقها؟

(الاستقهام حول: التدخلات الملموسة والتدخلات غير الملموسة)

- هل الأطفال من ذوي الاحتياجات الخاصة مخولون ولديهم الإمكانية للوصول إلى البرنامج التربوي الفردي المطور بالكامل والمحدث (IEP)؟ إذا كانت الإجابة "نعم"، كم عدد الأطفال؟

- ما رأيك في مفهوم "التعليم الشامل" لجميع الطلاب ، بما في ذلك الأطفال ذوي الإعاقة؟

  - ما هي نقاط القوة والضعف في برنامج التعليم الجامع برأيك؟

  - - هل هو مفهوم واقعي؟ لماذا ا؟

(التحقيق في: الاحتمال المتوقع للنجاح ، ومقبولية النظام ، إلخ.)

  - هل هي خطوة ضرورية في المدارس العامة؟ لماذا ا؟

  - - هل يجب أن يكون "التعليم الشامل" أمرًا يفرضه القانون على المدارس؟

إذا كانت الإجابة "لا" ، فلماذا؟

إذا كانت الإجابة بنعم ، فهل ينطبق هذا على المدارس الحكومية أم الخاصة؟ لماذا ا؟

- كم عدد الأطفال الذين أحرزوا تقدماً ناجحاً في البرنامج ، كما ورد في البرنامج التربوي الفردي  الخاص بهم ؟

- في المتوسط، كم ساعة يقضي الطفل في البرنامج التربوي الفردي بغرفة المصادر، في اليوم الواحد؟

- هل الأطفال من ذوي الاحتياجات الخاصة أكثر أو أقل احتمالية بالمشاركة في أنشطة التعلم المدرسية مقابل زملائهم (الأصحاء) ؟

- من وجهة نظرك، هل برنامج التعليم الشامل يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة من حيث تمكينهم من المشاركة الكاملة في عملية التعلم ( كما هو الحال مع الأطفال الذين الأصحاء )

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

- برأيك ، إلى أي مدى تتماشى/تتطابق ممارساتك في الغرفة الصفية مع التدريب الذي تلقيته؟

  - هل تتلقى أي مساعدة لتمكينك من تطبيق الممارسات المتعلقة بعملية الإدماج ؟

- هل غرفة المصادر تستخدم بفعالية وكفاءة بما يتماشى مع  التدريب المقدم ؟

التآزر مع زارة التربية والتعليم

- ماذا تعرف عن استراتيجية التعليم الشامل الوطنية؟

  - إلى أي مدى يتماشى ويتوافق  برنامج التعليم الشامل مع الاستراتيجية الوطنية؟

  - إذا لم يتماش/يتوافق  برنامج التعليم الشامل مع الاستراتيجية الوطنية ، فما هي الفجوات بينهم وكيف يمكن معالجتها؟

- إلى أي مدى يتماشى/يتوافق برنامج التعليم الشامل مع الممارسات العالمية (لجنة حقوق الطفل، اتفاقية حقوق الأشخاص ذوي الإعاقة...)؟

- من وجهة نظرك، إلى أي مدى قد يكون برنامج التعليم الشامل فعالاً في تحقيق نتائج للأطفال من ذوي الاحتياجات الخاصة؟

- إلى أي مدى يمكن القول بأن  أهداف البرنامج  قد تحققت بفعالية من حيث

  - دعم التحاق الأطفال والاحتفاظ بهم في المدارس؟

  - هل تعتقد أن لديك القدرة على التأثير على التحاق الأطفال من ذوي الاحتياجات الخاصة والاحتفاظ بهم في المدارس؟ إذا كانت الإجابة "نعم"، إلى أي مدى؟

  - دعم تعلم الأطفال ومشاركتهم / التزامهم في المقررات الدراسية

  - تغيير سلوك الأطفال ومقدمي الرعاية والممارسات في المدارس.

- هل هناك أية عقبات تحد من تحقيق الأهداف المعنية من برنامج التعليم الشامل؟

إذا كانت الإجابة نعم، فماذا؟

- هل تعرف ما إذا كان سيتم تسليم هذا البرنامج في المستقبل إلى وزارة التربية والتعليم أو متى؟

- هل تم تسليم إدارة البرنامج إلى وزارة التربية والتعليم؟

إذا كانت الإجابة "نعم"

  - متى تم ذلك؟

  - كيف بدت العملية؟

  - هل كانت عملية النقل سهلة وميسرة؟

  - هل تأثر البرمانج منذ ذلك الحين؟ إذا كانت الإجاببة "نعم"، كيف ذلك؟

- هل لديك أي مخاوف بشأن هذا البرنامج الذي تشرف عليه وزارة التربية والتعليم؟

جلسات إعادة التأهيل والأجهزة المساعدة

الهدف:  تقييم مدى معرفة أولياء الأمور ومقدمي الرعاية بجلسات إعادة التأهيل والأجهزة المساعدة.

- بناءً على معرفتك، هل تقدم المدرسة  أي جلسات إعادة تأهيل للطلاب من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

  - أين يتم إعطاء هذه الجلسات؟ (الاستفسار حول: في الموقع (المدرسة) مقابل خارج الموقع (خارج المدرسة)، غرفة مخصصة، أجهرة مساعدة......الخ)

- هل لديك نظام إحالة للطلاب ذوي الاحتياجات الخاصة في المدرسة؟

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم":

- ما نوع نظام الإحالة المتواجد حالياً في المدرسة؟

- متى تم إنشاؤه ؟

- هل نظام الإحالة فعال في تحديد وضمان الوصول إلى الأطفال من ذوي الاحتياجات الخاصة المتواجدين في المدرسة؟

- لماذا تتم إحالة الطلاب؟

- أين تتم إحالة الطلاب؟

- هل عانى أو واجه نظام الإحالة من أي تغييرات بين عامي 2014 و 2019 ؟

إذا كانت الإجابة "نعم" ، يرجى وصف وشرح ما هي الاختلافات ولماذا تم تطبيقها.

زيادة الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الجهود المبذولة (إن وجدت) في نقل التصور السائد عند الطلاب وأولياء الامور تجاه الأطفال من ذوي الاحتياجات الخاصة وأهمية وجود نظام التعليم الشامل.

- هل قامت المدرسة ببذل أي جهود لزيادة الوعي تجاه ذوي الاحتياجات الخاصة وأهمية التعليم الشامل؟

إذا كانت الإجابة "لا":

- هل تتمنى لو قاموا بذلك؟  لماذا؟

- هل من الضروري أن يقوموا بذلك؟ لماذا؟

إذا كانت الإجابة "نعم":

- كيف كانت/بدت الحملة التوعوية التي قامت بها؟

(الاستفسار حول: المحاضرات ، الاجتماعات ، الكتيبات/ أوراق المعلومات...إلخ)

- كم عدد المحاضرات/الاجتماعات التي تم عقدها حول هذا الموضوع؟

- ما هو محتوى الحملة؟

- هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

- هل كانت جهودهم موجهة إلى طلاب أخرين أو لأولياء الأمور ومقدمي الرعاية مثلكم؟

- إلى أي مدى تغيرت آرائكم حول الأطفال من ذوي الاحتياجات الخاصه منذ 2014؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد اختتمنا الآن مناقشتنا لهذا اليوم.

شكرًا لحضروركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### الأطفال الملتحقين بالمدرسة من ذوي الإعاقات (الأعمار من 6 إلى 9)

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة، لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

- كم عمرك؟

- بأي مرحلة صفية؟

- هل تحب المدرسة؟ لماذا؟

- هل أنت على دراية بما ترغب بفعله في المستقبل؟ (الإستفهام حول: المسار الوظيفي.....الخ)

المقدمة

الهدف: فهم الطلاب ورغباتهم واحتياجاتهم مع التركيز على تجربتهم التعليمية.

- هل يعيق العجز/الإعاقة تعليمك؟ كيف؟

- هل تواجه أي صعوبات في التعلم؟

من وجهة نظرك، ما هي المشاكل التي يواجهها الطلاب مثلك في التعليم؟

- ما هي الحصص/ المواد المفضلة لديك؟ لماذا ا؟

- ما هي الحصص/المواد الأقل تفضيلاً لديك؟ لماذا ا؟

- هل أنت قادر على بناء صداقات في المدرسة؟

إذا كانت الإجابة "لا"، ماهو سبب ذلك باعتقادك؟

إذا كانت الإجابة "نعم":

- كيف تشعر أنهم ينظرون إلى الإعاقة/العجز الذي لديك؟

- هل لدى أحدهم أي إعاقة/عجز أيضاً ؟

- هل تعتقد أن مدرستك تحسن التعامل معك ومع الأشخاص من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "لا"، لما لا؟ (الإستفهام حول سهولة الوصول، عدم الخبرة، نقص المصادر/الموارد والمواد المناسبة... الخ)

إذا كانت الإجابة "نعم"، فلماذا تعتقد ذلك؟

- هل تحب معلميك ؟

- هل تعتقد أن معلميك يحسنون تعليمك وتعليم الأشخاص من ذوي الاحتياجات الخاصة بشكل جيد؟

- إذا كانت الإجابة "لا"، لما لا؟ (الاستفهام حول: نقص التدريب، عدم الخبرة، نقص المصادر/الموارد والمواد المناسبة... الخ)

- إذا كانت الإجابة "نعم"، فلماذا تعتقد ذلك؟

- كيف يتعامل المعلمون في الصف معك ؟

- هل يعاملونك كما يتعاملون مع أي طالب آخر في الصف؟

إذا كانت الإجابة "نعم" ، وضح كيف يقومون بمعاملتك بنفس الطريقة؟

إذا كان الإجابة "لا" ، كيف تختلف المعاملة ؟

- هل يمنحونك أي رعاية/اهتمام خاص؟

- هل يقدمون لك المساعدة؟ إذا كانت الإجابة "نعم" , ما نوع هذه المساعدة؟

الوعي تجاه  برنامج التعليم الدامج

الهدف: تقييم معرفة الطلاب ببرنامج التعليم الدامج وفهم تصوراتهم عنه

- هل تعرف ما هو برنامج التعليم الدامج؟

إذا كانت الإجابة "نعم" ما هو؟

- من وجهة نظرك، ما هي الجوانب الإيجابية والجوانب السلبية للبرنامج ؟

سهولة الوصول الفعلية/البدنية

الهدف: فهم التحسينات (إن وجدت)، التي قامت بها المدرسة على مبنى/مباني المدرسة والحرم المدرسي لجعلها أكثر سهولة للطلاب ذوي الاحتياجات الخاصة.

- هل يمكنك دخول مبنى المدرسة بكل سهولة ؟

- هل يمكنك التنقل والحركة في المدرسة بكل سهولة ؟ لماذا ؟

(الإستفهام حول: الأرصفة المعدة لذوي الاحتياجات الخاصة، إتاحة الكراسي المتحركة، إتاحة دورات مياه لذوي الاحتياجات الخاصة، أبواب وقاعات واسعة، إشارات برايل، مترجمي لغة الإشارة...إلخ.)

- هل كانت المدرسة دائماً على هذا الحال؟

أو أنها لم تكن سهلة الوصول في وقت معين بالسابق ؟ يرجى التوضيح ؟

- ماهي صفات/ميزات الأخرى التي تتمنى لو كانت مدرستك تمتلكها؟

- دعونا نتصور أو نتخيل قليلاً

ماذا لو كان لدى كل منكم عصا سحرية ، وكان عليك استخدام هذه العصا لجعل مدرستك  بأحسن صورة يمكن أن تكون عليها، هل يمكنكم جميعا تخيلها  في عقلكم؟ يرجى وصف ذلك.

- كيف تبدو ؟

- كيف يبدو صفك؟

- كيف تبدو مقاعدكم الدراسية ؟

- كيف تبدو المرافق ؟

- كيف يتعامل المعلمون معك ؟

- كيف يعاملك الطلاب الآخرون؟

- أين تقع ؟

- كيف كانت ستكون تجربتك التعليمية لو كانت لديك هذه الميزات؟

(الإستفهام حول: الفوائد العاطفية والوظيفية.. الخ)

جلسات إعادة التأهيل والأجهزة المساعدة:

الهدف:

- فهم ماهي المواد والمصادر/الموارد التي استثمرت بها المدرسة/تُوفرها المدرسة لطلابها (إن وجد) لمساعدة ذوي الاحتياجات الخاصة مع تسليط الضوء على الاحتياجات الأخرى.

- تقييم برامج إعادة التأهيل المدرسية (إن وجدت) ، وفهم سبل تحسينها.

- هل لديك غرفة مصادر/ موارد  خاصة في مدرستك؟

اذا كانت الاجابة "نعم"؟

- ما هي الموارد والادوات التي تحتاجها للتعلم ؟

- هل هم مفيدون؟

- هل يساعدونك في الفهم أو الدراسة؟

- هل يحتاج زملاؤك في الصف إلى هذه الموارد أيضًا ؟

- ما هي المصادر/الموارد والادوات التي تتمنى أن تمتلكها مدرستك لمساعدتك في التعلم؟

(الإستفهام حول ـ: مسجلات الصوت، الموقتات، أدلة القراءة، داعمات الكتابة، الآلات الحاسبة، وسائل التنظيم...إلخ.)

- هل تمتلك مدرستك أي مواد مساعدة (أجهزة) تساعدك في التعلم؟

(الإستفهام حول ـ: أوراق العمل الإلكترونية، برامج التهجئة الصوتية، الآلات الحاسبة الناطقة، مواد متغيرة، مسجلات السرعة...إلخ.)

- هل تحصل على مساعدة خاصة من معلميك؟ إذا كانت الإجابة "نعم" ، فهل تعتقد ان الإهتمام او التركيز الفردي يفيدك في الدراسة؟ لماذا؟

جلسات إعادة التأهيل:

- هل لديك أي جلسات خاصة مع مدرسين أو معالجين،لا يحضرها أصدقائك الآخرون؟

إذا كانت الإجابة "نعم":

- هل يمكن أن تخبرني ماذا تفعل هناك؟

- لماذا تحتاج هذه الجلسات؟

- كم مرة تلقيتها؟ (أسبوعياً ، شهرياً... إلخ)

- هل تحب هذه الجلسات؟لماذا ا؟

- هل تشعر أن معلميك يعلمون كيفية تعليمك مثلما يعلمون الطلاب الآخرين؟ لماذا؟

- ما الذي يجعلهم معلمون جيدون ؟

- إذا كنت تعتقد أنهم ليسوا معلمون جيدون، فلما ذلك؟

زيادة الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الجهود المبذولة (إن وجدت) في نقل التصور السائد عند الطلاب وأولياء الامور تجاه الأطفال من ذوي الاحتياجات الخاصة وأهمية وجود نظام التعليم الدامج

- هل تحب الذهاب الى المدرسة مع أطفال آخرين ليسوا من ذوي الاحتياجات الخاصة (أصحاء) ؟

(الإستفهام حول: الشعور بالاختلاف ، التعرض للتنمر ، الافتقار إلى إمكانية الوصول ... إلخ)

إذا كانت الإجابة "نعم" ، فلماذا؟ (الإستفهام حول: الاستقلالية ، الاختلاط بالأطفال الآخرين ، تكوين صداقات ، التسلية في المدرسة ... إلخ)

- هل تتمنى الذهاب إلى مدرسة للأطفال من ذوي الاحتياجات الخاصة فقط؟ لماذا؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### الأطفال الملتحقين بالمدرسة من ذوي الإعاقات (الأعمار من 10 إلى 14)( و 15 الى 18)

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة،لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

- كم عمرك؟

- بأي مرحلة صفية؟

- ماهي المدرسة التي تذهب إليها؟ (الاستفهام حول: الموقع، المخيم مقابل المجتمع المضيف)

- هل تحب المدرسة؟ لماذا؟

- هل أنت على دراية بما ترغب بفعله في المستقبل؟ (الاستفهام حول: الجامعة، العمل،  العيش المستقل)

المقدمة

الهدف: فهم الطلاب ورغباتهم واحتياجاتهم مع التركيز على تجربتهم التعليمية.

- هل يعيق العجز/ الإعاقة تعليمك؟ كيف؟

- هل تواجه أي صعوبات في التعلم؟

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم"، كيف؟

- هل قمت بالتغلب على هذه الصعوبات/التحديات؟  إذا كانت الإجابة "نعم"، كيف؟

- ما هي حصتك المفضل؟ لماذا؟

- ما هو الدرس الصعب بالنسبة لك؟ لماذا؟

- هل أنت قادر على بناء صداقات في المدرسة؟

إذا كانت الإجابة "لا"، ماهو سبب ذلك باعتقادك؟

إذا كانت الإجابة "نعم":

- كيف تشعر أنهم ينظرون إلى الإعاقة/ العجز الذي لديك؟

- هل لدى أحدهم أي إعاقة/عجز أيضاً ؟

- هل تعتقد أن مدرستك تحسن التعامل معك ومع الأشخاص الذين معك ومع الأشخاص الذين لديهم نفس العجز/الإعاقة التي لديك؟

إذا كانت الإجابة "لا"، لماذا لا؟ (الاستفهام حول: الملائمة وسهولة الوصول، عدم الخبرة، نقص الموارد والمواد المناسبة... الخ)

- هل تشعر أن معلميك قادرين على تعليمك/أو تعليم الأشخاص الذين يعانون من نفس نوع العجز/الإعاقة التي لديك؟

إذا كانت الإجابة "لا"، فلماذا؟ (الاستفهام حول: نقص التدريب، عدم الخبرة، نقص الموارد والمواد المناسبة... الخ)

إذا كانت الإجابة "نعم"، فلماذا تعتقد ذلك؟

- هل لديك معلم مساند؟ إذا كانت الإجابة "نعم" ، إلى أي مدى تستفيد من الدعم المقدم من المعلم المساند؟

- إلى أي مدى يساهم الدعم الفردي المقدم في غرفة المصادر في تقدمك في برنامج التعليم الدامج؟

إمكانية الوصول إلى التعليم

الهدف: فهم كيف تبدو تجربة التعلم من وجهة نظر الأطفال من ذوي الاحتياجات الخاصة، إضافةً إلى الصعوبات والعقبات التي تواجهها هذه الفئة.

- من وجهة نظرك، ماهي أكبر التحديات التي يواجهها الأطفال من ذوي الاحتياجات الخاصة فيما يتعلق بالتعليم في الاردن؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم.

- ماذا يتطلب الأمر بالنسبة للمدارس الحكومية للتغلب على هذه العقبات؟

- هل نظام التعليم في الأردن مناسب للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف؟

وإذا كانت الإجابة "لا"، فما الذي ينبغي أن يحدث للنظام التعليمي لاستيعاب ومراعاة الأطفال من ذوي الاحتياجات الخاصة؟

- هل مبنى المدرسة/الحرم المدرسي مناسب/سهل الوصول بالنسبة لك؟ يرجى الشرح

(الاستفهام حول: الأرصفة المعدة لذوي الاحتياجات الخاصة، إتاحة الكراسي المتحركة، دورات مياه لذوي الاحتياجات الخاصة، موقف لذوي الاحتياجات الخاصة، أبواب وقاعات واسعة، إشارات برايل، مترجمي لغة الإشارة...إلخ.)

- هل المدرسة ملائمة/ سهلة الوصول بالنسبة لك دائماً؟

- ماهي صفات/ميزات البنية التحتية الأخرى التي تتمنى لو كانت مدرستك تمتلكها؟

- كيف كانت ستكون تجرتك التعليمية لو كنت تملك هذه الميزات؟

(الاستفهام حول: الفوائد العاطفية والوظيفية... الخ).

جلسات إعادة التأهيل والأجهزة المساعدة:

الهدف:

- فهم ماهي المواد والمصادر/الموارد التي استثمرت بها المدرسة/تُوفرها المدرسة لطلابها (إن وجد) لمساعدة ذوي الاحتياجات الخاصة مع تسليط الضوء على الاحتياجات الأخرى.

- تقييم برامج إعادة التأهيل المدرسية (إن وجدت) ، وفهم سبل تحسينها.

- ما هو نوع الموارد والمواد التي تحتاجها في التعلم؟

- هل تمتلك مدرستك الموارد والمواد اللازمة لتلبية احتياجاتك واحتياجات شخص يعاني من نفس نوع العجز التي لديك؟

- ما هي الموارد والمواد التي تتمنى أن تمتلكها مدرستك لمساعدتك في التعلم؟

(الاستفهام حول ـ: مسجلات الصوت، الموقتات، أدلة القراءة، داعمات الكتابة، الآلات الحاسبة، وسائل التنظيم...إلخ.)

- هل تمتلك مدرستك أي أجهزة مساعدة تساعدك في التعلم؟

(الاستفهام حول ـ: أوراق العمل الإلكترونية، برامج التهجئة الصوتية، الآلات الحاسبة الناطقة، المتغير، مسجلات السرعة...إلخ.)

- كيف يمكن تحسين تجربتك التعليمية أيضاً؟

- هل التحقت بأي جلسات لإعادة التأهيل في المدرسة؟

إذا كانت الإجابة "لا"، هل تتمنى أن تقدم المدرسة جلسات إعادة التأهيل وجلسات علاج طبيعي؟

إذا كانت الإجابة "نعم":

- لماذا تمت التوصية بتلقيك جلسات إعادة التأهيل؟

- من هو صاحب القرار فيما يتعلق بحاجتك لتلقي جلسات إعادة التأهيل ؟ (الاستفهام حول: المعلمون، مدراء المدراس، طبيب متخصص، طبيب المدرسة، أولياء الأمور... الخ)

- ما نوع جلسات إعادة التأهيل التي تلقيتها؟ (الاستفهام حول: علاج النطق، العلاج الطبيعي، العلاج الوظيفي، مساعدة ذوي صعوبات التعلم في أي موضوع... الخ)

- هل كلفك ذلك أو تكلفت عائلتك أي شيء؟  إذا كانت الإجابة "نعم"، فما هو المبلغ؟

- أين تلقيت هذه الجلسات؟ (الاستفهام حول: الموقع، خارج الحرم المدرسي، في عيادة عامة/خاصة... إلخ)

- كم مرة تلقيتها؟ (أسبوعياً، شهرياً...إلخ)

- كم كانت مدة الجلسات؟

- على حد علمك، هل معلموك معتمدون ومؤهلون للعمل مع الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "لا"، فلماذا تعتقد أنهم غير مؤهلين؟

إذا كانت الإجابة "نعم":

- ما نوع الشهادة/المؤهل الذي لديهم ؟

- ما هي الإعاقات التي تدربوا على التعامل معها؟ (الاستفهام حول: ضعف البصر، ضعف النطق والسمع، الإعاقة الجسدية، الإعاقة الذهنية، المرض العقلي، اضطراب طيف التوحد...إلخ)

- هل هناك نظام إحالة للطلاب ذوي الاحتياجات الخاصة في المدرسة؟

إذا كانت الإجابة نعم:

- لماذا تتم إحالة الطلاب؟

- أين تتم إحالة الطلاب؟

الوعي تجاه الجهة المانحة و برنامج التعليم الدامج

- هل تعلم ما هو البرنامج التربوي الفردي؟

إذا كانت الإجابة "لا": انتقل إلى السؤال التالي

إذا كانت الإجابة "نعم":

- من وجهة نظرك، ما هي إيجابيات وسلبيات البرنامج؟

- على حد علمك، هل تمتلك المدرسة أي نظام مكتوب/ بروتوكول لنظام خاص؟

- متى التحقت المدرسة ببرنامج التعليم الدامج؟ (الاستفهام حول: شهر، سنة)

- كم من المدة قضت؟ وهل مازال مستمراً؟

(الاستفهام حول: إذا استمرت المدرسة في تشغيل البرنامج أم أن المعلمين يرون أنه لاداعي له أو مبالغ به)

- مانوع التدخلات التي تم تطبيقها؟

(الاستفهام حول: التدخلات الملموسة والتدخلات غير الملموسة)

- هل تأثر البرنامج بوباء الكورونا؟ إذا كانت الإجابة "نعم"، فكيف ذلك؟

- هل أنت مخول للوصول إلى البرنامج التربوي الفردي المطور بالكامل والمحدث (IEP)؟ إذا كانت الإجابة "نعم"، فكيف يبدو؟

- في المتوسط، كم ساعة تقضي في البرنامج التربوي الفردي أو في غرفة المصادر، في اليوم الواحد؟

- في حال احتجت إلى المساعدة في الصف، لمن تلجأ؟ ( الاستفهام حول: معلم الصف، الأستاذ/المعلم المساعد، غيرهم...... الخ)

- من وجهة نظرك، هل برنامج التعليم الدامج يلبي احتياجات الأطفال من ذوي الاحتياجات الخاصة من حيث تمكينهم من المشاركة الكاملة في عملية التعلم ( كما هو الحال مع الأطفال الأصحاء )

إذا كانت الإجابة "لا"، لماذا؟

إذا كانت الإجابة "نعم"، كيف ذلك؟

زيادة الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الجهود المبذولة (إن وجدت) في نقل التصور السائد عند الطلاب وأولياء الامور تجاه الأطفال من ذوي الاحتياجات الخاصة وأهمية وجود نظام التعليم الدامج

- ما هو رأيك في برنامج" التعليم الدامج" لكافة الطلاب بما فيهم الأطفال من ذوي الاحتياجات الخاصة؟

هل هو واقعي؟  لماذا؟

(الاستفهام حول ـ: الاحتمالية المتوقعة للنجاح، تقبل الآخرين...الخ).

- هل هي خطوة ضرورية يجب اتخاذها في المدارس الحكومية؟ لماذا؟

- هل قامت المدرسة ببذل أي جهود لزيادة الوعي تجاه ذوي الاحتياجات الخاصة وأهمية التعليم الدامج؟

إذا كانت الإجابة "لا":

- هل تتمنى لو قاموا بذلك؟  لماذا؟

- هل من الضروري أن يقوموا بذلك؟ لماذا؟

إذا كانت الإجابة "نعم":

- كيف كانت /بدت الحملة التوعوية التي قامت بها؟

(الاستفهام حول: المحاضرات ، الاجتماعات ، الكتيبات/ أوراق المعلومات...إلخ)

- ما هو محتوى الحملة؟

- هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

- هل كانت جهودهم موجهة إلى الطلاب في المدرسة أم إلى أولياء أمور الطلبة ؟

إذا كان كلاهما، فكيف اختلفت جهود الحملة؟

- هل أنت على علم ودراية بأية مشاريع أو برامج تنفذها منظمة الأمم المتحدة للطفولة (اليونيسيف) أو فيلق الرحمة (ميرسي كوربس) فيما يتعلق بالتعليم الدامج وتعزيز كفاءة المدارس الحكومية لجعلها مناسبة أكثر للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، فما الذي تعرفه عنها؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### الأطفال/الطلاب الملتحقين بالمدرسة (الأعمار من 6 إلى 9)

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة،لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم

- كم عمرك؟

- بأي مرحلة صفية؟

- هل تحب المدرسة؟ لماذا؟

- هل أنت على دراية بما ترغب بفعله في المستقبل؟ (الاستفهام حول: المسار الوظيفي.....الخ)

المقدمة

الهدف: فهم الطلاب ورغباتهم واحتياجاتهم مع التركيز على تجربتهم التعليمية.

- ما هي الحصص المفضلة لديك؟ لماذا؟

- ما هي الحصص الأقل تفضيلاً لديك؟ لماذا؟

- هل هناك أي طالب من ذوي الاحتياجات الخاصة في صفك الدراسي ؟

(الاستفهام حول: ضعف البصر، ضعف النطق والسمع، الإعاقة العقلية، الإعاقة الجسدية... إلخ).

- هل وجود زميل في الصف من ذوي الاحتياجات الخاصة يؤثر عليك؟ كيف؟

(الاستفهام حول: التشتيت، إهتمام المعلم الموجه للأطفال من ذوي الاحتياجات الخاصة... إلخ)

- هل تحب/لا تحب وجود زملاء من ذوي الاحتياجات الخاصة معك في الصف؟

- هل أنت صديق لهؤلاء الزملاء؟

(الاستفهام حول : هل تلعب معهم في المدرسة، هل تراهم خارج المدرسة...إلخ).

- ما هو شعورك حيال وجودهم معك في الصف؟

- هل تحب معلميك ؟

- هل يحتاج أحد زملائك أي رعاية /اهتمام خاص؟

إذا كانت الإجابة "نعم"، كيف تشعر تجاه ذلك؟

- لماذا تعتقد أن المعلم يمنحهم عناية خاصة؟

- هل يستغرق ذلك وقتاً طويلاً من الوقت المخصص لحصتك الدراسية

- هل تحصل على أي رعاية أو اهتمام خاص؟

سهولة الوصول الفعلية/البدنية

الهدف: فهم التحسينات التي قامت بها المدرسة (إن وجدت) على مبنى/مباني المدرسة والحرم المدرسي بهدف جعلها أكثر سهولة للطلاب ذوي الاحتياجات الخاصة.

- هل قامت مدرستك بعمل أي تعديلات على مبنى/مباني المدرسة؟

إذا كانت الإجابة "نعم"، ما نوع التعديلات التي قاموا بها؟

(الاستفهام حول: الأرصفة المعده لذوي الاحتياجات الخاصة، إتاحة الكراسي المتحركة، دورات مياه لذوي الاحتياجات الخاصة، مواقف لذوي الاحتياجات الخاصه، مداخل وقاعات واسعة، إشارات برايل، مترجمي لغة الإشارات...إلخ.)

- هل تعرف لماذا قامت مدرستك بهذه التحسينات؟

(الاستفهام حول: فهم الطلاب لسهولة وصول الأطفال من ذوي الاحتياجات الخاصة.....إلخ)

- ما نوع التحسينات التي تتمنى أن تقوم بها مدرستك؟

- دعونا نتصور أو نتخيل قليلاً

ماذا لو كان لدى كل منكم عصا سحرية ، وكان عليك استخدام هذه العصا لجعل مدرستك  بأحسن صورة يمكن أن تكون عليها، هل يمكنكم جميعا تخيلها  في عقلكم؟ يرجى وصف ذلك.

- كيف تبدو ؟

- كيف يبدو صفك؟

- كيف تبدو مقاعدكم الدراسية ؟

- كيف تبدو المرافق ؟

- كيف يبدو المعلمين؟

- أين تقع؟

- ما مدى اختلاف تجربتك الحالية عن التجربة التي تم وصفها للتو؟

- كيف كانت ستكون تجرتك التعليمية لو كنت تملك هذه الميزات؟

(الاستفهام حول: الفوائد العاطفية والوظيفية... الخ).

الوعي تجاه  برنامج التعليم الدامج

الهدف: تقييم معرفة الطلاب ببرنامج التعليم الدامج وفهم تصوراتهم عنه

- هل تعرف ما هو برنامج التعليم الدامج؟

إذا كانت الإجابة "نعم" ما هو؟

- من وجهة نظرك، ما هي الجوانب الإيجابية والجوانب السلبية للبرنامج ؟

المصادر/الموارد والمواد التعليمية

الهدف:

- فهم ماهي المواد والمصادر/الموارد التي استثمرت بها المدرسة/تُوفرها المدرسة لطلابها (إن وجد) لمساعدة ذوي الاحتياجات الخاصة مع تسليط الضوء على الاحتياجات الأخرى.

- تقييم برامج إعادة التأهيل المدرسية (إن وجدت) ، وفهم سبل تحسينها.

- ما نوع المصادر/الموارد والمواد التي تحتاجها في التعلم؟

- هل تمتلك مدرستك هذه المصادر/الموارد والمواد؟

- ما هي المصادر/الموارد والمواد التي تتمنى أن تمتلكها مدرستك لمساعدتك في التعلم؟

(الاستفهام حول ـ: مسجلات الصوت، الموقتات، أدلة القراءة، داعمات الكتابة، الآلات الحاسبة، وسائل التنظيم...إلخ.)

- ما هو شعوركم الآن تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا ا؟

لقد اختتمنا الآن مناقشتنا لهذا اليوم.

شكرًا لحضروركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم

### الأطفال الملتحقين بالمدرسة (الأعمار من 10 الى 14)( و 15 إلى 18)

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة، لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

- كم عمرك؟

- بأي مرحلة صفية؟

- هل تحب المدرسة؟ لماذا؟

- هل أنت على دراية بما ترغب بفعله في المستقبل؟ (الاستفهام  حول: الجامعة، العمل،  العيش المستقل)

المقدمة

الهدف: فهم الطلاب ورغباتهم واحتياجاتهم مع التركيز على تجربتهم التعليمية.

- ما هو شعورك تجاه المدرسة؟  لماذا؟

- هل تعتقد أن التعليم مهم؟  لماذا؟

- ما  هو رأيك في مدرستك؟

ما رأيك في:

  - مبنى المدرسة / الحرم المدرسي؟

  - المرافق ؟ (الاستفهام  حول  ـ: الملاعب ، الغرف الصفية ، الأرضيات، دورات المياه، مبرد المياه/كولر...إلخ)

  - الغرف الصفية ؟ (الاستفهام  حول: الحجم والمساحة، الحداثة، الدروج/المكاتب، الألواح الدراسية، نظام التهوية...إلخ)

  - المعلمون؟ (الاستفهام  حول  : الخبرات، القدرات، المهنية/الإحترافية...إلخ)

  - البيئة؟

- هل هناك أي طالب من ذوي الاحتياجات الخاصة في صفك الدراسي / مدرستك؟

(الاستفهام  حول: ضعف البصر، ضعف النطق والسمع، الإعاقة العقلية، الإعاقة الجسدية... إلخ).

- هل وجود زميل في الصف من ذوي الاحتياجات الخاصة يؤثر عليك؟ كيف؟

(الاستفهام  حول: التشتيت، إهتمام المعلم الموجه للأطفال من ذوي الاحتياجات الخاصة... إلخ).

- هل تحب/لا تحب وجود زملاء من ذوي الاحتياجات الخاصة معك في الصف؟

هل أنت صديق لهؤلاء الزملاء؟

(الاستفهام  حول : هل تلعب معهم في المدرسة، هل تراهم خارج المدرسة...إلخ).

- ما هو شعورك حيال وجودهم معك في الصف؟

- هل يعطي المعلمون في الصف الطلاب من ذوي الاحتياجات الخاصة أي رعاية /اهتمام خاص؟

إذا كانت الإجابة "نعم"، كيف تشعر تجاه ذلك؟

هل تحصل على أي رعاية أو اهتمام خاص؟

- برأيك، إلى أي مدى تُعد مدرستك ناجحة في دمج الطلاب ذوي الاحتياجات الخاصة؟  ما الذي يجعلك تقول هذا؟

سهولة الوصول الفعلية/البدنية

الهدف: فهم التحسينات التي قامت بها المدرسة (إن وجدت) على مبنى/مباني المدرسة والحرم المدرسي بهدف جعلها أكثر سهولة للطلاب ذوي الاحتياجات الخاصة.

- هل قامت مدرستك بعمل أي تحسينات على مبنى/مباني أو الحرم المدرسي؟

إذا كانت الإجابة "نعم":

  - ما نوع التحسينات التي قاموا بها؟

(الاستفهام  حول: الارصفة المعده لذوي الاحتياجات الخاصة، إتاحة الكراسي المتحركة، دورات مياه لذوي الاحتياجات الخاصة، مواقف لذوي الاحتياجات الخاصه، مداخل وقاعات واسعة، إشارات برايل، مترجمي لغة الإشارات...إلخ.)

- هل تعرف لماذا قامت مدرستك بهذه التحسينات؟ (الاستفهام  حول: فهم الطلاب لسهولة وصول الأطفال من ذوي الاحتياجات الخاصة.....إلخ)

  - ما نوع التحسينات التي تتمنى أن تقوم بها مدرستك؟

  - ما مدى اختلاف تجربتك الحالية عن التجربة التي تم وصفها للتو؟

  - كيف كانت ستكون تجرتك التعليمية لو كنت تملك هذه الميزات؟

(الاستفهام  حول: الفوائد العاطفية والوظيفية... الخ).

إذا كانت الإجابة "لا":

- ما نوع التحسينات التي تتمنى أن تقوم بها مدرستك؟

- كيف تبدو المدرسة المثالية؟

(الاستفهام  حول:  المرافق، الغرف الصفية ، الملاعب الرياضية...إلخ)

جلسات إعادة التأهيل والأجهزة المساعدة:

الهدف:

- فهم ماهي المواد والموارد التي استثمرت بها المدرسة/توفرها لطلابها (إن وجد) لمساعدة ذوي الاحتياجات الخاصة مع تسليط الضوء على الاحتياجات الأخرى.

- تقييم برامج إعادة التأهيل المدرسية (إن وجدت) ، وفهم سبل تحسينها.

- ما هو نوع الموارد والمواد التي تحتاجها في التعلم؟

- هل تمتلك مدرستك هذه الموارد والمواد؟

- هل تعرف ما هي الموارد والمواد التي يحتاجها الطلاب ذوي الاحتياجات الخاصة؟

- ما هي الموارد والمواد التي تتمنى أن تمتلكها مدرستك لمساعدتك في التعلم؟

(الاستفهام  حول ـ: مسجلات الصوت، الموقتات، أدلة القراءة، داعمات الكتابة، الآلات الحاسبة، وسائل التنظيم...إلخ.)

- هل تمتلك مدرستك أي أجهزة مساعدة تساعدك في التعلم؟

(الاستفهام  حول ـ: أوراق العمل الإلكترونية، برامج التهجئة الصوتية، الآلات الحاسبة الناطقة، المتغير، مسجلات السرعة...إلخ.)

- على حد علمك، ما هي الأجهزة المساعدة التي يحتاجها الطلاب ذوي الاحتياجات الخاصة؟

- هل تعلم ما إذا كانت مدرستك تقدم أي جلسات إعادة تأهيل للطلاب من ذوي الاحتياجات الخاصة؟

- على حد علمك، هل كان المعلمون في المدرسة معتمدون ومؤهلون للعمل مع الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم":

- ما نوع الشهادة/المؤهل الذي لديهم ؟

- ما هي الإعاقات التي تدربوا على التعامل معها؟(الاستفهام  حول: ضعف البصر، ضعف النطق والسمع، الإعاقة الجسدية، الإعاقة الذهنية، المرض العقلي، اضطراب طيف التوحد...إلخ)

- هل هناك نظام إحالة للطلاب ذوي الاحتياجات الخاصة في المدرسة؟

إذا كانت الإجابة "نعم":

- لماذا تتم إحالة الطلاب؟

- أين تتم إحالة الطلاب؟

زيادة الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الجهود المبذولة (إن وجدت) في نقل التصور السائد عند الطلاب وأولياء الامور تجاه الأطفال من ذوي الاحتياجات الخاصة وأهمية وجود نظام التعليم الدامج

- هل تعرف ما هو برنامج "التعليم الدامج" للطلاب ذوي الإحتياجات الخاصة؟

- ما هو رأيك في برنامج" التعليم الدامج" لكافة الطلاب بما فيهم الأطفال من ذوي الاحتياجات الخاصة؟

- ما هي نقاط القوة ونقاط الضعف في البرنامج؟

- هل هو واقعي؟  لماذا؟

(الاستفهام  حول ـ: الاحتمالية المتوقعة للنجاح، تقبل الآخرين...الخ).

- هل هي خطوة ضرورية يجب اتخاذها في المدارس الحكومية؟ لماذا؟

- هل قامت المدرسة ببذل أي جهود لزيادة الوعي تجاه ذوي الاحتياجات الخاصة وأهمية التعليم الدامج؟

إذا كانت الإجابة "لا":

- هل تتمنى لو قاموا بذلك؟  لماذا؟

- هل من الضروري أن يقوموا بذلك؟ لماذا؟

إذا كانت الإجابة "نعم":

- كيف كانت /بدت الحملة التوعوية التي قامت بها؟

(الاستفهام  حول: المحاضرات ، الاجتماعات ، الكتيبات/ أوراق المعلومات...إلخ)

- كم عدد المحاضرات/الاجتماعات التي تم عقدها حول هذا الموضوع؟

- ما هو محتوى الحملة؟

- هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

- هل كانت جهودهم موجهة إلى الطلاب في المدرسة أم إلى أولياء أمور الطلبة ؟

إذا كان كلاهما، فكيف اختلفت جهود الحملة؟

- هل أنت على علم ودراية بأية مشاريع أو برامج تنفذها منظمة الأمم المتحدة للطفولة (اليونيسيف) أو (ميرسي كور) فيما يتعلق بالتعليم الدامج وتعزيز كفاءة المدارس الحكومية لجعلها مناسبة أكثر للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، فما الذي تعرفه عنها؟

- هل تغيرت آرائكم حول الأطفال من ذوي الاحتياجات الخاصه ؟ كيف ذلك؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

لقد اختتمنا الآن مناقشتنا لهذا اليوم.

شكرًا لحضروركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### الأطفال الغير ملتحقين بالمدرسة (الأعمار من 10 الى 18)

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة،لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. ولكن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  تلك القواعد.

الأسئلة التمهيدية

لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

- كم عمرك؟

- ماذا تقضي وقتك عادةً خلال اليوم؟

الأسئلة الأساسية

إمكانية الوصول إلى التعليم

للطلاب المنقطعين

الهدف: تقييم مستويات الوعي لأية تحسينات تمت على المدارس كجزء من برنامج التعليم الدامج.

- هل تعلم ما إذا كانت المدرسة التي التحقت بها قد قامت بأي تحسينات على مبنى/مباني أو الحرم المدرسي في السنوات القليلة الماضية؟

إذا كانت الإجابة "نعم":

- ما نوع التحسينات التي قاموا بها؟

(الاستفهام حول: الأرصفة المعدة لذوي الاحتياجات الخاصة، إتاحة الكراسي المتحركة، دورات مياه لذوي الاحتياجات الخاصة، مواقف لذوي الاحتياجات الخاصة، مداخل وقاعات واسعة، إشارات برايل، مترجمي لغة الإشارة...إلخ.)

- هل تعرف لماذا قامت مدرستك بهذه التحسينات؟

(الاستفهام حول:  فهم الطلاب لسهولة وصول  الأطفال من ذوي الاحتياجات الخاصة.....إلخ)

- ما نوع التحسينات التي ترغب في أن تقوم بها مدرستك؟

- ما مدى اختلاف تجربتك الحالية عن التجربة التي تم وصفها للتو؟

- كيف كانت ستكون تجرتك التعليمية لو أن مدرستك  قامت بهذه التحسينات؟

(الاستفهام حول: الفوائد العاطفية والوظيفية... الخ).

- هل كانت هذه التحسينات ستشجعك على البقاء في المدرسة؟ لماذا؟

- بناءً على معرفتك،  هل النظام التعليمي والمدارس ملائمة وسهلة الوصول للأطفال من ذوي الاحتياجات الخاصه ؟

- اذا كانت الاجابة "نعم "، هل تعرف أي من الاطفال من ذوي الاحتياجات الخاصة ممن يذهبون إلى المدرسة ؟

- هل النظام التعليمي والعامة  مستعدون لعملية دمج الأطفال من ذوي الاحتياجات الخاصة؟

التجربة التعليمية المثالية

الهدف: فهم كيف ستبدو المدرسة المثالية وما هو الشعور نحوها. التركيز هنا على العناصر العاطفية والوظيفية للنظام التعليمي الناجح

- دعونا نغلق أعيننا ونتخيل أننا لدينا القدرة على تصميم المدرسة المثالية.

هل يمكنك أن تصفها لي؟ (بشكل عفوي)

الاستفهام حول:

  - أين تقع؟

  - كيف تبدو المرافق؟

(الاستفهام حول الملاعب الرياضية، دورات المياه ...الخ)

  - ما هي الموارد التي تملكها المدرسة؟

  - كيف تبدو الغرف الصفية؟ (الاستفهام حول: الحجم،المساحة، الألواح المدرسية ...إلخ)

- والآن دعونا نتخيل معاً تجربة الصفية المثالية.

  - كيف يبدو المعلم؟ (الاستفهام حول: مهني/محترف، مهتم ومراعي، صبور، متفهم، متعلم، مدرّب...إلخ.)

  - كيف تبدو الحصص الدراسية؟ (الاستفهام حول: طول الحصة الدراسية، توزيع الطلاب، التفاعل في الحصص...الخ).

  - كم عدد الطلاب معك في الصف؟

- هل تعرف ما هو برنامج "التعليم الدامج"؟ إذا كانت الإجابة "نعم"، فيُرجى الشرح.

ملاحظة لمنظم/ميسر الجلسة: التعليم الدامج، كما تم تعريفه من قبل اليونيسيف، هو طريقة فعالة لإعطاء جميع الأطفال فرصة عادلة للذهاب إلى المدرسة والتعلم وتنمية المهارات التي يحتاجون إليها في الحياة. التعليم الدامج يعني أن جميع الأطفال (من ذوي الاحتياجات الخاصة أو الأصحاء ) يلتحقون بنفس الصفوف وفي نفس المدارس.  وهذا يعني فرص التعلم الحقيقية للمجموعات التي تم استبعادها تقليدياً.  فالأنظمة الشاملة تقدر المساهمات الفريدة التي يقدمها الطلاب من كافة الخلفيات إلى الغرفة الصفية كما تسمح للمجموعات المختلفة والمتنوعة بالنمو جنباً إلى جنب، بما فيه منفعة الجميع.

- والآن وبعد أن عرفت  ما الذي يعنيه ( برنامج التعليم الدامج )

- ما رأيك في هذا المفهوم؟ (الاستفهام في :  الأفكار العاطفية والوظيفية حول الموضوع)

- هل هو واقعي؟  لماذا؟

- هل تعتقد أن ذلك سيكون ناجحاً؟  لماذا؟

- هل هي خطوة ضرورية يجب اتخاذها في المدارس الحكومية؟ لماذا؟

- هل ينبغي أن يكون هذا المفهوم أساسي وإلزامي في جميع المدارس؟ لماذا؟

الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة

الهدف: فهم الوعي والتصورات السائدة من قبل المشاركين تجاه الإعاقات والأطفال من ذوي الاحتياجات الخاصة.

- هل تعلم  ماهي أنواع الاعاقات/العاهات  المختلفة؟

(الاستفهام حول ـ: ضعف البصر والكلام وضعف السمع والإعاقات العقلية والإعاقات الجسدية...إلخ.)

- هل تعرف أي شخص من ذوي الاحتياجات االخاصة/الإعاقات ؟

إذا كانت الإجابة "نعم"

- هل يتقبلهم المجتمع؟

- هل يوفر لهم المجتمع الفرص والحقوق التي يستحقونها،....الخ ؟

- هل شاهدت أو سمعت عن أي حملات توعية بشأن الأطفال ذوي الاحتياجات الخاصه وأهمية التعليم الدامج ؟

إذا كانت الإجابة "نعم" :

- من الجهة الممولة لهذه الحملة؟

- كيف كانت/بدت الحملة التوعوية التي قامت بها؟

- ما هي رسالة الحملة ؟

- هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

- ما رأيك في الحملة؟ (الاستفهام حول: الإعجاب وعدم الإعجاب).  لماذا؟

- هل أنت على دراية وعلم بأية مشاريع أو برامج تنفذها منظمة الأمم المتحدة للطفولة (اليونيسيف) أو فيلق الرحمة (ميرسي كوربس) فيما يتعلق بالتعليم الدامج وتعزيز كفاءة المدارس الحكومية لجعلها مناسبة أكثر للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، فما الذي تعرفه عنها؟

الأسئلة الثانوية.

- من يهتم ويعتني بك؟

(الاستفهام حول: ولي الأمر أو الوصي الشرعي)

- هل تعتقد أن التعليم مهم؟  لماذا؟

- هل التحقت في المدرسة في مرحلة ما بالسابق؟

إذا كانت الإجابة "لا"، فلماذا؟

(الاستفهام حول ، قلة الرغبة سواء من قبل الطالب أو من قبل أولياء الأمور ، قلة الوسائل، الافتقار إلى المدارس التوعوية يعد أمر مهم...إلخ).

إذا كانت الإجابة "نعم":

- متى انقطعت عن الدراسة؟ (الاستفهام حول: السنة والصف)

- لماذا انقطعت عن الدراسة؟

(الاستفهام حول: ، قلة الاهتمام، الرسوب المدرسي، العمل/دعم الأسرة... إلخ).

- قرار من كان سبب الانقطاع؟

(الاستفهام حول: الأب، الأم، حدث ذلك بشكل تلقائي، قرار شخصي، الظروف... إلخ).

- ماذا أعجبك في المدرسة؟  ما الذي لم يعجبك في المدرسة؟

- هل ترغب في العودة إلى المدرسة في حال أتيحت لك الفرصة؟ لماذا؟

- هل تتلقى حالياً أي شكل من أشكال التعليم؟

إذا كانت الإجابة نعم، فماذا؟

(الاستفهام حول: التدريب المهني، التعليم المنزلي ...إلخ)

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

### الأطفال/الطلاب ذوي الإعاقات  الغير ملتحقين بالمدرسة (الأعمار من 15 الى 18)

مرحباً بكم في مجموعة النقاش هذه. نجتمع اليوم بهدف مناقشة تجربتكم التعليمية في المدرسة مع التركيز على الطلاب من ذوي الاحتياجات الخاصة.

أتمنى من الجميع المشاركة ،لذلك أرجو ألا تخجلوا. ما أطلبه منكم فقط أن نحترم بعضنا ونستمع إلى بعضنا البعض. يرجى العلم بأنه لا توجد إجابات صحيحة أو خاطئة وأن كافة الآراء مرحب بها هنا، كما نقدر مصداقيتكم للغاية.

كل ما سيتم تداوله في هذه المناقشة سري للغاية ولن يستخدم إلا لأغراض البحث. ولن يتم الكشف إطلاقاً عن هوية المتحدث أو انتمائه أو هوية أي مشارك آخر. كما لن نفصح عن أي بيان يُنسب إلى أو عائد على اسم أي مشارك. سيتم تسجيل الجلسة. إن أعضاء فريق البحث هم الوحيدون الذين بإمكانهم الوصول إلى هذه التسجيلات. كما أنهم الوحيدون الذين يمكنهم النظر إلى محضر الجلسة المكتوب كاملاً.

لذا وبعد سماع هذه الشروط، فإن بقائكم  في هذه المجموعة يشير إلى موافقتكم على  هذه القواعد.

الأسئلة التمهيدية

لكي يتسنى لنا التعرف عليكم بشكل أفضل ، لماذا لا تخبروننا قليلاً عن أنفسكم.

- كم عمرك؟

- هل تعمل؟ إذا كانت الإجابة "نعم"، فماذا تفعل؟

- هل التحقت في المدرسة في مرحلة ما بالسابق؟

إذا كانت الإجابة "لا"، فلماذا؟  (نظراً للعجز/الإعاقة، قلة الرغبة، قلة الوسائل، الافتقار إلى المدارس التوعوية يعد أمر مهم...إلخ).

- هل يعيق العجز تعليمك؟ إذا كان الأمر كذلك، فكيف؟

- هل يؤثر ذلك على قدراتك التعليمية؟ إذا كانت الإجابة "نعم"، فكيف؟

- الأسئلة الأساسية

- متى انقطعت عن الدراسة؟ (الاستفهام حول: السنة والصف)

- لماذا انقطعت عن الدراسة؟ (الاستفهام حول: العجز، قلة اهتمام، الرسوب المدرسي، العمل/دعم الأسرة... إلخ).

- قرار من كان سبب الانقطاع؟   (الاستفهام حول: الأب، الأم، حدث ذلك بشكل تلقائي، قرار شخصي، الظروف... إلخ).

- هل كانت تلك المدرسة ملائمة وسهلة الوصول بالنسبة لك؟

إذا كانت الإجابة "نعم"، فكيف كانت ملائمة وسهلة الوصول؟

إمكانية الوصول إلى التعليم

للطلاب المنقطعين

الهدف: تقييم مستويات الوعي لأية تحسينات تمت على المدارس كجزء من برنامج التعليم الدامج.

- هل تعلم ما إذا كانت المدرسة التي التحقت بها قد قامت بأي تحسينات على مبنى/مباني أو على الحرم المدرسي في السنوات القليلة الماضية؟

إذا كانت الإجابة "نعم":

  - ما نوع التحسينات التي قاموا بها؟

(الاستفهام حول: الأرصفة المعدة لذوي الاحتياجات الخاصة، إتاحة الكراسي المتحركة، دورات مياه لذوي الاحتياجات الخاصة، مواقف لذوي الاحتياجات الخاصة، مداخل وقاعات واسعة، إشارات برايل، مترجمي لغة الإشارة...إلخ.)

  - هل تعرف لماذا قامت مدرستك بهذه التحسينات؟

(الاستفهام حول:  فهم الطلاب لسهولة الوصول الأطفال من ذوي الاحتياجات الخاصة.....إلخ)

  - هل كانت التحسينات كافية لجعل المدرسة ملائمة وسهلة الوصول بالنسبة لك/لشخص يعاني من عجز معين؟  إذا كانت الإجابة "نعم"، فيُرجى التوضيح

إذا لم يكن الأمر كذلك، فما نوع التحسينات التي تتمنى أن تقوم بها مدرستك؟

- كيف كانت ستكون تجرتك التعليمية لو كنت تملك هذه الميزات؟

(الاستفهام حول: الفوائد العاطفية والوظيفية... الخ).

  - ما مدى اختلاف خبرتك التعليمية لو كانت المدرسة ملائمة وسهلة الوصول لك؟

(استفسر عن: الفوائد العاطفية والوظيفية... الخ).

  - هل كانت هذه التحسينات ستشجعك على البقاء في المدرسة؟ لماذا؟

- على حد علمك، هل كان المعلمون في المدرسة التي التحقت بها  مؤهلون ومعتمدون للعمل مع الأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "لا"، فلماذا تعتقد أنهم غير مؤهلين؟

إذا كانت الإجابة "نعم":

  - ما نوع الشهادة/المؤهل الذي لديهم ؟

  - ما هي الإعاقات التي تدربوا على التعامل معها؟ (الاستفهام حول: ضعف البصر، ضعف النطق والسمع، الإعاقة الجسدية، الإعاقة الذهنية، المرض العقلي، اضطراب طيف التوحد...إلخ)

- هل شعرت أن معلميك مدربون على تدريبك/أو تدريب الأشخاص الذين يعانون من نفس نوع الإعاقة/العجز الذي لديك؟

إذا كانت الإجابة "لا"، فلماذا؟ (الاستفهام حول: نقص التدريب، عدم الخبرة، نقص الموارد والمواد المناسبة... الخ)

إذا كانت الإجابة "نعم"، فلماذا تعتقد ذلك؟

لجميع الأطفال

- من وجهة نظرك، ماهي أكبر التحديات التي يواجهها الأطفال من ذوي الاحتياجات الخاصة فيما يتعلق بالتعليم في الاردن؟ لماذا؟

(الاستفهام حول: التصورات السائدة تجاه الأشخاص من ذوي الاحتياجات الخاصة (من قبل المجتمع ومن قبل أسرتهم)، قلة الوعي باحتياجات هذه الفئة ، عدم كفاية التمويل، قلة الاهتمام أو عدم الاهتمام من قبل الحكومة/وزارة التربية والتعليم.

- ماذا يتطلب الأمر بالنسبة للمدارس الحكومية للتغلب على هذه العقبات؟

- هل نظام التعليم في الأردن مناسب للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، كيف؟

وإذا كانت الإجابة "لا"، فما الذي ينبغي أن يحدث للنظام التعليمي لاستيعاب ومراعاة الأطفال من ذوي الاحتياجات الخاصة؟

جلسات إعادة التأهيل والأجهزة المساعدة:

الهدف:

- فهم المواد والمصادر/الموارد التي يحتاج إليها الأطفال من ذوي الاحتياجات الخاصة للتعلم ،وما إذا كانت المدارس التي ذهبوا إليها تملكها.

- فهم ماهي برامج إعادة التأهيل التي يحتاجها الأطفال من ذوي الاحتياجات الخاصة، وما إذا كانت المدارس التي ذهبوا إليها تملكها.

- لنفترض أنك ستلتحق بأحد المدارس غداً ، ما هي المصادر/الموارد والمواد التي تتمنى أن تمتلكها المدرسة لمساعدتك في التعلم؟

(الاستفهام حول ـ: مسجلات الصوت، الموقتات، أدلة القراءة، داعمات الكتابة، الآلات الحاسبة، وسائل التنظيم...إلخ.)

- كيف يمكن تحسين تجربتك التعليمية أيضاً؟

- هل تحتاج إلى جلسات إعادة التأهيل؟ إذا كانت الإجابة "نعم"، فما نوعها؟

- هل تعرف ما هي الأجهزة التقنية المساعدة؟

- إذا كانت الإجابة "نعم"، فهل تحتاج إلى أي منها؟

- ما هي؟

للطلاب المنقطعين فقط

- هل كانت المدرسة التي ذهبت إليها تمتلك المصادر/الموارد والمواد اللازمة لتلبية احتياجات شخص يعاني من نفس نوع العجز/الإعاقة التي لديك؟ (بما في ذلك الأجهزة المساعدة)

(الاستفهام حول ـ: أوراق العمل الإلكترونية، برامج التهجئة الصوتية، الآلات الحاسبة الناطقة، مواد متغيرة، مسجلات السرعة...إلخ.)

- هل التحقت بأي جلسات لإعادة التأهيل في المدرسة؟

إذا كانت الإجابة "لا"، هل تتمنى أن تقدم المدرسة جلسات إعادة تأهيل؟

إذا كانت الإجابة "نعم":

- لماذا تمت التوصية بتلقيك جلسات إعادة التأهيل؟

- من هو صاحب القرار فيما يتعلق بحاجتك لتلقي جلسات إعادة التأهيل؟ (الاستفهام حول: المعلمون، مدراء المدراس، طبيب متخصص، طبيب المدرسة، أولياء الأمور... الخ)

- ما نوع جلسات إعادة التأهيل التي تلقيتها؟ (الاستفهام حول: علاج النطق، العلاج الطبيعي... الخ)

- هل كلفك ذلك أو تكلفت عائلتك أي شيء؟  إذا كانت الإجابة "نعم"، فما هو المبلغ؟

- أين تلقيت هذه الجلسات؟ (الاستفهام حول: الموقع، خارج الحرم المدرسي، في عيادة عامة/خاصة... إلخ)

- كم مرة تلقيتها؟ (أسبوعياً، شهرياً...إلخ)

- كم كانت مدة الجلسات؟

- هل هناك نظام إحالة للطلاب ذوي الاحتياجات الخاصة في المدرسة؟

إذا كانت الإجابة "نعم":

- ما نوع نظام الإحالة الذي تملكه المدرسة؟

- لماذا تتم إحالة الطلاب؟

- أين تتم إحالة الطلاب؟

- من يتتبع هذه الحالات؟

الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة (CWD)

الهدف: فهم الوعي والتصورات السائدة من قبل المشاركين تجاه الإعاقات والأطفال من ذوي الاحتياجات الخاصة.

- هل تعلم ما هو برنامج اليونيسف للتعليم الدامج؟

إذا كانت الإجابة "نعم":

  - الى أي مدى يرتبط البرنامج وانشتطه في مراكز مكاني باحتياجات الأطفال ذوي الاحتياجات الخاصة المتسربين او غير الملتحقين في المدارس؟

- هل رأيت أو سمعت عن أية حملات توعية تتعلق بالأطفال من ذوي الاحتياجات الخاصة وأهمية برامج التعليم الدامجة؟

إذا كانت الإجابة "نعم":

  - كيف كانت/بدت حملة التوعية؟

  - ما هي رسالة الحملة؟

  - هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة ؟  لماذا؟

  - ما رأيك في الحملة؟ (الاستفهام حول: الإعجاب وعدم الإعجاب). لماذا؟

للطلبة المنقطعين

- هل قامت المدرسة التي التحقت بها ببذل أي جهود لزيادة الوعي تجاه ذوي الاحتياجات الخاصة وأهمية التعليم الدامج؟

إذا كانت الإجابة "لا":

  - هل تتمنى لو قاموا بذلك؟  لماذا؟

  - هل من الضروري أن يقوموا بذلك؟ لماذا؟

إذا كانت الإجابة "نعم":

  - من الجهة الممولة لهذه الحملة؟

  - كيف كانت/بدت الحملة التوعوية التي قامت بها؟

  - (الاستفهام حول: المحاضرات والاجتماعات والكتيبات/أوراق المعلومات...إلخ)

  - ما هو محتوى تلك الحملة؟

  - هل تشعر أن الحملة كانت ناجحة في رفع مستوى الوعي تجاه الأطفال من ذوي الاحتياجات الخاصة؟ لماذا؟

  - هل كانت جهودهم موجهة إلى الطلاب في المدرسة أو إلى أولياء أمور الطلاب؟

  - ما رأيك في الحملة؟ (الاستفهام حول: الإعجاب وعدم الإعجاب).  لماذا؟

- هل أنت على دراية وعلم بأية مشاريع أو برامج تنفذها منظمة الأمم المتحدة للطفولة (اليونيسيف) أو (ميرسي كوربس) فيما يتعلق بالتعليم الدامج وتعزيز كفاءة المدارس الحكومية لجعلها مناسبة أكثر للأطفال من ذوي الاحتياجات الخاصة؟

إذا كانت الإجابة "نعم"، فما الذي تعرفه عنها؟

- هل هناك أي شيء آخر ترغب في إضافته إلى هذه المناقشة؟

الأسئلة الثانوية

- هل ترغب في العودة إلى المدرسة في حال أتيحت لك الفرصة؟ لماذا؟

إذا كانت الإجابة "نعم"، فما الذي يمنعك من القيام بذلك؟

- هل تتلقى حالياً أي شكل من أشكال التعليم؟

إذا كانت الإجابة "نعم"، فماذا؟

(الاستفهام حول: التدريب المهني، التعليم المنزلي ...إلخ)

- كيف تشعر حيال عدم التحاقك بالمدرسة؟

- من يهتم ويعتني بك؟

(الاستفهام حول: ولي الأمر أو الوصي الشرعي)

- إلى أي مدى تحتاج إلى مساعدة ذويك او مقدمي الرعاية؟

(الاستفهام حول: طوال الوقت، للأنشطة اليومية الأساسية، أثناء الحركة والتنقل...إلخ)

التجربة التعليمية المثالية

الهدف: فهم احتياجات ورغبات الأطفال من ذوي الاحتياجات الخاصة وكيف تبدو تجربة التعليم المثالية من وجهة نظرهم.

- دعونا نغلق أعيننا ونتخيل أننا لدينا القدرة على تصميم المدرسة المثالية.

هل يمكنك أن تصفها لي؟ (بشكل عفوي)

  - أين تقع؟

  - كيف تبدو المرافق؟

(الاستفهام حول الملاعب الرياضية، دورات المياه ...الخ)

  - ما هي الموارد التي تملكها المدرسة؟

  - كيف تبدو الغرف الصفية؟ (الاستفهام حول: الحجم،المساحة، الألواح المدرسية ...إلخ)

- والآن دعونا نتخيل معاً تجربة الصفية المثالية.

  - كيف يبدو المعلم؟ (الاستفهام حول: مهني/محترف، مهتم ومراعي، صبور، متفهم، متعلم، مدرّب...إلخ.)

  - كيف تبدو الحصص الدراسية؟ (الاستفهام حول: طول الحصة الدراسية، توزيع الطلاب، التفاعل في الحصص...الخ).

  - كم عدد الطلاب معك في الصف؟

- هل تعرف ما هو برنامج "التعليم الدامج"؟ إذا كانت الإجابة "نعم"، فيُرجى الشرح.

ملاحظة لمنظم/ميسر الجلسة: التعليم الدامج، كما تم تعريفه من قبل اليونيسيف، هو طريقة فعالة لإعطاء جميع الأطفال فرصة عادلة للذهاب إلى المدرسة والتعلم وتنمية المهارات التي يحتاجون إليها في الحياة. التعليم الدامج يعني أن جميع الأطفال (من ذوي الاحتياجات الخاصة أو الأصحاء) يلتحقون بنفس الصفوف وفي نفس المدارس.  وهذا يعني فرص التعلم الحقيقية للمجموعات التي تم استبعادها تقليدياً.  فالأنظمة الشاملة تقدر المساهمات الفريدة التي يقدمها الطلاب من كافة الخلفيات إلى الغرفة الصفية كما تسمح للمجموعات المختلفة والمتنوعة بالنمو جنباً إلى جنب، بما فيه منفعة الجميع.

- والآن بعد أن عرفت ما يعنيه هذا المفهوم، ما رأيك به؟

  - هل هو واقعي؟  لماذا؟

(الاستفهام حول ـ: الاحتمالية المتوقعة للنجاح، تقبل الآخرين...الخ).

  - هل تعتقد أن ذلك سيكون ناجحاً؟  لماذا؟

  - هل هي خطوة ضرورية يجب اتخاذها في المدارس الحكومية؟ لماذا؟

  - هل ينبغي أن يكون هذا المفهوم أساسي وإلزامي في جميع المدارس؟ لماذا؟

لقد انتهينا الآن من مناقشتنا لهذا اليوم.

شكراً لحضوركم ولتحدثكم وللوقت الذي قضيتموه معنا اليوم.

## Translated Classroom Observation Tool

| أسئلة البيئة المدرسية/الصفية | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل ترتيب الغرفة الصفية يساعد كافة الطلاب على الحركة بسهولة؟ |  |  |  |
| - . هل ترتيب الغرفة الصفية يساعد الأطفال ذوي الاحتياجات الخاصة على التحرك بسهولة؟ |  |  |  |
| - هل يتم وضع مقعد الأطفال ذوي الاحتياجات الخاصة في مكان مناسب ؟ |  |  |  |
| - هل يتم وضع مقعد الطالب الذي يستخدم الكرسي المتحرك أو المشاية أو العكازات بالقرب من مدخل الصف؟؟ |  |  |  |
| - هل يتم وضع مقعد الطالب الذي يعاني من ضعف السمع (ليس أصم) أو يعاني من صعوبات في الاتصال والتواصل بالقرب من المعلم أي في مقدمة الغرفة الصفية؟ |  |  |  |
| - هل يتم وضع مقعد الطالب ضعيف البصر (غير المكفوف) بالقرب من مصدر جيد للضوء؟ |  |  |  |
| - - هل يوجد مقعد للطالب _____________ في مكان مناسب حسب عجزه / عجزها؟ |  |  |  |
| - هل ترتيب الغرفة الصفية هو نفسه بحيث يعرف الطلاب ضعاف البصر كيفية التحرك فيه؟ |  |  |  |
| - إذا تم إجراء تغييرات ، فهل يتم اتخاذ التدابير اللازمة لإبلاغ الطالب أو لمساعدته عند إجراء التغيير؟ |  |  |  |

الممارسات العامة للغرف الصفية (قد لا يكون من الممكن ملاحظة جميع النقاط التالية في جلسة واحدة في الغرفة الصفية، ولكن ربما في عدة غرف صفية في المدرسة.  ستقدم الملاحظات التراكمية للغرف الصفية في إحدى المدارس تغذية راجعة/ردود فعل في حال كانت هذه النقاط موجودة في المدرسة بأكملها).

| أسئلة البيئة الصفية الايجابية | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل هنالك جو إيجابي في الغرفة الصفية؟ |  |  |  |
| - هل سلوك المعلم ينبع من القيادة واللطف ؟ |  |  |  |
| - هل يشجع المعلم الطلاب على مشاركتهم في الأنشطة الصفية ؟ |  |  |  |
| - هل يكافئ المعلم النجاح/الإنجاز مع الأخذ بعين الاعتبار قدرات الطلاب؟ |  |  |  |
| - هل يتم عرض جميع أعمال الطلاب على لوحات الإعلانات أو يتم عرض ما يبدو جيداً فقط؟ |  |  |  |
| - هل يتم تشجيع الطلاب على مساعدة بعضهم البعض في المهام/الواجبات التي يطلبها المعلم؟ |  |  |  |
| - هل يخاطب المعلم الطلاب ذوي الاحتياجات الخاصة بنفس الأسلوب/النبرة التي يخاطب بها الطلاب الآخرون؟ |  |  |  |
| - هل لدى المعلم توقعات مرتفعة للانجازات من كافة الطلاب ؟ |  |  |  |
| - هل يضع المعلم توقعات لأفضل ما يمكن أن يقدمه الطلاب من ذوي الاحتياجات الخاصة أم أنه يقبل بكل ما يمكنهم فعله؟ |  |  |  |

| أسئلة إدارة الصف | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل هناك 5-7 قواعد للغرف الصفية معلقة/منشورة بحيث يمكن لكافة الطلاب مشاهدتها؟ |  |  |  |
| - هل يتم فرض هذه القواعد باستمرار من قبل المعلم؟ |  |  |  |
| 3. هل هناك عدد قليل من الطلاب الذين لا يلتزمون بالقواعد؟ ماذا يفعل المعلم في مثل هذه الحالة؟ |  |  |  |
| - هل للصف اجراءات روتينية يجب اتباعها؟ |  |  |  |
| - عند دخول أو مغادرة الغرفة الصفية |  |  |  |
| - عند الانتقال من نشاط إلى آخر |  |  |  |
| - عند توزيع الأوراق أو تسليمها |  |  |  |
| - عند الانتقال من المقعد الفردي إلى الجلوس ضمن مجموعات صغيره |  |  |  |

| أسئلة إدارة السلوك | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل يستخدم المعلم المؤثرات الإيجابية باستمرار (الاجتماعية أو الملموسة مثل الملصقات أو الرموز أو الأنشطة) طوال الدرس للسلوك المناسب؟ |  |  |  |
| - للسلوك المتيقظ/المهتم |  |  |  |
| - لاتباع قواعد الصف |  |  |  |
| - للعمل الصحيح/العمل المنجز بشكل جيد |  |  |  |
| - لبذل جهد جيد في العمل |  |  |  |
| - هل هناك نظام تعزيز يُستخدم لكافة الطلاب في الصف سواءً للسلوك الجيد أو لقراءة الكتب أولمتابعة الواجبات المنزليه...؟ |  |  |  |
| - هل هنالك ما يبدو كنظام لمعاقبة/مواجهة النتائج السلبية للسلوكيات غير المناسبة وللعمل الذي لم يتم انجازه ؟ |  |  |  |
| - هل يعطي المعلم فرصة ثانية لسوء السلوك/سوء التصرف الذي قد يحدث أثناء الدرس؟ |  |  |  |
| - هل هناك نظام لإدارة سلوك طالب واحد أو عدد قليل من الطلاب الذين يسيئون التصرف أو يشوشون ويخلون بنظام الصف باستمرار؟ |  |  |  |

| أسئلة تنظيم الدرس | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل للدرس بداية واضحة؟ |  |  |  |
| - هل للدرس نهاية واضحة؟ |  |  |  |
| - هل تم إعداد مواد هذا الدرس في وقت سابق؟ |  |  |  |
| - إذا كانت هناك حاجة إلى مواد تتناسب مع ذوي الاحتياجات الخاصة ، فهل هي متاحة بسهولة؟ |  |  |  |
| - هل تتم عملية الانتقال بوضوح وسلاسة من نشاط إلى آخر ضمن الدرس؟ |  |  |  |
| - هل التعليمات واضحة ومقدمة شفهياً ويتم كتابتها على اللوح المدرسي؟ |  |  |  |
| - هل يتم إدارة وقت الدرس بشكل جيد؟ |  |  |  |

| أسئلة طرق/أساليب التدريس | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل يعتمد/يبني المعلم على التجارب السابقة أو التعلم السابق للطلاب ؟ |  |  |  |
| - هل هدف الدرس واضح للجميع؟ إذا كان ينطبق، هل يسلط المعلم الضوء على كيف أن ما سيتم تعلمه مفيد للحياة اليومية للطلاب؟ |  |  |  |
| - هل ترتبط أنشطة الدرس بشكل مباشر بهدف الدرس؟ |  |  |  |
| - هل يستخدم المعلم النهج متعدد الحواس أثناء التدريس؟ |  |  |  |
| - هل يستخدم المعلم كلاً من طرق العمل الفردي والتعلم النشط/الجماعي أثناء الدروس؟ |  |  |  |
| - مجموعات ثنائية ( زوج ) |  |  |  |
| - مجموعة عمل صغيرة |  |  |  |
| - - كيف يضمن المعلم أن الطلاب والأطفال ذوي الاحتياجات الخاصة يفهمون المهمة التي يقومون بها؟ |  |  |  |
| - هل يحصل الطالب على الدعم لإنجاز المهمة التي يقوم بها ؟ |  |  |  |
| - هل يتم الحاق/ضم الطفل من ذوي الاحتياجات الخاصة مع طالب آخر يساعد الطالب؟ |  |  |  |
| - هل يتلقى الطالب من ذوي الاحتياجات الخاصة الدعم من المعلم الملازم \الموجه؟ |  |  |  |
| - هل يتلقى الطلاب تغذية راجعة ( ملاحظات) على كافة الإجابات الصحيحة وغير الصحيحة؟ |  |  |  |
| - هل تتلاءم المهام مع المستويات المختلفة للطلاب؟ |  |  |  |
| - هل يستطيع الطلاب من ذوي الاحتياجات الخاصة تقديم عملهم بطرق مختلفة عن باقي طلاب الصف ؟ |  |  |  |
| - إذا لم يتمكن الطالب من الكتابة، فهل يستطيع أن يقوم بالعمل شفهياً أو من الكتابة على جهاز لوحي (تابلت)؟؟ |  |  |  |
| - إذا كان الطالب يواجه صعوبة في التواصل، فهل يتم منحه طرقاً بديلة للإجابة عن الأسئلة أو قراءة الدروس؟ |  |  |  |
| - هل يتم تقييم آداء الطلاب ذوي الاحتياجات الخاصة بطريقة تناسب مع حالتهم؟ إذا كانت الاجابة "نعم"، يرجى التوضيح؟ |  |  |  |
| 11. هل تتم التعديلات الأساسية على المهام المقدمة لكافة الطلاب بما فيهم الطلاب من ذوي الاحتياجات الخاصة؟ |  |  |  |
| - هل تم إعطاء/منح وقت إضافي لإكمال مهمة أو تقييم؟ |  |  |  |
| - إذا احتاج الطالب إلى قارئ أو كاتب لمساعدته في مهمة أو تقييم، فهل هذا متوفر أو متاح؟ |  |  |  |
| 12 هل يتم النظر إلى الصعوبات في التعلم على أنها نابعة من الطالب أو من العلاقة بين المعلم والطالب وبيئة التعلم ؟ |  |  |  |

## Translated School Tour Observation Tool

| أسئلة البيئة المدرسية/الصفية | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل البيئة المدرسية (المدخل/المخرج، الممرات) مجهزة بطريقة تمكن جميع الطلاب من التنقل بحرية، خاصة للأطفال من ذوي الاحتياجات الخاصة؟ |  |  |  |
| - إذا لم يكن الأمر كذلك، ما هي التدابير الداعمة التي تم اتخاذها للأطفال من ذوي الاحتياجات الخاصة للتنقل في المدرسة خاصة في أوقات الازدحام،على سبيل المثال: وقت الدخول إلى المدرسة والخروج منها، والسير في الممرات. ضع دائرة حول الإجابات المناسبة: أصدقاء الأطفال ذوي الاحتياجات الخاصة ، الموجهون/المراقبون ، موظفي المدرسة، وغيرهم ___________ |  |  |  |
| - عندما ينضم طفل جديد من ذوي الاحتياجات الخاصة إلى المدرسة، هل يتم اعطائه توجيهات عن بيئة المدرسة؟ هل يتم تحديد المجالات التي يحتاج فيها الطالب من ذوي الاحتياجات الخاصة إلى المساعده وعليه يتم تحديد نوع هذه المساعدة؟ |  |  |  |
| - هل الملاعب (أو القاعات الداخلية لقضاء فترات الاستراحة في الشتاء) ملائمة للأطفال من ذوي الاحتياجات الخاصة ؟ إذا لم يتمكن الأطفال من ذوي الاحتياجات الخاصة من المشاركة في الأنشطة في أوقات الاستراحة المعتادة للطلاب، فهل يتم ايجاد/إجراء أي أنشطة بديلة لهم؟ |  |  |  |
| - هل الكفتيريا مناسبة/مجهزة لتنقل الأطفال من ذوي الاحتياجات الخاصة بكل سهولة ؟ |  |  |  |
| - إذا لم يكن الأمر كذلك، ما هي التدابير الداعمة التي تم اتخاذها لمساعدتهم في التنقل داخل الكافيتيريا؟ ضع دائرة حول الإجابات المناسبة: أصدقاء الأطفال ذوي الاحتياجات الخاصة ، الموجهون/المراقبون ، موظفي المدرسة، وغيرهم ___________ |  |  |  |
| - إذا واجه بعض الأطفال من ذوي الاحتياجات الخاصة صعوبة في التعامل مع النقود فمن يساعدهم في الشراء؟ |  |  |  |

| أسئلة الممارسات الدامجة | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| موظفي المدرسة |  |  |  |
| - هل يوجد برنامج تدريبي شامل للمدرسة قبل دمج الأطفال من ذوي الاحتياجات الخاصة؟ |  |  |  |
| - هل يشمل هذا البرنامج التدريبي كافة الموظفين مثل الإداريين وغير المعلمين؟ |  |  |  |
| - ما هي مجالات التدريب الرئيسية المتعلقة بالممارسات الدامجة المقدمة لأعضاء الهيئة التدريسية قبل دمج الأطفال ذوي الاحتياجات الخاصة؟ |  |  |  |
| - هل التدريب موجه لكافة معلمي المدرسة أم فقط للمعلمين الذين لديهم أطفال من ذوي الاحتياجات الخاصة في غرفهم الصفية ؟ |  |  |  |
| - على أي أساس يتم اختيار المعلمين الذين سيتم إدماج الأطفال من ذوي الاحتياجات الخاصة في صفوفهم الدراسية؟ |  |  |  |
| - هل عملية دمج الأطفال من ذوي الاحتياجات الخاصه تدريجية؟ |  |  |  |
| - ما هو الهدف من دمج عدد من الأطفال من ذوي الاحتياجات الخاصة في المدرسة بأكملها؟ |  |  |  |
| - إذا كان هناك عدد من الأطفال من ذوي الاحتياجات الخاصة في الصف الواحد، فكم عدد الصفوف في المدرسة؟ |  |  |  |
| - إذا كان هناك نسبة مئوية للأطفال من ذوي الاحتياجات الخاصة في المدرسة، فما هو العدد الإجمالي للطلاب و ماهي النسبة المئوية المستهدفة؟ |  |  |  |
| - هل كان تدريب الموظفين يتم لمرة واحدة فقط أم أنها برامج تدريب مستمرة؟ |  |  |  |
| - إذا كانت عملية مستمرة، فما هو التدريب الإضافي الذي يقدمونه وخاصة للمعلمين؟ |  |  |  |
| - ما هي الصعوبات التي يواجهوها مع الموظفين غير المعلمين والمعلمين في عملية دمج الطلاب مع الطلاب من ذوي الاحتياجات الخاصة؟ |  |  |  |
| - ما هي الاجراءات التي اتخذتها الإدارة لمساعدة أعضاء هيئة التدريس في التعامل مع طلابهم من ذوي الاحتياجات الخاصة ؟ |  |  |  |
| - هل لديهم مشرف على البرنامج؟ أم أن لديهم لجنة تضم العديد من الأشخاص الذين يقومون بالإشراف على البرنامج؟ - ما هي المؤهلات التي يمتلكها المشرف أو أعضاء اللجنة؟ |  |  |  |
| - هل يتعاون المعلمون لمناقشة وحل المشكلات \الصعوبات التي يواجهونها ؟ - هل هذا مقرر ضمن برنامجهم المدرسي؟ |  |  |  |
| - كيف يشارك المعلمون قصص نجاحهم مع أعضاء هيئة التدريس الآخرين؟ |  |  |  |
| - هل تخصص المدرسة وقتاً ضمن الجدول الدراسي للمعلمين الذين لديهم أطفال من ذوي الاحتياجات الخاصة لإتاحة الوقت لهم لإعداد المواد الخاصة بهؤلاء الاطفال؟ |  |  |  |

| أسئلة الممارسات الدامجة | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| الطلاب |  |  |  |
| - كيف تم تهيئة/إعداد طلاب المدرسة لدمج الأطفال من ذوي الاحتياجات الخاصة؟ |  |  |  |
| - أو هل كانت التهيئة فقط مخصصة لطلاب الصفوف التي تحتوي على أطفال من ذوي الاحتياجات الخاصة فقط ؟ |  |  |  |
| - ما هي السياسات التي تتبعها المدرسة في التعامل مع الإساءات التي يتعرض لها الأطفال من ذوي الاحتياجات الخاصة، مثل الإهانات والعزل والتنمر؟ |  |  |  |
| - هل الطلاب معنيون في دعم الأطفال من ذوي الاحتياجات الخاصة في التنقل داخل المدرسة، الكافتيريا..؟ |  |  |  |
| - هل لدى المدرسة أنشطة إضافية من خارج المناهج الدراسية؟ إذا كانت الإجابة "نعم"، فهل تشمل الطلاب من ذوي الاحتياجات الخاصة؟ |  |  |  |
| - إذا كانت الأنشطة الإضافية (من خارج المناهج الدراسية) غير مناسبة للأطفال من ذوي الاحتياجات الخاصة ، فهل أطلقت المدرسة أنشطة أخرى بحيث يتمكن الأطفال من ذوي الاحتياجات الخاصة المشاركة بها؟ |  |  |  |
| - هل نظمت المدرسة أنشطة بقصد إشراك جميع الطلاب من الطلاب الأصحاء والطلاب من ذوي الاحتياجات الخاصة بهدف بناء فهم مشترك وقبول من قبل بعضهم البعض؟ |  |  |  |
| - أعط أمثلة على هذه الأنشطة --------------------- |  |  |  |
| - هل تُظهر المدرسة إنجازات جميع طلابها أم فقط أصحاب الإنجازات المميزة؟ |  |  |  |
| - هل ترى المدرسة أن عملية الدمج تشكل عقبة أمام تحقيق مكانة أكاديمية عالية في المجتمع التربوي؟ |  |  |  |
| - هل تفضل المدرسة الإنجاز الأكاديمي/العلمي على تطوير قدرات جميع طلابها؟ |  |  |  |
| - هل تضم المدرسة أطفالاً من خلفيات ثقافية ووطنية ودينية واجتماعية اقتصادية مختلفة؟ |  |  |  |
| - إذا كانت الإجابة "نعم"، فهل يتم النظر إلى ذلك على أنه إثراء لمجتمعها أو أنه يمثل مشكلة؟ |  |  |  |

ملاحظة هامة: إن السؤالين 9 و10 يتناسبون مع مدارس المدينة وقد لا يتناسبون مع المدارس في المخيمات والمناطق القروية/الريفية.

| أسئلة الممارسات الدامجة | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| أولياء الأمور |  |  |  |
| - كيف تم إعداد أولياء أمور الطلاب لدمج الأطفال من ذوي الاحتياجات الخاصة مع أطفالهم؟ |  |  |  |
| - ما هي الصعوبات التي تمت مواجهتها مع أولياء الأمور بعد أن تم دمج الأطفال من ذوي الاحتياجات الخاصة في صفوف أطفالهم؟ |  |  |  |
| - كيف كانت استعدادات أولياء أمور الطلاب من ذوي الاحتياجات الخاصة لدمج أطفالهم في المدارس العادية؟ |  |  |  |
| - ما هي المخاوف التي كانت لديهم قبل عملية الدمج؟ بعد عملية الدمج؟ |  |  |  |
| - كيف تدعم المدرسة أولياء أمور الطلاب ذوي الاحتياجات داخل المدرسة وخارجها؟ |  |  |  |
| - هل يُعنى كافة أولياء أمور الطلاب بشؤون المدرسة أو بأنشطتها؟ إذا كانت الإجابة "نعم"، فكيف؟ |  |  |  |
| - هل يتم تخطيط أنشطة لأولياء أمور الطلاب الأصحاء وأولياء أمور الطلاب من ذوي الاحتياجات الخاصة مع بعضهم البعض بحيث تتاح لهم فرصة لفهم والتعرف على بعضهم البعض؟ |  |  |  |

| أسئلة المصادر المدرسية الأخرى غرفة المصادر (غرفة دراسية علاجية منفصلة ) | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - هل لدى المدرسة غرفة مصادر ؟ |  |  |  |
| - ما هو دور غرفة المصادر؟ |  |  |  |
| - مصدر لمساعدة المعلمين الذين لديهم أطفال من ذوي الاحتياجات الخاصة في غرفهم الصفية؟ |  |  |  |
| - صف تعليمي/دراسي للأطفال من ذوي الاحتياجات الخاصة الذين يتم إخراجهم من غرفة الصف العادية؟ |  |  |  |
| - كلاهما؟ |  |  |  |
| - ما هي نسبة الأطفال من ذوي الاحتياجات الخاصة الذين يتم إخراجهم لاستعمال غرفة المصادر؟ |  |  |  |
| - ما هي النسبة المئوية من ساعاتهم الدراسية التي يتم تخصيصها لإخراجهم عليها؟ |  |  |  |
| - هل هناك أي عملية أو إجراء متبع لتقليل الوقت الذي يقضية الأطفال من ذوي الاحتياجات الخاصة في غرفة المصادر تدريجياً، بناءً على قدراتهم والفجوة بينهم وبين زملائهم |  |  |  |

المعلم الملازم\الموجه

استناداً إلى تقارير منظمة فيلق الرحمة (ميرسي كورس) التي تمت قراءتها حتى الآن، فليس من الواضح ما هو دور المعلم الملازم/الموجه. حيث يبدو أن فهمنا لطبيعة دور المعلم الملازم/الموجه يختلف عن الأنشطة التي يشارك فيها في برنامج ميرسي كورس.

وسيتم تطوير الأسئلة بمجرد الحصول على وصف وظيفي من ميرسي كورس أو اليونيسيف.

| أسئلة تقييم البرنامج من وجهة نظر المدرسة | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| - من وجهة نظر المدرسة، منذ متى وأنتم تشاركون في مشروع ميرسي كورس واليونيسيف حول التعليم الدامج؟ |  |  |  |
| - برأيك، ما هي الفوائد التي اكتسبتها المدرسة بأكملها من هذا البرنامج؟ |  |  |  |
| - برأيك، ما هي العوائق/الصعوبات التي واجهتها المدرسة؟ |  |  |  |
| - ما هو المطلوب بالنسبة لكم للتغلب على هذه الصعوبات؟ |  |  |  |
| - من أجل المضي قدماً كمدرسة، ما الذي تحتاج إليه للحفاظ على استدامة هذا البرنامج؟ |  |  |  |
| - هل اخترت/تطوعت للمشاركة في هذا البرنامج أم أنه تم اختيارك للقيام بذلك؟ |  |  |  |
| - ما هي السياسات الجديدة التي يتعين عليك اتخاذها بعد قبول الأطفال من ذوي الاحتياجات الخاصة؟ |  |  |  |

| أسئلة الاستعداد للتسليم/النقل لوزارة التربية والتعليم | نعم | لا | ملاحظات |
| --- | --- | --- | --- |
| منذ بداية المشاركة في برنامج الدامج من MC/UNICEF ميرسي كور واليونيسيف، تم إعلامكم بأن وزارة التربية والتعليم سوف تشرف على برنامج الدمج الخاص بك في نهاية المطاف. |  |  |  |
| - كم سنة شاركت مدرستك في هذا البرنامج؟ |  |  |  |
| - متى يتوقع أن تقوم المدرسة بعملية التسليم/النقل إلى وزارة التربية والتعليم؟ |  |  |  |
| - هل تم إجراء أي تحضيرات للتسليم/للنقل ؟ |  |  |  |
| - إذا كانت الإجابة "نعم"، فما هي؟ |  |  |  |
| - هل قم بمقابلة الأشخاص المسؤولين عن هذا المشروع في وزارة التربية والتعليم ؟ |  |  |  |
| - ما هي المخاوف (إن وجدت) فيما يخص عملية التسليم/النقل؟ |  |  |  |

## Translated Teachers Survey

- هل أنت/ي معلم، مشرف أو مدير مدرسة؟

| - مشرف | - معلم |
| --- | --- |
| - لا شي مما ذكر (إنهاء الإستبيان) | - مدير مدرسة |

- هل تعمل/ي في مدرسة حكومية

| - لا (إنهاء الإستبيان) | - نعم |
| --- | --- |

- إذا كنت/ي معلم، ما الصف الذي تدرسه (يمكنك الإشارة الى أكثر من خيار)

| - الأول | - الثاني | - الثالث |
| --- | --- | --- |
| - الرابع | - الخامس | - السادس |
| - السابع | - الثامن | - التاسع |
| - العاشر |  |  |

- إذا كنت/ي معلم، هل أنت مربي صف؟

| - لا (إنهاء الإستبيان) | - نعم |
| --- | --- |

- إسم المدرسة التي تدرًس فيها:

- مكان المدرسة (المحافظة)

| - عمان | - عجلون | - الكرك |
| --- | --- | --- |
| - إربد | - جرش | - الطفيلة |
| - الزرقاء | - مادبا | - معان |
| - المفرق | - البلقاء | - العقبة |

- المادة التي تقوم بتدريسها

| - اللغة العربية | - اللغة الانجليزية |
| --- | --- |
| - الرياضيات | - الثقافة الاسلامية |
| - علوم | - رياضة |
| - تاريج | - جغرافيا |
| - غير ذلك، الرجاء التحديد ------- |  |

- هل تقوم بتدريس/ العمل مع أي طالب من ذوي الاحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

إذا كانت الإجابة نعم

  - هل أنت مدرس معتمد لتدريس الطلاب من ذوي الإحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

  - ما المدة الزمنية للتدريب الذي التحقت به؟

| - 1-3 أشهر | - 3-6 أشهر |
| --- | --- |
| - 6-12 شهر | - 12-24 شهر |
| - أكثر من 24 شهر |  |

  - أين تلقيت التدريب لتدريس الطلاب من ذوي الإحتياجات الخاصة؟

| - داخل الأردن | - خارج الاردن |
| --- | --- |

  - ما إسم الهيئة المعتمدة/ المرخصة للتدريب ؟

  - ما هي طبيعة الإعاقات/ العجز التي تدربت على العمل معها (يمكنك الإشارة الى أكثر من خيار)؟

| - بصري | - عقلي |
| --- | --- |
| - سمعي | - ذهني |
| - نطق | - إضطراب طيف التوحد |
| - جسدي/ حركي | - غيرها (يرجى التحديد) |

  - ما هي طبيعة الإعاقات/ العجز التي تعمل بها الآن أو عملت معها في السابق (يمكنك الإشارة الى أكثر من خيار)؟

| - بصري | - عقلي |
| --- | --- |
| - سمعي | - ذهني |
| - نطق | - إضطراب طيف التوحد |
| - جسدي/ حركي | - غيرها (يرجى التحديد) |

  - ما هي الفئة العمرية للطلاب من ذوي الإحتياجات الخاصة التي تعمل معها الآن أو عملت معها في السابق (يمكنك الإشارة الى أكثر من خيار)؟

| - أصغر من 6 | - 6-9 |
| --- | --- |
| - 10-14 | - 15-18 |

  - هل تجيد قراءة لغة بريل؟

| - نعم | - لا |
| --- | --- |

  - هل تجيد لغة الإشارة؟

| - نعم | - لا |
| --- | --- |

  - هل تقوم بإستخدام أي من الإدوات او الأجهزة التقنية المساندة عند تعليم الطلاب من ذوي الإحتياجات الخاصة

| - نعم | - لا |
| --- | --- |

إذا كانت الإجابة "نعم"

    - ما طبيعة هذه الأدوات/ الأجهزة التقنية المساندة  التي قمت بإستخدامها؟

| - أوراق عمل إلكترونية | - برامج التهجئة الصوتية |
| --- | --- |
| - الحاسبة الناطقة | - مسجل متغير السرعة |
| - المهارات الاجتماعية المسجلة بالفيديو | - غيرها(يرجى التحديد) |

  - هل تقدم المدرسة التي تعمل بها أي جلسات إعادة تأهيل للطلاب من ذوي الاحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

إذا كانت الإجابة "نعم"

    - أين يتم تقديم هذه الجلسات؟

| - في المدرسة | - خارج المدرسة |
| --- | --- |

  - هل لدى المدرسة التي تعمل بها نظام خاص لإحالة الطلاب من ذوي الاحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

  - من وجهة نظرك، ما هي اكبر التحديات التي تواجه تعليم الأشخاص من ذوي الاحتياجات الخاصة؟ (يمكنك الإشارة الى اكثر من خيار)

- نظرة المجتمع تجاه العجز او الإعاقة - نظرة افراد أسرة الطفل من ذوي الإحتياجات الخاصة - نفص الوعي بإحتياجات الإشخاص من ذوي الإحتياجات الخاصة - نقص أساليب التعلم - عدم كفاية التمويل من الجهات الحكومية - قلة الاهتمام من قبل الحكومة / وزارة التربية والتعليم - غير ذلك (يرجى التحديد] ________

- هل نظام التعليم الحالي في الأردن ملائم للإشخاص من ذوي الإحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

- هل بذلت المدرسة التي تعمل بها أي جهد لإدماج الطلاب من ذوي  الإحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

إذا كانت الإجابة "نعم"

  - ما طبيعة التحسينات التي قامت بها المدرسة لدمج الطلاب من ذوي الإحتياجات الخاصة؟ (يمكنك الإشارة الى أكثر من خيار)

| - إضافة مواقف سيارات خاصة | - إضافة منحدرات خاصة |
| --- | --- |
| - توسعة الممرات والابواب | - التدرج في الأرضيات |
| - إضافة مراحيض مخصصة | - تخصيص مساحة في الصف لطلاب من ذوي الإحتياجات الخاصة |
| - إضافة لغة بريل على اللوحات الارشادية | - توفير مترجمين للغة الإشارة |
| - غيرها (يرجى التحديد) |  |

- هل تعلم ما هو مفهوم "التعليم الدامج"؟

| - نعم | - لا |
| --- | --- |

إذا كانت الإجابة "نعم"

  - هل تم إختيار مدرستك لتكون جزءاً من برنامج التعليم الدامج؟

| - نعم | - لا |
| --- | --- |

  - من وجهة نظرك، هل يلبي برنامج التعليم الدامج احتياجات الطلاب من ذوي الاحتياجات الخاصة ​​من حيث تمكينهم من المشاركة الكاملة في عملية التعلم (كما هو الحال مع الأطفال الآخرين)

| - نعم | - لا |
| --- | --- |

- هل تؤمن أن لجميع الأطفال الحق في التعلم؟

| - نعم | - لا |
| --- | --- |

- هل تعتقد أنه لا ينبغي استبعاد أي طفل أو شخص بسبب إختلافاته؟

| - نعم | - لا |
| --- | --- |

- هل تعتقد أنه يجب ان يتأقلم نظام التعليم مع الطالب بدلاً من تأقلم الطالب مع النظام؟

| - نعم | - لا |
| --- | --- |

- هل تعتقد أن وزارة التربية والتعليم تقوم بكل ما يمكن للأطفال من ذوي الإحتياجات الخاصة؟

| - نعم | - لا |
| --- | --- |

- هل تؤمن بأن الطلاب من ذوي الإحتياجات الخاصة ليس لديهم القدرةعلى التعلم؟

| - نعم | - لا |
| --- | --- |

- هل بذلت المدرسة أي جهد لزيادة الوعي تجاه الطلاب من ذوي الإحتياجات الخاصة وأهمية التعليم الدامج؟

| - نعم | - لا |
| --- | --- |

إنهاء الإستبيان

## List of Reviewed Documents

    - Received Documents from UNICEF

- Mercy Corp Handover

- School handover plan

- 37 schools to be handed to MOE

- Arabic handover action plan

- Mercy Corps PD

- MC Programme document Final

- MC Programme document fully executed

- Program document 18.07.2017

- Mercy Corps Progress

- Final report september 2017-2019

- IE-Mercy Corps Progress Report 3

- IE-Mercy Corps Progress Report 4

- Mercy Corps CWD in formal education

- Programme Description

- Play area

- Playground description

- Training manual

- School supplies

- All school supplies from 2013

- Am Ammar School

- Maysaloon

    - Others

- Strategic Plan

- UNICEF Targets

- the 10-year strategy for inclusive education

- Inclusive education operational plan

- Inclusion of CWD in the formal education (policies and procedures)

    - Received Documents from Mercy Corps

- Covid Response in the host communities

- Parent meetings and awareness raising

- Students’ Progress Evaluation

- Case Study 2 Shadow Teachers support Summayya this was submitted to porticus but gives a good idea

- List of MC schools

- Lockdown Survey Report

- MC log frame

    - Documents from Secondary Research

- School and Classroom Disabilities Inclusion Guide for Low-and Middle-Income Countries, RTI, Jennae Bulat, Anne M. Hayes, Wykia Macon, Renáta Tichá, and Brian H. Abery Occasional Paper, Jan 2017

- Removing Barriers – The Path towards Inclusive Education, Australian Aid, 2018

- The Current Situation of Persons with Disabilities in Jordan, K4D, August 2018

- Inclusive Education in Jordanian Schools: Special Education and General Education Teachers’ Perspectives, Athens Journals, 2019

- Moving to Inclusive Education for Students with Disabilities in Jordan: Rhetoric, Practice and Prospects, Global Journal of Advanced Research, Hamza Mahmoud Al Shoura and Aznan Che Ama, 2015

- General Comment No. 4 (2016) Article 24: Right to inclusive education

- Inclusive education: Understanding Article 24 of the Convention on the Rights of Persons with Disabilities

- Conceptualizing Inclusive Education and Contextualizing it within the UNICEF Mission

- Legislation and Policies for Inclusive Education.

- Inclusive education: children with disabilities – paper commissioned by the GEMR 2020

- Index for Inclusion: developing learning and participation in schools

## Methodological note prepared for interviewers and facilitators - Ethical considerations[1]

Persons with disabilities are not “weak”, “helpless” or “useless”. They do not “suffer” from a disability and are not “victims” of a disability. In addition, persons with disabilities may or may not be a part of a “vulnerable population”, depending on their individual circumstances. Making generalizations regarding persons with disabilities based on stereotypes is wrong, and often serves to perpetuate the charity or medical models of disability. The social model of disability enshrined in the CRPD promotes persons with disabilities as fully deserving, autonomous and independent people.

Often, persons with disabilities will say that they just need “an opportunity to be myself and participate with my peers”. As a young woman from the Philippines will tell you, “value us for who we are and what we can do, not by how we look and what we cannot do”.

When communicating and/or working with persons with disabilities, common sense, sensitivity and basic interpersonal skills should be used. Children asking questions about persons with disabilities is a typical part of development, attitude formation and learning values. Therefore, it is important to teach children (even the very young ones) the most adequate ways of speaking to and about persons with disabilities.

The CRPD promotes the use of person-first terminology when referring to persons with disabilities. Therefore, you should say “a child with a disability” instead of “disabled child” to emphasize the individual as the primary subject. In addition, you should use terminology that is not demeaning and does not carry derogatory or negative meanings. Thus, you should say “child with polio” for example, and not “polio affected child”.

In all cases, be respectful of the person you are talking to or about. When in doubt, ask the person her/himself which is their preference, or ask an Organization of Persons with Disabilities (OPD) in the area. When distinguishing between children with and children without disabilities, do not use the term “normal”.

The following are some basic rules of etiquette to follow throughout the research:

- ASK BEFORE YOU ACT – when in doubt, ask a person with a disability how they would like to be addressed or how you should refer to their impairment or disability;

- Do not speak about a person with a disability as if they are not present, cannot hear you, or cannot understand you;

- In all cases, refer to people by their names – do not describe persons with disabilities as “the little blind girl” or “the man in crutches”;

- Do not talk to adults with disabilities as if they are children and cannot fully understand you or act on their own – even people with communication limitations can understand and take their own decisions;

- Speak from a position that is comfortable to anyone – if needed, sit down or crouch to be at eye level;

- Every person has the right to make their own decisions – if someone uses a wheelchair it may seem easier or faster to decide where/how to go on their behalf. But, making decisions is a right and you should give the opportunity and time needed for independent decision-making;

- Don’t think in terms of stereotypes, thinking that all persons with disabilities are tired, angry, frustrated, depressed, sick or vulnerable. Persons with disabilities are just people with their own individualities; do not attribute their behaviour to their disability;

TREAT PERSONS WITH DISABILITIES THE WAY YOU WOULD LIKE TO BE TREATED – respectfully and attentively, not with pity or paternalism.

[1] Adapted from: UNICEF (2015). Disability Orientation (video). Retrieved from https://www.unicef.org/66434.html

UNESCO (1994) The Salamanca Statement and Framework for Action on Special Needs Education, p.iii, http://www. unesco.org/education/pdf/SALAMA_E.PDF

UNESCO (2005) Guidelines for Inclusion: ensuring access to education for all, Paris.

https://sdgs.un.org/goals/goal4

UNICEF (2015) Conceptualizing Inclusive Education and Contextualizing it within the UNICEF Mission. New York. UNICEF

UNCRPD. (2016). General Comment no4 - Article 24: Right to inclusive education. Committee on the Rights of Persons with Disabilities. United Nations Committee on the Rights of Persons with Disabilities .

https://en.unesco.org/gem-report/report/2020/inclusion

https://en.unesco.org/gem-report/2020-background-papers

UNCRPD. (2016). General Comment no4 - Article 24: Right to inclusive education. Committee on the Rights of Persons with Disabilities. United Nations Committee on the Rights of Persons with Disabilities .

UN General Assembly (2007). Convention on the Rights of Persons with Disabilities. Resolution / adopted by the General Assembly, 24 January 2007, A/RES/61/106.

UN General Assembly, Convention on the Rights of the Child, 20 November 1989, United Nations, Treaty Series, vol. 1577, p. 3,

UNICEF. (2015). UNICEF Procedure for Ethical Standards in Research , Evaluation , Data Collection and Analysis [CF/PD/DRP/2015-001]. Geneva.

IBID