Evaluation Title: Evaluation of the Inclusive Education Programme Model UNICEF is implementing in Public Schools

Region: MENAR

Office: Jordan

Evaluation Year: 2022

Person-In-Charge for Follow-up to Management Response: Gemma Wilson-Clark, Gabrielle Tremblay

Overall Response to the Evaluation:

Management agrees with the overall findings of the evaluation report of a programme that had a significant impact and is aligned with the rights of children and young people. The findings will primarily serve as a tool to advocate for the inclusion rights of all children with disabilities in mainstream education and will support MoE and its main stakeholders in the operationalization of the 10-year National Strategy on Inclusion and Diversity.

The finding that the programme interventions were in line with international best practices and responded to a priority need at the onset of the Syrian crisis was highly appreciated. The fact that the programme cannot be sustained in schools by MOE at the same level of interventions is recognized, noting that the partnership with Mercy Corps was intended to provide direct support to children with disabilities, whilst also building system-level capacity. The Management also takes on board that data collection and management could be strengthened – noting that the programme has already started addressing this challenge by developing additional indicators to capture and update numbers of children supported on a monthly basis, with a focus on tracking children’s progress and retention in the school.

The Management also appreciated that the programme played a crucial contributing role to changing perceptions surrounding students with disabilities, as well as raising awareness and acceptance of children with disabilities while noting the need to further build the capacity of MoE to ensure sustainability. In terms of limitations, the management well noted the lack of institutional memory in every entity involved or concerned with the programme, particularly at the MoE. This is, in addition to the timing of the data collection, which took place after schools were closed for 1.5 years due to Covid-19, undoubtedly affected the respondents’ ability to recall important details.

The Management welcomed the recommendations made on how JCO can move forward and build on what has been achieved to date, specifically in terms of supporting policy dialogue and strengthening the national system to deliver on the strategy in close coordination with MoE and the relevant education partners.

The final evaluation report is of high quality and will inform greatly the future design of Inclusive Education in Jordan. Recommendations are practical and actionable.

Planned Use of Evaluation:

The findings from the evaluation report will inform future programming in support of the operationalization of the 10-year Inclusive Education Strategy, in light of the recently developed road map which outlines actions that need to be put in place to advance the agenda of inclusion and diversity in Jordan.

The evaluation report was shared with MoE and the relevant stakeholders, mainly UNESCO, GIZ, HCD (Higher Council for the Rights of Persons with Disabilities and Mercy Corps to ensure common understating and complementarity of efforts towards more inclusion in Jordan.

The findings and the recommendations will also be presented to all office staff with the purpose of engaging colleagues in discussions on how we can better mainstream inclusion across our programming in line with the new developed CPD (2023-2027),

Similarly, the findings were discussed with the implementing partner, Mercy Corpos,based on which certain activities in the new programme document  were amended to ensure increased effectiveness and efficiency and further capacity building of MoE staff at the school level for sustainability purposes.

The report was also shared with the Regional Disability Specialist prior to her visit to Jordan to help build a comprehensive overview of JCO’s work on inclusion and how best to move forward with the relationships established to date with the Ministry of Education, the Higher Council for the Rights of Persons with Disabilities and the relevant stakeholders.

UNICEF Evaluation Management Response

| UNICEF Evaluation Management Response Template |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| RECOMMENDATIONS and ACTIONS: |  |  |  |  |  |  |
| Evaluation Recommendation 1: Strengthen IE data organisation- better documentation on enrolment and retention, including monitoring of attendance and progress. This data should be centrally recorded and updated- based on a consistent definition- in the Open EMIS and on which all partners rely in their decision-making. |  |  |  |  |  |  |
| Management Response: Agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| As a member of the Ministry of Education Task Force on Inclusive Education, UNICEF will work to ensure that MoE prioritizes data collection and management in collaboration with the Higher Council for the Rights of Persons with Disabilities (HCD) and partners. To note that UNESCO as the national partner on Open EMIS is the lead partner on strengthening inclusiveness of MOE data through current program of technical assistance. The Context: Improving data collection and monitoring on Open EMIS is one of the priority recommendations of the 10-year National Strategy. | UNICEF Education | Gemma Wilson-Clark | 31/12/2023 | Not started |  |  |
| Evaluation Recommendation2: Institutionalize the investments made under the IE Programme such as the approval and systemic utilisation of the programme developed manuals, awareness raising kits, and Standard Operating Procedures (SOP’s) pertaining to IE including the development and implementation of the IEP’s. Additionally, advocating toward institutionalising the “shadow teacher” job description and capacity building (pre-service as well as in-service). |  |  |  |  |  |  |
| Management Response: Agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| Through its participation in the Task Force on Inclusive Education, UNICEF will leverage on its renewed partnership with the implementing partner to have the IE Operational Guidelines and the training manual reviewed and endorsed by MoE as well as advocate for the deployment of Assistant Teachers (shadow teacher). | UNICEF Education | Gemma Wilson-Clark | 30/06/2023 | Underway |  |  |
| Evaluation Recommendation 3: Require stronger project management and monitoring and evaluation functions and processes to ensure consistent and reliable data to inform programme decisions and continuous learning and improvement. |  |  |  |  |  |  |
| Management Response: Agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| For stronger project management purposes, UNICEF will ensure that the Monitoring Officer monitors progress against the agreed indicators by reviewing monthly and quarterly reports and coordinating directly with the Implementing Partner Manager on any challenges, making sure that data is properly collected, documented and analysed and used for better project implementation and planning. This will include use of data to inform and report on inclusion of children with disabilities by school and Directorates. | UNICEF Education | Gemma Wilson-Clark | 31/12/2023 | Not started | Partner supported Assistant Teachers will also meet quarterly with the lead teacher in each school to systematically review and record progress against student’s Individual Education Plans |  |
| Evaluation Recommendation 4: Refine the capacity building efforts through: a) More tailored trainings should be developed and delivered to ALL relevant MoE staff (at central, Field directorates and school levels) in order to equip them with the necessary knowledge, skills and attitudes to feel confident serving ALL students. b) a larger number of teachers need to be trained toward proper and effective inclusion of all students (including those with disabilities) in the classroom- moving away from the reliance on resource rooms and resource teachers. |  |  |  |  |  |  |
| Management Response: Partially agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: UNICEF is one of several agencies supporting MOE on Inclusive Education and more specifically on teacher professional development in inclusive education. Partners such as GIZ, UNESCO and FCDO have funds allocated to support the operationalization of the National Inclusive Eductaion Strategy, including building the capacity of teachers on including children in mainstream education. UNICEF is only directly supporting training of teachers in refugee camps and therefore can only take responsibility for this subsect of teachers trainings. |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| UNICEF will support through our implementing partner the delivery of the inclusive education training to Assistant Teachers, in the camp schools to help them develop the necessary knowledge, skills and attitudes ensure all children are included and are provided with the needed support. | UNICEF Education | Gemma Wilson-Clark | 31/12/2023 | Not started |  |  |
| Evaluation Recommendation 5: Develop a mechanism through which teachers, parents and other professionals work collaboratively on the development and implementation of Individual Education Plans (IEP’s) for students with disabilities. |  |  |  |  |  |  |
| Management Response: Agree with UNICEF responsible for developing this mechanism in the camp schools, not nationwide. |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| UNICEF will deploy Assistant Teachers in camps schools, who will be working collaboratively with MoE teachers on the development of IEPs, as well as on following up with parents on progress achieved against objectives set in these IEPs for children in the camp. | UNICEF Education | Gemma Wilson-Clark | 30/06/2023 | Not started |  |  |
| Evaluation Recommendation 6: Systemize the awareness raising interventions: materials and sessions for awareness raising need to reach all schools. Awareness raising should focus on recognising the abilities and strengths of children with disabilities beyond acceptance. |  |  |  |  |  |  |
| Management Response: Agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |
| Actions plan ned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| UNICEF will review the materials and coordinate with the Implementing Partner on having them adapted to also focus on highlighting the abilities of CWDs beyond acceptance. These awareness raising materials are also included in the MOE Operational Guidelines, which once endorsed, will be disseminated at a national level by MoE. | UNICEF Education | Gemma Wilson-Clark | 31/12/2023 | Not started |  |  |
| Evaluation Recommendation 7: Develop a comprehensive list of assistive technology and devices (with specifications) so that schools are instructed and can procure the needed resources in order to accommodate any and all disabilities. |  |  |  |  |  |  |
| Management Response: Partially Agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: Partially accepted as it is unlikely that schools can afford equipment for any and all disabilities. |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| UNICEF will advocate for MOH and MOSD to strengthen school level referrals and support for assistive devices for children with disabilities, within the framework of the 10-year National Strategy. MoE, though its partnership with MoH will ensure that all children will receive the equipment required to accommodate their disabilities. UNICEF will provide guidance to MoE in developing a comprehensive list of assistive technology and devices based on the schools identified needs. | UNICEF Education | Gemma Wilson-Clark | 31/12/2023 | Not started |  |  |
| Evaluation Recommendation 8: Mobilise existing structures (such as the SDDP school or directorate level committees) toward leveraging comprehensive and sustainable resources and services to students with disabilities (including but not limited to physical infrastructure improvement for accessibility, rehabilitation sessions and psycho-social support). |  |  |  |  |  |  |
| Management Response: Agree |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| UNICEF will pilot the implementation of the Effective Leadership Framework, expected to be launched with the start of the new academic year 2022/2023. The framework builds on existing structures, mainly SDDP, and covers three main areas: Administration, Teaching and Learning as well as Inclusion and Well-being, with the latter addressing inclusion-related matters at the school and directorate levels. | UNICEF Education | Gemma Wilson-Clark | 31/12/2023 | Not started |  |  |