JOINT EVALUATION OF THE UNFPA-UNICEF JOINT PROGRAMME ON THE ABANDONMENT OF FEMALE GENITAL MUTILATION: ACCELERATING CHANGE

PHASE III: 2018-2021

# Terms of Reference

Secondary bidding: lot 2 – UNFPA long term agreement for the supply of evaluation services in the thematic areas of female genital mutilation and gender equality

Evaluation Offices

August 2020

2020

Contents

Acronyms	2

1.	Introduction	3

2.	Users of the evaluation	3

3.	Global context and UNFPA and UNICEF support to the abandonment of FGM	3

3.1	Global context of FGM	3

3.2	Global normative framework	4

3.3	UNFPA and UNICEF Strategic Framework	5

3.4	UNFPA and UNICEF Joint Programme on FGM: Accelerating Change	6

3.4.1 Phase I and II (2008-2017)	6

3.4.1	Phase III (2018-2021)	7

3.4.2	Governance of the Joint Programme	11

4.	Evaluation purpose, objectives and scope	12

5.	Evaluation approach and methodology	13

5.1	Evaluation criteria and indicative areas for investigation	14

5.2	Methods for data collection	16

5.3	Methods for data analysis	17

6.	Evaluation process	18

6.1	Inception phase	18

6.2	Data collection (remote)	18

6.3	Reporting phase	18

7.	Indicative time schedule	19

8.	Management and governance of the evaluation	20

9.	The evaluation team	21

10.	Quality assurance and assessment	25

11.	Cost of the evaluation and payment modalities	25

12.	Bidding instructions for the preparation of the technical offer for this evaluation,	26

●	Annexes of the Terms of reference	28

o	Annex 1: Evaluation Matrix (template)	28

o	28

Annex 2: Structure for the evaluation report	29

Annex 3: Editing guidelines	31

Annex 4: Evolution of the results frameworks	32

Annex 5: Code of conduct and norms for evaluation in the UN system	34

Annex 6: Governance and management note	35

| # Acronyms |  |
| --- | --- |
| CO | Country office |
| CEDAW | Convention on the Elimination of All Forms of Discrimination Against Women |
| EO FGM | Evaluation Office Female Genital Mutilation |
| HIV/AIDS | Human immunodeficiency virus/ Acquired immunodeficiency syndrome |
| ICPD | International Conference on Population and Development |
| OECD-DAC | Organisation for Economic Co-operation and Development/Development Assistance Committee |
| RO | Regional Office |
| TOR | Terms of Reference |
| UNEG | United Nations Evaluation Group |
| UNICEF | United Nations Children’s Fund |
| UNFPA UN | United Nations Population Fund United Nations |

# Introduction

The Evaluation Offices of United Nations Population Fund (UNFPA - lead agency) and the United Nations Children’s Fund (UNICEF) will jointly conduct an independent evaluation of Phase III of the UNFPA/UNICEF joint programme on the abandonment of Female Genital Mutilation (FGM).

In September 2017, the Director of the UNFPA Evaluation Office presented to the UNFPA and UNICEF Joint Programme Steering Committee two options for the evaluation of Phase III: option I: focus on accountability (summative Evaluation); option II: focus on learning (formative evaluation). The Steering Committee passed a decision in favour of a formative evaluation. The formative evaluation is planned to commence in the fourth quarter of 2020.

An external, multidisciplinary team comprised of evaluation and thematic experts, will support the UNFPA and UNICEF Evaluation Offices carrying out the evaluation. The selected evaluation team is expected to conduct the evaluation in conformity with the present terms of reference and under the overall leadership from the lead evaluation manager.

Due to the impact of the current global COVID19 pandemic and travel restrictions that derive from it, the evaluation will not include in-country missions and will base its methodological approach on document review and analysis and remote interviews with global, regional and country-level stakeholders.

# Users of the evaluation

The main users of the evaluation include staff members of the joint programme at UNFPA and UNICEF at the global, regional and country level; partner country governments; donors; civil society, including non-governmental organizations, feminists and women’s rights activists; and gender equality advocates. In particular, the evaluation will provide useful information to the managers and the steering committee of the UNFPA/UNICEF joint programme.

As the joint programme moves into its last year of implementation of phase III, it will seek to build on the lessons learned from the implementation of the current phase, whereby this evaluation will play a critical role in its realization. Hence, it is expected that the evaluation will provide useful lessons and recommendations that will feed into the design of a potential fourth phase of the Programme.

# Global context and UNFPA and UNICEF support to the abandonment of FGM

## Global context of FGM

Globally, it is estimated at least 200 million girls and women have undergone some form of FGM in 31 countries. FGM refers to all procedures involving the partial or total removal of the external female genitalia or other injury to the female genital organs for cultural or other non-medical reasons. The age at which FGM is performed varies. In some communities it is carried out during infancy, while in others it may occur during childhood, at the time of marriage, during a woman's first pregnancy or after the birth of her first child. The most typical age is 7 to 10 years old or just before puberty, although reports suggest that the age is dropping in some areas.

FGM has both immediate and long-term consequences to the health and wellbeing of girls and women, negatively impacts maternal and neonatal outcomes, and also increases the risk of HIV/AIDS transmission. FGM also has negative economic consequences, due in part to the financial cost of healthcare for women living with conditions caused by the practice. The total cost amounts to USD 1.4 billion annually.

In the 30 countries with nationally representative FGM prevalence data, around one in three girls aged 15–19 today have undergone the practice. In the last three decades, some countries have seen a decline in overall prevalence, even in countries with high levels of FGM prevalence. Progress, however, is uneven, and the pace of decline is insufficient to keep up with population growth: an estimated 4.6 million girls annually, or a total of 68 million girls, will be at risk of FGM between now and 2030. However, opposition to the practice is also growing, particularly among adolescent girls: in high-prevalence countries, where over 50 percent of girls and women have undergone FGM, over 60 percent of girls aged 15-19 years have heard of FGM and think the practice should stop. In addition, in 12 out of 19 countries with data on the attitudes of boys and men, more than 50 percent of those surveyed think the practice should stop.

## Global normative framework

Female genital mutilation is internationally recognized as a harmful practice often resulting in serious injury, disability and death. It is also a violation of the rights of women and girls to bodily integrity and freedom from injury and coercion. There is a growing awareness of the profound challenges of addressing the complex, context responsive, and enduring set of drivers which sustain the practice of FGM. Efforts to end FGM have increasingly been framed within the wider agenda of addressing gender equality and fostering gender transformative strategies.

The first international instrument explicitly addressing violence and other harmful practices against women, with specific reference to female genital mutilation and other harmful practices, was the Declaration on the Elimination of Violence against Women (1993). The Africa region has been at the forefront of the global normative efforts reflected in the signing in 2003 by most of the countries in the African Union to “The Protocol to the African Charter on Human and Peoples’ Rights on the Rights of Women in Africa”, known as the Maputo Protocol, which includes an article on the Elimination of Harmful Practices, calling for the prohibition of all forms of female genital mutilation. Subsequent statements and resolutions from UN entities and member states have led to the United Nations General Assembly adopting a Resolution to ban female genital mutilation worldwide in 2012. The Resolution [A/RES/67/146] was cosponsored by two thirds of the General Assembly, including the entire African Group, and was adopted by consensus by all UN members. Ensuing resolutions have called for the intensification of efforts for the elimination of FGM.

The elimination of violence against women has been taken up by the 2030 Agenda for Sustainable Development. Violence against women is addressed explicitly in Goal 5, Target 5.3, which calls for the elimination of harmful practices, such as “child, early and forced marriage and female genital mutilation”, by 2030.

At the 2019 Nairobi Summit on ICPD25, representatives from governments, grassroots organizations, development agencies and the private sector moved beyond pledges and resolutions, and committed to ending harmful practices. By June 2020, participants had made a total of 226 commitments towards addressing gender-based violence and harmful practices, including ending female genital mutilation.

## UNFPA and UNICEF Strategic Framework

Putting an end to gender-based violence and all harmful practices, including female genital mutilation, is one of the three transformative and people-centered results that UNFPA has put at the center of its strategic plan for 2018-2021. UNFPA targets the elimination of FGM in two of the four outcomes of the strategic plan. In Outcome 2, the Strategic Plan recognizes that a focus on girls during early adolescence is critical to stop harmful practices that directly threaten the human rights, health and wellbeing of girls and aims to promote youth-oriented, multisectoral policies and programmes to address issues affecting young girls. In Outcome 3, prevention and response to gender-based violence, and the elimination of harmful practices, are at the basis of UNFPA’s strategic approach to support gender equality and the empowerment of women, which includes strengthening policy, legal and accountability frameworks. Under Outcome 3, UNFPA’s Strategic Plan recognizes that work on eliminating harmful practices is built on Joint Programmes, including with UNICEF to address FGM.

FGM is also recognized in UNICEF’s 2018-2021 Strategic Plan as a harmful practice that undermines children’s safety and well-being. The strategic plan’s Goal Area 3 is based on the premise that every child has the right to be protected from violence, exploitation and abuse. In the Results Framework of the strategic plan, UNICEF tracks progress on addressing harmful practices through several indicators, counting the prevalence of FGM (Impact indicator), and measuring progress in strengthening prevention and protection services through UNICEF-supported programmes (outcome indicators).

UNFPA’s strategic focus on FGM is further illustrated by the theme of its annual flagship report, the State of World Population, which in 2020 addressed different forms of harmful practices that affect women and young girls. In a specific section on FGM, the report provides an overview of the global context for this harmful practice, gives voice to survivors, and analyses its root causes. The report also gives an updated overview of prevalence rates across the world.

## UNFPA and UNICEF Joint Programme on FGM: Accelerating Change

In 2007, UNFPA organised a Global Consultation on FGM which led to the creation of the UNFPA - UNICEF Joint Programme on Eliminating Female Genital Mutilation. Since its launch, the joint programme has given greater prominence to the issue, mobilized substantial additional resources, and provided new impetus to the global movement to end the practice.

The Joint Programme is the world’s largest and most comprehensive effort seeking to eliminate FGM, and plays an important role in achieving Sustainable Development Goal 5, Target 5.3.

### 3.4.1 Phase I and II (2008-2017)

The first phase of the Joint Programme was implemented from 2008 to 2013. It began operating in 8 countries, but by the conclusion of the first phase, the joint programme was operating in 15 countries. The objective of the first phase of the joint programme was “to contribute to a 40 percent reduction of the practice among girls aged 0-15 years, with at least one country declared free of FGM/C by 2012”. The total expenditures of the JP between 2008 and 2013 amounted to 31.6 million USD.

In 2013, a joint evaluation of the first phase concluded that the Joint Programme showed significant strengths and results of the first phase were overall positive, albeit with varying degrees of progress in strengthening countries’ legal and policy frameworks, raising awareness and knowledge of FGM by key actors and the general public, and increasing commitments by community leaders towards the abandonment of FGM. The evaluation led the Joint Programme to increase its focus on social norms work and strengthen monitoring systems and tools, capacities and resources available for longer-term data collection and analysis.

Phase II of the Joint Programme began in 2014 and ended in 2017. The objective of the programme was revised from Phase I, to “contribute to the acceleration of the total abandonment of FGM in the next generation (i.e. next 20 years) through a 40% decrease in prevalence among girls 0-14 years in at least 5 countries and at least one country declaring total abandonment by the end of 2017”. The operation of the programme was expanded to 17 countries, with the addition in 2014 of Nigeria and Yemen. In four years of implementation, the reported total expenditures of the Joint Programme were 60.3 million USD, close to double that of Phase I.

The 2019 evaluation of Phase I and Phase II found that the Joint Programme had contributed to notable achievements, including at the global level by ensuring a continued presence of FGM on the international development agenda, and by strengthening legal frameworks and coordination at the national level. It also emphasized on the long-term investments needed for social norms changes that support FGM abandonment. The evaluation recommended that the Joint Programme place itself strategically within a gender-responsive framework to support a wider transformative agenda, using long-term approaches that strengthen systems and encourage long-term changes and national ownership.

The evolution of the results framework across phase 1, 2 and 3, including changes in outcomes and outputs, is presented in annex 4.

### Phase III (2018-2021)

Phase III of the Joint Programme on Female Genital Mutilation covers the years 2018 to 2021 and takes a holistic and comprehensive approach to creating an enabling environment through policy and legislation, supporting access to comprehensive services, and empowering communities to drive social change. Recognizing the interlinkages between its areas of interventions, Phase III is built around interventions targeting accountability mechanisms for governments’ obligations to eliminate FGM (Outcome 1), and interventions that support the rights, needs and agency of girls and women, while expanding engagement of men and boys in promoting and achieving gender equality (Outcome 2), also targeting service provision for FGM prevention, protection and care, including access to technical expertise and legal representation (Outcome 3). Phase III also focuses on capturing good practices and lessons learned for effective knowledge sharing and learning, as well as developing mechanisms to measure changes in social norms and create an evidence base for scaling up effective interventions to end FGM (Outcome 4). Table 1 presents the resource allocation by outcome areas.

With the key goal of challenging and changing social norms, the Joint Programme’s approach consists of community dialogues and human rights education, reaching commitments to FGM abandonment through organized diffusion of knowledge to larger portions of the community, and to other communities and localities. This approach relies on support in the four outcome areas and on the engagement of community leaders, religious leaders and youth, including using innovative tools and social media for knowledge sharing mechanisms.

Strategic partnerships of the Joint programme include UN Women and WHO at the global level, with additional partnerships with key global players on innovation, data generation and advocacy. At the regional level, the JP continues to support and engage with the African Union Commission, the League of Arab States, the Organization of Islamic Cooperation and other relevant sub-regional political and economical structures. Country-level partnerships focus on work with sectoral ministries and government coordination bodies. Finally, at the local level the Joint Programme partners with local actors and stakeholders to engage with girls, women and communities.

Table 1: Joint Programme Phase III - Resource allocation by outcome areas (USD)

| JP Outcome | Resource allocation 2018-2021 | % of total allocation |
| --- | --- | --- |
| Outcome 1: Countries have an enabling environment for the elimination of FGM practices at all levels and in line with human right standards. | 18,346,768 | 24% |
| Outcome 2: Girls and women are empowered to exercise and express their rights by transforming social and gender norms in communities to eliminate FGM. | 44,338,022 | 58% |
| Outcome 3: Girls and women have access to appropriate, quality and systemic services for FGM prevention, protection and care. | 9,937,833 | 13% |
| Outcome 4: Countries have better capacity to generate and use evidence and data for policy-making and improving programming. | 3,822,243 | 5% |

Source:  Programme Proposal for Phase III of the UNFPA-UNICEF joint programme Elimination of Female Genital Mutilation: Accelerating Change, page 46

The planned distribution of funds by outcome reflects that of the implemented previous phases, as found by the joint evaluation of Phases I and II, where 56% of expenditures were allocated to the “Accepting the norm of eliminating FGM” outcome, while 26% were spent on activities related to legal and policy frameworks and 18% to service provision. For the first year of implementation of Phase III, the 2018 Annual report of the Joint Programme presents a more equal distribution of expenditures between outcomes 1 and 2, with 36% allocated to each. However, the report notes that investment levels will be higher in Outcome 2, starting from 2019, as this Outcome area represents the primary focus of the programme’s approach.

Figure 1: 2018 and 2019 Budget and expenditures by implementation level (USD)

Source: UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation – Annual Report 2018 - page 107, and Annual Report 2019 - page 68

Figure 2: Budget and Expenditure, 2018-2019 (USD)

Source: UNFPA – UNICEF Joint Programme data

For the period 2018-19, the total expenditures of the Joint Programme amounted to $ 27,765,195, while the total budgeted amount was $33,218,893. Complete financial data for 2020 is not yet available.

Table 2: Budget and Expenditures by Country (2018-2019)

| COUNTRY OFFICES | 2018 BUDGET (USD) | 2018 EXPENDITURE (USD) | 2019 BUDGET (USD) | 2019 EXPENDITURE (USD) |
| --- | --- | --- | --- | --- |
| Burkina Faso | 1,000,000 | 888,459 | 1,200,000 | 1,157,015 |
| Djibouti | 400,000 | 259,467 | 700,000 | 636,962 |
| Egypt | 800,000 | 593,871 | 1,500,000 | 1,328,419 |
| Eritrea |  |  | 418,057 | 309,322 |
| Ethiopia | 1,000,000 | 838,908 | 1,313,282 | 1,217,406 |
| Gambia |  |  | 721,400 | 515,704 |
| Guinea |  |  | 865,259 | 810,277 |
| Guinea-Bissau |  |  | 401,751 | 386,650 |
| Kenya | 1,042,184 | 1,032,611 | 2,026,350 | 1,793,612 |
| Mali |  |  | 500,000 | 464,831 |
| Mauritania |  |  | 700,000 | 653,550 |
| Nigeria | 1,038,635 | 1,035,677 | 1,200,000 | 1,012,277 |
| Senegal | 1,000,000 | 749,089 | 1,200,000 | 856,865 |
| Somalia |  |  | 500,000 | 480,333 |
| Sudan | 642,800 | 473,431 | 1,000,000 | 782,833 |
| Uganda |  |  | 500,000 | 498,499 |
| Total country level | 11,806,482 | 10,200,949 | 14,746,099 | 12,904,554 |

Source: UNFPA – UNICEF Joint Programme data

Phase III of the Joint Programme is supported by a range of donors, including Austria, the European Union, France, Iceland, Italy, Luxembourg, Norway, Spain, Sweden and the United Kingdom. For the years 2008 to 2017, contributions from the three largest donors (Norway, the United Kingdom and Italy) represented over 72% of the total contribution. While the consistency of support from key donors is an indication of confidence in the Joint Programme, the Proposal for Phase III also recognizes that expanding the donor base is necessary to mitigate certain financial risks.

Donor contributions to the joint programme received in 2019 ($25.7m) are significantly higher than in 2018 ($14.3m), mainly due to the increase of funds from Norway and Sweden, and the addition of Austria and France to the donor pool.

Table 3: Joint Programme Phase III - Donor funds (USD)

| Donor | 2018 | 2019 |
| --- | --- | --- |
| Austria |  | 1,111,111 |
| France |  | 148,515 |
| Iceland | 200,000 | 200,000 |
| Italy | 2,122,642 | 1,969,365 |
| Luxemburg | 119,474 | 109,890 |
| Norway | 2,927,058 | 10,899,183 |
| Spain | 455,063 | 550,055 |
| Sweden | 8,243,570 | 10,463,304 |
| United Kingdom | 319,285 | 327,225 |
| Total | 14,387,091 | 25,778,648 |

Source: UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation –  2018 and 2019 Annual Reports

Figure 3: Geographic coverage of the Joint Programme

The Programme works in 17 countries. They are divided into three tiers according to needs and priorities.  The tier system represents the Programme’s approach for prioritizing investments and interventions, built on the underlying principles of the 2030 Agenda.

Source: UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation – Annual Report 2018

Since early 2020, the Joint Programme supports the development of preparedness and response plans addressing the impact of the COVID-19 pandemic on girls and women at risk of and affected by female genital mutilation.  A Technical Note published by the Joint Programme highlights the critical importance of understanding how the pandemic increases girls’ and women’s vulnerability and marginalization, while also recognizing some potential opportunities presented by the pandemic in ending FGM. Overall, restricted movement and confinement due to the pandemic can limit access to prevention, protection and care services for girls at risk of and affected by female genital mutilation, especially in hard-to-reach areas. This situation will disrupt meeting the SDGs, including SDG Target 5.3, for the elimination of female genital mutilation by 2030, and calls for integrated FGM risk mitigation and response within GBV and child protection COVID-19 preparedness and response plans.

### Governance of the Joint Programme

UNFPA and UNICEF co-manage at global, regional and country levels with overall governance by a Joint Programme steering committee.  This committee meets at least twice a year and is composed of donors that are contributing to the joint programme as well as members of the joint programme of both UNFPA and UNICEF.

The role of the Joint Programme Steering Committee is to:

- Facilitate the effective and efficient collaboration between participating UN Agencies and donors for the implementation of the joint programme;

- Review and approve  the  Joint  Programme  Document and any subsequent revisions;

- Approve the consolidated joint work plan and consolidated budget on an annual basis;

- Instruct the Administrative Agent (UNFPA) to disburse funds, as per the approved budget;

- Review the implementation of the Joint Programme;

- Review and approve consolidated financial and narrative reports;

- Review evaluation findings for appropriate communication and future planning;

- Support advocacy and resource mobilization efforts.

Overall technical and management oversight is provided by a coordination team, led by a programme coordinator of each agency at their headquarter offices. The responsibilities of the coordination team include administration and financial management, partnership, knowledge management of the joint programme, encompassing the production of annual reports, conference reports, brochures, dissemination of relevant material to regional, sub-regional and country offices; capacity development and technical assistance to regional and country offices. Activities are undertaken in collaboration with relevant units within the respective organization, including the UNICEF Programme Division (especially the Child Protection and Communications for Development (C4D) Sections), the UNICEF Division of Data, Analytics, Planning & Monitoring (DAPM), and the UNFPA Gender and Human Rights Branch and the Population and Development Branch.

In the programme countries, UNFPA and UNICEF Country Representatives develop a plan of action in line which serves as the basis for budget allocations. Approval of country-specific allocations is done by the Joint Programme Steering Committee based on consolidated UNFPA and UNICEF work plans agreed at country level and based on fund availability. Similarly, in Regional Offices where the programme operates, UNFPA and UNICEF offices also develop a plan of action to support sub-regional and country efforts. The Joint Programme continues to use the pass-through fund management mechanism, whereby UNFPA continues to be the Administrative Agent (AA).

# Evaluation purpose, objectives and scope

The joint evaluation will be forward-looking and strategic in nature and will aim to inform a planned phase IV of the Joint Programme including the strategic direction, gaps and opportunities for UNFPA and UNICEF joint programme in addressing gender and social norms change. It will provide an opportunity to produce evaluative evidence on the joint programme’s performance in achieving results, to support evidence-based decision-making, and to contribute to the learning and sharing of good practice. Finally, the evaluation will also provide input to inform the strategic positioning of UNFPA and UNICEF joint programme within a gender-responsive agenda, reflecting the changing environment and alignment with the 2030 development agenda.

The primary objectives of the evaluation are:

- To assess the relevance (including gender responsiveness), coherence, effectiveness and sustainability of the UNFPA/UNICEF Joint Programme support to accelerate FGM abandonment in the programme countries and provide recommendations on how to further accelerate progress in ending FGM;

- To identify lessons learned and generate knowledge from phase III, to inform the design of phase IV; including identifying what packages of strategies and interventions to continue and/or discontinue and in what context, and providing corrective actions on the gaps and opportunities.

- To assess the extent to which UNFPA and UNICEF, through the Joint Programme, have effectively positioned themselves as key players, including at regional level, in contributing to the broader 2030 development agenda, in particular Goal 5, Target 5.3 relating to FGM.

Scope

Temporal scope - The evaluation will cover the implementation and the results of the UNFPA/UNICEF joint programme support during the period 2018-2021 (May) with particular emphasis on the 3 first years.

An evaluation of Phase I and II of the joint programme was finalized in 2019, initially covering the implementation of the joint programme from 2008 to 2017. As the evaluation started in 2018 and data collection continued until January 2019, the scope of the evaluation was expanded to include results from the first year of Phase III.  In this sense, the present evaluation of Phase III will build on results from the previous evaluation and will carefully review and follow-up the implementation of the 2019 evaluation recommendations.

Thematic scope – given the results of the previous evaluation and the focus of phase III on the gender transformative aspects of the joint programme the evaluation will focus on the following aspects:

- Gender transformative element: the extent to which the Joint Programme has integrated a gender responsive approach;

- Regional level support: assess the benefit of having regional offices supporting country offices and contributing to building a conducive environment to accelerate the abandonment of FGM in the 3 regions;

- Response to Covid 19: the extent to which the Joint Programme has timely responded to the pandemic.

Its scope will focus on the more explicit gender-responsive approaches taken by the Joint Programme in Phase III, as well as the strategic placement of the Joint Programme within a gender-responsive framework. To this end, findings, conclusions and recommendations from evaluations on Gender-Based Violence and harmful practices (2018) and Gender Equality and Women’s Empowerment (2021) conducted by UNFPA, as well as, the Gender equality evaluation conducted (2019) by UNICEF, will also be used as building blocks for the evaluation.

Geographic scope: while the evaluation will cover 3 programme levels – global, regional and national – and their interconnections, attention will be paid particularly to the programme’s regional level positioning, including its partnership with the African Union and other regional bodies. The evaluation scope will not explicitly cover the sub-national level/community level.

# Evaluation approach and methodology

The evaluation will be both backward-looking to review the performance of the joint programme (phase III) as well as forward-looking to identify lessons learned to inform the design of phase IV.  The evaluation will apply an adaptive learning and utilisation-focused approach. This approach calls for a hybrid exercise comprising of a backward-looking assessing phase III programme contribution to outputs and outcomes at global, regional and country level, as well as, a learning-focused, forward-looking providing real time insights for the design of phase IV.

## Evaluation criteria and indicative areas for investigation

The proposed evaluation criteria are selected from the 2019 Organisation for Economic Co-operation and Development/Development Assistance Committee (OECD/DAC) criteria, as defined below:

| Relevance | to national needs, the needs of affected populations, government priorities and UNFPA and UNICEF policies and strategies, and how they address different and changing national contexts |
| --- | --- |
| Coherence | Joint Programme’s consistency and synergies with national and partner FGM interventions |
| Effectiveness | the extent to which Joint Programme’s intended results (contribution to outputs and progress towards outcomes) were achieved (or are likely to be achieved) |
| Sustainability | the extent to which the benefits from the joint programme are likely to continue, after it has been completed |

To narrow down the scope of the evaluation, efficiency and coordination are not explicitly considered as criteria in this evaluation – although some of their dimensions may be assessed through other criteria.

The evaluation criteria have been translated into areas of inquiry (see table 4). These will be used as a starting point for developing the specific set of evaluation questions, assumptions and respective indicators. The indicative areas for investigation are intended to give a more precise form to the evaluation criteria and to articulate the key areas of interest that have emerged from document review as well as from consultations with key stakeholders, thereby optimizing utility of the evaluation.

The indicative areas of inquiry will be further consolidated and refined within the inception report (when the evaluation team will have a clearer understanding of data availability and methodological feasibility and evaluability). Following broader consultations and detailed documentary review, final evaluation questions will be agreed upon by the evaluation reference group. The evaluation questions will be integrated into an evaluation matrix. The matrix is intended as a framework for the collection and analysis of data as well as reporting. The evaluation matrix shall present the evaluation questions and break them down into assumptions, indicators associated to these assumptions, sources and tools for data collection. The column on sources of information should link the evaluation questions with the stakeholder mapping and pave the way for the production of the interview protocols per type of stakeholder, the tool that links the evaluation matrix with data collection (see annex 1- Evaluation Matrix template).

| Table 4. Indicative areas of inquiry (Evaluation Questions) | Evaluation criteria |
| --- | --- |
| 1 - The extent to which the Joint Programme phase III support is aligned with and responds to: (i) partner government priorities, national needs and the needs of affected populations; (ii) global priorities (SDG, GA, HR Council Resolutions, African Union and other regional bodies commitments); and (iii) UNFPA and UNICEF policies and strategies in line with human rights standards: - supporting girls and women receiving appropriate, quality and systemic services for FGM prevention, protection and care. | Relevance |
| 2 - The extent to which the Joint Programme phase III is gender responsive to contribute to accelerating the abandonment of FGM at the national level, including cross-border regions: - Integrating a systemic perspective including institutional and political dimensions of gender transformative approach; - Integrating community engagement approaches including use of innovative tools and digital platforms (in addition to mechanisms to ensure feedback on quality and accessibility of approaches and services, enabling of scale up of gender responsive and transformative issues). |  |
| 3 - How well the joint programme created linkages with other streams of work (such as: child marriage and GBV) to create opportunities for empowering girls and women; how well the programme is strengthening systems to provide linkages and referrals to girls and women for services including leveraging on resources | Coherence |
| 4 - The extent to which the Joint Programme has effectively partnered with regional intergovernmental organizations, CSOs including community-based organization to create mechanisms for holding governments (at national and sub national levels) accountable for meeting their obligations to eliminate FGM: - strengthening regional accountability mechanisms for ensuring increased national commitment to end FGM - accountability should include developing and implementing evidence-based policy and legislative framework | Effectiveness |
| 5 - The extent to which the Joint Programme has contributed to strengthening national policies and legislative frameworks on the elimination of FGM through integration of evidence-based analysis on FGM emerging issues namely: - rising trends on the medicalization of FGM (performed by a health-care provider) - cross-border FGM (girls and women undergo FGM in neighbouring countries to avoid prosecution at home). | Effectiveness and Sustainability |
| 6 - The extent to which the Joint Programme has contributed (or is likely to contribute) to the acceptance of a new social norm to keep girls intact in targeted populations, through: - Strengthening the rights, needs and agency of girls and women; - Expanding the engagement of men and boys in promoting and achieving gender equality and the elimination of FGM; - Creating opportunities for young people to proactively engage with governments to inform FGM policies and programmes. |  |
| 7 - The extent to which the Joint Programme phase III has put in place a space, across countries and regions, for knowledge sharing and learning including on: - Identifying field-level key contextual factors relevant to accelerate FGM abandonment - Measuring changes in social norms and gender norms transformation. | Effectiveness |
| 8 - The extent to which the Joint Programme phase III has responded and adapted programming to respond to challenges resulting from humanitarian crisis including during the COVID-19 pandemic, comprising reduced access to services and support. - Implementing an adaptive approach in times of crisis (active conflict, natural disaster including during the recent pandemic). - Integrating FGM risk mitigation and response within GBV and child protection COVID-19 preparedness and response plans | Effectiveness |

## Methods for data collection

UNFPA and UNICEF draw attention to the uncertainty of the COVID-19 pandemic and evolving of the response at global, regional and national levels. The implementation of the evaluation should minimize its potential impact on the overall national health response to COVID-19. Furthermore, in view of the evolution of COVID-19 response worldwide, national response, measures and relevant restriction in border control and physical distancing must be respected and taken into account, as UNFPA and UNICEF are placing priority on health and wellbeing of its personnel, including external consultants data collection will be conducted remotely (unless the security situation changes).

Data will be collected using both qualitative and quantitative methods. For each evaluation question, there are at least three different methods from which information will be collected, namely:

- Document/ data review constitutes one of the most important data sources for the evaluation which includes:

- Structured review of strategic and planning documents, progress reports, monitoring data, financial data, reviews and evaluations, research on FGM and other relevant reports and existing quantitative data sources at country, regional and global levels.

- Relevant websites and social media platforms (e.g. covid 19 and FGM; global and regional advocacy campaigns on FGM abandonment and social and gender norms change). One option is to consider is using social media analytics to capture sentiment trends (in programme countries with high social media penetration). Examples of tools are: Crimson Hexagon; python or other tools.

- Semi-structured (remote) key informant interviews and group discussions will be undertaken at:

  - country (16 programme countries – implementing partners, government partners, CSOs and academia, other UN agencies and donors among other key stakeholders and partners, including stakeholders who are not participating in the implementation of the Joint Programme);

  - regional (UNFPA and UNICEF regional offices and regional partners and stakeholders in the 3 regions: MENA/ Arab States; and the two African regions) and

  - global levels (UNFPA and UNICEF headquarters, other UN agencies, partners and donors).

- Online survey, the survey will complement the data collected from the case studies. The content of the questionnaire will be determined at the inception phase. A web-based tool such as SurveyMonkey® will be used to roll out the survey which should be available in English and French.

- Rapid mobile surveys using U-Report or a similar tool will be used to obtain viewpoints of adolescents in Joint Programme countries and determine knowledge, attitudes and practices regarding FGM. This assessment can also act as a baseline for a potential Phase IV.

## Methods for data analysis

The evaluation matrix will provide the guiding structure for data analysis for all components of the evaluation.

UNFPA and UNICEF welcomes the use of diverse and innovative evaluation methods and this will be considered in the selection of evaluation proposals. QCA or process tracing, for instance, could be considered. This said, the following methods of data analysis and synthesis are encouraged to be used:

- Contribution analysis - to assess the extent to which the joint programme contributed to (or is likely to) expected outputs and outcomes of phase III. The team is encouraged to gather evidence to confirm the validity of the theory of change in different contexts, and to identify any logical and information gaps that it contained; examine whether and what types of alternative explanations/reasons exist for noted changes; teste assumptions, examine influencing factors, and identify alternative assumptions for each pathway of change.

- Descriptive analysis - to identify and understand the contexts in which the joint programme has evolved, and to describe the types of interventions and other characteristics of the programme.

- Content analysis - to analyze documents, interviews, group discussions and focus groups notes and qualitative data from the survey to identify emerging common trends, themes and patterns for each key evaluation question, at all levels of analyses. Content analysis can be used to highlight diverging views and opposing trends. The emerging issues and trends provide the basis for preliminary observations and evaluation findings.

- Quantitative analysis - to interpret quantitative data, in particular data emerging from the survey, as well as from the joint programme annual reports, and included descriptive statistical analysis.

# Evaluation process

## Inception phase

The exercise will commence with the preparation of an Inception report. Drawing on the ToR, the evaluation team will:

- review all documents housed in the document repository provided by the UNFPA-UNICEF offices and any other documentation outside of this which may be relevant to the evaluation.

- review the ToR areas for investigation and prepare the evaluation matrix (evaluation questions, assumptions and indictors – see annex 1)

- review and further develop the methods and tools for data collection and analysis including interview protocols, questionnaire for online survey, and a tool to record and organize all data collected,

- prepare the work plan for the evaluation.

Finally, the inception report should include comments on any challenges or difficulties which might arise in structuring and conducting the evaluation, suggesting solutions when applicable.

## Data collection (remote)

The data collection will open with a half-day remote induction workshop bringing together the evaluation team and the evaluation managers to prepare for the data collection.

Guided by the inception report and finalized work plan, the evaluation team will continue an in-depth documentary review, conduct remote interviews and e-focus group discussions (phone and skype/ zoom), and undertake a survey.

The evaluation team will be expected to present the results of the data collection including the results of the survey to the evaluation reference group (see calendar).

## Reporting phase

The reporting phase will open with half a day analysis workshop (remote) bringing together the evaluation team and the evaluation management group to discuss the results of the data collection. The objective is to help the various team members to deepen their analysis with a view to identifying the evaluation’s findings. The evaluation team then proceeds with the drafting of the findings of the report.

The first draft of the evaluation report (no conclusions and recommendations yet) will be submitted to the evaluation management group for comments. If the quality of the draft report is satisfactory (form and substance), the chair of the evaluation management group will circulate it to the reference group members for review and comments. In the event that the quality is unsatisfactory, the evaluation team will be required to produce a new version of the draft report.

Prior to the submission the second draft final evaluation report, a half a day workshop (remote) will be organized with the evaluation team and evaluation management group to agree on the conclusions, and discuss elements of the recommendations.

The evaluation team will then present the second draft report (including conclusions and recommendations) to the evaluation reference group.

Based on the inputs and comments from the meeting, the evaluation team should make appropriate amendments and prepare the final draft of the evaluation report. To ensure all comments from the reference group meeting have been fully address, the evaluation team shall prepare an audit trail of their responses to the comments.

The final report should clearly account for the strength of evidences on which findings are made so as to support the reliability and validity of the evaluation. The report should reflect a rigorous, methodical and thoughtful approach, whereby conclusions and recommendations build upon findings. The final report will follow the structure set out in Annex 2.  The report is considered final once it is formally approved by the chair of the evaluation management group after consultation with the other evaluation management group members.

The evaluation report along with the management response, will be published on the UNFPA/UNICEF evaluation webpage.

# Indicative time schedule

The evaluation will be conducted from October 2020 – May 2021

| Phase | Task | Date |
| --- | --- | --- |
| Inception phase | Initial documentary review and inception interviews | October 2020 |
|  | Submission of draft inception report | End October |
|  | Comments from the Evaluation Management Group (EMG) on the draft inception report | Nov |
|  | Submission of the revised draft (including the outline for the survey). | Mid Nov |
|  | First Evaluation Reference Group meeting (virtual) - Presentation of the methodological approach and work plan | End of Nov |
|  | Submission of the final inception report | Early December |
|  | Evaluation team and EMG induction workshop (half day) | Early December |
| Data collection | Remote interviews and documentary review – Global and regional levels | December – January 2021 |
|  | Remote interviews - Country level | Jan - March |
|  | Survey (Country and regional) | February /March |
|  | Second Evaluation Reference Group Meeting (virtual) Presentation of preliminary findings stemming from the data collection | Mid March |
| Reporting | Evaluation team and evaluation managers data analysis workshop (half day - virtual) |  |
|  | Submission of the draft Evaluation Report – introduction and findings chapters | Early April |
|  | Comments from the Evaluation Management Group (EMG) and the ERG on the first draft Evaluation Report | April |
|  | Evaluation team (core team) and evaluation managers conclusions and recommendation workshop (half day - virtual) | Mid April |
|  | Working session with the JP coordination team for the finalization of the recommendations (virtual) | Mid April |
|  | Review and address comments from evaluation management group and reference group members. Submission of the final evaluation report + Submission of Audit Trail (responses to comments) + Power Point Presentation | May |
|  | Third Evaluation Reference Group Meeting Presentation of the final report focusing on the conclusions and recommendations (team leader) (virtual) | Mid May |
| Dissemination | Presentation of the final report to JP Steering committee meeting (team leader and chair of the EMG) (virtual) | (tbc) |
|  | Professional copy editing of the evaluation report provided by the company | May |
|  | Production of an evaluation brief in English (two pages) and translation in Spanish, Arabic, Portuguese and French | May/June |

Legend:

| Deliverables to be produced and submitted by the evaluation team | Meetings/ evaluation team workshops (remote/ virtual) |
| --- | --- |

# Management and governance of the evaluation

The responsibility for the management and supervision of the evaluation will rest with the evaluation management group (EMG) chaired by the UNFPA EO lead evaluation manager. The evaluation management group will be composed of senior staff members of the UNFPA and UNICEF Evaluation Offices supported by a research evaluation assistant. The evaluation management group will have overall responsibility for the management of the evaluation process, including the hiring and managing the team of external consultants. The evaluation management group are responsible for ensuring the quality and independence of the evaluation in line with UNEG Norms and Standards and Ethical Guidelines. The chair of the EMG is responsible for day to day aspects of the evaluation process; acting as the main interlocutor with the evaluation team and relevant stakeholders.

The progress of the evaluation will also be followed closely by the evaluation reference group consisting of members of UNFPA/UNICEF relevant units. The reference group will support the evaluation at key moments of the evaluation process.

For further details on the roles and responsibilities of the EMG and ERG, please refer to the governance and management note – see annex 6.

# The evaluation team

The evaluation will be carried out by a highly qualified, multi-disciplinary team with extensive knowledge and experience in evaluation of development programming. Specific experience in evaluating programming to prevent, respond to and eliminate harmful practices particularly FGM will be required.

The team must also demonstrate a clear understanding of the UN system and ensure that the evaluation is conducted in line with the UNEG Norms and Standards for Evaluation in the UN System and abides by UNEG Ethical Guidelines and Code of Conduct (see annex 5) as well as any other relevant ethical codes UNEG Guidelines. UNEG guidance on Integrating Human Rights and Gender Equality in Evaluation should also be reflected throughout the evaluation.

Knowledge and Expertise

The evaluation team should be able to carry out all the work and deliver all deliverables listed in these Terms of Reference to the necessary quality standards

The evaluation team will collectively bring the below expertise and experience:

- Extensive experience in conducting complex evaluations for international development organizations with a specific focus on gender equality, harmful practices including FGM and social norms change.

- Demonstrable experience conducting gender responsive evaluations (ensuring a human rights-based approach to evaluation), as evidenced by previous assignments

- In-depth knowledge of evaluation methodologies and mixed-method approaches

- In-depth knowledge of and thematic expertise in the following areas: (i) FGM; (ii) social and gender norms change; (ii) gender equality and the rights of women and girls with a specific focus on sexual reproductive health and reproductive rights; (iii) community based development and movement building for social norm change and FGM abandonment.

- Strong ability to interact with a wide range of stakeholders, particularly on issues that are politically sensitive

- Knowledge of the UN system and UN programming at the country level, will bring additional points.

- Demonstrable analytical, communication and drafting writing skills in English.

- Fluency in French (past work experience in French)  will be required for the team members leading on the Francophone region/countries remote interviews

- Fluency in Arabic (or use of interpreters) will be required for key remote interviews in the Arab region.

The core evaluation team is to be drawn mostly from the profiles and from the approved experts included in the respective Long Term Agreement with UNFPA and is expected to be composed of three members: A team leader and senior evaluator with experience leading gender responsive evaluations; a senior gender and social norms expert; a medium level gender responsive evaluation expert

A junior evaluation assistant will provide administrative support to the work of the team.

A) The team leader (senior evaluator: 10 + years)

The team leader must possess the following:

- An advanced degree (Master or PHD) in social sciences or related fields

- A minimum of 10 years of experience working in international development

- Out of this 10 years, a minimum of 8 years experience specifically conducting gender responsive evaluations for international organizations or development agencies

- Conducting, as team leader, a minimum of 4 evaluations of similar size and complexity.

- In-depth knowledge of and long-standing experience in developing and implementing evaluation methodologies and methods best able to comprehensively assess complex shifts in power and social, political and economic change.

- Experience working with the United Nations, particularly UNFPA and UNICEF.

- Demonstrable analytical and writing/drafting skills in English.

- Fluency in French (past work experience in French) will bring additional points.

Main responsibilities:

- The team leader is expected to lead and contribute to the large majority of her/his time to the implementation of the evaluation, across all phases and respective deliverables. Specifically she/he is expected to:

  - Develop the work plan and ensure adherence to timelines and deliverables among the team

  - draft the inception report (with inputs from the other team members),

  - review and analyse documentation, websites, social media platforms

  - lead the design of the surveys

  - conduct remote interviews at global and regional levels of key stakeholders such as: UNFPA/UNICEF and other UN staff, donors, other development partners, civil society and academia and implementing partners.

  - conduct selected interviews at country level

  - lead the drafting of the evaluation report (with inputs from the other team members)

  - lead the preparation of the powerpoint presentation with the evaluation results.

  - attend events and present the evaluation results as requested

  - the team leader is ultimately responsible for assuring the quality, internal consistency and soundness of all evaluation deliverables, including the final evaluation report.

B) Senior thematic expert - gender equality and on social norm change (8 + years)

The thematic expert should possess the following:

- An advanced degree (Master or PHD) in social sciences or related fields

- A minimum of 8 years of experience in girl/women’s human rights and gender equality with a specific focus on FGM, social norm change, gender norms, sexual and reproductive health and reproductive rights; child rights; child protection.

- Previous direct experience working with a range of groups and movements to advance gender equality and tackle underlying drivers of discrimination.

- Experience contributing to and/or exposure to gender responsive evaluations is preferred will bring additional points.

- Demonstrable analytical and writing/drafting skills in English.

- Fluency in French (past work experience in French) will bring additional points.

Main responsibilities:

- The gender and social norms expert is responsible for contributing a significant amount of time to each phase of the evaluation and respective deliverables to ensure solid thematic focus and expertise throughout the process.  The thematic expert is expected to:

  - review and analyse documentation, websites, social media platforms

  - conduct remote interviews at global, regional and country levels of key stakeholders such as UNFPA/UNICEF and other UN staff, donors, civil society and academia and implementing partners.

  - contribute to the design of the survey

  - contribute to the drafting of the evaluation report,

  - contribute to the power point presentation with the evaluation results.

C) Medium level gender responsive evaluation expert (6 + years)

The medium level expert should possess the following:

- An advanced degree (Master) in social sciences or related fields.

- A minimum of 6 years of experience working in international development

- Experience conducting/contributing to programme level evaluations – including specifically gender responsive evaluations.

- Extensive previous experience in data collection and analysis, including designing and analysing data from surveys, documentary review and interviews.

- Capable of organizing and analysing large sets of data is a requirement.

- Strong statistical skills and advanced user of Excel and Stata, SPSS, R and/or Python;

- Strong skills in conducting financial analysis;

- Demonstrable analytical and writing/drafting skills in English.

- Fluency in French will bring additional points.

Main responsibilities:

- The medium level gender responsive evaluation expert is expected to conduct desk data collection & analysis, including:

  - conducting documentary review and remote interviews at country level of key stakeholders such as UNFPA and other UN staff, donors, civil society and academia, and implementing  partners).

  - building excel workbooks containing quantitative and qualitative information from UNFPA/UNICEF reporting and monitoring systems;

  - supporting the team leader in designing a survey.

  - administrating the survey, analysing the data generated and reporting back to the team leader

  - contribute to the drafting of the evaluation report.

D) Evaluation assistant (junior expert):

The evaluation assistant should possess the following:

- A degree in social sciences or related fields.

- A minimum of 2 years of experience working in international development

- Experience contributing to evaluations/ research projects will bring additional points.

- Capable of organizing large sets of documents/ data is a requirement.

- Excellent computer skills

- Experience with PowerPoint, infographics and other presentation tools.

- Demonstrable administrative and organizational skills

- Excellent drafting skills in English.

- Fluency in French will bring additional points.

Main responsibilities:

- The evaluation assistant is expected to provide administrative and organizational support, including:

  - collecting and uploading documentation on the evaluation google drive, ensuring the evaluation google drive is well organized and updated

  - organizing (including zoom links, calendar invitations) and scheduling interviews with all key informants (at country, regional and global levels) and for all members of the evaluation team

  - keeping track of the key informants list and interviews completed

  - taking notes; drafting letters, formatting documents/ presentations, etc.

Table 5: evaluation team expected level of effort:

| Core team | Inception | Data Collection | Analyses and Reporting |
| --- | --- | --- | --- |
| Team Leader (senior evaluator) | 50% | 30% | 40% |
| Gender and social norms expert (senior thematic expert) | 30% | 30% | 30% |
| Gender responsive evaluation specialist (medium evaluator) | 10% | 20% | 20% |
| Other relevant profiles |  |  |  |
| Evaluation assistant (junior expert) | 5% | 10% | 5% |
| Quality Assurance Adviser (senior evaluator) | 5% | NA | 5% |
| Total team level of effort per phase | 100% | 100% | 100% |

As reflected in the table the Evaluation Office expects the team leader, in particular, to be fully engaged and available throughout the evaluation process. An adequate number of days should be allocated to this role within the evaluation budget and planning, in order to fulfil the requirements of the role and the tight timeline.

The evaluation core team members should not have been involved in the design, implementation or monitoring of UNFPA UNICEF Joint Programme on the elimination of FGM during the period under review, nor will they have other conflict of interest or bias on the subject (see annex 3).

# Quality assurance and assessment

The contractor, will conduct quality control of all outputs (including drafts) prior to submission to the chair of the evaluation management group.

Levels of quality assurance:

- The first level of quality assurance of all evaluation deliverables (including drafts) will be conducted by the contractor prior to submitting the deliverables to the review of the evaluation management group.

- The second level of quality assurance of the evaluation deliverables will be conducted by the evaluation management group.

- The third level of quality assurance of the evaluation report will be conducted by the evaluation reference group.

Finally, the final evaluation report will be subject to assessment by an independent evaluation quality assessment provider using UNFPA Evaluation Office quality assessment grid.  The evaluation quality assessment grid will be published along with the evaluation report on the UNFPA Evaluation Office website. For more details on the quality assurance and assessment, please refer to the Long-term agreement terms of reference.

# Cost of the evaluation and payment modalities

The budget range for the overall cost of the evaluation is USD 220,000 - 270,000. The costs of the evaluation include:

- The evaluation as defined in the Terms of Reference (including expenses associated with the copy editing and translation)

LTA holders should not include travel costs in the financial offer. No travel is expected to happen given the pandemic.

Deliverables

- Inception report

- Evaluation report and PowerPoint presentation of the evaluation results (written in English; professionally designed and printed)

- Evaluation brief in English (two pages); translated in Arabic, Spanish, Portuguese and French

Payment Modalities

The payment modalities shall be as follow:

- 30% on acceptance of the draft inception report

- 40% on acceptance of the draft final evaluation report

- 20% on acceptance of the final joint evaluation report

- 10% on acceptance of the translation of the evaluation brief in Spanish, Arabic, Portuguese  and French

The production of each evaluation deliverables may entail several revisions until the chair of the evaluation management group and lead evaluation manager considers the deliverable final.  It is the responsibility of the contractor that all deliverables meet UNFPA evaluation quality standards, minimum UN editorial standards (see Annex 3: Editing guidelines), including formatting and presentation.  The UNFPA Evaluation Office will reject any deliverables that do not meet these standards.

The final evaluation report and the evaluation brief should be professionally copy edited by the contractor.

No payment will be processed until the corresponding deliverables are formally approved by the chair of the evaluation management group and lead evaluation manager.

# Bidding instructions for the preparation of the technical offer for this evaluation,

Instructions for submission of offers please refer to separate document - RFQ Nº UNFPA/USA/RFQ/20/099’.

Bibliography

United Nations General Assembly. Transforming our world: the 2030 Agenda for Sustainable Development. 25 September 2015. Available at: http://www.un.org/ga/search/view_doc.asp?symbol=A/RES/70/1&Lang=E

Programme of Action of the 1994 International Conference on Population and Development (ICPD), 1994. Available at:  https://www.unfpa.org/public/home/publications/pid/1973

ICPD Review Report, 2014. Available at: http://issuu.com/shiralevine/docs/icpd_review_global_report_a_69_62_e

UNICEF Female genital mutilation/cutting: A global concern

https://data.unicef.org/resources/female-genital-mutilationcutting-global-concern/

Female Genital Mutilation/ Cutting Country Profiles

https://data.unicef.org/resources/female-genital-mutilation-cutting-country-profiles/

United Nations Population Fund strategic plan 2014-2017 (DP/FPA/2013/12). Available at: http://www.unfpa.org/public/home/about/strategic-direction

UNFPA-UNICEF Annual Reports on the Joint Programme on Female Genital Mutilation/Cutting:

http://www.unfpa.org/publications-listing-page/Female%20genital%20mutilation

UNFPA Manual on Social Norms and Change

http://www.unfpa.org/publications-listing-page/Female%20genital%20mutilation

UNFPA Demographic Perspectives on Female Genital Mutilation

http://www.unfpa.org/publications/demographic-perspectives-female-genital-mutilation

United Nations Population Fund Annual reports. Available at: https://www.unfpa.org/public/cache/offonce/home/publications/annual_reports

The Beijing Declaration and Platform for Action adopted at the Fourth World Conference on Women. 15 September 1995. Available at http://www.un.org/womenwatch/daw/beijing/pdf/BDPfA%20E.pdf

United Nations General Assembly. Declaration on the Elimination of Violence against Women. 20 December 1993. Available at http://www.un.org/documents/ga/res/48/a48r104.htm

UN Women. UN System Wide Action Plan on Gender Equality and the Empowerment of Women UN System Wide Action Plan on Gender Equality and the Empowerment of Women. April 2012. Available at http://www.unwomen.org/~/media/Headquarters/Attachments/Sections/How%20We%20Work/UNSystemCoordination/UN-SWAP-Framework-Dec-2012.pdf

# Annexes of the Terms of reference

## Annex 1: Evaluation Matrix (template)

| Evaluation Question 1: To what extent is the programme design responsive … Criteria: Relevance and effectiveness |  |  |  |  |
| --- | --- | --- | --- | --- |
| Assumptions to be assessed | Indicators |  | Data Collection Sources and Tools |  |
| Assumption 1.1 Joint programme interventions at the national and sub-national level are based … | - Evidence of contextualization of strategies and interventions, … |  | Documents - Minutes of country/regional level coordination meetings - … Interviews/Discussions - Joint Programme coordinators - UNFPA/UNICEF management teams (ROs/COs) - …. |  |
| Assumption 1.2 The combination of approaches and strategies is appropriate to address FGM in … | - Evidence of ownership of community level programme interventions by civil society and other partners/stakeholders - … |  | Documents - Country work plans - … Interviews/Discussions - Implementing partners (INGOs, local NGOs) - … |  |
| Evaluation Question 2: To what extent the … |  |  |  |  |
| Assumptions to be assessed |  | Indicators |  | Data Collection Sources and Tools |
| Assumption 2.1 The programme has … |  | - Number of … - .. |  | Documents - … Interviews/Discussions - … |
| Assumption 2.2 Joint Programme acted as a catalyst … |  | Evidence of .. |  | Documents - … Interviews/Discussions - … |

## Annex 2: Structure for the evaluation report

I. Final report

Number of pages: 70-80 pages without the annexes

Table of Contents

List of Acronyms

List of Tables (*)

List of Figures

Executive Summary: 5 pages: objectives, short summary of the methodology and key conclusions and recommendations

1	Introduction

Should include: purpose of the evaluation; mandate and strategy of UNFPA/UNICEF support …

2	Methodology

Should include: overview of the evaluation process; methods and tools used in evaluation design; analysis of UNFPA/UNICEF strategic framework; evaluation questions and assumptions to be assessed; methods and tools used for data collection; desk review; survey; limitations to data collection; methods and tools used for data analysis; methods of judgment; the approach to triangulation and validation

3	Main findings and analysis

Should include for each response to evaluation question: evaluation criteria covered; summary of the response; detailed response

4	Conclusions

Should include for each conclusion: summary; origin (which evaluation question(s) the conclusion is based on); detailed conclusion

5	Recommendations

Should include for each recommendation: summary; priority level (very high/high/medium); target (business unit(s) to which the recommendation is addressed); origin (which conclusion(s) the recommendation is based on); operational implications. Recommendations must be: linked to the conclusions; clustered, prioritized; accompanied by timing for implementation; useful and operational

Annexes shall be confined to a separate volume

Should include: evaluation matrix; portfolio of interventions; methodological instruments used (survey, focus groups, interview guides etc.); bibliography; list of people interviewed; terms of reference; minutes of the ERG meetings.

(*) Tables, Graphs, diagrams, maps etc. presented in the final evaluation report must also be provided to the Evaluation Office in their original version (in Excel, PowerPoint or word files, etc.).

Cover for the Final Evaluation Report

UNFPA/UNICEF logo (there should be no other logo/ name of company)

Title of the evaluation:

Evaluation Office

Date

The following information should appear on page 2:

- Name of the evaluation manager(s)

- Names of the evaluation team

- Names of the members of the reference group

Copyright © UNFPA/UNICEF 2021, all rights reserved.

The analysis and recommendations of this report do not necessarily reflect the views of the United Nations Population Fund or the United Nations Children’s Fund. This is an independent publication by the Evaluation Office of UNFPA and UNICEF.

Any enquiries about this report should be addressed to:

Evaluation Office, United Nations Population Fund, e-mail: evb@unfpa.org

For further information on the evaluation please consult the Evaluation Office webpage:

http://www.unfpa.org/evaluation

Editing: xxxx

Design: XXX

Cover photos provided by: XXXX

## Annex 3: Editing guidelines

Evaluation reports formal documents. Therefore they shall be drafted in a language and style which is appropriate and consistent and which follows UN editing rules:

Acronyms: In each section of the report, words shall be spelt out followed by the corresponding acronym between parentheses. Acronyms should be used only when mentioned repeatedly throughout the text. The authors must refrain from using too many acronyms. In tables and figures, acronyms should be spelt out in a note below the table/figure.

Capitalization: Capitalize high ranking officials' titles even when not followed by a name of a specific individual. Capitalize national, political, social, civil etc. groups – e.g. Conference for Gender Equity, Committee on HIV/AIDS, Commission on Regional Development, Government of South Africa.

- Capitalize common nouns when they are used as a shortened title, for example, the ‘Conference’ (referring to the Conference on Gender Equity) or the ‘Committee’ (referring to the Committee on HIV/AIDS). However, do not capitalize when used as common nouns – e.g. ‘there were several regional conferences.’

- Some titles corresponding to acronyms are not capitalized – e.g. human development index (HDI), country office (CO).

- Use lower case for: UNFPA headquarters; country office; country programme; country programme evaluation; regional office, country programme document; results framework; evaluation system.

Numbers: Spell out single-digit whole numbers. Use numerals for numbers greater than nine. Always spell out simple fractions and use hyphens with them (e.g. one-half of…, a two-thirds majority). Hyphenate all compound numbers from twenty-one through ninety-nine. Write out a number if it begins a sentence. Use % symbol in tables and “per cent” in the text

Terminology: Use “UN organizations” not “sister agencies.” Do not use possessive for innate objects (UNFPA’s, the Government’s, the country’s, etc.).  Instead, use:  the UNFPA programme, the government programme, the UNFPA intervention, etc.

Bibliography

Author (last name first), Title of the book, City: Publisher, Date of publication.

Author (last name first), "Article title," Name of magazine (type of medium). Volume number, (Date): page numbers, date of issue.

URL (Uniform Resource Locator or WWW address), author (or item's name, if mentioned), date.

List of people consulted: should include the full name and title of people interviewed as well as the organization should be organized in alphabetical order (English version) with last name first; should be structured by type of organization

See United Nations Editorial Manual Online at: http://dd.dgacm.org/editorialman

## Annex 4: Evolution of the results frameworks

## Annex 5: Code of conduct and norms for evaluation in the UN system

Evaluations of UNFPA-supported activities need to be independent, impartial and rigorous and evaluators must demonstrate personal and professional integrity. In particular:

- To avoid conflict of interest and undue pressure, evaluators need to be independent. The members of the evaluation team must not have been directly responsible for the policy/programming-setting, design, or overall management of the subject under evaluation, nor should they expect to be in the near future. Evaluators must have no vested interest and should have the full freedom to conduct impartially their evaluative work, without potential negative effects on their career development. They must be able to express their opinion in a free manner.

- The evaluators should protect the anonymity and confidentiality of individual informants.  They should provide maximum notice, minimize demands on time, and respect people’s right not to engage.  Evaluators must respect people’s right to provide information in confidence, and must ensure that sensitive information cannot be traced to its source. Evaluators are not expected to evaluate individuals, and must balance an evaluation of management functions with this general principle.

- At times, evaluations uncover evidence of wrongdoing.  Such cases must be reported discreetly to the appropriate investigative body.

- Evaluators should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relations with all stakeholders. In line with the UN Universal Declaration of Human Rights, evaluators must be sensitive to, and address issues of discrimination and gender equality.  They should avoid offending the dignity and self-respect of those persons with whom they come in contact in the course of the evaluation. Knowing that evaluation might negatively affect the interests of some stakeholders, evaluators should conduct the evaluation and communicate its purpose and results in a way that clearly respects the dignity and self-worth of all stakeholders.

- Evaluators are responsible for the clear, accurate and fair written and/or oral presentation of study limitations, evidence based findings, conclusions and recommendations.

A declaration of absence of conflict of interest must be signed by each member of the team and shall be annexed to the offer. No team member should have participated in the preparation, programming or implementation of UNFPA /UNICEF interventions on FGM during the period under evaluation.

## Annex 6: Governance and management note

The evaluation will be conducted jointly by UNFPA (lead agency) and UNICEF.

- A joint evaluation management group (EMG) composed by the members of the UNICEF and UNFPA evaluation offices will be the main decision-making body for the evaluation and have overall responsibility for management of the evaluation process including hiring and managing the team of external consultants. UNFPA Evaluation Office will chair the EMG.

The joint EMG is responsible for ensuring the quality and independence of the evaluation and to guarantee its alignment with UNEG Norms and Standards and Ethical Guidelines.

Key roles and responsibilities of the joint EMG include:

- To prepare the terms of reference for the joint evaluation in coordination with the joint ERG

- To liaise with the joint ERG and convene review meetings with the evaluation team

- To lead the hiring of the team of external consultants, reviewing proposals and approving the selection of the evaluation team.

- To supervise and guide the evaluation team in each step of the evaluation process

- To identify and ensure the participation of relevant stakeholders in coordination with the joint ERG throughout the evaluation process.

- To participate in the data collection process (conduct interviews, facilitate group discussions and focus groups) both at inception and data collection phases.

- To review, provide substantive comments and approve the inception report, including the workplan, analytical framework, methodology.

- To review and provide substantive feedback on the draft and final evaluation reports, for quality assurance purposes. To approve the final evaluation report and all evaluation deliverables.

- To contribute to learning, knowledge sharing, the dissemination of the evaluation findings, conclusions and recommendations.

2 - 	A joint evaluation reference group (ERG) will be established to support the evaluation at key moments and ensure broad participation in the conceptualization of the exercise, access to information, high technical quality of the evaluation products as well as learning and knowledge generation. UNFPA Evaluation Office will chair the ERG.

The joint ERG will be consulted by the EMG on key aspects of the evaluation process. The joint ERG will consist of technical staff from relevant business units in the two agencies in both headquarters and in the regional offices.  The ERG will have a balance of expertise in FGM, gender and other related areas as deemed relevant. The ERG will provide substantive technical inputs during the evaluation process as well as feedback on the evaluation results and recommendations.

Key roles and responsibilities of joint ERG members include:

- To contribute to the conceptualization, preparation, and design of the evaluation including providing feedback on the terms of reference and comments on the inception report.

- To provide comments and substantive feedback to ensure the quality – from a technical point of view - of the draft and final evaluation reports, including providing inputs to draft recommendations ensuring they are relevant and actionable

- To act as a source of knowledge for the evaluation and coordinate feedback from other UNFPA and UNICEF services from headquarters, the regions and from the field, in particular to facilitate access to information and documentation.

- To assist in identifying both internal and external stakeholders to be consulted during the process.

- To participate in review meetings of the joint EMG and with the evaluation team as required.

- To play a key role in learning and knowledge sharing from the evaluation results, contributing to disseminating the findings of the evaluation and follow-up on the implementation of the management response.

3 - The joint programme Steering Committee will be informed by the EMG chair of progress at key stages of the evaluation: inception; preliminary findings from data collection; final report.

Minutes of UNFPA and UNICEF Joint Programme Steering Committee meeting, September 19 2017.

UNFPA, State of the World Population 2020, “Against my will – Defying the practices that harm women and girls and undermine equality”, June 2020, page 66. Available at https://www.unfpa.org/sites/default/files/pub-pdf/UNFPA_PUB_2020_EN_State_of_World_Population.pdf

World Health Organization, “Health risks of female genital mutilation (FGM)”, available at https://www.who.int/sexual-and-reproductive-health/health-risks-of-female-genital-mutilation

World Health Organization, “The economic cost of female genital mutilation”, February 2020. See https://www.who.int/news-room/detail/06-02-2020-economic-cost-of-female-genital-mutilation

UNFPA, State of the World Population 2020, “Against my will – Defying the practices that harm women and girls and undermine equality”, June 2020, page 78

UNFPA, “Accountability for eliminating female genital mutilation – a focus on the third cycle of the Universal Periodic Review”, June 2020, page 1. Available at https://www.unfpa.org/sites/default/files/resource-pdf/FGM_factsheet_13-online.pdf

UNFPA, State of the World Population 2020, “Against my will – Defying the practices that harm women and girls and undermine equality”, June 2020, pages 80-81.

See: https://sustainabledevelopment.un.org/sdg5

The Nairobi Summit on ICPD25 was held from 12-14 November 2019, and co-convened by the governments of Kenya, Denmark and by UNFPA. The summit led to a total of 1379 commitments, 21% (226) of which address gender-based violence and harmful practices, including female genital mutilation. See https://www.nairobisummiticpd.org/commitments

Outcome 2: Every adolescent and youth, in particular adolescent girls, is empowered to have access to sexual and reproductive health and reproductive rights, in all contexts.

Outcome 3: Gender equality, the empowerment of all women and girls, and reproductive rights are advanced in development and humanitarian settings.

Outcome Statement 3: Girls and boys, especially the most vulnerable and those affected by humanitarian situations, are protected from all forms of violence, exploitation, abuse and harmful practices.

UNFPA, State of the World Population 2020, “Against my will – Defying the practices that harm women and girls and undermine equality”, June 2020. Available at https://www.unfpa.org/sites/default/files/pub-pdf/UNFPA_PUB_2020_EN_State_of_World_Population.pdf

UNFPA, State of the World Population 2020, “Against my will – Defying the practices that harm women and girls and undermine equality”, June 2020, page 64.

Burkina Faso, Djibouti, Egypt, Eritrea, Ethiopia, the Gambia, Guinea, Guinea-Bissau, Kenya, Mali, Mauritania, Senegal, Somalia, Sudan and Uganda.

Joint Evaluation of the UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation: Accelerating Change Phase I and II (2008–2017), page 49

The Joint evaluation of Phase I is available at https://www.unfpa.org/admin-resource/unfpa-unicef-joint-evaluation-unfpa-unicef-joint-programme-female-genital

Joint Evaluation of the UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation: Accelerating Change Phase I and II (2008–2017), page 49. Available at: https://www.unfpa.org/admin-resource/joint-evaluation-unfpa-unicef-joint-programme-abandonment-female-genital-mutilation

Ibid, pages VIII-IX.

Proposal for Phase III of the UNFPA-UNICEF joint programme Elimination of Female Genital Mutilation: Accelerating Change, page 7.

Joint Evaluation of the UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation: Accelerating Change Phase I and II (2008–2017)

UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation – Annual Report 2018, page 106. Available here: https://www.unfpa.org/fgm-annual-report

Joint Evaluation of the UNFPA-UNICEF Joint Programme on the Abandonment of Female Genital Mutilation: Accelerating Change Phase I and II (2008–2017), page 47.

Proposal for Phase III of the UNFPA-UNICEF joint programme Elimination of Female Genital Mutilation: Accelerating Change, page 49

In 2018, funding constraints initially limited programme interventions to Tier 1 countries. Uganda and Mali received financial and technical support by the middle of the year, 2018 Annual Report, page 6.

COVID-19 DISRUPTING SDG 5.3: ELIMINATING FEMALE GENITAL MUTILATION. Technical Note, April 2020. Available at https://www.unfpa.org/sites/default/files/resource-pdf/COVID-19_Disrupting_SDG.3_Eliminating_Female_Genital_Mutilation.pdf

The Administrative Agent is responsible for the following: Signing of a new Memorandum of Understanding with UNICEF for Phase II; Negotiating and signing a Standard Administrative Arrangement with donors contributing to the Joint Programme; Receiving contributions and disbursing funds to UNICEF, in accordance with annual work plans, budget availability and decisions of the Joint Programme Steering  Committee; Preparing consolidated narrative progress and financial reports, incorporating content of reports submitted by UNICEF, and submitting them to the Steering Committee.

Both criteria have been extensively used on the evaluation of phase I and II in addition data and findings from EQs covering efficiency and coordination are still relevant.

Given the pandemic and the limitations regarding traveling data collection will be conducted remotely through virtual interviews, phone interviews and a survey.

See: http://www.unevaluation.org/document/guidance-documents

See: http://www.unevaluation.org/document/guidance-documents

The grid is available here:  https://www.unfpa.org/admin-resource/evaluation-quality-assurance-and-assessment-tools-and-guidance

This brief is separate from the executive summary.