TERMS OF REFERENCE

| Project Title: | Evaluation of the project ‘Promoting Kyrgyzstan`s youth cohesion and interaction towards Uzbekistan’ (2019-2020) |
| --- | --- |
| Consultancy/Services Title: | Consultancy to conduct final evaluation of the project. |
| Consultancy Mode: | National International |
| Type of Contract: | Consultant Individual Contractor Institutional |
| Mode of Selection: | Competitive Single Source ECARO Roster |
| Duration of Contract: | From: August-March 2021 |

Goal of consultancy

UNICEF-Kyrgyzstan seeks an individual international consultant to conduct a summative evaluation of the project “Promoting Kyrgyzstan`s youth cohesion and interaction towards Uzbekistan” on social inclusion and inter-ethnic cohesion at the border areas with Uzbekistan.  The international consultant will be part of an evaluation team and work together with a national consultant.

- BACKGROUND AND CONTEXT OF THE PROJECT

Currently 85% of the 1378 km border between Kyrgyzstan and Uzbekistan have been agreed upon and  36 disputed territories or 217 km border remain unresolved. The problematic relations and unsettled border demarcation between Kyrgyzstan and Uzbekistan have been an open issue leading to various levels of conflicts since the collapse of the Soviet Union in 1991. All uprisings taking place in Kyrgyzstan, especially the one leading to the confrontation between Kyrgyz and Uzbek communities in June 2010 included a combination of triggers of economic, social and political reasons, including the ones related to border disputes.  The inter-ethnic tensions between the Kyrgyz and the Uzbek living side by side in the south of the country have been overtly influenced and heavily dependent by the overall difficult relations between the two states.

However, the change of leadership in Uzbekistan in 2016 with opening of new perspectives in terms of civil and political liberties, governance and human rights led to a series of initiatives at the highest level to overcome acrimonies of the past. Joint action plan with Uzbek government for 2017-2019 which broadly determines cooperation between different branches and levels of the government including the local self-governments, local state administrations to establish economic, trade, cultural and humanitarian cooperation across the border was approved.  Each of the three southern provinces of Kyrgyzstan bordering with Uzbekistan developed their own action plans of cooperation with their bordering peer province on the other side. The State Agency for Youth and Sports of Kyrgyzstan also signed a Memorandum of Understanding and a joint plan with a similar entity in Uzbekistan.  These plans have been identified as key national strategic document that formulates the intention of investing in the creation of positive peace with the Uzbek counterpart and to have a positive in-country effect within ethnic communities.

The project “Promoting Kyrgyzstan`s youth cohesion and interaction towards Uzbekistan’” was initiated in 2018 by UNICEF, UNDP, UNFPA  in response to the call for proposals for the UN Peacebuilding Funds’ (PBF) Gender and Youth Promotion Initiative, which supports the empowerment of women and young people to ensure their inclusion and participation in peacebuilding and decision-making processes at all levels.  It was identified as the one better fitting with the requirements of the call and more in line with the peacebuilding agenda in the country during in-depth discussions within the UN Country Team members and therefore was submitted to PBF for funding under 2018 call for proposals.  Upon the result of PBF`s selection, this project has become the first and the only Youth Promotion Initiative (YPI) project implemented by Recipient United Nations Organizations (RUNOs), while other YPI projects in the country have been implemented by Civil Society Organizations (CSOs).

The project took stock of the momentum in the cooperation between the two States and aimed at entrenching positive peace factors.  The project aimed to support the implementation of the already existing national and subnational mechanisms  such as the “Memorandum of Understanding between youth-related government agencies of Kyrgyzstan and Uzbekistan” and action plan of cooperation between Batken, Osh and Jalalabad regions in Kyrgyzstan with respective neighbor regions  in Uzbekistan in order to facilitate the increasing opportunity of exchanges between the two countries by mitigating the challenges related to access to services, economic trades, family unifications and provision of documentations and contribute to the social cohesion in border areas and beyond with catalytic effects across the entire country. Project activities span from the improvement of cultural exchanges, youth interactions reaching out also to cooperation with relevant law enforcement bodies, Ombudsman institution and the Prosecutor’s Office to the further development of such plans with more inclusive participation of the youth. Due to the high number of young people in border areas, youth, in particular young women, were identified as the target group to invest.

The project interventions were planned to be complementary to the ongoing peacebuilding interventions under the approved Peacebuilding Priority Plan (PPP) for the period 2017-2020, in which a significant component is devoted to increasing resilience of young people to violent ideologies and enhancing youth participation in peacebuilding. The project was informed by Sustainable Development Goal 16 in the understanding that durable peace can be achieved through ensuring inclusive justice and accountability vis-a-vis all sections of the population. At the same time, the project is enshrined with the main messages of United Nations Security Council Resolutions 2250 of 2015 and 2419 of 2018 recognizing the critical and positive role that young people play in building peace.

The project implementation started on January 1, 2019.  Although the project duration was 18 months initially, in 2020 the project was extended till 15 November 2020.   All project activities are taking place within the Kyrgyz side of the border with some activities involving youth and authorities from Uzbekistan.

It is important to note that this project is one of many peacebuilding projects funded by the Peacebuilding Fund in Kyrgyzstan under the Gender and Youth Promotion Initiative. Other projects are implemented by RUNO and CSOs.

- PROJECT THEORY OF CHANGE

Project was aimed to support 1) duty bearers, i.e. government institutions entrusted to implement joint action plans with Uzbek counterparts and  2) right holders such as youth of border areas,  and especially young women who are  of higher risk of being deprived of their rights and being subject to violence, including forced marriages, 3)  parents and community members who help to create conducive environment for young people’s initiatives.

Young women and men, including children, their parents and caregivers, staff of Local Self-Government and the Local Council in nine target municipalities (full list is in Section 4), staff of youth-related  government authorities are the key target beneficiaries of the project

The Theory of change of the project:  If Kyrgyzstani young women and men and the local governance institutions build inclusive dialogue and cooperation with their counterparts across the Uzbek border and if grass-roots positive cross-border interactions amass, supporting and expanding the on-going inter-governmental collaboration efforts, then interethnic cohesion improves within the border areas and beyond, because the more positive interactions there will be the less the perception of  “the other” among the different groups will exist.

The project results were defined as follows (more details in Annex I):

Outcome: Kyrgyz youth and relevant government agencies collaborate and further develop cooperation plans to improve positive interactions with their Uzbek counterparts.

Output 1.1.

Young people have improved critical/design thinking and demonstrate support for diversity and equal rights by initiating projects that contribute to the implementation of plans for local development and positive cooperation of youth between Kyrgyzstan and Uzbekistan

Output 1.2:

Parents of young people, community members improve their understanding of diversity, have enhanced knowledge and tools to support and participate in youth -led initiatives.

Output 1.3. Government representatives have strengthened capacity to provide services in cross-border communities and commit to support youth-driven initiatives aiming at improving the cross-border cooperation

- RATIONALE, OBJECTIVE and USE OF THE EVALUATION

Conducting a summative evaluation of the project is one of key requirements under the Monitoring and Evaluation provision of the project that was planned to be conducted at the end of the project implementation.

The main objective of this summative evaluation is to assess whether the project has met its objectives, whether its objectives were relevant to the context. The evaluation would assess the circumstances influencing the project’s achievements and the challenges that hindered it and to generate findings, lessons learned and recommendations regarding the relevance, coherence, effectiveness, efficiency, impact and sustainability of the project results. It is essential that the evaluation measures the result of the project in terms of outcome and outputs it has delivered for target groups and beneficiaries.

Primary intended users of the evaluation results are the decision-makers from government, implementing partners, the implementing agencies UNICEF, UNDP, UNFPA, and the Peacebuilding Fund.  Secondary intended users are local self-government staff in project communities and project beneficiaries. Evaluation results will inform the Government’s, Peacebuilding Fund’s and Implementing UN Agencies’ future programs and provide evidence for further implementation or scale up of joint action plans between the bordering countries. The evaluation report and management response will be made public.

- EVALUATION SCOPE

The evaluation will cover all project activities during the period from January 1, 2019 to November 15, 2020.

Geographically, the evaluation will cover remotely at least four out of nine target municipalities in Osh (Kara-Suu, Kashkar-Kyshtak, Tepe-Korgon), Jalalabad (Kerben, Kashka-Suu, Kok-Serek) and Batken (Aidarken, Birlik, Suu-Bashy) provinces.  Target municipalities will be identified at the Inception phase.

Since all project activities took place in Kyrgyzstan, all evaluation activities will take place on the Kyrgyz side of the border as well.  If some key informants from the Uzbek authorities or youth will be identified as crucial in the Inception Phase or in the course of the evaluation, their inclusion will be considered.

Due to the epidemiological situation and social distancing requirements related to Covid-19, remote data collection methods will be employed. Remote data collection might entail limitations and challenges such as lack of direct interaction and different group dynamics during online focus groups, limited access to the Internet or mobile phone by target respondents, low bandwidth for some participants, etc.  Also due to the Covid-19 situation, there might be delays in response and cancellations due to respondents’ health or care responsibilities of their family members. In order to address some of the limitations implementing partners will provide support by providing space and access to the Internet from their premises for target respondents with limited access to the Internet or mobile phones. Fieldwork timeline was also extended from initial two weeks to three weeks in order to allow the evaluation team to reach as many respondents as possible.  This and other issues with regards to data collection logistics and arrangements will be discussed and agreed during the inception phase.

This summative evaluation intends to answer the questions as per all the OECD-DAC criteria for evaluation but with a specific attention to relevance, coherence, efficiency and effectiveness.

- EVALUATION QUESTIONS

The evaluation will be guided by UNEG Norms and Standards for Evaluation and will address the standard OECD DAC evaluation criteria of relevance, coherence, efficiency, effectiveness, impact and sustainability.  Further, the evaluation will incorporate gender, equity and human rights perspectives throughout the analysis.  The following is a suggested list of evaluation questions which the evaluation team is welcome to revise, develop criteria of judgement and measurement indicators:

Relevance

- To what extent were the design and objectives of the project-based on solid conflict analysis?  To what extent were the project results relevant to the needs and priorities of the beneficiaries, especially of the young women and men?

- To what extent is the project consistent with key national development strategies, including in the area of peacebuilding, and youth empowerment?

- To what extent is the project based on a valid Theory of Change and how relevant and coherent was it in practice?

- To what extent and how has the issue of equity been integrated into the design, planning and implementation of the project activities?

Coherence

- To what extent UNICEF, UNDP and UNFPA were able to ensure synergies and interlinkages in design and implementation of the project?  Has UNICEF, as the leading agency, been able to make the most of integrated and cross-sectoral working to increase the overall contribution of the project?

- To what extent interventions under this project were complimentary, harmonized, coordinated with the governments’ and other peacebuilding actors’ interventions?

Effectiveness

- To what extent have the expected results of the project been achieved on both outcome and output levels?

- To what extent have the strategies and approaches been innovative in achieving the project results? Were timely corrective actions taken when and where necessary during the course of the project, including actions related to Covid-19 situation?

- How effective have the project strategies and approaches been in contributing to peace and stability in border areas?

- How did the project succeed or not in involving and building the capacities of rights-holders (including young women and men), duty-bearers as well as the project partners? How did the young women and men benefit from the project?

- What were the main factors influencing achievement or non-achievement of the project results and in what ways?

Efficiency

- To what extent the level of achievements (outputs and outcome) justify the financial and human resources used?

- Have project interventions been implemented within intended timeframe or timeframe reasonably adjusted to the demands of the evolving context?

- To what extent does the management structure of the project support efficiency for programme implementation and achievement of results?

- To what extent are the monitoring mechanisms in place effective in measuring and informing management of the project performance and progress towards the targets?

Impact

- What are the indirect, unintended positive and negative and potential consequences of the intervention in the areas where the project was implemented? What might be the most significant, long-term and potentially transformative effects of the project?

- How likely is it that the project will contribute to a broader positive impact of improved social cohesion and peacebuilding in border areas?

- How did young women and men contribute to social cohesion and peacebuilding in their communities or beyond?

Sustainability

- How effectively has the project generated national ownership of the results achieved?

- How effectively has the established partnerships with relevant stakeholders developed national capacities to ensure sustainability of efforts and results?

The evaluation should also look into the lessons learnt, recommendations and cross-cutting issues:

- What are the lessons learnt from the project?

- What are the good practices that could be applied in the future activities and similar projects?

- To what extent are gender, human rights and equity considerations included in the project’s development and implementation?

- METHODOLOGY.

It is a summative, utilisation-focused, context specific, and equity-oriented evaluation using a theory-based design. The evaluation team is expected to assess the project theory of change (TOC) and make it useful to the evaluation and propose an appropriate design. The evaluation team is also welcome to develop an appropriate conceptual framework to guide the evaluation methodology, explain results and contextualize the recommendations.

It is expected that most of the desk-review analysis can be done based on the (i) existing programme documentation (programme document; results framework; annual and quarterly reports and monitoring results (gender, age disaggregation) (ii) data from the baseline survey report (November, 2019, disaggregated by gender, age, ethnicity, location); (iii) UN Peacebuilding Priority Plans 2013-2016 and 2016-2020; (iv)additional knowledge products covering the respective geographical areas; V)  relevant thematic literature on the subject matter, i.e. theoretical conceptual frameworks, etc.

In addition to the secondary data sources, it is expected that qualitative and quantitative data collection methods and instruments will be used capturing the perspectives of the stakeholders  and beneficiaries involved in the project including most vulnerable groups of the affected population i.e. youth and women living in the border areas with Uzbekistan. Given the current development of epidemiological situation where numbers of Covid-19 infections and death toll from Covid-19 are on the rise and the second wave is projected to start in September, it is too risky to undertake field work using traditional face-to-face methods. “Do no harm” is one of UNICEF’s key principles when undertaking any kind of evaluation or research.  Therefore, any proposed inception report should be based on this assumption and suggest a remote data collection plan.

The evaluation team is welcome to use any innovations (as applicable) throughout the evaluation with regard to the design (any innovative designs or a mix of them), data collection (using Big Data, if possible), analysis (using machine analysis and algorithm, etc.) and writing up and dissemination stages. A kick-off meeting will be conducted at the start of the assignment with UNICEF to identify the most appropriate course of action.

The Inception phase will be used as an evaluability stage where available evidence will be collected and assessed for scope, quality and reliability.  In doing so, the team will make use of PBF Guideline on Assessing Readiness for Remote Evaluation.

During the Inception phase the team will explore different options on how to optimally use available data collection approaches and tools to engage all relevant project stakeholders and beneficiaries, especially the most vulnerable and hard to reach ones. The detailed remote data collection methodology will be developed by the evaluation team as part of the Inception Report and in close consultation with UNICEF as per below Workplan.

The Inception Report will outline detailed scope, evaluation framework; methodology; sampling, data collection methods (considering the risks related to COVID-19, timeline for activities and submission of deliverables, materials for Ethics Review, etc. and meet the criteria outlined in the UNICEF Quality Review and Ethics Review Checklists.

The evaluation will follow the UNEG Norms and standards throughout its all stages.

- ETHICAL CONSIDERATIONS

The evaluation will be guided by UNEG Ethical Guidelines and UNICEF Procedure for Ethical Standards.  Due to planned involvement of young people below 18 in the fieldwork, ethical clearance from UNICEF external Ethical Review Facility will be required. The common guiding principles will be used to ensure ethical safety during the evaluation process:

- preventing direct harm, and ensuring benefits, to individual participants, their families and wider community groups

- ensuring informed consent by all participants

- ensuring the privacy and confidentiality of subjects

- identifying and addressing actual or potential conflict of interest by UNICEF staff and/or evaluation team, including funding considerations.

Informed consent must be sought from all participants. The evaluation team will explain to the participants the purpose and use of the evaluation; they will also make it explicitly clear to the participants that their participation is voluntary, and they can withdraw at any moment. The nature of the informed consent must be noted in the ethics section of the proposal and any final report.

Throughout the process, the evaluation team should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relationships with all stakeholders and do no harm.

The evaluation team should clearly identify any potential ethical issues and approaches and oversight of the evaluation process in the inception report.  Materials required for the Ethics Review will be developed as part of the inception report.

- WORKPLAN

|  | Description | Responsible | Timeline | Associated deliverables |
| --- | --- | --- | --- | --- |
|  | Inception |  |  |  |
| 1 | Set up a Reference Group | UNICEF | Prior to the start of the evaluation | ERG set up |
| 23 | Kick-off meeting with UNICEF | UNICEF | Immediately upon signature of the contract with both consultants | A timeline and initial methodology discussed |
| 3 | Preparation of all project documentations and materials for review | UNICEF | Ready by the time contract is signed | Ready to use library |
| 4 | Desk review of relevant documents and sources of data | Consultants (documents to be provided by UNICEF) | By September 10, 2020 | Findings of desk review which will go as Annex to the Inception Report |
| 5 | Logistics (arranging meetings/interviews) | UNICEF | August- September 2020 | A schedule of meetings |
| 6 | Preparation of the draft Inception report | Consultants | By September 24, 2020 | Drafts Inception report |
| 7 | Evaluation launch workshop with ERG Presentation of the draft Inception Report | UNICEF with participation of at least one evaluation team member | By September 30, 2020 | Inception Report is presented to ERG |
| 8 | Rounds of comments from ERG | UNICEF | By October 9, 2020 | Comments provided |
| 9 | Address ERG comments to the Inception Report | Consultants | By October 19, 2020 |  |
| 10 | Send the Inception Report for External Quality Assurance and Ethical clearance | UNICEF | By October 19, 2020 |  |
| 11 | External Quality Assurance of the Inception Report Ethical clearance | UNICEF | By October 26, 2020 | External QA facility rating received Ethical clearance is received |
| 12 | Address comments from the External Quality Assurance Facility and Ethics Board Final inception report | Consultants | November 4, 2020 | Final inception report |
|  | Data collection |  |  |  |
| 13 | Fieldwork (meetings w/UNICEF, ERG, partners and stakeholders; remote data collection with respondents); Further review of secondary data | Evaluation team (with support from UNICEF) | Duration of fieldwork: November 9-30, 2020 | Data collection completed; review of secondary data completed |
|  | Report writing |  |  |  |
| 14 | Discussion of preliminary key findings from desk review and field work to ERG | UNICEF and Evaluation team | By December 11, 2020 | The first draft report is presented |
| 15 | Writing up findings of primary data and secondary data analysis Synthesis of findings, drawing conclusions, recommendations and lessons learned Submission of the 1st draft report | Evaluation team | By December 24, 2020 | The 1st draft report is submitted |
| 16 | Feedback on the 1st draft report from ERG and UNICEF | UNICEF | January 11, 2021 |  |
| 17 | Submission of 2nd draft report | Evaluation team | By January 25, 2021 | The 2nd draft report is submitted |
| 18 | Feedback on the second draft report from ERG and UNICEF | UNICEF | By February 11, 2021 | Comments are consolidated and provided to the evaluation team |
| 19 | Presentation of the final report to ERG and verification of recommendations | UNICEF and Evaluation team | By February 19, 2021 |  |
| 20 | External Quality Assurance Mature Final Report | UNICEF | By March 1, 2021 | External QA facility rating received |
| 21 | Finalisation and submission of the final report | Evaluation team | By March 15, 2021 |  |
|  | Dissemination |  |  |  |
| 22 | Human interest stories based on fieldwork | National consultant | By December 11, 2020 | At least three human interest stories |
| 23 | Maximum 5-page evaluation results summary with policy recommendations | National consultant | By March 15, 2021 | Evaluation results summary brief |

- STRUCTURE OF THE REPORTS

The inception and evaluation reports to be produced must be compliant with the UNICEF Evaluation Reports Standards  and the GEROS Quality Assessment System.

The final evaluation report should be written in English and should not exceed 50 pages (excluding annexes). The report should be structured according to the following rubrics:

- Title page and opening pages

- Executive summary

- Background including brief conflict analysis

- Purpose of the evaluation; scope and objectives

- Description of methodology (TOC and conceptual framework and any modifications of TOC made practical for the evaluation)

- Ethical issues

- Evaluation findings,

- Conclusions and lessons learned

- Recommendations (by stakeholders)

- Annexes (including an evaluation matrix with evaluation questions, sources of data, judgment criteria, etc.)

Wherever possible, the report shall contain photos, graphs and charts to illustrate key facts and/or findings.

- DELIVERABLES AND PAYMENT SCHEDULE

The expected result of the assignment is the final evaluation report presenting the results of evaluation as well as lessons learned and recommendations regarding relevance, coherence, effectiveness, efficiency, impact and sustainability of the project activities.   See below table for deliverables and payment schedule:

| Deliverables | Timeline* | Payment |
| --- | --- | --- |
| - Approved Inception report - Presentation of the inception report to ERG | By October 26, 2020 | 30% |
| - Draft evaluation report | By December 24, 2020 | 50% |
| - Max. 50-page final evaluation report (excluding annexes) which meets UNICEF Quality Assurance standards - Presentation of the final report to ERG. | By March 15, 2021 | 20% |

*Timeline for deliverables may be adjusted depending on the recruitment of the team and epidemiological situation in the country.

- MANAGEMENT AND ORGANIZATION

The evaluation will be managed by UNICEF Country Office in Kyrgyzstan. The National Consultant and the Team Leader  will work under direct supervision of UNICEF Child Rights Monitoring Specialist. The support will be sought from the UNICEF Europe and Central Asia Regional Office and external review body as per existing arrangements. The Reference Group will be involved throughout the review process and will contribute to the design, interviews, discussions and finalization of the evaluation report.

The international consultant will conduct the evaluation by fulfilling the contractual arrangements in line with the ToR, UNEG/UNICEF norms and standards and ethical guidelines. This includes preparing an inception report, conducting desk review, undertaking field work, drafting/finalizing report.

UNICEF international consultant will follow the Guidance on External Academic Publishing (January 2017) when engaging in external academic publishing, whether in print or digital form.

Quality assurance of inception report and final draft report is mandatory. UNICEF has external quality assurance mechanism provided through Long-Term Agreements. Consultants will be provided with Quality Assurance requirements in advance.

The UNICEF premises will be available, if needed. UNICEF will provide support in organizing meetings for the purposes of data collection and interviews.  It is expected that the consultant will use his/her own laptop.

The International Consultant will participate in the selection of a national consultant.

The consultant’s fee may be reduced if the assignments/deliverables are not fulfilled to the required standard. In a case of serious dissatisfaction with the consultant’s performance the contract may be terminated in line with UNICEF procedure in such matters and as spelled out in the contract.

Duty station and official travel involved

Due to Covid-19 situation no travel is foreseen under this assignment for international and national consultant.

The evaluation team will consist of one international consultant (Team Leader) and one national consultant.   It is expected that international consultant will work 42 days.  The evaluation team Leader will be in charge of leading the entire process through working with the team member and the Evaluation manager. The Team leader will be responsible for timely and quality deliverables of the entire process as well as of the evaluation outputs.

An international consultant (team leader) will have the following minimum qualifications and experience:

- An advanced university degree (Master’s degree or higher) in political science, sociology or other relevant field;

- A minimum of 6-8 years of experience in leading the design and conduct of international development and peacebuilding programmes and projects evaluations;

- Extensive knowledge and experience in qualitative evaluation methods;

- Demonstrated ability to engage effectively with stakeholders at all level;

- Knowledge of the political and social contexts of Kyrgyzstan;

- Excellent analytical and report writing skills in English;

- Fluency in English is required.  Knowledge of Russian/Kyrgyz is an asset;

- Experience collaborating with UNICEF or other UN agencies;

Expected deliverables from an international consultant:

- Participate in the selection of process of national consultant;

- Undertake desk review of program related documentation and available program data in English language or as per internal division with national consultant;

- Finalize and submit the inception report;

- Participate in the Evaluation launch workshop with ERG and present pre-final Inception Report;

- Undertake the field work that can be conducted in English language or as per division of labour with national consultant;

- Present the final report to ERG and verify recommendations;

- Finalize and submit final report.

| Drafted: | Tolgonai Berdikeyeva, CRM Specialist |
| --- | --- |
| Reviewed: | Aizhan Barakanova, OIC Operation Manager |
| Approved: | Gerrit Maritz, OIC Deputy Representative |
| Date: | August 12, 2020 |

Annex I Project results.

Outcome: Kyrgyz youth and relevant government agencies collaborate and further develop cooperation plans to improve positive interactions with their Uzbek counterparts.

Output 1.1.

Young people have improved critical/design thinking and demonstrate support for diversity and equal rights by initiating projects that contribute to the implementation of plans for local development and positive cooperation of youth between Kyrgyzstan and Uzbekistan

1.1.1. Build young people’s leadership, problem solving skills and promote positive attitudes of peaceful coexistence through collaborative participation in developing local action plans and contributing to the cooperation plans including issues concerning the youth;

1.1.2.  Facilitate youth-led innovative grass-roots solutions to border and cross-border challenges as well as those moving forward regional cooperation across the communities.

1.1.3. Organize national and sub-national events and initiatives of youth organizations in multiple fields and formats jointly with the national youth-related government agencies of Kyrgyzstan and Uzbekistan (conferences, forums, exhibitions, technology quests, Make-thones etc).

Output 1.2:

Parents of young people, community members improve their understanding of diversity, have enhanced knowledge and tools to support and participate in youth -led initiatives.

1.2.1. Provision of knowledge and tools to parents to support youth-led initiatives of young people at local level;

1.2.2. Build capacity of young people to work with the local community members so the youth-led initiatives are inclusive;

Output 1.3.

Government representatives have strengthened capacity to provide services in cross-border communities and commit to support youth-driven initiatives aiming at improving the cross-border cooperation.

1.3.1.  Build the capacity of the youth relevant government agencies on inclusive, gender and conflict sensitive youth work in the field and facilitate exchange meetings with related youth serving Uzbekistan government counterparts;

1.3.2. Build capacities of service providers, justice, rule of law and ombudsman institutions (Osh, Jalal-Abad and Batken branches) and strengthen the complaint mechanism to enhance young women’s and men’s access to services, justice and increase trust, with learning from the collaborative arrangements of similar institutions

Please, follow this link to download full project proposal.

https://mail.kz/ru/news/world-news/glava-kyrgyzstana-podpisal-zakon-ob-uregulirovanii-granicy-s-uzbekistanom

http://www.uneval.org/normsandstandards/index.jsp?doc_cat_source_id=4.

http://www.unevaluation.org/document/detail/102

UNICEF PROCEDURE FOR ETHICAL STANDARDS IN RESEARCH, EVALUATION, DATA COLLECTION AND ANALYSIS, April 2015

https://www.unicef.org/evaldatabase/files/UNICEF_adapated_reporting_standards_updated_June_2017_FINAL(1).pdf

https://www.unicef.org/evaldatabase/files/GEROS_Handbook_FINAL_full_document.pdf