Inception Report – Summative Evaluation of the Impact of using Drones on Population Health and Other Outcomes

Submitted to

UNICEF Malawi Country Office

Submitted by

Edward Chigwedere [MPH, MSc]

Cell: +265 992 829 332

Email: edwardch250@gmail.com

27 December 2020

Implementation Period of Project Being Evaluated

January to September 2020

Table of Contents

Acronyms	3

1.0 INTRODUCTION	4

1.1 Programme Background and Context	4

1.1.1 Health Outcomes:	5

1.1.2 Disaster Management and Preparedness: Climate variability, Rainfall, and Floods	5

1.1.3 Unmanned Aerial Vehicles (Drones)	6

1.1.4 Object of Evaluation	6

1.1.5 Purpose of the Assignment	8

1.1.6 Objectives	8

1.1.7 Scope of Work	9

1.1.8 Evaluation Criteria	9

2.0 METHODOLOGY	10

2.1 Evaluation Strategy	10

2.2 Evaluation Questions	11

2.3 Data Collection Methods	12

a) Desk review	12

b) Analysis of Secondary Data	12

c) Qualitative Interviews	13

2.4 Analytical Approaches  (Including Sampling and Sample Sizes)	15

2.5 Risks and Challenges	16

2.6 Evaluation Ethics	17

2.7 Evaluation Management Arrangements	18

2.8 Evaluation Quality Assurance	18

3.0 EVALUATION WORK PLAN	19

3.1 Team Composition & Responsibilities	19

3.2 Management and Logistics Support	19

3.3 Schedule of Work, Fieldwork Plan & Payment Schedule	19

a) Schedule of Work	19

b) Fieldwork Plan for Chikwawa & Nsanje	20

c) Payment Schedule	21

Annexes	23

Annex 1 Evaluation Matrix	23

Annex 2 Stakeholder Map	29

Annex 3 Evaluation Ethics Standards	30

Annex 4 Tentative Outline of the Report	30

Annex 5 Phases of the Evaluation	32

Annex 6 Detailed Workplan	33

Annex 7 Terms of Reference	34

Annex 8 List of Documents Consulted	58

Annex 9 Data Collection Tools	59

Annex 10 Informed Consent Guide	66

Annex 11 Assent Guide	68

# Acronyms

ARI 			Acute Respiratory Infections

DAC 			Department of Civil Aviation

DFID 			Department for International Development

FCDO			Federal Commonwealth Development Office

FGD			Focus Group Discussion

GBP			Great British Pound

GE			Gender Equity

GDP			Gross Domestic Product

HR			Human Rights

MDG			Millennium Development Goals

MDHS			Malawi Demographic Health Survey

MoH			Ministry of Health

OECD			Organization for Economic Cooperation & Development

REKM			Research Evaluation & Knowledge Management

TA			Traditional Authority

ToR			Terms of Reference

UAV 			Unmanned Aerial Vehicle

UNICEF		United Nations Children’s Fund

UNEG			United Nations Evaluation Group

# 1.0 INTRODUCTION

This Inception Report is submitted in conformity with UNICEF/UNEG Norms Standards and UNEG Ethical Guidelines for Evaluation and technical requirements before commencement of any evaluation. It reflects the consultant’s understanding of the Terms of Reference (ToR) for the Summative Evaluation of Impact of Using Drones on Population Health and other Outcomes he was contracted to undertake by UNICEF - the organization that commissioned the evaluation. It also presents an evaluation methodology based on the same understanding of the ToR. The proposed approach was reached following a review of different key project documents, reviewing of some secondary data gathered during the implementation of the project and scoping discussions with key project personnel from UNICEF REKM Team and other key stakeholders involved in the design, implementation and coordination of the project. This Inception Report is the first deliverable in the evaluation process. It reflects a common understanding reached with respect to how and when the evaluation has to be conducted as guided by the evaluation’s ToR and in full understanding of the challenges posed by COVID-19, and the need for limited movements, social distancing and wearing of face masks/shields as part of COVID-19 preventive measures. Its approval will mark the beginning of the evaluation process. In terms of presentation, the Inception Report starts by presenting an overall background of the project, purpose and objectives of the evaluation. It goes on to present the proposed methodology in meeting evaluation objectives including timelines. Data collection tools, consent forms, list of targeted respondents, among other documents, are attached to the report.

## 1.1 Programme Background and Context

Malawi is a landlocked country with a population of nearly 18 million people – which is estimated to surpass 20 million in the next five years. The country has 28 administrative districts, which are further divided into Traditional Authorities (TA) with villages being the smallest administrative unit. Malawi’s economy has expanded over the past 30 years, with real GDP growth estimated at 4.4% in 2019. It remains predominantly an agricultural country, with agriculture, forestry, and fishing contributing 28% of GDP. Currently, GDP per capita is approximately $380, and given that inflation and population growth currently outpace economic growth, average living standards are falling. About 70 percent of the population lives below the international poverty line of US$1.90 per day (WDI, 2018). Poverty remains particularly prevalent in rural areas, where more than 80% of the population lives.

### 1.1.1 Health Outcomes:

Despite recent achievements, Malawi has not yet achieved optimal health outcomes. Life expectancy remains low at 61 years. Over half of the country’s total disability-adjusted life years are a result of the top four leading causes– HIV/AIDS, lower respiratory infections, malaria, and diarrheal diseases. Malawi has reduced its child mortality rate, leading to achievement of Millennium Development Goal (MDG) 4. However, other indicators remain stagnant or even face declines. The leading cause of morbidity in under-five children is malaria (29%), diarrhea (22%) and Acute Respiratory Infections (ARI) (5%) (MDHS, 2015).

The Malawi health sector operates under a decentralised system guided by the Local Government Act (1998). The Act delegates authority and funding from central government ministries to district assemblies, who guide health sector planning, budgeting, procurement, and service delivery at district and community levels. At central level, the Ministry of Health (MoH) sets strategic direction and formulates sector-wide governing policies. Twenty-nine district health offices oversee services provided in and outside of the district hospital. Five Zonal Health Support Offices (ZHSOs) provide technical support to districts in planning, delivery, supervision, and monitoring of health services. In total, the percentage of government expenditure going toward public health averaged 10.4% from 2012-13 to 2014-15, well below the Abuja target of 15%. Donors have therefore contributed most resources for the health sector in recent years.

### 1.1.2 Disaster Management and Preparedness: Climate variability, Rainfall, and Floods

Malawi is highly vulnerable to the impacts of extreme weather events given its location along the great African Rift Valley, rapid population growth, unsustainable urbanization, climate variability and change, and environmental degradation. The most common weather-related shocks affecting Malawi include floods, drought, stormy rains and hailstorms. Over the past five decades, Malawi has experienced more than 19 major floods and seven droughts, with these events increasing in frequency, magnitude and scope over the years.

In early March 2019, heavy rains developed from a Tropical Depression 11 that formed offshore central Mozambique. Heavy rains hit Malawi, causing severe flooding in the Southern and, to a lesser extent, Central Region of the country. These disaster events have had a significant impact on people’s lives, livelihoods and socio-economic infrastructure in the affected areas, pushing many people into poverty and food insecurity. In total, an estimated 975,000 people were affected, with 86,976 displaced, 60 killed and 672 injured. The devastating heavy rains and floods caused substantive damage and loss across the social, productive and infrastructure sectors, with the social sector experiencing most of these effects. The housing subsector experienced the greatest damage, with 288,371 houses being partially or destroyed. Most affected people were accommodated in temporary internally displaced people (IDP) camps, mostly located in classrooms and school facilities, with limited access to safe water and sanitation facilities. This resulted in significant disruptions to learning and teaching activities at the school. In addition, the 2019 floods affected roads, bridges, power supply lines, irrigation infrastructure and mature crops. Power supplies were interrupted for more than two days across the country.

The extent, time, and impact of natural disasters such as Cyclone Idai could be predicted and the damage to sectors, assets, facilities and infrastructure could be mitigated or reduced, if geographical information systems would be supported by necessary accurate flood modelling and prediction analysis. Subsequently, such analysis would significantly improve disaster preparedness plans and early warning systems, ensuring that affected and vulnerable communities get all the necessary support and commodities in a timely manner, without big delays. Currently, early warning systems and innovative disaster preparedness practices in Malawi are developing; however, much of the evidence used to make informed decisions is scattered, not optimized, and not even hosted on geographic information systems. This makes the preparedness process complicated and inconsistent, which ultimately leads to the situation of vulnerable communities not getting necessary humanitarian help.

### 1.1.3 Unmanned Aerial Vehicles (Drones)

In the wake of the above context, the UNICEF Malawi Drones Program has been operational since 2016 and has proven to be a successful intervention in delivering development and humanitarian aid. Drones in Malawi are used as a transportation modality, to conduct site surveys and aerial monitoring, acquiring images, mapping, and remote sensing. The uses have been singular in their operations: drones technology application in Malawi up until now has been used for a single purpose at a time in their execution. As the use of drones is maturing, there is a need to understand ways in which the efficiency, efficacy, and versatility of the use of these drones can be increased. The drones project commenced without an elaborate theory of change or logic model. This summative evaluation is also expected to retrospectively construct a theory of change in consultation with all key partners.

### 1.1.4 Object of Evaluation

The object of this Summative Evaluation covers the Sustained Multipurpose Unmanned Aerial Vehicle (UAV) Operations in Southern Malawi pilot project. The project focused on the flood-prone districts of Chikwawa and Nsanje. These districts are in need of alternative transportation modalities during rainy and flood seasons, as some of the health facilities are in hard-to-reach areas. Both districts have a need for better access to information about flood-affected and flood-prone areas. High resolution aerial imagery was to be captured as part of the project. This imagery is used, in other projects, to create contingency and emergency preparedness plans, evacuation plans, and other analytical assets for improved emergency response.

The project utilized a comprehensive, continuous multi-purpose drone operation, to provide two important functions: (1) Collecting detailed, hard-to-access aerial data, which can then be turned into vulnerability maps (flood modelling, community planning, mosquito breeding site identification, infrastructure inspection and similar) to help make detailed emergency preparedness and resilience plans, run flood modelling, identify potential hotspots for disease outbreaks, evaluate crop health and yields, and others; (2). Delivery and pick-up of medical commodities, emergency medicine, diagnostic samples and results, providing timely regular or emergency on-demand delivery services for medical centers. The main purpose of the project is to establish a viable multi-purpose UAV (drone) operations in Malawi, to realize the impact of UAVs in development and humanitarian contexts in a financially sustainable, long-term manner. The project has been using drones to deliver healthcare in Malawi and also conducting aerial imaging ultimately used for disaster management. In view of the above some expected outputs from the project included aerial data collected from hard to reach areas, vulnerability maps developed, medical commodities, emergency medicine, diagnostic samples and lab results picked and delivered in a timely manner.

The pilot drone operations were conducted from January to September 2020. The pilot phase was designed to understand answers to four key questions: (1) Does the project have a positive social impact? (2) Do users engage with it? (3) Does the technology of drones work? (4) Will the use of drones grow after the pilot? The pilot and its constituent drone operations were spread over four phases, called Sprints, with a total budget of GBP 150,000. Each phase had specific experiments to derive learning from. To date, more than 1,180 flights have been conducted, totaling 38,500 km flown in Malawi, and the operations employed five full-time Malawian employees. These flights have delivered medical supplies, medicines, vaccines, and medical bio-samples within the areas of Nsanje (Tengani, Chididi, Ndamera, Nyamithuthu, Mbenje, Lulwe, Phokera, Kalemba, Makhanga, Trinity, Masenjere, Sankhulani, Osiyana), Chikwawa (Bereu, Mapelera, Nchalo, Chapananga, Majete). More than 30 of these flights are related to the COVID-19 response.

The project was designed by DFID and UNICEF, and implemented by UNICEF, Swoop Aero (drone operator), UKaid Department for International Development (DFID) and FTL (technology advisor to DFID). UNICEF and UKaid have together considered how to use drones more widely as tools to more effectively deliver their collective mandates. For the purposes of this project, an Australia-based drone logistics company Swoop Aero was selected, to conduct the multi-purpose drone operations. UKaid and UNICEF Malawi closely worked with University of Malawi, College of Medicine, a Malawi-based academic institution that is focused on knowledge and research strengthening in the fields of medicine. College of Medicine was a co-investigator of the project, responsible for conducting a thorough ethical clearance, monitoring and evaluation of the project’s health-related outcomes, as well as ensuring the project’s alignment with the health system’s stakeholders in both districts. The project closely collaborated with District Commissioners (Nsanje and Chikwawa), respective district officers (District Health Officers, Disaster Risk Reduction Officers, and others) and their national counterparts from Ministry of Health, Department of Disaster Management Affairs, Central Medical Stores, as well as Water Resources Department. Department of Civil Aviation (DCA) was an integral part of the project, as they are responsible for inspecting and approving flight operations, including the transportation of dangerous goods. The DCA as per regular protocol, conducts regular check-ins with the drone team to ensure the highest standards of safety and operational practices in the field. Whilst gender equity and human rights are critical issues to UNICEF, it is worth noting that most of the documents reviewed in preparation of submitting this Inception Report are silent about these issues. It is yet to be established during interviews and further secondary review if indeed this project missed these issues.

## 1.1.5 Purpose of the Assignment

The major purpose of the summative evaluation is to draw some lessons from the implementation of the pilot project while examining and evaluating its relevance, effectiveness, efficiency and sustainability. It, therefore, aims to collect high-quality, impartial evidence focusing on learning that could enable evidence-based decision-making by identifying strengths and weaknesses of the pilot project. Finally, the summative evaluation is expected to make recommendations for project quality improvement and further action related to the sustainability and scaling up. The target audiences of the evaluation and their expected use of learning from evaluation include:

- UNICEF Malawi Country Office and the Regional Office to determine lessons learnt from the pilot project, its efficiency and effectiveness potential for scale up in Malawi or within the region;

- Drone operating partners notably Swoop Aero and FTL in understanding the impact of their social investment

- Government partners notably the Ministry of Health, Ministry of Agriculture, Irrigation and Water Development and Ministry of Local Government for policy guidance on future programs and learning on innovative approaches in emergency preparedness and delivery/picking of emergency medical supplies in hard to reach areas across the country.

- Host communities in Chikwawa and Nsanje and other districts in Malawi  to learn about benefits from these drone operations, and;

- Donors, notably FCDO/DFID for project accountability, and determining efficiency and effectiveness

## 1.1.6 Objectives

The primary objectives of this evaluation are:

- To assess the extent to which the DFID-funded drone transportation project on health service provision and flood mapping was successful in achieving desired results

- To determine whether the project was able to find answers for the four key research questions – (1) Does the project have a positive social impact? (2) Do users engage with it, (3) Does the drone technology work? (4)  Will the use of drone grow after the pilot

- To assess the extent to which the project was sustainable, scalable and how much difference it made and whether it was executed efficiently?

The specific objectives of the evaluation are to:

- Assess the extent to which project activities were implemented in the cost-efficient manner across genders and all socio-cultural groups including the vulnerable in the targeted communities

- Assess effectiveness of the drone project in producing the expected results for both men and women, boys and girls across all socio-cultural groups including the marginalized and vulnerable in the targeted communities

- Assess the outcomes of drone operations and to which extent the project has contributed to improving the health outcomes and disaster preparedness in Nsanje and Chikwawa

- Evaluate whether the drone transportation was relevant to address the main bottlenecks across all socio-cultural groups including the vulnerable in the targeted communities

- Assess the extent to which the intervention promoted observance of HR and GE and how stakeholders regardless of sex, geographical location, disabilities, age have benefited from the ntervention

- Document lessons, key challenges/gaps, strengths, good practices

- Assess how sustainable the drone program is at the district and national levels.

## 1.1.7 Scope of Work

The drones project was implemented from January to September 2020. This evaluation shall focus on the project implementation period (January to September).  Preparatory activities undertaken prior to implementation of the project, particularly in relation to the theory of change, will be included. With regards to geographic coverage, most of the evaluation activiites shall be at district and community level focusing on the two districts of Chikwawa (including the 19 project catchment areas of Ndakwera, Mapelera, Chipwayira, Mkumaniza, Gaga, Gola, Makuwira, Mfera, Nchalohanga, St. Montfort, Ngabu, Chithumba, Majete, Kakoma, Chapananga, Bereu, Misomali, Kapichira, and Dolo) and Nsanje (including the 15 project catchment areas of Mbenje, Lurwe, Chididi, Nyamithuthu, Tengani, Ndamera, Kalemba, Masenjere, Trinity, Sorgin, Oseana, Makhanga, Sankhulani, Masenjere, and Phokera). As noted in the objectives section above, this evaluation will assess the relevance, effectiveness, efficiency, sustainability and observance of human rights and gender equality not excluding lessons learnt, strengths, gaps and making recommendations. The effect of the project to (1) people’s lives and community well-being, (2) access to health, nutririon and infrastructure, and quality of knowledge and learning from the project will also be assessed. Beyond the two districts of Nsanje and Chikwawa, this evaluation shall also assess the relevance and sustainability of such a project at national level and equally highlight lessons, challenges, gaps and strengths of a project of this nature at national level.

## 1.1.8 Evaluation Criteria

The OECD/DAC Evaluation Criteria will guide this evaluation. Particular focus shall be on the relevance, effectiveness, efficiency, sustainability and the extent to which gender and human rights issues were addressed during project implementation. The following definitions, adopted from the OECD/DAC evaluation criteria, shall guide this evaluation.

Relevance - The extent to which the project design and implementation was relevant to national/provincial priorities and needs of men and women beneficiaries in terms of achieving expected results across all socio-cultural groups including the vulnerable in the targeted communities

Effectiveness -The extent in which the implementation strategies were effective and successful in achieving the planned outcomes/results for rich and poor men and women across all socio-cultural groups including the vulnerable in the targeted communities

Efficiency- The extent to which the outputs of the intervention has been achieved (in terms of quality and quantity) with the allocated resources/inputs (such as funds, time, and procedures)

Sustainability - The extent to which various stakeholders including the public sector, civil society and households are likely to sustain the behavior change related to the goals of the project after it has ended

Gender and Human Rights - The extent to which the intervention contributed to observance of human rights and gender equality in Malawi and the targeted communities. The extent to which stakeholders regardless of sex, geographical location, disabilities, age have benefited from the intervention

# 2.0 METHODOLOGY

This section briefly presents the proposed approach in undertaking this evaluation following some scoping meetings with key project personnel and a review of project documents. Suffice noting that this project was implemented without (1) a baseline or clear description of the situation before the start of the project and (2) a clear statement of intended outcomes upon completion of the pilot project. There however are some project documents (noted in the desk review section) that give a list of activities (experiments) that had to be undertaken over four phases (referred to as sprints) with itemized budgets for each phase/sprint, expected timeframes etc. There also are some progress update reports and data from the University of Malawi, College of Medicine, Swoop Aero and FTL that give a picture on how the project progressed. Suffice noting though that these reports do not give a clear indication of outcome results at different reporting periods but rather present a list of activities undertaken. Furthermore, most of the data is not disaggregated by sex and there is very little to no reporting on the socio-cultural, gender equity and human rights components of the project. Against this background, a mixed-methods approach is proposed in meeting the evaluation objectives. It is assumed triangulation of different methods will assist in getting an overall impression of lessons learnt in the implementation of the project.

## 2.1 Evaluation Strategy

A mixed-methods approach is proposed in undertaking the summative evaluation of this pilot drones project. Essentially desk review, analysis of secondary data (gathered by College of Medicine, Swoop Aero and from the Health Management Information System in Chikwawa and Nsanje Districts)  coupled with qualitative evaluation methods in the form of Key Informant Interviews, in-depth interviews, Focus Group Discussions (FGDs), case studies, observations, photographs etc are going to be used.  Appreciating the need for this evaluation to also assess the social-cultural and gender inclusion, a social impact assessment of the project shall be imbedded in the evaluation strategy. Figure 1 presents the proposed framework in undertaking the evaluation with subsequent section presenting detailed information on each of the proposed methodology. No quantitative interviews are going to be used as they are deemed not appropriate given the design of the project noted above.

With regards to sampling of participants for qualitative interviews, non-probability sampling methods like headhunting, referrals, snowballing are going to be used at community level. The consultant will establish catchment areas where the project was implemented, and guided by the traditional leadership in the implementation area, select participants to be interviewed for this evaluation. Out of the 19 project areas in Chikwawa and 15 in Nsanje, three project catchment areas have been randomly selected for each of the districts for qualitive interivews. These are Trinity, Sankhulani and Chididi in Nsanje and Gaga, Chitumba & Ngabu in Chikwawa.

Whilst theoretical saturation is expected to determine sample size for the qualitative interviews, it should be made clear that COVID-19 related restrictions and the tight project deadlines are likely to limit the extent to which exhaustive interviews, particularly at community and district level, are undertaken. Interviews with key informants are proposed to be undertaken virtually (using Zoom, Microsoft Teams, Skype, WhatsApp) or using phones. In line with ethical standards in research/evaluation, all participants sampled for the evaluation will have to give informed consent before being interviewed.

Figure 1 Proposed Framework in Undertaking the Summative Drones Evaluation

## 2.2 Evaluation Questions

This summative seeks to respond to 3 overall questions vis:

- To what extent were Unmanned Aerial Vehicles (drones) under this project successful in capturing high resolution aerial imagery that can be turned into vulnerability maps useful for emergency preparedness and resilience plans

- To what extent were drones in the project successful in delivering and picking medical commodities, emergency medicine, diagnostic samples and results providing emergency on-demand delivery services for health centers?

- “To what extent were the 4 project questions [(i) Does the project have a positive social impact? (ii) Do users engage with it? (iii) Does the technology of drones work? (iv) Will the use of drones grow after the pilot?] answered?

Guided by the objectives of the evaluation and the OECD/DAC evaluation criteria, this evaluation should also answer the following specific questions:

- Were the project design and implementation relevant to national, district and community needs and priorities including men, women, children and other vulnerable members of society in targeted communities?

- Was the project effective/successful in achieving planned outcomes/results including for poor men and women across all socio-cultural groups including the vulnerable in the targeted communities?

- Were project activities implemented efficiently/on time and within the allocated resource/input limits?

- Is the project sustainable/going to continue beyond the pilot phase?

- To what extent did the project contribute to observance of human rights and gender equity in Malawi and the targeted communities?

- What challenges and key lessons were learnt during the course of the pilot project? ,

It should be noted that the three above noted overall research questions of the project shall be reviewed/evaluated under the effectiveness evaluation criteria. Some more specific questions on each of the OECD/DAC evaluation criteria are presented in the matrix (Annex 1).

## 2.3 Data Collection Methods

### a) Desk review

A review of project documents had been initiated and is ongoing. Documents being reviewed include:

- DFID, UNICEF, FTL and Swoop Aero Project Document – Sustainable Multi Purpose Drones Operations in Southern Malawi

- Proposal and supporting documents submitted to the College of Medicine for ethical review

- PR Document

- Minutes of Stakeholder Meetings

- Project Handover Plan

- Sprint 1,2,3 and 4 plans and budgets

- Sprint Reviews

- Emails between different stakeholders

- The Sustained Drones Operations in Southern Malawi July 2020 Report by College of Medicine

- The Sustained Drones Operations in Southern Malawi October/November 2020 Report by College of Medicine

- UNEG Norms and Standards

- UNICEF procedures for ethical standards

Desk review will be undertaken to get a detailed background on why and how the project was implemented. Desk reviews also allow tracking of exact figures, dates, gaps etc of project activities that were undertaken from inception of the project up to the end – a very important activity in end of project evaluations. It has been observed from the desk review so far that there is very little to no reporting on how project activities were to be implemented across genders, socio-cultural groups including the vulnerable in targeted communities. This information is expected to be gathered through triangulation with the other evaluation methods noted below.

### b) Analysis of Secondary Data

Secondary analysis of data, as earlier noted, is going to be undertaken. There are four sources of secondary that have since been identified. These are:

- Swoop Aero data that details operations of the drones. Data availed so far reflects the number of flights undertaken, duration of the flights, success rate, cost data among other indicators.

- College of Medicine data that presents commodities/supplies delivered to targeted destinations/health centers using drones during the project

- Chikwawa and Nsanje Health Management Information System data on some selected indicators related/linked to deliveries made to respective health facilities within the two districts

- Supply chain data (focusing on last mile distributions, distance covered in distributions, supply fill rate, last mile conformance) from the Central Medical Stores Trust, the Nsanje and Chikwawa DHOs and the targeted health centers in assessing the effectiveness and cost efficiency of drones.

This summative evaluation is not going to gather any quantitative data because the design of the project, right from inception, does not allow much usage of such data.  There was no baseline for the project for example that one could use to compare the situation before and after the project. Accordingly, a review of secondary project data from the aforementioned data sources is proposed so as to allow assessing possible effect of the project on project related indicators that were tracked before and during the project. A time series analysis of secondary data from relevant HMIS indicators, supply chain activities for 1 – 5 years preceding the project is proposed so as to assess how much effect the project might have had across a number of indicators. Some of these indicators to be reviewed from the HMIS system cover early infant diagnosis, viral load tests, sputum transportation, TB tests etc, Furthermore, it has been noted through desk review that the project documents are a little silent on gender equity and human rights issues. A review of GE and HR related data is envisaged to present a better understanding of the project in these areas.

### c) Qualitative Interviews

A combination of qualitative methods as presented below is going to be used in this evaluation. Key among them are:

- Key Informant Interviews

Key Informant Interviews are going to be undertaken with key project stakeholders that were involved in the planning, implementation and review of the project. These are stakeholders whose roles are noted to have been key in planning, financing and overseeing the overall implementation of the project at national/higher level. These include relevant personnel from (1) UNICEF Malawi and other UNICEF personnel outside the Malawi office who were involved in the design and implementation of the project, (2) Swoop Aero, (3) DFID/FCDO Malawi, (4) University of Malawi, College of Medicine, (5) Department of Civil Aviation. Also targeted for these interviews are other national counterparts from the (6) Ministry of Health, (7) Department of Disaster Management Affairs, (8) Water Resources Department and (9) Central Medical Stores and the Central Medical Stores Trust. These key informant interviews are expected to allow filling in of gaps picked from review of project documents and analysis of secondary data. In other words key informant interviews are proposed to provide a clear picture on important grey areas in the designing and implementation of the project that is not captured in project documents and available project data. An interview guide has been developed for these interviews. Refer to Annex 9.

- In-depth Interviews

In-depth interviews are also going to be undertaken at district and community level in Chikwawa and Nsanje. Targeted interviewees are persons that were involved in the day-to-day running or implementation/coordination of the project both at district and community level. These should include (1) relevant personnel from Nsanje & Chikwawa District Commissions, (2) District Health Officers or their representatives in Nsanje and Chikwawa, (3) Disaster Risk Reduction Officers from Chikwawa and Nsanje Districts, (5) health in-charges or their representatives from 5 targeted health centers in Chikwawa and 3 health centers in Nsanje, (6) traditional leaders (such as Traditional Authorities, Village Headmen/Headwomen) from health facility catchment areas of the sampled 5 health centers in Chikwawa and 3 health centers in Nsanje, (7) community health workers/volunteers/riders for health from sampled areas in Chikwawa and Nsanje. These in-depth interviews are envisaged to provide a district and community level perception on the effectiveness, relevance, sustainability and human rights and gender perspective on the project. They are expected to provide an unfiltered review of the entire project mostly from a beneficiary perspective. An interview guide has been developed for these interviews. Refer to Annex 9 for the guides.

- Focus Group Discussions

Focus Group Discussions (FGDs) with community members from sampled health facility catchment areas in 5 and 3 sampled project implementation areas in Chikwawa and Nsanje respectively are also going to be undertaken. FGDs are proposed as they are seen to provide an opportunity to get detailed community level qualitative opinions/information from a sizeable number of targeted project beneficiaries on how the project was implemented particularly with regards to effectiveness, relevance and gender and human rights issues. These FGDs are also envisaged to assist in drawing some lessons with respect to how socio-cultural issues are addressed when new technologies are introduced, lessons on potential or possibilities of scaling up etc. These FGDs are going to target men and women in the project implementation areas. In line with FGD recommendations, each FGD will constitute 6 – 12 participants. A total of 5 FGDs are planned in Nsanje and 3 in Chikwawa. Final determination on the exact health center catchment areas to be sampled for FGDs will be made upon getting detailed information on the location of the 19-targeted communities in Chikwawa and 15-targeted communities in Nsanje when fieldwork starts. More FGDs are planned in Nsanje than Chikwawa because the targeted project communities are much more in Nsanje than Chikwawa. Participatory FGD facilitation methods such as Venn diagrams, force field analysis/contribution analysis, ranking will be used. Refer to Annex 9 for the guides

- Social Impact Assessment

Given the keen interest in assessing the extent to which the project had a social impact on community members in the project implementation areas, a mini social impact assessment is going to be embedded in this summative evaluation. The social impact assessment will essentially assess the intended and unintended, both positive and negative social change processes invoked by the drone project. Particular attention will be paid on the extent to which community members’ lives were changed from a socio-cultural, economic, gender equity and human rights perspective.  These issues will be included/covered in the qualitative interview guides used during in-depth interviews and FGDs at community level.  Refer to Annex 9 – HR & GE sections.

- Case Studies

Some case studies are going to be used in qualifying some project outcomes across different activities that were implemented during the drones pilot project. They are also expected magnify some key themes about drones, population health and development as learning experiences since these are new innovations.

d) Cost Efficiency Assessment

An assessment of the extent to which project activities were undertaken in the most cost efficient manner is also embedded in this summative evaluation. Effectively a review of actions taken to ensure accomplishment of objectives with the lowest expenditure of resources will be explored. This will imply assessing the different activities that were undertaken, why those activities were undertaken compared to alternatives and the cost of the activities undertaken compared to the alternative options. As such costing data from the project will be used. It is however hoped most of the essential costing data will be available for the assessment from both Swoop Aero and the College of Medicine. Preliminary data provided by Swoop Aero does have some of the costing data though there are also some gaps that will require following up. It is hoped that the College of Medicine will also be able to provide such cost data based on the budgets used in the implementation of the project.

Observations and Photos

During field visits in Nsanje and Chikwawa observations and phots shall also be used in assessing the effect, relevance, efficiency, sustainability and overall response to gender equity and human rights issues where possible. Observations and photos are chosen because they, if used appropriately, provide a rich and full explanation on a subject under review. In appreciation of the challenges associated with observations and photos, particularly the possibility of erroneous attributions, these two methods will be triangulated with qualitiative methods, desk review and secondary data to ensure that inappropriate attributions are avoided.

## 2.4 Analytical Approaches

This evaluation shall make use of all relevant secondary data availed to the consultant. Basing on the quantitative data that has been provided, simple descriptive analysis of secondary data using Excel is proposed. Should there be some big datasets to be provided, especially from the HMIS, SPSS or Epi Infor will be used. No advanced statistical approaches will however be used even if large volumes of data are to be presented later because of the overall design of the project. With regards to qualitative data, N-vivo shall be used in undertaking thematic and content analysis of all qualitative data.

## 2.5 Risks and Challenges

This summative evaluation is going to be undertaken during the COVID-19 pandemic. Despite the current low cases of COVID-19 in Malawi, the risk for one to contract the virus is still there. It will therefore be mandatory for the consultant to adhere to recommended COVID-19 prevention measures such as social distancing, wearing of facemasks/shields, and putting on hand gloves and washing of hands regularly to minimize the chances of infection. Protective preventive equipment such as facemasks, hand sanitizers, hand gloves will be part of the essential supplies the consultant will take when he travels to Chikwawa or Nsanje, The consultant proposes to drive himself in his personal 4x4 vehicle to minimize the risk of infection when drivers and other supporting staff is hired.

Because of COVID-19, most organizations are encouraging their personnel to operate from home. Whilst the practice limits the chances of spreading COVID-19, this may also delay the speed with which data collection will be conducted. As such, contacting targeted respondents early and usage of virtual communication systems such as Zoom, Microsoft Teams, Skype and telephones is suggested wherever feasible. These virtual communication systems are however not feasible with targeted community level respondents in Chikwawa and Nsanje. It will therefore be mandatory for the consultant to travel to the two districts. As earlier noted, the consultant will operate under strict COVID-19 prevention measures.

Documents and secondary data reviewed in preparation of this Inception Report have revealed some big gaps in availability of data particularly around progress in meeting project outcomes, the extent to which men, women, children and other vulnerable members of society were reached by the project, the extent to which the project fostered observance of human rights and gender equity among other indicators. Despite a few documents and data still to be provided to the consultant for review, it is very unlikely they will address any of the noted gaps. This consultant, as noted above, is proposing to use HMIS data, district level reports and have face-to-face interviews with district community level personnel that were involved in the project implementation and community members in the project implementation areas and triangulate findings in an attempt to compensate for the data gaps and present a more objective evaluation. Accordingly, fieldwork will be very necessary.

Whilst going to the field will be very critical, it should also be noted that this evaluation is coinciding with the beginning of a rainy season in districts that are vulnerable to floods. It is therefore planned that fieldwork be conducted as early as possible before the rainy season gets to peak and a 4x4 vehicle will be used during fieldwork.

The revised schedule of the evaluation has coincided with the starting of the festive holidays. This is likely going to be challenging in meeting targeted people at district level. Efforts are however underway, with support from UNICEF, to contact expected respondents prior going into the field. Follow-up plans will be made should the consultant fail to meet most of the targeted persons.

To ensure protection of evaluation participants, no names shall be recorded and reported during the evaluation process. This also applies to every participant in the evaluation including the vulnerable members of society. Evaluation numbers or pseudo names shall be used instead whenever there is need for referring to a name with that information also clarified.

## 2.6 Evaluation Ethics

Guided by the UNEG Norms and Standard and the UNEG Ethical Guidelines, the following ethical issues were considered:

- There are no conflicts of interest that have been identified in this project that can be reported. Should any be identified, due processes will be followed in reporting.

- With regards to inclusion and exclusion criteria, people who were involved in the design, implementation, coordination including community members in project implementation areas are all targeted using non-probability sampling methods. Only respondents who do not know anything about the project, those not willing or unable to participate for various reasons will be excluded from participation because participation has to be voluntary and by design of this evaluation, only people knowledgeable about the project are best recruited upon giving consent or getting assent.

- There will be no payment or compensation for participating in this summative evaluation in an effort to avoid inducement. The consultant will make sure he visits potential respondents (at community level) or makes telephone calls so as to avoid respondents incurring any costs from participating in this evaluation.

- This evaluation is, by design, considered a low risk evaluation with little to no stress expected to be experienced by respondents. Since secondary data particularly from the project and HMIS is going to be used, it is likely that some respondents may end up being identified if due processes are not followed during analysis. To ensure such harmful events do not happen, all personal identifiers on all secondary data will be removed and replaced with new codes and delinked from any data sources linked to personal identifiers.

- With regards to consenting, all respondents will be interviewed upon giving consent. In line with COVID-19 preventive measures, informed consenting is proposed to be verbal so as to limit contacts through  exchanging/sharing of papers, pens etc – experiences that can work in spreading the virus. Apparently, most of the interviews with key stakeholders are going to be done over the phones or virtually. Informed consenting will be done in a language the participant is most comfortable with. At community level, this is likely to be in Chichewa (the local language for Nsanje and Chikwawa).

- To ensure confidentiality and privacy during the data collection process and upon collecting the required data, all interviews shall be conducted in secluded places where respondents’ views/opinions are not overhead by other people. All interview notes and any other hard copies of project data will be kept at the consultant’s office in a locked cabinet only accessed by the consultant. All electronic data will be saved and password protected so that only the consultant can access the data/or any electronic information gathered during the course of the evaluation.

- With regards to dissemination of evaluation findings, it is important to convey findings of the evaluation to different respondents at different levels including respondents. UNICEF Malawi will be coordinating and undertaking that. As such evaluation results or any information/data with personal identifiers or any features/characteristics that may lead to harmful identification of certain individuals will be delinked or anonymised during analysis.

This evaluation, as clarified by the REKM Team, will go for independent (arranged by UNICEF) ethics approval. As such this Inception Report has been submitted guided by UNICEF Research Ethics guidelines with informed consent/assent guides appended in the Inception Report.

## 2.7 Evaluation Management Arrangements

In line with UNICEF’s evaluation policy, this evaluation will be managed by the Chief REKM (Mussarrat Youssuf) as the Evaluation Manager with Abiba Longwe Ngwira, Benson Kazembe and Zuheb Siddiqui being part of the Evaluation Reference Group providing guidance and direction in the entire evaluation exercise. The consultant will be responsible for the impartial and independent evaluation of the project in line with project’s evaluation objectives. He has developed the interview guides and will undertake the interviews, analyze all collected data and write the report. Looking at the tight deadlines of the assignment, the consultant will engage one Research Assistant to assist with the data collection particularly at community level. The Research Assistant will assist in undertaking qualitative interviews at community level.  All costs for the Research Assistant are going to be met from the consultant’s budget.

## 2.8 Evaluation Quality Assurance

All evaluation reports shall, in line with UNICEF’s quality assurance policy, be reviewed by the REKM Team and the consultant will address any queries or issues raised. The consultant shall also make sure evaluation ethics relating to respect for individuals, beneficence/non-maleficence, justice/equity are adhered to during the entire course of the evaluation. Detailed weekly updates to UNICEF Malawi and the entire REKM Team on how the evaluation is progressing will also work as a quality control mechanisms as discussions on what is happening will allow assessing if recommended evaluation procedures are being followed as per agreed timelines.

# 3.0 EVALUATION WORK PLAN

## 3.1 Team Composition & Responsibilities

This is an individual consultancy where the consultant shall be responsible for all evaluation activities from the start up to the completion of the assignment.

## 3.2 Management and Logistics Support

UNICEF Malawi and the REKM Team will be responsible for the management of this evaluation exercise. Whilst the consultant shall be responsible for the actual designing and implementation of summative evaluation with UNICEF REKM Team overseeing the whole process, UNICEF Malawi will also be responsible for making the following logistical arrangements:

- Introducing the consultant to stakeholders at national and district level

- Preparing an introduction letter to be taken by the consultant when going to the field

- Making internal UNICEF logistical arrangements in preparation of the consultant’s departure for fieldwork

- Making logistical arrangements for validation workshops

- Making logistical arrangements in preparation of policy briefs and informatics

## 3.3 Schedule of Work, Fieldwork Plan & Payment Schedule

### a) Schedule of Work

Table 1 presents the proposed schedule of work for this evaluation presenting activities, deliverables, estimated number of days, estimated completion date and responsible person/institution.

Table 1 Schedule of Work

| Key activities/tasks | Deliverable | Estimated number of days | Estimated completion date | Responsible person/institution |
| --- | --- | --- | --- | --- |
| Draft Inception Report including data collection tools, informed consent guides + fieldwork protocols, | Initial Inception Report, tools, consent forms & field protocols | 15 days | 01 Dec. 2020 | Edward |
| Revision of Inception Report, tools, informed consent guides & submission of Final Inception Report | Final Inception Report | 2 | 10 Dec. 2020 | Edward |
| Document review, Data collection with key stakeholders/collection and analysis of secondary data | Data collection updates | 25 | Dec-January 2021 | Edward |
| Fieldwork in Chikwawa & Nsanje | Fieldwork updates | 8 | January 08 2021 | Edward |
| Triangulation of collected data/writing | Data analysis updates | 10 | 18 January 2021 | Edward |
| Submission of Draft Report vs 1.0 | Draft Report vs 1.0 | 4 | 22 January 2021 | Edward |
| Review /Discussion on preliminary findings with key stakeholders/soliciting feedback | Remote workshop | 1 | 23 January 2021 |  |
| Submission of Revised Report | Draft Report vs 1.1 | 3 | 28 Jan 2021 | Edward |
| Preparation & submission of powerpoint presentation; Draft policy brief & inforgraphics | Draft PPT, policy briefs & inforgraphics | 15 | 15 February 2021 | Edward |
| dissemination workshop and presentation of evaluation findings/recommendations | Presentation | 1 | 20 February 2021 | Edward & UNICEF |
| Review & submission of final report (hard copy) | Final Report | 6 | 25 February 2021 | Edward |

### b) Fieldwork Plan for Chikwawa & Nsanje

A total of 7 days have been set aside for collection of district level data in Chikwawa and Nsanje. Table 2 presents suggested activities, proposed dates and the number of days undertaking each activity.

Table 2 Chikwawa Nsanje Fieldwork Plan

| Activity Dates | Activity | Number of Days |
| --- | --- | --- |
| 1 Jan 2021 | Travel from Lilongwe to Blantyre | 1 |
| 2 – 4 Jan 2021 | Fieldwork in Chikwawa/Nsanje | 3 |
| 4 Jan 2021 | Travel to Nsanje | - |
| 5 – 7 Jan 2021 | Fieldwork in Nsanje | 2 |
| 07 Jan 2021 | Travel from Nsanje to Blantyre | - |
| 08 Jan 2021 | Travel from Blantyre to Lilongwe | 1 |

### c) Payment Schedule

Table 3 presents proposed payment schedule linked to deliverables.

| Deliverable | Expected Completion Date | Payment ration (%) |
| --- | --- | --- |
| Inception Report with work plan | 31 Dec 2020 | 20 |
| Draft evaluation report, policy review & infographics | 24 Feb 2021 | 40 |
| Presentation at validation workshop | 15 March 2021 | 10 |
| Final Evaluation Report incorporating comments from the validation workshop accompanied by policy brief, infographics | 30 March 2021 | 30 |

# Annexes

## Annex 1 Evaluation Matrix

| Key Evaluation Questions | Specific sub questions | Data Collection Methods | Data Source | Indicators/Success Standards | Methods of Analysis |
| --- | --- | --- | --- | --- | --- |
| Relevance To what extent was the project design and implementation relevant to the national/district priorities and needs of men and women beneficiaries in terms of achieving expected results across all socio-cultural groups including the vulnerable targeted communities? | - How relevant and meaningful were the project objectives and activities in terms of addressing the needs and priorities of marginalized and vulnerable children, men and women, in the project areas? - To what extent were the objectives and strategies used relevant to national (Government of Malawi) priorities and policies related to health outcomes? - How relevant is the selection and targeting of project areas (districts and villages) with regard to program objectives? | Desk review + secondary review of project data + qualitative interviews. | -Project reports -Project secondary data -Qualitative interviews -Literature on disaster response | - Number/type of project activities addressing health transportation challenges and disaster management emergencies at national level - Types/number of health transportation problems affecting project implementation areas addressed by the project - Types/number of emergency disaster management challenges affecting the project in targeted areas addressed by the project - Number of districts and villages vulnerable to floods and with health facilities situated long distances from village that were targeted under the project. - Case studies and/or Most Significant Change stories Explanations/quotes on relevance of the project | - Descriptive analysis of secondary data Content analysis of qualitative data and project documents |
| Effectiveness To what extent were implementation strategies effective and successful in achieving the planned outcomes/results for rich, poor men and women across all socio-cultural groups including the vulnerable in the targeted communities? | - To what extent did the DFID-funded drone transportation project on health service provision and flood mapping, including multi-purpose drone operations was successful in achieving its objectives? - What were the major factors influencing the achievement or non-achievement of the objectives? - To what extent has the implementation of strategies and project approaches - such as use of multi-purpose drones- worked as intended? - How effectively UNICEF engaged with the Government to strengthen coordination and how far government leadership and political will influenced the achievement of results, or vice versa? - How successful was UNICEF in reaching the most vulnerable groups in the target areas? - What other changes (positive/negative, direct/indirect, intended/unintended) have occurred as a result of the project interventions? | Desk review + secondary review of HMIS, Swoop data + qualitative interviews including case studies. | -Project reports -Project secondary data -Qualitative interviews | - Number of planned health services transportation flights achieved including factors facilitating/hindering progress - Number of planned aerial mapping flights achieved including factors facilitating/hindering progress - Proportion of men, women including vulnerable people in targeted communities reached by the project - Number of most vulnerable groups in target communities reached by the project - Number of engagements UNICEF had with Government to strengthen coordination and influencing political will in achievement of project results - Case studies or Most Significant Change stories attributable to the project - Photos showing effects of the project at district or community level - Explnanations/quotes on effectiveness of the project | - Descriptive analysis of secondary data - Content analysis of qualitative data and project documents |
| Efficiency To what extent were the outputs of the intervention (in terms of quality and quantity) with the allocated resources/inputs (such as funds, time and resources) | How well have UNICEF’s resources, both human and financial, been managed to ensure the timely, cost-effective and efficient attainment of results? | Desk review + analysis of secondary project data + budgets reviews + cost efficient analysis + key informant interviews | - Project reports - Project budget - Qualitative interviews | - Number of planned project activities that were implemented within budget - Number of planned project activities that were implemented on time/within schedule Cases/stories reflecting peoject efficiency | - Descriptive analysis of secondary data from project including information from budgets and workplans Content analysis of qualitative data & project documents |
| Sustainability To what extent are various stakeholders including the public sector, civil society and households likely to sustain the project after it has ended? | - To what extent has the program contributed to the strengthened capacity of duty bearers / service providers in health and other relevant sectors? - What evidence exists to inform the view that particular activities in the project are being replicated beyond the initially intended reach of the project (e.g. outside of geographic areas or target groups)? - What internal/external factors and drivers contribute to or constrain the sustainability of the program? | Desk review + secondary review of project data + qualitative interviews. | -Project reports -Project secondary data -Qualitative interviews | - Number and cadre of duty bearers/service providers in health and relevant sectors whose capacity was strengthened by the project and will continue providing services in areas where capacity was provided. - Number/type of activities/initiatives introduced because of the project that are continuing within the project area and beyond including internal/external factors that contributed to or constrained sustainability - Case studies and qualitative explanations/quotes on sustainability of the project | - Descriptive analysis of secondary data - Content analysis of qualitative data and disaster response literature |
| Gender and human rights To what extent did the project contribute to the observance of human rights and gender equity in Malawi? | - To what extent was the intervention aligned with UNICEF’s equity agenda in addressing the needs of the target groups (i.e.to what extent the initiative reached different groups including the most marginalized)? - Has the intervention contributed to equitable participation/reach and benefits to various groups (men, women, children and differently abled people)? | Desk review + secondary review of project data + qualitative interviews including social impact analysis | -Project reports -Project secondary data -Qualitative interviews | - Number of men, women, children and other vulnerable/marginalized groups of people reached by the project - Number of project committees, project activities that have equal participation/reach of men, women, children and differently abled people. - Case studies and/or Most Significant Change stories or general stories in communities reflecting on gender equity and human rights issues. | - Descriptive analysis of secondary data - Content analysis of qualitative data and project documents |
| Theory of Change What was the project’s theory of change? | - What did the project intend to change? - What conditions/outcomes were/are to change for the project to achieve its long-term objectives? - What activities were undertaken to achieve the objectives of the project? - What assumptions were built in meeting the project’s long-term objectives? - To what extent were project outcomes achieved? Why? | Desk review + secondary review of project data + qualitative interviews including case studies. | Project reports -Project secondary data -Qualitative interviews | - Project outcome level indicators should be referred to upon getting clarification from key stakeholders | - Descriptive analysis of secondary data - Content analysis of qualitative data and project documents |
| Lessons learnt, gaps, strengths, good practices What lessons were learnt, challenges were faced and strengths and good practices from the project? | - What lessons were learnt from the project? - What challenges were met? - How were the challenges solved/meant to be solved/way forward? - What are the strengths and good practices of the project? - What can be done differently in the design and implementation of this project if it is to be implemented elsewhere? | Desk review + secondary review of project data + qualitative interviews including case studies. | -Project reports -Project secondary data -Qualitative interviews including case studies. | - Lessons learnt and success stories - Reports/stories on challenges/gaps, strengths, and good practices | - Descriptive analysis of secondary data - Content analysis of qualitative data and project documents |

Note

The evaluation shall include overall performance rating rubrics for each of the above evaluation criteria, based on the following scale:

- Highly satisfactory (in most cases exceeded the plan);

- More than satisfactory (fully according to plan or better)

- Satisfactory (on balance according to plan, positive aspects outweighing negative aspects);

- Less than satisfactory (not sufficiently according to plan, taking account of the evolving context; a few positive aspects, but outweighed by negative aspects):

- Highly unsatisfactory (seriously deficient, very few or no positive aspects).

## Annex 2 Stakeholder Map

The following is the list of different stakeholders of this project that will also be targeted for the evaluation exercise. They are categorized into national, district and community stakeholders as presented below.

| National Stakeholders | District Stakeholders | Community Stakeholders |
| --- | --- | --- |
| UNICEF | Chikwawa District Commissioner | Community workers such as Health Surveillance Assistants and other volunteers (including those Riders for Health) |
| DFID/FCDO | Nsanje District Commissioner | Traditional Authorities and community members from the health center catchment center areas of Ndakwera, Mapelera, Chipwayira, Mkumaniza, Gaga, Gola, Makuwira, Mfera, Nchalohanga, St. Montfort, Ngabu, Chithumba, Majete, Kakoma, Chapananga, Bereu, Misomali, Kapichira, and Dolo in Chikwawa |
| Malawi College of Medicine | Chikwawa DHO | Traditional Authorities and community members from the health center catchment center areas of Mbenje, Lurwe, Chididi, Nyamithuthu, Tengani, Ndamera, Kalemba, Masenjere, Trinity, Sorgin, Oseana, Makhanga, Sankhulani, Masenjere, and Phokera in Nsanje |
| Swoop Aero | Nsanje DHO |  |
| FTI | Chikwawa and Nsanje Departments of Water Resources |  |
| Department of Civil Aviation | Chikwawa & Nsanje Departments of Disaster Management |  |
| Department of Water Resources | 19 Health Centers in Chikwawa namely Ndakwera, Mapelera, Chipwayira, Mkumaniza, Gaga, Gola, Makuwira, Mfera, Nchalohanga, St. Montfort, Ngabu, Chithumba, Majete, Kakoma, Chapananga, Bereu, Misomali, Kapichira, and Dolo |  |
| Department of Disaster Management | 15 Health Centers in Nsanje namely Mbenje, Lurwe, Chididi, Nyamithuthu, Tengani, Ndamera, Kalemba, Masenjere, Trinity, Sorgin, Oseana, Makhanga, Sankhulani, Masenjere, and Phokera |  |
| Central Medical Stores Trust |  |  |
| Riders for Health |  |  |

## Annex 3 Evaluation Ethics Standards

Guided by UNICEF’s Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis: Document Number CF/PD/DRP/2015-001, ethical standards shall be followed whilst undertaking this summative evaluation. Effectively the rights and welfare of all participants in this evaluation will be protected through (1) informing the participants on the purpose of the study, (2) ensuring participation is voluntary and confidential – only participants willing to take part in the evaluation will be interviewed and interviews will only be undertaken under environments that ensures confidentiality (closed rooms or isolated places), (3) adult participants provide informed consent and parents or guardians for children provide assent before participation (in this case informed consent will be verbal consent given the low risks associated with the evaluation and the fact that some of the interviews will be conducted virtually) and (4) data collection and analysis does not result in the violation of privacy, or discrimination (where data provided has person identifiers, these will be removed and replaced with evaluation codes that are delinked from personal information of the participants).

Documents from the following links have and will continue guiding evaluation ethics standards throughout this evaluation.

- www.unicef.org/supply/files/attachments/_iv-unicef_procedures_for_ethical_standard.pdf  [UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis; Document Number: CF/PD/DRP/2015-001; Effective Date: 01 April 2015]

- www.unevaluation.org_ethicalguidelines  or https://www.google.com/url?sa=t&rct=j&q=&esrc=s&source=web&cd=&cad=rja&uact=8&ved=2ahUKEwij-e-z2qftAhWHfMAKHcy_C8wQFjAAegQIARAC&url=http%3A%2F%2Fwww.unevaluation.org%2Fethicalguidelines&usg=AOvVaw0ZKygnKjv3_6M5u_OGZlhN UNEG Ethical Guidelines]

## Annex 4 Tentative Outline of the Report

Guided by UNICEF’s Evaluation Report Standards, this evaluation report shall follow the following report outline

- Title page

- Table of contents

- Executive Summary, including the purpose of the evaluation, key findings, conclusions and recommendations in priority order ( 3-4 pages)

- Background/context of the evaluation, including a description of project interventions, log frame/results matrix (Theory of Change)

- Purpose and objectives of the evaluation

- Scope of the evaluation

- Limitations and mitigation strategies

- Evaluation criteria and key questions

- Methodology (including ethical review)

- Findings per criteria

- Lessons learned

- Conclusions and recommendations, explicitly linked to the findings

The consultant shall use the GEROS UNICEF tools in assessing the report before it is submitted.

## Annex 5 Phases of the Evaluation

The figure below presents the 3 phases of this evaluation

## Annex 6 Detailed Workplan

| Key activities/tasks | Deliverable | Estimated number of days | Estimated completion date | Responsible person/institution |
| --- | --- | --- | --- | --- |
| Draft Inception Report including data collection tools, informed consent guides + fieldwork protocols, | Initial Inception Report, tools, consent forms & field protocols | 15 days | 01 Dec. 2020 | Edward |
| Revision of Inception Report, tools, informed consent guides & submission of Final Inception Report | Final Inception Report | 2 | 10 Dec. 2020 | Edward |
| Document review, Data collection with key stakeholders/collection and analysis of secondary data | Data collection updates | 25 | Dec-January 2021 | Edward |
| Fieldwork in Chikwawa & Nsanje | Fieldwork updates | 8 | January 08 2021 | Edward |
| Triangulation of collected data/writing | Data analysis updates | 10 | 18 January 2021 | Edward |
| Submission of Draft Report vs 1.0 | Draft Report vs 1.0 | 4 | 22 January 2021 | Edward |
| Review /Discussion on preliminary findings with key stakeholders/soliciting feedback | Remote workshop | 1 | 23 January 2021 |  |
| Submission of Revised Report | Draft Report vs 1.1 | 3 | 28 Jan 2021 | Edward |
| Preparation & submission of powerpoint presentation; Draft policy brief & inforgraphics | Draft PPT, policy briefs & inforgraphics | 15 | 15 February 2021 | Edward |
| dissemination workshop and presentation of evaluation findings/recommendations | Presentation | 1 | 20 February 2021 | Edward & UNICEF |
| Review & submission of final report (hard copy) | Final Report | 6 | 25 February 2021 | Edward |

## Annex 7 Terms of Reference

TERMS OF REFERENCE FOR INDIVIDUAL CONSULTANTS/CONTRACTORS

| PART I |  |  |
| --- | --- | --- |
| Title of Assignment | Summative Evaluation of Impact of using Drones on Population Health and Other Outcomes |  |
| Section | Research, Evaluation and Knowledge Management Section (REKM) |  |
| Location | International consultancy – remote work National consultancy – based in Lilongwe |  |
| Duration | 18 weeks |  |
| Start and End Date | From: 28 September 2020 | To: 31 January 2021 |

| PART II (this information is for INTERNAL use only; shall not be shared with prospective candidates) |  |  |
| --- | --- | --- |
| Contract Supervisor | Mussarrat Youssuf, Chief of Research, Evaluation and Knowledge Management |  |
| Planned Budget/Estimated Cost of assignment | Fee per day at # of days | National: $250 per day for 85 days International: $400 per day for 85 days |
|  | Living costs (DSA) at # of days | n/a |
|  | Travel (flight cost) | n/a |
|  | Transport in-country |  |
|  | TOTAL estimated contract value: | 250x85 = $21,250 (for national) 400x85 = $34,000 (for international) |
| Budget Code | SC190496 and Non-Grant |  |
| AWP Activity | WBS: 2690/A0/06/880/006/004 |  |
| Proposed assignment is included in the approved MCO Annual Service Procurement Plan | - Yes | No |
| Proposed methodology for sourcing of qualified candidates (i.e. TMS, Web-Relief, Rolodex, approved Rosters, other) | Advertisement, Roster |  |
| Names and contact details of institutions to contact for distribution of advertisement/in case of roster sourcing, names and contact details of suitable consultants (copy of pre-approved roster with related signatures to be attached) |  |  |

| PART III: Signatures |  |  |  |
| --- | --- | --- | --- |
| Function | Name | Signature | Date |
| Prepared by Research and Evaluation Specialist | Abiba Lincy Phegamengo Longwe-Ngwira |  |  |
| Reviewed by Chief of Research, Evaluation & Knowledge Management | Mussarrat Youssuf |  |  |
| Budget Owner Innovation Manager | Marie-Claudine Villacorta |  |  |
| Reviewed by HR Specialist | Ronelle Sasser |  |  |
| Endorsed by Dep Rep | Margarita Tileva |  |  |
| Approved by Representative | Rudolf Schwenk |  |  |

BACKGROUND

Malawi is a landlocked country with a population of nearly 18 million people – which is estimated to surpass 20 million in the next five years. Malawi has 28 administrative districts, which are further divided into traditional authorities (TA) and villages, the smallest administrative unit. Malawi’s economy has expanded over the past 30 years, with real GDP growth estimated at 4.4% in 2019. It remains predominantly an agricultural country, with agriculture, forestry, and fishing contributing 28% of GDP. Currently, GDP per capita is approximately $380, and given that inflation and population growth currently outpace economic growth, average living standards are falling. About 70 percent of the population live below the international poverty line of US$1.90 per day (WDI, 2018). Poverty remains particularly prevalent in rural areas, where more than 80% of the population live.

Health Outcomes:

Despite recent achievements, Malawi has not yet achieved optimal health outcomes. Life expectancy remains low at 61 years. Over half of the country’s total disability-adjusted life years are a result of the top four leading causes– HIV/AIDS, lower respiratory infections, malaria, and diarrheal diseases. Malawi has reduced its child mortality rate, leading to achievement of Millennium Development Goal (MDG) 4. However, other indicators remain stagnant or even face declines. The leading cause of morbidity in under five children are Malaria (29%), diarrhea (22%) and Acute Respiratory Infections (ARI) (5%) (MDHS, 2015).

The Malawi health sector operates under a decentralised system guided by the Local Government Act (1998). The Act delegates authority and funding from central government ministries to district assemblies, who guide health sector planning, budgeting, procurement, and service delivery at district and community levels. At central level, the Ministry of Health (MoH) sets strategic direction and formulates sector-wide governing policies. 29 district health offices oversee services provided in and outside of the district hospital. Five Zonal Health Support Offices (ZHSOs) provide technical support to districts in planning, delivery, supervision, and monitoring of health services. In total, the percent of government expenditure going toward public health averaged 10.4% from 2012-13 to 2014-15, well below the Abuja target of 15%. Therefore, donors have contributed most resources for the health sector in recent years.

Disaster Management and Preparedness: Climate variability, Rainfall, and Floods

Malawi is highly vulnerable to the impacts of extreme weather events given its location along the great African Rift Valley, rapid population growth, unsustainable urbanization, climate variability and change, and environmental degradation. The most common weather-related shocks affecting Malawi include floods, drought, stormy rains and hailstorms. Over the past five decades, Malawi has experienced more than 19 major floods and seven droughts, with these events increasing in frequency, magnitude and scope over the years.

In early March 2019, heavy rains developed from a Tropical Depression 11 that formed offshore central Mozambique. Heavy rains hit Malawi, causing severe flooding in the Southern and, to a lesser extent, Central Region of the country. These disaster events have had a significant impact on people’s lives, livelihoods and socio-economic infrastructure in the affected areas, pushing many people into poverty and food insecurity. In total, an estimated 975,000 people were affected, with 86,976 displaced, 60 killed and 672 injured. The devastating heavy rains and floods caused substantive damage and loss across the social, productive and infrastructure sectors, with the social sector experiencing most of these effects. The housing subsector experienced the greatest damage, with 288,371 houses being partially or destroyed. Most affected people were accommodated in temporary internally displaced people (IDP) camps, mostly located in classrooms and school facilities, with limited access to safe water and sanitation facilities. This resulted in significant disruptions to learning and teaching activities at the school. In addition, the 2019 floods affected roads, bridges, power supply lines, irrigation infrastructure and mature crops. Power supplies were interrupted for more than two days across the country.

The extent, time, and impact of natural disasters such as Cyclone Idai could be predicted and the damage to sectors, assets, facilities and infrastructure could be mitigated or reduced, if geographical information systems would be supported by necessary accurate flood modelling and prediction analysis. Subsequently, such analysis would significantly improve disaster preparedness plans and early warning systems, ensuring that affected and vulnerable communities get all the necessary support and commodities in a timely manner, without big delays.

Currently, early warning systems and innovative disaster preparedness practices in Malawi are developing; however, much of the evidence used to make informed decisions is scattered, not optimized, and not even hosted on geographic information systems. This makes the preparedness process complicated and inconsistent, which ultimately leads to the situation of vulnerable communities not getting necessary humanitarian help.

Unmanned Aerial Vehicles (Drones)

In the wake of the above context, the UNICEF Malawi Drones Program has been operational since 2016 and has proven to be a successful intervention in delivering development and humanitarian aid. Drones in Malawi are used as a transportation modality, to conduct site surveys and aerial monitoring, acquiring images, mapping, and remote sensing. The uses have been singular in their operations: drones technology application in Malawi up until now has been used for a single purpose at a time in their execution. As the use of drones is maturing, there is a need to understand ways in which the efficiency, efficacy, and versatility of the use of these drones can be increased.

JUSTIFICATION

Given the above background, the summative evaluation of the drones project is needed at this time to understand the project’s achivements during the period of implemenation under review. The evaluation will also assist in understanding the extent to which the programme has contributed to improving the transportation and information problems highlighted above.

The findings will provide valuable lessons on what has worked and what has not worked in using drones to improve health service delivery and disaster preparedness for consideration in the design and implementation of other similar programmes in future.

THE PROGRAMME (OBJECT OF EVALUATION)

The object of this Summative Evaluation covers the Sustained Multipurpose Unmanned Aerial Vehicle (UAV) Operations in Southern Malawi pilot project. The project focuses on the flood-prone districts of Chikwawa and Nsanje. These districts are in need alternative transportation modalities during rainy and flood seasons, as some of the health facilities are in hard-to-reach areas. Both districts have a need for better access to information about flood-affected and flood-prone areas. High resolution aerial imagery is to be captured as part of the project. This imagery is used, in other projects, to create contingency and emergency preparedness plans, evacuation plans, and other analytical assets for improved emergency response. Further information on the project has been placed at Annex 1.

The project utilizes a comprehensive, continuous multi-purpose drone operation, to provide two important functions: (1). Collecting detailed, hard-to-access aerial data, which can then be turned into vulnerability maps (flood modelling, community planning, mosquito breeding site identification, infrastructure inspection and similar) to help make detailed emergency preparedness and resilience plans, run flood modelling, identify potential hotspots for disease outbreaks, evaluate crop health and yields, and others; (2). Delivery and pick-up of medical commodities, emergency medicine, diagnostic samples and results, providing timely regular or emergency on-demand delivery services for medical centers.

The main purpose of the project is to establish a viable multi-purpose UAV (drone) operations in Malawi, to realize the impact of UAVs in development and humanitarian contexts in a financially sustainable, long-term manner. The project has been using drones to deliver healthcare in Malawi and also conducting aerial imaging ultimately used for disaster management.   In view of the above some expected outputs from the project included aerial data collected from hard to reach areas, vulnerability maps developed, medical commodities, emergency medicine, diagnostic samples and lab results picked and delivered in a timely manner.

The pilot drone operations have been conducted since January 2020 and will continue through September 2020.   The pilot phase was designed to understand answers to four key questions: (1) Does the project have a positive social impact? (2) Do users engage with it? (3) Does the technology of drones work? (4) Will the use of drones grow after the pilot?

The pilot and its constituent drone operations were spread over four phases, called Sprints, with a budget of GBP 150,000. Each phase has specific experiments to derive learnings from, the details of these experiments will be provided as part of the project documents packet to the Evaluator.

To date, more than 1,180 flights have been conducted, totaling 38,500 km flown in Malawi, and the operations employed five full-time Malawian employees. These flights have delivered medical supplies, medicines, vaccines, and medical bio-samples within the areas of Nsanje (Tengani, Chididi, Ndamera, Nyamithuthu, Mbenje, Lulwe, Phokera, Kalemba, Makhanga, Trinity, Masenjere, Sankhulani, Osiyana), Chikwawa (Bereu, Mapelera, Nchalo, Chapananga, Majete). More than 30 of these flights are related to the COVID-19 response.

The project was designed by DFID and UNICEF, and implemented by UNICEF, Swoop Aero (drone operator), UKaid Department for International Development (DFID) and FTL (technology advisor to DFID). UNICEF and UKaid have together considered how to use drones more widely as tools to more effectively deliver their collective mandates. For the purposes of this project, an Australia-based drone logistics company Swoop Aero was selected, to conduct the multi-purpose drone operations. UKaid and UNICEF Malawi have closely worked with University of Malawi, College of Medicine, a Malawi-based academic institution, that is focused on knowledge and research strengthening in the fields of medicine. College of Medicine is a co-investigator of the project, responsible for conducting a thorough ethical clearance, monitoring and evaluation of the project’s health-related outcomes, as well as for ensuring the project’s alignment with the health system’s stakeholders in both districts. The project closely collaborates with both District Commissioners (Nsanje and Chikwawa), respective district officers (District Health Officers, Disaster Risk Reduction Officers, and other) and their national counterparts from Ministry of Health, Department of Disaster Management Affairs, Central Medical Stores, as well as Water Resources Department. Department of Civil Aviation (DCA) is an integral part of the project, as they are responsible for inspecting and approving flight operations, including the transportation of dangerous goods. The DCA as per regular protocol, conducts regular check-ins with the drone team to ensure the highest standards of safety and operational practices in the field.

The pilot project commenced without an elaborate theory of change. As part of the summative evaluation, the Evaluator is requested to retroactively construct a theory of change in consultation with all key partners to better understand the program logic and how it worked to achieve the desired results of conducting aerial imaging and mapping for humanitarian and developmental goals. The project also introduced the requirement of exploring multipurpose drone flights, and using data acquired by these drones for various purposes such as flood mapping, disaster response preparedness, disease risk, etc. UNICEF thus expects the evaluator to develop a ToC for the project during the inception phase.

PURPOSE OF THE ASSIGNMENT

The major purpose of the summative evaluation is to elicit learning gained from the implementation of the pilot project while examining and evaluating its relevance, effectiveness, efficiency, sustainability and impact. It, therefore, aims to collect high-quality, impartial evidence focusing on learning that could enable evidence-based decision-making by identifying strengths and weaknesses of the pilot project.  Finally, the summative evaluation is expected to make recommendations for project quality improvement and further action related to the sustainability and scaling up. The target audiences of the evaluation and their expected use of learning from evaluation include:

- UNICEF to determine lessons learnt from the pilot project, its efficiency and effectiveness;

- Drone operating partners understanding of the impact of their social investments;

- Government partners including Ministry of Health, Ministry of Agriculture, Irrigation and Water Development and Ministry of Local Government for policy guidance on future programs;

- Host communities to learn about benefits from these drone operations, and;

- Donors, for project accountability, and determining efficiency and effectiveness

SCOPE OF WORK/OBJECTIVES

Evaluation Objectives

The primary objective of evaluation is to answer the fundamental question: Did the DFID-funded drone transportation project, on health service provision and flood mapping, succeed in achieving its desired results. The evaluation will also determine whether the pilot was able to find answers to the four key research questions: (1) Does the project have a positive social impact? (2) Do users engage with it? (3) Does the technology of drones work? (4) Will this use of drones grow after the pilot? The summative evaluation also seeks answers to what extent did this project make a difference, its sustainability and scalability (for future funding opportunities); and has the execution of the project been efficient.

The specific objectives of the summative evaluation are therefore to:

- Assess the extent to which project activities were implemented in the cost-efficient manner across genders and all socio-cultural groups including the vulnerable in the targeted communities

- Assess effectiveness of the drone project in producing the expected results for both men and women, boys and girls across all socio-cultural groups including the marginalized and vulnerable in the targeted communities

- Assess the outcomes of drone operations and to which extent the project has contributed to improving the health outcomes and disaster preparedness in Nsanje and Chikwawa

- Evaluate whether the drone transportation was relevant to address the main bottlenecks across all socio-cultural groups including the vulnerable in the targeted communities

- Assess the extent to which the intervention promoted observance of HR and GE and how stakeholders regardless of sex, geographical location, disabilities, age have benefited from the intervention

- Document lessons, key challenges/gaps, strengths, good practices

- Assess how sustainable the drone program is at the district and national levels

EVALUATION SCOPE

Geographic scope: This summative evaluation will review the entire set of activities undertaken during the four phases of pilot project (from inception in January to its completion in September), as implemented by UNICEF, Swoop Aero, DFID, FTL and other partners. Geographically, it will cover the entire project areas of Nsanje (Tengani, Chididi, Ndamera, Nyamithuthu, Mbenje, Lulwe, Phokera, Kalemba, Makhanga, Trinity, Masenjere, Sankhlani & Osiyana) and Chikwawa (Bereu, Mapelera, Nchalo, Chapananga, Majete).

Programmatic scope: This summative evaluation will examine the relevance, efficiency, effectiveness, sustainability, and impact of drones and data (e.g. artificial intelligence) on (a) people’s lives and community well-being, (b) access to health, nutrition, and infrastructure, and (c) the quality of knowledge and learnings from this project. The evaluation will also cover the use of drones as a transportation modality, their multi-purpose use, and in aerial imaging and mapping for humanitarian and developmental goals. Ultimately, the summative evaluation will attempt to analyse the social return on investment in drone use.

EVALUATION CRITERIA AND KEY EVALUATION QUESTIONS

The evaluation will use the UNEG standards for an impartial, coherent and effective evaluation. The OECD/DAC criteria - including relevance, efficiency, effectiveness and sustainability - will be used to assess the project. The evaluation will not measure the criterion of impact in this evaluation due to the short span of project (less than a year) and because it is not intended to be an impact evaluation. Any long-term outcomes will be assessed under the criterion of effectiveness. Additionally, cross cutting areas of gender and human rights will also be used as part of the evaluation criteria in this exercise.  All major evaluation questions are given in the following under the OECD/DAC criteria:

| Relevance | The extent to which the project design and implementation was relevant to national/provincial priorities and needs of men and women beneficiaries in terms of achieving expected results across all socio-cultural groups including the vulnerable in the targeted communities |
| --- | --- |
| Effectiveness | The extent in which the implementation strategies were effective and successful in achieving the planned outcomes/results for rich and poor men and women across all socio-cultural groups including the vulnerable in the targeted communities |
| Efficiency | The extent to which the outputs of the intervention has been achieved (in terms of quality and quantity) with the allocated resources/inputs (such as funds, time, and procedures) |
| Sustainability | The extent to which various stakeholders including the public sector, civil society and households are likely to sustain the behavior change related to the goals of the project after it has ended |
| Gender and Human Rights | The extent to which the intervention contributed to observance of human rights and gender equality in Malawi The extent to which stakeholders regardless of sex, geographical location, disabilities, age have benefited from the intervention |

KEY EVALUATION QUESTIONS

The Evaluation Criteria (in the preceding section), except for the Impact criterion, will guide the key questions, identification of key metrics, the analysis and in the synthesis of findings, recommendations, and next steps. Relevant questions will be developed according to the Evaluation Criteria in service of the programmatic questions listed above. These questions will pertain to the following key categories (with some example questions suggested):

Relevance:

- How relevant and meaningful are the project objectives and activities in terms of addressing the needs and priorities of marginalized and vulnerable children, men and women, in the project areas?

- To what extent the objectives and strategies used are relevant to national (Government of Malawi) priorities and policies related to health outcomes?

- How relevant is the selection and targeting of project areas (districts and villages) with regard to programme objectives?

Effectiveness:

- To what extent the DFID-funded drone transportation project on health service provision and flood mapping, including multi-purpose drone operations was successful in achieving its objectives?

- What were the major factors influencing the achievement or non-achievement of the objectives?

- To what extent has the implementation of strategies and project approaches - such as use of multi-purpose drones- worked as intended?

- How effectively UNICEF engaged with the Government to strengthen coordination and how far government leadership and political will influenced the achievement of results, or vice versa?

- How successful was UNICEF in reaching the most vulnerable groups in the target areas?

- What other changes (positive/negative, direct/indirect, intended/unintended) have occurred as a result of the project interventions?

Efficiency:

- How well have UNICEF’s resources, both human and financial, been managed to ensure the timely, cost-effective and efficient attainment of results?

Sustainability:

- To what extent has the programme contributed to the strengthened capacity of duty bearers / service providers in health and other relevant sectors?

- What evidence exists to inform the view that particular activities in the project are being replicated beyond the initially intended reach of the project (e.g. outside of geographic areas or target groups)?

- What internal/external factors and drivers contribute to or constrain the sustainability of the programme?

Gender and human rights:

- To what extent has the intervention aligned with UNICEF’s equity agenda in addressing the needs of the target groups (i.e.to what extent the initiative reached different groups including the most marginalized)?

- Has the intervention contributed to equitable participation/reach and benefits to various groups (men, women, children and differently abled people)?

The evaluation shall include overall performance rating rubrics for each of the above evaluation criteria, based on the following scale:

- Highly satisfactory (in most cases exceeded the plan);

- More than satisfactory (fully according to plan or better)

- Satisfactory (on balance according to plan, positive aspects outweighing negative aspects);

- Less than satisfactory (not sufficiently according to plan, taking account of the evolving context; a few positive aspects, but outweighed by negative aspects):

- Highly unsatisfactory (seriously deficient, very few or no positive aspects).

The above ratings scales are for general reference and the consultants may propose an alternative rating approach. Each rating will be stated as part of the conclusions for each of the criteria.

EVALUABILITY ASSESSMENT

Evaluability is the extent to which the project can be evaluated in a reliable and credible manner. Evaluability is high if the subject has: (a) a clear description of the situation before/at the start that can be used as reference point to measure change (baseline); (b) a clear statement of intended outcomes, i.e. the desired changes that should be observable once implementation is under way or completed; (c) a set of clearly defined and appropriate indicators with which to measure changes; and (d) a defined timeframe by which outcomes should be occurring; and (e) a system for regularly collecting, storing and analyzing performance data.

The level of evaluability of the “Drones” project to meet the objectives set out in section 5 is assessed to medium because a) A baseline was not conducted at the beginning of the project; b) Regular monitoring of the project has taken place and is documented. As such, some information exists for assessing the achievements of intended outcomes and the utilization of resources over the period under review. A detailed evaluability assessment should be carried out at the inception phase to determine the appropriateness of the methodological approach proposed in section 10 below. It is expected that the evaluation will make use of already existing data as follows:

- Routine Progress Reports

- Project proposal including the Logical Framework and Key Deliverables

- Monitoring data and reports

- Quarterly and semi-annual reports/updates

- Partners’ reports (progress and monitoring)

- Any assessment or review report (if conducted)

- Any other project related documentation

METHODOLOGY

This is a summative evaluation expected to provide a comprehensive overview of projects achievements of desired objectives, contribution to outcomes, challenges and lessons learned. Therefore, the applicants are invited to propose a robust design with a mixed methods approach - using both qualitative and quantitative approaches – triangulating information from different methods and sources to enhance the reliability of findings. The absence of baselines is a challenge to measure the progress and changes caused by the project to the lives of beneficiaries. The consultant may reconstruct baseline information from secondary sources that will be shared by the concerned project manager. Robust and adequate use of qualitative methods can also be helpful in the absence of baselines for the programme, however, other innovative measures to address this gap may also be proposed by the consultant. Accordingly, a comprehensive methodology will be expected from the consultant with adequate proposed measures to address this gap by considering all the project details and indicative methodology and approaches. The consultant will be expected to capture the entire set of the above given evaluation criteria, with gender-responsive and equity focused analytical approaches providing a reliable assessment of project’s achievement and contribution toward short- and long-term outcomes and measuring value for money. Traditionally, cost-effectiveness, cost-utility and cost-benefit analyses have been used to assess value-for-money of public health interventions. For any proposed methodology, the consultant will be expected to provide details regarding the relevant approaches, data collection methods, sample size and data analysis approaches while meeting the quality criteria.

Prior to submission of the inception report, the selected consultant will be expected to undertake an extensive literature and desk review of all key documents, including the project proposal, surveys, work plans, progress reports and routine monitoring data etc. This summative evaluation will follow gender responsive, equity-focused, transparent, collaborative and participatory approaches to ensure involvement of men and women from the project areas specially from the marginalized and vulnerable groups. Participation of all key stakeholders such as the Innovations team, Swoop Aero, DFID and FTL and any other relevant partners will be ensured in the overall evaluation design and process. The evaluator will propose the methodological design which should demonstrate impartiality and lack of bias by relying on a cross-section of information sources (e.g. stakeholder groups, including beneficiaries, etc.). The consultant will use existing project data pertaining to drone operations, the nature, quantity, and purpose of commodities the drones transported, the distances flown, the types, quality, and footprint of imagery acquired. The consultant will be supported by the College of Medicine to elicit data from primary sources, the populations and/or communities served, the impact on health outcomes (as available), and number of patients helped.

A refined evaluation matrix based on the evaluation criteria and questions is expected to be provided in the inception report. An evaluation plan will be used to demonstrate a clear understanding and realistic plan of work for the evaluation, checking that the evaluation plan is in agreement with the TOR and the overall project vision for the evaluation. Data collection and analysis methods should be selected based on their appropriateness to answer the key evaluation questions and based on what is realistic in the timeframe and the resources available. Proposed primary evaluation methods can include:

- Desk review

- Key informant and stakeholder interviews and discussions (also from field sources including but not limited to Riders for Health)

- Case studies (of best practices)

- Questionnaires as appropriate will be used as a particular form of qualitative analysis. These will be to analyze the action and its implementation from organization staff, concerned stakeholders and beneficiaries’ perceptions.

The data analysis methods shall be in line with the design of the evaluation to provide fair, unbiased judgement of the project. There may be some challenges in data reliability and disaggregation of data by sex, age group, etc. It is proposed that some of the risks could be mitigated through triangulation, cross-referencing, and other means. The secondary data on the relevant indicators from the national surveys may not be reliable at a district level because of sample size limitations. Reliability could improve, among others, by pooling samples.

In preparing the results of the evaluation, the findings will be evidence-based and have clear references to respective sources. The structure and quality of the evaluation report  must adhere to UNICEF quality standards,  and include the following report structure:

- Title page

- Table of contents

- Executive Summary, including the purpose of the evaluation, key findings, conclusions and recommendations in priority order ( 3-4 pages)

- Background/context of the evaluation, including a description of project interventions, log frame/results matrix (Theory of Change)

- Purpose and objectives of the evaluation

- Scope of the evaluation

- Limitations and mitigation strategies

- Evaluation criteria and key questions

- Methodology (including ethical review)

- Findings per criteria

- Lessons learned

- Conclusions and recommendations, explicitly linked to the findings

The final report should follow the UNICEF Evaluation Report Standards and will be reported on UNICEF’s global reporting system known as GEROS. The selected evaluator will receive these guidelines at the first meeting following issuance of the contract. A formal presentation of the final report and key findings for the evaluation is required. To ensure better understanding and use of evaluation, the evaluation report will be complemented with policy briefs (with infographics) targeting the policy makers. The hired institution will keep the project management team regularly informed of progress and key issues arising that may require additional direction or suggestions for other key informants or reference material.

GENDER AND HUMAN RIGHTS

Social constructs like gender, ethnicity or disability, and societal norms that dictate what a person should or should not do, influence the decisions of those in power. The voices, views and needs of those who have low status, minorities, those who are very poor, women, girls and children are often ignored when staff and policy makers take decisions, for example, over the location and equipment of health facilities or services in the national policies. This means that decisions can reinforce underlying inequalities and patriarchal norms.

Guided by the UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluation (2014), the evaluation process should carefully consider issues of gender equality and human rights and all stages. T Gender equality and empowerment of women should be mainstreamed throughout the evaluation. Further details of the criteria can be sourced from: http://www.unevaluation.org/document/detail/22. The evaluation process, gender concerns should be addressed. UNICEF Malawi stands for gender responsive and equity-focused evaluation approaches, therefore, throughout the evaluation process, gender concerns will be addressed, and all data will be disaggregated by sex and age. Among other issues, the consultant will explore whether the transportation interventions are appropriate and socially impactful for both women, men, boys, girls and other marginalized groups.  The study will also explore shortcomings of existing health services provision and the needs of specific user groups with regards to healthcare infrastructure. The issues to be explored includes but not limited to the following: security and safety, privacy, accessibility, comfort. Different needs of women, men, children and of marginalized groups targeted by the intervention will be considered throughout the evaluation process. The aspect of human rights will be assessed to give a measure of how the design and delivery incorporated rights issues. Community participation will be emphasized and how UNICEF ensures that communities were involved throughout the project cycle.

RISK ASSESSMENT AND MITIGATION

The consultant will need to take into consideration and provide workable solutions to the following challenges and possible limitation of the evaluation: (1) identification of data sources and data acquisition, and (2) operational, logistical, and travel limitations as posed by COVID-19 and any other environmental (e.g. rains, floods) that may be experienced. To mitigate these, there may be a requirement for remote coordination and/or data collection, implementation of safety measures during field visits, and appropriate study and evaluation design that account for the challenges posed by these.

ETHICAL CONSIDERATIONS

The evaluation will follow UNICEF procedure of Ethics in Evidence Generation and all its guidelines on the ethical participation of human participants, including children. The inception report will be ethically reviewed and cleared by the Malawi government’s ethical review board. No filed work will commence before the final clearance of the inception report by the country’s ethical standards. All participants in the study will be fully informed about the nature and purpose of the evaluation and their requested involvement. Only participants who have given their written or verbal consent (documented) will be included in the study.

The prospective consultant is expected to provide a detailed plan on how the following principles will be ensured throughout the study: 1) Respect for dignity and diversity 2) Fair representation; 3) Compliance with codes for vulnerable groups (e.g., ethics of research involving young children or vulnerable groups); 4) Redress; 5) Confidentiality; and 6) Avoidance of harm.

The consultant is therefore required to clearly identify any potential ethical issues and approaches, as well as the processes for ethical review and oversight of the evaluation process in their proposal. Specific safeguards must be put in place to protect the safety (both physical and psychological) of both respondents and those collecting the data. These should include:

- A plan is in place to protect the rights of the respondent, including privacy and confidentiality

- The interviewer or data collector is trained in collecting sensitive information

- Data collection tools are designed in a way that are culturally appropriate and do not create distress for respondents

- Data collection visits are organized at the appropriate time and place to minimize risk to respondents

- The interviewer or data collector can provide information on how individuals in situations of risk can seek support

The consultant may not publish or disseminate the Evaluation Report, data collection tools, collected data or any other documents produced from this consultancy without the express permission of, and acknowledgement of UNICEF (may need to add partners’ names here, including government).

REPORTING REQUIREMENTS

In accordance with UNICEF’s evaluation policy, this evaluation will be managed by Chief of REKM as Evaluation Manager, with close coordination support from the UNICEF Malawi Innovations Program team. As part of the quality assurance mechanism, an evaluation reference group (ERG) will be established with members from key programmes, UN partners and UNICEF Regional Office for Eastern and Southern Africa (ESARO). All key deliverables of the evaluation – inception report, and final report – are required to be reviewed by the ERG and accepted by the Chief of REKM before payment is made to the evaluation agency. The final evaluation report will strictly follow “UNICEF Evaluation Report Standards” and UNICEF Evaluation Technical Notes which are aligned with UNEG Standards and Norms.  A self-assessment of the draft report against the GEROS UNICEF tool will also be required by the evaluation consultant. Feedback to the consultant will be provided after the review of each deliverable. Performance evaluation of the supplier will be done at the end of the assignment or whenever a contract amendment is sought.

EXPECTED DELIVERABLES

The evaluation is expected to be carried for a period of 18 weeks. In alignment with the scope of work as described above, the consultant will be expected to perform the following activities and deliverables as per the schedule and estimated dates below:

| No | Key activities and tasks | Deliverable | Estimated number of days required | Estimated Completion Date* | % of total fee payable |
| --- | --- | --- | --- | --- | --- |
| 1 | Draft Inception Report, including: - Introductory work: Meetings, document gathering, etc. - Plans, protocols, analytical framework, and indicators | Initial Inception Report | 7 days | October 6, 2020 |  |
| 2 | - Review of the study plan, protocol, analytical framework and indicators by UNICEF - Feedback and revision; acceptance of the inception report | Final Inception Report + Work Plan | 7 days | Oct 15, 2020 | 20 |
| 3 | Data collection, data repository structure, and information and decision flow design | Data repository + Information and decision flow chart(s) | 21 days | Nov 13, 2020 |  |
| 4 | Data Analysis | Data analysis reports with visualization | 15 days | Dec 4, 2020 |  |
| 5 | Preparation and submission of draft report, policy briefs and infographics | Draft Evaluation Report, Policy Brief and Infographic | 15 days | Dec 28, 2020 | 40 |
| 6 | Preparation and submission of revised final report, revised policy briefs and infographic | Revised Draft Evaluation Report, policy brief and infographic for Review | 7 days | Jan 15, 2021 |  |
| 7 | Validation workshop | Stakeholder workshop | 2 days | Jan 21, 2021 | 10 |
| 8 | Submission of final report and final policy briefs and infographic | Final Evaluation Report | 5 days | Jan 29, 2021 | 30 |

* Exact deadlines will be mutually agreed upon contract signature.

However, as the actual starting date may impact the dates estimated in the TOR, the exact timeframes and actual delivery dates will be jointly agreed upon between the consultant and the supervisor upon contract signature.

Inception Report: as per UNICEF standards, will include but not be limited to the following: Background, details about the project to be evaluated (object of evaluation), theory of change of the project and its explanation and how it will be used for evaluation, evaluation design detailing the sampling frame and method, data collection tools, Interview guides, evaluation forms or other data collection instruments to be used, data analysis plan, Quality Assurance Plan, Field work plan/Timeline and the Reconstructed baseline information from secondary sources (as an appendix of the inception report).

Evaluation Report:

The draft evaluation report will be reviewed by the ERG and the feedback will be used by the consultant for refining and finalizing the evaluation report. The final report will be high-quality, ethically assured, gender responsive and utilization-focused evaluation informing decisions to deliver effective project. The evaluation report should be clear and include the following elements: an executive summary of maximum 4 pages, total report of not more than 30 pages (without annexes),  a profile of the evaluated Programme, description of methodology and data collection tools, the main findings, lessons learned, conclusions and recommendations, attachments (TOR, reconstructed Theory of Changes, evaluation matrix and data collection tools, list of persons interviewed etc.). The findings and conclusions of the evaluation will answer the evaluation questions. The final evaluation report will be complemented with one policy briefs based on its key findings and recommendations targeting key decision-makers. Likewise, the consultant to produce one infographic.

QUALITY ASSURANCE

The quality of all evaluation reports (Inception Report and Draft Report) will be assessed by a company external to UNICEF and will be facilitated by UNICEF Malawi. The Contractor will be responsible for ensuring that recommendations for quality improvement of the report(s) are fully addressed. The Draft Report will be considered as a final one only after passing through the external quality assessment, addressing all comments and having final positive rating as “Satisfactory” or “Highly Satisfactory”. The Final Evaluation report will be also submitted to the Global Evaluation Reports Oversight System (GEROS) for final quality assessment with feedback provided to the UNICEF Malawi office on the quality of the evaluation (could be shared with contractors upon request).

PERFORMANCE INIDICATORS FOR EVALUATION OF RESULTS

The performance of work will be evaluated based on the following indicators:

- Completion of tasks specified in TOR

- Compliance with the established deadlines for submission of deliverables

- Quality of work

- Demonstration of high standards in cooperation and communication with UNICEF and counterparts

PAYMENT SCHEDULE

All payments, without exception, will be made upon certification from the supervisor of the contract, of the satisfactory and quality completion of deliverables and upon receipt of the respective and approved invoice. The payment will be tied to submission of acceptable quality deliverables. The following show the key deliverables and associated proposed milestone payments:

| S. No. | Deliverable | Expected completion date | Payment ratio (%) |
| --- | --- | --- | --- |
| 1 | Inception Report with workplan | Oct 15, 2020 | 20 |
| 2 | Draft Evaluation Report, policy brief and infographic for review | Dec 28, 2020 | 40 |
| 3 | A presentation at a validation workshop | Jan 21, 2021 | 10 |
| 4 | Final Evaluation Report report incorporating comments from the validation workshop accompanied by policy brief, infographic and Micro datasets in an appropriate format with corresponding syntax/script files | Jan 29, 2021 | 30 |

Travel (international and local) costs will be reimbursed on actual expenditures and upon presentation of original supporting documents. As per UNICEF operational guidelines, travel for international consultancies, will  be in economy class and will use the most economical route.

DESIRED COMPETENCIES, TECHNICAL BACKGROUND AND EXPERIENCE

The evaluation consultant will not have been involved in the design or implementation of the project to be evaluated or have any other conflicts of interest. It is expected that the consultant will disclose any potential conflict of interest.

Academic qualification:

- The consultant must have an advanced University degree in one of the following disciplines (or related) Decision Science, Operations Research, Policy Analysis, International Development, Social Sciences, or Management Science(s).

Work experience, Technical skills and competencies

- The consultant must have at least 6 years of experience leading, designing and conducting impact evaluations.

- Expertise in designing methodology and data collection tools and demonstrated experience in leading similar evaluations.

- Must have leadership, analytical and communication skills, including a track record of excellent writing and presentation skills.

- Proven experience evaluating Technology and Innovation dependent programs.

- Experience and good knowledge of gender issues and tools for integrating human rights and their link with the innovation

- Exceptional data analysis skills for both qualitative and quantitative data;

Languages:

- Proficiency in English and local languages

ADMINISTRATIVE ISSUES

UNICEF will regularly communicate with the specialist and provide feedback and guidance and necessary support so to achieve objectives of the work, as well as remain aware of any upcoming issues related to the performance and quality of work.

As per policy on consultants and individual contractors, the individual will be expected to complete a list of mandatory training, including policies on Prohibiting and Combatting Fraud and Corruption; Prohibition of discrimination, harassment, sexual harassment and abuse of authority and other relevant policies for their information and acknowledgment. Within 5 days of the contract commencement, the consultant/individual contractor is requested to complete the applicable mandatory trainings.

The consultant/evaluation agency will work from their own workplace, with regular phone/Skype meetings with UNICEF Malawi, Research, Evaluation and Knowledge Management Section (REKM) and innovation programme with a clear schedule of online meetings. The consultant may need to travel for in-person interviews, if travel restrictions were removed at a later stage. The field sites will be determined in consultation with UNICEF and government counterparts once it is safe to travel and collect data face-to-face.

The consultants will provide their own laptop and working space.

CONDITIONS

- The candidate selected will be governed by and subject to UNICEF’s General Terms and Conditions for individual contracts.

- No contract may commence unless the contract is signed by both UNICEF and the consultant.

- The evaluation will be conducted using remote methods of data collection and consultation such as online meetings. All data required from the field will be provided by the Innovation team, their partner institution, i.e. College of Medicine, relevant departments of Ministry or Health, and the drone operator Swoop Aero.

- The consultant will be paid an all-inclusive fee (stationary, communication and other miscellaneous expenses) as per the stipulated deliverable and payment schedule.

- Under the consultancy agreements, a month is defined as 21 working days, and fees are prorated accordingly for actual days worked.

- The consultant is not entitled to payment for overtime, weekends or public holidays, medical insurance, taxes, and any form of leave.

- Travel expenses for official in-country trips, including living costs, will be covered in accordance with UNICEF’s rules and tariffs, by the consultant and reimbursed against actuals, unless otherwise agreed.

- Transport will be provided to the consultant during in-country field travel, if planned and approved.

- No travel should take place without an email travel authorization from section prior to the commencement of the journey from the duty station.

- Standard UNICEF procedures will apply for invoicing and all other financial management requirements set out in the contract.

- Standard penalty clauses will also apply for late and poor-quality deliverables. The supervisor of the contract will provide the consultant with the criteria for the evaluation of the quality of each deliverable.

- Additional details of UNICEF rules, regulations and conditions will be attached to the contract.

- Consultants will not have supervisory responsibilities or authority on UNICEF budget.

- The assignment is an on-site/off-site support.

HOW TO APPLY

Interested consultants should provide the following:

- Curriculum Vitae

- Brief technical proposal (no longer than five pages) demonstrating the consultant’s understanding of the assignment and approach/methodology to the assignment, proposed work plan showing detailed sequence and timeline for each activity; quality assurance mechanism and risk mitigation measures put in place and ethical considerations and how the selected candidate will address them.

- Financial proposal including a breakdown of their all-inclusive fees (including professional fees, travel, living cost, visa and other costs). Complete the attached form.

- References details

ANNEX 1

Objectives and Scope of Project

So far, the majority of UAV delivery tests across the world have been sporadic and isolated demonstrations rather than a fully integrated, continuous operational process involving multiple different stakeholders. Additionally, the areas mapped by a drone in Africa is minimal. This multi-functional, sustained operation will contribute to the breakthrough in mapping of Malawi and its vulnerable areas for better emergency preparedness and for improved socio-economic development of the country, as well as it will introduce the new transport modality for the health supply chain in reaching the most hard-to-access health centers.

Within the scope of this project and in the context of the above described challenges the project will utilize a comprehensive, continuous multi-purpose drone operation, providing two important functions:

- Collecting detailed, hard-to-access aerial data, which can then be turned into vulnerability maps (flood modelling, community planning, mosquito breeding site identification, infrastructure inspection and similar) to help make detailed emergency preparedness and resilience plans, run flood modelling, identify potential hotspots for disease outbreaks, evaluate crop health and yields, and others.

Aerial data will be collected in a way, so that no individual or other human subject information is recognizable. In order to anonymize the data, the drone will be flown at approx. 80-100 m. altitude, and the camera will be set up to capture images at a resolution of 2-3 cm per pixel, ensuring that no human face or other human features can be recognized. The camera will also be flown at 90-degree angle to reduce any chances of recognizability. Below is an example of aerial data and the detail that is captured. It is evident that no individual human information can be extracted from this image.
The collected aerial data, maps and analytical insights will be made available for district and national governmental agencies, and will be hosted on UNICEF’s data platform 4P2C available here: https://malawi.4p2c.org/portal/home/

- Delivery and pick-up of medical commodities, emergency medicine, diagnostic samples and results, providing timely regular or emergency on-demand delivery services for medical centers.

The first phase of the project will focus on the demands assessment and site scoping, in order to identify the health facilities which are in the most need for quicker transportation of the above mentioned commodities. In doing so, project’s partners will closely work with the Districts’ health management team, in order to be able to incorporate their feedback and inputs, as well as will enable them to choose 2-3 facilities per district.

The project will not be collecting any human subject data related to delivery. As opposed to that, the project will look only at the quantities, types, frequencies, and stockouts of medical commodities requested and delivered. Where it concerns medical samples and their results, the data will be coded under unique personal identifier, ensuring that neither drone service provider nor other project partners have access to patient data. 
By running such continuous drone operation, evidence, such as flights, delivery contents and their quantities, and aerial imagery will be collected and monitored, to then subsequently provide materials for monitoring and evaluation activity, which will be completed by the co-investigator of the project. Should this turn into full-pledged research project, a separate, specific activity-focused ethics clearance would be undergone.

## Annex 8 List of Documents Consulted

- DFID, UNICEF, FTL and Swoop Aero Project Document – Sustainable Multi Purpose Drones Operations in Southern Malawi

- Proposal and supporting documents submitted to the College of Medicine for ethical review

- PR Document

- Minutes of Stakeholder Meetings

- Project Handover Plan

- Sprint 1,2,3 and 4 plans and budgets

- Sprint Reviews

- Emails between different stakeholders

- The Sustained Drones Operations in Southern Malawi July 2020 Report by College of Medicine

- The Sustained Drones Operations in Southern Malawi October/November 2020 Report by College of Medicine

- UNEG Norms and Standards

- UNICEF procedures for ethical standards

- “Bi-directional drones to strengthen healthcare provision: experiences and lessons from Madagascar, Malawi and Senegal” Knoblauch AM et al (2019) BMJ Global Health Journal 2019;e001541.doi:10.1136/bmhgh-2019-001541

## Annex 9 Data Collection Tools

1. Key Informant Interview Guide – National Level

Introduction

This interview guide targets key people involved in the design, coordination, and implementation of the drones project. These are people from UNICEF, Swoop Aero, DFID/FCDO, FTI and Malawi College of Medicine who played key roles in the project. Personnel from other key stakeholders like the Department of Civil Aviation, Department of Disaster Management, Water Resources Department, Central Medical Stores Trust are also targeted.

Background Information

- Date of Interview

- Name of respondent

- Organization where respondent works

- Duration working for the organization

- Key responsibilities in the organization

- Key role/responsibilities in the drones project

Relevance

- To what extent are the objectives and strategies adopted in the DFID-funded drones project relevant to Malawi Government’s national priorities and policies related to health outcomes?  Probe relevance in relation to SDGs, Malawi Growth & Development Strategy among other key national development roadmaps in relation to the lagging health and emergency response indicators.

- To what extent do the objectives and activities of the DFID-funded drones project address the needs and priorities of marginalized and vulnerable children, men and women, in the project areas?

- How relevant was the selection and targeting of Chikwawa and Nsanje Districts including the 19 health centers in Chikwawa and 13 health centers in Nsanje.

Effectiveness

- To what extent was the DFID-funded drone project successful in achieving objectives relating to (1) health service provision, (2) flood mapping and (3) multi-purpose drone operations? Probe activities that were undertaken under each of the aforementioned three areas and the extent to which the objectives were met.

- What factors influencing the achievement or non-achievement of the objectives?

- To what extent were project activities implemented in a cost effective manner across genders and socio-economic groups including vulnerable people in the targeted communities? Probe cost efficiency measures taken against each of the project activities.

- Was UNICEF effective in engaging with the government and other key stakeholders in strengthening coordination and government leadership and political will in influencing the achievement of results or vise versa? Probe how effective it was.

- How successful was the drone project in reaching men, women, boys and girls across all socio-cultural groups including the marginalized and the most vulnerable groups in the target areas?  Probe factors leading to success or failure to reach most vulnerable groups

- What changes (positive/negative, direct/indirect, intended/unintended) have occurred as a  result of the project interventions?

Efficiency

- How well were resources, both human and financial, managed to ensure timely, cost-effective and efficient attainment of results?  Probe areas for reasons where there was untimely, or cost ineffective or inefficient utilization of resources.

Gender Equity and Human Rights

- To what extent did the project align gender equity and human rights issues in addressing the needs of the target groups? Did the project reach different groups of people including the most marginalized members of society such women, children and people with special needs?

- Has the intervention contributed to equitable participation/reach and benefits to various groups such as men, women, children and differently abled people?  How/why did the project contribute or fail to contribute to equitable participation/reach of men, women, children and other vulnerable members of the society?

Sustainability

- Will this project continue should funding from DFID and support from UNICEF, Swoop Aero and FTI stop? Why? Probe why in relation to the support provided by each of the aforementioned key stakeholders

- To what extent has the project built or strengthened capacity in (1) drone technology, (2) drone operations, (3) drone acceptability at national, district and community level.

- Is the project being implemented in other districts/communities outside the initial project areas? If yes, where is it being implemented and is it a replication of the same project? If no, why is the project not being implemented anywhere outside the targeted districts? Which areas may need support for the project to continue or be scaled up?

- What internal/external factors contribute or constrain the sustainability of this project?

- What should be done for this project to be scaled up? Probe lessons (positive and negative) learnt from this drone project for scaling up.

Lessons Learnt/Key Challenges/Gaps/Strengths, Good Practices & Recommendations

- As a pilot project what lessons have been learnt in the designing, implementation, coordination and scale-up of the project?

- If the project is to be scaled-up elsewhere, what would recommend to be done differently? Why? What good practices would you recommend to be repeated? Why?

- What challenges were faced in the course of the project? Probe challenges faced from design to the end of the project. How were these challenges addressed?

- What do you recommend to be done in addressing such challenges

2. In-depth Interview Guide – District Level

Introduction

This interview guide targets key people involved in the day-to-day running and administration of the project at district level. These are people from Chikwawa and Nsanje DHO (notably the District Health Officer/representative & Health Center In-charges/representatives in targeted project communities), College of Medicine Project Coordinator(s), District Level Officers from the Departments of Disaster Management, Water Resources and Civil Aviation.

Background Information

- Date of Interview

- District where interview is taking place

- Name of respondent

- Organization where respondent works

- Duration working for the organization

- Key responsibilities in the organization

- Key role/responsibilities in the drones project

Relevance

- To what extent was this project relevant to this district and targeted communities?

- To what extent did the objectives and activities of this project address the needs and priorities of marginalized and vulnerable children, men and women, in the project areas?

- How relevant was the selection and targeting of Chikwawa and Nsanje Districts including the 19 health centers in Chikwawa and 13 health centers in Nsanje. Probe if there are any areas in the district that were not targeted and the reasons for not targeting these areas.

Effectiveness

- To what extent was the drone project successful in achieving objectives relating to (1) health service provision, (2) flood mapping and (3) multi-purpose drone operations? Probe activities that were undertaken under each of the aforementioned three areas and the extent to which the objectives were met.

- What factors influencing the achievement or non-achievement of the objectives?

- To what extent were project activities implemented in a cost effective manner across genders and socio-economic groups including vulnerable people in the targeted communities? Probe cost efficiency measures taken against each of the project activities.

- Was UNICEF effective in engaging with key stakeholders at district level in strengthening coordination and administration of the project? How effective?

- How successful was the drone project in reaching men, women, boys and girls across all socio-cultural groups including the marginalized and the most vulnerable groups in the target areas?  Probe factors leading to success or failure to reach most vulnerable groups

- What changes (positive/negative, direct/indirect, intended/unintended) have occurred as a  result of the project interventions?

Efficiency

- How well were resources, both human and financial, managed to ensure timely, cost-effective and efficient attainment of results?  Probe for activities that were undertaken and how they were implemented in a cost effective manner.

- Are there some project activities that were not implemented on time and cost effectively? What and activities and why?

Gender Equity and Human Rights

- Did the project reach different groups of people including the most marginalized members of society such women, children and people with special needs?  If yes, probe for records indicating numbers of children, women and people with special needs and the activities that reached them.

- Has the intervention contributed to equitable participation/reach and benefits to various groups such as men, women, children and differently abled people?  How/why did the project contribute or fail to contribute to equitable participation/reach of men, women, children and other vulnerable members of the society?

Sustainability

- Will this project continue should support from DFID, UNICEF, Swoop Aero and FTI stop? Why? Probe why in relation to the support provided by each of the aforementioned key stakeholders

- What has been done at district level to ensure that the project continues when the supporting partners withdraw? Probe plans with regards to the drones, pilots hired etc if there are any plans and resources committed for continued support.

- What internal/external factors contribute or constrain the sustainability of projects like this one?

- What should be done for this project to be scaled up? Probe lessons (positive and negative) learnt from this drone project for scaling up.

Lessons Learnt/Key Challenges/Gaps/Strengths, Good Practices & Recommendations

- What lessons have been learnt from the project in the designing, implementation, coordination and scale-up of the project?

- If the project is to be scaled-up elsewhere, what would recommend to be done differently? Why? What good practices would you recommend to be repeated? Why?

- What challenges were faced in the course of the project? Probe challenges faced from design to the end of the project. How were these challenges addressed?

- What do you recommend to be done in addressing such challenges

3. In-depth/FGD Interview Guide – Community Level

Introduction

This interview guide targets community leaders, community workers/volunteers and community members.

Background Information

- Date of Interview

- Name of District

- Name of community where interview is taking place

- Role or position in community of respondent(s)

- Sex of respondent(s)

- Age of respondent(s)

Relevance

- Before the project started, were you and other community members informed about the project? What information was provided about the project? How was the information about the project disseminated and by whom?

- Was this project relevant to community? Why? Was it justifiable introducing this project in this area? Why? Probe how fears about drones and socio-cultural suspicions around moving samples (like blood, sputum) using drones were addressed, it at all they were addressed.

- Did the project address the needs and priorities of this community? What needs/priorities were addressed? How were they addressed?

- Were the needs of children, women, men and other vulnerable/marginalized members of this community addressed? What needs were addressed and how were they addressed?

Effectiveness

- What did this project seek to achieve in this community? Did it achieve the intended objectives? How?

- What factors influenced the achievement or non-achievement of the project objectives?

- Were project activities implemented with the intention of cutting costs? How?

- Was the District Office/College of Medicine/Health Center effective in engaging with key stakeholders at community level in strengthening coordination and administration of the project? How effective?

- How successful was the drone project in reaching men, women, boys and girls across all socio-cultural groups including the marginalized and the most vulnerable groups in the target areas?  Probe factors leading to success or failure to reach most vulnerable groups

- What changes (positive/negative, direct/indirect, intended/unintended) have occurred as a  result of the project interventions?

Efficiency

- Were project activities implemented on time? Probe if there were any delays in the overall execution of the project.

- What factors supported/hindered timely implementation of project activities.

Gender Equity and Human Rights

- Did the project reach different groups of people including the most marginalized members of society such women, children and people with special needs?  If yes, probe how and possible number of people reached in the community disaggregated by the aforementioned categories. If no figures are available probe for cases or case studies.

- Has the project contributed to equitable participation/reach and benefits to various groups such as men, women, children and differently abled people?  How/why did the project contribute or fail to contribute to equitable participation/reach of men, women, children and other vulnerable members of the society? Why?

Sustainability

- Would you want to see this project continue? Why? Do you see this project continuing? Why? What measures have been put in place to ensure that the project continues? Probe if there are any systems or structures that have been created to support continuation of the project.

- If this project is to continue or to be implemented elsewhere, what do you recommend should be done for a project like this one to continue?

- What internal/external factors contribute or constrain the sustainability of projects like this one?

Lessons Learnt/Key Challenges/Gaps/Strengths, Good Practices & Recommendations

- What lessons have been learnt from the project in the designing, implementation, coordination and scale-up of the project?

- If the project is to be scaled-up elsewhere, what would recommend to be done differently? Why? What good practices would you recommend to be repeated? Why?

- What challenges were faced in the course of the project? Probe challenges faced from design to the end of the project. How were these challenges addressed?

- What do you recommend to be done in addressing such challenges

## Annex 10 Informed Consent Guide

Informed Consent Form

Participant ID: ___________________________

Hello, my name is Edward Chigwedere. I am an Independent Consultant undertaking an evaluation of the Drones Project that was implemented by UNICEF/DFID/Swoop Aero/FTI/DCA/College of Medicine among other stakeholders in Chikwawa and Nsanje Districts. You are being asked to take part in this summative evaluation to find out how relevant, effective, efficient, sustainable and human rights and gender equity inclusive the project was. This evaluation also seeks to draw some lesson learnt from this pilot project. I will explain what is involved in this evaluation and how it will affect you. This informed consent form describes the evaluation procedures, risks, and benefits of taking part, as well as how your confidentiality will be maintained. Please take your time to ask questions and feel comfortable making a decision whether or not to participate. This interview will take 30 – 45 minutes. If you decide to take part in this study, you will be asked to give verbal consent and you will not sign anywhere. Let me know if you would want to proceed. [Only proceed if respondents consents]

What is the purpose of the project and this summative evaluation? UNICEF/DFID/Swoop Aero/FTI/DCA/College of Medicine among other stakeholders implemented the UAV/drones project in Chikwawa and Nsanje Districts that sought to establish viable multipurpose drone operations and realize the impact of drones in development and humanitarian work. The project has been using drones to deliver health services and conducting aerial imaging needed for disaster management between January and September 2020. This evaluation seeks to assess the extent to which the project was effective, efficient, relevant, sustainable and incorporated human right and gender equity during its implementation. It also seeks to draw some lessons from this pilot project.

What will happen? I will ask you some questions about your knowledge/experiences in the effectiveness, efficiency, sustainability, relevance, human rights, gender equity and some lessons learnt from this project. You are free not to answer any of the questions I ask you should you not want to. Your choice not to answer any question will not result in you being denied any services at the nearest heatlh facility or facing any consequencies. It is your right to only respond to issues that you want to.

What are the risks of taking part in the evaluation? There may be minimal risk in sharing information on what you know about this project. This interview will however be conducted in a confidential area. You are free to stop if you do not feel comfortable. Stopping and refusing to participate in the evaluation will in no way affect your daily life or status or position in at work/community.

What are the benefits of taking part in the evaluation? There is no compensation or direct benefit in participating in this evaluation. The information you provide will however help UNICEF, DFID/FCDO, Government of Malawi among other stakeholders to get a better understanding on operations of drones and draw lessons on whether they can be another option in health commodities and services transportation and disaster/emergency preparedness and management.

Do I have to take part in the evaluation? Your taking part in this study is completely voluntary. You can decide not to take part in the study at all. You may stop this interview at any time without any impact on your employment or wellbeing.

Request to FGD participants All issues to be discussed during this evaluation are expected to be confidential. Participants in FGDs are expected to keep everything discussed or said by any of the participants confidential.

If I have any questions or concerns about this evaluation, who can I talk to? You may ask any questions about this project in the future.  If you have questions about this project or if you feel that you have been harmed as the result of taking part in the study, you may contact The Country Representative:

_UNICEF Malawi____________________

Address: Ministry of Health, P.O. Box 30375, Lilongwe, Malawi

Phone: 01 770 788

You will be offered a copy of this consent form if you need it for any reason.

How will my privacy be protected? Your name, telephone number, and address will not be recorded in any forms or reports that come from dissemination of evaluation results. The evaluation will only report group results. All the information that we collect will be kept confidential. All the information you have provided will be carefully destroyed/discarded upon the end of the evaluation.

Finally, you are free to ask any question that you may have regarding the study or the procedure involved before we proceed. If you agree to take part in the study, kindly sign your name in the space provided below indicating your voluntary decision to take part in the study.

CONSENT STATEMENT

PARTICIPANT

I have read this consent form.  I understand why the evaluation is being done, what will be done in the study, and the risks and benefits as described in this written summary. I was given the chance to ask questions and these have been answered satisfactorily. I agree to take part in this study and my taking part is voluntary.

Date: __ __ / __ __ / 202_

Consultant

I have explained the purpose of this evaluation to the participant and have answered all of her/his questions.  To the best of my knowledge, s/he understands the purpose, procedures, risks, and benefits of this study.

Study staff signature (Print): ______________________________	Date: __ __ / __ __ / 202_

Name of Interviewer (Print): ________________________________

All information in this section comes from the HSSP II, the NCHS Situation Assessment, and the Malawi Demographic Health Survey; please refer to these documents for sources.