Final Evaluation of the Project Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro

Inception report

Zehra Kacapor-Dzihic – Team Leader

Jasna Zarkovic- National Expert

June/2022

Contents

Abbreviations	4

1.	Introduction	6

1.1. Context	6

2.	Subject of the evaluation	9

2.1. Subject evaluated	9

3 Objectives and Scope of the evaluation	14

3.1 Objectives of the evaluation	14

3.2 Scope of the Evaluation	15

4 Methodology	18

4.1 Evaluability assessment	18

4.2 Evaluation design and approach	18

4.3 Sampling	19

4.4 Data collection methods and tools	21

4.5 Data collection tools	21

4.6 Evaluation phases	22

4.7 Ethical considerations	24

5 Evaluation workplan and logistics	26

5.1 Timeframe and logistics	26

5.2 Support and information required from PUNOs	27

5.3 Roles and responsibilities	27

6 Quality Assurance	28

Annexes	30

Annex 1: Terms of reference	30

Annex 2: Evaluation matrix	41

Annex 3: Results framework	53

Annex 4: Detailed stakeholder analysis	57

Annex 5: Interview guides	66

Annex 6: Informed Consent Forms	73

Annex 7: Bibliography	74

Tables

Table 1. Scope of assessment under evaluation criteria	15

Table 2 Overview of evaluation questions and proposed changes	16

Table 3. Overview of JP activities in communities	20

Table 4: Consultation Strategy	23

Table 5: Risks and mitigation strategies	25

Table 6: evaluation schedule	26

Table 7: Summarized Evaluation Schedule – primary data collection Phase	27

Table 8: Roles and responsibilities of the evaluation team	27

Figures

Figure 1. Budget overview (as of 30 April 2022)	9

Figure 4. Stakeholder map	19

# Abbreviations

| 3Cs | Coherence, communication and complementarity |
| --- | --- |
| CODI | Core Diagnostics Instruments |
| CSO | Civil Society organization |
| DAC | Development Assistance Committee |
| EC | European Commission |
| EM | Evaluation Manager |
| EQ | Evaluation Question |
| ET | Evaluation Team |
| EU | European Union |
| GDP | Gross Domestic Products |
| HCD | Human-centered design |
| IFIs | International Financial Institutions |
| ILO | International Labour Organization |
| IOM | International Organisation for Migration |
| IR | Inception Report |
| JP | Joint Programme |
| KI | Key informants |
| KII | Key Informant Interviews |
| MAPS | Mainstreaming, Acceleration and Policy Support |
| MFSW | Ministry of Finance and Social Welfare |
| MONSTAT | Statistical Office of Montenegro |
| NATO | North Atlantic Treaty Organization |
| NEET | Not in Education, Employment, or Training |
| NGO | Non-Governmental Organization |
| NSDD | National Strategy for Sustainable Development |
| OECD | Organisation for Economic Co-operation and Development |
| PUNO | Participating UN Organization |
| RCO | Resident Coordinator Office |
| RSIA | Rapid Social Impact Assessment |
| SDG | Sustainable Development Goals |
| SDGs | Sustainable Development Goals |
| SILC | Survey of income and Living Conditions |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UN | United Nations |
| UNCT | United Nations County Team |
| UNDP | United Nations Development Programme |
| UNHCR | UN Refugee Agency |
| UNICEF | United Nations Children’s Fund |
| WHO | World Health Organization |

# 1.	Introduction

This Inception Report represents a road map to the Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro (hereinafter: Activate! Joint Programme (JP)), a programme jointly implemented by five United Nations agencies – the United Nations Children’s Fund (UNICEF), the International Labour Organization (ILO), the United Nations Development Programme (UNDP), UN Refugee Agency (UNHCR) and International Organisation for Migration (IOM) from December 2019 until 31 July 2022. This Inception Report (IR) is for a summative evaluation which will assess the Joint programme’s (JP) contribution to the enhance the capacities of the social protection system in Montenegro to better serve people in need.

The purpose of this IR is to present the scope, purpose, and objectives of the evaluation and its plan. It summarises some of the key information about the context and programme that is to be evaluated and identifies key stakeholders. The document also outlines the intended evaluation approach and methodology and describes how the evaluation will be organized.

The Inception Report is a working tool to ensure that the expectations of the evaluation from the commissioning body (UNDP and UN Resident Coordinator Office (RCO)) and Participating UN Organizations (PUNOs) and key stakeholders are properly integrated into the evaluation plan by the Evaluation Team (ET). It also serves as the contract of agreement between the Evaluation Manager (EM) and the ET for all aspects of the evaluation operational plan. The IR is built on the Evaluation Terms of Reference (TOR) (Annex 1).

The Inception Phase of the evaluation started with a kick-off meeting on 10 May 2022 with Project team and a number of introductory meetings with Participating UN Organisations (PUNOs) in the period between 16 -19 May 2022. The purpose of these introductory meetings with PUNOs was to familiarise with the Project, to discuss the scope of the evaluation and expectations regarding the design of the evaluation framework, methodology and workplan.

Aside from the above meetings, no interviews with JP stakeholders ahead of submission of the inception report. As a result, no particular issues about the JP have emerged during the Inception Phase.

## 1.1. Context

Montenegro with population of 0.62 million is located in Western Balkans, bordering the five Western Balkans countries and separated from Italy by the Adriatic Sea. Montenegro faces challenges of population ageing, with the population's median age being 38.8. The share of children (aged 0-17) in the total population is estimated at 21.6% in May 2022, while 16% of the total population are aged 65 and above. Two-thirds of the total population are working-age population (aged 15-64 years). Most population live in urban areas (67.6% in 2020).

Concerning the accession to the European Union, Montenegro is a candidate country which applied for EU membership in December 2008 and opened the accession negotiations in June 2012. By May 2022, Montenegro has opened 33 chapters, including chapter 19 on social policy and employment, and three are provisionally closed. Furthermore, Montenegro became NATO's member in June 2017.

The political situation, in the period 2020-2022, was marked by a fragmented and polarised political scene and by tensions between political actors. As a result of the August 2020 elections, the first change of power in Montenegro happened after almost 30 years. The deep political polarization continued in the post-election period, including within the ruling majority. The government which took office in December 2020, was replaced by the new minority government elected by the Assembly in April 2022. With the Government appointed in December 2020, competency over social and child protection was moved to the Ministry of Finance, and it was returned to the Ministry of Labour in May 2022.

The European Commission (EC) 2021 Report on Montenegro highlight that country is moderately prepared in developing a functioning market economy and coping with competitive pressures and market forces within the EU. The country relies significantly on the services sector as this sector accounts for around 58% of GDP, and 74% of all jobs are in the service sector. Montenegro is a tourism-dependent economy (more than 20% of GDP), which showed vulnerability to the COVID-19 pandemic. Namely, Montenegro faced a sharp recession in 2020 due to the COVID-19, with GDP growth declining from 4.1% in 2019 to – 15.2% in 2020. GDP per capita stood at some 46% of the EU-27 average in 2020, which is 4% lower than in 2019. To support the economy, several economic support packages were implemented by the government, which amounted to 6% of GDP in 2020 and an additional 7% of GDP in 2021. Driven by a rapid recovery in tourism and government supporting economic measures, Montenegro’s economy began to recover and recorded a very high GDP growth of 12.4% in 2021. Due to a large budget deficit in 2020, the debt ratio increased from 76.5% in 2019 to 105% in 2020, and EC estimated its decline at 78% of GDP in 2022.

Human Development index 2020 was 0.829 for Montenegro, ranking 48 out of 189 countries, while Gender Inequality Index 2019 was 0.109, ranking Montenegro 26 out of 162 countries.  Recent data shows that COVID impacted the growing unemployment trends. In the period 2019-2021, the unemployment rates of Montenegro was ranging from 15.1% in 2019, 17.9% in 2020 to 16.6% in 2021. Unemployment was particularly high among young people (the youth unemployment rate in 2020 was 30.7%). In 2020, 26.6% of youth (15-29 years) were not in education, employment or training (NEET), which is higher than in 2019 (21.3%), and significantly higher than the EU average (14% in 2020, 12.9% in 2019). Youth participation in the labour market is marked by disparity between labour supply and demand, as a significant number of university graduates find a job that is not well matched to their level of education (lower qualified jobs).

According to the SILC (survey of income and living conditions) data for 2020, 22.6% of the population was at risk of poverty, while 32.6% of children lived in income-poor households. Poor and vulnerable groups are children, young people, migrants and refugees, Roma and Egyptian, people who remain without stable legal status, victims of sex trafficking, returnees under a Readmission Agreement, long-term unemployed, people with disabilities, and the rural population.

Montenegro has developed various government strategies to ensure the social protection of vulnerable groups and the legal framework that guarantees the protection of fundamental rights and is in line with European standards. Some of policies documents are the Strategy for the Development of the Social and Child Protection System for the period from 2018 to 2022, the Roadmap of Reforms on Social assistance and social and child protection services in Montenegro (adopted in July 2021), the Strategy for Social Inclusion of Roma and Egyptians in Montenegro 2021 - 2025, the Strategy for the Realization of Child Rights (2019-2023), the Western Balkans Declaration on ensuring sustainable labour market integration of young people (endorsed in July 2021), the Strategy on Migration and Reintegration of Returnees in Montenegro for 2021-2025, Strategy for Combatting Trafficking in Human Beings 2019-2024, the Strategy for Integration of Persons with Disabilities in Montenegro for the period 2016-2020, Youth Strategy 2017-2021.

The social protection expenditure of Montenegro was 16.3% of GDP in 2019, which was decreased by 0.4 percentage compared to 2018, and lower than the EU average (19.3% in 2019). Out of the total amount of social protection expenditure, 97% was spent on social protection benefits. EC 2021 Montenegro report suggested that ‘based on the Roadmap of Social Protection Reform, continue the evidenced based reform of the social protection system, keeping in mind links to employment activation and social inclusion with an anti-poverty focus.’

As regards COVID-19, Montenegro declared an epidemic outbreak on 26 March 2020 which was followed by the introduction of containment measures to mitigate transmission of COVID-19. By 15 May 2021, Montenegro had recorded 236,320 cases and about 2,719 deaths related to the COVID-19 pandemic, around 45% of the population had been fully vaccinated (first and second dose). As mentioned above, this pandemic heavily affected the tourism-dependent economy of Montenegro, which is the worst affected country in the region. The UN Socio-economic response plan to COVID-19 in Montenegro (developed in July 2020) noticed that the COVID-19 pandemic particularly negatively affected the most vulnerable groups such as ‘people living in poverty, children, elderly, persons with disabilities, minorities, refugees, asylum seekers and persons at risk of statelessness and migrant workers’, but also ‘have contributed to the emergence of new groups of vulnerable people (“new poor”), whose household income largely depends on the informal economy and who are not covered by social protection and/or eligible for employment benefits’. EC 2021 Montenegro report and the Rapid Social Impact Assessment of the Covid-19 effect outbreak in Montenegro (RSIA) noted that the COVID-19 pandemic negatively affected the living conditions of children and access to education, access to health, mental health and social services of children, those from socially disadvantaged families and children with disabilities.

# 2.	Subject of the evaluation

## 2.1. Subject evaluated

Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro is 32 months long programme, running from December 2019 through July 2022, designed to ‘enhance the capacities of the social protection system to better serve people in need – through a dual focus on improving the effectiveness of social policies as well as delivery of social services’. This is a Joint Programme (JP) implemented and funded by ILO, UNDP, UNHCR, UNICEF and IOM and the Joint SDG Fund, with a total budget of USD 2,689,00.00. Until April 30, 2022, a total 82% was utilised (See Figure 1 below).

Figure 1. Budget overview (as of 30 April 2022)

Source: UN

The programme has introduced innovative policy making on social protection through applying policy simulations tools which improve targeting, coverage and adequacy of social protection (related to Outcome 1), and innovative practices in labour activation of vulnerable youth (e.g. NEET) and other vulnerable group through applying human-centred approach (related to Outcomes 2).

The JP has focused on adolescents and youth (including NEETS), Roma, people with disabilities, children, ex-Yugoslav refugees, asylum seekers, stateless/persons at risk of statelessness, migrants, returnees, people living in poverty, and addresses root causes of human trafficking, while supporting decent work and employability/skills development. JP intended to pay attention to cross-cutting needs of women and children within the above categories.

The JP has worked with wide stakeholder groups such as various line ministries - the Ministry of Labour and Social Welfare, the Ministry of Finance (later Ministry of Finance and Social Welfare), the Ministry of Economic Development, the Ministry of Interior, Ministry of Education, Science, Culture and Sports; Statistics Office of Montenegro (MONSTAT); Local Employment Offices; Centres for Social Welfare; Civil society organizations (CSOs) - Red Cross, various youth organizations/associations, local NGOs working with Roma communities, trade unions, employers’ federations, etc; media; international organisations such as World Bank (in the area of job creation) and WHO (in the area of mental health barriers to employment).

The JP also drew on the expertise of other United Nations County Team (UNCT) members, such as UNCT in Albania and ILO in Western Balkans countries to address cross-cutting issues of improving the work of labour market institutions and of other community level service provisions to better serve people in need. In addition, UNDP Montenegro has collaborated with UNDP Moldova in regard to use of human-centered design (HCD) methodology for co-design of services for labour activation of most vulnerable.

Theory of Change Programme`s Theory of Change was based on three key hypotheses: If national social protection policies are better informed by updated evidence on poverty, especially related to marginalized groups and the impact of these policies can be modelled and predicted before they are submitted for adoption then the social protection system can more effectively alleviate poverty and accelerate sustainable human development within existing fiscal space. If the most vulnerable youth have increased access to social protection services or can co-design programmes/ services targeted to their needs and are equipped with relevant skills then they will be more resilient, able to lead more productive lives and better fulfil their potential, thus reducing dependency on social assistance and helping to break intergenerational cycles of poverty. Finally, if Montenegro’s social protection system can more effectively alleviate poverty and reduce social exclusion, and if more young people in Montenegro lead productive lives and fulfil their potential, then progress towards more sustainable human development will accelerate.

Intervention logic of the JP - objective, results and activities

The objective is that by 2022, Montenegro has improved capacity to design impact-oriented, evidence-informed social protection policies and deliver integrated human-centred services that reduce poverty and social exclusion of the most vulnerable and marginalized, focusing on young men and women, thus accelerating sustainable human development.

Outcome 1: Social policy simulations based on data and evidence, including on the impact of COVID-19, and subsequent scenarios for social protection system reform will result in more just, better targeted and more adequate social protection programmes and services for the most vulnerable groups (e.g. youth, migrants, returnees, refugees, stateless persons, children and victims of trafficking). The programmes and services complement labour market activation for decent work and development of employability skills. This work builds on the international CODI (Core Diagnostics Instruments) Assessment and a UN Rapid Social Impact Assessment (RSIA) of COVID-19, as well as the MAPS SDG acceleration reports and is fully aligned with the national institutional reform approach.

Output 1.1: New tool supports analysis of poverty-related data and simulation of policy impact

| Planned Activity | Lead PUNO | Achievements |
| --- | --- | --- |
| 1.1 Provide deeper analysis of poverty data to identify furthest behind | UNDP UNICEF | Developed tools for planning and implementation of more effective social policies. Designed three social policy options for poverty reduction (means tested benefits, child allowance and income taxation) Implemented trainings for the MFSW staff to capacitate them for the use of simulation model and present simulation results. Several areas for improvement of SILC data were identified and were shared with the Ministry in order to improve the processes related to overall quality of data collection and processing. UNDP supported the MFSW and MONSTAT Statistical Office to improve SILC data that are needed for simulation and modelling in future period. Reports of three round RSIA were produced and published. |
| 1.2 Operationalize recommendations from CODI to increase effectiveness, efficiency, capacity to address poverty within fiscal space | UNICEF |  |
| 1.3 Develop poverty reduction scenarios to target furthest behind | UNDP |  |
| 1.4 Accelerate implementation of optimum scenario(s) | UNDP/UNICEF |  |

Estimated rate of completion as of May 2022: 99%.

Outcome 2: Innovative skills building, mental health and labour market activation measures will increase the participation of young men and women in education, employment or training, strengthen their resilience, prevent passivation and reduce their dependence on social assistance. The intervention would expand the coverage of children by social transfers by 50% and, combined with labour activation measures and other interventions in social protection, could potentially reduce the national poverty rate by 3 percentage points (compared to the recalculated poverty rate after COVID-19 impact, available once the simulation exercise is completed). Given the expected socio-economic COVID-19 impact in terms of increased unemployment and poverty as well as newly emerging vulnerable groups this target remains important but is also ambitious.

Output 2.1: Human-centered, integrated service delivery at community-level, focusing on youth, to increase their participation in education, employment or training to reduce dependence on social assistance, are rolled-out.

| Planned Activity | Lead PUNO | Achievements |
| --- | --- | --- |
| 2.1 Profile NEETs, registered beneficiaries of SP, those without access to SP system, to refine targeting and design an activation programme | ILO | ILO support implementation of the active labour market measure “Activate women” resulted in around 79 women were activated from the registry of Employment Agency of Montenegro, 19 of them transited to work during the 2022. Supported design a Youth Guarantee Scheme (e.g. mapping NEETs, relevant legal and policy reviews, etc) - ongoing |
| 2.2. Support “first-time” access to SP system/employment for refugees/persons at-risk of statelessness/readmitted nationals by supporting regularization of legal status and social inclusion and enhancing multi-sectoral coordination and referral mechanisms for vulnerable groups | UNHCR IOM | UNHCR: 996 persons (99,6% completion rate) were supported by UNHCR through 2,171 legal advices towards regularizing their legal status. UNHCR: Organized 3 statelessness workshops in the northern, central and southern part of Montenegro. UNHCR: Supported development of the Strategy on Migration and Reintegration of Returnees in Montenegro for 2021-2025 and UNHCR supported strengthening the birth registration and the statelessness determination procedures. UNHCR: Organized an International Conference on Statelessness: Best Practices in Montenegro and France. IOM: Training for relevant national stakeholders aiming to enhance national institutions’ capacities to provide integrated reintegration assistance to readmitted nationals – ongoing |
| 2.3 Increase access to human-centered, effective social support services for targeted groups, including labour market activation | UNDP IOM | Applied Human-centred design (HCD) methodology for co-design of services for labour activation of most vulnerable, especially youth. Challenges and bottlenecks related to labour activation, both on the side of beneficiaries and service providers were identified. Analysis of integrated work under the sector of social protection and employment related to labour activation of able-to-work social beneficiaries. Analysis of system for professional rehabilitation and employment of persons with disabilities. Support development of government strategies and programmes for youth, such as digital platform for the government’s pilot project digital skills development for youth, youth strategy, and youth card programme. New pilot project in 10 municipalities with approximately 80 participants, focusing on the individualized and tailored support to the unemployed was designed and rolled out in 2022. IOM: Vocational trainings to readmitted nationals deficient and potentially innovative at the labour market – ongoing |
| 2.4 Strengthen resilience through “21st century” skills development, including socio-emotional/self-care skills tailored to unique needs (e.g., mobile-based delivery) | UNICEF | 823 adolescents have gone through the social-emotional skills programmes which was deployed through a blended approach, using both online tools and face-to-face workshops in the southern (4 municipalities) and central region (4 municipalities). Programmes for the Northern region of Montenegro is ongoing. Baseline study on youth needs for development of the National Youth Strategy. Mental health portal and workshops on improving well-being and mental health including self-coping mechanisms for adolescents. |
| 2.5 Enhance identification of victims of trafficking and raise awareness on the dangers of trafficking, targeting youth with a focus on marginalized groups | IOM | Social workers have gone through the capacity building activities on strengthening competences of professionals in identification, protection, assistance and reintegration of victims of trafficking. Awareness raising campaign on dangers of trafficking in human beings (e.g. art contest for students (aged 12-18 years), 4 workshops, etc. ) – ongoing |

Estimated rate of completion as of May 2022: 75% (UNHCR 100%, UNDP 80%, ILO 70%, IOM 60%, UNICEF 65%).

The JP is planned to contribute to an acceleration of progress towards 6 out of 17 SDGs such as Goals 1 - No poverty, 3 - Good Health and Well-Being, 4 - Quality Education, 5 - Gender Equality, 8 - Decent Work and Economic Growth, and 10 - Reduced Inequalities. In addition, the JP is planned to work towards objectives of the National Strategy for Sustainable Development of Montenegro by 2030 that were focused on improvement of state of human resources and strengthening of social inclusion, support to values, norms and behaviours patterns significant for sustainability of the society, and stimulate employability and social inclusion.

Intervention logic of the JP is presented in Figure 1 below.

Figure 1. Intervention logic of the JP

# 3 Objectives and Scope of the evaluation

## 3.1 Objectives of the evaluation

As stipulated in the TOR, the evaluation will be both summative and formative in nature, fulfilling the accountability and learning purpose. Hence, the evaluation will provide summative assessment of the achievements of the JP by assessing the approach taken by PUNOs, whether the assumptions made in the JP’s ToC were appropriate, and whether activities and interventions indeed contributed to progress within the framework of the ToC. The evaluation will explore whether the proposed approach was scalable and to determine the extent to which the desired change has occurred. Its formative element will be fulfilled by assessing the degree to which the joint programme met its intended objectives and results, as input to derive key forward-looking lessons about successful approaches and operational practices, identifying areas for improvement for future similar programmes.

The information, findings, lessons learned, and recommendations generated by the programme evaluation will be used by the Joint Programme Board and other relevant stakeholders to inform future programming, but also for PUNOs to potentially modify practices and further improve delivering-as-one approach.

The ToR, therefore, includes the following evaluation objectives:

- To assess the project accomplishments against planned results, objectives, targets and indicators, including the aspects of effectiveness and efficiency of the intervention and sustainability of project benefits beyond the lifetime of the project;

- To assess, to the extent possible, contribution to improving the situation of vulnerable groups identified in the JP, including persons with disability;

- To assess contribution to SDG acceleration;

- To assess contribution to UN reforms (including UNCT coherence);

- To assess contribution to SDG Fund global goals;

- To assess, to the extent possible, contribution to the National Strategy for Sustainable Development (NSSD) of Montenegro;

- To assess the relevance, effectiveness, design, efficiency, coherence and sustainability of the joint programme from its inception to its completion;

- To provide reflections on the previous state of play and capacities of the main actors as compared to the beginning of the project implementation and in relation to that, provide recommendations and guidance for future similar JP initiatives;

- To provide gender-sensitive assessment of the joint programme by maximizing the use of existing data to support mainstreaming of gender analysis across all questions, including those unrelated to gender;

- To identify and consolidate good practices, human stories, lessons learned and make recommendations on processes, management, partnerships and other aspects of project implementation that would benefit future joint programmes agencies in this area.

The evaluation will focus attention on human rights, in particular of the most marginalised groups targeted by the evaluation including persons with disabilities, refugees, migrants and stateless persons or those at risk of statelessness, by assessing the extent to which:

- Joint programme design, implementation, and monitoring have been inclusive of persons with disabilities (accessibility, non-discrimination, participation of organizations of persons with disabilities, data disaggregation) and other most vulnerable groups (refugees, migrants and stateless persons or those at risk of statelessness)

- Joint programme effectively contributed to the socio-economic inclusion of persons with disabilities and other marginalised groups by providing income security, coverage of health care, and disability-related costs across the life cycle.

In addition, the evaluation will take a due attention to gender mainstreaming in JP design, implementation and monitoring by providing and insight into the gender lens and mainstreaming of gender across Program design, implementation  and monitoring. In particular the evaluation looks into the Programmes GEWE contributions.

The primary users of the evaluation are the UN RCO in Montenegro and PUNOs, the Government of Montenegro and in particular the relevant ministries, and development partners.

## 3.2 Scope of the Evaluation

Programme components: The ToR stipulates that the programme will be assessed in its entirety, hence this evaluation will therefore assess the JP’s results framework as a whole, while also looking into individual outcome/output areas. The insights from outcome/output areas of the JP are assumed to be necessary to reach results in a sustainable, efficient, and equitable manner. The results will therefore be used to inform the assessment of higher-level results (ToC).

Time period: During the inception phase, the time scope was reconfirmed as December 2019- June 2022.

Geographic scope: The evaluation geographic scope will be nation-wide.

Evaluation questions: The questions that will guide this evaluation are aligned with the evaluation criteria developed by the OECD Development Assistance Committee (DAC). The ToR requests the evaluation to focus on the key OECD/DAC evaluation criteria. Based on review of ToR and initial round of meetings with PUNOs, the ET includes the criterion of Coherence, communication and complementarity (3Cs) to respond to evaluation’s objective and specific EQs included under effectiveness and efficiency. During the Inception phase the following scope per criteria is confirmed:

Table 1. Scope of assessment under evaluation criteria

| Criterion | Scope |
| --- | --- |
| Relevance/appropriateness | Assessing the extent to which programme objectives, and design are appropriate to the Montenegrin context and can respond and adapt to the needs of beneficiaries and other stakeholders in this changing context (particularly COVID-19 and volatile political context). The assessment will also include the assessment of the definition and implementation of appropriate coordination, management and financing arrangements. Relevance to SDGs (in particular, Goals 1, 3, 4, 5, 8 and 10). Under this criterion, gender/equity and disability will be integrated through indicators, to ensure the full spectrum of evaluation objectives is covered. This will allow assessing the extent to which human rights, child rights, disability inclusion and gender equality and equity have been addressed within the programme. |
| Effectiveness | Assessing the extent to which the JP achieved, or is expected to achieve, its objectives including support for / working with others including government. Particular focus will be placed on assessment of the extent to which the programme effectively identified, outreached, and engaged target groups, as well as marginalized groups (i.e. youth, persons with disabilities, returnees, internally displaced, ex-Yugoslav refugees, persons at risk of statelessness, minorities...) and supported gender mainstreaming and women’s empowerment. The assessment will also include coherence and complementarities with other similar programmes (e.g. regional project - Inclusive Labour Market Solutions Project: Promoting Inclusive Labour Market Solutions in the Western Balkans implemented by UNDP and ILO). Under this criterion, gender/equity and disability will be integrated through indicators, to ensure the full spectrum of evaluation objectives is covered. This will allow assessing the extent to which the JP contributed to promotion and fulfilment of human rights, child rights, disability inclusion and gender equality and equity. |
| Efficiency | Assessing the utility of financial, human and technical resources to achieve results, as well as assessing the programme design, coordination and management. Importantly, the evaluation will assess the degree to which political developments in the country, as well as COVID-19 pandemic, influenced the programme’s efficiency. |
| 3 Cs | Based on the review of ToR and initial round of meetings with PUNOs, the ET includes the criterion of Coherence to respond to evaluation’s objective and EQ included under efficiency that calls for assessment of coherence and communication between the JP and implementing partners, stakeholders and programme beneficiaries. |
| Impact | The TOR stipulates a number of EQs relating to likelihood of impact of the programme on the most vulnerable groups and SDG attainment. The ET will attempt to collect sufficient evidence to provide some insight into the impact of the programme. However, it is understood that impact is hard to measure, particularly in case where implementation is still underway. Under this criterion, gender/equity and disability will be integrated through indicators, to ensure the full spectrum of evaluation objectives is covered. This will allow assessing the extent to which the JP contributed to transformational results when it comes to fulfilment of human rights, child rights, disability inclusion and gender equality and equity. |
| Sustainability | Assessing the extent to which JP work has succeeded in creating potential adoption by the government and local institutions in future and enhancing the likelihood that results will continue in future. Under this criterion, gender/equity and disability will be integrated through indicators, to ensure the full spectrum of evaluation objectives is covered. |

A summary of the original ToR evaluation questions and the proposed changes is shown in Table 2. Each of the OECD-DAC criteria above, the key evaluation focus areas and additional elements raised during the inception phase are presented as specific lines of inquiry and indicators under the relevant EQs in the detailed Evaluation Matrix (Annex 2).

Table 2 Overview of evaluation questions and proposed changes

| Relevance |  |
| --- | --- |
| EQ 1. Were the programme’s objectives relevant to the needs of the programme beneficiaries, having in mind political, social and institutional context of the country where the programme is implemented? | No change to EQ This EQ will include equality, equity and disability dimensions |
| EQ 2. Was the programme relevant to the SDGs, specifically Goals 1, 3, 4, 5, 8 and 10? | No change |
| EQ 3. Were coordination, management and financing arrangements clearly defined at the design stage and did these support institutional strengthening and local ownership? | No change |
| EQ 4. Was the programme successful in adjusting its implementation strategy and approach to the new circumstances imposed by the COVID-19 pandemic? | No change |
| Effectiveness |  |
| EQ 5. To what extent were the programme activities implemented and intended results achieved? What are the main programme accomplishments, with reference to the Results framework but also SDG Fund global goals? | Reference to SDG goals removed as this segment is covered in EQ 15 below under impact. |
| EQ 6. What are the positive or negative, intended or unintended, changes brought about by the programme? |  |
| EQ 7. How well did the programme collect and use data to monitor results? How effectively was updated data used to manage the programme? | Proposed to move this EQ to Efficiency |
| EQ 8. To what extent has the programme effectively identified, outreached, and engaged target groups, as well as marginalized groups (i.e. youth, persons with disabilities, returnees, internally displaced, ex-Yugoslav refugees, persons at risk of statelessness, minorities...) and supported gender mainstreaming and women’s empowerment? | No change |
| EQ 9. To what extent complementarity of agency-led activities was achieved? | Proposed to move this EQ to 3Cs |
| EQ 10. How effective was the programme’s interaction with other complementary projects/programs (including implemented by the UN) in order to trigger synergies maximizing development results? | Proposed to move this EQ to 3 Cs |
| EQ 11. Was the programme well-timed to capitalize on a specific window of opportunity? | No change |
| Efficiency |  |
| EQ 12. Have resources (financial, human, technical) been allocated strategically to achieve the programme results? | No change |
| EQ 13. Were there any weaknesses in programme design, coordination, management, human resource skills, and resources? | No change |
| EQ 14. How well did the programme team communicate with implementing partners, stakeholders and programme beneficiaries on its progress? In what aspects and to what extent did the programme contribute to UNCT coherence? | Proposed to move this EQ to 3 Cs |
| To what degree did the political developments in the country, as well as COVID-19 pandemic, influence the programme’s efficiency? | Separated from EQ above to become stand alone EQ |
| Impact |  |
| EQ 15. Has the programme contributed or is likely to contribute to medium or long-term social, economic, or other results, esp. with reference to SDGs 1, 3, 4, 5, 8 and 10 and the relevant NSSD chapters? | No change |
| EQ 16. What are the main benefits (qualitative and quantitative) for the target groups, including for vulnerable groups? How have cross-cutting issues, such as gender equality, disability, and reaching the most vulnerable, been effectively taken up? | No change |
| EQ 17. To what extent are key stakeholders/final beneficiaries satisfied with the programme implementation, specifically in terms of the partnership support and what are specific expectations for the potential follow-up assistance? | Proposed to remove this EQ as it will be tackled across indicators under Effectiveness criterion as it talks about perceptions |
| EQ 18. What is the impact of COVID-19 on the programme implementation and how the limitations imposed by the pandemic were lifted? | Covered under question under Efficiency |
| Sustainability |  |
| EQ 19. To what extent are the programme outputs sustainable? | No change |
| EQ 20. To what extent has the programme approach (intervention strategy) managed to create ownership of the key national stakeholders? | No change |
| Going forward – lessons learned and recommendations (EQs moved from sustainability) |  |
| What are the key lessons to be drawn at this point of the joint programme implementation? What are the main recommendations for the remainder, as well as for future programming? |  |
| How could the programme results be further sustainably projected and expanded? |  |
| At this stage of programme implementation, what could be possible after- programme priority interventions and general recommendations, which could further ensure sustainability and scaling up of programme achievements? |  |
| What would be future priority interventions to ensure long-term sustainability of the programme achievements, having in mind the current COVID- 19 related context? |  |

# 4 Methodology

## 4.1 Evaluability assessment

Evaluability is the extent to which any activity or programme can be evaluated in a credible fashion. It is informed by data availability, reliability, and validity as well as the programme's results framework and ToC, or logistical or cultural constraints which may influence evaluation data collection activities.

In terms of data availability, relevant documentation has been provided to the ET (including the overall programme, and component level-documentation; assessments, monitoring reports and studies; donor reports; as well as some documents pertaining to the normative framework for social protection and employability in Montenegro. These documents provide a good documentary basis for the analysis of the JP, and It is expected that the team will collect and analyse further documents throughout the evaluation process.

The JP includes an elaborate intervention logic. As the evaluation scope includes assessment of the entire set of JP interventions implemented by the five UN agencies, the intervention logic will be used to guide a contribution analysis. The ToC combined with available programme and monitoring data can provide a way to assess the JP performance and results.

The JP Programme Document contains a set of indicators at different levels, though they do not seem to fully capture the hierarchy of results (particularly outcome level). This may prevent full use of indicators for reflection on outcome level results and their catalytic potential. As noted above, the evaluation scope includes assessment of the impact, for which indicator assessment could be useful. The ET will use global outcome indicators for this assessment. Besides, the evaluation will apply theory based approach, which will help seek transformative potential of the programme. Based on the initial assessment of documentation and familiarisation with Montenegrin context, the evaluability of higher level of results (outcomes, impact) will be constrained.

ET will visit targeted regions and communities to understand factors for success or otherwise. This will substantially improve evaluability.

The breadth of scope of the programme activities within each area of intervention and the array of national stakeholders that the programme worked within elements of individual components do present some difficulties in generalizability but triangulation with key informant interviews at different levels should produce reliable evidence for the targeted evaluation criteria.

To conclude, assessment shows that potential constraints exist for evaluability. Still, the ET believes that the evaluation can be confidently undertaken given the documentation already compiled and interviews to be undertaken in-person and remotely.

## 4.2 Evaluation design and approach

The evaluation is designed as utilization-focused and consultative, maximizing the value of the evaluation findings, conclusions and recommendations for the intended users and supporting lessons learning for future interventions.

Taking into account the fact that the Programme is based on a robust ToC, the ET will employ a theory-based approach, whereby the primary focus of the assessment is on understanding cause-effect interactions between individual components and the programme’s desired outcomes. The theory-based approach aims to generate both an understanding of what has worked, but also an understanding of why it has worked. The JP has elaborated intervention logic and a ToC, which forms the foundation for the qualitative and quantitative research, providing a framework against which collected data will be analysed to enable testing the findings against the theories to see whether the hypothesized mechanisms do indeed work, and if so, under what conditions.

As required by the ToR, this evaluation will apply a mixed methods approach. The ET will combine the use of qualitative and quantitative data and rely on both primary and secondary data sources throughout the evaluation process. During both the inception and field phases, and considering the evolving COVID-19 situation, the ET will continuously adapt the techniques and instruments as required to maximize data collection efforts, applying a hybrid data collection approach. The data collection strategy is outlined below.

The evaluation data is needed to answer all the evaluation questions and enable an understanding of relevant contextual factors. Data will therefore be collected through a series of methods and tools for collecting, structuring, processing, and analysing data. The combination of data collection methods and techniques will vary depending on the scope and focus of the EQs, sub-questions and indicators.

The evaluation process will include three main phases: inception phase, field phase, and synthesis phase. The ET will use a variety of data collection methods (including both secondary (policy review and documentary analysis) and primary data (interviews) which are considered to be adequate given data needs, budget, and time constraints. Some of the data collection methods have already been used to produce this Inception Report, including literature review of relevant key policy and strategic documents of the five implementing partners and of the JP, and national level strategic frameworks.

Once completed, evaluation findings will then be disseminated widely to support learning and the buy-in for the evaluation findings.

## 4.3 Sampling

Consultations with stakeholders will be undertaken with a primary emphasis on understanding the qualitative aspects of the JP in all output areas. The ET will apply a purposive sampling approach to interviews, selecting the most relevant stakeholders, against the following criteria: level of engagement in and familiarity with JP interventions; understanding of JP focus themes, approaches, and their results; ability to share the perspectives and priorities of their respective institutions in relation with JP engagement. Besides, interlocutors knowledgeable of the JP focus theme(s) and operational context surrounding the work of the JP will also be engaged to contribute to the evaluation.

The specific selection of interviewees will be based on the following criteria:

- Information richness - are the respondents sufficiently familiar with the activities to provide insights from different perspectives including gender, ethnicity, disability, or regional dynamics?

- Accessibility - can the stakeholders be accessed by the evaluation team?

During the inception phase, initial stakeholder mapping was conducted and presented in Annex 4, resulting in a set of broad categories of stakeholders as summarized in the figure below.

Figure 2. Stakeholder map

To confirm information richness, the final selection will be made in consultation with PUNOs. Further considerations of the sampling strategy for selection of the communities to be visited include the following:

- Coverage: The team will select locations that present – as much as is feasible– the diversity in terms of Montenegro’s regional contexts and situations impacting beneficiaries, as well as balancing rural and urban experiences of beneficiaries.

- Realistic: The team will propose a realistic sample that is feasible within the time and budget constraints.

Based on the criteria above and in addition to Podgorica, the ET plans to visit Berane and Bar, to cover all three regions in Montenegro. As presented in Table below, these communities provide convergence of themes and interventions and coverage. The ET will also meet with relevant social sector authorities and NGOs (also those not engaging in JP activities) in these communities.

Table 3. Overview of JP activities in communities

| Municipality | ILO | IOM | UNDP | UNHCR | UNICEF |
| --- | --- | --- | --- | --- | --- |
| Overview of main activities at local level by PUNOs | Active labour market measure “Activate women” resulted in around 79 women were activated from the registry of Employment Agency of Montenegro. Ongoing | Awareness raising campaign on dangers of trafficking in human beings (e.g. students, youth from Roma and Egyptian settlements (12-18 years) from 4 municipalities). Ongoing | Pilot service with NGO HELP, above 80 beneficiaries | 996 persons were supported by UNHCR through 2,171 legal advices towards regularizing their legal status | 823 adolescents have gone through the social-emotional skills programmes which was deployed using both online tools and face-to-face workshops in the southern and central region |
| Bar | X |  | X | X |  |
| Berane | X | X |  | X |  |
| Podgorica | X | X | X | X | X |
| Tuzi |  |  | X |  |  |
| Golubovci |  |  | X |  | X |
| Bijelo Polje | X |  | X |  |  |
| Rozaje |  |  | X |  |  |
| Savnik |  |  | X |  |  |
| Pluzine |  |  | X |  |  |
| Ulcinj |  |  | X |  | X |
| Niksic | X | X | X |  | X |
| Tivat | X | X |  |  |  |
| Budva |  |  |  | X | X |
| Cetinje |  |  |  |  |  |
| Danilovgrad |  |  |  |  | X |
| Herceg Novi |  |  |  |  | X |
| Other |  |  |  | X |  |

## 4.4 Data collection methods and tools

Data will be collected using multiple methods for collecting, structuring, processing, and analysing data as appropriate. Such methods will include: stakeholder mapping; context mapping; in-depth and structured documentary review of the JP design, implementation approaches, results and processes; structured desk analysis of policy documents and legislative frameworks; analysis and testing of the ToC; analysis of results from M&E systems and data at national and subnational levels; aggregation and analysis of data collected via the data mapping templates; contribution analysis to determine factors which promoted or impeded the progress against intended results and attribution analysis to the extent possible; systems analysis of management, monitoring, quality control and assurance strategies; analysis of sustainability strategies and systemic barriers to sustainability; in-depth interviews and site observation during site visits to the sampled localities.

The evaluation will apply the following primary data collection methods: 1) KIIs, and 2) site observations. As noted above, the bulk of the primary qualitative data will be conducted via semi-structured KII with a range of stakeholders in Table 5 below and Annex 4. Seeking information from diverse stakeholders is intended to promote the participation of different groups and seeks to avoid biases through triangulation. The ET envisages that a total of approximately 50 key interlocuters will be interviewed at the national level and community level.

In addition, ET will organise approximately 20 interviews with participants of activities implemented and supported by UNICEF (up to 5 - directors of schools, teachers, camp managers), ILO (trainers, participants – up to 5), UNDP (mentor, participants – up to 8), IOM (members of the local teams that provided direct support to returners – up to 3). Following the inception phase discussions with PUNOs, it was decided not to organise FGD as they are not possible to do as participants are from different municipalities, or the same municipalities but attended different activities, some of them still ongoing.

During the field missions, ET will conduct site observations of IOM and UNICEF’s supported activities in sampled communities. Detailed site observations plan will be finalized once the sample is confirmed.

## 4.5 Data collection tools

Key Informant Interview Guide – UNICEF

    - Key Informant Interview Guide – PUNOs

    - Key Informant Interview Guide –Government and service providers

    - Key Informant Interview Guide – Development partners (UN agencies, donors, other development partners)

These guides are based on the questions outlined in the evaluation matrix and are sufficiently general to be applied in interviews, allowing for adaptations as appropriate to the expertise and relevance of the stakeholders to the programme under review.

Connection of Tools to Evaluation Dimension. The tools profiled in Annex 5 also describe the link between specific questions on the tools and the overarching evaluation dimensions. The Evaluation Matrix (Annex 2) provides a summary of the link between each data source and the indicators to be reviewed as part of the process of building conclusions.

## 4.6 Evaluation phases

### Documentary analysis – inception and desk review phase

The document review will include the following types of reports:

UNICEF’s, UNDP’s, ILO’s, UNHCR’s, IOM’s and RCO’s corporate policy documents, guidelines; JP framework, monitoring data, reports, and studies as well as other types of documentation that can provide an insight into the Joint Programme focus and results across areas of intervention (see Annex 7 Bibliography) to extract relevant findings related to the JP performance in Montenegro.

Analysis of external sources pertaining to the JP focus areas and country context. This group includes all other studies, analyses, evaluations, and policy documents produced by non-UN entities (e.g., EU, IFIs, civil society, academic, think tanks, international organisations, etc.). This group is especially important to see how others have researched and assessed UN agencies’ support to the social protection sector but also overall country development when it comes to social protection.

### Primary data collection phase

The evaluation primary data collection is planned for June 2022.  Initial meetings with PUNOs during inception helped the team familiarise with the JP and also to discuss the approaches to primary data collection. It was decided that the primary data collection will be conducted applying a hybrid approach, whereby the ET will be in Podgorica in the period between 30 May – 1 June 2022, followed by in-person field missions to Berane and Bar by national team member; while team leader will conduct remaining meetings remotely.  Remote primary data collection will be organised using platforms such as MS Teams, Zoom, Skype, or phone for all interviews.

For all these approaches, the team will strictly adhere to confidentiality rules and data protection, which will contribute to greater openness of the interviewees and safeguard them against possible risks. The following data collection tools will be applied:

Key informant interviews

Most of the primary data will be collected from a selection of priority stakeholders during the field phase. During the primary data collection phase, semi-structured key informant interviews (KII) will be carried out with: i) Joint Programme implementing partners, ii) key national stakeholders (key government interlocutors, implementing partners, civil society) and iii) development partners.

The final beneficiaries of the programme – children and adolescents – will not be interviewed as agreed during the inception meeting with the Joint Evaluation Management Group. The ET envisages that a total of approximately 80 (34 UN staff, 14 consultant, 6 CSOs implementing partners, 1 municipality as implementing partners, 16 representatives of line ministries, 4 staff of Employment Agency, 3 staff of MONSTAT) key informants will be included in the consultation process. The most critical KII will be confirmed prior to filed work in consultation with PUNOs. An overview of those stakeholders to be consulted is presented in Table 3. The evaluation matrix will form the guides for semi-structured interviews to be conducted.

The ET will not conduct any interviews with the final beneficiaries of the project:  children or adolescents.

Table 4: Consultation Strategy

|  |  | No. of people | Relevance | Effectiveness | Efficiency | 3CS | Impact | Sustainability | Evaluation Phase | Tools |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Stakeholder group | Types of stakeholders |  |  |  |  |  |  |  |  |  |
| UN | RCO | 6 |  |  |  |  |  |  | All stages | Interviews |
|  | ILO | 2 |  |  |  |  |  |  | All stages | Interviews |
|  | IOM | 3 |  |  |  |  |  |  | All stages | Interviews |
|  | UNDP | 8 |  |  |  |  |  |  | All stages | Interviews |
|  | UNHCR | 5 |  |  |  |  |  |  | All stages | Interviews |
|  | UNICEF | 9 |  |  |  |  |  |  | All stages | Interviews |
|  | WHO | 1 |  |  |  |  |  |  | Filed phase | Interview |
| Ministries | Ministry of Finance | 5 |  |  |  |  |  |  | Filed phase | Interviews |
|  | Ministry of Labour and Social Welfare | 5 |  |  |  |  |  |  | Filed phase | Interviews |
|  | Ministry of Interior | 5 |  |  |  |  |  |  | Filed phase | Interviews |
|  | Ministry of Education | 1 |  |  |  |  |  |  | Filed phase | Interviews |
| Government agencies/bodies /municipalities | Employment Agency of Montenegro | 4 |  |  |  |  |  |  | Filed phase | Interviews |
|  | Centres for Social Work | TBC |  |  |  |  |  |  | Filed phase | Interviews |
|  | MONSTAT | 3 |  |  |  |  |  |  | Filed phase | Interviews |
|  | Municipality of Bar | 1 |  |  |  |  |  |  | Filed phase | Interviews |
| Civil society (implementing partners) | Montenegrin Employers Federation | 1 |  |  |  |  |  |  | Filed phase | Interviews |
|  | NGO Help | 1 |  |  |  |  |  |  | Filed phase | Interviews |
|  | NGO Civic Alliance | 1 |  |  |  |  |  |  | Filed phase | Interviews |
|  | NGO Pedagogical Center | 1 |  |  |  |  |  |  | Filed phase | Interviews |
|  | Association of Scouts | 1 |  |  |  |  |  |  | Filed phase | Interviews |
|  | NGO Defendology | 1 |  |  |  |  |  |  | Filed phase | Interviews |
| Consultants | Individual consultants | 11 |  |  |  |  |  |  | Filed phase | Interviews |
|  | University of Maastricht | 3 |  |  |  |  |  |  | Filed phase | Interviews |
| Final beneficiaries | Final beneficiaries from Podgorica, Berane, Bare | 20 |  |  |  |  |  |  |  | Interviews |

## Data analysis

Once the primary data collection is finalised, the ET will embark on full-fledged analysis and synthesis of evidence in order to distillate most important findings. The members of the evaluation team will internally share and review interview notes as a basis for reflection on main areas of intervention of the UN Joint Programme and its performance. Data analysis methods employ appropriate analysis methods spending on type of data. For instance, the documentary review will rely on thematic narrative analysis for highlighting key themes identified in the documents and connect them to the relevant points in the evaluation matrix. The pre-existing quantitative data will be processed via descriptive and comparative quantitative analysis. This will involve frequency analysis of key patterns with cross tabulation for dimensions of interest (such as gender or geographic location or thematic area as available). Where possible, the analysis will seek to identify trends across criteria or time and will be disaggregated by gender or disability where possible.  Qualitative iterative data analysis is based on an iterative process of identifying key thought units related to each evaluation question from KIIs, organizing these thought units into clusters and identifying the key themes within each cluster. These are then clustered into categories and emergent themes from each category for further analysis and re-categorization to identify key patterns. Evidence for conclusions is to be built via triangulation analysis. As the evaluation is theory based and strategic in nature, Contribution analysis will assist to understand the linkage to observed programme effects and will play a role in conclusions regarding effectiveness, relevance, and sustainability. The ToC will serve as basis for assessment of the perceived relationships between the various linkages in the chain of results and the validity of the assumptions. These will be used to generate a plausible argument for programme contribution.

Due to the importance of triangulation of findings from different sources in the exercise, a key component of the data analysis will be the debriefings at the end of the field phase to be used to substantiate the findings and to develop the conclusions and recommendations in response to the evaluation questions. Triangulation involves comparing information from different sources, collected by different evaluators and obtained from different methods. In alignment with the utilization focused principle of the evaluation, findings and conclusions will be shared with PUNOs to elicit feedback or correct of facts according to the agreed schedules and templates.

## 4.7 Ethical considerations

The evaluation will ensure compliance with ethical and moral principles, including the application of the UNEG Code of Conduct for Evaluation and Ethical Guidelines for Evaluation. The ET will also adhere to the Standard Operations Procedures for Quality Assurance and Ethical Standards in UNICEF-supported Research, Studies, and Evaluations and the Core Commitment for Children in Humanitarian Action.

Children and adolescents will not be interviewed. Across all interviews, the evaluation will adhere to the ethical considerations related to safety, confidentiality, and data protection regarding its treatment of participants in the evaluation process.

The team will apply ethical standards to the data collection process including the protection of rights and dignity of evaluation informants. This includes applying the principles of informed consent, voluntary participation, assurances of anonymity and confidentiality of data protection and do no harm principles in all parts of a data collection exercise.

### Protocols for Safety, Confidentiality, and Data Protection.

The principles of informed consent and the maintenance of confidentiality are crucial pillars of this evaluation. Interviewees will be informed at the start of the interview regarding the purpose of the evaluation, assurances of voluntary participation, and confidentiality of all responses. Potential interviewees are likely to have high workloads and the ET will use the principle of mutual respect by ensuring that the interviews are as concise and as efficient as possible. Verbal Consent forms are included in Annex 6.

Data protection measures will be used to ensure respondent confidentiality across all data instruments. All interview notes will be kept electronically on password encrypted computers. Personal names and other potential personal identifiers will be removed from the data prior to analysis. Data analysis will be carried out only by ET members to ensure confidentiality. Data compiled in reporting will be aggregated so that individual responses cannot be traced to specific locations or individuals. After the finalization of the report, the personal identifiers will be deleted to further protect individuals from possible identification.

## 4.8 Risks and assumptions

The evaluation is likely to face several external risks over which the ET will only have limited control. These are presented in the Table 4 along with our approach to mitigating or preventing them.

Table 5: Risks and mitigation strategies

| Risk (probability) | Potential Impact | Mitigation and preventative measures |
| --- | --- | --- |
| Non-availability of stakeholders to participate in data collection activities (Medium). | High | To avoid this, the ET will undertake a detailed preparation for the primary data collection and clear communication with interview partners to ensure proper execution of the evaluation. All relevant stakeholders will be approached in advance to set appointments for meetings. In cases where interviews happen online, communication will be followed up with distribution of relevant links for teams/zoom/other feasible platforms. Moreover, confidentiality and data protection will be ensured and communicated clearly from the beginning to ensure all participants feel safe. |
| The evaluation design and data collection tools do not yield robust evaluation results (Low). | Medium | The ET will always adopt a reflective approach during the evaluation. The Team Leader will monitor the evaluation process to ensure any necessary adjustments are made. Throughout the process, constant communication with the Joint Evaluation Management Group will be guaranteed to ensure that challenges are identified and addressed as soon as possible. |
| Interviewees are reluctant to share their true standpoints or tend to provide biased rather than critical responses (Medium). | High | The ET will use a variety of triangulation methods to ensure that the respective area of inquiry where potential for biased response or halo effect is noted is fully analysed. The team will conduct interviews with a range of stakeholders coming from different sectors (government institutions at national, regional, and subregional level; CSOs, UN agencies, donors, and other development partners). The interview guides include areas of inquiry to ensure that similar questions or areas are prompted with these different stakeholders. Triangulation of data received from these sources, including documentary evidence, will be conducted to ensure that full stock of views, examples, and evidence is collected to provide for balanced assessment. Limitations concerning the reliability of data or data collection tools will be made explicit. |
| Inconclusive evidence on some of the evaluation questions (Medium). | High | The ET will remain transparent where evidence may not be conclusive and will apply triangulation methods to mitigate where possible. |
| Access to stakeholders in the field and security (High). | High | The COVID-19 situation is evolving and will present risks in terms of access to stakeholders. The ET will use their own and the UN’s risk management tools to identify risk alerts. |

# 5 Evaluation workplan and logistics

## 5.1 Timeframe and logistics

The dates presented in Table 6 present a proposal of the timeline for the evaluation to be agreed with the Joint Evaluation management Group.

Table 6: evaluation schedule

| Phases, Deliverables and Timeline | Dates |
| --- | --- |
| Phase 1 - Inception |  |
| Initial Virtual Briefing | 10 May 2022 |
| Inception Report Draft 1 submission to Evaluation Management Group (EMG) | 20 May 2022 |
| EMG comments | 16 June 2022 |
| Final Inception Report | 18 June2022 |
| Phase 2 – Data collection |  |
| Data collection – online data collection Montenegro/home-base | 30 May – 30 June 2022 |
| Internal Evaluation Team Data Analysis Workshop and Findings and conclusions building | 30 – 8 July 2022 |
| Debriefing with EMG | 6 July 2022 |
| Phase 3 - Data Analysis and Reporting |  |
| Submission Draft ER | 15 July 2022 |
| Comments from EMG | 22 July 2022 |
| Validation meeting with EMG (virtual) | 27 July 2022 |
| Submission ER Final | 28 July 2022 |
| Final ER for approval by EMG | 29 July 2022 |

The evaluation team will conduct the data collection between 30 May-14 June 2022 (Table 6). The primary data collection will be  continued through the month of June 2022 to ensure that any meetings that cannot happen within the originally envisaged data collection timeframe can still be conducted. The mission schedule may still need to be adapted depending on further consultation with PUNOs regarding logistical feasibility or availability of stakeholders. The final schedule will be confirmed with the EMG prior to the field visit.

Table 7: Summarized Evaluation Schedule – primary data collection Phase

| Days/dates | Team member | Location | Stakeholders |
| --- | --- | --- | --- |
| 30 June -2 July 2022 | Full Team | Podgorica, Montenegro | Interviews with: - UNICEF Team - UNDP Team - ILO Team - UNHCR team - IOM Team Interviews with key Ministries and national institutions Interviews with key implementing partners |
| 2-June 2022 | National Expert | Niksic Podgorica | Interviews with other main government stakeholders Interviews with NGOs |
| 3 – 6 June 2022 | National Expert | Podgorica | Interviews with other main government stakeholders Beneficiaries Interviews with NGOs |
| 7 - June | National Expert | Bar | Interviews with local government stakeholders Mentors, beneficiaries |
| 8 – June | National Expert | Podgorica | Beneficiaries |
| 9 – June | National Expert | Berane | Interviews with local government stakeholders Mentor |
| 10 – June | National Expert | Podgorica | Interviews with other main government stakeholders |
| 13-24 June 2022 | Full Team | Remote | Any outstanding meetings |
| 27-28 June 202 | Full Team | Remote | Internal Data Analysis Workshop and Conclusions |
| 6 July 2022 | Full Team | Remote | Presentation of Preliminary Findings and Conclusions |

## 5.2 Support and information required from PUNOs

Throughout the evaluation, the ET may require support from PUNOs. As present, two key areas of support have been identified: support to introducing the ET to assist scheduling of meetings/interviews and organizing field visits.

Scheduling of meetings: Support is requested from PUNOs to make official requests for meetings, particularly for national government institutions but also others. Support needed includes:

- PUNOs will be requested to officially introduce the ET to facilitate the preparation of the agenda of remote meetings (sending out the initial emails regarding the evaluation to all stakeholders).

Field visits to the the three communities: Support will be needed to identify the list of stakeholders to be engaged in community-level consultations and facilitating the preparation of the schedule of meetings with those stakeholders that are identified.

## 5.3 Roles and responsibilities

The ET consists of two team members (one international, Team leader and one national senior expert), with each one having specific responsibilities within the evaluation. Table 7 presents an overview of main roles of the evaluation team members.

Table 8: Roles and responsibilities of the evaluation team

| Team Members | Primary Role | Specific tasks within the Evaluation | Deliverables |
| --- | --- | --- | --- |
| Zehra Kacapor-Dzihic | Team Leader | - Design the evaluation approach, and methodology - Ensure evaluation incorporates gender analysis in its design and that team members are prepared for applying it throughout the evaluation - Coordinate evaluation process and lead team – ensure that team members’ activities are properly coordinated and that the team members can contribute to data collection, analysis, and conclusion development. - Represent the team in meetings - Oversee collection and analysis of field and desk data (interviews, , literature) - Lead the process for drafting and revision of the inception package, feedback presentation and draft and final evaluation reports in line with established standards - Lead the data analysis/validation workshop - Present preliminary findings to the key stakeholders from the evaluation reference group. - Provide feedback as needed on the evaluation process | - Draft Inception Package - Finalize Inception Package - Lead evaluation field mission - Lead Exit Debriefing - Draft Evaluation Report - Final Evaluation Report |
| Jasna Zarkovic | National expert | - Conduct desk review - Contribute to inception process - Contribute to methodology design and lead the tool development, - Ensure that gender issues are addressed in coverage areas - Conduct fieldwork and participate in meetings with evaluation team and stakeholders - Contribute to drafting / revision of evaluation products: inception package, feedback presentation, evaluation report(s); - Contribute to the data analysis and drafting of the final report - Provide feedback as needed on the evaluation process. | - Conduct desk review - Liaise with team lead on field mission logistics and stakeholder identification - Contribute to Inception Package - Provide feedback for finalizing Inception Package - Participate in evaluation field mission - Participate in Exit Debriefing Presentations - Contribute to drafting Evaluation Report - Provide feedback to final Evaluation Report |

# 6 Quality Assurance

Quality assurance (QA) in evaluation refers to the process by which evaluation standards will be upheld. In this case, UNICEF uses the Global Evaluation Reports Oversight System (GEROS). The evaluation quality will be addressed in several ways throughout the process. First, through the application of core GEROS standards; second, through approaches supporting data reliability, consistency, and accuracy; and third, through internal quality assurance of internal team deliverables by team leader.

The EMG will provide quality assurance for the evaluation process and all deliverables (inception report, preliminary findings presentation and draft report). The EMG will liaise with UNICEF external quality assurance and internal ethical review structures to ensure their review and quality assurance support including sign-off. The EMG will also review the final deliverables to ensure their quality. The final inception and evaluation reports will be assessed by external independent company in the framework of GEROS.

An EMG will provide input, guidance, and feedback on the draft deliverables to ensure that the evaluation is appropriate, relevant, and useful for the intended objectives. The EMG will also be the primary audience for the exit debriefing presentation conducted at the end of the field phase (July 2022-date TB) to present preliminary findings and conclusions. The EMG will provide immediate feedback to the preliminary findings which the evaluation team will take into consideration in the development of the final evaluation report. The EMG will also review proposed recommendations and provide feedback on feasibility and relevance to the Montenegro context.

The ET also has internal quality assurance checks which include:

- Adoption of a systematic approach to analysis, ensuring validity and transparency in the relationship between findings, conclusions, and recommendations. Findings from diverse evidence streams will be consolidated in a structured way through an evaluation grid.

- Triangulation methods will include the following: (i) findings will be based on data from more than one source; (ii) the use of different methods to explore the same aspect; (iii) the involvement of different team members to explore the same aspect of the evaluation and ensure that findings are fully endorsed by team members.

- Share analysis –the evaluation team will come together virtually during the analysis to ensure full consolidation of evidence against the evaluation matrix and to confirm and debate emerging analytical themes. The use of structured tools will ensure that findings are directly traceable to evidence and any tensions or contradictions within the evidence are transparently recorded so that they can be explored and assessed through the analytical process.

There is no conflict of interest affecting members of the ET in relation to this Joint Programme.

# Annexes

# Annex 1: Terms of reference

Background and context of evaluation subject

Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro is a Joint Programme (JP) implemented and funded by ILO, UNDP, UNHCR, UNICEF and IOM and the Joint SDG Fund in the total amount of USD 2,689,00.00, with the aim to enhance the capacities of the social protection system in Montenegro to better serve people in need. The programme applies advanced methodologies (foresight, human-centred design, policy simulation tools, etc.) in order to improve targeting, expand coverage, and address adequacy of social protection, but also activate Montenegro’s youth who are currently not in education, employment or training (NEET) and other vulnerable and marginalized groups through enhanced labour activation.

The JP aims to enhance the capacities of the key stakeholders of the national social welfare system to better serve people in need, regardless of their citizenship status. It strives to render policy making evidence-based and policies cost-effective, while ensuring service provision is well-targeted and user- centred. In order to reach vulnerable and marginalized groups, the JP focuses on the most pressing problems of the current social protection system, including targeting, coverage, and adequacy of social assistance and effectiveness of services. Programme`s theory of change rests on three key hypotheses:

If national SP policies are better informed by updated evidence on poverty, especially related to marginalized groups and the impact of these policies can be modelled and predicted before they are submitted for adoption then the SP system can more effectively alleviate poverty and accelerate sustainable human development within existing fiscal space.

If the most vulnerable youth have increased access to SP services or can co-design programmes/ services targeted to their needs and are equipped with relevant skills then they will be more resilient, able to lead more productive lives and better fulfil their potential, thus reducing dependency on social assistance and helping to break intergenerational cycles of poverty.

Finally, if Montenegro’s SP system can more effectively alleviate poverty and reduce social exclusion, and if more young people in Montenegro lead productive lives and fulfil their potential, then progress towards more sustainable human development will accelerate.

Accordingly, programme entails the following objective, outcomes and related activities:

Objective: By 2022, Montenegro has improved capacity to design impact-oriented, evidence-informed social protection policies and deliver integrated human-centred services that reduce poverty and social exclusion of the most vulnerable and marginalized, focusing on young men and women, thus accelerating sustainable human development.

Outcome 1: Social policy simulations based on data and evidence, including on the impact of COVID- 19, and subsequent scenarios for social protection system reform will result in more just, better targeted and more adequate social protection programmes and services for the most vulnerable groups (e.g. youth, migrants, returnees, refugees, stateless persons, children and victims of trafficking). The programmes and services complement labour market activation for decent work and development of employability skills. This work builds on the international CODI (Core Diagnostics Instruments) Assessment and a UN Rapid Social Impact Assessment (RSIA) of COVID-19, as well as the MAPS SDG acceleration reports and is fully aligned with the national institutional reform approach.

Output: New tool supports analysis of poverty-related data and simulation of policy impact. Activities:

1.1 Provide deeper analysis of poverty data to identify furthest behind

1.2 Operationalize recommendations from CODI to increase effectiveness, efficiency, capacity to address poverty within fiscal space

1.3 Develop poverty reduction scenarios to target furthest behind

1.4 Accelerate implementation of optimum scenario(s)

Outcome 2: Innovative skills building, mental health and labour market activation measures will increase the participation of young men and women in education, employment or training, strengthen their resilience, prevent passivation and reduce their dependence on social assistance.

The intervention would expand the coverage of children by social transfers by 50% and, combined with labour activation measures and other interventions in social protection, could potentially reduce the national poverty rate by 3 percentage points (compared to the recalculated poverty rate after COVID-19 impact, available once the simulation exercise is completed). Given the expected socio- economic COVID-19 impact in terms of increased unemployment and poverty as well as newly emerging vulnerable groups this target remains important but is also ambitious.

Output: Human-centered, integrated service delivery at community-level, focusing on youth, to increase their participation in education, employment or training to reduce dependence on social assistance, are rolled-out.

Activities:

2.1 Profile NEETs, registered beneficiaries of SP, those without access to SP system, to refine targeting and design an activation programme

2.2 Support “first-time” access to SP system/employment for refugees/persons at-risk of statelessness/readmitted nationals by supporting regularization of legal status and social inclusion and enhancing multi-sectoral coordination and referral mechanisms for vulnerable groups

2.3 Increase access to human-centred, effective social support services for targeted groups, including labour market activation

2.4 Strengthen resilience through “21st century” skills development, including socio- emotional/self-care skills tailored to unique needs (e.g., mobile-based delivery)

2.5 Enhance identification of victims of trafficking and raise awareness on the dangers of trafficking, targeting youth with a focus on marginalized groups

By the end of the JP, both outputs will have been embedded in Government processes, after an iterative process of piloting, testing, user feedback and monitoring. Consequently, the most vulnerable women, men, boys and girls will benefit from:

- Laws designed to reduce poverty and increase social inclusion,

- Cash transfers that are well-targeted, adequate and cover all those who are in need of social assistance,

- Labour activation and other related services which respond to the specific needs of users,

- Innovative skills and resilience building programmes,

- Inclusion into the social protection system of those previously invisible.

As a result, those who are most in need will be protected by the social protection system and have the skills and support that enable them to lead independent, productive lives. By producing such impact, the programme helps the country in direct achievement of the following Sustainable Development Goals (SDGs):

Goal 1 End poverty in all its forms everywhere.

1.1. By 2030, eradicate extreme poverty for all people everywhere

1.2. By 2030, reduce at least by half the proportion of men, women and children of all ages living in poverty in all its dimensions according to national definitions

1.3 Implement nationally appropriate social protection systems and measures for all, including floors, and by 2030 achieve substantial coverage of the poor and the vulnerable

1.b. Create sound policy frameworks at the national, regional and international levels, based on pro-poor and gender-sensitive development strategies, to support accelerated investment in poverty eradication actions

Goal 3 Ensure healthy lives and promote well-being for all at all ages

3.4 By 2030, reduce by one third premature mortality from non-communicable diseases through prevention and treatment and promote mental health and well-being

Goal 4 Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all

4.4 By 2030 substantially increase the number of youth and adults who have relevant skills, including technical and vocational skills, for employment, decent jobs and entrepreneurship.

Goal 8 Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all

8.6 By 2020, substantially reduce the proportion of youth not in employment, education, or training

Goal 10 Reduce inequality within and among countries

10.2 By 2030, empower and promote the social, economic and political inclusion of all, irrespective of age, sex, disability, race, ethnicity, origin, religion or economic or other

Expected SDG impact

In 2019 and 2020, there was a unique window of opportunity to integrate SDG acceleration – specifically Goals 1, 3, 4, 5, 8 and 10. An important entry-point was a first-of-its-kind comprehensive SP system assessment using Core Diagnostic Instrument (CODI). The key objective was to break the vicious cycle of inter-generational poverty by turning it into a virtuous cycle. The mutual reinforcements between the SDG targets are obvious: A better targeted social protection system with expanded coverage will ensure that those who are most marginalized receive adequate support, while those who are able to work, can find decent employment and thus lift themselves out of poverty and contribute to society and a better funded social protection system (double win).

Relevant objective/s from the national SDG framework

National Strategy for Sustainable Development 2030 (NSSD):

- 4.1 Improvement of state of human resources and strengthening of social inclusion
- 4.2 Support to values, norms and behaviour patterns significant for sustainability of the society - 4.2.5 Stimulate employability and social inclusion

The evaluation will also take into account overall result framework, including programme result framework as well as Joint SDG Fund Outcome and Output indicators, and operational performance indicators.

Target groups

The Activate! JP targeted the most vulnerable and marginalized people focusing on youth (including NEETs), Roma, people with disabilities, people facing mental health challenges, persons at risk of violence, abuse, exploitation or exclusion (e.g., due to ‘invisibility’ in the current system), ex-Yugoslav refugees, asylum seekers, stateless/persons at risk of statelessness, migrants, returnees, people living in poverty and others. Particular attention was paid to cross-cutting needs of women and children within the above categories, e.g., the capacity of children to access cash transfers and improved protection services, thus contributing to alleviation of long-term and inter-generational poverty. Target groups and proposed programme approaches have been selected based on key data and the most pertinent recommendations of human rights mechanisms.

Partner organizations and other stakeholders

- Line ministries and other relevant public bodies - Ministry of Economic Development and Ministry of Finance and Social Welfare, Employment Agency, and other key Ministries (governing the departments of Education, Interior, Youth and Sports, Human and Minority Rights-Department for Gender Equality, Health). Local service providers have also been engaged, such as local employment bureaus and Centres for Social Welfare.

- Civil society organizations (CSOs) - Red Cross, various youth organizations/associations, local NGOs working with Roma communities, trade unions, employers’ federations, as well as NGOs licensed to provide shelter to victims of trafficking is an important asset of this JP.

- IOs - World Bank which in Montenegro is focusing on the Jobs and Growth agenda, and WHO which contributes with technical expertise on mental health barriers to employment.

- Montenegro Statistics Office (MONSTAT), to provide data concerning disaggregation of poverty related data and to participate in data processing.

- Media engaged in trafficking awareness raising campaign and in other relevant communication endeavours.

Timeframe

The initial timeframe of the Activate! Joint Programme was December 1st, 2019- November 30th, 2021 (24 months). However, the Joint Programme has been granted a non-cost extension, duly justified by external constraints causing nearly nine-month delay in its implementation. This was primarily due to prolonged process of the new Government being formed following the August 2020 national elections in Montenegro, and the majority of the Government cabinets being in place only at the end of Q1 2021. In addition, during the implementation period, the Activate! Joint Programme has been prudently managed with timely adjustments to account for the Covid-19 emergence and its aftermath by prioritizing workplan readjustment, implementation and continuation of cooperation with the new Government once in place.

For these reasons, and upon granted non-cost extension, the updated implementation timeframe of the Activate! Join Programme is 1st December 2019- 31st July 2022 (32 months).

II. Evaluation purpose

The purpose of this Final Evaluation is to provide summative assessment of the achievements of the

Joint UN Programme Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro (short- Activate! Joint Programme (JP)). The Final Evaluation will be participatory, involving relevant stakeholders, and in line with the United Nations Evaluation Group’s (UNEG) Norms and Standards for Evaluation in the UN System, using the guidance on Joint Evaluation and relevant UNDG guidance on evaluations.

The evaluation will provide an independent and equity, age and gender-sensitive assessment of the joint programme. In particular, it will assess the approach taken by PUNOs, whether the assumptions made in the JP’s ToC were appropriate, and whether activities and interventions indeed contributed to progress within the framework of the ToC, i.e. whether the proposed approach was scalable and to determine to what extent the desired change has occurred. The evaluation will also be forward- looking by reinforcing good practices, identifying areas for improvement for future similar programmes, and providing conclusions and recommendations on potential further areas of intervention.

In assessing the degree to which the joint programme met its intended objectives and results, the Final Evaluation will provide key lessons about successful approaches and operational practices, as well as highlight areas where the programme performed effectively than anticipated. In that sense, this Final Evaluation is equally about impact and accountability as it is about learning. The information, findings, lessons learned, and recommendations generated by the programme evaluation will be used by the Joint Programme Board and other relevant stakeholders to inform future programming, but also for PUNOs to potentially modify practices and further improve delivering-as-one approach.

III. Evaluation scope and objectives

Evaluation scope

The independent and equity, age and gender-sensitive evaluation will be undertaken for Activate! Joint Programme’s interventions across Montenegro in the period between December 2019 and April

2022, bearing in mind that the final evaluation must be completed three months prior to the JP’s implementation end date - July 31, 2022. The evaluation will be conducted in close consultation with the JP Programme team (Joint Evaluation Management Group), led by UNDP, throughout the process to ensure the principles of national ownership, transparency and mutual accountabilities are followed. The evaluation process will be participative and will involve all relevant programme’s stakeholders and partners, as well as final beneficiaries. Evaluation results will be disseminated amongst government, development partners, civil society, and other stakeholders.

The evaluation will comprise the following key stages:

Desk review: The Evaluation Team will conduct a detailed review of the programme materials and deliverables including but not limited to the Project Document, theory of change and results framework, monitoring reports, annual workplans, consolidated progress reports, relevant national surveys and data, knowledge products, as well as policy and legal documents.

Finalization of evaluation methodology and work plan: In consultation with the Joint Evaluation Management Group, the Evaluation Team will finalize the appropriate methodology to address the key objectives of this evaluation. The methodology will entail a participatory process for data collection, generating an evidence base to substantiate all findings while ensuring that the data collection methods and data analysis is of high quality and that stakeholders are involved in data collection processes and debriefed on regular basis to address any unforeseen challenges requiring support or clarification. Data collected should be disaggregated by age, gender, disability status, site, etc. where relevant.

Data collection - field visits, focus groups and key informant interviews: The Evaluation Team will conduct field visit supported by UNDP and collect data from the representatives of main institutional partners and implementing partners, as well as final beneficiaries, using a mix of qualitative and quantitative approaches. For the interviews, the Evaluation Team is expected to design evaluation questions around relevance, effectiveness, efficiency and sustainability criteria, tailored to different stakeholders to be interviewed. In the occurrence of Covid19 travel and meeting restrictions, the Evaluation Team will conduct the interviews remotely when necessary, using virtual technological solutions.

Preparation of the draft evaluation report and finalization of the report: The Evaluation Team will prepare the draft evaluation report, submit it to the Evaluation Management Group for comments and final approval upon addressing the comments provided.

Debriefing: The Evaluation Team will debrief the Evaluation Management Group about the findings including key observations and recommendations based on verifiable facts and figures.

Evaluation objectives:

- To assess the project accomplishments against planned results, objectives, targets and indicators, including the aspects of effectiveness and efficiency of the intervention and sustainability of project benefits beyond the lifetime of the project;

- To assess, to the extent possible, contribution to improving the situation of vulnerable groups identified in the JP, including persons with disability;

- To assess contribution to SDG acceleration;

- To assess contribution to UN reforms (including UNCT coherence);

- To assess contribution to SDG Fund global goals;

- To assess, to the extent possible, contribution to the National Strategy for Sustainable

Development (NSSD) of Montenegro;

- To assess the relevance, effectiveness, design, efficiency, coherence and sustainability of

the joint programme from its inception to its completion;

- To provide reflections on the previous state of play and capacities of the main actors as

compared to the beginning of the project implementation and in relation to that, provide

recommendations and guidance for future similar JP initiatives;

- To provide gender-sensitive assessment of the joint programme by maximizing the use of

existing data to support mainstreaming of gender analysis across all questions, including

those unrelated to gender;

- To identify and consolidate good practices, human stories, lessons learned and make

recommendations on processes, management, partnerships and other aspects of project implementation that would benefit future joint programmes agencies in this area.

As persons with disabilities are among the most vulnerable and marginalized groups across the evaluation will therefore assess to what extent:

IV.

Joint programme design, implementation, and monitoring have been inclusive of persons with disabilities (accessibility, non-discrimination, participation of organizations of persons with disabilities, data disaggregation)
Joint programme effectively contributed to the socio-economic inclusion of persons with disabilities by providing income security, coverage of health care, and disability-related costs across the life cycle.

Guiding questions on Persons with Disabilities will be provided to the consultant.

Evaluation questions

The Evaluation is to answer the following questions, based on the identified main objectives, to determine the Joint Programme’s relevance, performance, results, effectiveness, efficiency, impact and sustainability, including lessons learned and forward- looking recommendations.

The Evaluation questions proposed below are not limited. Evaluation questions will be further refined by the evaluation team during the desk review phase and in consultation with the Evaluation Management Group (EMG) – to focus on the questions that, if well answered, have the greatest potential to impact on policies, strategies, and future programming. The Evaluation Team is expected to offer a final set of evaluation questions and tools and include them in the Inception report.

Relevance

- -  Were the programme’s objectives relevant to the needs of the programme beneficiaries, having in mind political, social and institutional context of the country where the programme is implemented?

- -  Was the programme relevant to the SDGs, specifically Goals 1, 3, 4, 5, 8 and 10?

- -  Were coordination, management and financing arrangements clearly defined at the design stage and did these support institutional strengthening and local ownership?

- -  Was the programme successful in adjusting its implementation strategy and approach to the new circumstances imposed by the COVID-19 pandemic?

Effectiveness

- -  To what extent were the programme activities implemented and intended results achieved? What are the main programme accomplishments, with reference to the Results framework but also SDG Fund global goals?

- -  What are the positive or negative, intended or unintended, changes brought about by the programme?

- -  How well did the programme collect and use data to monitor results? How effectively was updated data used to manage the programme?

- -  To what extent has the programme effectively identified, outreached, and engaged target groups, as well as marginalized groups (i.e. youth, persons with disabilities, returnees, internally displaced, ex-Yugoslav refugees, persons at risk of statelessness, minorities...) and supported gender mainstreaming and women’s empowerment?

- -  To what extent complementarity of agency-led activities was achieved?

- -  How effective was the programme’s interaction with other complementary projects/programs (including implemented by the UN) in order to trigger synergies

maximizing development results?

- -  Was the programme well-timed to capitalize on a specific window of opportunity?

Efficiency

- Have resources (financial, human, technical) been allocated strategically to achieve the programme results?

-  Were there any weaknesses in programme design, coordination, management, human resource skills, and resources?

- -  How well did the programme team communicate with implementing partners, stakeholders and programme beneficiaries on its progress? In what aspects and to what extent did the programme contribute to UNCT coherence? To what degree did the political developments in the country, as well as COVID-19 pandemic, influence the programme’s efficiency?

Impact

- -  Has the programme contributed or is likely to contribute to medium or long-term social, economic, or other results, esp. with reference to SDGs 1, 3, 4, 5, 8 and 10 and the relevant NSSD chapters?

- -  What are the main benefits (qualitative and quantitative) for the target groups, including for vulnerable groups? How have cross-cutting issues, such as gender equality, disability, and reaching the most vulnerable, been effectively taken up?

- -  To what extent are key stakeholders/final beneficiaries satisfied with the programme implementation, specifically in terms of the partnership support and what are specific expectations for the potential follow-up assistance?

- -  What are the key lessons to be drawn at this point of the joint programme implementation? What are the main recommendations for the remainder, as well as for future programming?

- -  What is the impact of COVID-19 on the programme implementation and how the limitations imposed by the pandemic were lifted?

Sustainability

- -  To what extent are the programme outputs sustainable? How could the programme results be further sustainably projected and expanded?

- -  To what extent has the programme approach (intervention strategy) managed to create ownership of the key national stakeholders?

- -  At this stage of programme implementation, what could be possible after- programme priority interventions and general recommendations, which could further ensure sustainability and scaling up of programme achievements?

- -  What would be future priority interventions to ensure long-term sustainability of the programme achievements, having in mind the current COVID- 19 related context?

V. Methodology

The Evaluation Team will propose an adjusted evaluative approach/ methodology that will be used to conduct the evaluation effectively in the COVID – 19 pandemics circumstances, including application of safety guidance, extended desk reviews and virtual stakeholder meetings and interviews by evaluators and agree on a detailed plan for the assignment as part of the evaluation Inception Report. The proposed methodology may employ any relevant and appropriate quantitative, qualitative or combined methods to conduct the programme evaluation, exploring specific, gender sensitive data collecting and analytical methods and tools applicable in the concrete case. The Evaluation Team is expected to creatively combine the standard and other evaluation tools and technics to ensure proper triangulation, maximum reliability of data and validity of the evaluation findings.

At a minimum, the evaluation will draw on the following methods:

Literature review and desk review of background documents and other relevant data, including review and analysis of secondary quantitative data;
Key Informant Interviews with the stakeholders and partners;
Review of programme documentation in each site;

Focus Group Discussions with relevant stakeholders at the national and sub-national level; In-depth interviews with local service providers and other relevant institutions/organisations and beneficiaries regarding new and/or improved services resulting from the programme; Cost analysis of the implementation of the joint programme;

Collation of existing statistical data, where available, and quantitative data relevant to the evaluation questions;
Collected data should be disaggregated by age, gender, disability status, legal status (where relevant) and site (where relevant).

Evaluation team and evaluation management

The Activate! Joint Programme will be subjected to a joint final independent evaluation managed jointly by PUNOs1 as per established process for independent evaluations. The evaluations will follow the United Nations Evaluation Group’s (UNEG) Norms and Standards for Evaluation in the UN System, using the guidance on Joint Evaluation and relevant UNDG guidance on evaluations.

From UN side, the Evaluation will be overseen by Evaluation Management group (EMG), consisted of PUNOs implementing the programme (UNICEF, UNDP, ILO, IOM, UNHCR) and UN Resident Coordinator`s Office (RCO). The EMG will be Co-chaired by RCO and UNDP as Evaluation implementor.

The management and implementation of the joint evaluation will have due regard to the evaluation policies of PUNOs to ensure the requirements of those policies are met and the evaluation is conducted with use of appropriate guidance from PUNOs on joint evaluation.

The Final Evaluation will be conducted by the Evaluation Team composed of an International Evaluation Consultant/Team Leader and a National Evaluation Consultant. The International Evaluation Consultant will lead the evaluation process and decide on planning and distribution of the evaluation workload and tasks among the evaluation team. She/he will closely collaborate with the National Evaluation Consultant who will provide support throughout the evaluation process.

The International Evaluation Consultant/Team Leader will be responsible for the overall design and writing of the Final Evaluation Report, preparing the methodology, assessing the collected data, drafting the report and participating in the reviewing and debriefing with the Joint Evaluation Management Group.

The National Consultant will be responsible for compilation of data via desk research and interviews, assist in translation of key information data, assess emerging trends with respect to regulatory framework and overall provide support to the Evaluation Team Leader.

VII. Evaluation deliverables

Under the supervision of the UNDP Programme Manager, and in close cooperation with Joint Evaluation Management Group, the Evaluation Team is expected to deliver the following:

Deliverables:

- Inception Report to be presented before the Final Evaluation starts, showing how evaluation objectives will be met, proposing the final list of evaluation questions and how they will be answered, proposing methods, sources of data and data collection procedures. The Inception Report should be carried out following and based on preliminary discussions with Joint programme team after the desk review and should be produced before the evaluation starts (before any formal evaluation interviews, or field visits). It should also elaborate an evaluation matrix for the programme and propose a schedule of tasks, activities, and evaluation deliverables. The Evaluation Inception Report should follow the structure/guidelines proposed in the UNEG Resource Pack on Joint Evaluations p. 101-105.

- Data collection: Upon the approval of the Inception Report, the Evaluation Team is expected to carry out the programme evaluation, based on the approved methodology. The proposed data collecting methodologies presented in the Evaluation Inception Report should limit the exposure of any consultant, team member, beneficiary or stakeholder to the pandemic.

- Draft Final Evaluation Report: Based on the findings generated through desk review and data collection process, the Evaluation Team will prepare and submit the Draft Evaluation Report to the Evaluation Management Group for review.

- Final Evaluation review: Comments, questions, suggestions and requests for clarification on the evaluation draft will be submitted to the Evaluation Team Leader and addressed in the agreed timeframe.

- Final Evaluation debriefings: will be held with implementing UN Agencies and other key stakeholders to present main findings and recommendations either face-to-face or in a form of an online briefing. In addition, short briefings on immediate findings with Joint Programme Team will be considered after completion of the initial assessment.

- Final Evaluation Report to be submitted to and approved by the Evaluation Management Group includes executive summary, evaluation methodology, analysis and findings, good practices, human stories & lessons learnt and recommendations. It should be logically structured, contain data and evidence-based findings provided by stakeholders and partners, and be presented in a way that makes the information accessible and comprehensible. In addition, based on the evaluation findings and in a distinct report section, the Evaluation Team will provide forward-looking actionable recommendations, outlining key strategic priorities to be addressed in the potential next phase of the programme.2

# Annex 2: Evaluation matrix

The purpose of the evaluation matrix is to provide a clear analytical framework that helps to reduce subjectivity in the evaluative judgement identifying for question: i) Evaluation questions; ii) indicators; iii) data sources; and iv) data collection and analysis methods

| Evaluation Questions |  | Judgement Indicators | Sources of Information |  | Data collection and analysis methods |
| --- | --- | --- | --- | --- | --- |
| RELEVANCE |  |  |  |  |  |
| Q1 | Were the programme’s objectives relevant to the needs of the programme beneficiaries, having in mind political, social and institutional context of the country where the programme is implemented? | - Degree to which the objectives and results of the Joint Programme were aligned with national social sector priorities and frameworks - Objectives and results of the Joint Programme are responsive to observed critical bottlenecks to social protection, the realization of rights and meeting the needs of the vulnerable groups targeted by the programme– in terms of the enabling environment, supply and quality of services and demand factors. - Evidence of application by Joint Programme and individual agencies of equity and gender-based programmatic approach in design and implementation of interventions - Existence of gender- and equity- sensitive framework and reporting within the JP and individual agencies - Perceptions of stakeholders on the relevance of measures included within the Joint Programme with the needs of vulnerable groups | - Programme documentation - National social protection strategies and legislation - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q2 | Was the programme relevant to the SDGs, specifically Goals 1, 3, 4, 5, 8 and 10? | - Degree of relevance and alignment of the Programme with SDGs (specifically Goals 1, 3, 4, 5, 8 and 10) | - Programme documentation - National SDG framework - PUNO’s corporate documents - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q3 | Were coordination, management and financing arrangements clearly defined at the design stage and did these support institutional strengthening and local ownership? | - Extent to which the UN RCO and PUNOs jointly established and utilised clear coordination, management and financing arrangements - Degree of involvement of national / subnational Government in the preparation of the JP - The degree to which the JP arrangements provided for holistic approach to support institutional strengthening and local ownership | - Programme documentation - National social protection strategies and legislation - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q4 | Was the programme successful in adjusting its implementation strategy and approach to the new circumstances imposed by the COVID-19 pandemic? | - Objectives of JP are adapted to the arising needs under COVID-19 (e.g. in terms of adaptation of support intervention in response to arising needs and restrictions relating to COVID-19) based on comprehensive analysis of context and needs in specific areas of interest of the JP - Evidence of the Programme’s adaptability to emerging needs and vulnerabilities of the most marginalised groups (e.g. young women, persons with disability, refugees, migrants, stateless or persons at risk of statelessness, long term unemployed and NEET) resulting from COVID-19 pandemic | - Programme documentation - UN Agencies’ and other national or international studies and reports on impact of COVID-19 in Montenegro - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Coherence |  |  |  |  |  |
| Q 5 | To what extent complementarity of agency-led activities was achieved? | - Degree to which the joint programme approach presented added value to the results of the programme vs. if components were implemented in isolation - Evidence and examples of ways in which each PUNO contributed to the programme implementation by engaging in areas where they have comparative advantage | - Programme documentation - National social protection strategies and legislation - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q6 | How effective was the programme’s interaction with other complementary projects/programs (including implemented by the UN) in order to trigger synergies maximizing development results? | - Evidence of synergies between the JP and other complementary projects/programmes implemented by UN - Examples of areas/opportunities where complementary approaches between JP and UN agencies were/were not exploited and their reasons - Evidence and examples of partnerships that contributed to development results | - Programme documentation - National social protection strategies and legislation - PUNOs’ and other UN studies, reports and other monitoring data - UN RCO documents and reports - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q7 | How well did the programme team communicate with implementing partners, stakeholders and programme beneficiaries on its progress? | - Evidence and examples of communication strategy and practices to inform implementing partners, stakeholders and programme beneficiaries on its progress | - Programme documentation - National social protection strategies and legislation - PUNOs’ and other UN studies, reports and other monitoring data - UN RCO documents and reports - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q8 | In what aspects and to what extent did the programme contribute to UNCT coherence? | - Extent to which the objectives, results and thematic contributions and mandates of the five UN Agencies contribute to the achievement of the Joint programme’s results in terms of addressing the country’s development priorities and challenges | - Programme documentation - National social protection strategies and legislation - PUNOs’ and other UN studies, reports and other monitoring data - UN RCO documents and reports - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document review, KII interviews, group discussions - Document review identifying iterative themes and comparison between JP and national level documentation - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| EFFECTIVENESS |  |  |  |  |  |
| Q9 | To what extent were the programme activities implemented and intended results achieved? What are the main programme accomplishments, with reference to the Results framework? | - Evidence from pre-existing and quantitative data regarding sufficient achievement of intended outputs - Evidence of application by Joint Programme and individual agencies of equity, disability and gender-based programmatic approach in design and implementation of interventions - Degree of change in government capacity to design social policies that are informed by evidence, tested, and tailored to the needs of vulnerable groups and impact-oriented in terms of reducing poverty and dependency on social welfare. - Degree to which the human-centred services for increased participation, empowerment and/or employment of young people in Montenegro are piloted, tested, and rolled out to inform social policies - Degree of change in terms of delivery of effective, tailored-to-needs social protection - Evidence and examples of programme’s concrete results in terms of Gender and women empowerment - Evidence and examples of programme’s engagement with and built capacity of PWD - Stakeholder perceptions regarding programme results as having been achieved and contributing to overall positive change in Montenegro - Degree and type of drivers that promoted programme implementation - Degree and type of hindering factors affecting programme implementation | - Programme documentation - National social protection strategies and legislation - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNos - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews and group discussions - ToC analysis and contribution analysis tracing activities to results. - Qualitative Iterative Data Analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q10 | What are the positive or negative, intended or unintended, changes brought about by the programme? | - Examples of unexpected positive results of the programme. - Examples of unintended negative results. - Evidence of strategies to mitigate potential risks | - Programme documentation and monitoring data - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Group discussions - Document review identifying iterative themes - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q11 | To what extent has the programme effectively identified, outreached, and engaged target groups, as well as marginalized groups (i.e. youth, persons with disabilities, returnees, internally displaced, ex-Yugoslav refugees, persons at risk of statelessness, minorities...) and supported gender mainstreaming and women’s empowerment? | - Evidence that integration of equity principles in targeting and implementation of interventions reaching the most vulnerable persons to food security adds value in terms of outreach, coverage and fulfilment of results - Evidence and examples of measures taken by the programme to identify, outreach, and engage target groups, as well as marginalized groups (i.e. youth, persons with disabilities, returnees, internally displaced, ex-Yugoslav refugees, persons at risk of statelessness, minorities...) - Evidence and examples of supported gender mainstreaming and women’s empowerment - Evidence and examples of integration of issues of disability in JP interventions | - Programme documentation - National social protection strategies and legislation - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews and group discussions - ToC analysis and contribution analysis tracing activities to results. - Qualitative Iterative Data Analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q12 | Was the programme well-timed to capitalize on a specific window of opportunity? | - The degree to which the Programme was strategically positioned to achieve set results - The degree to which the timing of the programme created opportunities to achieve results | - Programme documentation - National social protection strategies and legislation - UNICEF’s, UNDP’s and ILO’s studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews and group discussions - ToC analysis and contribution analysis tracing activities to results. - Qualitative Iterative Data Analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Efficiency |  |  |  |  |  |
| Q 13 | Have resources (financial, human, technical) been allocated strategically to achieve the programme results? | - Degree of adequacy of: - Budgets - Material - Human resources vis- à-vis the volume of tasks carried out - Disbursement rates (expenditure vs. planned) per component and activity, per year - Proportion of JP interventions that demonstrate implementation on schedule and per planned budget - Stakeholder perceptions that the implementation of activities is sufficiently timely, efficient and appropriate to context requirements. | - Programme documentation and monitoring data - PUNOs’ reports and other monitoring data - External sources - Qualitative data from KIIs from - PUNOs - Implementing partners - donor | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Qualitative Iterative Data Analysis Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |  |
| Q 14 | Were there any weaknesses in programme design, coordination, management, human resource skills, and resources? | - The degree to which the programme design, coordination, management, human resource skills, and resources were sound and resilient to weaknesses - The role of UN RCO in ensuring smooth implementation | - Programme documentation and monitoring data - PUNOs’ reports and other monitoring data - External sources - Qualitative data from KIIs from - PUNOs - Implementing partners donor | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Qualitative Iterative Data Analysis Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |  |
| Q 15 | How well did the programme collect and use data to monitor results? How effectively was updated data used to manage the programme? | - Existence of mechanisms for ongoing, periodic collection, documentation, analysis and utilization of gender- and equity- sensitive monitoring data to inform programme adjustment and planning - Existence of system and framework and reporting within the JP and individual agencies | - Programme documentation and monitoring data - PUNOs’ reports and other monitoring data - External sources - Qualitative data from KIIs from - PUNOs - Implementing partners - donor | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Qualitative Iterative Data Analysis Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |  |
| Q16 | To what degree did the political developments in the country, as well as COVID-19 pandemic, influence the programme’s efficiency? | - Evidence of application of efficient procedures to mitigate negative effects of COVID-19 crisis on programme implementation - Evidence of achievement of output level results planned despite the COVID-19 crisis | - Programme documentation and monitoring data - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Document review identifying iterative themes - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Impact |  |  |  |  |  |
|  | Has the programme contributed or is likely to contribute to medium or long-term social, economic, or other results, esp. with reference to SDGs 1, 3, 4, 5, 8 and 10 and the relevant NSSD chapters? | - Stakeholder perceptions regarding programme results as having been achieved and contributing to overall positive change in Montenegro across sectors to leave no one behind. - Evidence and examples where JP’s results contributed to the achievement of UNDAF outcome/s, national development and SDG priorities | - Programme documentation - National social protection strategies and legislation - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - UNRCO - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews and group discussions - ToC analysis and contribution analysis tracing activities to results. - Qualitative Iterative Data Analysis - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Q12 | What are the main benefits (qualitative and quantitative) for the target groups, including for vulnerable groups? How have cross-cutting issues, such as gender equality, disability, and reaching the most vulnerable, been effectively taken up? | - Evidence of (qualitative and quantitative) benefits for the target groups, including for vulnerable groups - Evidence that the JP maintained strong adherence to principles of accessibility, non-discrimination, participation of organizations of persons with disabilities, data disaggregation - Evidence from pre-existing and quantitative data regarding progress towards achievement of intended results in terms of social protection and activation of persons with disabilities | - Programme documentation and monitoring data - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - UN RCO - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Group discussions - Document review identifying iterative themes - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
| Sustainability |  |  |  |  |  |
|  | To what extent are the programme outputs sustainable? | - Evidence of: - Concrete changes in national policies, regulations, and plans that can sustain achieved JP results - Institutional capacity in place to sustain levels of achievement or a strategy/plan exists and funded - Perceptions on sustainability by community and government representatives | - Programme documentation and monitoring data - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - UN RCO - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Group discussions - Document review identifying iterative themes - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |
|  | To what extent has the programme approach (intervention strategy) managed to create ownership of the key national stakeholders? | - The degree of participation of national government stakeholders in the programme design and implementation - Evidence of ownership of key national stakeholders over programme results and readiness to create mechanisms to sustain results | - Programme documentation and monitoring data - PUNOs’ studies, reports and other monitoring data regarding the social protection sector - External sources - Qualitative data from KIIs from - PUNOs - UN RCO - Other UN Agencies - Government stakeholders (national and subnational level) - NGOs - Development partners |  | - Document Review to identify themes among documentation sources for comparison - Semi-Structured Interviews - Group discussions - Document review identifying iterative themes - Qualitative iterative data analysis of the KIIs with key stakeholders - Triangulation between data sources, data collection techniques, and data types according to principles of iterative analysis |

Going forward – lessons learned and recommendations (EQs moved from sustainability)

What are the key lessons to be drawn at this point of the joint programme implementation? What are the main recommendations for the remainder, as well as for future programming?

How could the programme results be further sustainably projected and expanded?

At this stage of programme implementation, what could be possible after- programme priority interventions and general recommendations, which could further ensure sustainability and scaling up of programme achievements?

What would be future priority interventions to ensure long-term sustainability of the programme achievements, having in mind the current COVID- 19 related context?

# Annex 3: Results framework

1. JP contribution to global Fund’s programmatic results

Global Impact: Progress towards SDGs

Select up to 3 SDG indicators that your Joint Programme primarily contributed to (in relation to SDG targets listed in your JP ProDoc)

SDG Goal 1: End poverty in all its forms everywhere.

- 1.2 By 2030, reduce at least by half the proportion of men, women and children of all ages living in poverty in all its dimensions according to national definitions

- 1.3 Implement nationally appropriate social protection systems and measures for all, including floors, and by 2030 achieve substantial coverage of the poor and the vulnerable

SDG Goal 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all

8.6 By 2020, substantially reduce the proportion of youth not in employment, education, or training

Global Outcome 1: Integrated multi-sectoral policies to accelerate SDG achievement implemented with greater scope and scale

| Outcome indicators | Expected 2021 target | 2021 result | Reasons for variance from planned target (if any) | Expected final target |
| --- | --- | --- | --- | --- |
| 1.1: Number of integrated multi-sectoral policies that accelerated SDG progress in terms of scope | 1 | 0 | n/a | 1 |
| List the policies: n/a |  |  |  |  |
| 1.2: Number of integrated multi-sectoral policies that accelerated SDG progress in terms of scale | n/a | n/a | n/a | n/a |

Global Output 3: Integrated policy solutions for accelerating SDG progress implemented

| Output indicators | Expected 2021 target | 2021 result | Reasons for variance from planned target (if any) | Expected final target |
| --- | --- | --- | --- | --- |
| 3.1 Number of innovative solutions that were tested (disaggregated by % successful-unsuccessful) | 3 | 2 | Pilot service for labour activation will be rolled out in 2022, since the activity timeline was extended | 3 |
| 3.2: Number of integrated policy solutions that have been implemented with the national partners in lead | 2 | 1 | Evidence for reforming the poverty-targeted benefit and its means-test could not be obtained due to the need to improve SILC data. Next round of SILC data is expected in December 2022, after which the model can be utilized to provide evidence to the MFSW on the effects of the means-test reform and variables that are correlated to poverty. This would allow means-test reform in 2023. | 3 |
| 3.3: Number and share of countries where national capacities to implement integrated, cross-sectoral SDG accelerators has been strengthened | 1 | 0 | n/a | 1 |

Did your Joint Programme contribute to strengthening of national capacities to implement integrated, cross-sectoral SDG accelerators in 2020-2021?

Yes

No

Explain briefly:

2. Results as per JP Programmatic Results Framework

| Result / Indicators | Baseline | Expected 2021 target | 2021 Result | Reasons for variance from planned target (if any) | Expected final target |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Social policies are informed by evidence, tested, and tailored to needs of vulnerable […] |  |  |  |  |  |
| New policies for social protection/inclusion are informed by the latest poverty data | No | Yes | Yes | One reform scenario (CA) has been informed by poverty data. It is likely that another reform (poverty targeted Family Material Allowance) will be influenced by the scenario in 2022 and 2023. The UN system should strive to further establish ex-ante simulations as standard practice before any social protection reform which related to poverty (in agreement with CODI analysis recommendations) and to enable the MFSW to independently implement policy simulations | Yes |
| Output 1.1 New tool supports analysis of poverty-related data and simulation of policy impact |  |  |  |  |  |
| Availability of a tool to ex-ante simulate policy impact | No | Yes | Yes | n/a | Yes |
| Number of poverty reduction scenarios developed for the consideration of the Government | 0 | 3 | Yes | n/a | 3 |
| Output 2.1. Human-centered, integrated service delivery at community-level, focusing on youth, to increase their participation in education, employment or training, including reintegration assistance, to reduce dependence on social assistance, are rolled-out. |  |  |  |  |  |
| Employment agency applies gender sensitive and innovative services and tools for increased youth participation in the labor market | No | Yes | Yes | n/a | Yes |
| Reduction in the number of NEETs in Montenegro | 28.900 | 28.322 | Data for 2021 is not yet available | n/a | Yes |
| Output 2.1. Human-centered, integrated service delivery at community-level, focusing on youth, to increase their participation in education, employment, or training, including reintegration assistance, to reduce dependence on social assistance, are rolled-out |  |  |  |  |  |
| Number of service providers applying HCD in service (re)design | 0 | 5 (EA local branches) 2 (CSWs) | 9 local, 1 central 9 CSWs | More towns than planned were targeted | 9 local, 1 central 9 CSWs |
| Number of people benefiting from piloted human-centered and integrated services, disaggregated by gender and municipality | 0 | 100, out of which at least 50% women (UNDP) 30, out of which at least 30% women (IOM) | 28 beneficiaries were involved in HCD process | up to 100 beneficiaries are expected to benefit from rolled out pilot service in 2022, since the activity timeline was extended | 130 |
| Number of identified victims of trafficking, disaggregated by gender | 8 | 12, out of which 8 women/girls | 5, out of which 4 women/girls | Delayed start of activity implementation due to COVID-19 | 12, out of which 8 women/girls |
| Number of ex-Yugoslav refugees with unresolved status and stateless persons/persons at risk of statelessness benefiting from assistance in resolving their legal status | 0 | 1,000, out of which is women/girls | 996 | N/A | 1,000 |
| Number of persons reached by the anti-trafficking related awareness campaign, disaggregated by gender | 0 | 300, out of which at least 50% women (IOM) | No | Delays of activity implementation due to COVID-19 | 300, out of which at least 50% women |
| Availability of an assessment of welfare/inactivity traps | No | Yes | No |  | Yes |
| Number of young long-term unemployed transitioned from welfare to work | 0 | 72 young long-term unemployed (at least 35 of which women) | 42 young women employed 9 young women transitioned to work |  |  |
| Number of vulnerable young men and women benefitting from the skills building programme at municipal level | 0 | 1500 | 823 | COVID-19 pandemic related restrictions (movements restrictions and group gathering) | 1500 |
| Number of municipalities where skills building programmes for vulnerable youth are provided | 0 | 8 | 4 |  | 8 |
| Availability of a mobile-based tool for mental health support, targeting vulnerable young men and women | No | Yes | No | n/a | Yes |

# Annex 4: Detailed stakeholder analysis

| Stakeholder | Contact | Contact / email | Main points of engagement in the JP (how/when they were engaged with the project) | Main areas of program me these stakeholders can provide for evaluation | Level of importance of the meeting |
| --- | --- | --- | --- | --- | --- |
| UNHCR, UNICEF, UNDP, ILO, IOM (INTERNAL STAKEHOLDERS) |  |  |  |  |  |
| UN Resident Coordinator | Peter Lundberg | peter.lundberg@un.org | Current Resident Coordinator. Arrived in Montenegro in January 2022. In charge of support overall coordination and monitoring, provide guidance on the implementation of the JP, including liaison with senior government officials. | All areas of the JP work, key information | C |
| ex-UN Resident Coordinator | Fiona McCluney | fiona.mccluney@un.org | UN Resident Coordinator in times of project development. In charge of support overall coordination and monitoring, provide guidance on the implementation of the JP, including liaison with senior government officials. |  | C |
| Head of RCO | Ana Zec | ana.zec@un.org | Head of RCO | The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders and donor. | C |
| ex-Head of RCO, Development Coordination Officer | Miloš Popović | milos.popovic@un.org | RCO Main JP Focal Point |  | C |
| RCO, Communications and Advocacy Officer | Vlatko Otasevic | vlatko.otasevic@un.org | Contact person for Joint Communications |  | C |
| RCO, Human Rights Adviser | Anjet Lanting | anjet.lanting@un.org | Team member in RSIA implementation | Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | D |
| UNDP Resident Representative | Daniela Gasparikova | daniela.gasparikova@undp.org |  | The internal stakeholders and users of the evaluation | D |
| UNDP Assistent Resident Representative and Social Inclusion Team Leader | Miodrag Dragisic | miodrag.dragisic@undp.org | Team member in Outcome 1 | Outcome 1 area of JP work, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| UNDP, Programme Manager | Jelena Miljanic | jelena.miljanic@undp.org | Team member in project monitoring and coordination (Outcome 2) Also focal point for UNDP activities under Outcome 2, HCD-piloting integrated services for activation, digital skills platform pilot, integrated activation analysis, youth strategy activities..Also RSIA implementation | Outcome 2 area of JP work, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| UNDP, Project Coordinator | Milica Scepovic | milica.scepovic@undp.org | Team member in project monitoring and coordination (Outcome 2) | Outcome 2 area of JP work | D |
| UNDP, Programme Manager | Igor Topalovic | igor.topalovic@undp.org | Team member in RSIA implementation, also focal point for undp Activity on persons with disability, short expert opinion on the institutional set up in the area of professional rehabilitation of PWD | Outcome 1 ad 2 area of JP work, key information | C |
| UNDP, Programme Manager | Kaca Djurickovic | kaca.djurickovic@undp.org | Team member in RSIA implementation | Outcome 1 area of JP work | D |
| UNDP, project coordinator | Masa Vucinic | masa.vucinic@undp.org | Team member in RSIA implementation |  | D |
| UNDP, project coordinator | Sanja Zindovic | sanja.zindovic@undp.org | Team member in RSIA implementation |  | D |
| UNICEF Representative | Juan Santander | jsantander@unicef.org |  | The internal stakeholders and users of the evaluation | D |
| ex-UNICEF Representative | Osama Makkawi | omakkawi@unicef.org | UNICEF Representative in times of project development. |  | L |
| UNICEF Deputy Representative | Sabina Žunić | szunic@unicef.org | Lead Agency Main JP Focal Point | Outcome 1 and 2, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| ex-UNICEF Representative | Michaela Bauer | mbauer@unicef.org | UNICEF Deputy in times of project development, and the UNCT focal point for developing the project. |  | D |
| UNICEF JP Activate Coordinator | Slavica Nikolić | snikolic@unicef.org | UNICEF JP Activate Coordinator | JP coordination, Outcome 1, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| ex UNICEF Social Policy Officer and Child Rights Monitoring and Evaluation Specialist | Marija Novković | mnovkovic@unicef.org | UNICEF member of the team in times of project development | JP monitoring and evaluation | D |
| UNICEF Social Policy Officer | Danilo Smolović | dsmolovic@unicef.org | UNICEF team member in project monitoring and coordination |  | C |
| UNICEF Adolescent Development Officer | Nikola Vulić | nvulic@unicef.org | UNICEF member of the team (Outcome 2) | Outcome 2, key information | C |
| UNICEF, Child Protection Officer | Nada Djurovic Martinovic | nmartinovic@unicef.org | Team member in RSIA implementation (Outcome 1) | Outcome 1, key information | D |
| UNHCR Representative | Jean Yves Bouchardy | bouchard@unhcr.org |  | The internal stakeholders and users of the evaluation | D |
| ex-UNHCR Representative | Roberta Montevecchi | montevr@unhcr.org |  |  | L |
| UNHCR, Protection | Ana Rašović | rasovic@unhcr.org | UNHCR team member in project implementation, monitoring and coordination | Outcome 2, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| UNHCR, External Relations Officer | Mensur Bajramspahic | bajramsp@unhcr.org | UNHCR team member in project development, monitoring and coordination |  | C |
| UNHCR, Senior Protection Associate | Slobodan Rascanin | rascanin@unhcr.org | UNHCR team member in project implementation, monitoring and coordination |  | C |
| ILO, National Project Coordinator | Nina Krgovic | krgovic@ilo.org | ILO member of the team in times of project development | Outcome 2, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| ILO, Project Coordinator | Ines Pajovic | pajovic@ilo.org | ILO team member in project monitoring and coordination |  | C |
| IOM Head of Office | Dušica Živković | dzivkovic@iom.int |  | Outcome 2, key information The main internal stakeholders and users of the evaluation; Key informants; facilitate the evaluation team’s contacts with external stakeholders. | C |
| IOM, Project assistant | Ivana Ban | iban@iom.int | IOM team member in project monitoring and coordination |  | C |
| IOM, Project Assistant | Anica Andjelkovic | aandelkovic@iom.int | Team member in RSIA implementation | Outcome 1, key information | D |
| WHO Head of Office | Mina Brajović | brajovicm@who.int |  | The internal stakeholders and users of the evaluation | D |
| Consultant and implementation partners |  |  |  |  |  |
| Consultant for component of UNDP and UNICEF | Franziska Gassman | franziska.gassmann@maastrichtuniversity.nl | Lead Expert -Simulations, Outcome 1 | Outcome 1 - simulations, key information | C |
|  | Francesco Iacoella | iacoella@merit.unu.edu | Expert - Simulations |  | D |
|  | Giulio Bordon | g.bordon@maastrichtuniversity.nl | Expert - Simulations |  | D |
|  | Jelena Žarković | jelena.zarkovic@ekof.bg.ac.rs | Individual International Consultant-Simulations |  | C |
|  | Olivera Komar | olivera@defacto.me | Consultant-RSIA | Outcome 1 – RSIA, key information | C |
| Consultant for component of ILO | Irma Lutovac | irmalutovac@gmail.com | Expert - NEETs | Outcome 2, Profile NEETs information | D |
| Implementation partner of ILO | Zvezdana Oluic, Montenegrin Employers Federation (MEF) | 067 448 890, 067 659 555 | Lead Coordinator - Grant Agreement MEF | Outcome 2, active labour market measure “Activate young women” | C |
| Implementation partner of ILO | Tanja Spicanovic, municipality of Bar | tanja.spicanovic@bar.me | Lead Coordinator - Grant Agreement Municipality Bar | Outcome 2, active labour market measure “Activate young women” | C |
| Implementation partner of UNDP | Anna Molnar, NGO HELP | molnar@help-montenegro.org | NGO HELP is implementing UNDP pilot project for labour activation | Outcome 2, pilot project for labour activation | C |
| Consultant for component of UNDP | Tamara Čirgić | tamara.cirgic@gmail.com | UNDP, consultant for human centred design | Outcome 2, human centred design | D |
| Consultant for component of UNDP | Danka Ćetković | danka.cetkovic@gmail.com | UNDP, consultant for human centred design | Outcome 2, human centred design | C |
| Consultant for component of UNDP | Nevenka Žegarac | nelazegarac@gmail.com | UNDP, consultant for integrated work on labour activation | Outcome 2, integrated work on labour activation | D |
| Consultant for component of UNDP | Vojin Golubović | vgolubovic2004@gmail.com | UNDP, consultant for ethnographic research and integrated work on labour activation | Outcome 2, ethnographic research and integrated work on labour activation | C |
| Consultant for component of UNDP | Dimitrije Jovićević | contact@dimitrije.eu | UNDP, junior consultant for support of development of the new national Youth Strategy | Outcome 2, support of development of the new national Youth Strategy | L |
| Consultant for component of UNDP | Ajša Hadžibegović | ajsa.hadzibegovic@gmail.com | UNDP, senior consultant for support of development of the new national Youth Strategy | Outcome 2, support of development of the new national Youth Strategy | D |
| Consultant for component of UNDP | Amir Sarajlić | amir.vet.bosnia@gmail.com | UNDP, international consultant to support development of applicable model of students employment in Montenegro | Outcome 2, support development of applicable model of students employment | L |
| Consultant for component of UNDP | Dmitri Belan | belan87@gmail.com | UNDP, international consultant to support application of human-centred design (HCD) methodology in programme and service design | Outcome 2, human centred design methodology | D |
| Implementation partner of UNHCR | Jelena Ristović, Civic Alliance, Project Coordinator | jelena@gamn.org | Support regularization of legal status and social inclusion of statelessness and persons from the former Yugoslavia | Outcome 2, Support regularization of legal status and social inclusion of statelessness and persons from the former | C |
| Implementation partner of UNICEF | Marijana Blečić, NGO Pedagogical Center | marijanab@ucg.ac.me | Implementing partner for social-emotional skills development | Outcome 2, social-emotional skills development | C |
| Implementation partner of UNICEF | Peko Vukadinović, Association of Scouts | peko@scouts.org.me | Implementing partner for mental health activities | Outcome 2, mental health activities | C |
| Implementation partner of IOM | Jelena Milic, NGO "Defendologija" | jelenamilic.defendologijamne@gmail.com | Conducting counter-trafficking awareness-raising campaign | Outcome 2, Counter-trafficking awareness-raising campaign | C |
| KEY NATIONAL STAKEHOLDERS |  |  |  |  |  |
| Ex Ministry of Finance and Social Welfare | Biljana Vucetic, coordinator of directorate | biljana.vucetic@mif.gov.me | Government Joint Programme Focal Point (Outcome 1 and 2) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ex Ministry of Finance and Social Welfare | Ida Kolinovic, Advisor | ida.kolinovic@mif.gov.me | Outcome 1, policy simulations and modelling for poverty reduction (UNDP and UNICEF) |  | D |
| Ex Ministry of Finance and Social Welfare | Andjela Bulatovic, Advisor | andjela.bulatovic@mif.gov.me | Outcome 1. Participation in the workshops related to simulations, policy simulations and modelling for poverty reduction (UNDP and UNICEF) | Stakeholder’s views on the key results of the programmes | D |
|  | Tamara Ivkovic, Advisor | tamara.ivkovic@mif.gov.me |  |  | D |
| Ex Ministry of Finance and Social Welfare | Janko Odovic, State Secretary | janko.odovic@mif.gov.me | Outcome 1, policy simulations and modelling for poverty reduction (UNDP and UNICEF) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans | C |
| Ministry of Labour and Social Welfare, ex Ministry of Finance and Social Welfare | Jelena Raicevic, Advisor | jelena.raicevic@mif.gov.me, | Outcome 1, policy simulations and modelling for poverty reduction (UNDP and UNICEF) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ministry of Labour and Social Welfare, ex Ministry of Finance and Social Welfare | Marija Stajović, Ex director of directorate for social protection | ruzic.marija85@gmail.com | Outcome 2. integrated labour activation, HCD, now mentor on the pilot project implemented by Help (UNDP consultant) Outcome 1. RSIA implementation, contacts for CSWs (UNDP and UNICEF) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ministry of Labour and Social Welfare, ex Ministry of Finance and Social Welfare | Milica Vujović | milica.vujovic@mif.gov.me | Contact person for Activate, integrated labour activation, HCD and HELP project, also integrated labour activation analysis (UNDP) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | D |
| Ministry of Labour and Social Welfare, ex Ministry of Economic Development | Edina Desic | edina.desic@mrs.gov.me | Outcome 2. Activate young women, Youth Guarantee Scheme (ILO) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ministry of Labour and Social Welfare, ex Ministry of Economic Development | Jevrosima Pejovic | jevrosima.pejovic@mek.gov.me | Outcome 2. Director General for Labor and Employment, integrated labour activation, HCD and HELP project, also digital skills platform focal point (UNDP) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ministry of Interior | Miroslav Zeković | miroslav.zekovic@mup.gov.me | Outcome 2. Related to support to stateless and persons from the former Yugoslavia (ILO) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ministry of Interior | Milanka Baković | milanka.bakovic@mup.gov.me | Outcome 2. Related to support to stateless and persons from the former Yugoslavia (ILO) |  | C |
| Ministry of Interior, Department for Combating Trafficking in Human Beings | Tijana Sukovic | tijana.sukovic@mup.gov.me | Outcome 2. identification, protection, assistance and reintegration of victims of trafficking (IOM) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Ministry of Interior, Directorate for Administrative Affairs, Citizenship and Foreigners | Mirela Skenderovic | mirela.skenderovic@mup.gov.me | Outcome 2. identification, protection, assistance and reintegration of victims of trafficking (IOM) |  | D |
|  | Dragica Vucinic | d.vucinic@mup.gov.me |  |  | D |
| Ex ministry of eduction, culture, science and sports | Krsto Vukadinovic | krsto.vukadinovic@mpnks.gov.me | Outcome 2. youth strategy design process and youth benefits card programme development (UNDP) | The success of the project in influencing ministries and government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans Programmed outputs, both in quantity and quality, as well as their usefulness and timeliness | C |
| Employment Agency of Montenegro | Dragica Rustemagic | dragica.rustemagic@zzzcg.me | Outcome 2. active labour market measure “Activate women’ (ILO) | The degree to which the project was accessible to decision makers and other relevant interest groups, and what effect has this had on the project intervention areas. The success of the project in influencing government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans | C |
|  | Sanja Rabrenovic | sanja.rabrenovic@zzzcg.me |  |  | C |
|  | Milutin Vucinic | milutin.vucinic@zzzcg.me |  |  | C |
| Employment Agency of Montenegro | Ljiljana Nisavic | ljiljana.nisavic@zzzcg.me | Outcome 2. contact person for Activate, integrated labour activation, HCD and HELP project (UNDP) | The degree to which the project was accessible to decision makers and other relevant interest groups, and what effect has this had on the project intervention areas. The success of the project in influencing government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans | C |
| MONSTAT | Miroslav Pejovic, director | miroslav.pejovic@monstat.org | Outcome 1, improvement of SILC data (UNDP and UNICEF) | The degree to which the project was accessible to decision makers and other relevant interest groups, and what effect has this had on the project intervention areas. The success of the project in influencing government agencies Effectiveness of implementation, sustainability over time and monitoring of policies and plans | D |
|  | Snezana Remikovic, assistant director, Social Statistics and Demography Sector | snezana.remikovic@monstat.org |  |  | C |
|  | Milena Vukotic, head of the Department for Living and Social Services Statistics | milena.vukotic@monstat.org |  |  | C |
| Centre for Social Work |  |  | Outcomes related to work of UNDP, UNHCR, and IOM | Stakeholder’s views on the key results of the programmes | D |
| - Final beneficiaries |  |  | Outcomes related to Outcomes 2 work of ILO (women), UNHCR (stateless and person from ex-YU), UNDP (beneficiaries of pilot service), UNICEF (beneficiaries of social-emotional skills programmes), IOM (participants of workshops). | Stakeholder’s views on the key results of the programmes | D |

# Annex 5: Interview guides

The following text shall serve as basis for interviews and discussions with Key informants

We are an evaluation team commissioned to carry out a summative evaluation of the Joint programme Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro. The evaluation offers the opportunity to critically assess the joint programme contribution to social protection sector reforms and provision of more equitable and quality services in the country. The findings of the evaluation will be used as a basis for discussions, planning and programming between UN, Government of Montenegro and other key national and international stakeholders.

We are asking you to participate in the evaluation because you are in a position to contribute a relevant and valuable perspective on the functioning of this program. If you decide to participate, you will be interviewed by members of the evaluation team for a duration of approximately 1 hour.

Participation is voluntary: Your participation in the interview is voluntary. You can withdraw from the interview after it has begun, for any reason, with no penalty. Participating or not in the interview will not affect the benefits to the organizations or communities from the Joint Programme.

Risks and benefits: This review is designed to help improve the program by learning from the perspectives of everyone involved. You may not benefit personally from being in this research review. There may be uncommon or previously unknown risks. You should report any problems to [_________________________].

Confidentiality: The reports from this and the other meetings will collect and summarize the views and opinions of participants without connecting them to specific individuals and without using names at any time. Any report of this research will be presented in a way that makes it as difficult as possible for anyone to determine the identity of individuals participating in the evaluation.

If you have any questions, now or at any time in the future, you may call _________________

Are you willing to be part of this discussion? (verbal response only requested)

Respondent: ________________________________________

Title and Function: ____________________________________

Interviewer Name: ____________________________________

Date: _____________________________________________

Location: ___________________________________________

KII- Interview Guide PUNO Representatives

| Evaluation Questions and Sub-Questions | Interview Questions |
| --- | --- |
| 0.0 GENERAL Questions - What have been the most noted results, successes, challenges, and comparative advantage of JP |  |
| 0.1 Role and Connection | - What is your current position and in what ways have you interacted with the JP? - How long have you been connected to JP? |
| 0.2 Results | - Thinking back to when JP began implementation, what changes have you seen in the system as a result of JP support? |
| 0.3 Strengths and weaknesses | - What do you see JP as being particularly good at in this intervention? - What do you see JP as being particularly weak at in this intervention? |
| 1.0 RELEVANCE and COHERENCE |  |
| - To what extent the objectives and results of the JP were aligned with the national social sector priorities and frameworks? - Has this remained appropriate through any changes in context? - What actions have you seen JP take to ensure that its strategic positioning remains fit for purpose? - To what extent is JPs strategic positioning in line with Montenegro Institutions’ priorities? - In your experience, what do you see as JPs primary comparative advantage for supporting the mix of stakeholders in Montenegro? |  |
| - To what extent the objectives, results and thematic contributions and mandates of the participating UN Agencies contribute to the achievement of the Joint programme’s results? - How aligned were the three organization in terms of addressing the country’s development priorities and challenges? - Were their implementation strategies relevant to the context in Montenegro? If not, why were they not relevant? - Which implementation strategies supported by JP do you see as having been the most useful? |  |
| - Were the objectives of JP adapted to the arising needs under COVID-19? - What adjustments were needed to be made to JP to keep it relevant to the changing needs of its target population? |  |
| - How did JP ensure coherence and synergies across components? |  |
| - To what extent did PUNOs actively participate and promote coordination mechanisms with government, development partners and other UN agencies to avoid overlaps, leverage contributions and catalyse joint work? - Have you encountered any overlaps? Do you have an example of successful synergies? |  |

2.0 EFFECTIVENESS

- What were the key programme results achieved under the programme priorities? - How did JP contribute to the design of an integrated social protection entity/mechanism? - What were the driving factors that promoted programme implementation? What were the hindering factors affecting programme implementation?

- How have Gender or equity issues been integrated into the implementation of the programme models? What could be done to better integrate these issues?

- To what extent did the programme effectively contribute to accelerating the SDGs at the national level? What is missing?

- To what extent do you assess programme results as having been achieved and contributing to overall positive change in Montenegro across sectors to leave no one behind? - To what extent did the programme effectively produce a catalytic effect in terms of generating systems change across sectors to leave no one behind? What is missing?

- To what extent were the planned output level results achieved despite the COVID-19 crisis and political/government changes?

- What have been some important unintended consequences from JP programming? - If there were any unintended negative outcomes, which were the three most important ones? How were they handled? - If there were any unintended positive outcomes, which were the three most important ones? How were they handled? - What do you see as some of the key internal factors that promoted or inhibited achieving the programme outputs? (in the respective priority areas)? - What do you see as some of the key external factors that promoted or inhibited achieving the programme outputs (in the respective priority areas?

3.0 EFFICIENCY

- Were the available financial, material and human resources adequate to meet the set objectives, including in times of the pandemic? - To what extent were planned activities and outputs delivered within the intended timeframe? - To what extent were planned activities and outputs efficient and appropriate to context requirements? - Are there particular types of planned activities that have struggled with timeliness or efficiency more than others? Which ones?

- SUSTAINABILITY

- What was the envisioned sustainability in the short and in the long term? What can promote sustainability in the short and in the long term? - What were some of the concrete changes in national policies, regulations, and plans that can sustain achieved JP results? Are there any concrete plans to scale up the interventions? - Can you offer any examples of change in Government’s allocations of national budget and/or other donor resources towards better supply of services? - Can you offer any examples of change in Institutional capacity in place to sustain levels of achievement or a strategy/plan exists and funded? - What is the progress towards ensuring the LNOB principle and enhancing the social protection system?

- What are some of the comparative evidences of change in Government’s Legislative and policy framework in the social sector prior and post programme implementation? - To what extent did the JP has facilitated participatory and inclusive programme and national planning processes? - How likely will the results be sustained beyond the JP through the action of Government and other stakeholders and/or UNCTs?

- IMPACT

- How have vulnerable groups, including women, children and persons with disabilities benefited (directly and indirectly) from the JP? - To what extend have the intended outcomes and overall goals of the Programme contributed to the changes in terms of achievement of integrated and sustainable social protection system? - To what extend have the intended outcomes and overall goals of the Programme contributed to the capacity of the government to improve social protection coverage for all citizens, in particular the most vulnerable, across Montenegro?

- To what extent, JP design, implementation, and monitoring have been inclusive of persons with disabilities (i.e. accessibility, non-discrimination, participation of organizations of persons with disabilities, data disaggregation)?

KII- Interview Guide- government institutions and civil society at central level

| Evaluation Questions and Sub-Questions | Interview Questions |
| --- | --- |
| 0.0 GENERAL Questions - What have been the most noted results, successes, challenges, and comparative advantage of JP |  |
| 0.1 Role and Connection | - What is your current position and in what ways have you interacted with the JP? - How long have you been connected to JP? |
| 0.2 Results | - Thinking back to when JP began implementation, what changes have you seen in the system as a result of JP support? |
| 0.3 Strengths and weaknesses | - What do you see JP as being particularly good at in this intervention? - What do you see JP as being particularly weak at in this intervention? |
| 1.0 RELEVANCE and COHERENCE |  |
| - To what extent the objectives and results of the JP were aligned with the national social sector priorities and frameworks? - Has this remained appropriate through any changes in context? - In your experience, what do you see as JPs primary comparative advantage for supporting the mix of stakeholders in Montenegro? |  |
| - To what extent the objectives, results and thematic contributions and mandates of the participating UN Agencies contribute to the achievement of the Joint programme’s results? - How aligned were the three organization in terms of addressing the country’s development priorities and challenges? |  |
| - Were the objectives of JP adapted to the arising needs under COVID-19 and political changes? - What adjustments were needed to be made to JP to keep it relevant to the changing needs of its target population? |  |
| - How did JP ensure coherence and synergies across components? |  |
| - To what extent did PUNOs actively participate and promote coordination mechanisms with government, development partners and other UN agencies to avoid overlaps, leverage contributions and catalyse joint work? - Have you encountered any overlaps? Do you have an example of successful synergies? |  |

2.0 EFFECTIVENESS

- What were the key programme results achieved under the programme priorities? - How did JP contribute to the design of an integrated social protection? - What were the driving factors that promoted programme implementation? What were the hindering factors affecting programme implementation?

- How have Gender or equity issues been integrated into the implementation of the programme models? What could be done to better integrate these issues?

- To what extent did the programme effectively contribute to accelerating the SDGs at the national level? What is missing?

- To what extent do you assess programme results as having been achieved and contributing to overall positive change in Montenegro across sectors to leave no one behind? - To what extent did the programme effectively produce a catalytic effect in terms of generating systems change across sectors to leave no one behind? What is missing?

- To what extent were the planned output level results achieved despite the COVID-19 crisis and political/government changes?

- What have been some important unintended consequences from JP programming?

3.0 EFFICIENCY

- Were the available financial, material and human resources adequate to meet the set objectives, including in times of the pandemic? - To what extent were planned activities and outputs delivered within the intended timeframe? - To what extent were planned activities and outputs efficient and appropriate to context requirements?

- SUSTAINABILITY

- What was the envisioned sustainability in the short and in the long term? What can promote sustainability in the short and in the long term? - What were some of the concrete changes in national policies, regulations, and plans that can sustain achieved JP results? Are there any concrete plans to scale up the interventions? - Can you offer any examples of change in Government’s allocations of national budget and/or other donor resources towards better supply of services? - Can you offer any examples of change in Institutional capacity in place to sustain levels of achievement or a strategy/plan exists and funded? - What is the progress towards ensuring the LNOB principle and enhancing the social protection system?

- What are some of the comparative evidences of change in Government’s Legislative and policy framework in the social sector prior and post programme implementation? - To what extent did the JP has facilitated participatory and inclusive programme and national planning processes? - How likely will the results be sustained beyond the JP through the action of Government and other stakeholders and/or UNCTs?

- IMPACT

- How have vulnerable groups, including women, children and persons with disabilities benefited (directly and indirectly) from the JP? - To what extend have the intended outcomes and overall goals of the Programme contributed to the changes in terms of achievement of integrated and sustainable social protection system? - To what extend have the intended outcomes and overall goals of the Programme contributed to the capacity of the government to improve social protection coverage for all citizens, in particular the most vulnerable, across Montenegro?

- To what extent, JP design, implementation, and monitoring have been inclusive of persons with disabilities (i.e. accessibility, non-discrimination, participation of organizations of persons with disabilities, data disaggregation)?

KII- Interview Guide Institution/Civil Society Representatives- Local Level

| Evaluation Questions and Sub-Questions | Interview Questions |
| --- | --- |
| 0.0 GENERAL Questions - What have been the most noted results, successes, challenges, and comparative advantage of JP |  |
| 0.1 Role and Connection | - What is your current position and in what ways have you interacted with the JP? - How long have you been connected to JP? |
| 0.2 Results | - Thinking back to when JP began implementation, what changes have you seen in the system as a result of JP support? |
| 0.3 Strengths and weaknesses | - What do you see JP as being particularly good at in this intervention? - What do you see JP as being particularly weak at in this intervention? |
| 1.0 RELEVANCE |  |
| - To what extent the objectives and results of the JP were aligned with the national and local social sector priorities and frameworks? - Has this remained appropriate through any changes in context? - To what extent is JPs strategic positioning in line with Montenegro’s Institutions’ priorities? - Did the programme respond to your institutions’/ beneficiaries’ needs? What was missing? |  |
| - To what extent the objectives, results and thematic contributions and mandates of UN Agencies contribute to the achievement of the Joint programme’s results? |  |
| - Were the objectives of JP adapted to the arising needs under COVID-19? What adjustments were needed to be made to JP to keep it relevant to the changing needs of its target population? |  |
| 2.0 EFFECTIVENESS |  |
| - To what extent were the planned programme results achieved? Which factors promoted implementation? Were there factors hindering implementation? - How did JP contribute to the design of an integrated social protection/ALMM/process for legal status for migrants/refuges/stateless persons or those at risk? |  |
| - How have Gender or equity issues been integrated into the implementation of the programme models? What could be done to better integrate these issues? |  |
| - To what extent do you assess programme results as having been achieved and contributing to overall positive change in Montenegro across sectors to leave no one behind? |  |
| - To what extent were the planned output level results [note to interviewer: mention which ones] achieved despite the COVID-19 crisis? |  |
| 3.0 EFFICIENCY |  |
| - In your opinion, did PUNOs implement efficiently the activities in which you engaged in terms of time management, accuracy, quality? What was missing? |  |
| - SUSTAINABILITY |  |
| - What was the envisioned sustainability in the short and in the long term? What can promote sustainability in the short and in the long term? - What were some of the concrete changes in national policies, regulations, and plans that can sustain achieved JP results? Are there any concrete plans to scale up the interventions? |  |
| - IMPACT |  |
| - How have vulnerable groups, including women, children and persons with disabilities benefited (directly and indirectly) from the JP? - To what extend have the intended outcomes and overall goals of the Programme contributed to the changes in terms of achievement of integrated and sustainable social protection system? - To what extend have the intended outcomes and overall goals of the Programme contributed to the capacity of the government to improve social protection coverage for all citizens, in particular the most vulnerable, across Montenegro |  |
| - What are some examples of main results achieved by the JP and most salient success stories? - Why were these activities successful/what were the enabling factors? |  |
| - SYNERGIES |  |
| - Have you encountered any projects implemented by other donors/partners on the same subject? Do you have an example of successful synergies? |  |

# Annex 6: Informed Consent Forms

Informed Verbal Consent Form (KIIs)

Title: Evaluation of the Joint Programme Activate! Integrated Social Protection and Employment to Accelerate Progress for Young People in Montenegro

Before agreeing to participate in this evaluation, it is important that you read the following explanation. This statement describes the purpose, procedures, risks, discomforts, and precautions of the program. Also described are the alternative procedures available to you, as well as your right to withdraw from the study at any time. No guarantees or assurances can be made as to the result of the evaluation.

Explanation of Procedures: The purpose of this meeting is to explore your experiences with and views about implementation of the Joint Programme “Activate!”, main results, hindering factors and drivers and your opinions about the opportunities ahead of PUNOs in the next cycle. Participation in this evaluation involves a series of questions and asking for your responses. Your contribution is very important to identify the achievements and challenges, draw lessons and structure forward looking recommendations. Our discussion today will take app. 45 minutes.

Risks and Discomforts: The decision to participate in this study is entirely up to you, and you have the right to refuse to take part in the study at any time without affecting your relationship with the ET or UN Agencies. There are no risks or discomforts that are anticipated from your participation in this evaluation. However, you have every right to not to answer any type of questions that might cause discomfort.

Confidentiality and use of data collected through the interview: The information gathered during this study will remain confidential. The notes collected by the evaluation team contain only the name of the institution and not your name. This means that your personal information will not be included in any written form, so it will not be available to anyone. The notes that we are taking will be used only internally for the purpose of our analysis only and will be strictly confidential and not to be shared with any person outside of the evaluation team. The written version of interviews will be destroyed at the completion of the evaluation. Data compiled in reporting will be aggregated so that individual responses cannot be traced to specific locations or individuals.

Withdrawal without Prejudice: Participation in this study is voluntary; refusal to participate will involve no penalty. Each participant is free to withdraw consent and discontinue participation in this interview at any time without prejudice from the evaluation team

Payment: You will not be compensated in any way for participation in this study.

Agreement: This agreement states that you have received a copy of this informed consent and that you have agreed verbally to participate in the interview.

Please, contact MS Slavica Nikolic on snikolic@unicef.org for any further details with regards to this Evaluation.

# Annex 7: Bibliography

Background:

- China – CEE Institute, Montenegro economy briefing: Economic Outlook 2022 (https://china-cee.eu/2022/02/28/montenegro-economy-briefing-economic-outlook-2022/)

- Demography, Labour Market Statistics and Survey on Income and Living Conditions (SILC) 2019 published by MONSTAT (www.monstat.org)

- EC Montenegro 2021 report

- EC Montenegro 2020 report

- EC website (https://ec.europa.eu/neighbourhood-enlargement/enlargement-policy/negotiations-status/montenegro_en)

European Western Balkans portal

- (https://europeanwesternbalkans.com/2022/04/28/new-government-of-montenegro-elected-by-the-assembly/)

- Eurostat, Young people neither in employment nor in education and training (NEET), https://appsso.eurostat.ec.europa.eu/nui/show.do?dataset=lfsi_neet_a&lang=en

- Government of Montenegro, Information on Youth Employment Programme in Montenegro for 2022 (https://wapi.gov.me/download-preview/8def027b-cd7b-441f-81c5-7ac720c4bfd8?version=1.0)

- https://www.covidodgovor.me/

- NATO website (https://www.nato.int/cps/en/natohq/news_144647.htm)

- National Strategy for Sustainable Development (NSSD) of Montenegro

Roadmap of Social Protection Reforms

Roma inclusion strategy for 2021-2025

- Statistical data on average age population, urbanization from www.statistica.com

Strategy for Combatting Trafficking in Human Beings 2019-2024

Strategy for Integration of Persons with Disabilities in Montenegro for the period 2016-2020

Strategy for the Development of the Social and Child Protection System for the period from 2018 to 2022,

Strategy for the Realization of Child Rights (2019-2023)

Strategy on Migration and Reintegration of Returnees in Montenegro for 2021-2025

The UN Socio-economic response plan to COVID-19 in Montenegro

- UNDP, Global Human Development Indicators 2020, http://hdr.undp.org/en/countries/, https://hdr.undp.org/sites/default/files/Country-Profiles/MNE.pdf

Western Balkans Declaration on ensuring sustainable labour market integration of young people

World Bank, World Bank Open Data (database), https://data.worldbank.org

Youth Strategy 2017-2021

UN Joint Programme related documents

- UN Joint Programme Document

- Terms of Reference for Evaluation of Activate! Joint Programme

- Joint Programme 2021 Annual Progress Report

- Joint Programme 2020 Annual Progress Report

- LNOB portfolio questionnaire 2020-21, quarterly checks

- Rapid Social Impact assessment of the COVID-19 Outbreak in Montenegro (September 2020)

- Rapid Social Impact Assessment of the COVID-19 outbreak in Montenegro (April–June 2020)

- International institutional consultancy to provide technical expertise to develop policy simulation tools for redistributive social policy scenarios in Montenegro, draft report

- JP Concept Notes and ToRs for different activities

- JP various policy and legal analysis related to labour market in Montenegro, draft versions

- JP Presentations

https://www.monstat.org/userfiles/file/demografija/procjene%20stanovnistva/2019/n/Estimation%20of%20population%20and%20basic%20demographic%20indicators%20(1).pdf

https://www.statista.com/statistics/528765/average-age-of-the-population-in-montenegro/

http://monstat.org/eng/novosti.php?id=3504

https://www.statista.com/statistics/528718/urbanization-in-montenegro/

https://ec.europa.eu/neighbourhood-enlargement/enlargement-policy/negotiations-status/montenegro_en

https://www.nato.int/cps/en/natohq/news_144647.htm

EC Montenegro 2020 report, EC Montenegro 2021 report.

https://europeanwesternbalkans.com/2022/04/28/new-government-of-montenegro-elected-by-the-assembly/

EC Montenegro 2021 report, https://ec.europa.eu/neighbourhood-enlargement/system/files/2021-10/Montenegro%202021%20report.PDF

World Bank, World Bank Open Data (database), https://data.worldbank.org

EC Montenegro 2021 report

EC Montenegro 2021 report

https://webgate.ec.europa.eu/isdb_results/factsheets/country/overview_montenegro_en.pdf

EC Montenegro 2021 report

https://china-cee.eu/2022/02/28/montenegro-economy-briefing-economic-outlook-2022/

UNDP, Global Human Development Indicators 2020, http://hdr.undp.org/en/countries/

https://hdr.undp.org/sites/default/files/Country-Profiles/MNE.pdf

MONSTAT. Labour Force Survey 2019, 2020, 2021, https://monstat.org/cg/page.php?id=660&pageid=22

https://wapi.gov.me/download-preview/8def027b-cd7b-441f-81c5-7ac720c4bfd8?version=1.0

Eurostat, Young people neither in employment nor in education and training (NEET), https://appsso.eurostat.ec.europa.eu/nui/show.do?dataset=lfsi_neet_a&lang=en

RELEASE_Survey_on_Income_and_Living_Conditions_EU-SILC_2020.pdf (monstat.org)

http://www.monstat.org/uploads/files/espross/2019/Saopstenje%20ESSPROS-%202019-%20eng.pdf

https://ec.europa.eu/eurostat/databrowser/view/gov_10a_exp/default/table?lang=en

http://www.monstat.org/uploads/files/espross/2019/Saopstenje%20ESSPROS-%202019-%20eng.pdf

EC Montenegro 2021 report, page 87.

https://www.covidodgovor.me/me/statistika

https://www.covidodgovor.me/

The UN Socio-economic response plan to COVID-19 in Montenegro

This section is based on Joint Programme Document and Terms of Reference

Joint Programme Document, page 1

Joint Programme Document, page 35

Based on ToR

Based on Joint Programme 2021 Annual Progress Report and initial interviews.

Source: UN

Based on Joint Programme 2021 Annual Progress Report and initial interviews.

The DAC evaluation criteria of relevance, effectiveness, efficiency, impact and sustainability were first outlined in 1991 under the OECD, and they are currently under revision. Please refer to OECD 2019.

Patton, Michael Quinn. 2010. Qualitative Research and Evaluation. Sage Publication. San Francisco, California.

See ALNAP. Evaluation of Humanitarian Action: Pilot Guide, ODI, 2013:140 for definitions of each type of triangulation.

Presented results are as of 31 December 2021, Annex 1: Consolidated Annual Results of Final Annual Progress report for 2021, page 16-19

Scope=substantive expansion: additional thematic areas/components added or mechanisms/systems replicated.

Scale=geographical expansion: local solutions adopted at the regional and national level or a national solution adopted in one or more countries.

C - Critical/D - Desirable/L - Less priority

Not all questions can be asked in all interviews. Different sections will need to be prioritized from different stakeholders. Blue coded questions should be prioritized in any section

Not all questions can be asked in all interviews. Different sections will need to be prioritized from different stakeholders. Blue coded questions should be prioritized in any section

Not all questions can be asked in all interviews. Different sections will need to be prioritized from different stakeholders. Blue coded questions should be prioritized in any section