Evaluation Title: Real-Time Assessment of UNICEF’s support to the COVID-19 vaccine rollout and immunization programme strengthening in the Latin America and the Caribbean region

Region: Latin America and Caribbean (LACRO)

Office: LACRO

Evaluation Year: 2022

Person-In-Charge for Follow-up to Management Response: Gary Conille (LACRO RD)

Overall Response to the Evaluation: The RTA is meeting its objectives helping to inform UNICEF’s ongoing support to the roll out of COVID-19 vaccinations and identify ways to strategically position UNICEF in routine immunization and the health sector. More specifically the RTA informs a forward-looking reflection for UNICEF LACRO on the following issues:

    - The current implementation of UNICEF LACRO and CO’s support to the COVID-19 vaccine rollout

    - Achievements in the rollout of COVID-19 vaccines.

    - The repositioning of UNICEF in overall immunization programme strengthening.

    - Strategic, programmatic, and advocacy actions for UNICEF to strengthen its role in routine immunization.

The RTA assessed the planning, coordination, and delivery of activities across different technical areas including health, communications, communications for development (C4D), supply, and technology for development (T4D), while also providing early insights on the outputs and outcomes achieved

Furthermore, the RTA synthesis report was based on 3 country cases studies and 4 desk reviews. Findings and recommendations resulted from a participatory process. The initial recommendations and actions identified below in this management response were validated during a regional validation workshop (November 2022), involving staff from the CO and LACRO at the end of November 2022. During this workshop participants validated, adjusted and refined these recommendations, prioritizing each action, identifying the timeline and allocating responsibilities for implementation. As such he RTA/Evaluation Response Plan is oriented to respond to six Recommendations arising from the RTA/evaluation process:

R1: Develop a regional strategy and action plan to strengthen regular immunization systems and services in the context of PHC in LAC countries, including a resource mobilization plan and timeframe.

R2: Strengthen its regional capacity for cold chain procurement and management.

R3: Strengthen its own communication and advocacy efforts to support COs’ ability to execute effective advocacy for more equitable PHC services ensuring that marginalized/minority groups are specifically targeted.

R4: Support COs in assessing the relevance and feasibility of scaling up technological innovations for PHC and regular immunization services.

R5: Strengthen its regional collaboration and coordination with PAHO’s HQ in support of PHC and regular immunization services.

R6: Increase its technical support to COs for strengthening existing PHC and regular immunization services, with an emphasis on countries with large numbers of zero-dose children, and/or inadequate coverage of childhood vaccination.

Planned Use of the RTA: The RTA Covax response helps LACRO together with 3 CO draw lessons learned. The RTA includes the following purposes.

To assess UNICEF’s support in the roll out of COVID-19 vaccines in the selected seven countries, including its potential contribution to the overall routine immunization programmes and PHC.

To use a forward-looking reflection on the implementation of the response to the roll out of COVID-19 at both national and regional levels.

To feed into and will contribute to develop a regional strategy to strengthen regular immunization systems and services in the context of PHC

In addition to the final report, two additional communication products were produced: an evaluation brief and a policy brief. The policy brief will be a living document that will be used and discussed in different network meetings and with governments and donors.

The three RTA case studies (Bolivia, Guatemala and Paraguay) count on their own management response based on their specific Country reports, recommendations, evaluation briefs and policy briefs.

UNICEF Evaluation Management Response

| Allowed Editors: Maaike Arts, Ralph Midy, Ivana Camacho and Carlos Rodriguez-Ariza, |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RECOMMENDATIONS and ACTIONS: |  |  |  |  |  |  |  |
| Evaluation Recommendation 1: Develop a regional strategy and action plan to strengthen regular immunization systems and services in the context of PHC in LAC countries, including a resource mobilization plan and timeframe. |  |  |  |  |  |  |  |
| Management Response: (Agree, Partially Agree, Disagree): Agree |  |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| - 1.1. Develop regional strategy to strengthen regular immunization systems and services in the context of PHC, with inputs from COs, and including the following key aspects: - Planning based on national contexts, including catch up activities and strengthening systems - Integration COVID-19 and routine immunization - Zero-dose children and targeting of groups most left behind - Governance - Human resources - Supplies (cold chain, other where relevant) - SBC/RCCE - Gender aspects - Others (Advocacy for PHC services investment, innovations to accelerate strengthening children routine immunization services, building health systems resilience based on KM/PHC best practices...) | LACRO Survive & Thrive (through consultant) | Ralph Midy (Immunisation regional adviser) | Priority: High Timeframe: 6-12 months | Underway | On going |  |
| - 1.2. Develop a regional resource mobilization plan for the implementation of the strategy (also based on the UNICEF added value and the proof of concept from the RTA) | LACRO PPD & PFP | Mark Connolly & Javier Martos LACRO PPD & PFP advisors | Priority: High Timeframe: 7-months | Underway |  |  |
| - 1.3. Set up an operational plan and timeframe for the launching and implementation of the strategy. | LACRO Survive & Thrive | Ralph Midy (Immunisation regional adviser) | Priority: Medium Timeframe 8-months (2 months after launchng the strategy) | Not started |  |  |
| 1.4. With LACRO coordination and support, Country Offices design national action plans based on the regional strategy, national plans and existing CPDs and other plans. | LACRO Survive & Thrive | Ralph Midy (Immunisation regional adviser) Country Offices (all with priority for zero-dose countries, which might have a different timeline) | Priority: High Timeframe: 9-months (4 months after launching the strategy) | Not started |  |  |
| Evaluation Recommendation 2: Assist, upon request of COs, in strengthening regional capacity for the acquisition and management of the cold chain. |  |  |  |  |  |  |  |
| Management Response: (Agree, Partially Agree, Disagree): Agree with adaptations in actions of this recommendation |  |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| 2.1. Provide technical support in the development of best practices in areas such as cold chain supply planning, freight/lead-time estimation, procurement of services around cold chain implementation, maintenance, and training on its use, or expediting customs processes for goods on arrival. Leading the production of standard operating procedures and guidelines Creating learning hubs, products and services for UNICEF staff and their country-based counterparts. | LACRO Supplies/ Operations with support from LACRO Survive & Thrive | Maryvonne Christ (Adviser of Supplies/ Operations) | Priority: High Timeframe: 6-12 months |  |  |  |
| 2.2. Advocacy to assess regional needs (in case) to develop a capacity building plan for UNICEF CO staff on CCE. | LACRO Supplies/ Operations with support from LACRO Survive & Thrive | Maryvonne Christ (Adviser of Supplies/ Operations) | Priority: Medium Timeframe: 6-18 months |  |  |  |
| 2.3. In coordination with COs, develop a plan for capacity strengthening of country government staff in charge of the cold chain management, including managers (national level) and technical specialists (sub-national level). In coordination with CO, under request, support the process of contracting a company to develop the capacity of government staff following the development of strong technical ToR, specifying the characteristics of the services to be provided; such terms of reference would be developed by the program and the bid can assist in this effort. | LACRO Supplies/ Operations with support from LACRO Survive & Thrive | Maryvonne Christ (Adviser of Supplies/ Operations) | Priority: Medium Timeframe: 6-18 months |  |  |  |
| 2.4. LACRO will support the evaluation process in the CO recruitment of CCE specialists, under request and where needed. | LACRO Supplies/ Operations with support from LACRO Survive & Thrive | Maryvonne Christ (Adviser of Supplies/ Operations) Country Offices | Priority: Medium Timeframe: 6-18 months |  |  |  |
| Evaluation Recommendation 3: Strengthen LACRO’s own communication and advocacy efforts to support COs’ ability to execute effective advocacy and demand generation for more equitable PHC services ensuring that marginalized/minority groups are specifically targeted. |  |  |  |  |  |  |  |
| Management Response: (Agree, Partially Agree, Disagree): Agree with adaptations in actions of this recommendation |  |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| 3.1. Design and implementation of a LACRO advocacy, and demand generation plans for COs. The initial step includes technical support for a comprehensive stakeholder analysis and behaviour drivers as a key piece of evidence which will allow UNICEF COs to identify target groups and behaviour insights as well as allies and opponents to select action messages and apply Social and Behaviour Change (SBC) approaches, including Human Centred Design for improved PHC services. | LACRO Survive & Thrive Team / MCH Specialist LACRO SBC Team LACRO Communications / Advocacy Team | Ralph Midy (S & T adviser) Cassia Ayres (SBC adviser) Laurent Duvillier (C / A adviser) | Priority: Medium Timeframe: 12-18 months | Underway, subject to availability of funding | Global campaign public campaign on routine immunization will be adapted and tailored to the LAC COs. To be implemented in Q3 and Q4. Stories and good practices on routine immunization are being produced and compiled. |  |
| 3.2. LACRO to regionalize global key messages and evidence-based tools in SBC that COs can adapt, and use based on their context so that it saves them time in the implementation. | LACRO Survive & Thrive Team / MCH Specialist LACRO SBC Team LACRO Communications / Advocacy Team | Ralph Midy (S & T adviser) Cassia Ayres (SBC adviser) Laurent Duvillier (C / A adviser) | Priority: Medium Timeframe: 6months | Underway | Regional messaging is being developed as part of the SOWC launch in April 2023. To be shared with LAC COs in April ahead of the launch. |  |
| 3.3. LACRO to monitor and provide mentoring to UNICEF COs to address bottlenecks and gaps in advocacy and in demand generation for scaling up and equitable PHC services. | LACRO Survive & Thrive Team / MCH Specialist LACRO SBC Team LACRO Communications / Advocacy Team | Ralph Midy (S & T adviser) Cassia Ayres (SBC adviser) Laurent Duvillier (C / A adviser) | Priority: Medium Timeframe: 12-18 months | Not started, subject to additional funding |  |  |
| Evaluation Recommendation 4: Support COs in assessing the relevance and feasibility of scaling up technological innovations for PHC, with immunization services being an entry point. |  |  |  |  |  |  |  |
| Management Response: (Agree, Partially Agree, Disagree): Agree |  |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| 4.1. In coordination with UNICEF CO and PAHO, LACRO will support the regional mapping of planned and deployed digital health tools and technologies in the region. | LACRO Information Communication (ICT) Technology LACRO Survive & Thrive Team / MCH Specialist PAHO | Massamba Sow (LACRO T4DT4D / Business Analyst), Emily Nicholson, LACRO Survive and Thrive/Digital Health Specialist | Priority: Medium Timeframe: 12 months | Underway |  |  |
| 4.2. In coordination with UNICEF COs identify additional global and regional digital solutions, both internal and external to UNICEF, for the improved provision of primary health care services in LAC, with a first focus on immunization services. | LACRO Information Communication (ICT) Technology LACRO Survive & Thrive Team / MCH Specialist UNICEF COs | Massamba Sow (LACRO T4DT4D / Business Analyst) , Emily Nicholson, LACRO Survive and Thrive/Digital Health Specialist | Priority: Medium Timeframe: 12 months | Underway |  |  |
| 4.3. Develop a menu of applicable digital solutions for LACR CO to use and adapt for primary health care and immunization activities. | LACRO Information Communication (ICT) Technology LACRO Survive & Thrive Team / MCH Specialist | Massamba Sow (LACRO T4DT4D / Business Analyst) , Emily Nicholson, LACRO Survive and Thrive/Digital Health Specialist | Priority: Medium Timeframe: 12 months | Not started |  |  |
| 4.4. Assess identified digital solutions considering their potential to be applied for other goal areas, enabling multi-sectoral interventions. Some of these technological innovations include a geospatial information system in Nicaragua and the adaptation of the existing e-registry of COVID-19 vaccinations to include additional health information in El Salvador. | LACRO Information Communication (ICT) Technology LACRO Survive & Thrive Team / MCH Specialist | Massamba Sow (LACRO T4DT4D / Business Analyst) , Emily Nicholson, LACRO Survive and Thrive/Digital Health Specialist | Priority: Medium Timeframe: 12 months | Not started |  |  |
| 4.5. Provide technical assistance to UNICEF COs in the deployment and scale up of digital solutions to facilitate improved primary health outcomes and the provision of routine immunization services | LACRO Information Communication (ICT) Technology LACRO Survive & Thrive Team / MCH Specialist | Massamba Sow (LACRO T4D / Business Analysts), Emily Nicholson, LACRO Survive and Thrive/Digital Health Specialist | Priority: Medium Timeframe: 12 months | Underway |  |  |
| Evaluation Recommendation 5: Strengthen LACROs’ regional collaboration and coordination with PAHO’s HQ in support of PHC and regular immunization services. |  |  |  |  |  |  |  |
| Management Response: (Agree, Partially Agree, Disagree): Agree |  |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| 5.1. Design a UNICEF / PAHO joint plan, (a) to test and scale up technical and service delivery innovations, and (b) to jointly advocate to governments for equitable population access to regular immunization and PHC services | LACRO Survive & Thrive / MCH Specialist LACRO R4D Team LACRO RCCE Specialist LACRO Epidemiology / Data Analyst (to recruit) UNICEF HQ Health PAHO | Ralph Midy (S & T adviser) | Priority: High Timeframe: 6 months | Underway |  |  |
| 5.2. Increase communication between UNICEF and PAHO to coordinate further. | LACRO Survive & Thrive / MCH Specialist LACRO R4D Team LACRO RCCE Specialist LACRO Epidemiology / Data Analyst (to recruit) UNICEF HQ Health PAHO | Ralph Midy (S & T adviser) | Priority: High Timeframe: 6 months | Underway |  |  |
| 5.3. Recommendations generated from regional level to facilitate coordination and support between UNICEF and PAHO at CO level. | LACRO Survive & Thrive / MCH Specialist LACRO R4D Team LACRO RCCE Specialist LACRO Epidemiology / Data Analyst (to recruit) UNICEF HQ Health PAHO | Ralph Midy (S & T adviser) Depends on CO | Priority: High Timeframe: 6 - 12 months (depending on each country) | Not started |  |  |
| 5.4. Leverage ongoing work/added value of UNICEF for vaccination (i.e., RCCE, C4D, CCE) to facilitate further coordination with PAHO. Increase access to technical workshops organized by PAHO. | LACRO Survive & Thrive / MCH Specialist LACRO R4D Team LACRO RCCE Specialist LACRO Epidemiology / Data Analyst (to recruit) UNICEF HQ Health PAHO | Ralph Midy (S & T adviser) |  | Underway |  |  |
| Evaluation Recommendation 6: Increase LACRO’s technical support to COs for strengthening existing PHC and regular immunization services, with an emphasis on countries with large numbers of zero-dose children, and/or inadequate coverage of childhood vaccination. |  |  |  |  |  |  |  |
| Management Response: (Agree, Partially Agree, Disagree): Partially agree |  |  |  |  |  |  |  |
| If recommendation is rejected or partially accepted, report reasons: |  |  |  |  |  |  |  |
| Actions planned | Responsible Office | Responsible Person | Expected completion date | Implementation stage: Not started Underway Completed Cancelled | Actions taken | Supporting documents |
| 6.1. Monitoring system: Oversight and technical assistance to design and implement an internal monitoring/tracking system to verify the receipt of UNICEF-supported goods and services to their intended beneficiaries, upon request of the country offices carrying out this type of activity. | LACRO Survive & Thrive CO Representatives Bi-directional dialogue between LACRO and COs | Ralph Midy (S & T adviser) + Depending on CO advances and availabilities | Priority: High Timeframe: 12 – 18 months (depending on the CO) | Not started |  |  |
| 6.2. KM activities: Identify opportunities to facilitate learning from other COs (i.e., regional workshops). Coordinate documentation with COs and share lessons learned (positive and challenging ones) in regional meetings about the support that UNICEF has delivered for COVID-19 roll out and immunisation programs reinforcement in LAC. | LACRO Survive & Thrive CO Representatives Bi-directional dialogue between LACRO and COs | Ralph Midy (S & T adviser) | Priority: High Timeframe: 12 - 18 months | Not started |  |  |
| 6.4. Identify a talent pool with Spanish skills for CC technical support. | LACRO Survive & Thrive CO Representatives Bi-directional dialogue between LACRO and COs | Ralph Midy (S & T adviser) coordinated with the human resources team | Priority: Medium Timeframe: 6-12 months | Not started |  |  |
| 6.5. Coordinate with COs for financial support to continue the work on routine immunization, including support to COs for local resource mobilization. | LACRO Survive & Thrive CO Representatives Bi-directional dialogue between LACRO and COs | Ralph Midy (S & T adviser) | Priority: Medium Timeframe: 6-12 months | Underway |  |  |
| 6.6. Guidance for an early and strong collaboration of COs with the in-country PAHO teams and other international development, civil society and private sector organizations to advocate to the host country government for the equitable delivery of regular immunization services and PHC, and to coordinate the efficient use of their mobilized resources. | LACRO Survive & Thrive CO Representatives Bi-directional dialogue between LACRO and COs | Ralph Midy (S & T adviser) | Priority: Medium Timeframe: 12 - 18 months | Underway |  |  |