Evaluation of the Bringing Back Learning Programme in Myanmar

Inception Report

(Photo Source)

Version: Draft 20230314

Date: 03 April 2023

Author:

James Shoobridge

Dr. Tun Lwin

# Preliminary Material

## Table of Contents

Preliminary Material	2

Table of Contents	2

List of Tables	4

List of Figures	4

ACKNOWLEDGEMENTS	5

Definitions	6

Acronyms	8

Executive Summary	10

1	Background and Context	13

1.1	Structure of the Inception Report	13

1.2	Background and Context	14

1.3	Impact of Recent Events on Education	17

1.4	Learning Challenge	20

1.5	Impact of Recent Events on Donor Support and Funding	20

1.1	Bringing Back Learning (BBL)	22

2	Purpose, Objectives and Scope of the Evaluation	36

2.1	Evaluation Purpose, Objectives and Scope	36

2.2	Deviations from TOR	37

2.3	Evaluation Questions	38

3	Evaluation Methodology	40

3.1	Overview of Methodology and Approach	40

3.2	Evaluation Matrix	43

3.3	Literature review	51

3.4	Secondary data	51

3.5	Financial Process and Cost-effectiveness analysis	52

3.6	Primary data sources	52

3.7	Stratification	55

3.8	Data analysis	55

3.1	Report Templates	56

3.2	Data Protection Protocol and Evaluation Ethics	56

3.3	Limitations and Risk to the Evaluation	59

4	Evaluation Workplan and Process	61

4.1	Workplan	61

4.2	Deliverables	61

4.3	Schedule of Work	62

4.4	Team and Roles and Responsibilities	62

4.5	Quality Assurance	66

4.6	Communication of Findings	66

4.7	Support required from UNICEF	67

Annex 1.	Terms of Reference	68

Scope of Work:	68

Key Questions:	68

Suggested Methodology:	70

Proposed Timeframe:	72

Annex 2.	People interviewed for the Inception Phase	73

Annex 3.	Preliminary List of Key Informant Interviews	74

Annex 4.	BBL Context Timeline	76

Annex 5.	Result Framework – Bringing Back Learning (BBL)	81

Annex 6.	BBL Programme Data	84

Annex 7.	Region and Site Selection Criteria	108

Annex 8.	Online Perception Survey	110

Annex 9.	Key Informant Questionnaires	113

Form 1: Consent Form	113

Form 2: FGD and Case Study Informed Parental and Student Consent Form	115

Form 3: Facilitator (Teacher) Focal Group Discussion (FGD) Introduction and General Guidelines	117

Form 4: Child / Parent Focal Group Discussion (FGD) Introduction and General Guidelines	119

Form 5: Ethical Guidelines for conducting Interviews/FGD with children 	121

Form 6: Introduction Letter to Key Informant Interviews (KII)	122

Tool 1: Implementation Partner (IP) KII	123

Tool 2: Centre Head KII	127

Tool 3: Facilitators FGD	130

Tool 4: Parents, Caregivers, Community Members of the Parent Committee and Students FGD	133

Tool 5: Donor and UNICEF KII	135

Tool 6: Case Study Form.  Parents/Guardians and Students	136

Tool 7: Site Observation Form	137

Annex 10.	Structure of Final Report	140

Annex 1.	List of Partners and Programmes	142

Annex 2.	Additional Ethics Material	143

## List of Tables

Table 1.	Structure of the Inception Report	14

Table 2.	Implementation Partners DCT Amount, Funds Received Date and Disbursement, 	36

Table 3.	Evaluation Matrix	45

Table 4.	KII Number of KII / FGD Envisioned	54

Table 5.	Risks, Limitations, and Mitigation of the Evaluation	60

Table 6.	Fees (payment schedule) allocated to each deliverable	62

Table 7.	Members of the Evaluation Taskforce	63

Table 8.	BBL Evaluation Schedule of Work	65

Table 9.	Preliminary List of Key Informant Interviews	75

Table 10.	Myanmar Timeline of Events	77

Table 11.	Results Framework BBL Programme	82

Table 12.	BBL Partners, Start and End Date, and Contributions to Output Areas	85

Table 13.	BBL Children and Facilitators Reached in 2022 by Partner and Township	89

Table 14.	OOSC, IP Coverage and Number of IP, UNESCO Site Selection	109

Table 15.	Site Selection for Site Evaluation Visits	110

Table 16.	List of Partners and Programmes	143

## List of Figures

Figure 1.	Overview of Myanmar school system structure	17

Figure 2.	Education Cluster Structure	22

Figure 3.	Children affected by the BBL Programme in 2022 by Output Area and IP	30

Figure 4.	Facilitators Affected by the BBL Programme in 2022 by Output Area and IP	30

Figure 5.	States and Townships  covered under the BBL Phase II	32

Figure 6.	BBL Implementation Partners Contract Start and End Date	33

Figure 7.	BBL Implementation Partner and UNICEF financial contributions (USD equivalents), 	34

Figure 8.	Original DCT vs Percentage Disbursement as of Last Date Received	34

Figure 9.	Purpose, Scope and Objectives for the Evaluation of the BBL	37

Figure 10.	People interviewed for the Inception Phase	73

Figure 11.	BBL Programme Financial Contributions to Implementation Partners	86

## ACKNOWLEDGEMENTS

The Evaluation Consultants would like to thank all those who have supported and informed this Inception Report prepared for the Evaluation of the Bringing Back Learning Programmme for Maynmar (BBL) scheduled to be conducted between January and May 2023. We are particularly thankful to Dr. Shweta Sandilya, Mitsue Uemura, Hyunjung Lee, Stephen Close, Yanhong Zhang, Aye Myint Than Htay for their continuous support and input during the Inception Report. We are also grateful to the implementing partners and donors for their reflective and constructive input during inception interviews and working group discussions. Your active and committed participation during the inception confirms the feasibility and usefulness of our suggested participatory methodology for the BBL. Finally, we want to thank other key stakeholders who have dedicated time and provided important perceptions on the evaluation of the BBL.

The evaluation Team Leader, James Shoobridge, is the principal author of this report and was supported by team members Dr. Tun Lwin, National Consultant.

Disclaimer

The opinions expressed are those of the independent evaluator, and do not necessarily reflect those of UNICEF. Responsibility for the opinions expressed in this report rests solely with the author. Publication of this document does not imply endorsement by UNICEF of the opinions expressed.

The designations employed and the presentation of material in the maps and other material do not imply the expression of any opinion whatsoever on the part of UNICEF concerning the legal or constitutional status of any country, territory, or sea area, or concerning the delimitation of frontiers.

## Definitions

To avoid unnecessary confusion, the Bringing Back Learning Evaluation (BBLE) has applied the following definitions for common concepts used. The BBLE recognizes that there are many other definitions that might be valid for other circumstances.

| Concept | Working definition |
| --- | --- |
| Accessibility | The extent to which project activities can be reached / obtained by targeted beneficiaries; e.g., knowledge about the possibilities to participate, location of distributions, etc. |
| Activity | Actions taken or work performed through which inputs, such as funds, technical assistance and other types of resources are mobilized to produce specific outputs. |
| Acute Malnutrition | Weight for height below normal standards. Also referred to as wasting. |
| Administrative Data | Admin data is data collected as part of the routine provision of a service. In the context of EMIS this includes: All school and student data, including student management data, student learning data, school finance data, etc. |
| Advocacy | Any attempt to persuade another side to agree to one’s demands. |
| Capacity Development / Building / Strengthening | The process by which individuals, groups, organizations, institutions and countries develop, enhance and organize their systems, resources and knowledge, all reflected in their abilities, individually and collectively, to perform functions, solve problems and achieve objectives. |
| Coherence | The extent to which activities of different actors are complementary or contradictory. |
| Communication | The process of transmitting information in a way that will be understood and thus communication goes beyond simple information dissemination. To ensure that the information will be understood any communication should be based on a good knowledge of the context of the target group, in terms of values, priorities, resources, capacities, etc. Communication becomes even more important and takes on added dimensions when it involves inter-cultural or inter-organizational communication. |
| Consultation | A process that finds out what targeted stakeholders think about specific activities, projects, or approaches. Focus groups, questionnaires, and interviews are common consultation techniques. |
| Convergence | Coming together and integration of two or more distinct entities (e.g., sectors, programmes, departments, agencies, or levels of implementation) to work towards a common goal. Convergent programming refers to meaningful programmatic linkages that work to achieve greater results. Multisectoral approaches aim to address one problem using different sectors. Multi-pronged is when several distinct aspects or elements (prongs) converge to attack a common target from different angles. |
| Coordination | The process of systematically analyzing a situation, developing relevant information, and informing appropriate command authority of viable alternatives for selection of the most effective combination of available resources to meet specific objectives |
| Equity | All children have an opportunity to survive, develop and reach their full potential without discrimination, bias or favouritism. |
| Equity based approach | An approach that seeks to understand and address the root causes of inequity so that all children, particularly those who suffer the worst deprivations in society, have access to education, health care, sanitation, clean water, protection, and other services necessary for their survival, growth and development. |
| Gender equality | Women and men, and girls and boys, enjoy the same rights, resources, opportunities, and protections. It does not require that girls and boys, or women and men, be the same, or that they be treated exactly alike. |
| Harmonization | The process through which two or more parties apply consistency in their procedures, rules, and regulations for specific activities. |
| Knowledge management | The process of defining, structuring, retaining and sharing the knowledge and experience within an organization. |
| National | This refers to the whole country. In the survey, the national level refers to legislation mandated by the central government. |
| Needs Assessment | Identification of required interventions to achieve the stated objectives of the program / project based on a comprehensive evaluation of the baseline situation. |
| Normative work | Refers to different aspects of strengthening legislation and policy as well as implementation: 1/development of norms and standards, 2/support to governments and others to integrate norms and standards into legislation, policies, and development plans, and 3/support to governments and others to implement legislation, policies, and development plans based on international norms, standards, and conventions. |
| Ownership | The targeted stakeholders such as communities, local and national authorities exercise effective leadership over the project activities. Ownership is closely linked to effective participation, which should allow only to implement activities that have been identified as priorities by the targeted stakeholders. |
| Participation | Participation is about including targeted stakeholders in decision-making processes, including identifying needs and solutions and be actively involved in project and program design, implementation, and monitoring and evaluation. Common participatory techniques include facilitated community meetings and workshops. |
| Social Protection | Policies and programmes designed to protect people from shocks and stresses throughout their lives. It can include safety nets, social insurance schemes, labour market regulations or facilitated access to essential services. |
| Stakeholders | Agencies, organizations, groups, or individuals who have a direct or indirect role and interest in the objectives and implementation of the Cash project and its evaluation. |
| Sub‐national | This refers to administrative levels that fall below the national level. In the context Myanmar these are states/regions, districts, townships. |

## Acronyms

AF		Accelerated Fund

ADB		Asian Development Bank

AG		Advisory Group

CREATE	Curriculum Reform at Primary Level of Basic Education

CSO		Civil Society Organisations

CwD		Children with Disabilities

DFA		de facto authorities

DFAT		Department of Foreign Affairs and Trade, Australia

EAO		Ethnic Armed Organisations

EiE 		Education in Emergencies

EU		European Union

FCDO		Foreign, Commonwealth and Development Office, United Kingdom

FERD 		Foreign Economic Relations Department

GBV		Gender-based Violence

GEDSI		Gender Equality, Disability and Social Inclusion

GPE		Global Partnership for Education

HACT		Harmonised Approach to Cash Transfer

HBL		Home-based Learning

HRP		Humanitarian Response Plan

ICT		Information Communication and Technology

JICA		Japanese International Cooperation Agency

IIEP		International Institute for Educational Planning

IP		Implementing Partner

JRF		Joint Response Framework

KMSS		Karuna Mission Social Solidarity

KBC_SM	Karen Baptist Convention Social Mission

LTAs 		Long Term Agreements

MBAPF 	Myanmar Book Aid and Preservation Foundation

MC		Management Committee

MEAL		Monitoring, Evaluation, Assessment and Learning

MHPSS		Mental Health and Psychosocial Support

MLRC		Myanmar Literacy Resource Centre

MoE		Ministry of Education

NFPE		Non-formal Primary Education

NFE		Non-formal Education

NGO		Non-government Organisation

NUG		National Unity Government of the Republic of the Union of Myanmar

OL		Open Learning

OOSC		Out-of-school Children

PCA		Partnership Cooperation Arrangement

PCC		Programme Coordination Committee

PD		programme document

PSEAH		Prevention of Sexual Exploitation Abuse and Harassment

SAC		State Administration Council

SC		Steering Committee

SDG		Sustainable Development Goal

SEL		Social Emotional Learning

SERRP		Socio-Economic Resilience and Response Plan

ST-HBL	short-term home-based learning

UN		United Nations

UNCT		United Nations Country Team

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNICEF	United Nations Children’s Fund

# Executive Summary

This inception report details the methodology and approach to evaluation of the Bringing Back Learning Programme (BBL) for Myanmar.  The BBL Programme is a programme designed to respond to the twin crisis which have emerged in Myanmar.  The first being the Covid-19 pandemic which reached Myanmar on 23 March 2020.  The second being the February 2021 coup d'état in Myanmar when the democratically elected members of the country's ruling party, the National League for Democracy (NLD), were deposed by the Tatmadaw, Myanmar's military, which then vested power in a military junta.  The confluence of Covid19 and the coup has resulted in millions of children and youth now facing significant challenges in accessing and continuing with their education due to a multitude of complex factor, particularly the most vulnerable children with long-lasting consequences for their cognitive development and their socio-economic futures.

The BBL programme seeks to address the crisis by providing targeted girls and boys, aged 3 to 18 years old, who have been out of learning and have not yet started or completed a primary level education, with catch up and remedial education opportunities within their community, with a particular focus on literacy, numeracy, life skills and Social and Emotional Learning.  It seeks to achieve this by: i)  providing girls and boys aged between 3 years old and 18 years old, whose learning has been disrupted, with access to education literacy, numeracy, and wellbeing support; ii) Ensuring facilitators, CSO resource persons, and community members are well equipped with relevant capacities and receive appropriate technical support to deliver context responsive gender sensitive, equity-focused, quality education and wellbeing support.  The BBL Programme has special emphasis on those vulnerable children most likely to have been impacted by the crisis.  This aligns with the partner Joint Response Framework (JRF) objective of ensuring that children and youth in Myanmar re-engage in quality, meaningful, inclusive and gender responsive learning in safe, protective environments, with a particular focus on the most vulnerable learners such as children from Internally Displaced Persons (IDPs), migrant communities, and ethnic minority and girls and boys with disabilities or developmental delays and adolescent girls.

The BBL Programme operates under the operational modalities advised in the United Nations Country Team (UNCT) guidelines (2021) which emphasis the need to not establish a parallel education system while at the same time limiting engagement with De Facto Authorities (DFA).   This has placed an emphasis on implementing activities through alternative modalities including partnering with International Non Government Organisations (INGO) and National Non Government Organisations (NNGO), community-based organizations and CSOs, whilst not excluding any child from accessing services.  The BBL Programme has a wide geographic focus being active in 6 regions with high deprivation, and 46 townships throughout Myanmar.  NGO/CSO selected as implementation partner’s are responsible for strengthening and delivering education services in accordance with separate Implementation Partner (IP) agreements.

Sources of funding include Japan, Norway, GWA, Global Partnership for Education (GPE), Korea International Cooperation Agency (KOICA), Department of Foreign Affairs and Trade (DFAT) as AusAID.  During 2021 to 2022 GPE funds were utalised to implement the BBL.  UNICEF and DFAT signed an agreement in February 2022 to enable utalisation of DFAT funding from June 2022 to June 2023.

The purpose of the Inception Report is to set out the evaluation team’s approach and methodologies to the BBL Evaluation based on a document review of the context and the BBL Programme preparatory and implementation description, as well as interviews with key stakeholders as described in the following sections. As such, the Inception Phase has allowed the BBL Evaluation Team to familiarize itself with the content, scope, challenges, and opportunities of the BBL Programme and its context. Moreover, an important continuous dialogue has been established between the BBL Evaluation Team and the UNICEF Myanmar Country Office (MCO). As a result, the BBL evaluation scope, evaluation questions and design and methodology have been further refined.

The BBL Evaluation objectives and scope are described in the Terms of Reference (TOR) (annex 1).  The BBL Evaluation is commissioned by UNICEF Country Office in the Myanmar (MCO) who are also the responsible managing authority for the evaluation.  Following the TOR, the BBL Evaluation is carried out as an independent exercise by the evaluation team, lead by an international consultant working in conjunction with a national consultant an enumerators to implement the evaluation.

Consistent with the United Nations (UN) Evaluation Norms and Standards (2016), the purpose of this evaluation will be formative and summative.  The formative component responds the evaluation questions which are clustered under Organisation for Economic Co-operation and Development (OECD) Development Assistance Committee (DAC),  and UNEG criteria of relevance, effectiveness, efficiency, and sustainability and Gender and Inclusion.  The summative attempts to draw conclusions as to the likely possibility of the BBL achieving its objective and outcomes.  The evaluation matrix presented in this report connects evaluation questions to data collection tools and methods employed through this evaluation and is thematically aligned with UNEG.

The purpose of the BBLE is to: i) provide evidence on how the programme has progressed as envisaged initially; ii) Determine whether the processes have effectively contributed to its stated objectives and achieved the intended results during that period.  The BBLE specific objectives are: i) Identify how processes contribute to the results by understanding the achievements to date; ii) Provide secondary evidence on the Theory of Change, and the extent to which project objectives have been reached; iii) Determine the relevance of the various strategies in meeting the education needs of children in a dual crisis situation; iv) To evaluate the approach towards GEDSI within the context of the twin crisis and deprivation experienced throughout Myanmar.  Other considerations include: i) The way each of the involved partners has fulfilled their part of the initiatives obligations; ii) How communities and partners have collaborated to reach the project’s objectives; iii) Provide additional qualitative and quantitative evidence of fulfillment/nonfulfillment of the project’s objectives.  The BBLE scope includes all IP agreements and the period from June 2021 to June 2023.  Users of the BBLE will include the BBL programme’s main implementing partners and stakeholders including donors of the project BBL.

The key activities of the Inception Phase have included:

  - Review of relevant documents and identification of their use in the BBL Programme as referenced in the inception report.

  - Preliminary discussions with the informal UNICEF BBL Evaluation Taskforce established to facilitate the BBL Evaluation. The inception meetings have included a kick-off meeting and weekly check-in meetings. These meetings have allowed a close dialogue on the issues at stake for the BBL Programme.

  - Meeting with other the Australian Department for Foreign Trade who are a primary donor to the BBL Programme for 2022.

  - Liaising and further dialogue of how the BBL Programme should be conducted: focus, approach and methodology, stakeholders, key sources of information, programme for the data collection. The revision took place in close dialogue with the informal BBL Evaluation Taskforce that also helped in identifying key resources to inform the BBL Evaluation.

  - Preparation of this Inception Report as the basis for the BBL Evaluation itself.

The inception interviews pointed to issues that would need special attention in the BBL Evaluation itself:

  - Diversity in approach to implementing the BBL throughout Myanmar. The BBL Programme has been implemented under a twin crisis and thus the challenges and the approach towards meeting challenges vary between IP, regionally and between townships.

  - Focus on vulnerable persons.  The twin crisis has exacerbated the challenges encountered by the most vulnerable throughout Myanmar while at the same time greatly increasing the number of vulnerable persons.  The impact of the crisis will be most felt by vulnerable persons.  It will be important to apply a focus throughout the BBL Evaluation towards gender, disability, and other requirements for social inclusion.

  - Special consideration for the crisis situation.  The evaluation takes place in a conflict environment and thus faces specific challenges.  These may include: i) the possibility of suspicious or intransient government or local officials; ii) the need to protect identities of informants; iii) consideration for the safety of the evaluation team including enumerators; iv) consideration to local languages, customs and norms.

  - A focus on the operational modalities, organisational modalities and utilisation of funds in the context of responding to a humanitarian crisis.  Consideration must be given to the extreme context of the BBL programme and the lessons which can be learnt for possible application in the broader context of humanitarian response globally and towards informing future programming within Myanmar.

The above listed issues are all covered by the suggested evaluation framework presented in the inception report. To date there have been no changes to the original TOR evaluation questions but the evaluation team is open to changes during the evaluation process given the fluid nature of the situation within Myanmar at the time of conduct of the evaluation.

# Background and Context

## Structure of the Inception Report

Structure of the Inception Report

| Chapter |  | Content |
| --- | --- | --- |
| 1. | Background / Context | - Introduction to the Inception Report - Description of the context in which the BBL is being implemented including the dynamic and unforeseeable aspects. - Description of the BBL: background, design, focus, change strategies, key implementing partners, partnerships, role in the development of Myanmar, budget, and results framework. - BBL geographic coverage - Theory of Change (TOC) and Results Framework |
| 2. | Evaluation Purpose, Objectives and Scope | - BBL evaluation purpose, scope, objectives, justification for the Evaluation - BBL evaluation coverage thematically, geographically, and timewise as well as focus |
| 6. | Evaluation Methodology | - BBL Evaluation (BBLE) approach, data sources, data collection processes and methods, and data analysis approach and methods - Data protection protocol and evaluation ethics - BBL Evaluation criteria and questions presented in a logical manner and reflecting gender, equity, and human rights - Risk assessment of the BBL Evaluation, limitations, and mitigation measures |
| 7. | Workplan and Deliverables | - BBL Evaluation process workplan with deliverables and a schedule of work - Team roles and responsibilities - Quality assurance processes, roles and responsibilities and criteria - Communication of fundings - Required support from UNICEF |
| 8. | Governance Arrangements | - Team roles - Governance arrangements - Quality assurance for the BBLE process and products |
| 9. | Annexes | - Terms of reference - People interviewed for the inception phase - Preliminary list of key informant interviews - BBL context timeline - Result framework – Bringing Back Learning (BBL) - BBL programme data - Region and site selection criteria - Online perception survey - Key informant questionnaires - Structure of final report - Check partner questionnaire |

## Background and Context

### Country Context

The Union of Myanmar is geographically situated in Southeast Asia, bounded on the north and northeast by the People’s Republic of China, on the east and southeast by the Lao’s People Democratic Republic and the Kingdom of Thailand, on the south by the Andaman Sea and the Bay of Bengal and on the west by the People’s Republic of Bangladesh and the Republic of India. Myanmar with a land area of 676,553 square kilometres is the largest country in mainland Southeast Asia. The Union of Myanmar is administratively divided into seven states and seven divisions.

Myanmar has been subject to significant political and social upheaval in recent years.  During February 2021, a coup d'état in Myanmar occurred when the democratically elected members of the country's ruling party, the National League for Democracy (NLD), were deposed by the Tatmadaw, Myanmar's military, which then vested power in a military junta.  In addition, Covid-19 was confirmed to have reached Myanmar on 23 March 2020.  Although the government rapidly implemented containment measures and public health responses, the country had experienced one of the most severe Covid-19 outbreaks in Southeast Asia by late 2020. The UN raised concerns about Myanmar's vulnerability to the pandemic due to its weak healthcare infrastructure following poor investment over six decades of military rule, as well as ongoing internal conflict.  Gross Domestic Product (GDP) was estimated to be 78.93 billion USD in 2020.   However the pandemic and the political upheaval have greatly disrupted the country's economy and Myanmar's Gross Domestic Product (GDP) shrank by 5% to 65.09 Billion in 2021 and to have contracted a further 3% during 2022.

According to census, the total population is estimated at 55 million (55,335,883) as of 2022; of which there are 93.02 males per 100 females (GPI 1.08). Myanmar has favourable demographics with the median age being 29.0 years. Most people live in rural areas (78.6 percent) Only 31.4 percent of the population is urban (17,068,066 people in 2020). The annual population growth rate is 2 percent.

There are as many as 135 ethnic groups. It is estimated that 65.4 per cent of the population is engaged in the agricultural sector, 14.0 per cent in the industrial sector and 20.6 per cent in the services sector. Since ancient times, people enjoy freedom of worship. Buddhism is practised by 45.2 million people (87.9 per cent of the population), Christianity by 3.0 million (6.2 per cent ), Islam by 1.1 million ( 4.3 per cent ), Hinduism by 0.3 million ( 0.5 per cent ), Animism by 0.4 million ( 0.8 per cent), other religions by 0.1 million ( 0.2 per cent ).

Poor education and poverty are closely associated, and education can be an effective means of raising people out of poverty.  A recent poverty estimate based on 2015 living conditions released by the Ministry of Planning and Finance and the World Bank finds that poverty is estimated at 32per cent in 2015.  Poverty in Myanmar’s rural areas is substantially higher than that in its urban areas: 38.8per cent of the rural population are estimated to be poor compared to 14.5per cent of those in its towns and cities.  Further, poverty remains geographically spread in Myanmar: in the coastal and mountainous areas, 4 in 10 of the population are poor and 1 in 6 will struggle to meet their basic food needs, while 65per cent of the poor live in the Dry Zone and Delta.

The report associates poorer households as those being characterized as having more family members and more young and elderly dependents per working age adult and that children of poor households have limited access to official documents that enable access to public services and formal credit sources such as formal education.

### Myanmar Education System

Schooling is compulsory in Myanmar until the end of the elementary (primary) level, or approximately to age 9, while at the international level it is compulsory up to age 16. There are 3,830 high schools, 14,280 middle schools and 27,871 primary schools, or a total of 45,981 basic education schools. Just over 41,000 of these are in rural areas. Nearly all are government operated, although there has been a recent increase in private schools. Monastic schools operate under the supervision of the Ministry of Religious Affairs and some ethnic schools run by ethnic communities also provide the national basic education curriculum.

In principle, primary school is free and lasts five years, from age 5 to 9. The school year is broken down into two semesters and lasts roughly 36 weeks.

For basic education from primary to upper secondary, the academic year begins in June and ends in March. Until 2015, Myanmar had a “5:4:2” formal education structure, where primary school lasted for five grades. This broke down into lower primary (grades 1 to 3) and upper primary (grades 4 to 5). The first grade was also be referred to as "reception year" or "kindergarten" (KG). Secondary school was divided into two “cycles”: lower secondary consisted of grades 6 through 9 and upper secondary consisted of grades 10 through 11. Lower secondary was also referred to as "middle school" and upper secondary as "high school." Students sat for an exam at the end of Grade 5 and at the end of Grade 9, as well as the Basic Education High School Exam at the end of upper secondary.

For those continuing on to higher education, there are 48 universities and degree colleges under MOE, 24 teaching colleges and 60 technology and computer universities; there are 26 universities under other ministries. There are also 33 technical schools (Myanmar DTVET, March 2017), 25 nursing schools, 22 midwifery schools and 4 sports academies (Myanmar Ministry of Health and Sports [MOHS] 2017).

A high-level representation of the structure of the education system in Myanmar is presented in the diagram below.  As part of the educational reform outlined in the National Education Sector Plan (NESP) 2016-2021, the Myanmar Ministry of Education has introduced a new basic education curriculum, which is being implemented gradually alongside the restructuring of the school grades. It is not clear whether the education reform has been continued under the current government.

Overview of Myanmar school system structure

Technical and vocational education and training in Myanmar is provided by relevant ministries (MoE and Ministry of Science and Technology (MoST)) and the private sector through approximately 372 technical and vocational education and training centres. For adults in the general public, the MOE provides some access to alternative education through a Non-Formal Primary Education Equivalency Programme (NFPE) for out of school children and a Summer Basic Literacy Programme (SBLP).

## Impact of Recent Events on Education

Prior to 2021, conflict affected several states in Myanmar, including Kachin, Northern Shan and Rakhine. The prior government was working to accelerate efforts in the peace process under the leadership of State Counsellor,.  These efforts were largely halted in 2020 when, on February 1st, Myanmar armed forces (the Tatmadaw) staged a military coup declaring fraud in the November 2020 multiparty general election won by the National League for Democracy. A year-long state of emergency was ordered which was extended to the current date. In addition, Covid 19 was confirmed to have reached Myanmar on 23 March 2020.  Although the government rapidly implemented containment measures and public health responses, the country had experienced one of the most severe COVID-19 outbreaks in Southeast Asia by late 2020,  (refer timeline in Annex 4).

When the COVID-19 pandemic hit Myanmar in March 2020, all organized education services for children were largely halted, impacting 12.5 million children, including 2.8 million children aged 3-5 years, and 9.7 million school aged children.​ Alternative education services such as Non-formal Primary Education (NFPE) and Non-Formal Middle School Education (NFMSE) supported by the Ministry of Education (MoE) were also closed and, as a result, 8,000 children who would otherwise had been enrolled in non-formal education have also been out of learning.

Before-COVID, the challenges for education were significant with an estimated 2.3 million of children aged 5 – 18 years out of school.  The confluence of Covid19 and the coup has resulted in millions of children and youth now facing significant challenges in accessing and continuing with their education due to a multitude of complex factor, particularly the most vulnerable children with long-lasting consequences for their cognitive development and their socio-economic futures..

The Ministry of Education (MoE) under the De Facto Authorities (DFA) commenced reopening of schools as of 1 November 2021. However, as of mid 2022 this had not happened in all areas and thousands of schools and other learning facilities remained closed. Many schools which had opened were subject to closure owing to COVID-19, conflict, community tensions, and the impacts of natural hazards such as flooding. As of mid 2022, and according to different sources, only 3.5 million student being approximately a quarter of the total were back in MoE schools. Hundreds of thousands of students were studying through Ethnic Based Education Providers and some others were receiving education in Temporary Learning Centres (TLCs) and monastic schools, but a large but unknown number of children were still out of education entirely and the situation is unlikely to have improved significantly by the end of 2022. Enrolment rates vary significantly across the different states and regions of Myanmar. A significant proportion of the population were choosing not to send their children to formal schools due to concerns around safety and security, and COVID-19.

The Myanmar Education Cluster Strategy (MECS) (2022-2025) identifies the main inter-related challenges as:

- Children and youth in Myanmar have poor access to safe, inclusive education.  Children from all affected population groups, especially from Internally Displaced Persons (IDP) and conflict affected communities, face challenges in accessing safe, inclusive and quality learning opportunities.  Displacements exacerbate children and families’ vulnerabilities and keep them away from all modes of education.

- Many schools represent a structural danger themselves, as the almost two-year closure has had a strong impact on buildings, compounds, WASH facilities and fences.

- The crisis has resulted in a significant teacher shortage. 125,000 Facilitators have been suspended for joining the Civil Disobedience Movement (CDM) and only 6,000 Facilitators have been newly recruited against the MoE’s plan for 23,000.  Many of these Facilitators are not sufficiently equipped to handle a ‘condensed curriculum’ and attend to students’ well-being. They are also facing significant pressure, threats and harassment.

- Limited opportunities to engage in all types of learning including a lack of home-based learning and self-study/open learning materials. Dropouts are high due to year-long school closures and limited access to electricity and Internet affect most children and youth in Myanmar, which contributes to the general decline of opportunities to engage in learning.

- Economic barriers in most communities also play a substantial role in the lack of access to education, as so many families have lost their income and cannot afford their children to learn and/or pay for school supplies.  These issues have been exacerbated by cash shortages and depreciation of the national currency and a rise in poverty projected to increase to pre-2005 levels, with estimates that 46 percent of the population will be living below the poverty line by early 2022.

- The level of quality in education remains a key concern in most parts of Myanmar.  Nearly all of the 11.6 million school-aged children in Myanmar were without education for almost two years and this is having a long-term impact on their learning. This is an even greater challenge for children with learning difficulties or other learning needs and disabilities, as they may take longer to get back to the stage they were at previously, and parent and carers are even less likely to prioritise education for them, with the additional new challenges.

- For all states and regions, the question of learners with disabilities is critical as not enough support is available and as the three-layered crisis affects learners with additional vulnerabilities even more severely.

- Parents, caregivers, educators, CSOs and NGOs face a multitude of challenges in all states and regions due to the lack of access to education for safety and protection reasons. Many communities have no ability to create safe learning spaces and they actually face security risks in providing community level education, especially in IDP/returned & resettled IDP communities and host communities where the presence ofarmed forces is a constant threat.

- In some areas, an increasing number of families opt to send their children to the schools of ethnic/indigenous education providers, but often the providers lack resources to accommodate the large increase in students.

As such overcoming access constraints remains a top concern in delivery of humanitarian assistance by local and national partners, who are also faced with security concerns and the need to prioritise in the face of overwhelming needs. Communities and alternative providers have become focal points for delivery of education services and opportunities.  Strengthening the existing capacities of communities, local CSOs, and national NGOs and providing support to build capacity according to their identified needs has become a main focus of development partners and in an effort to ensure education in Myanmar is more resilient for the present and future crises whether related to politics, armed conflict, or climate change.

## Learning Challenge

A learning crisis existed in Myanmar even before the prolonged school closure due to COVID-19, exacerbated by the military takeover on 1 February 2021. Across Myanmar, 2.7 million children were out of school prior to the crisis and have not completed primary education. The South-East Asia Primary Learning Metrics (SEA-PLM) 2019 assessment showed that 60 percent of grade 5 children in Myanmar were in the lowest proficiency band for reading. Poor learning outcomes for children, especially children from minority groups and children with disabilities, is also confirmed by findings from both the Early Grade Reading Assessment and Early Grade Mathematics Assessment. At the national level, it was estimated that less than 30 percent of grade 3 students in government schools achieve fluency in reading grade-appropriate text in the Myanmar language. In 2018, UNICEF reported that 47 percent of CwD were out-of-school with the analysis indicating that education outcomes for girls with a disability were worse than those for boys with disabilities. With almost two years of learning loss for most children in Myanmar, the gaps are expected to be far greater now.

## Impact of Recent Events on Donor Support and Funding

Since the military takeover and the ensuing political crisis, the majority of partner engagement with the Ministry of Education (MoE)/Ministry of Science and Technology (MoST) has been paused. While it is widely recognized that there are increasing needs to support the continuity of learning, the complex political and operational environment characterized by an increased politicization of education and a deteriorated security situation, makes education partners’ interventions extremely challenging.  A full timeline of events and challenges is presented in Annex 4.

In response, education partners have developed a joint education response framework to respond to the educational needs arising from the prolonged learning crisis exacerbated by the military takeover in a coordinated, coherent and transparent way.  The overall objective of the Joint Response Framework (JRF) is to “ensure that children and youth in Myanmar re-engage in quality, meaningful, inclusive and gender responsive learning in safe, protective environments, with a particular focus on the most vulnerable learners such as children from IDPs, migrant communities, and ethnic minority and girls and boys with disabilities or developmental delays and adolescent girls.”

The specific objectives of the Joint Response Framework are to:

- Outline key programmatic priorities, strategies, and parameters of engagement for development partners to respond to the educational needs arising from the compounded crises.

- Serve as a key guiding document for development partners to ensure that their support to the education sector during the agreed interim period remains well-coordinated.

- Strengthen the development-humanitarian nexus and foster closer coordination and alignment between development and humanitarian partners in the education sector.

The JRF details broad strategies for providing education support and strengthening throughout Myanmar in the absence of direct engagement with government while ensuring and targeting the most disadvantaged and vulnerable who will be most affected in times of crisis.  The JRF is informed by six existing documents:

The 2021 Myanmar Humanitarian Response Plan (HRP):

- Myanmar Interim Emergency Response Plan (June – December 2021)

- The Myanmar Education Sector Assessment

- The EiE Sector Provisional Strategy

- The 2020 Education Sector Analysis

- The Myanmar Education Cluster Strategy (MECS) (2022-2025)

The Bringing Back Learning Programme aligns directly to the JRF strategic objective under basic education, including early learning. It aligns to all three programmes including programme 1 on access, programme 2 on quality and learning, and programme 3 on management. In terms of the sub-programmes, this proposal aligns with sub programme 1.1, 1.2, 1.3, and 1.4. Under programme 2 it aligns with all five sub-programmes and under programme 3, it aligns especially to sub-programme 3.1, 3.2, 3.3 and 3.4 as per the draft JRF, version available as of 11 February 2022.

The Myanmar Education Cluster Strategy  provides further direction concerning the needs, response activities, and collective Cluster priorities for the three-year period from 2022 to 2025. It provides a common approach and operational plan among Education Cluster partners throughout Myanmar to prepare for and respond to the emerging humanitarian crisis. The MECS provides a guiding framework which articulates the education related humanitarian needs, identifies the scope of interventions required to help address the crisis and defines areas for collaboration between stakeholders.  The three main objectives of the MECS are:

- Crisis-affected and other vulnerable children and youth with humanitarian needs have continued access to safe, inclusive, quality learning opportunities.

- Crisis-affected and other vulnerable children and youth with humanitarian needs receive quality, protective, and inclusive education that caters for their mental health and psychosocial needs.

- The capacity of communities and local/national education partners is strengthened to support safer, coordinated education that monitors and responds to identified needs, and mitigates impacts of shocks and crises.

Education Cluster Structure

The BBL programme commenced in June 2021, prior to the drafting of the partner strategies, and helped inform the strategic approach adopted by partners through the MECS and JRF.  However, despite coming first, the BBL Programme also operates under the general umbrella of the MECS/JRF and falls within the same structure (refer below).

## Bringing Back Learning (BBL)

### BBL Rationale

Following the military takeover, UNICEF transitioned from a programme that mainly provided upstream support to the government to ensuring humanitarian response was delivered through Community Based Organisations (CBOs) and national and international non-governmental organisations (NGO).

The rational for the BBL Programme were:

- The need to strengthen community capacity to support children to continue learning to make education services more resilient at the grassroots level.  This was important given the erosion in the provision of government services since February 2021 and the inability of many partners, including the UN, to engage DFA MoE was limited, in line with the United Nations Country Team (UNCT) guidance, .   As such community libraries, hubs, and community learning centres presented a strong opportunity for temporary provision of education to children, as well as being able to continue providing supplementary education in the longer-term.

- The need to support children, including girls and boys and children with disabilities, with foundational skills of literacy, numeracy and Social Emotional Learning (SEL), with Mental Health and Psychosocial Support (MHPSS).

- The need to support adolescents, including girls and boys and CWD, with literacy, numeracy and SEL and primary equivalency programmes.  This was important as since February 2021, most of the out-of-school children and adolescents who were accessing non-formal education through the MoE were unable to do so. They now relied on support from CSO and other partners who have minimal capacity in this area, and hence are largely offering limited non-formal education, numeracy and literacy which, while offering important benefits, does not create a pathway back into more formal education. The situation was exacerbated by the closure of schools and the increase in the proportion of students unable to access learning for almost two years.

- The need to ensure children have access to relevant, inclusive, gender-sensitive learning materials.  Girls and boys need to be supported at the community level with supplementary and flexible learning approaches that are gender-sensitive to mitigate learning loss with a focus on children aged between 5 and 10 years of age and on teaching and learning materials focused on literacy, numeracy and Social and Emotional Learning (SEL).

- The need to focus on Gender Equality, Disability and Social Inclusion and to mitigate safety and security concerns as much as possible and provide education services close to where children live so they do not need to travel.   This includes ensuring that appropriate support services and assistance is available for CwD, including in ethnic languages, appropriate teaching and learning materials

- The need for monitoring of children’s learning outcomes adapted to the challenges prevalent in Myanmar.  Such approaches should focus on assessing a child’s existing proficiency in various areas, allowing facilitators to provide appropriate materials and guidance to support the child to progress and achieve key competencies.

- The need to tackle COVID-19 and ensure safe learning spaces with the provision adequate WASH facilities and practices and Information, Education and Communication (IEC) materials on COVID-19 prevention.

- The need to adhere to United Nations Country Team (UNCT) guidelines while not establishing a parallel education system.   The guidelines stipulate limited engagement with DFA and on implementing activities through alternative modalities including partnering with INGO/NNGO, community-based organizations and CSOs, whilst not excluding any child from accessing services.

### BBL General Approach, Principals and Assumptions

In response to the challenges, the BBL undertook an approach which included: i) Community libraries, community learning centres ‘hubs’ as a key approach to support all children to catch-up and continue learning; ii) Opportunity for replication and outreach building on upgradation of library hubs for replication in other communities that have an interest in establishing their own library or hub; iii) Community library or hub facilitators being supported with comprehensive capacity building delivered by trained CSO partners so that they can make the libraries more effective spaces for learning and ensure implementation of effective COVID prevention measures; iv) Community mobilisation to encourage parents and caregivers to support learning in which a ‘do no harm’ approach is used to develop a standardised risk-informed community engagement approach; v) Working with and through CSOs as local partners for implement the key interventions.

The key principals of the BBL programme were: i) Consultation with children, parents, communities and Facilitators to hear their voices to decide programme work, including location for learning, modes of delivery, contents; ii)  Safety, well-being and protection of children, Facilitators and school staff are enablers to support children’s learning and therefore need to be prioritized; iii) Do no harm; iv) Focus on support to children, not schools; v) Equity.

The assumptions of the BBL Programme were: i) The situation will not get worse in terms of civil unrest; ii) it is not feasible to rely on Facilitators to deliver the teaching; iii) the support to ‘schools’ may be seen as not neutral. v) structured learning will have to be put (back) in place to enable children in learning and could be school or home-based and might take some time; v) The first few months are an interim period during which alternative interim learning opportunities were provided; vi) School reopening; vi) Civil Society Organizations and community structures will be ready and willing to cooperate with UNICEF and take up additional/new responsibilities.

### BBL Theory of Change

The BBL Theory of Change (TOC) was developed by UNICEF Myanmar Country Office (MCO) and reflects the objectives and modalities of the BBL. The BBL will be used to provide a framework to help visualize relationships between the different contributions towards the desired outcomes of the BBL.

The BBL TOC aligns with the JRF and MECS, which seeks to ensure that children and youth in Myanmar re-engage in quality and meaningful learning and training in safe protective environments, with a particular focus on the most vulnerable learners.  It articulates the logic towards achieving the desired outcomes which are: i) Continuity of expected quality learning including Life skills and Socio Emotional Learning (SEL) and wellbeing for children and adolescents attained; ii) Replicable Community Learning Resource Centre model tested and piloted.  This will be achieved through the three output areas being: i) Children aged between 3 to 18 years old have continued their learning using the opportunities provided to them; ii) Facilitators/educators/parents have acquired required capacity and motivation through the training and resources made available to them; iii) CSO partners and communities can support continuation and replication of community learning resource centres.

The theory of change follows the broad logic that the outputs will be achieved if, : i) Existing community libraries or learning hubs are supported with technical and material resources to support children’s learning; ii) Children, especially those aged between 5 and 15 years, can safely access equipped community libraries or learning hubs; iii) Families and communities are willing to take on responsibilities of motivating their children to access the education opportunities, and are provided with necessary technical support and resources to assist their children’s learning and wellbeing; iv) Facilitators are enabled to provide relevant, quality GEDSI sensitive education support focusing on literacy, numeracy and social emotional learning; v) CSO partners are supported to provide children, especially those who have experienced substantial learning discontinuity, with relevant learning and wellbeing support (including Open Learning, MHPSS, life skills, etc.) and their technical capacities to maintain quality of services are strengthened by dedicated partners; vi) Children will have the ability to continue their learning in a safe and protective environment, which will contribute to meaningful learning, improved learning outcomes and socio-emotional well-being.

The barriers and challenges are also highlighted in the TOC being: i) Disruption of learning due to Covid19 and military takeover; ii) Lack of alternative learning resources and opportunities; iii) Economic hardship (child labour); iv) Security risks; Resource constrained families/care givers (access to electricity/internet/smart phones etc.); v) Inadequate number of qualified facilitators; vi) Low capacity and motivation of facilitators; vii) Low technical capacity of CSO partners; viii) Deepening learning crisis; ix) Lack of multi-lingual resources; x) Non-existent/dysfunctional PTAs/VECs; xi) Low monitoring capacity and mechanisms; xii) Low parental education and community engagement to support education of children.

Not shown but also likely to be significant risks are: i) Climate & disaster vulnerability, including epidemics and pandemics that disrupt the development paths, and ii) Conflicts in regions targeted (linked to security risks).

Replicable Community Learning Resource Centre model tested and piloted.

Continuity of expected quality learning including Lifeskills and Socio Emotional Learning (SEL) and wellbeing for children and adolescents attained.

Outputs

Children aged between 3 to 18 years old have continued their learning using the opportunities provided to them.

CSO partners and communities can support continuation and replication of community learning resource centres.

Facilitators/educators/parents have acquired required capacity and motivation through the training and resources made available to them.

Outcomes

Upgrade community libraries or “hubs” to provide additional resources and learning support to communities, including reasonable adaptations to accommodate children with disabilities (CwDs), and COVID prevention measures.

Support facilitators to be able to utilize tools and strategies to help them teach children in their mother tongue (including Myanmar language)

Provide Teaching and Learning Materials (TLM) focused on literacy and numeracy, including audio-visual materials and tool kits to support all learners, including CwDs and those with low levels of literacy in the family (children 5-10 years)

Provide resource support, including materials on mental health, and Social Emotional Learning (SEL), and Prevention of Sexual Exploitation Abuse and Harassment (PSEAH)​.

Establish PTAs/VECs etc., for effective functioning of community learning resource centres.

Provide simple assistive devices (e.g. glasses, hearing aid, crutches etc.) to children with disabilities (CwDs), where feasible

Identify, recruit, and provide incentives to facilitators, in line with local agreements and those discussed and agreed through the Education cluster.

Set up remote learning options for NFPE (children 11-15 years old), including through low tech, audio-based and wherever possible digital options.

Activities/Inputs/Approaches

Provide of storybooks in relevant mother tongue languages (including Myanmar).

Mobilise parents and communities to support children’s learning. ​(5-10 years)

Develop and provide basic placement tools for formative assessment and help children develop individual learning plans, with suggested reading and learning materials, and monitor children's learning​ - including through Learning Passport (as appropriate). (5-10 years).

Identify and build the capacity of CSOs with Myanmar Literacy Resource Centre (MLRC) acting as a technical partner to provide NFPE support to facilitators.

Build capacity of local CSOs to support replication of community learning resource centre model.

Provide TLM for adolescents, including motivational items. ​

Provide transportation costs for learners, and/or nutritional snacks where appropriate.

Train CSO education partners on foundational literacy and numeracy assessment and pedagogy, with particular attention to multi-lingual contexts.

Establish robust but simple monitoring mechanisms to generate required quality evidence.

Assumptions

Barriers/Challenges/Constraints

The Theory of Change takes a holistic approach to tackle demand and supply barriers as well as operational and capacity constraints children and communities are facing to continue their learning.

Notes

Disruption of learning due to Covid19 and military takeover.

Lack of alternative learning resources and opportunities.

Economic hardship (child labour).

Inadequate number of qualified facilitators.

Low capacity and motivation of facilitators

Low technical capacity of CSO partners.

Deepening learning crisis.

Nonexistent/dysfunctional PTAs/VECs.

Low monitoring capacity and mechanisms.

Low parental education and community engagement to support education of children.

Communities are willing to take on increased responsibilities and leadership.

Children especially adolescents themselves are keen to strive for learning continuity.

Local market and overall fiduciary situation don’t deteriorate further.

CSO partners are willing to engage in a systematic capacity building process.

Technical partners e.g. MLRC/MBAPF, are ready to continue to support the implementing CSOs.

Facilitators training is delivered in a high quality, engaging manner with high participation.

CSOs continue to have access to the communities.

.

Security risks.

Resource constrained families/care givers (access to electricity/internet/smart phones etc.)

Lack of multi-lingual resources.

The BBL TOC does not detail assumptions and inputs.  External assumptions can be decisive for the programme performance if not realized. The external assumptions present a given critical context that needs to be fulfilled for the programme to take place as planned. The key external assumptions for the BBL logic may be determined based on the programme modalities and funding and are: i) Continued partner commitment towards funding programmes within Myanmar; ii) Continued ability to be able to operate within the regions selected; iii) CSO support towards improving children and adolescents’ rights to education and protection; iv) Stable and timely funding for BBL activities in general; v) Political status quo ensuring the current situation continues.

There are also causal assumptions, which present the underlying logic of the generation of the changes in the TOC. If these assumptions are not realized, this will have an impact on the BBL performance but contrary to external assumptions causal assumptions can be changed by the programme management, for instance, based on the result of monitoring and evaluations. The key causal assumptions include selected barriers and risks: i) Implementation through thematic sector and multi-sector programming and supported by cross-sectoral expertise will allow and integrated holistic approach that will generate overall changes (WASH/Education/peacebuilding); ii) Social behaviour, particularly that of parents, can be changed through evidence generation, policy dialogue, advocacy; iii) Community hubs can be changed to accommodate, enable, and support child rights and protection; iv) Multi-stakeholder partnering with communities, parents, academia and others including children and adolescents will increase BBL performance; iii) Economic hardship such as child labour can be overcome through advocacy and support; iv) Resource constrained families/care givers/Facilitators can have adequate access to electricity/internet/smart phones etc.; v) An adequate number of qualified facilitators/Facilitators can be identified, motivated and retained with support; vi) the provision of adequate teaching and learning materials.

### BBL Phased Approach, Results Framework and Beneficiaries

The BBL programme does is not a tested approached. It has evolved based on a necessary response to the advent of the twin crisis in Myanmar and in response to the needs of the children, particularly those most vulnerable. Therefore, it is anticipated that the results framework may is not be as precise and accurate as expected for programmes occurring in less volatile and evolving situation. UNICEF note that the results framework has evolved based upon: i) necessary responses to the fluid crisis situation occurring throughout Myanmar; ii) experiences from past programming within Myanmar and globally; iii) the changing funding and engagement of donors throughout the twin crisis; iv) the changing and evolving capacity of IP to operate within each target region.

The BBL programme can be divided into two distinct phases:

Phase I June 2021 to June 2023: Phase I was mainly funded through GPE funding and took place between June 2021 to June 2022. Contracts which commenced during this time are considered part of Phase I.  This phase was characterised by changes in operational modality to adjust to the ‘new norms’ including school closure from the Covid19 outbreak and the military coup.  For the most part this meant building on and further developing relationships with existing partners.  IP agreements were staggered throughout this period.  An Annual Work Plan (AWP) was used in place of a results framework (refer annex 12).  Some IP agreements had been signed before June 2021.

Phase II June 2022 – June 2023: Phase II was mainly funded through DFAT funding which was negotiated between November 2021 and April 2022 and includes contracts which commenced on or after June 2022.  This includes contacts for KBC SM, KMSS, and SF which commenced after June 2022.  This phase enabled a more structured approach based on operational modalities developed during phase I.  The results framework (annex 5) was developed for Phase II which added 46 townships and 6 new regions to the BBL programme.

The BBL results framework was finalised in April 2022 and is shown in Annex 5.  The results framework aligns with the TOC and provides a basis for monitoring progress towards programme outcomes.  The results framework gives a thematic breakdown of outcome areas and outputs and details the baseline, targets and means of verification (MoV) for each output.

The overall objective of the BBL is to provide targeted girls and boys, aged 3 to 18 years old, who have been out of learning and have not yet started or completed a primary level education, with catch up and remedial education opportunities within their community, with a particular focus on literacy, numeracy, life skills and Social and Emotional Learning.

Outcome 1: Provide girls and boys aged between 3 years old and 18 years old, whose learning has been disrupted, with access to education literacy, numeracy, and wellbeing support.

- Output 1.1 Girls and boys attend quality education in a protected, inclusive learning environment.

- Output 1.2 Girls and Boys have access to contextual, inclusive, quality teaching learning materials.

Objective 2: Ensure facilitators, CSO resource persons, and community members are well equipped with relevant capacities and receive appropriate technical support to deliver context responsive equity-focused, quality education and wellbeing support.

- Output 2.1 PTAs/ Community structures strengthened to implement community based strategic and sustainability plans towards improving learning of children.

- Output 2.2 Provide mental health and psychosocial support, counselling support to children and families impacted by conflict.

- Output 2.3 Girls and Boys access quality education and adolescent learning outcomes are improved through improved community volunteers well- being and teaching capacity.

The evaluation will be updated with the latest results from the BBL programme which will include a results framework for both phases of the BBL.

A total of 65 community libraries (CLs), hubs or community learning centres have been targeted with facility for up to 100. The BBL is premised on replicating Myanmar Book Aid and Preservation Foundation’s (MBAPF)’s ‘community library’ (CL) model as a community owned and managed learning opportunity for children. “Beneficiaries have been determined based on the outcome of the MBAPF which classified beneficiaries into two categories.  The first category of beneficiaries are those who are already benefiting from the libraries established by MBAPF.  Forty (40) out of 65 targeted CLs have been supported by MBAPF. Some of these CLs are located in urban and peri-urban communities with high population concentration. Hence, enrollment rate is high in these CLs compared to the rest. MBAPF uses two approaches to enroll learners; the first group of children is from the immediate members of the communities who own the libraries. The second group comprises of those children who are enrolled through leveraging local networks e.g., Youth Network, Early Childhood Care and Development (ECCD) network etc. The second set of beneficiaries are those who will benefit from enrolling in the remaining 25 CLs to be established or upgraded by the three Ips. Most of these CLs are in the rural communities with low population density. Therefore, the average beneficiaries’ number varies quite significantly e.g., 250 for MBAPF supported CLs and 45 for the other CLs, between these two groups of CLs. Keeping the above-mentioned details in mind, a minimum and maximum range is used to define the direct beneficiaries of this programme.”.

The results framework shown in annex 5 is therefore based on direct beneficiaries and total numbers for Phase II of the programme and are estimated owing to the uncertainty and fluidity of the situation throughout Myanmar.  UNICEF make the following estimations for direct and indirect beneficiaries:

- Direct beneficiaries (Children): The total number of children directly benefiting from CLs at the lower end of the spectrum is 12,550, whereas the upper bound total is 75,050.

- Indirect beneficiaries (Children): The total number of children indirectly benefiting from CLs at the lower end of the spectrum is 26,000, and the upper end total is 125,000.

- The total number of caregivers, parents and community members who will directly and indirectly benefit from this programme is 12,000 – 6,000 men and 6,000 women.

- The total number of facilitators in the community hubs directly targeted by this programme is 540 – including 275 women and 265 men.

- The total number of direct and indirect beneficiaries of the Bringing Back Learning programme at the lower end is 50,950 and the upper end target is 212,450.

The following page shows children and Facilitators affected by the BBL programme for the 2021 to 2022 year and so is only partially relevant to each of the results framework presented in Annex 5 and to the annual work plan presented in Annex 12.  Data is displayed by output area (refer annex 6 for data).

Children affected by the BBL Programme in 2022 by Output Area and IP

Facilitators Affected by the BBL Programme in 2022 by Output Area and IP

### BBL Geographic Coverage Phase I and II

Geographic areas were selected based on the following principals: i) The need for flexibility in the selection of geographical locations due to the rapidly changing security context and to ensure interventions do not overlap with other funds partners may receive; ii) The need to align with other programmes and ensuring BBL does not overlap with the areas covered by the GPE Accelerated Fund (AF) and other programmes; iii) Reaching the most marginalised children by focusing on selected, disadvantaged townships and states within government-controlled areas; iv) Focusing on selected locations/townships being applied under all outcome areas for increased efficiency, impact, coherence and value for money; v) Prioritizing locations where there were existing libraries or “hubs”; Working in areas where Implementation Partners (IP) CSOsheree existing operations.

For Phase I and II, the geographic focus was in 18 regions and 196 townships during 2022 (refer data annex 6).

For Phase II, the geographic focus has been in 6 regions and 46 townships throughout Myanmar.  Regions include: Sagaing (13 townships); Chin (4 townships); Ayeyarwardy (10 townships); Mandalay (2 townships); Magway (12 townships); Bago (6 townships) as depicted on the map below.

### BBL and Innovation

In accordance with UNICEF’s global education strategy, the BBL has been designed to foster and encourage innovation including: i) reaching the most disadvantaged through outreach, and reasonable adaptations to hubs to accommodate Children with Disability (CwDs) and improve COVID-19 prevention measures; ii) Using hubs to facilitate community outreach to neighbouring villages, in order to reach more children, and assist with replication and expansion in future programmes; iii) Providing capacity building in the development of individual learning plans, particularly for children requiring the most support; iv) Expanding open learning in multiple formats, and online and offline modalities, to better support CwDs and children in areas where parents may have low functional literacy in Myanmar language; v) Piloting of the new long-term open learning materials, and training focused on their content and use; vi) Mother tongue language (including Myanmar) acquisition activities have been offered to children up to 10 years old, rather than 8 years, in recognition of the 2 years of learning loss; vii) Building the capacity of CSOs to provide Non-formal Primary Education, utilising the one main CSO with this technical capacity to train other CSOs, so this can be scaled up; viii) setting up remote learning options for NFPE, including through low-tech, audio-based and, where possible, digital options.

States and Townships  covered under the BBL Phase II

Ayeyarwardy

10 townships

Bago

6 townships

Chin

4 townships

Magway

12 townships

Mandalay

2 townships

Sagaing

13 townships

Township 46

State/Region 6

### BBL Approach to Partnerships

Implementation partners are the recipients of funds and are responsible for strengthening and delivering education services within each area in accordance with each Implementation Partner (IP) agreement. Partners were identified by UNICEF based on: i) existing working relationship; ii) those who are already operating active community libraries or “hubs” and had supported additional innovations that enable these hubs to offer support and opportunities that are more structured, while remaining supplementary to and non-duplicative of formal systems; iii) Partners active in areas determined to be deprived (refer annex 7).

Partnership modalities follow: i)  ‘Guidance for Civil Society Organizations on Partnership with UNICEF’; In line with L2 emergency procedures, single source partnerships, with existing trusted partners, were utilised; Partnership Cooperation Arrangement (PCA) were used; Timely delivery of products assessed through field monitoring and review of reports as well as client satisfaction assessments; Consultation with communities; Participation in the Programme Coordination Committee (PCC);  Utilization of funds and accounting in line with UNICEF and Donor standards; Compliance and quality standards in accordance with UNICEF guidance on Prevent and Respond to Sexual Exploitation and Abuse and Sexual Harassment (PSEAH), child protection, prevention of fraud and the misappropriation of funding; Capacity strengthening of CSO partners; Other UNICEF regulations (guidelines) as relevant to such partnerships and detailed in the BBL proposal to DFAT (2022).

### BBL Budget, Progress and Funding

Phase I         Phase II

Sources of funding include Japan, Norway, Global Partnership for Education (GPE), Korea International Cooperation Agency (KOICA), Department of Foreign Affairs and Trade (DFAT) as AusAID, and Department for International Development (DFID).  Phase I was funded by GPE Covid and other partners.  The majority of the funds for Phase II were committed by DFAT from June 2022 to June 2023.  Funds have been committed to partners through the IP agreements with varying start and end dates for each partner as shown in the graph below (refer annex 6).  Partners issued contracts for Phase II were also operating during Phase I but these are not shown in the graph below (being KBC SM, KMSS, and SF).

BBL Implementation Partners Contract Start and End Date

Funds allocated to each partner through the IP contracts are shown in Annex 6 and in the figure below and totalling $12,536,770 USD equivalent. Four partners have been contracted the bulk of the funds being: Karuna Mission Social Solidarity KMSS, 2,816,200 USD, 22.5%; Succor Foundation, 2,391,441 USD, 19.1%; Myanmar Baptist Convention, 2,199,900 USD, 17.5%; Kachin Baptist Convention Kbc 996,999 USD, 8.0%.

BBL Implementation Partner and UNICEF financial contributions (USD equivalents),

The disbursement as a percentage of the original commitment from UNICEF is shown in the figure and table below as of last date confirmed received by each agency (refer annex 6).

Original DCT vs Percentage Disbursement as of Last Date Received

Implementation Partners DCT Amount, Funds Received Date and Disbursement,

| Outcome/Output | Original DCT Amount Kyat | Amount Reported Kyat | Original DCT amount Kyat | Amount Reported Kyat | First date Received | Last date Received | Outstanding Balance Kyat | Outstanding Balance USD | % Utalised as of Last Date Received |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kachin Baptist Convention Kbc | 2,116,040,866 | 1,004,818,040 | 998,132 | 473,971 | 08/02/2021 | 28/10/2022 | 1,111,222,826.00 | 524,162 | 47.5% |
| Kbc Social Mission | 3,232,811,550 | 2,629,855,661 | 1,524,911 | 1,240,498 | 20/05/2021 | 17/12/2022 | 602,955,889.00 | 284,413 | 81.3% |
| Metta Development Foundation | 2,489,889,053 | 1,901,309,206 | 1,174,476 | 896,844 | 12/07/2021 | 16/12/2022 | 588,579,847.12 | 277,632 | 76.4% |
| Myanmar Literacy Resource Centre Mlrc | 706,081,651 | 645,474,651 | 333,057 | 304,469 | 02/11/2021 | 27/11/2022 | 60,607,000.00 | 28,588 | 91.4% |
| Myanmar Baptist Convention | 3,144,787,931 | 2,897,582,109 | 1,483,391 | 1,366,784 | 26/11/2021 | 15/12/2022 | 247,205,822.00 | 116,607 | 92.1% |
| Terre Des Hommes Lausanne Myanmar | 316,316,017 | 0 | 149,206 | 0 | 21/09/2022 | 02/11/2022 | 316,316,017.00 | 149,206 | 0.0% |
| Rvwang Culture And Literature Society Of Myanmar | 139,831,000 | 0 | 65,958 | 0 | 14/11/2022 | 23/11/2022 | 139,831,000.00 | 65,958 | 0.0% |
| Karuna Mission Social Solidarity Kmss | 8,800,847,669.00 | 5,218,886,860.00 | 4,151,343 | 2,461,739 |  |  | 1,363,749,069.00 | 643,278 | 59.3% |
| Succor Foundation | 4,880,912,050.00 | 1,782,135,633.00 | 2,302,317 | 840,630 |  |  | 962,246,500.00 | 453,890 | 36.5% |
| Border Areas Development Association | 808,363,400.00 | 808,363,400.00 | 381,303 | 381,303 |  |  |  | 0 | 100.0% |
| Total | 12,145,758,068 | 9,079,039,667 | 5,729,131 | 4,282,566 |  |  | 3,066,718,401 | 2,543,733 | 74.8% |

# Purpose, Objectives and Scope of the Evaluation

## Evaluation Purpose, Objectives and Scope

The Terms of Reference (ToR) set out the purpose, objectives, methodology and operational modalities for an individual consultancy to evaluate the Bringing Back Learning programme to improve and strengthen its implementation (refer annex 1).

The purpose of the evaluation is defined by the nature of the BBL programme which has been to support learning for children in Myanmar during a period of crisis and in which development partners have limited interaction with the government.   The purpose is therefore to:

- Provide evidence on how the programme has progressed as envisaged initially;

- Determine whether the BBL processes have effectively contributed to its stated objectives and achieved the intended results during that period.

The justifications for the evaluation of the BBL are to learn and apply lessons and knowledge: i) To help inform future partner programming in Myanmar as defined in the JRF; ii) Towards programming in similar environments elsewhere globally; iii) Towards the possible expansion of the BBL following the conclusion of the current funding in June 2023; iv) As part of the well-established programme cycle of UNICEF which consists of preparation, programming, implementation, and monitoring and evaluation functions for all programmes so that UNICEF as an organisation can learn and apply lessons and other aspects, such as innovations and products, elsewhere nationally, throughout the region and globally, with a strong focus on learning in addition to accountability; v) For both donors, implementation partners and beneficiaries such as community representatives, Facilitators and facilitators, parents and caregivers may also learn which aspects of the BBL were beneficial and can be expanded and supported within their communities; vi) To evaluate the approach towards GEDSI which is mainstreamed throughout the BBL.

The specific objectives of the evaluation are to:

- understanding of achievements to date will be necessary to identify how processes contribute to the results;

- Provide secondary evidence on the Theory of Change, and the extent to which project objectives have been reached;

- The relevance of the various strategies in meeting the education needs of children in a dual crisis situation.

- To evaluate the approach towards GEDSI within the context of the twin crisis and deprivation experienced throughout Myanmar.

Considerations for the evaluation include:  i) the way each of the involved partners has fulfilled their part of the initiatives obligations; ii) how communities and partners have collaborated to reach the project’s objectives; iii) provide additional qualitative and quantitative evidence of fulfillment/nonfulfillment of the project’s objectives.

The primary audience for the evaluation will be the BBLs main Implementing Partners (IP) and stakeholders including donors of the project BBL.  Secondary audiences include those stakeholders who may receive information at UNICEF’s discretion such as information on lessons learned from the BBL evaluation.  Secondary audiences, may include: implementation partners and beneficiaries such as community representatives, Facilitators and facilitators, parents and caregivers.

The scope of the evaluation is to assess the Bringing Back Learning programme over the entire project period and across different funding, from June 2021 to June 2023 and will cover the geographic location of all IP agreements.  The scope will include interaction with the donors, UNICEF, the Implementation Partners and beneficiaries of the BBL.  Geographically the scope will include the 6 regions and 46 townships throughout Myanmar.  Four regions will be focal regions in which qualitative data will be directly obtained via enumerators.

The purpose, objectives and scope of the evaluation of the BLL are highlighted in the figure below.

Purpose, Scope and Objectives for the Evaluation of the BBL

BBL Evaluation Purpose

Timeline

June 2021 to June 2023

- provide evidence on how the programme has progressed as envisaged initially

- Determine whether the processes have effectively contributed to its stated objectives and achieved the intended results during that period.

Users

BBL programme’s main implementing partners and stakeholders including donors of the project BBL.

Considerations

Objectives

- The way each of the involved partners has fulfilled their part of the initiatives obligations.

- How communities and partners have collaborated to reach the project’s objectives.

- Provide additional qualitative and quantitative evidence of fulfillment/nonfulfillment of the project’s objectives.

.

- Identify how processes contribute to the results by understanding the achievements to date.

- Provide secondary evidence on the Theory of Change, and the extent to which project objectives have been reached.

- Determine the relevance of the various strategies in meeting the education needs of children in a dual crisis situation.

- To evaluate the approach towards GEDSI within the context of the twin crisis and deprivation experienced throughout Myanmar.

BBL Evaluation Scope

## Deviations from TOR

There main deviation from the TOR is in the methodology.  A perception survey has been suggested to obtain feedback from a wide range of stakeholders, in addition to the KII and case studies recommended in the TOR.

## Evaluation Questions

Evaluation questions are clustered under OECD/DAC criteria of relevance, effectiveness, efficiency, and sustainability (2009) and, 2010) and are derived from the TOR (refer annex 1).  Gender, Equality, Disability and Social Inclusion are often mainstreamed through evaluation questions but given the importance to the BBL these are given their own criteria (thematic area) for this evaluation.  Evaluation Questions are as follows.

Relevance:

- To what extent have the objectives and implementation strategies of the BBL programme been consistent with the requirements of the target groups and country needs?

- Have the implementation strategies been flexible to meet the different situations of communities based on location?

- Have the objectives and implementation strategies of the BBL programme been consistent with Joint Response Framework priorities, as well as partner and donor policies?

- Were the project areas chosen include states that were severely impacted by the conflict and crisis (thematic and geographical)?

Coherence:

- How well does BBL complement and fit with the community level activities to advocate home and community level learning among children, especially girls?

- Are there overlaps or inconsistencies between different programmes?

Efficiency:

- Was the budget defined adequately ex ante? Did the project budget make adequate provisions for all important goals, e.g., addressing gender and inclusion related specific objectives/activities?

- Were funds and activities delivered in a timely manner? If not, what were the bottlenecks encountered? How do banking issues affect financial disbursement?

- How efficiently have resources (human resources, time, expertise, supplies, transportation, funds etc.) been allocated and used to achieve the projects objectives?

- Did the results achieved justify the costs?

- Could the same results have been attained with fewer resources?

- To what extent do the output and outcomes offset the cost of the chosen inputs?

- How have beneficiaries and target groups been involved in decision making during implementation, and how has feedback been gathered?

- What is the level of involvement of the Community, parents/caregivers, community workers, natural community leaders, local organizations, Facilitators, community structures, and other stakeholders in the programme to support immediate provision of learning to children and strengthening community resilience for sustaining gender sensitive quality education services in crisis situation.

Effectiveness and Impact

- Has the project contributed to reengagement of children to learning at community level?

- How well has the BBL initiative addressed the learning crisis coming after COVID-19 and the military takeover period? What are the major factors that have led to achievement or non-achievement of the project’s objectives?

- Which of these factors are related to the Theory of Change, including the risks and assumptions associated with it, and which to the implementation of the project (such as procurement and co-financing)?

- Have the programme strategy and programme management been steering towards impact and set up in a way to allow achievement of expected outcomes and impacts?

- Was focus on impacts given during the implementation process?

- What are the key takeaways from the implemented strategies and processes

Sustainability

- Has a realistic and effective exit strategy been developed and applied?

- What evidence exists to suggest that the benefits of the project will be sustained or institutionalized and scaled in the future? Please base the analysis of this based on evidence around the financial, institutional, environmental, technical, and social sustainability.

- To what extent has BBL made progress toward localization as a sustainability strategy? What recommendation can the Consultant(s) give in terms of criteria for sustainability?

- What are the key lessons learnt which education sector overall can build on in designing similar projects in the future?

- What are recommendations for future projects, in regard to achieving the Joint Response Framework target

Gender, Equality, Disability and Social Inclusion

- To what extent was BBL able to understand the needs related to gender, disability, and other requirements for social inclusion? To what extent did the design and implementation of BBL respond to these needs? (Relevance)

- Have representatives from women’s groups, Organisations of Persons with Disabilities (OPDs), and other groups for marginalized communities been involved in understanding the needs and response of BBL? (Relevance)

- Did the project budget make adequate provisions for all important goals, e.g. addressing gender and inclusion related specific objectives/activities? (Efficiency)

- What factors of BBL have worked well to achieve results for girls, and what has worked less well? For children with disabilities? For children from ethnic groups? And other traditionally marginalized populations? (Effectiveness and Impact)

- What evidence exists that any gains toward GEDSI will be sustained? What recommendations are there for future projects for sustainable efforts toward GEDSI? (Sustainability)

# Evaluation Methodology

## Overview of Methodology and Approach

This section details the general methodology and approach to the evaluation, methods of quality assurance applied during the evaluation, sampling methodology and qualitative and quantitative data analysis methods.

The BBL Programme is challenging operating in a conflict environment during a pandemic. The evaluation team understands the objectives the BBL has set to support which is reflected in the evaluation methodology which will consider the limitations and constraints imposed thereupon.   Therefore, the approach combines robust technical expertise with a focus on utility. It is also sensitive to the need for flexibility, leaving room for adaptations during the evaluation depending on changing circumstances within Myanmar.

The evaluation will be guided by the UNICEF’s revised Evaluation Policy (2018), the United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation (2016), UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluation (2014), UNEG Ethical Guidelines for Evaluation (2020), UNICEF Procedure for Ethical Standards and Research, Evaluation and Data Collection and Analysis (2021) and UNICEF-Adapted UNEG Evaluation Report Standards (2017). Moreover, the evaluation will consider throughout issues of equity, gender equality and human rights. The evaluation will consider triangulation, sampling, ethical considerations (including, ethical clearance) and methodological limitations and mitigation measures.

Consistent with the United Nations (UN) Evaluation Norms and Standards (2016), the purpose of this evaluation will be formative and summative.  The formative component responds the evaluation questions which are clustered under Organisation for Economic Co-operation and Development (OECD) Development Assistance Committee (DAC),  and UNEG criteria of relevance, effectiveness, efficiency, and sustainability and Gender and Inclusion.  The summative attempts to draw conclusions as to the likely possibility of the BBL achieving its objective and outcomes.  The evaluation matrix presented below connects evaluation questions to data collection tools and methods employed through this evaluation and is thematically aligned with UNEG.

- Refer to Annex 9 for the BBL Perception Survey

- Refer to Annex 9 for the BBL Implementation Partners Questionnaire

- Refer to Annex 9 BBL Beneficiaries Questionnaire

As envisioned in the TOR (annex 1), a theory-based approach has been adopted.  The evaluation will employ non-experimental, mixed methods approach drawing on key project documents, the constructed Theory of Change and the monitoring framework for guidance.  This involves analysing the progress and impact of the BBL based on the TOCs that defines the programme.

To ensure that the BBL evaluation is an inclusive and constructive exercise, the evaluation team will apply an Appreciative Inquiry approach to data collection. The approach is premised on the belief that by focusing on positive results, the evaluation becomes a more constructive and inclusive exercise, promoting ownership of the evaluation’s findings, conclusions, and recommendations. The world of evaluation approaches and methods is large and confusing, with many overlapping definitions. For instance, ‘Appreciative Inquiry’ is referred to as a ‘data collection method’ in UNICEF’s RBM Handbook while the United Nations Evaluation Group (UNEG) refers to it as an ‘evaluation methodology.’ For the BBL Evaluation, the Appreciative Inquiry will be used as a qualitative data collection approach focusing on learning from successful experiences, exploring the BBL’s results and impacts, and identifying perceived key contributing factors. By focusing on strengths and opportunities identified through narratives or perceptions, the BBL evaluation will provide a positive outlook for future programming. This does not mean that challenges and problems are ignored. Rather, they will be addressed from a positive and learning perspective in line with the overall objective of the BBL in terms of learning.

An essential condition for the success of Appreciative Inquiry for data collection is the engagement of key stakeholders in the process of identifying: 1/ success stories, contributing factors, and challenges; 2/ positive and negative unexpected results; and 3/ how this can be used in future programming. These elements will be addressed through different data collection modalities, including Key Informant Interviews for identifying and unpacking success stories and unintended impacts of the BBL, a Perception Survey among key partners on the BBL’s success stories, document reviews and Focal Group Discussions (FGD). The tools are designed in such a way as to not only identify outcomes in terms of success stories but also to unpack the process to reach that point. To do this effectively the BBL evaluation will complement the Appreciative Inquiry approach with other tools for data analysis. As such, the major potential limitation might be limited participation of key stakeholders in the primary data collection, whether interviews, FGD, or the proposed online perception survey. To counter this limitation the BBL team will maintain a close dialogue with the UNICEF MCO.

For data analysis, Appreciative Inquiry will be complemented by a Realist Evaluation approach and mapping of causal paths.,  The realist evaluation approach sets out to explain what works, how, why, for whom, to what extent, and in what circumstances. It assumes that programme effectiveness will always be conditional, and it is oriented to improve understanding of the key contexts and mechanisms contributing to how and why programmes work. Key to Realist Evaluations is the assumption that nothing works everywhere or for everyone, and that context is critical for programme results. This requires a good understanding of the context, which will be ensured through a comprehensive context analysis to frame BBL results and performance against major events such as environmental impact and conflict. The robustness of the explanatory framework will be based on the data sources that will be triangulated. While a major strength of the realist evaluation approach for a theory-based evaluation is its recognition of assumptions which are context-based, drawing broader lessons-learned can be challenging as well as specific attribution of changes to the BBL. The BBL evaluation will therefore complement the realist evaluation with a contribution assessment to map out causal paths based on the narratives collected during the primary and secondary data collection.

The BBL team will ensure a human rights-based approach (HRBA) is applied throughout the evaluation process. The evaluation report will use gender sensitive, child-sensitive, and human rights-based language, including, when possible, data disaggregated by sex, age, and disability.

Recognizing the challenges of capturing the results of complex programmes implemented in complex environments with multiple actors’ activities, the data analysis will also be guided by an overall contribution assessment approach of the BBL’s contribution to the capacity of key BBL’s stakeholders, including Implementation Partners, Learning Centres, Facilitators, Parents and Students. The contributions will be identified through the mapping of causal paths based on the initial question “what are the main changes that can be observed, perceived, or have otherwise been noted.” Once answers to this key question have been identified during the comprehensive document review, interviews and the online perception survey, the follow-up question is “what has led to these changes.” During data analysis the most common changes will be identified as well as the most common causal paths. As the attribution/contribution assessment to a large degree are based on the narratives identified during the data collection, it should be noted that narratives are perceptions which are formed by many different impressions and narratives can become generalized among different stakeholder groups without necessarily be true stories of what happened. To the extent possible, the BBL will triangulate data and use both quantitative and qualitative data, as a means to overcome the challenge of narratives, respond the evaluation questions and make recommendations for the future of programming to help guide future planning and partnerships.

A mixed methods approach will be used to consolidate the findings from qualitative and quantitative evidence gathered from multiple sources.  The evaluation will utilise a focused, non-experimental design, utilising the following methods:

- Literature review of background documents and other relevant data including a literature review of implementation partner reports and BBL financing and design documents.

- Review of the external environment influencing BBL including other partner programmes and reports, the external environment and education sector data.

- Analysis of Secondary Data

- Financial Process and Cost-effectiveness analysis by reviewing results of a country survey containing questions on development and operational budget.

- Data on enrolments, learning outcomes, Facilitators trained, Learning centers equipped and other available data as resented in this report.

- Collection and analysis of primary data consisting of:

  - Discussions with key implementing partners and stakeholders as listed in Annex 2.

  - Site observation for enumerators visiting selected target townships.

  - Key Informant Interviews (KII) with UNICEF programme staff, BBL programme staff, Implementing partners, Facilitators and Parents who have participated in or benefited from the BBL programme.

  - Focal Group Discussions (FGD) of parents and Facilitators who have been beneficiaries of the BBL programme.

  - Case studies of children participating in the project.

  - Online Perception Survey for Implementing partners, donors and other stakeholders able to respond.

## Evaluation Matrix

To ensure consistency during the data collection and analysis, an Evaluation Matrix has been developed based on the key questions presented in the TOR. The evaluation matrix defines the evaluation questions, key criteria considerations, main sources of information, and data collection and analysis tools. The following are important criteria when considering the evaluation matrix:

- Some questions are summative in nature and also relate to conclusions and recommendations, but will be responded under the appropriate question heading in the final report.

- Child rights and protection of both children and adolescents are important aspects of most questions and will be considered as overarching criteria.

- Gender Equality and Empowerment of Women (GEEW) will be considered in all questions as appropriate.

- Equity, including people living with disabilities, will be considered in all questions as appropriate.

- Human Rights will be considered in all questions as appropriate.

- The context relating to implementation of the BBL programme and timeline of events occurring in Myanmar (annex 4) are important considerations relating to most questions.

- Variations in localities and groups of people are important considerations for most questions.

- Variations in approach of each implementation partner owing to differing modalities of operation will be considered for most questions.

.

Evaluation Matrix

| SN | Evaluation Questions/ | Key Criteria Considerations | Main Sources of Information | Main Data Collection / Analytical Methods |
| --- | --- | --- | --- | --- |
|  | RELEVANCE |  |  |  |
| Q1 | To what extent have the objectives and implementation strategies of the BBL programme been consistent with the requirements of the target groups and country needs? | - Timeline of events - Changing context owing to conflict - Variations in localities and groups and consideration for variations in programme design - Variations in approach of IP | - KII informants - Secondary data from IP and UNICEF - Programme reports - TOC and Monitoring Framework - Timeline of events | - KII, FGD, Case Studies - Secondary data analysis - Analysis of reports |
| Q2 | Have the implementation strategies been flexible to meet the different situations of communities based on location? | - Timeline of events - Changing context owing to conflict - Variations in localities and groups - Variations in approach of IP | - KII informants - TOC - Programme reports - Site observations | - KII, FGD, Case Studies - Secondary data analysis - Analysis of reports |
| Q3 | Have the objectives and implementation strategies of the BBL programme been consistent with Joint Response Framework priorities, as well as partner and donor policies? | - Variations in IP approach - Variations in donor policies | - Joint Response framework - Partner and donor policies - BBL IP agreements - TOC and Monitoring Framework | - Analysis of reports - KII with IP and Donors |
| Q4 | Were the project areas chosen include states that were severely impacted by the conflict and crisis (thematic and geographical)? | - Timeline of events - Variations in local context and consideration for variations in programme design | - BBL Target analysis - Timeline of events - IP and Donor KII informants - Programme Reports | - Analysis of data and timeline - KII with IP and Donors |
|  | COHERENCE |  |  |  |
| Q5 | How well does BBL complement and fit with the community level activities to advocate home and community level learning among children? | - Variations in local context - Variations in localities and groups | - KII, FGD informants - IP and Donor data on learning outcomes, participation - IP and Donor reports | - KII, FGD, Case Studies - Site observations - Analysis of data |
| Q6 | Are there overlaps or inconsistencies between different programmes? | - Variations in partner contribution to output areas in each locality | - IP and Donor reports - KII, FDG informants | - Programme mapping - KII with IP, beneficiaries and Donors |
|  | EFFICIENCY |  |  |  |
| Q7 | Was the budget defined adequately ex ante? Did the project budget make adequate provisions for all important goals, e.g., addressing gender and inclusion related specific objectives/activities? | - Timeline of events - Variations in local context - Variations in localities and groups | - IP and Donor reports - Budget spreadsheets - KII Donor, IP and beneficiaries - Data on participation and learning outcomes | - Unit cost analysis - Analysis of participation data - IP and Donor KII - Beneficiary KII |
| Q8 | Were funds and activities delivered in a timely manner? If not, what were the bottlenecks encountered? How do banking issues affect financial disbursement? | - Timeline events - Variations in local context - Variations in localities and groups | - IP and Donor reports - Budget spreadsheets - KII Donor, IP and beneficiaries | - Barrier and Bottleneck analysis - Process and budget analysis - IP and Donor KII - Beneficiary KII |
| Q9 | How efficiently have resources (human resources, time, expertise, supplies, transportation, funds etc.) been allocated and used to achieve the projects objectives? | - Timeline events - Variations in local context - Variations in localities and groups | - IP and Donor reports - Budget spreadsheets - KII Donor, IP and beneficiaries | - Barrier and Bottleneck analysis - Process and budget analysis - IP and Donor KII - Beneficiary KII - TOC and Monitoring Framework |
| Q10 | Did the results achieved justify the costs? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports | - Unit cost analysis - Beneficiary stories - Analysis of flow rates and learning outcomes |
| Q11 | Could the same results have been attained with fewer resources? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports | - Unit cost analysis - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework - Process analysis |
| Q12 | To what extent do the output and outcomes offset the cost of the chosen inputs? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports | - Unit cost analysis - Beneficiary stories - Analysis of flow rates and learning outcomes |
| Q13 | How have beneficiaries and target groups been involved in decision making during implementation, and how has feedback been gathered? | - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports | - Process analysis - IP and Donor KII - Beneficiary stories |
| Q14 | What is the level of involvement of the Community, parents/caregivers, community workers, natural community leaders, local organizations, Facilitators, community structures, and other stakeholders in the programme to support immediate provision of learning to children and strengthening community resilience for sustaining education services in crisis situation. | - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports | - Process analysis - IP and Donor KII - Beneficiary stories |
| Q15 | To what extent has the project contributed to reengagement of children to learning at community level? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports | - Unit cost analysis - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework |
| Q16 | How well has the BBL initiative addressed the learning crisis coming after COVID-19 and the military takeover period? What are the major factors that have led to achievement or non-achievement of the project’s objectives? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework |
|  | EFFECTIVENESS AND IMPACT |  |  |  |
| Q17 | Which of these factors are related to the Theory of Change, including the risks and assumptions associated with it, and which to the implementation of the project (such as procurement and co-financing)? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports | - Unit cost analysis - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework |
| Q18 | Have the programme strategy and programme management been steering towards impact and set up in a way to allow achievement of expected outcomes and impacts? | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework |
| Q19 | Was focus on impacts given during the implementation process? | - Timeline events - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework - Process Analysis - Donor and IP KII interviews |
| Q20 | What are the key takeaways from the implemented strategies and processes | - Timeline events - Variations in local context - Variations in localities and group - Variations in Donor strategies and policies | - KII for all groups - Donor and IP programme reports - Programme design documents | - TOC and Monitoring Framework - Process Analysis - Donor and IP KII interviews |
|  | SUSTAINABILITY |  |  |  |
| Q21 | Has a realistic and effective exit strategy been developed and applied? | - Variations in local context - Variations in localities and group - Variations in Donor strategies and policies - Variations in IP strategies | - KII for all groups - Donor and IP programme reports - Programme design documents | - TOC and Monitoring Framework - Process Analysis |
| Q22 | What evidence exists to suggest that the benefits of the project will be sustained or institutionalized and scaled in the future? Please base the analysis of this based on evidence around the financial, institutional, environmental, technical, and social sustainability. | - Timeline events - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework - Donor and IP KII interviews - Impact analysis |
| Q23 | To what extent has BBL made progress toward localization as a sustainability strategy? What recommendation can the Consultant(s) give in terms of criteria for sustainability? | - Timeline events - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework - Donor and IP KII interviews |
| Q24 | What are the key lessons learnt which education sector overall can build on in designing similar projects in the future? | - Timeline events - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports | - Donor and IP KII interviews - Process analysis - Impact analysis |
| Q25 | What are recommendations for future projects, in regard to achieving the Joint Response Framework target | - Timeline events - Variations in local context - Variations in localities and group | - Joint response framework - KII for all groups - Donor and IP programme reports - Programme design documents | - TOC and Monitoring Framework - Donor and IP KII interviews - Impact analysis |
|  | GENDER, EQUITY, DISABILITY, SOCIAL INCLUSION |  |  |  |
| Q26 | To what extent was BBL able to understand the needs related to gender, disability, and other requirements for social inclusion? To what extent did the design and implementation of BBL respond to these needs? (Relevance) | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework - Donor and IP KII interviews - Impact analysis |
| Q27 | Have representatives from women’s groups, Organisations of Persons with Disabilities (OPDs), and other groups for marginalized communities been involved in understanding the needs and response of BBL? (Relevance) | - Timeline events - Variations in local context - Variations in localities and group | - Participation and learning outcome data - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Analysis of flow rates and learning outcomes - TOC and Monitoring Framework - Donor and IP KII interviews - Process analysis |
| Q28 | Did the project budget make adequate provisions for all important goals, e.g. addressing gender and inclusion related specific objectives/activities? (Efficiency) | - Timeline events - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - Budget and unit cost analysis - TOC and Monitoring Framework - Process Analysis - Donor and IP KII interviews - Participation data analysis |
| Q29 | What factors of BBL have worked well to achieve results for girls, and what has worked less well? For children with disabilities? For children from ethnic groups? And other traditionally marginalized populations? (Effectiveness and Impact) | - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - TOC and Monitoring Framework - Process Analysis - Donor and IP KII interviews - Analysis of flow rates and learning outcomes |
| Q30 | What evidence exists that any gains toward GEDSI will be sustained? What recommendations are there for future projects for sustainable efforts toward GEDSI? (Sustainability) | - Variations in local context - Variations in localities and group | - KII for all groups - Donor and IP programme reports - Programme design documents | - Beneficiary stories - TOC and Monitoring Framework - Donor and IP KII interviews - Impact analysis |

## Literature review

The consultant shall conduct a review of the extensive documentation available on the BBL programme, including the programme design and concept documents, donor strategies and policies, implementation partner strategies and policies and information on the programme progress such as monthly reports. The literature review will also include, where possible, sources for comparative analysis, such as cost estimates and strategies employed from similar programmes operating in comparable environments.  The consultant will also review available information on Myanmar post February 2021, since the advent of the conflict and literature available on disadvantaged groups within Myanmar.  A sample of the literature reviewed is presented as references in this inception report.

## Secondary data

Secondary data analysis will be derived from BBL programme data.  Other data will also be used to contextualise the regions and townships such as the poverty index, estimated out of school children (OOSC), data from other programmes some of which may have concluded at the launching of the Coup, and government published data from the basic education sector or the inter censal population survey (2019).  These will be used to contextualise the BBL programme as well as to, where possible, provide comparative data on promotion rates, dropout rates, achievement rates (learning outcomes), poverty rates, rates of indigenous people and other disadvantaged groups.

| Indicator analysed | Disaggregation | Method of Display | Notes |
| --- | --- | --- | --- |
| Dropout | Gender, Disability, Ethnic Status, Township | Percentages | Uncertain whether individual child data will be made available and in what formats and conditions and the specific application when responding the evaluation questions. |
| Promotion | Gender, Disability, Ethnic Status, Township | Percentages |  |
| Graduation | Gender, Disability, Ethnic Status, Township | Percentages |  |

Programme data will be used to evaluate correlations between dropout, promotion and achievement rates and factors such as background information on students such as their gender, disability status, ethnic status.  These findings will be compared against government data from other sectors and programmes to help inform qualitative data derived from KII and FGD and respond the evaluation questions.

Given the small sample sizes of the BBL programme in each township, it is unlikely that analysis statistically significant.  Therefore, such as analysis correlating background information to learning outcomes or dropout rates will only be able to be provided to give guidance.  Given these limitations, statistical analysis and reporting will be restricted to reporting numbers and per cents as well as calculating indicators.

Given the context of conflict and upheaval, it is anticipated that secondary data may be sparse and may not be able to be disaggregated by desired indices such as those recommended in Sustainable Development Goal (SDG) 4.5.1.  In the absence of adequate data, qualitative data will be used to draw conclusions such as qualitative data concerning Children With Disabilities.

## Financial Process and Cost-effectiveness analysis

UNICEF and Implementation Partner budgets will be used to help determine allocations to different aspects of the BBL and under the differing contexts and partner modalities.  A financial process flow diagram will be developed to highlight the process for requesting and allocating funds. Bottlenecks and barriers will be examined through KII with UNICEF, Implementation partners and Donors.  The effectiveness of fund allocations will be examined through unit cost analysis.  Unit costs will be determined for learning centres supplied, Facilitators trained and children impacted by the programme and compared to student flow rates and retention to help determine effectiveness.  In doing so consideration should be given to intangible and tangible benefits which may span beyond the programme.  In the case of children as beneficiaries this may include inferences which can be drawn concerning the long-term impact on the family and community, in the case of training Facilitators this may include the capacity to reach more children upon completion of the BBL programme. Cost analysis will be contextual to the challenges evident in the timeline of events which took place during the programme (refer annex 4).

Judgements over reliability and applicability of the data will be made prior to making any comparative analytical conclusions and data may be disregarded altogether if deemed unreliable.  Any cost effectiveness or cost comparative judgements will be made with caveats and gaps identified.

## Primary data sources

### Key Informant Interviews (KII) and Focal Group Discussions (FGD)

Key informants will be interviewed to help bring in-depth knowledge and understanding to the evaluation.   There are several main categories of key informants to be interviewed.  These are:

- UNICEF: Representatives of UNICEF who have been involved the BBL programme.

- Donors: Representatives of Donors who have contributed finding to the BBL programme.

- Implementation Partners (IP): Who are the CSO and NGO responsible for implementing the BBL Programme.

- Beneficiaries:

  - Facilitators: Facilitators who have participated in the BBL programme in any way or who may have worked in Centres which have benefitted from the BBL Programme by any means.

  - Librarians or Learning Centre Heads: Who have presided over Learning Centres which have benefitted from the BBL Programme.

  - Parents, Caregivers and Community Members: Of students who have benefited from the BBL Programme directly or indirectly as described below.

  - Students: Who have participated in the BBL Programme directly, been taught by a teacher trained through the programme, or who have attended a Centre which may have benefited from the BBL Programme.

The following criteria and caveats apply to KII and FGD:

- The participation of parents, caregivers and students will be contingent upon ethical approval from UNICEF in accordance with UN guidelines for the evaluation of vulnerable groups of people.

- UNICEF, Donors and IP will be interviewed by the International Consultant via webchat.  In cases where the Donor or IP may not have reliable internet connectivity, a national consultant enumerator will conduct the interview in person at the site location.

- KII with Facilitators, principals or learning centre heads, parents/caregivers and Students will be conducted by Enumerators who will be recruited from the region so as to facilitate communication, to ensure cultural and social understanding and to help contextualise findings to the context in each region.  Enumerators may also conduct interviews with IP in cases where IP staff do not speak English or where internet connections are poor.

A combination of online and face-to-face primary data collection allows flexibility in the data collection. Follow-up interviews with respondents able to be contacted via webchat might take place if deemed necessary during the data analysis for clarity or to fill in any information gap. At the end of the first interviews, key informants will be asked whether the evaluation team might come with additional questions. The key informants’ position at that time will be noted and only key informants who have accepted follow-up interviews will be contacted in an eventual second interview.

The table below gives a summary of anticipated KII and FGD.  Please note Facilitators may also participate in KII with Centre Heads.

KII Number of KII / FGD Envisioned

| SN | KI category | Number of Regions | Number of Townships per Region | Number of Centres per Township | Number of KII / FGD Per Centre | Total KII / FGD | Total Person Time Allocated (Days) | Delivered By |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | UNICEF (KII) | NA | NA | NA | 4 KII | 4 | 1 day | Consultant |
| 2 | Donors (KII) | NA | NA | NA | 2 KII | 2 | 1/2 day | Consultant |
| 3 | Implementation Partners (IP) (KII) | NA | NA | NA | 12 KII | 12 | 3 Days | Consultant or Enumerator |
| 4 | Principals or Learning Centre Heads (KII) | 4 | 3 | 2 | 1 | 24 | 6 days | Enumerator |
| 5 | Facilitators (FGD) | 4 | 3 | 2 | 2 | 48 | 12 days | Enumerator |
| 6 | Parents or Caregivers, Community and Students (FGD) | 4 | 3 | 2 | 2 | 48 | 12 days | Enumerator |

### Key Informant Interview (KII) Tools

KII tools are in the form of semi-structured questionnaires which are in alignment with the evaluation matrix. The questionnaires are to be delivered by enumerators or the consultant dependent on capacity to engage.  KII may be conducted remotely via webchat or via face to face depending on capacity to engage directly.  Enumerators will be given orientation in the KII prior to being deployed.  The following KII semi structured questionnaires will be used:

- Tool 1: Implementation Partner (IP) KII: For use by enumerators and the consultant to capture primary data from Implementation Partners as a KII.

- Tool 2: Centre Head KII:  For use by enumerators to capture primary data from Centre Heads as a KII.

- Tool 3: Facilitators FGD: For use by enumerators to capture primary data from Facilitators as an FGD

- Tool 4: Parents, Caregiver, Community Members and Students FGD: For use by enumerators to capture primary data from Parents, Caregivers and Students as FGD.

- Tool 5: Donor and UNICEF KII.  For use by the consultant to capture primary data from Donors and UNICEF as KII.

- Tool 6: Case Study Form.  For use by IP, Centre Heads, Facilitators, Parents/guardians and students to document case studies.

- Tool 7: Site Observation Form. For use by enumerators to complete a site observation.

For those interviews conducted directly, either via webchat or via face-to-face interviews, the consultant or enumerator will have the opportunity to ask follow up questions in a semi-structured manner.  The consultant or enumerator will take notes of main points and may record interviews if respondents permit.  A full transcript of all interviews is not envisioned as the intention is to capture the relevant points.

For those participants who respond electronically, the consultant may send follow up questions via email if clarification or further information is required.

### Site Observation

Site observation will be undertaken to evaluate the quality of instruction, the effectiveness of the curriculum and the quality of learning centre facilities and pedagogical supply.  Site observation will not be conducted to an intensive level as enumerators are generally not qualified to undertake this level of evaluation unless specifically recruited for the purpose.  Instead, general remarks can be made on the quality and quantity of materials supplied and correlated against supply data.  General notes can be made concerning subject matter content; organisation; rapport; teaching methods; pedagogical materials; presentation; management; sensitivity; assistance to students; personal; and physical aspects of learning environment.

### Case Studies

Requests for case studies will be made to IP, Centre Heads and Facilitators and are included on Tools 1, 2 and 3.  Enumerators will ask each respondent to identify any child, Teacher, Centre Head or Centre which have experienced positive change throughout the BBL programme and as a result of the BBL programme interventions.  The case study form 6 will then be used to collect information concerning the case study.  Triangulation between sources will be attempted by interviewing and documenting responses from IP, Centre Heads, Facilitators, Parents/Guardians and Students where feasible.  As described above, appreciative inquiry will be used to enquire as to positive change.

### Perception Survey

A Perception survey of major stakeholders is proposed for assessment of BBL’s positioning, comparative advantages and outcomes.  This survey results will be incorporated into the final report.  The perception survey format is presented in Annex 8.

### Sampling of Primary Data

All Donors, IP and relevant UNICEF staff will undertake KII if available and if willing to participate.  The sampling of the remaining respondents for primary data collection is purposive, ensuring appropriate representation of the each respondent group and beneficiaries of each output area for the BBL programme .

Data for site selection is presented in Annex 7.  Site selection is based upon the following criteria: i) Ensuring diversity of IP and a high number of IP; ii) Diverse Ruralisation; iii) High Out of School Children OOSC; iv) High percentage coverage of townships; v) High level of Poverty; vi) Accessibility; vi) Acceptable security; vii) Ease of recruiting skilled enumerators.

Criteria such as urbanisation, location of IP and rates of OOSC were considerations in selecting regions.  Based on these criteria the evaluation team recommends site visits to: Bago East; Bago West; Chin; Kayin; Magway; Rakhine; Sagaing and for enumerators to visit (at least) 3 townships in each location and at least 2 learning centres in each township for a total of 6 site visits per region and 24 site visits for the evaluation.  The final decision concerning townships to visit in each region will be done in consultation with UNICEF.  IP and UNICEF will advise on which learning centres to visit within each township and will assist with logistical arrangements such as contacts and meeting dates/times.

An invitation letter is shown in Annex 9.  Once the individual invitees have responded positively to the invitation letter, the BBL evaluation team will follow-up to agree on an interview schedule as well as a written consent letter that will be shared through email; alternatively, verbal consent will be recorded.  Interviews may be transcribed in written form or recorded upon agreement of the respondent.

## Stratification

Stratification is not required for this evaluation.

## Data analysis

KII and FGD primary data may be analysed for positive or negative responses and noted during narration.  The frequency of positive and negative responses may be noted where required and referenced in the final report.  Judgements for inclusion of responses will be made based on frequency and: a) the extent to which qualitative and/or quantitative evidence generated from different sources point to the same conclusion, and b) the quality of the individual data and/or source of evidence as determined by reliability/completeness of response and capacity of the respondent to make an assessment or offer an opinion.

Triangulation will be used as a key tool for validating and analysing findings. Data triangulation will take two forms in the evaluation. The evaluation team will either validate findings from one data type or source with findings from other sources and thereby strengthening the reliability of the conclusions or will qualify them by divergent findings from other sources and thereby increasing the validity of conclusions.

Results from KII and FGD will be summarised as bullet points under the relevant thematic categories (relevance, coherency, efficiency etc.).  It is likely that categorisation under each evaluation question will result in too much duplication and result in important relationships being missed.

For the data analysis, the evaluation will use a set of standard analysis tools and frameworks, including:

- Results analysis; A systematic analysis of the different components and implementation strategies’ contribution to the BBL’s purpose and objectives.

- Analysis of the BBL programme coherence; The challenging, heterogeneous, and dynamic context for the operations makes it particularly critical that the implementation strategies and initiatives are coherent.

- Gender sensitivity and vulnerable person responsiveness, and transformative analysis; An overall assessment of the gender sensitivity and responsiveness of the BBL programme design, programming, implementation, and monitoring and evaluation will be carried out. Given the context, the assessment will give special attention to protection issues concerning vulnerable persons.

- Equity with special attention to equal access to basic social services will be assessed with special attention to different vulnerability factors: disability, religion, indigenous peoples, and poverty and for different age groups of children and adolescents. When disaggregated data cannot be obtained evaluation will consider these limitations as important evaluation information per se.

- Assumption analysis will be applied through a systematic analysis of the assumptions and hypothesis presented in the overall theory of change. Special attention will be given to the dynamic and diversity of the perceptions among key stakeholders regarding the assumptions.

- Process analysis will be applied to analyse the impact of the BBL programme’s processes on anticipated outcomes through each outcome area of the programme, and taking into account the need to address challenges and a changing political and social environment.

The distinction between findings, conclusions, lessons-learned, and recommendations will be carefully observed, and reflected in the structure of the evaluation report.

Secondary quantitative data will be disaggregated by sex, age, disability, states, etc. where relevant and feasible.

## Report Templates

The final report template is presented in Annex 10 and is subject to modification in accordance with the recommendations of UNICEF.

## Data Protection Protocol and Evaluation Ethics

Protecting personal data is essential in any evaluation to respect dignity and ensure security of all stakeholders involved and to protect the identities of persons. Given the current status of conflict throughout Myanmar, confidentiality of personal data will be especially important for this evaluation.

The Evaluation team commits to maintain confidentiality of sources of data obtained during primary data collection. In coordination with UNICEF, the evaluation team will ensure that the evaluation complies with local and national data protection and privacy laws. Throughout, the evaluation, primary and secondary data collected will be recorded systematically within an evaluation assessment framework. This comprehensive data source will then be used to validate and verify findings as they emerge against the evaluation questions and indicators. The identity of informants for primary data collection will be anonymized in the evaluation assessment framework and only the evaluation team and UNICEF will be aware of the names. During the evaluation process all primary data collected will be kept in a password protected shared drive that only the evaluation team and UNICEF have access to. All data analysis files and all files with raw data from the primary data collection will be the property of UNICEF.

The evaluation team commits to the obligation not to publish or otherwise communicate to third parties, through any medium whatsoever, any information on the participants in the evaluation consultations. In their communication with all stakeholders, the evaluation team will explain the commitments to confidentiality and anonymity in a transparent way in order for stakeholders to understand the data protection protocol and based on that, they can decide whether to participate or not in the evaluation.

The Evaluation team will strictly follow the UNEG ethical guidelines and the UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis throughout the evaluation process. The evaluation team will ensure that the principles of integrity, independence and impartiality and accuracy, completeness and reliability are respected. Hence, the Evaluation team will prevent any form of potential conflict of interest and ensure that the evaluation is conducted in a transparent and accountable manner. The Evaluation process, including quality assurance procedures will ensure that evidence in the Evaluation cannot be traced back to any individual informant.

The main ethical issues anticipated in the Evaluation relate to the stakeholders whom the evaluators will interview and engage with, and involve considerations of confidentiality, data protection, protecting vulnerable respondents and particularly those in conflict environments and ensure that the evaluation process avoids causing harm. In specific terms, the evaluators will adhere to ethical principles for evaluations which include:

- Principle 1 Informed consent: The Evaluation team will inform participants on how information and data obtained will be used, processed, shared, disposed of, prior to obtaining consent. First, informed consent of stakeholders will always be sought. Stakeholders will be informed of the purpose of data collection and will be offered the opportunity to withdraw from the process at any time. Second, all data will be collected under the guarantee of confidentiality. If it is decided that the Evaluation team wants to attribute evidence to a particular stakeholder, the Evaluation team leader will seek their written consent first; alternatively, verbal consent will be recorded (see Annex 9 for Informed Consent Forms).

- Principle 2 Avoiding harm: Evaluation team will ensure that the basic human rights of individuals and groups with whom they interact, as well as their health and safety (risks related to Covid-19, for example) are protected. The Evaluation team will ensure that all risks are discussed with UNICEF and that mitigation plans are drawn up prior to any data collection.

- Principle 3 Treatment of participants: The Evaluation team is aware of differences in culture, local customs, religious beliefs and practices, personal interaction and gender roles, disability, age, and ethnicity, and will be mindful of the potential implications of these differences when planning, carrying out and reporting on the evaluation.

- Principle 4 Voluntary participation: Participation in the evaluation should be voluntary and free from external pressure. Information should not be withheld from prospective participants that might affect their willingness to participate. All participants have a right to withdraw from the evaluation and withdraw any data concerning them at any point without fear of penalty.

- Principle 5 Ensuring confidentiality: The evaluator will respect people’s right to provide information in confidence and will ensure that information cannot be traced to its source if the latter is an individual.

- Principle 6 Independence and impartiality of the Evaluation team: While a participatory process will lead the consultant’s engagement with UNICEF staff and other stakeholders, impartiality and independence will be strictly maintained.

As for COVID-19 protocols, the first rule will be to follow all UNICEF and country’s COVID-19 protocols, applying to all team members. Beyond this, the evaluation team has included an extra layer of COVID-19 protocols aimed at protecting team members and evaluation stakeholders. This includes the following:

- All team members, who are fully vaccinated, will abide to all COVID-19 protocols in place in the Myanmar.

- All team members will take their temperatures every morning and evening while in the field.

- Any team member with any symptoms consistent with being COVID-19 positive will isolate and test, and will not engage with other team members, or stakeholders, until a negative test result is secured.

- Distancing and masking rules will be applied to any group meetings/discussions as required by UNICEF and the Government of the Myanmar.

## Limitations and Risk to the Evaluation

The following limitations and risks have been identified at inception phase:

Risks, Limitations, and Mitigation of the Evaluation

| Risk | Risk rating | Mitigation |
| --- | --- | --- |
| The evaluation is subject to uncertainty because of emergencies including COVID-19, disasters, Conflict and instability | Medium | The Evaluation Team believes that the evaluation approach and methodology outlined in this inception report is sufficiently flexible to ensure that primary data collection can be carried out. It is expected that the primary data collection will consist of a mix of face-to-face and online interviews and workshops. The Evaluation Team has positive experience in using online methods for data collection. The Evaluation Team will work closely with the UNICEF CO to discuss interview logistics, including the choice of whether to conduct online interviews or face to face interviews in regions which may be challenging but in which primary data is sought. |
| Key stakeholders for the full evaluation period are not available or no longer in position. The evaluation covers a time-frame during which significant disruptions have occurred and staff may have rotated into other positions, which may affect the possibility of obtaining views of those who were in place in the earlier period. | Medium | The evaluation team will seek to obtain contact details and introductions from UNICEF to key staff and other stakeholders who have moved onto other positions. |
| Key stakeholders might be overwhelmed by evaluation demands and be less willing to respond, considering the local disruptions which may be occurring. | Medium | Overall, the evaluation team will coordinate with the UNICEF CO to ensure that the evaluation does not lead to overloading specific informants with information requests. Continuous updates with the UNICEF CO will help ensure proper coordination. |
| Lack of timely, disaggregated, and high-quality data that can be used in the evaluation owing to the challenging nature of the work and environment. | Medium to High | During the inception phase, the Evaluation team and UNICEF have already made efforts to put together a comprehensive e-library. The evaluation team will communicate with the UNICEF CO regularly as gaps in documentation and data are realised. The team will also follow-up with country-level stakeholders to understand discrepancies and gaps in data. Triangulation can mitigate some of the data availability challenges. |
| There is a risk of Research Bias owing to the small size of the evaluation team. | Low | This risk is mitigated by several factors: a) the experience of the evaluation team; b) the quality assurance process; c) the process of triangulation; d) the review process. |
| Many of the evaluation regions have distinct regional languages and it is likely that many of the documents will be in the local Myanmar language and respondents may communicate in the local language. | High | To counter this the evaluation team will derive enumerators from local regions who speak the local dialect/language and the national language. The lead national consultant is fluent in English and Myanmar. |
| Disaggregated data may not be available at the local level, or the quality of available data may not be satisfactory | High | Limitations will be noted in the analysis of data. All efforts will be made to use proxy data or implementing partner data if available to compensate and extrapolate for data gaps. All assumptions and exceptions will be noted when presenting analysis and drawing conclusions. |

# Evaluation Workplan and Process

## Workplan

The timings in the workplan have been adjusted from the TOR to account for the start of the assignment. The schedule otherwise follows the timings outlined in the consultant’s proposal with the project carried out in four broad phases:

- Inception and desk review phase: During this phase, UNICEF and the consultant have held discussions together to further define the purpose and scope of the review to ensure alignment with the objectives, and to finalise the primary data collection strategy. The consultant has conducted a desk review of literature on the BBL Programme which has informed the further development of the approach and methodology for the evaluation, including the development of the tools for conducting primary data collection, stakeholder mapping and identification of key informants, the evaluation matrix, and a detailed plan for data collection, including selection of programme sites and beneficiaries. The methodology and instruments have been shared with UNICEF for confirmation and input.

- Primary Data collection (PDC) phase: The consultant will further review the desk of available literature and data pertaining to BBL Programme.  The team will interview BBL Programme stakeholders as detailed in the inception report and visit each selected township and centre over the period of approximately 5 weeks.  All data collection exercises including primary qualitative as well as obtaining secondary quantitative, will be completed.   The consultant will be quality assuring data as it is produced from interviews to ensure completeness and consistency.

- Analysis and Reporting phase: The consultant will consolidate the analysis from the previous phases into a single, consolidated report responding to the evaluation questions, presenting findings and recommendations and providing synthesis responses to evaluation objectives. UNICEF and selected stakeholders will provide feedback on the draft report to help produce the final report.

## Deliverables

The evaluation will take place from January 2023 to June 2023. Deliverables and dates are detailed in the table below.  The schedule will be contingent on ensuring sites can be visited before the water festival (Thingyan).  If some site visits are delayed to after the holiday period then it will have a cascading impact on the dates of later deliverables.

Fees (payment schedule) allocated to each deliverable

| SN | Phase | Deliverables | Date |
| --- | --- | --- | --- |
| 1 | Inception | Draft Inception Report (including site selection) | 28/02/2023 |
| 2 | Inception | Comments Matrix from UNICEF Evaluation Taskforce | 06/03/2023 |
| 3 | Inception | Final Inception Report | 09/03/2023 |
| 4 | Inception | PowerPoint for reference group (in English and Myanmar) Comments matrix with response to comments | 27/02/2023 |
| 5 | PDC | Preliminary evaluation findings report (incl. desk review and literature search) | 14/04/2023 |
| 6 | PDC | PowerPoint presentation concerning preliminary findings (in English and Myanmar) |  |
| 7 | Reporting | Draft Report | 19/05/2023 |
| 8 | Reporting | Evaluation Commenting Matrix from UNICEF Evaluation Taskforce | 26/05/2023 |
| 9 | Reporting | Second draft report and executive summary | 02/06/2023 |
| 10 | Reporting | Powerpoint presentation in English and Myanmar | 02/06/2023 |
| 11 | Reporting | Evaluation commenting matrix 2 from the workshop and partners | 09/06/2023 |
| 12 | Reporting | Final Evaluation Report executive summary, infographic and other materials (in English and Myanmar). | 16/06/2023 |

## Schedule of Work

The schedule of work is presented in the table on the next page.  The schedule will be contingent on ensuring sites can be visited before the water festival (Thingyan).  If some site visits are delayed to after the holiday period then it will have a cascading impact on the dates of later deliverables.

## Team and Roles and Responsibilities

The evaluation team’s composition and roles and responsibilities are detailed below:

- An independent, external consultant, James Shoobridge, will conduct the evaluation.  His responsibilities include:

  - Plan and manage implementation of the evaluation, with responsibility for timely delivery of high-quality deliverables in line with the TOR;

  - Task management and coordination of the data collection phase;

  - Communication with UNICEF on the scope of work, progress and feedback on deliverables.

- A National Consultant, Dr. Tun Win, will coordinate the National Enumerators during the data collection phase and will translate all required materials into the Myanmar language and aid in quality assurance of the deliverables.  National Enumerators will be recruited in each region to be included for site visits.

- The UNICEF Evaluation Taskforce is responsible for the overall management of the evaluation and quality assurance of the deliverables. The UNICEF Evaluation Taskforce will act as the primary liaison between the consultant and the other stakeholders and provide logistical assistance and advice as required. The UNICEF Evaluation taskforce will provide quality assurance and feedback on all deliverables.  Members of the evaluation Taskforce are included in Annex 3 and are listed below:

Members of the Evaluation Taskforce

| SN | Name | Organisation | Position and Role in BBL | Email |
| --- | --- | --- | --- | --- |
| 1 | Shweta Sandilya | UNICEF | Education Manager BBL | ssandilya@unicef.org |
| 2 | Nicole Starkey | UNICEF | Education Specialist | nstarkey@unicef.org |
| 3 | Hyunjung Lee (Amelia) | UNICEF | Education Officer | hyunlee@unicef.org |
| 4 | Aye Myint Than Htay (AMTH) | UNICEF | Education Specialist | amthtay@unicef.org |
| 5 | Kyaw Lwin Latt (KLL) | UNICEF | Education Officer - data & monitoring, Facilitators' resource | kllatt@unicef.org |
| 6 | Malar San (Malar) | UNICEF | Education Officer - MHPSS, RH, equity | msan@unicef.org |
| 7 | Aye Aye Yee (Aye Aye) | UNICEF | Education Specialist - ECE | aayee@unicef.org |
| 8 | Myo Wai (Myo Myo) | UNICEF | Education Officer - Open Learning (OL) materials, Inclusive education | mwai@unicef.org |
| 9 | Khin Mon Nyein (Mon Mon) | UNICEF | Education Specialist - NFPE | knyein@unicef.org |

BBL Evaluation Schedule of Work

| SN | Phase | Activity | Deliverable / Output | Resource | Contingent Notes | Date | Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Inception | Draft Inception Report and Literature Review | Draft Inception Report | Consultant | None | 13/01/2023 | 13/02/2023 |
| 2 | Inception | Comments Matrix from UNICEF Evaluation Taskforce | Comments Matrix from UNICEF Evaluation Taskforce | UNICEF |  | 20/02/2023 | 20/02/2023 |
| 3 | Inception | Final Inception Report | Final Inception Report | Consultant |  | 22/02/2023 | 22/02/2023 |
| 4 | Inception | PowerPoint for reference group (in English and Myanmar) Comments matrix with response to comments | PowerPoint for reference group (in English and Myanmar) Comments matrix with response to comments | Consultant |  | 27/02/2023 | 27/02/2023 |
|  | PDC | Recruit and mobilize enumerators |  | Consultant | Approval of site selection | 13/01/2023 | 26/02/2023 |
|  | PDC | Orientate Enumerators |  | Consultant Enumerators | Mobilization of enumerators complete |  | 01/03/2023 |
|  | PDC | Enumeration in four regions | KII, FGD records, enumeration matrix completed | Consultant Enumerators | Orientation enumerators | 02/03/2023 | 31/03/2023 |
| 5 | PDC | Preliminary evaluation findings report (incl. desk review and literature search) | Preliminary evaluation findings report (incl. desk review and literature search) | Consultant |  | 01/04/2023 | 14/04/2023 |
| 6 | PDC | PowerPoint presentation concerning preliminary findings (in English and Myanmar) | PowerPoint presentation concerning preliminary findings (in English and Myanmar) | Consultant |  |  | 21/04/2023 |
|  | PDC | Feedback from draft findings | Input from presentation draft findings | UNICEF |  | 21/04/2023 | 28/04/2023 |
| 7 | Reporting | Draft Report | Draft Report | Consultant |  | 21/05/2023 | 19/05/2023 |
| 8 | Reporting | Evaluation Commenting Matrix from UNICEF Evaluation Taskforce | Evaluation Commenting Matrix from UNICEF Evaluation Taskforce | UNICEF |  | 19/05/2023 | 26/05/2023 |
| 9 | Reporting | Second draft report and executive summary (exclusive gender analysis) | Second draft report and executive summary and gender analysis report | Consultant |  | 19/05/2023 | 02/06/2023 |
| 10 | Reporting | Powerpoint presentation in English and Myanmar | Powerpoint presentation in English and Myanmar | Consultant |  | 25/05/2023 | 02/06/2023 |
| 11 | Reporting | Evaluation commenting matrix 2 from the workshop and partners | Evaluation commenting matrix 2 from the workshop and partners | UNICEF |  | 02/06/2023 | 09/06/2023 |
| 12 | Reporting | Final Evaluation Report executive summary, gender analysis, infographic and other materials (in English and Myanmar). | Final Evaluation Report executive summary, gender analysis, infographic and other materials (in English and Myanmar). | Consultant |  | 09/06/2023 | 16/06/2023 |

## Quality Assurance

Quality Assurance will be undertaken using the following methods.

### Comprehensive Review Process

The Quality Assurance System (QAS) will intervene step-by-step providing the most appropriate type of quality support according to the phase of the process and the activity taking place and in accordance with the standards upon which the evaluation is based (refer section ‘Overview of Methodology’).

As noted under the section ‘Team Roles and Responsibilities’, quality assurance of products will occur at each phase of deliverable.  The BBL Evaluation Taskforce lead by UNICEF is responsible for overall quality assurance of the deliverables.  The Consultant, in conjunction with the BBL Evaluation Taskforce will ensure the quality of the evaluation process. Collectively they will provide quality assurance by, providing inputs to the development of the Terms of Reference and providing feedback on draft deliverables such as the draft evaluation report and providing guidance on the appropriate actions to be taken in response to evaluation recommendations.

The following evaluation protocols will help ensure the quality of data:

- Write-up of all interview notes and analysis of findings;

- Triangulation of findings against different sources, both qualitative and quantitative.

- Adherence to UNEG norms and standards and with UNICEF Evaluation Policy for development evaluation;

- Process organisation within the evaluation team and applied methodologies according to best professional standards;

- Timeliness and reliability of service delivery;

- Ongoing communication through regular meetings with the BBL Evaluation Taskforce

- Robustness of the methodological process illustrated in the inception report and then implemented during the field and reporting phase, and, thus, robustness of the analysis and relevant findings;

- Completeness of the study in response to the needs of the BBL Programme.

Triangulation will also be important to help ensure the quality and adequacy of data reflecting the evidence and their contextual interpretation. As such, data will be validated through triangulation in a number of ways.

- Asking similar questions to multiple respondents in each field site;

- Asking the same questions in multiple field sites;

- Integrating qualitative and quantitative findings;

- Evaluation protocol.

For interviews, data will be triangulated, where feasible, by comparing responses to questions from multiple sources and comparing results from interviews from different sources.

## Communication of Findings

The main communication modalities to be employed will be via email and webchat.  The consultant will attempt to respond to all emails within 24 hours.  When required the team will undertake webchat calls to clarify issues and align schedules.  Regular meetings are scheduled with the BBL Evaluation Taskforce to facilitate communication.

## Support required from UNICEF

The BBL Evaluation team are grateful for the support already provided by the MCO and BBL Evaluation Taskforce during the inception phase. For the Primary Data Collection (PDC) and Reporting, the following support will be required:

  - Facilitation of ethical approval.

  - Provide an update to the evaluation Results Framework (annex 5).

  - Support identification and contacts with key informants, including detailed contact information and introduction.

  - Support identification and contact details for informants to participate in the possible perception survey.

  - Support identification and access to additional documentation and data required for the BBL Evaluation. This will happen as part of the constant dialogue between the BBL Evaluation team and the BBL Evaluation Taskforce manager.

  - Provide feedback and quality assurance as part of the BBL Evaluation Taskforce.

  - Schedule, invite participants, and provide the meeting platform for the planned BBL evaluation meetings.

Terms of Reference

International Consultant to undertake the Evaluation of Bring Back Learning Programme in Myanmar

## Scope of Work:

The Terms of Reference (ToR) set out the purpose, objectives, methodology and operational modalities for an individual consultancy to evaluate the Bringing Back Learning programme to improve and strengthen its implementation. This evaluation will assess the Bringing Back Learning programme over the entire project period and across different funding, from June 2021 to June 2023. The evaluation shall provide evidence on how the programme has progressed as envisaged initially, whether its processes have effectively contributed to its stated objectives and achieved the intended results during that period. Because an understanding of achievements to date will be necessary to identify how processes contribute to the results. The process evaluation will provide secondary evidence on the Theory of Change, and the extent to which project objectives have been reached. The focus will be on the relevance of the various strategies in meeting the education needs of children in a dual crisis situation.

The consultant hired under this ToR will take a closer look at the processes which have led to the fulfillment/non- fulfillment of the programme objectives. He/she will particularly consider (1) the way each of the involved partners has fulfilled their part of the initiatives obligations as well as (2) how communities and partners have collaborated to reach the project’s objectives. Further, the consultant will (3) provide additional qualitative and quantitative evidence of fulfillment/nonfulfillment of the project’s objectives.

The primary audiences for this process evaluation are the project’s main implementing partners and stakeholders including donors of the project BBL.

## Key Questions:

Based on the ToC, the consultant hired under these ToR will take a closer look at the processes which have led to fulfillment/non-fulfilment of the project’s objectives. He/she will particularly consider (1) the way each of the involved partners has fulfilled their part of the project’s obligations as well as (2) how communities and partners have collaborated to reach the project’s objectives. Further, the consultant will (3) provide quantitative and qualitative evidence of fulfillment/nonfulfillment of the project’s objectives. The evaluation will comprise of mixed-methods/process-focused part and will be based on the OECD/DAC criteria. Following these criteria, the evaluation will explore the relevance, effectiveness, efficiency, impact, and sustainability of the project. Within the criteria, there will also be an emphasis on gender equality, disability, and other types of social inclusion (GEDSI). Questions related to GEDSI are outlined separately below to add to this emphasis. The process evaluation focuses, as the name implies, on the criteria of effectiveness and efficiency. The goal of the proposed qualitative evaluation is to embed these results into the broader context of the project. For each of the OECD/DAC criteria, key questions are defined below. These key questions define the results that the evaluator is expected to provide. There is no baseline for this programme so this process evaluation will provide evidence for further programming in Myanmar within the criteria of relevance, efficiency, and sustainability, while taking into account (and evaluating from a broader perspective) the provided results on effectiveness and potentially (early) impact. The evaluator is invited to propose (additional) sub-questions to these criteria as he/she sees fit.

Relevance:

- To what extent have the objectives and implementation strategies of the BBL programme been consistent with the requirements of the target groups and country needs?

- Have the implementation strategies been flexible to meet the different situations of communities based on location?

- Have the objectives and implementation strategies of the BBL programme been consistent with Joint Response Framework priorities, as well as partner and donor policies?

- Were the project areas chosen include states that were severely impacted by the conflict and crisis (thematic and geographical)?

Coherence:

- How well does BBL complement and fit with the community level activities to advocate home and community level learning among children?

- Are there overlaps or inconsistencies between different programmes?

Efficiency:

- Was the budget defined adequately ex ante? Did the project budget make adequate provisions for all important goals, e.g., addressing gender and inclusion related specific objectives/activities?

- Were funds and activities delivered in a timely manner? If not, what were the bottlenecks encountered? How do banking issues affect financial disbursement?

- How efficiently have resources (human resources, time, expertise, supplies, transportation, funds etc.) been allocated and used to achieve the projects objectives?

- Did the results achieved justify the costs?

- Could the same results have been attained with fewer resources?

- To what extent do the output and outcomes offset the cost of the chosen inputs?

- How have beneficiaries and target groups been involved in decision making during implementation, and how has feedback been gathered?

- What is the level of involvement of the Community, parents/caregivers, community workers, natural community leaders, local organizations, Facilitators, community structures, and other stakeholders in the programme to support immediate provision of learning to children and strengthening community resilience for sustaining education services in crisis situation.

Effectiveness and Impact

- Has the project contributed to reengagement of children to learning at community level?

- How well has the BBL initiative addressed the learning crisis coming after COVID-19 and the military takeover period? What are the major factors that have led to achievement or non-achievement of the project’s objectives?

- Which of these factors are related to the Theory of Change, including the risks and assumptions associated with it, and which to the implementation of the project (such as procurement and co-financing)?

- Have the programme strategy and programme management been steering towards impact and set up in a way to allow achievement of expected outcomes and impacts?

- Was focus on impacts given during the implementation process?

- What are the key takeaways from the implemented strategies and processes

Sustainability

- Has a realistic and effective exit strategy been developed and applied?

- What evidence exists to suggest that the benefits of the project will be sustained or institutionalized and scaled in the future? Please base the analysis of this based on evidence around the financial, institutional, environmental, technical, and social sustainability.

- To what extent has BBL made progress toward localization as a sustainability strategy? What recommendation can the Consultant(s) give in terms of criteria for sustainability?

- What are the key lessons learnt which education sector overall can build on in designing similar projects in the future?

- What are recommendations for future projects, in regard to achieving the Joint Response Framework target

Gender, Equality, Disability and Social Inclusion

- To what extent was BBL able to understand the needs related to gender, disability, and other requirements for social inclusion? To what extent did the design and implementation of BBL respond to these needs? (Relevance)

- Have representatives from women’s groups, Organisations of Persons with Disabilities (OPDs) Organisations of Persons with Disabilities, and other groups for marginalized communities been involved in understanding the needs and response of BBL? (Relevance)

- Did the project budget make adequate provisions for all important goals, e.g. addressing gender and inclusion related specific objectives/activities? (Efficiency)

- What factors of BBL have worked well to achieve results for girls, and what has worked less well? For children with disabilities? For children from ethnic groups? And other traditionally marginalized populations? (Effectiveness and Impact)

- What evidence exists that any gains toward GEDSI will be sustained? What recommendations are there for future projects for sustainable efforts toward GEDSI? (Sustainability)

## Suggested Methodology:

Based on the objectives of the evaluation, this section indicates a possible approach, methods, and processes for the evaluation. Methodological rigor will be given significant consideration in the assessment of the proposals. Hence consultants are invited to interrogate the approach and methodology proffered in the ToR and improve on it, or propose an approach they deem more appropriate, which should be guided by the UNICEF’s revised Evaluation Policy (2018) , the United Nations Evaluation Group(UNEG) Norms and Standards for Evaluation (2016) , UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluation (2014) , UN SWAP Evaluation Performance Indicator, UNEG Ethical Guidelines for Evaluation (2020) , UNICEF Procedure for Ethical Standards and Research, Evaluation and Data Collection and Analysis (2021) and UNICEF-Adapted UNEG Evaluation Report Standards (2017). Moreover, the evaluation should consider throughout issues of equity, gender equality and human rights. In their proposal, consultants should clearly refer to triangulation, sampling plan, ethical considerations (including, ethical clearance) and methodological limitations and mitigation measures. They are encouraged to also demonstrate methodological expertise in evaluating education programmes.

It is expected that the evaluation will employ non-experimental, mixed methods approach drawing on key project documents, the constructed Theory of Change and the monitoring framework for guidance.

The evaluation takes a process evaluation approach with the purpose of informing the potential adjustments in the Programme design and its delivery system. At minimum, the evaluation will draw on the following methods that would allow both processes as well as achievement of results and early impacts to be assessed.

- Desk review of project documents and other relevant data Review and analysis of secondary quantitative data;

- Key Informant Interviews (KIIs); Focus Group Discussions (FGDs);

- Case studies of children participating in the project; x Cost-effectiveness analysis; Observation of Programme processes;

- Consultant is encouraged to propose alternative quantitative and/or qualitative tools supporting collection of data amongst programme beneficiaries and implementers

The evaluation is expected to be done remotely, though in person data collection will be done by a team of enumerators who will need to be organized/recruited by the team leader. In case the team leader cannot find a team of enumerators, UNICEF can provide details of partners who could support data collection. These would be hired and managed by the evaluation team leader.

The Programme has national coverage. Thus, locations selected for data collection need to be proposed by the consultant, along with a sampling framework and detailed considerations for the selection of the locations. Locations selected should lead to the evaluation considering different contexts/ circumstances of programme implementation. Locations will be finally agreed on with UNICEF.

The data collected should be disaggregated by sex, age, disability, states, etc. where relevant and focus on both the implementers and the rights holders (children and caregivers) and the key informants at central and sub-national levels.

Sampling of KIIs and FGDs should be done in consultation with UNICEF. The evaluation sample should reconsider a balance of criteria such as socioeconomic indicators, remoteness, ethnicities, etc., as well as conditions related to safety and access.

To enrich the analysis, the evaluation will use to the extent possible, quantitative/qualitative data gathered by UNICEF such as donor reports, Quarterly reports from Implementing partners, Annual report 2021 and field monitoring reports

Conventional ethical guidelines are to be followed during the evaluation. Specific reference is made to the revised UNEG Norms and Standards for Evaluation in the UN System and UNEG Ethical Guidelines as well as to the UNICEF’s revised Evaluation Policy, and the UNICEF Procedure for Ethical Standards in Research.

Evaluation and Data Collection and Analysis and UNICEF’s Evaluation Reporting Standards. In case children or vulnerable populations are expected to be included under the data collection, ethical review from an IRB will be required and will be responsibility of the evaluation team upon approval of the inception report. Good practices not covered therein are also to be followed. Any sensitive issues or concerns should be raised with the evaluation management team as soon as they are identified.

There are several limitations to the evaluation which can hinder the process, notably: (i) disaggregated data may not be available at the local level, or the quality of available data may not be satisfactory; (ii) uncertainty about the possibility to access communities at the time of data collection (iii) reliability of the data collected online. The applicants should discuss the above or other potential limitations (including limitations of proposed methodologies and sampling) in their proposal and further identify during the inception phase. The limitations that could lead to changes in evaluation questions and scope of analysis and mitigation measures should be clearly identified at the inception phase before initiation of data collection. Specific scenarios are expected to be presented in the proposal.

## Proposed Timeframe:

5 months including field data collection. An estimated budget has been allocated for this evaluation. As reflected in Table 1, the evaluation has a timeline of four months, from November 2022 to March 2023. Adequate effort should be allocated to the evaluation to ensure timely submission of all deliverables, approximately 17 weeks on the part of the evaluation team.

People interviewed for the Inception Phase

People interviewed for the Inception Phase

| SN | Name | Organisation | Position and Role in BBL | Email |
| --- | --- | --- | --- | --- |
| 1 | Shweta Sandilya | UNICEF | Education Manager BBL | ssandilya@unicef.org |
| 2 | Nicole Starkey | UNICEF | Education Specialist | nstarkey@unicef.org |
| 3 | Hyunjung Lee (Amelia) | UNICEF | Education Officer | hyunlee@unicef.org |
| 4 | Aye Myint Than Htay (AMTH) | UNICEF | Education Specialist | amthtay@unicef.org |
| 5 | Kyaw Lwin Latt (KLL) | UNICEF | Education Officer - data & monitoring, Facilitators' resource | kllatt@unicef.org |
| 6 | Malar San (Malar) | UNICEF | Education Officer - MHPSS, RH, equity | msan@unicef.org |
| 7 | Aye Aye Yee (Aye Aye) | UNICEF | Education Specialist - ECE | aayee@unicef.org |
| 8 | Myo Wai (Myo Myo) | UNICEF | Education Officer - Open Learning (OL) materials, Inclusive education | mwai@unicef.org |
| 9 | Khin Mon Nyein (Mon Mon) | UNICEF | Education Specialist - NFPE | knyein@unicef.org |
| 10 | Ei Phyu | DFAT | Partnership Finance and Compliance Manager Australian Embassy – Yangon, Myanmar | ei.phyu@dfat.gov.au |
| 11 | Stephen Close | DFAT | First Secretary – Development Australian Embassy – Yangon, Myanmar | stephen.close@dfat.gov.au |
| 12 | Tun Win | UNICEF | National Consultant Evaluation | mailto:htunlwin@gmail.com |
| 13 | James Shoobridge | UNICEF | International Evaluation Consultant | jimshoobridge@hotmail.com |
| 14 | Mitsue Uemura | UNICEF | Regional Education Adviser, EAPRO | muemura@unicef.org |

Preliminary List of Key Informant Interviews

Preliminary List of Key Informant Interviews

| SN | Organisation | Position and Role in BBL | Name | Email | Category | Tool |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | UNICEF | Education Manager BBL | Shweta Sandilya | ssandilya@unicef.org |  |  |
| 2 | UNICEF | Education Specialist – Community consultation | Nicole Starkey | nstarkey@unicef.org |  |  |
| 3 | UNICEF | Education Officer- coordinating | Hyunjung Lee (Amelia) | hyunlee@unicef.org |  |  |
| 4 | UNICEF | Education Specialist - Managing programe operation and IPs | Aye Myint Than Htayamthtay (AMTH) | amthtay@unicef.org |  |  |
| 5 | UNICEF | Education Officer - data & monitoring, Facilitators' resource | Kyaw Lwin Latt (KLL) | kllatt@unicef.org |  |  |
| 6 | UNICEF | Education Officer - MHPSS, RH, equity | Malar San (Malar) | msan@unicef.org |  |  |
| 7 | UNICEF | Education Specialist - ECC | Aye Aye Yee (Aye Aye) | aayee@unicef.org |  |  |
| 8 | UNICEF | Education Officer - Open Learning(OL) materials, Inclusive education | Myo Wai (Myo Myo) | mwai@unicef.org |  |  |
| 9 | UNICEF | Education Specialist - NFPE | Khin Mon Nyein (Mon Mon) | knyein@unicef.org |  |  |
| 10 | DFAT | Partnership Finance and Compliance Manager Australian Embassy – Yangon, Myanmar | Ei Phyu | ei.phyu@dfat.gov.au | Donor |  |
| 11 | DFAT | First Secretary – Development Australian Embassy – Yangon, Myanmar | Stephen Close | stephen.close@dfat.gov.au | Donor |  |
| 12 | Kbc Social Mission |  | Saw Settminthu | sawsettminthu@gmail.com | IP |  |
| 13 | Myanmar Literacy Resource Centre Mlrc |  | Tin Maung Win | tinmaungwin54@gmail.com |  |  |
| 14 | Myanmar Baptist Convention |  | Akari | bblc.mbc@gmail.com |  |  |
| 15 | Karuna Mission Social Solidarity Kmss |  | Mee Phyaw | meephyaw@kmss.org.mm |  |  |
| 16 | World Vision International Myanmar |  | Yuzana_thin | yuzana_thin@wvi.org |  |  |
| 17 | Border Areas Development Association |  |  |  |  |  |
| 18 | Metta Development Foundation |  | Hkawn Nu | hkawn.nu@metta-myanmar.org |  |  |
| 19 | Succor Foundation |  | Htet Aung | htetaung@mbapf.org |  |  |
| 20 | Terre Des Hommes Lausanne Myanmar |  | Zaw OO | zaw.oo@tdh.ch |  |  |
| 21 | Kachin Baptist Convention Kbc | Associate Project Manager | Awng Lat | awnglat@kbchdd.org |  |  |
| 22 | Rvwang Culture And Literature Society Of Myanmar |  |  |  |  |  |

.

BBL Context Timeline

Myanmar Timeline of Events

| SN | Date | Event | Event Type | Impact on Education Service Delivery |
| --- | --- | --- | --- | --- |
| 1 | February 2021 | On February 1st, Myanmar armed forces (the Tatmadaw) stages a military coup declaring fraud in the November 2020 multiparty general election won by the National League for Democracy. A year-long state of emergency is ordered with a promise that new elections would take place in one year. | Conflict | Negative |
| 2 | February 2021 | The military junta expels the UN envoy. | Conflict | Negative |
| 3 | February 2021 | A Civil Disobedience Movement (CDM) is launched in response to the military coup and protesters take to the streets. | Conflict |  |
| 4 | March 2021 | Martial law imposed in 11 townships in the Yangon and Mandalay regions. | Conflict | Negative |
| 5 | March 2021 | UNICEF expands and adapts its partnerships with local NGOs and other partners to ensure implementation of its activities. | UNICEF | Positive |
| 6 | March 2021 | UNICEF requests a rapid scale up of emergency assistance outside the current Humanitarian Response Plan (HRP) locations | UNICEF | Positive |
| 7 | 8 March 2021 | Operationalization of UNCT engagement principles guidance for Programme Review | UN | Positive |
| 8 | 5 May 2021 | The People’s Defence Forces (PDF) are formed by the National Unity Government (NUG) to unite anti-coup resistance. The military clashes with the PDF in the southeast and northwest regions. | Conflict | Negative |
| 9 | June 2021 | The junta attempts to reopen schools nationwide, but more than half of the country’s 400,000 Facilitators are on strike and just 10 percent of the estimated 9 million students nationwide opt to enrol. | MoE |  |
| 10 | 1 July 2021 | UNICEF activates L2 emergency for 8 months (until March 30, 2022) | UNICEF | Positive |
| 11 | July 2021 | Severe flooding affects large parts of Myanmar | Disaster | Negative |
| 12 | 9 July 2021 | COVID-19 pandemic worsens: A third wave of COVID-19 hits the country. Schools that reopened in June were closed again | Disaster | Negative |
| 13 | August 2021 | Military extend the state of emergency until August 2023. | Conflict | Negative |
| 14 | 1 August 2021 | UNICEF releases the 2021 HAC appeal revision for Myanmar tripling the numbers in need (3.1 million people of which 1.2 million children). | UNICEF |  |
| 15 | November 2021 | Schools across Myanmar, except for 46 townships where COVID-19 restrictions remain in place, are allowed to reopen after a 4-month closure. However, many schools remain closed or with poorly attended. | MoE | Positive |
| 16 | November 2021 | UN Security Council calls for end to violence. | UN | Positive |
| 17 | Oct – Nov 2021 | Many sectors remain underfunded such as WASH with a current gap of 60 percent of UNICEF funding requirements. | UNICEF |  |
| 18 | February 2022 | The number of internally displaced persons (IDP) significantly increased across the country, particularly in the city of Sagaing, and more than a million have been forced to flee into neighbouring countries (Bangladesh, Malaysia, and Thailand). | Conflict | Negative |
| 19 | February 2022 | UNCT programmatic engagement guidelines version one plus is released | UN | Positive |
| 20 | Early 2022 | UNICEF releases its 2022 HAC appeal for Myanmar with 14.4 million people in need, of which 5 million children | UNICEF | Positive |
| 21 | 28 March 2022 | The Northwest region, including the city of Sagaing, Chin and Magway, has 308,600 IDPs out of a total of 558,000 people displaced since February 2021. | Conflict | Negative |
| 22 | 30 March 2022 | UNICEF extends L2 emergency until September 30, 2022. | UNICEF | Positive |
| 23 | May 2022 | A reported 694,300 civilians have been displaced nationally by the conflict, more than double that of the figure of 320,900 at the end of 2021. | Conflict | Negative |
| 24 | June 2022 | UNICEF providing activities to ensure uninterrupted water supply to IDPs and expanding its response to protect children from landmines and explosives risk by ensuring that Explosive Ordnance Risk Education is integrated across all relevant sectors of its humanitarian response. | UNICEF | Positive |
| 25 | June 2022 | The number of displaced men, women and children in Myanmar remains above one million, including 760,000 displaced by the conflict and insecurity since the military takeover in February last year. | Conflict | Negative |
| 26 | June 2022 | Many schools reopened with the beginning of the new school year (2022–2023), while many remain closed, particularly in rural areas: 96 per cent in Rakhine, 92 per cent in Mon, 80 per cent in Shan, 71 per cent in Kayin, 35 per cent in Chin, and 18 per cent in Kayah. According to UNICEF, 4.5 million children – half of the school-aged children in Myanmar – have not accessed education for two academic years, and that nearly six million children currently have restricted or no access to learning. |  | Positive |
| 27 | 27 June 2022 | The monsoon season continues to cause heavy rain and flooding. | Natural Disaster | Negative |
| 28 | June 2022 | Active fighting is reported in the northwest and southeast regions, resulting in continuous population displacement. Particularly, surge of displacement is reported in Sagaing, with a total of 395,600 IDPs located within the region, including an estimated 146,000 children and their families with immediate needs for essential services. | Conflict | Negative |
| 29 | June 2022 | IDP numbers remains stable in the southeast (in Kayah state) and new displacements have been offset by reported returns. |  | Positive |
| 30 | June 2022 | Immediate delivery of humanitarian assistance was provided by UNICEF through direct distribution modality. | UNICEF | Positive |
| 31 | June 2022 | A total of 16,023 individuals in Loikaw and Demoso townships received basic WASH, child protection, education, health and nutrition supplies. | UNICEF | Positive |
| 32 | June 2022 | UNICEF continued to build upon this experience to foster unimpeded and continuous access to areas previously out of reach. | UNICEF | Positive |
| 33 | July 2022 | Number of IDPs increased to 470,000 in the Sagaing region. | Conflict | Negative |
| 34 | August 2022 | Escalation in armed conflict in the northwest and southeast regions and in Kachin state, resulting in increased displacement. | Conflict | Negative |
| 35 | August 2022 | As of August 29th, an estimated 974,4001 people had been internally displaced since February 2021, which has resulted in more than 1.3 million IDPs, with the northwest region being the most affected. | Conflict | Negative |
| 36 | August 2022 | Access for aid workers not improved, as the de facto authorities maintain tight control on issuing travel authorizations. |  | Negative |
| 37 | August 2022 | Humanitarian situation remains unpredictable in Rakhine due to the heightened tension and clashes between the Arakan Army and the Myanmar Armed Forces. 219,000 people remain in a situation of protracted displacement. | Conflict | Negative |
| 38 | August 2022 | The HCT has approved an Inter Cluster Coordination Group (ICCG) for the northwest to address strategic operational issues. | UN/RCO | Positive |
| 39 | August 2022 | UNICEF improves its MHPSS activities, even in hard-to-reach areas, with a 53 per cent increase compared to the previous month thanks to virtual access and hotlines, capacity building and communities empowering. | UNICEF | Positive |
| 40 | September 2022 | On 16 September, at least 11 children died as a result of an air strike and indiscriminate fire in civilian areas, including a school, in Tabayin Township, in the Sagaing region. | Conflict | Negative |
| 41 | September 2022 | Deteriorating security situation in Rakhine. Movement restrictions imposed due to continuing clashes between the Arakan Army and Myanmar Armed Forces, severely affecting humanitarian interventions and the ability of aid workers to reach the affected population. | Conflict | Negative |
| 42 | September 2022 | Conflict also reported in the in Loikaw township in Kayah, resulting in civilian casualties and displacement. | Conflict | Negative |
| 43 | September 2022 | Humanitarian situation closely monitored by UNICEF and partners despite challenges posed by movement restrictions and security measures, preventing access to the affected population. | UNICEF | Positive |
| 44 | September 2022 | UNICEF distributing WASH, child protection, health, and nutrition supplies to 21,095 people in 48 displacement sites in Loikaw and Demoso township in Kayah state. | UNICEF | Positive |
| 45 | October 2022 | On 23 October, airstrikes killed and injured 100 people in Hpakant in Kachin state, continuing to deteriorate the security situation of the country. | Conflict | Negative |
| 46 | October 2022 | On October 28th, the State Administration Council endorsed a new law on the registration of associations, repealing the one of 2014, which makes registration compulsory for both national and international NGOs and associations. This law could have implications for humanitarian operations. |  |  |
| 47 | October 2022 | Since February 2021, UNICEF and its implementing partners have provided legal aid support to 3,985 children and young people. | UNICEF | Positive |
| 48 | October 2022 | Intensifying conflict is reported in Rakhine, with reported clashes in northern Maungdaw, northern Rathedaung, southern Buthidaung, Kyauktaw, Minbya and Paletwa townships. | Conflict | Negative |
| 49 | October 2022 | On 25 October, cyclone Sitrang impacted Rakhine coasts. Damages of WASH infrastructures located in the displaced camps of Sittwe and Pauktaw are reported. | Natural Disaster | Negative |
| 50 | November 2022 | Additional 29,200 displaced people compared to October, mainly in North and Central Rakhine and Kachin state | Conflict | Negative |
| 51 | November 2022 | Prolonged violence and conflict, access constraints and blocked transportation routes keep hindering the work of humanitarian workers and the possibility to support children and their families. | Conflict | Negative |
| 52 | November 2022 | Casualties from landmines and explosive remnants of war are reported mostly in Shan State and also in Sagaing. | Conflict | Negative |
| 53 | November 2022 | Essential medical supplies for primary health care services have been distributed to partners in Northwest and Southeast regions. | UNICEF | Positive |
| 54 | November 2022 | In-person and remote MHPSS activities provided to a total of 10,370 children and 2,062 caregivers. | UNICEF | Positive |
| 55 | November 2022 | Nearly 28,000 temporarily displaced people in Kayin, Kayah, Magway and Tanintharyi received life-saving WASH supplies. | UNICEF | Positive |
| 56 | November 2022 | UNICEF provided cash assistance to a total of 8,467 participants through its Maternal and Child Cash Transfer programme so far. | UNICEF | Positive |

Result Framework – Bringing Back Learning (BBL)

Results Framework BBL Programme

| KEY INDICATOR | Indicator Definitions | Data Source | Disaggregation | Collection Schedule/Frequency of data collection | Baseline | End of Project Target |
| --- | --- | --- | --- | --- | --- | --- |
| Overall objective: Provide targeted girls and boys, aged 3 to 18 years old, who have been out of learning and have not yet started or completed a primary level education, with catch up and remedial education opportunities within their community, with a particular focus on literacy, numeracy, life skills and Social and Emotional Learning. |  |  |  |  |  |  |
| Objective/Outcome 1: Provide girls and boys aged between 3 years old and 18 years old, whose learning has been disrupted, with access to education literacy, numeracy, and wellbeing support |  |  |  |  |  |  |
| O-1: # of girls and boys aged between 3 to 18 years old who have benefitted from learning opportunities, by the end of the programme | Total number of children benefitting from NFE, EXCEL, Outreach and Community Hub | Reports collected from IPs | Gender/disability | Quarterly | 0 | 40,000 (at least 50% girls) |
| Output 1.1 Girls and boys attend quality education in a protected, inclusive learning environment |  |  |  |  |  |  |
| 1.1.1: # of community libraries upgraded and functioning as learning hub | Community libraries renovated into child-friendly, safe and protective learning environments | Report from the IPs; TPM | N/A | Quarterly | 0 | 65 |
| 1.1.2: # of children accessing and benefitting from the interventions through the outreach programme | Children attending the outreach centers and participating in group activities | Attendance report; Report from the IPs | Gender/disability | Quarterly | 0 | 19,450 (at least 50% girls) |
| 1.1.3: # of community library with gender and inclusive sensitive WASH facilities | Community libraries provided with gender and inclusive sensitive WASH facilities | Report from the IPs; | N/A | Quarterly | 0 | 65 |
| Output 1.2 Girls and Boys have access to contextual, inclusive, quality teaching learning materials |  |  |  |  |  |  |
| 1.2.1: # of children benefitting from the books | Total number of children visiting community library or attending outreach programme and able to access books | Attendance registers from libraries; mobile libraries Report from the IPs; TPM | Gender/disability | Quarterly | 0 | 34,450 (at least 50% girls) |
| 1.2.2: # of children receiving Open Learning /ST-HBL materials | Total number of children receiving Open Learning materials | Distribution list; Report from the IPs; TPM | N/A | Quarterly | 0 | 34,450 (at least 50% girls) |
| 1.2.3: # of children benefitting from NFE programme | Children attending the NFE and EXCEL programme | Attendance report; Report from the IPs | Gender/disability | Quarterly | 0 | 5,550 (at least 50% girls) |
| Objective 2: Ensure facilitators, CSO resource persons, and community members are well equipped with relevant capacities and receive appropriate technical support to deliver context responsive equity-focused, quality education and wellbeing support |  |  |  |  |  |  |
| O-2: # of facilitators/CSO staff/parents, who have benefitted from capacity building support and other resources | All stakeholders at community level receive training on NFE, EXCEL, library management, PSEA, MHPSS, literacy and numeracy, outreach programme, digital literacy, etc. | Training Report | Gender | Quarterly | 0 | 7,500 (50% female) |
| Output 2.1 PTAs/ Community structures strengthened to implement community based strategic and sustainability plans towards improving learning of children |  |  |  |  |  |  |
| 2.1.1: # of consultation meeting organised on continuing of learning among all children | Consultation meeting at community level to promote learning of all children by attending community hubs or participating in outreach progamme | Report from the IPs; TPM | N/A | Quarterly | 0 | 130 |
| # of functional community management committees | The community management committees established, have plans, meet regularly, discuss progress and challenges to promote learning at community level | Report from the IPs; TPM | N/A | Quarterly | TBC | 80% |
| Output 2.2 Provide mental health and psychosocial support, counselling support to children and families impacted by conflict |  |  |  |  |  |  |
| 2.2.1: # of facilitators with enhanced skills on SEL, CwD, PSS | Facilitators trained on child-centred teaching skills, SEL, CwD, PSS | Training Report, TPM, Report from the IPs | Gender/disability | Quarterly | 0 | 400 (50% female) |
| 2.2.2: # of awareness session conducted at community level to promote MHPSS | All communication campaigns on MHPSS through community meetings | Activity Report; Field Monitoring Visit | N/A | Quarterly | 0 | 65 |
| Output 2.3 Girls and Boys access quality education and adolescent learning outcomes are improved through improved community volunteers well- being and teaching capacity |  |  |  |  |  |  |
| 2.3.1: # of facilitators with enhanced knowledge and skills on alternative education for children | Facilitators trained on NFE & EXCEL | Training Report, TPM, Report from the IPs | Gender/disability | Quarterly | 0 | 140 (50% female) |
| 2.3.2: # of facilitators receiving incentives | Facilitators receive cash grant as incentive to facilitate learning for children at community level | Cash distribution register; TPM; Report from the IPs | Gender/disability | Monthly |  | 400 (50% female) |
| 2.3.3: % of children with improved literacy and numeracy skills | Measuring the foundational literacy and numeracy based on the strategies implemented. | Data collected by IP | Gender/disability | Half yearly | TBC (no of children assessed) | 60% children show improvement |

BBL Programme Data

BBL Partners, Start and End Date, and Contributions to Output Areas

| # | Partner | Document Type | Document Title | Start Date | End Date | Grants |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | KBC SOCIAL MISSION | PD | Bring Back Learning to Children | 17/05/2021 | 16/05/2023 | Output 1: RR and SM210104 Output 2: JCU Family Grant (SC190200), SC220246 (DFAT BBL) Output 3: Global Education Thematic SC189904, SC220246 (DFAT BBL), and SM210104 (GoJ SB) |
| 2 | KACHIN BAPTIST CONVENTION KBC | PD | Bring Back Learning to children | 15/07/2021 | 14/07/2022 |  |
| 3 | MYANMAR LITERACY RESOURCE CENTRE MLRC | PD | Capacity building to NGO partners on Non-Formal Education_Bring Back Learning to Children | 15/10/2021 | 21/07/2023 | SC220246, SM210104, SC189904 and GC |
| 4 | MYANMAR BAPTIST CONVENTION | HPD | Bring Back learning to children | 08/11/2021 | 07/02/2023 | Output 1: Non-Grant Output 2: SC190371_JCU AEON |
| 5 | KARUNA MISSION SOCIAL SOLIDARITY KMSS | HPD | Providing learning opportunities to children | 25/11/2021 | 30/06/2023 | Output 1: PR Non-Grant, Government of Japan SM210104 Output 2: GPE COVID fund SC200370, SC220246 (DFAT BBL) Output 3: GPE COVID fund SC200370, PR Non-Grant, SC220246 (DFAT BBL) |
| 6 | WORLD VISION INTERNATIONAL MYANMAR | HPD | Bring Back Learning Program | 15/11/2021 | 14/11/2022 | Output 1: GPE COVID fund SC200370, RR 2021, China SM:200293 Output 2: GPE COVID fund SC200370, |
| 7 | BORDER AREAS DEVELOPMENT ASSOCIATION | SSFA | Bring Back Learning to Primary Children through Short Term-Home Base Learning materials, Psychosocial Support and WASH Hygiene Promotion | 08/12/2021 | 07/06/2022 |  |
| 8 | METTA DEVELOPMENT FOUNDATION | HPD | Bring Back Learning to Children | 15/12/2021 | 28/02/2023 |  |
| 9 | SUCCOR FOUNDATION | HPD | Bringing Back Learning to the children of Myanmar | 06/07/2022 | 30/06/2023 | SC220246 (DFAT BBL) |
| 10 | TERRE DES HOMMES LAUSANNE MYANMAR | HPD | Bring Back Learning of children from the crisis-affected township of Hlaingtharya, Yangon Region by providing Open Learning assistance and EXCEL (Extended and Continuous Education and Learning) curriculum | 01/08/2022 | 30/04/2023 |  |
| 11 | KACHIN BAPTIST CONVENTION KBC | HPD | Improve Education access and Bring back Learning activities for conflict-Affected children and adolescents in Kachin, Shan State and Sagaing Region | 01/09/2022 | 31/08/2023 | Output 1: SC200370, SM200293 and SM210104; Output 2: SC189904 Output 3: SC180743, SM220325 and SC220090 |
| 12 | RVWANG CULTURE AND LITERATURE SOCIETY OF MYANMAR | PD | Providing Bring Back Learning Opportunity to Children through Local Curriculum in Kachin State | 26/10/2022 | 26/04/2023 | Output2: Non-Grant |

BBL Programme Financial Contributions to Implementation Partners

| # | Partner | Start Date | End Date | UNICEF Cash (MMK) | UNICEF Cash (USD) | UNICEF Supply (USD) | Partners (MMK) | Partners (USD) | Total Budget | Total Budget USD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | KBC SOCIAL MISSION | 17/05/2021 | 16/05/2023 | 3,457,361,698 | 1,631,601 | 553,160 | 647,084,050 | 305,372 | MMK 4,104,445,748 and USD 553,160 | 2,490,132 |
| 2 | KACHIN BAPTIST CONVENTION KBC | 15/07/2021 | 14/07/2022 |  |  |  |  |  |  |  |
| 3 | MYANMAR LITERACY RESOURCE CENTRE MLRC | 15/10/2021 | 21/07/2023 | 423,489,400 | 199,853 | 4,956 | 2,688,000 | 1,269 | MMK 426,177,400 and USD 4,956 | 206,078 |
| 4 | MYANMAR BAPTIST CONVENTION | 08/11/2021 | 07/02/2023 | 2,545,142,562 | 1,201,106 | 874,249 | 263,912,000 | 124,546 | MMK 2,809,054,562 and USD 874,249 | 2,199,900 |
| 5 | KARUNA MISSION SOCIAL SOLIDARITY KMSS | 25/11/2021 | 30/06/2023 | 4,109,006,677 | 1,939,125 | 845,248 | 67,440,000 | 31,826 | MMK 4,176,446,677 and Supplies USD 845,248 | 2,816,200 |
| 6 | WORLD VISION INTERNATIONAL MYANMAR | 15/11/2021 | 14/11/2022 | 451,477 (USD) | 451,477 | 2,789 | 44,040 (USD) | 44,040 | USD 498,306 | 498,306 |
| 7 | BORDER AREAS DEVELOPMENT ASSOCIATION | 08/12/2021 | 07/06/2022 | 89,985,700 | 42,466 | 22,135 | 8,400,000 | 3,964 |  | 68,565 |
| 8 | METTA DEVELOPMENT FOUNDATION | 15/12/2021 | 28/02/2023 | 1,110,004,374 | 523,834 | 42,237 | 9,330,000 | 4,403 | MMK 1,119,334,374 and USD 42,237 | 570,474 |
| 9 | SUCCOR FOUNDATION | 06/07/2022 | 30/06/2023 | 4,741,610,100 | 2,237,664 | 148,350 | 11,500,000 | 5,427 | MMK 4,753,110,100 and $148,350 | 2,391,441 |
| 10 | TERRE DES HOMMES LAUSANNE MYANMAR | 01/08/2022 | 30/04/2023 | 424,569,588 | 200,363 | 95,652 | 5,636,034 | 2,660 | MMK 430,205,622 and 95,652 USD | 298,675 |
| 11 | KACHIN BAPTIST CONVENTION KBC | 01/09/2022 | 31/08/2023 | 1,622,965,951 | 765,911 | 76,761 | 327,018,116 | 154,327 | MMK 1,949,984,067 & Supply USD 76,761 | 996,999 |
| 12 | RVWANG CULTURE AND LITERATURE SOCIETY OF MYANMAR | 26/10/2022 | 26/04/2023 | 148,826,770 MMK |  |  | 900,000 |  | 149726770 MMK |  |
|  | Total |  |  |  |  |  |  |  |  | 12,536,770 |

BBL Children and Facilitators Reached in 2022 by Partner and Township

| IP Name | Project Title | State/ Region | Township | BBL Children |  |  | BBL Facilitators |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | O1 | O2 | O3 | O1 | O2 | O3 |
| BDA | Bring Back Learning to Primary Children through Short Term-Home Base Learning materials, Psychosocial Support and WASH Hygiene Promotion in Monywa Township | TOTAL |  | 0 | 8,622 | 0 | 0 | 153 | 0 |
|  |  | Sagaing | Monywa |  | 8,622 |  |  | 153 |  |
| KBC | Bring Back Learning to Children | TOTAL |  | 22,297 | 0 | 1,350 | 590 | 0 | 0 |
|  |  | Kachin | Bhamo | 532 |  | 332 | 405 |  |  |
|  |  |  | Chipwi |  |  | 238 | 35 |  |  |
|  |  |  | Myitkyina | 19,472 |  |  |  |  |  |
|  |  |  | Nawngmun |  |  | 50 |  |  |  |
|  |  |  | Waingmaw | 1,651 |  |  | 60 |  |  |
|  |  | Mandalay | Pyinoolwin | 642 |  | 140 | 30 |  |  |
|  |  | Shan (East) | Kengtung |  |  | 130 |  |  |  |
|  |  | Shan (North) | Kutkai |  |  | 200 |  |  |  |
|  |  |  | Lashio |  |  | 200 | 30 |  |  |
|  |  |  | Mongmit |  |  | 60 |  |  |  |
|  |  |  | Muse |  |  |  | 30 |  |  |
| KBC | Improve Education access and Bring back learning activities for conflict-affected childen and adolescens in Kachin, Shan State and Sagaing Region | TOTAL |  | 1,697 | 0 | 3,501 | 30 | 0 | 0 |
|  |  | Kachin | Mogaung | 1,480 |  | 333 | 30 |  |  |
|  |  |  | Momauk |  |  | 199 |  |  |  |
|  |  |  | Myitkyina |  |  | 647 |  |  |  |
|  |  |  | Puta-O |  |  | 317 |  |  |  |
|  |  |  | Sumprabum | 960 |  | 251 | 30 |  |  |
|  |  |  | Waingmaw | 701 |  | 1,437 |  |  |  |
|  |  |  | Chipwi |  |  | 300 |  |  |  |
|  |  |  | Mansi |  |  | 150 |  |  |  |
|  |  |  | Mohnyin |  |  | 150 |  |  |  |
|  |  |  | Nawngmun |  |  | 50 |  |  |  |
|  |  | Shan (East) | Kengtung | 36 |  |  |  |  |  |
| KBC SM | Bring Back Learning to Children | TOTAL |  | 15,859 | 39,907 | 3,510 | 2,113 | 30 | 149 |
|  |  | Ayeyarwady | Bogale | 193 | 524 |  |  |  |  |
|  |  |  | Danubyu | 103 | 187 |  |  |  |  |
|  |  |  | Dedaye | 29 | 118 |  |  |  |  |
|  |  |  | Einme | 455 | 1,401 | 211 | 16 |  |  |
|  |  |  | Hinthada | 190 | 368 |  | 108 |  |  |
|  |  |  | Ingapu | 72 | 143 |  |  |  |  |
|  |  |  | Kangyidaunt | 250 | 715 | 63 |  |  |  |
|  |  |  | Kyaiklat | 151 | 221 |  |  |  |  |
|  |  |  | Kyaunggon | 335 | 1,066 |  |  |  |  |
|  |  |  | Kyonpyaw | 30 | 82 |  |  |  |  |
|  |  |  | Labutta | 74 | 343 | 122 |  |  |  |
|  |  |  | Maubin | 100 | 576 | 102 |  |  |  |
|  |  |  | Mawlamyinegyun | 221 | 571 |  |  |  |  |
|  |  |  | Myanaung | 23 | 34 |  |  |  |  |
|  |  |  | Myaungmya | 772 | 1,595 |  | 42 |  |  |
|  |  |  | Ngapudaw | 1,294 | 4,546 | 212 | 82 |  |  |
|  |  |  | Nyaungdon | 16 | 15 |  |  |  |  |
|  |  |  | Pantanaw | 38 | 190 |  |  |  |  |
|  |  |  | Pathein | 1,276 | 3,088 | 572 | 280 |  |  |
|  |  |  | Pyapon | 133 | 279 |  |  |  |  |
|  |  |  | Thabaung |  | 334 | 140 |  |  |  |
|  |  |  | Zalun | 133 | 327 |  |  |  |  |
|  |  | Bago (East) | Bago | 63 | 376 |  |  |  |  |
|  |  |  | Daik-U | 27 |  |  | 4 |  |  |
|  |  |  | Htantabin | 495 | 1,540 |  |  |  |  |
|  |  |  | Kyaukkyi | 1,390 | 2,248 | 589 | 238 |  | 20 |
|  |  |  | Kyauktaga | 667 | 1,177 |  | 14 |  |  |
|  |  |  | Nyaunglebin |  |  |  | 30 |  |  |
|  |  |  | Oktwin | 21 | 70 |  |  |  |  |
|  |  |  | Phyu | 115 | 306 |  |  |  |  |
|  |  |  | Shwegyin | 111 | 223 |  | 4 |  |  |
|  |  |  | Taungoo | 223 | 765 |  | 60 |  |  |
|  |  |  | Waw | 14 | 36 |  |  |  |  |
|  |  |  | Yedashe | 24 | 87 |  |  |  |  |
|  |  | Bago (West) | Letpadan | 60 | 108 |  |  |  |  |
|  |  |  | Minhla | 53 | 73 |  |  |  |  |
|  |  |  | Nattalin | 21 | 52 |  |  |  |  |
|  |  |  | Okpho | 57 | 210 |  |  |  |  |
|  |  |  | Thayarwady | 103 | 282 |  | 76 |  |  |
|  |  | Kachin | Hpakant | 7 | 48 |  | 2 | 2 |  |
|  |  |  | Myitkyina | 15 | 67 |  | 2 | 2 |  |
|  |  | Kayah | Demoso | 1,570 | 3,933 | 564 | 106 |  | 25 |
|  |  |  | Loikaw | 249 | 631 |  | 46 |  |  |
|  |  |  | Mese | 281 | 781 |  |  |  |  |
|  |  |  | Bawlake |  |  |  | 4 |  |  |
|  |  |  | Hpruso |  |  |  | 18 |  |  |
|  |  |  | Mese |  |  |  | 4 |  |  |
|  |  | Kayin | (State/Region-wide) |  | 42 |  |  |  |  |
|  |  |  | Hlaingbwe | 88 | 180 |  |  |  |  |
|  |  |  | Hpa-An | 39 | 134 |  | 122 |  |  |
|  |  |  | Hpapun | 183 | 258 |  |  |  |  |
|  |  |  | Kawkareik | 124 | 216 |  | 4 |  |  |
|  |  |  | Kyainseikgyi | 1,173 | 1,698 |  | 52 |  |  |
|  |  |  | Kyainseikgyi | 213 | 227 |  | 208 |  | 52 |
|  |  |  | Myawaddy | 75 | 116 |  | 2 | 2 |  |
|  |  |  | Thandaunggyi | 1,283 | 4,636 | 935 | 208 |  | 52 |
|  |  | Mandalay | Meiktila | 26 | 66 |  | 2 | 2 |  |
|  |  |  | Pyinoolwin | 9 | 19 |  | 2 | 2 |  |
|  |  | Nay Pyi Taw | Pyinmana | 111 | 149 |  | 2 | 2 |  |
|  |  | Sagaing | Katha | 12 | 24 |  | 2 | 2 |  |
|  |  |  | Tigyaing | 21 | 59 |  |  |  |  |
|  |  | Shan (North) | Lashio | 6 | 20 |  | 2 | 2 |  |
|  |  |  | Mabein | 10 | 24 |  | 2 | 2 |  |
|  |  |  | Namtu | 23 | 80 |  | 4 | 4 |  |
|  |  |  | Tangyan | 5 | 11 |  | 2 | 2 |  |
|  |  | Shan (South) | Kalaw |  | 21 |  | 2 | 2 |  |
|  |  |  | Monghsu | 7 | 19 |  | 2 | 2 |  |
|  |  |  | Pinlaung | 3 | 19 |  | 2 | 2 |  |
|  |  | Tanintharyi | Dawei | 520 | 1,247 |  | 56 |  |  |
|  |  |  | Myeik |  |  |  | 76 |  |  |
|  |  |  | Palaw |  |  |  | 34 |  |  |
|  |  |  | Thayetchaung | 43 | 40 |  | 2 |  |  |
|  |  | Yangon | (State/Region-wide) |  |  |  | 185 |  |  |
|  |  |  | Ahlone | 21 | 28 |  | 2 |  |  |
|  |  |  | Hlegu | 30 | 76 |  |  |  |  |
|  |  |  | Hmawbi | 161 | 235 |  |  |  |  |
|  |  |  | Htantabin | 98 | 285 |  |  |  |  |
|  |  |  | Shwepyithar | 45 | 42 |  |  |  |  |
|  |  |  | Taikkyi | 69 | 179 |  |  |  |  |
|  |  |  | Thanlyin | 7 | 21 |  | 2 |  |  |
| MBC | Bring Back Learning to Children and Adolescents | TOTAL |  | 2,772 | 11,400 | 856 | 173 | 317 | 42 |
|  |  | Ayeyarwady | Pantanaw |  |  |  |  | 4 |  |
|  |  | Chin | Tedim | 468 | 3,066 | 571 | 2 | 32 | 19 |
|  |  |  | Tonzang | 32 | 477 | 63 |  |  | 5 |
|  |  | Kayin | Hpa-An | 172 | 393 |  | 18 |  |  |
|  |  | Mandalay | Pyinoolwin |  |  |  |  | 3 |  |
|  |  | Rakhine | Ann | 110 | 210 |  | 6 |  |  |
|  |  |  | Minbya | 60 | 199 |  | 2 |  |  |
|  |  |  | Myebon | 239 | 1,131 |  | 17 | 33 |  |
|  |  | Sagaing | Hkamti | 84 | 306 |  | 6 | 56 |  |
|  |  |  | Homalin | 39 | 201 |  | 3 |  |  |
|  |  |  | Lahe | 150 | 517 |  | 13 |  |  |
|  |  |  | Lay Shi | 125 | 742 |  | 11 | 20 |  |
|  |  | Shan (East) | Kengtung | 234 | 716 | 54 | 22 | 34 | 4 |
|  |  |  | Monghpyak | 20 |  |  | 1 |  |  |
|  |  |  | Monghsat | 45 | 451 | 31 | 3 | 4 | 4 |
|  |  |  | Tachileik | 84 | 502 |  | 10 | 5 |  |
|  |  | Shan (North) | Hopang | 141 | 154 |  | 9 | 3 |  |
|  |  |  | Hseni | 25 |  |  | 1 |  |  |
|  |  |  | Kutkai | 67 | 147 |  | 4 |  |  |
|  |  |  | Lashio | 174 | 212 | 137 | 13 | 6 | 10 |
|  |  |  | Manton |  | 43 |  |  | 2 |  |
|  |  |  | Mongmit | 85 | 260 |  | 6 |  |  |
|  |  |  | Tangyan | 255 | 405 |  | 9 |  |  |
|  |  | Shan (South) | Loilen | 20 | 84 |  |  | 2 |  |
|  |  |  | Mongnai | 20 | 138 |  | 1 |  |  |
|  |  |  | Nansang | 26 | 548 |  | 2 |  |  |
|  |  |  | Taunggyi | 20 | 376 |  | 2 |  |  |
|  |  |  | Nyaungshwe |  |  |  |  | 1 |  |
|  |  |  | Taunggyi |  |  |  | 2 | 39 |  |
|  |  | Tanintharyi | Tanintharyi | 77 | 122 |  | 10 | 1 |  |
|  |  | Yangon | Ahlone |  |  |  |  | 72 |  |
| METTA | Bring Back Learning to Children | TOTAL |  | 200 | 268 | 3,637 | 32 | 91 | 8 |
|  |  | Kachin | Momauk |  |  | 997 |  |  |  |
|  |  |  | Waingmaw |  |  | 2,640 |  |  |  |
|  |  |  | Mansi |  |  |  |  |  | 3 |
|  |  | Shan (North) | Lashio | 113 |  |  | 3 | 17 | 2 |
|  |  |  | Manton | 68 | 268 |  | 5 | 20 |  |
|  |  |  | Namtu | 19 |  |  | 4 | 5 | 1 |
|  |  |  | Hseni |  |  |  |  | 1 |  |
|  |  |  | Kunlong |  |  |  | 2 | 8 |  |
|  |  |  | Kutkai |  |  |  | 15 | 32 | 2 |
|  |  |  | Muse |  |  |  | 2 | 3 |  |
|  |  |  | Namhkan |  |  |  | 1 | 5 |  |
| MLRC | Capacity building to NGO partners on NFE_Bring Back Learning to Children | TOTAL |  | 0 | 0 | 9,686 | 0 | 0 | 97 |
|  |  | Mon | Bilin |  |  | 153 |  |  |  |
|  |  |  | Chaungzon |  |  | 106 |  |  |  |
|  |  |  | Kyaikmaraw |  |  | 21 |  |  |  |
|  |  |  | Kyaikto |  |  | 98 |  |  |  |
|  |  |  | Mawlamyine |  |  | 105 |  |  |  |
|  |  |  | Mudon |  |  | 205 |  |  |  |
|  |  |  | Paung |  |  | 87 |  |  |  |
|  |  |  | Thanbyuzayat |  |  | 59 |  |  |  |
|  |  |  | Thaton |  |  | 69 |  |  |  |
|  |  |  | Ye |  |  | 22 |  |  |  |
|  |  | Ayeyarwady | Dedaye |  |  | 49 |  |  |  |
|  |  |  | Einme |  |  | 82 |  |  |  |
|  |  |  | Hinthada |  |  | 111 |  |  |  |
|  |  |  | Ingapu |  |  | 68 |  |  |  |
|  |  |  | Kyaiklat |  |  | 150 |  |  |  |
|  |  |  | Kyangin |  |  | 83 |  |  |  |
|  |  |  | Kyaunggon |  |  | 110 |  |  |  |
|  |  |  | Kyonpyaw |  |  | 77 |  |  |  |
|  |  |  | Lemyethna |  |  | 142 |  |  |  |
|  |  |  | Maubin |  |  | 111 |  |  |  |
|  |  |  | Myaungmya |  |  | 41 |  |  |  |
|  |  |  | Pantanaw |  |  | 134 |  |  |  |
|  |  |  | Pyapon |  |  | 272 |  |  |  |
|  |  |  | Wakema |  |  | 80 |  |  |  |
|  |  | Bago (East) | Kyauktaga |  |  | 47 |  |  |  |
|  |  |  | Taungoo |  |  | 20 |  |  |  |
|  |  |  | Waw |  |  | 26 |  |  |  |
|  |  |  | Yedashe |  |  | 65 |  |  |  |
|  |  | Bago (West) | Gyobingauk |  |  | 12 |  |  |  |
|  |  |  | Letpadan |  |  | 52 |  |  |  |
|  |  |  | Minhla |  |  | 51 |  |  |  |
|  |  |  | Padaung |  |  | 33 |  |  |  |
|  |  |  | Paukkhaung |  |  | 7 |  |  |  |
|  |  |  | Paungde |  |  | 25 |  |  |  |
|  |  |  | Pyay |  |  | 114 |  |  |  |
|  |  |  | Thegon |  |  | 101 |  |  |  |
|  |  | Kayin | Hlaingbwe |  |  | 109 |  |  |  |
|  |  |  | Kawkareik |  |  | 236 |  |  |  |
|  |  |  | Kyainseikgyi |  |  | 131 |  |  |  |
|  |  |  | Myawaddy |  |  | 487 |  |  |  |
|  |  | Magway | Magway |  |  | 190 |  |  |  |
|  |  |  | Minbu |  |  | 6 |  |  |  |
|  |  |  | Myothit |  |  | 24 |  |  |  |
|  |  |  | Salin |  |  | 16 |  |  |  |
|  |  | Mandalay | Aungmyaythazan |  |  | 64 |  |  |  |
|  |  |  | Chanmyathazi |  |  | 20 |  |  |  |
|  |  |  | Madaya |  |  | 98 |  |  |  |
|  |  |  | Myingyan |  |  | 59 |  |  |  |
|  |  |  | Nyaung-U |  |  | 48 |  |  |  |
|  |  |  | Pyigyitagon |  |  | 479 |  |  |  |
|  |  |  | Pyinoolwin |  |  | 177 |  |  |  |
|  |  | Nay Pyi Taw | Pyinmana |  |  | 54 |  |  |  |
|  |  | Rakhine | Ann |  |  | 181 |  |  |  |
|  |  |  | Gwa |  |  | 5 |  |  |  |
|  |  |  | Kyaukpyu |  |  | 66 |  |  |  |
|  |  |  | Kyauktaw |  |  | 246 |  |  |  |
|  |  |  | Mrauk-U |  |  | 578 |  |  |  |
|  |  |  | Myebon |  |  | 268 |  |  |  |
|  |  |  | Rathedaung |  |  | 301 |  |  |  |
|  |  |  | Sittwe |  |  | 128 |  |  |  |
|  |  |  | Thandwe |  |  | 157 |  |  |  |
|  |  |  | Toungup |  |  | 60 |  |  |  |
|  |  | Sagaing | Kawlin |  |  | 67 |  |  |  |
|  |  | Shan (South) | Hopong |  |  | 297 |  |  |  |
|  |  |  | Loilen |  |  | 55 |  |  |  |
|  |  |  | Nyaungshwe |  |  | 50 |  |  |  |
|  |  |  | Taunggyi |  |  | 125 |  |  |  |
|  |  | Tanintharyi | Kawthoung |  |  | 55 |  |  |  |
|  |  |  | Kyunsu |  |  | 69 |  |  |  |
|  |  |  | Myeik |  |  | 228 |  |  |  |
|  |  | Yangon | (State/Region-wide) |  |  |  |  |  | 97 |
|  |  | Yangon | Dagon Myothit (Seikkan) |  |  | 170 |  |  |  |
|  |  |  | Dagon Myothit (South) |  |  | 167 |  |  |  |
|  |  |  | Dala |  |  | 216 |  |  |  |
|  |  |  | Hlaingtharya (East) |  |  | 119 |  |  |  |
|  |  |  | Hlaingtharya (West) |  |  | 98 |  |  |  |
|  |  |  | Kawhmu |  |  | 79 |  |  |  |
|  |  |  | Kyauktan |  |  | 240 |  |  |  |
|  |  |  | Kyeemyindaing |  |  | 25 |  |  |  |
|  |  |  | Mingaladon |  |  | 56 |  |  |  |
|  |  |  | Shwepyithar |  |  | 287 |  |  |  |
|  |  |  | Thaketa |  |  | 79 |  |  |  |
|  |  |  | Thanlyin |  |  | 28 |  |  |  |
| TdH | Bring Back Learning of children from the crisis-affected township of Hlaingtharya, Yangon Region by providing Open Learning assistance and EXCEL (Extended and Continuous Education and Learning) curriculum | TOTAL |  | 20,000 | 103 | 103 | 0 | 0 | 0 |
|  |  | Yangon | Hlaingtharya | 20,000 | 103 | 103 |  |  |  |
| WVI-M | Bring Back Learning to Children | TOTAL |  | 2,343 | 8,163 | 0 | 102 | 130 | 0 |
|  |  | Kayin | Hlaingbwe | 724 | 3,424 |  | 27 | 40 |  |
|  |  | Magway | Chauk | 719 | 1,222 |  | 30 | 20 |  |
|  |  | Mandalay | Aungmyaythazan | 433 | 663 |  | 20 | 20 |  |
|  |  | Rakhine | Buthidaung |  | 664 |  |  | 12 |  |
|  |  |  | Maungdaw |  | 205 |  |  | 8 |  |
|  |  | Yangon | Taikkyi | 140 | 1,547 |  | 10 | 15 |  |
|  |  |  | Thanlyin | 327 | 438 |  | 15 | 15 |  |
| KMSS | Providing learning opportunities to children | TOTAL |  | 8,207 | 30,873 | 451 | 257 | 434 | 142 |
|  |  | Chin | Falam | 106 | 3,536 |  |  |  | 17 |
|  |  |  | Hakha | 271 | 3,721 | 25 |  |  | 9 |
|  |  |  | Kanpetlet | 431 | 1,782 |  |  |  | 18 |
|  |  |  | Matupi | 541 | 2,826 |  |  |  | 18 |
|  |  |  | Mindat | 1,654 | 2,367 |  |  |  |  |
|  |  |  | Tedim | 422 | 1,379 | 21 |  |  |  |
|  |  |  | Thantlang | 616 | 5,544 | 25 |  |  |  |
|  |  |  | Tonzang | 451 | 787 |  |  |  |  |
|  |  | Magway | Taungdwingyi | 503 | 798 | 53 | 11 | 18 | 14 |
|  |  | Rakhine | Ann | 245 | 1,038 | 17 | 16 | 32 | 1 |
|  |  | Sagaing | shwebo | 584 | 942 | 45 | 10 | 30 | 32 |
|  |  |  | Kale | 318 | 1,145 | 20 | 12 | 19 | 17 |
|  |  | Shan (South) | Pekon | 838 | 1,737 | 40 | 20 | 40 | 2 |
|  |  |  | Nyaungshwe | 668 | 2,127 | 78 | 20 | 40 | 2 |
|  |  | Ayeyarwady | Danubyu | 215 | 286 |  | 12 | 11 | 4 |
|  |  |  | Labutta | 204 | 563 | 127 | 11 | 10 |  |
|  |  |  | Zalun | 140 | 295 |  | 6 | 5 |  |
|  |  | Chin | Falam |  |  |  | 9 | 18 |  |
|  |  |  | Hakha |  |  |  | 12 | 28 | 1 |
|  |  |  | Kanpetlet |  |  |  | 13 |  |  |
|  |  |  | Matupi |  |  |  | 12 | 26 |  |
|  |  |  | Mindat |  |  |  | 10 |  |  |
|  |  |  | Tedim |  |  |  | 10 | 22 | 1 |
|  |  |  | Thantlang |  |  |  | 14 | 37 | 1 |
|  |  |  | Tonzang |  |  |  | 10 | 10 |  |
|  |  | Magway | Taungdwingyi |  |  |  | 11 | 18 | 1 |
|  |  | Rakhine | Ann |  |  |  | 16 | 21 | 1 |
|  |  | Sagaing | Kale |  |  |  | 10 | 30 | 1 |
|  |  |  | shwebo |  |  |  | 12 | 19 | 2 |
| SF | Bringing Back Learning to the Children of Myanmar | TOTAL |  | 6,864 | 4,858 | 0 | 0 | 0 | 415 |
|  |  | Ayeyarwady | Labutta |  | 350 |  |  |  | 3 |
|  |  |  | Mawlamyinegyun |  | 199 |  |  |  | 3 |
|  |  |  | Pyapon |  | 105 |  |  |  |  |
|  |  | Bago (East) | Oktwin | 355 | 710 |  |  |  | 4 |
|  |  | Magway | Magway | 312 | 270 |  |  |  | 11 |
|  |  |  | Minbu | 313 | 626 |  |  |  | 26 |
|  |  |  | Myaing | 479 |  |  |  |  | 5 |
|  |  |  | Natmauk | 45 |  |  |  |  | 24 |
|  |  |  | Pakokku | 183 |  |  |  |  | 34 |
|  |  |  | Pauk | 546 |  |  |  |  | 8 |
|  |  |  | Pwintbyu | 985 | 1,948 |  |  |  | 19 |
|  |  |  | Saw | 152 |  |  |  |  | 35 |
|  |  |  | Tilin |  |  |  |  |  | 12 |
|  |  |  | Yesagyo | 241 |  |  |  |  | 31 |
|  |  | Mandalay | Meiktila | 251 | 502 |  |  |  | 3 |
|  |  |  | Nyaung-U | 74 | 148 |  |  |  | 5 |
|  |  | Sagaing | Budalin |  |  |  |  |  | 9 |
|  |  |  | Kale | 325 |  |  |  |  | 17 |
|  |  |  | Kanbalu | 207 |  |  |  |  | 15 |
|  |  |  | Kani | 221 |  |  |  |  | 6 |
|  |  |  | Katha | 425 |  |  |  |  | 5 |
|  |  |  | Mingin | 160 |  |  |  |  | 8 |
|  |  |  | Monywa | 525 |  |  |  |  | 9 |
|  |  |  | Sagaing | 215 |  |  |  |  | 57 |
|  |  |  | Salingyi | 127 |  |  |  |  | 6 |
|  |  |  | Tigyaing | 322 |  |  |  |  | 6 |
|  |  |  | Wuntho | 221 |  |  |  |  | 8 |
|  |  |  | Yinmarbin | 180 |  |  |  |  | 46 |
|  | GRAND TOTAL |  |  | 81,719 | 104,194 | 23,427 | 3,327 | 1,155 | 853 |

| Partner's Name | Project Title | State/ Region | Township | Output 1 | Output 2 | Output 3 | Output 1 | Output 2 | Output 3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BDA | Bring Back Learning to Primary Children through Short Term-Home Base Learning materials, Psychosocial Support and WASH Hygiene Promotion in Monywa Township | Sagaing | Monywa |  | 8622 |  |  | 153 |  |
| KBC | Bring Back Learning to Children | Kachin | Bhamo | 532 |  | 332 | 405 |  |  |
| KBC |  |  | Chipwi |  |  | 238 | 35 |  |  |
| KBC |  |  | Myitkyina | 19472 |  |  |  |  |  |
| KBC |  |  | Nawngmun |  |  | 50 |  |  |  |
| KBC |  |  | Waingmaw | 1651 |  |  | 60 |  |  |
| KBC |  | Mandalay | Pyinoolwin | 642 |  | 140 | 30 |  |  |
| KBC |  | Shan (East) | Kengtung |  |  | 130 |  |  |  |
| KBC |  | Shan (North) | Kutkai |  |  | 200 |  |  |  |
| KBC |  |  | Lashio |  |  | 200 | 30 |  |  |
| KBC |  |  | Mongmit |  |  | 60 |  |  |  |
| KBC |  |  | Muse |  |  |  | 30 |  |  |
| KBC | Improve Education access and Bring back learning activities for conflict-affected childen and adolescens in Kachin, Shan State and Sagaing Region | Kachin | Mogaung | 1480 |  | 333 | 30 |  |  |
| KBC |  |  | Momauk |  |  | 199 |  |  |  |
| KBC |  |  | Myitkyina |  |  | 647 |  |  |  |
| KBC |  |  | Puta-O |  |  | 317 |  |  |  |
| KBC |  |  | Sumprabum | 960 |  | 251 | 30 |  |  |
| KBC |  |  | Waingmaw | 701 |  | 1437 |  |  |  |
| KBC |  |  | Chipwi |  |  | 300 |  |  |  |
| KBC |  |  | Mansi |  |  | 150 |  |  |  |
| KBC |  |  | Mohnyin |  |  | 150 |  |  |  |
| KBC |  |  | Nawngmun |  |  | 50 |  |  |  |
| KBC |  | Shan (East) | Kengtung | 36 |  |  |  |  |  |
| KBC SM | Bring Back Learning to Children | Ayeyarwady | Bogale | 193 | 524 |  |  |  |  |
|  |  |  | Danubyu | 103 | 187 |  |  |  |  |
|  |  |  | Dedaye | 29 | 118 |  |  |  |  |
|  |  |  | Einme | 455 | 1401 | 211 | 16 |  |  |
|  |  |  | Hinthada | 190 | 368 |  | 108 |  |  |
|  |  |  | Ingapu | 72 | 143 |  |  |  |  |
|  |  |  | Kangyidaunt | 250 | 715 | 63 |  |  |  |
|  |  |  | Kyaiklat | 151 | 221 |  |  |  |  |
|  |  |  | Kyaunggon | 335 | 1066 |  |  |  |  |
|  |  |  | Kyonpyaw | 30 | 82 |  |  |  |  |
|  |  |  | Labutta | 74 | 343 | 122 |  |  |  |
|  |  |  | Maubin | 100 | 576 | 102 |  |  |  |
|  |  |  | Mawlamyinegyun | 221 | 571 |  |  |  |  |
|  |  |  | Myanaung | 23 | 34 |  |  |  |  |
|  |  |  | Myaungmya | 772 | 1595 |  | 42 |  |  |
|  |  |  | Ngapudaw | 1294 | 4546 | 212 | 82 |  |  |
|  |  |  | Nyaungdon | 16 | 15 |  |  |  |  |
|  |  |  | Pantanaw | 38 | 190 |  |  |  |  |
|  |  |  | Pathein | 1276 | 3088 | 572 | 280 |  |  |
|  |  |  | Pyapon | 133 | 279 |  |  |  |  |
|  |  |  | Thabaung |  | 334 | 140 |  |  |  |
|  |  |  | Zalun | 133 | 327 |  |  |  |  |
|  |  | Bago (East) | Bago | 63 | 376 |  |  |  |  |
|  |  |  | Daik-U | 27 |  |  | 4 |  |  |
|  |  |  | Htantabin | 495 | 1540 |  |  |  |  |
|  |  |  | Kyaukkyi | 1390 | 2248 | 589 | 238 |  | 20 |
|  |  |  | Kyauktaga | 667 | 1177 |  | 14 |  |  |
|  |  |  | Nyaunglebin |  |  |  | 30 |  |  |
|  |  |  | Oktwin | 21 | 70 |  |  |  |  |
|  |  |  | Phyu | 115 | 306 |  |  |  |  |
|  |  |  | Shwegyin | 111 | 223 |  | 4 |  |  |
|  |  |  | Taungoo | 223 | 765 |  | 60 |  |  |
|  |  |  | Waw | 14 | 36 |  |  |  |  |
|  |  |  | Yedashe | 24 | 87 |  |  |  |  |
|  |  | Bago (West) | Letpadan | 60 | 108 |  |  |  |  |
|  |  |  | Minhla | 53 | 73 |  |  |  |  |
|  |  |  | Nattalin | 21 | 52 |  |  |  |  |
|  |  |  | Okpho | 57 | 210 |  |  |  |  |
|  |  |  | Thayarwady | 103 | 282 |  | 76 |  |  |
|  |  | Kachin | Hpakant | 7 | 48 |  | 2 | 2 |  |
|  |  |  | Myitkyina | 15 | 67 |  | 2 | 2 |  |
|  |  | Kayah | Demoso | 1570 | 3933 | 564 | 106 |  | 25 |
|  |  |  | Loikaw | 249 | 631 |  | 46 |  |  |
|  |  |  | Mese | 281 | 781 |  |  |  |  |
|  |  |  | Bawlake |  |  |  | 4 |  |  |
|  |  |  | Hpruso |  |  |  | 18 |  |  |
|  |  |  | Mese |  |  |  | 4 |  |  |
|  |  | Kayin | (State/Region-wide) |  | 42 |  |  |  |  |
|  |  |  | Hlaingbwe | 88 | 180 |  |  |  |  |
|  |  |  | Hpa-An | 39 | 134 |  | 122 |  |  |
|  |  |  | Hpapun | 183 | 258 |  |  |  |  |
|  |  |  | Kawkareik | 124 | 216 |  | 4 |  |  |
|  |  |  | Kyainseikgyi | 1173 | 1698 |  | 52 |  |  |
|  |  |  | Kyainseikgyi | 213 | 227 |  | 208 |  | 52 |
|  |  |  | Myawaddy | 75 | 116 |  | 2 | 2 |  |
|  |  |  | Thandaunggyi | 1283 | 4636 | 935 | 208 |  | 52 |
|  |  | Mandalay | Meiktila | 26 | 66 |  | 2 | 2 |  |
|  |  |  | Pyinoolwin | 9 | 19 |  | 2 | 2 |  |
|  |  | Nay Pyi Taw | Pyinmana | 111 | 149 |  | 2 | 2 |  |
|  |  | Sagaing | Katha | 12 | 24 |  | 2 | 2 |  |
|  |  |  | Tigyaing | 21 | 59 |  |  |  |  |
|  |  | Shan (North) | Lashio | 6 | 20 |  | 2 | 2 |  |
|  |  |  | Mabein | 10 | 24 |  | 2 | 2 |  |
|  |  |  | Namtu | 23 | 80 |  | 4 | 4 |  |
|  |  |  | Tangyan | 5 | 11 |  | 2 | 2 |  |
|  |  | Shan (South) | Kalaw |  | 21 |  | 2 | 2 |  |
|  |  |  | Monghsu | 7 | 19 |  | 2 | 2 |  |
|  |  |  | Pinlaung | 3 | 19 |  | 2 | 2 |  |
|  |  | Tanintharyi | Dawei | 520 | 1247 |  | 56 |  |  |
|  |  |  | Myeik |  |  |  | 76 |  |  |
|  |  |  | Palaw |  |  |  | 34 |  |  |
|  |  |  | Thayetchaung | 43 | 40 |  | 2 |  |  |
|  |  | Yangon | (State/Region-wide) |  |  |  | 185 |  |  |
|  |  |  | Ahlone | 21 | 28 |  | 2 |  |  |
|  |  |  | Hlegu | 30 | 76 |  |  |  |  |
|  |  |  | Hmawbi | 161 | 235 |  |  |  |  |
|  |  |  | Htantabin | 98 | 285 |  |  |  |  |
|  |  |  | Shwepyithar | 45 | 42 |  |  |  |  |
|  |  |  | Taikkyi | 69 | 179 |  |  |  |  |
|  |  |  | Thanlyin | 7 | 21 |  | 2 |  |  |
| MBC | Bring Back Learning to Children and Adolescents | Ayeyarwady | Pantanaw |  |  |  |  | 4 |  |
|  |  | Chin | Tedim | 468 | 3066 | 571 | 2 | 32 | 19 |
|  |  |  | Tonzang | 32 | 477 | 63 |  |  | 5 |
|  |  | Kayin | Hpa-An | 172 | 393 |  | 18 |  |  |
|  |  | Mandalay | Pyinoolwin |  |  |  |  | 3 |  |
|  |  | Rakhine | Ann | 110 | 210 |  | 6 |  |  |
|  |  |  | Minbya | 60 | 199 |  | 2 |  |  |
|  |  |  | Myebon | 239 | 1131 |  | 17 | 33 |  |
|  |  | Sagaing | Hkamti | 84 | 306 |  | 6 | 56 |  |
|  |  |  | Homalin | 39 | 201 |  | 3 |  |  |
|  |  |  | Lahe | 150 | 517 |  | 13 |  |  |
|  |  |  | Lay Shi | 125 | 742 |  | 11 | 20 |  |
|  |  | Shan (East) | Kengtung | 234 | 716 | 54 | 22 | 34 | 4 |
|  |  |  | Monghpyak | 20 |  |  | 1 |  |  |
|  |  |  | Monghsat | 45 | 451 | 31 | 3 | 4 | 4 |
|  |  |  | Tachileik | 84 | 502 |  | 10 | 5 |  |
|  |  | Shan (North) | Hopang | 141 | 154 |  | 9 | 3 |  |
|  |  |  | Hseni | 25 |  |  | 1 |  |  |
|  |  |  | Kutkai | 67 | 147 |  | 4 |  |  |
|  |  |  | Lashio | 174 | 212 | 137 | 13 | 6 | 10 |
|  |  |  | Manton |  | 43 |  |  | 2 |  |
|  |  |  | Mongmit | 85 | 260 |  | 6 |  |  |
|  |  |  | Tangyan | 255 | 405 |  | 9 |  |  |
|  |  | Shan (South) | Loilen | 20 | 84 |  |  | 2 |  |
|  |  |  | Mongnai | 20 | 138 |  | 1 |  |  |
|  |  |  | Nansang | 26 | 548 |  | 2 |  |  |
|  |  |  | Taunggyi | 20 | 376 |  | 2 |  |  |
|  |  |  | Nyaungshwe |  |  |  |  | 1 |  |
|  |  |  | Taunggyi |  |  |  | 2 | 39 |  |
|  |  | Tanintharyi | Tanintharyi | 77 | 122 |  | 10 | 1 |  |
|  |  | Yangon | Ahlone |  |  |  |  | 72 |  |
| METTA | Bring Back Learning to Children | Kachin | Momauk |  |  | 997 |  |  |  |
|  |  |  | Waingmaw |  |  | 2640 |  |  |  |
|  |  |  | Mansi |  |  |  |  |  | 3 |
|  |  | Shan (North) | Lashio | 113 |  |  | 3 | 17 | 2 |
|  |  |  | Manton | 68 | 268 |  | 5 | 20 |  |
|  |  |  | Namtu | 19 |  |  | 4 | 5 | 1 |
|  |  |  | Hseni |  |  |  |  | 1 |  |
|  |  |  | Kunlong |  |  |  | 2 | 8 |  |
|  |  |  | Kutkai |  |  |  | 15 | 32 | 2 |
|  |  |  | Muse |  |  |  | 2 | 3 |  |
|  |  |  | Namhkan |  |  |  | 1 | 5 |  |
| MLRC | Capacity building to NGO partners on NFE_Bring Back Learning to Children | Mon | Bilin |  |  | 153 |  |  |  |
|  |  |  | Chaungzon |  |  | 106 |  |  |  |
|  |  |  | Kyaikmaraw |  |  | 21 |  |  |  |
|  |  |  | Kyaikto |  |  | 98 |  |  |  |
|  |  |  | Mawlamyine |  |  | 105 |  |  |  |
|  |  |  | Mudon |  |  | 205 |  |  |  |
|  |  |  | Paung |  |  | 87 |  |  |  |
|  |  |  | Thanbyuzayat |  |  | 59 |  |  |  |
|  |  |  | Thaton |  |  | 69 |  |  |  |
|  |  |  | Ye |  |  | 22 |  |  |  |
|  |  | Ayeyarwady | Dedaye |  |  | 49 |  |  |  |
|  |  |  | Einme |  |  | 82 |  |  |  |
|  |  |  | Hinthada |  |  | 111 |  |  |  |
|  |  |  | Ingapu |  |  | 68 |  |  |  |
|  |  |  | Kyaiklat |  |  | 150 |  |  |  |
|  |  |  | Kyangin |  |  | 83 |  |  |  |
|  |  |  | Kyaunggon |  |  | 110 |  |  |  |
|  |  |  | Kyonpyaw |  |  | 77 |  |  |  |
|  |  |  | Lemyethna |  |  | 142 |  |  |  |
|  |  |  | Maubin |  |  | 111 |  |  |  |
|  |  |  | Myaungmya |  |  | 41 |  |  |  |
|  |  |  | Pantanaw |  |  | 134 |  |  |  |
|  |  |  | Pyapon |  |  | 272 |  |  |  |
|  |  |  | Wakema |  |  | 80 |  |  |  |
|  |  | Bago (East) | Kyauktaga |  |  | 47 |  |  |  |
|  |  |  | Taungoo |  |  | 20 |  |  |  |
|  |  |  | Waw |  |  | 26 |  |  |  |
|  |  |  | Yedashe |  |  | 65 |  |  |  |
|  |  | Bago (West) | Gyobingauk |  |  | 12 |  |  |  |
|  |  |  | Letpadan |  |  | 52 |  |  |  |
|  |  |  | Minhla |  |  | 51 |  |  |  |
|  |  |  | Padaung |  |  | 33 |  |  |  |
|  |  |  | Paukkhaung |  |  | 7 |  |  |  |
|  |  |  | Paungde |  |  | 25 |  |  |  |
|  |  |  | Pyay |  |  | 114 |  |  |  |
|  |  |  | Thegon |  |  | 101 |  |  |  |
|  |  | Kayin | Hlaingbwe |  |  | 109 |  |  |  |
|  |  |  | Kawkareik |  |  | 236 |  |  |  |
|  |  |  | Kyainseikgyi |  |  | 131 |  |  |  |
|  |  |  | Myawaddy |  |  | 487 |  |  |  |
|  |  | Magway | Magway |  |  | 190 |  |  |  |
|  |  |  | Minbu |  |  | 6 |  |  |  |
|  |  |  | Myothit |  |  | 24 |  |  |  |
|  |  |  | Salin |  |  | 16 |  |  |  |
|  |  | Mandalay | Aungmyaythazan |  |  | 64 |  |  |  |
|  |  |  | Chanmyathazi |  |  | 20 |  |  |  |
|  |  |  | Madaya |  |  | 98 |  |  |  |
|  |  |  | Myingyan |  |  | 59 |  |  |  |
|  |  |  | Nyaung-U |  |  | 48 |  |  |  |
|  |  |  | Pyigyitagon |  |  | 479 |  |  |  |
|  |  |  | Pyinoolwin |  |  | 177 |  |  |  |
|  |  | Nay Pyi Taw | Pyinmana |  |  | 54 |  |  |  |
|  |  | Rakhine | Ann |  |  | 181 |  |  |  |
|  |  |  | Gwa |  |  | 5 |  |  |  |
|  |  |  | Kyaukpyu |  |  | 66 |  |  |  |
|  |  |  | Kyauktaw |  |  | 246 |  |  |  |
|  |  |  | Mrauk-U |  |  | 578 |  |  |  |
|  |  |  | Myebon |  |  | 268 |  |  |  |
|  |  |  | Rathedaung |  |  | 301 |  |  |  |
|  |  |  | Sittwe |  |  | 128 |  |  |  |
|  |  |  | Thandwe |  |  | 157 |  |  |  |
|  |  |  | Toungup |  |  | 60 |  |  |  |
|  |  | Sagaing | Kawlin |  |  | 67 |  |  |  |
|  |  | Shan (South) | Hopong |  |  | 297 |  |  |  |
|  |  |  | Loilen |  |  | 55 |  |  |  |
|  |  |  | Nyaungshwe |  |  | 50 |  |  |  |
|  |  |  | Taunggyi |  |  | 125 |  |  |  |
|  |  | Tanintharyi | Kawthoung |  |  | 55 |  |  |  |
|  |  |  | Kyunsu |  |  | 69 |  |  |  |
|  |  |  | Myeik |  |  | 228 |  |  |  |
|  |  | Yangon | (State/Region-wide) |  |  |  |  |  | 97 |
|  |  | Yangon | Dagon Myothit (Seikkan) |  |  | 170 |  |  |  |
|  |  |  | Dagon Myothit (South) |  |  | 167 |  |  |  |
|  |  |  | Dala |  |  | 216 |  |  |  |
|  |  |  | Hlaingtharya (East) |  |  | 119 |  |  |  |
|  |  |  | Hlaingtharya (West) |  |  | 98 |  |  |  |
|  |  |  | Kawhmu |  |  | 79 |  |  |  |
|  |  |  | Kyauktan |  |  | 240 |  |  |  |
|  |  |  | Kyeemyindaing |  |  | 25 |  |  |  |
|  |  |  | Mingaladon |  |  | 56 |  |  |  |
|  |  |  | Shwepyithar |  |  | 287 |  |  |  |
|  |  |  | Thaketa |  |  | 79 |  |  |  |
|  |  |  | Thanlyin |  |  | 28 |  |  |  |
| TdH | Bring Back Learning of children from the crisis-affected township of Hlaingtharya, Yangon Region by providing Open Learning assistance and EXCEL (Extended and Continuous Education and Learning) curriculum | Yangon | Hlaingtharya | 20000 | 103 | 103 |  |  |  |
| WVI-M | Bring Back Learning to Children | Kayin | Hlaingbwe | 724 | 3424 |  | 27 | 40 |  |
|  |  | Magway | Chauk | 719 | 1222 |  | 30 | 20 |  |
|  |  | Mandalay | Aungmyaythazan | 433 | 663 |  | 20 | 20 |  |
|  |  | Rakhine | Buthidaung |  | 664 |  |  | 12 |  |
|  |  |  | Maungdaw |  | 205 |  |  | 8 |  |
|  |  | Yangon | Taikkyi | 140 | 1547 |  | 10 | 15 |  |
|  |  |  | Thanlyin | 327 | 438 |  | 15 | 15 |  |
| KMSS | Providing learning opportunities to children | Chin | Falam | 106 | 3536 |  |  |  | 17 |
|  |  |  | Hakha | 271 | 3721 | 25 |  |  | 9 |
|  |  |  | Kanpetlet | 431 | 1782 |  |  |  | 18 |
|  |  |  | Matupi | 541 | 2826 |  |  |  | 18 |
|  |  |  | Mindat | 1654 | 2367 |  |  |  |  |
|  |  |  | Tedim | 422 | 1379 | 21 |  |  |  |
|  |  |  | Thantlang | 616 | 5544 | 25 |  |  |  |
|  |  |  | Tonzang | 451 | 787 |  |  |  |  |
|  |  | Magway | Taungdwingyi | 503 | 798 | 53 | 11 | 18 | 14 |
|  |  | Rakhine | Ann | 245 | 1038 | 17 | 16 | 32 | 1 |
|  |  | Sagaing | shwebo | 584 | 942 | 45 | 10 | 30 | 32 |
|  |  |  | Kale | 318 | 1145 | 20 | 12 | 19 | 17 |
|  |  | Shan (South) | Pekon | 838 | 1737 | 40 | 20 | 40 | 2 |
|  |  |  | Nyaungshwe | 668 | 2127 | 78 | 20 | 40 | 2 |
|  |  | Ayeyarwady | Danubyu | 215 | 286 |  | 12 | 11 | 4 |
|  |  |  | Labutta | 204 | 563 | 127 | 11 | 10 |  |
|  |  |  | Zalun | 140 | 295 |  | 6 | 5 |  |
|  |  | Chin | Falam |  |  |  | 9 | 18 |  |
|  |  |  | Hakha |  |  |  | 12 | 28 | 1 |
|  |  |  | Kanpetlet |  |  |  | 13 |  |  |
|  |  |  | Matupi |  |  |  | 12 | 26 |  |
|  |  |  | Mindat |  |  |  | 10 |  |  |
|  |  |  | Tedim |  |  |  | 10 | 22 | 1 |
|  |  |  | Thantlang |  |  |  | 14 | 37 | 1 |
|  |  |  | Tonzang |  |  |  | 10 | 10 |  |
|  |  | Magway | Taungdwingyi |  |  |  | 11 | 18 | 1 |
|  |  | Rakhine | Ann |  |  |  | 16 | 21 | 1 |
|  |  | Sagaing | Kale |  |  |  | 10 | 30 | 1 |
|  |  |  | shwebo |  |  |  | 12 | 19 | 2 |
| SF | Bringing Back Learning to the Children of Myanmar | Ayeyarwady | Labutta |  | 350 |  |  |  | 3 |
|  |  |  | Mawlamyinegyun |  | 199 |  |  |  | 3 |
|  |  |  | Pyapon |  | 105 |  |  |  |  |
|  |  | Bago (East) | Oktwin | 355 | 710 |  |  |  | 4 |
|  |  | Magway | Magway | 312 | 270 |  |  |  | 11 |
|  |  |  | Minbu | 313 | 626 |  |  |  | 26 |
|  |  |  | Myaing | 479 |  |  |  |  | 5 |
|  |  |  | Natmauk | 45 |  |  |  |  | 24 |
|  |  |  | Pakokku | 183 |  |  |  |  | 34 |
|  |  |  | Pauk | 546 |  |  |  |  | 8 |
|  |  |  | Pwintbyu | 985 | 1948 |  |  |  | 19 |
|  |  |  | Saw | 152 |  |  |  |  | 35 |
|  |  |  | Tilin |  |  |  |  |  | 12 |
|  |  |  | Yesagyo | 241 |  |  |  |  | 31 |
|  |  | Mandalay | Meiktila | 251 | 502 |  |  |  | 3 |
|  |  |  | Nyaung-U | 74 | 148 |  |  |  | 5 |
|  |  | Sagaing | Budalin |  |  |  |  |  | 9 |
|  |  |  | Kale | 325 |  |  |  |  | 17 |
|  |  |  | Kanbalu | 207 |  |  |  |  | 15 |
|  |  |  | Kani | 221 |  |  |  |  | 6 |
|  |  |  | Katha | 425 |  |  |  |  | 5 |
|  |  |  | Mingin | 160 |  |  |  |  | 8 |
|  |  |  | Monywa | 525 |  |  |  |  | 9 |
|  |  |  | Sagaing | 215 |  |  |  |  | 57 |
|  |  |  | Salingyi | 127 |  |  |  |  | 6 |
|  |  |  | Tigyaing | 322 |  |  |  |  | 6 |
|  |  |  | Wuntho | 221 |  |  |  |  | 8 |
|  |  |  | Yinmarbin | 180 |  |  |  |  | 46 |
|  | GRAND TOTAL |  |  | 81,719 | 104,194 | 23,427 | 3,327 | 1,155 | 853 |

Region and Site Selection Criteria

OOSC, IP Coverage and Number of IP, UNESCO Site Selection

|  | Children Population (Est.) | Poverty Rate - headcount | Urban Poulation (UNFPA, 2019) | OOSC (Est.) |  | PIN 2023 | IP coverage- all edu pro (Jan to Oct 2022) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| State | Total Number | % | % | Total Number | % | Total Number | BBL covered | No. Township | % | IP |
| Ayeyarwady | 2,056,819 | 31.7 | 14.3 | 148,504 | 7% | 69,207 | 25 | 26 | 96% | 7 |
| Bago | 1,520,335 | 17.4 | 18 | 367,688 | 24% | 288,618 | 23 | 28 | 82% | 7 |
| Chin | 252,499 | 58 | 20.2 | 86,814 | 34% | 107,214 | 9 | 9 | 100% | 8 |
| Kachin | 671,845 | 36.6 | 32.1 | 131,731 | 20% | 171,984 | 14 | 18 | 78% | 7 |
| Kayah | 106,954 | 32 | 21.3 | 33,177 | 31% | 89,670 | 7 | 7 | 100% | 5 |
| Kayin | 661,865 | 24.2 | 18.5 | 120,989 | 18% | 154,691 | 7 | 7 | 100% | 16 |
| Magway | 1,187,533 | 35.6 | 13.7 | 343,656 | 29% | 342,682 | 13 | 25 | 52% | 5 |
| Mandalay | 1,927,296 | 13.2 | 32.1 | 536,579 | 28% | 300,366 | 15 | 28 | 54% | 9 |
| Mon | 655038 | 19.2 | 25.7 | 89,333 | 14% | 88,766 | 10 | 10 | 100% | 6 |
| Nay Pyi Taw | 362,798 | 22.1 | 26 | 29,027 | 8% | 16,901 | 1 | 8 | 13% | 2 |
| Rakhine | 1,217,268 | 41.6 | 16.7 | 120,546 | 10% | 426,734 | 14 | 17 | 82% | 12 |
| Sagaing | 1,801,140 | 30.7 | 16.7 | 876,053 | 49% | 1,074,200 | 21 | 37 | 57% | 9 |
| Shan | 2,377,411 | 28.6 | 29.1 | 260,290 | 11% | 337,117 | 31 | 81 | 38% | 14 |
| Tanintharyi | 564,053 | 13.2 | 23.7 | 191,744 | 34% | 159,842 | 8 | 10 | 80% | 4 |
| Yangon | 2,350,783 | 13.7 | 69.1 | 397,579 | 17% | 147,078 | 18 | 47 | 38% | 7 |
| Total | 17,713,637 |  |  | 3,733,710 | 334% | 3,775,070 | 216 | 358 |  |  |

Site Selection for Site Evaluation Visits

|  | Poverty Rate headcount % | Urban Poulation % | OOSC (Est.) | OOSC (Est.) | Townships |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| State | % | % | Total Number | % | No | covered | % Covered | IP |
| Ayeyarwady | 31.7 | 14.3 | 148,504 | 7% | 26 | 25 | 96% | 7 |
| Bago | 17.4 | 18 | 367,688 | 24% | 28 | 23 | 82% | 7 |
| Chin | 58 | 20.2 | 86,814 | 34% | 9 | 9 | 100% | 8 |
| Kachin | 36.6 | 32.1 | 131,731 | 20% | 18 | 14 | 78% | 7 |
| Kayah | 32 | 21.3 | 33,177 | 31% | 7 | 7 | 100% | 5 |
| Kayin | 24.2 | 18.5 | 120,989 | 18% | 7 | 7 | 100% | 16 |
| Magway (Monaway) | 35.6 | 13.7 | 343,656 | 29% | 25 | 13 | 52% | 5 |
| Mandalay | 13.2 | 32.1 | 536,579 | 28% | 28 | 15 | 54% | 9 |
| Mon | 19.2 | 25.7 | 89,333 | 14% | 10 | 10 | 100% | 6 |
| Nay Pyi Taw | 22.1 | 26 | 29,027 | 8% | 8 | 1 | 13% | 2 |
| Rakhine | 41.6 | 16.7 | 120,546 | 10% | 17 | 14 | 82% | 12 |
| Sagaing (Safe) | 30.7 | 16.7 | 876,053 | 49% | 37 | 21 | 57% | 9 |
| Shan | 28.6 | 29.1 | 260,290 | 11% | 81 | 31 | 38% | 14 |
| Tanintharyi | 13.2 | 23.7 | 191,744 | 34% | 10 | 8 | 80% | 4 |
| Yangon | 13.7 | 69.1 | 397,579 | 17% | 47 | 18 | 38% | 7 |

Online Perception Survey

Background

To get a better understanding of stakeholders’ appreciation of the BBL Programme, an online perception survey is administered to a broad range of stakeholders representing Donors, UNICEF, IP and Beneficiaries with knowledge of the BBL Programme as well as at least some knowledge of children rights and protection issues.

It is proposed that the survey be anonymous and administered by the Team Leader using the Google Online Form platform.

Introduction letter

Evaluation of the Bringing Back Learning Programme in Myanmar

OUTLINE ONLINE PERCEPTION SURVEY

Dear……

UNICEF Myanmar has managed the Bringing Back Learning (BBL) Programme since April 2021.  The BBL Programme is currently being reviewed by an independent evaluator, James Shoobridge.

The BBL programme is UNICEF’s response to the twin crisis which have emerged in Myanmar starting February 2021.  The confluence of recent events has resulted in millions of children and youth now facing significant challenges in accessing and continuing with their education due to a multitude of complex factor, particularly the most vulnerable children with long-lasting consequences for their cognitive development and their socio-economic futures.

This evaluation will assess the Bringing Back Learning programme over the entire project period and across different funding, from June 2021 to June 2023. The evaluation shall provide evidence on how the programme has progressed as envisaged initially, whether its processes have effectively contributed to its stated objectives and achieved the intended results during that period.   The results of the evaluation will help inform BBL programme’s main implementing partners and stakeholders including donors of the project BBL and provide valuable insights into future programming to help achieve the ultimate goal in which no child in Myanmar is left behind.

It is therefore important to understand key stakeholders’ perception about the positive aspects of the BBL and what factors may play a critical role for successes. It is equally important to understand the challenges and how they may be addressed in the future.  To help identify the success stories, the evaluation team has developed a short survey (link inserted below / attached) to which we kindly invite you to respond.

The survey takes about fifteen minutes to complete and seeks the opinion of key partners who, directly or indirectly, support realization of BBL Programme in Myanmar.  The survey complements other data collection tools for the review, namely a document review and interviews.

You participation in the online perception survey is voluntary and your decision to participate or not will not be recorded anywhere. Likewise, while we hope you will answer all questions you might choose only to answer some of the questions. That decision will not be recorded anywhere either. The survey is anonymous and will be administered by the independent evaluator. All information will be kept confidential, so please feel free to express your views!

We hope you will be able to fill in the survey by <date 2023>. If you have any questions don’t hesitate to contact the team leader for the evaluation Mr. James Shoobridge on email: jimshoobridge@hotmail.com.

Name (Optional):

Organisation Name (Optional):

Position (Optional):

Email (Optional):

Gender:  <Select from>: Male, Female, Transgender, gender neutral, non-binary, Other.

About you:  <select from>

- Donor

- Implementation Partner (CSO/NGO)

- Learning Centre Head

- Learning Centre Teacher

Question 1: Please describe in a few lines what you consider to be the BBL Programmes most important success story in Myanmar, that is a BBL initiative or activity which has contributed or is likely to contribute to an important change in the community, or towards individuals.

Question 2: Please identify some key factors that you believe allowed this to become a success story.

- External factors, for instance related to other initiatives happening at the same time, policy changes, local community support etc.

- Internal factors related to the BBL’s approach, thematic focus, geographic focus, role and/or characteristics, for instance its engagement in partnerships, consultations, technical assistance, staff profiles, etc.

Question 3: If you were to recommend others, either in the Myanmar or abroad, to learn from the success story, what would you want them to pay particular attention to when adopting or replicating the success story?

Question 4: What are the things the BBL programme does best that you would like to see it continue doing in the future?

Question 5: In your view, could BBL be doing anything differently to optimize results for children, adolescents, children with disabilities, children speaking ethnic languages and girls?

- In General

- For the most marginalized and vulnerable

Question 6: Are there any other things related to the BBL activities and performance in Myanmar that you would like to share?

Question 7: Please rate the BBL Programmes performance on a scale of 1-5 (5 being excellent, 1 being very poor), for the following areas:

- Relevance:  How relevant do you think BBL Programme has been towards addressing the learning crisis in Myanmar and providing learning opportunities to 5-15 year olds within the community?

  - Scale <Very relevant, relevant, partially relevant, low relevance, not relevant>

  - Please comment (optional):

- Coherence:  How well does the BBL complement and fit in with community level activities to advocate home and community level learning among children?

  - Scale <High coherence, coherent, partially coherent, low coherence, No coherence>

  - Please comment (optional):

- Efficiency:  How would you rate the BBL programme in terms of efficient use of resources and with respect to addressing gender and inclusion related specific objectives/activities?

  - Scale <Highly efficient, efficient, partially efficient, low efficiency, not efficient>

  - Please comment (optional):

- Effectiveness: Do you think the BBL programme has been effective in achieving its goals of re-engaging children to learn at the community level?

  - Scale <Highly effective, effective, partially effective, low effectiveness, not effective>

  - Please comment (optional):

- Sustainability: Do you think the gains made under the BBL programmes will be sustainable when the programme has concluded?

  - Scale <Highly sustainable, sustainable, partially sustainable, low sustainability, not sustainable>

  - Please comment (optional):

- Gender, Equality, Disability and Social Inclusion: Do you think the BBL programme has adequately understand and address the needs of the most vulnerable in the communitya?

  - Gender: Scale <Highly inclusive, inclusive, partially inclusive, low inclusion, not inclusive>

  - Children With Disabilities: Scale <Highly inclusive, inclusive, partially inclusive, low inclusion, not inclusive>

  - Ethnic Children: Scale <Highly inclusive, inclusive, partially inclusive, low inclusion, not inclusive>

  - Children from Poor Backgrounds: Scale <Highly inclusive, inclusive, partially inclusive, low inclusion, not inclusive>

Question 8:  Final Comments:  Do you have any final comments you would like to say concerning the BBL programme?

Key Informant Questionnaires

## Form 1: Consent Form

For use with: Tool 1, Tool 2, Tool 5

Consent Form for Interviews

Thank you for participating in this interview/focal group discussion concerning the evaluation of the Bringing Back Learning (BBL) Programme. If you are happy to participate then please complete and sign the form below. Please initial the boxes below to confirm that you agree with each statement:

|  | Please Initial box: |
| --- | --- |
| I confirm that I have listened to the introduction and understood the purpose and conduct of the interview/focal group discussion and have had the opportunity to ask questions. |  |
| I understand that my participation is voluntary and that I am free to withdraw at any time without giving any reason and without there being any negative consequences. In addition, should I not wish to answer any particular question or questions, I am free to decline. |  |
| I understand that my responses will be kept strictly confidential. I understand that my name will not be linked with the evaluation materials, and will not be identified or identifiable in the report or reports that result from the research. I understand that my responses will in no way impact or influence my status within the BBL programme or in any way inhibit my application to future programmes. |  |
| I agree for this interview to be tape-recorded. I understand that the audio recording made of this interview will be used only for analysis for the evaluation. I understand that no other use will be made of the recording without my written permission, and that no one outside the evaluation team will be allowed access to the original recording. |  |
| I agree that my anonymised data will be kept for future evaluation purposes such as publications related to this study after the completion of the study but only to be referenced in anonymous form. |  |
| I agree to take part in this interview/focal group discussion. |  |

________________________	________________         ___________________

Name of participant	Date                                     Signature

_________________________	__________________         _____________________

Principal Evaluator	Date                                     Signature

To be counter-signed and dated in the presence of the participant for face to face interviews

Copies: Once this has been signed by all parties the participant should receive a copy of the signed and dated participant consent form, and introduction statement. A copy of the signed and dated consent form should be placed in the main evaluation file which must be kept in a secure location.

## Form 2: FGD and Case Study Informed Parental and Student Consent Form

For use with Tools 4 and 6

We invite you and your child to take part in an evaluation being conducted by [Principal Investigator’s name] who is working under the Bring Back Learning Programme supported by UNICEF and Partners,

The evaluation, as well as your rights as a participant, are described below.

Description: This study will examine children’s experiences under the Bring Back Learning Programme.  Your child’s identity will not be revealed to anyone.  Children’s answers will be not be associated with any identifying information.   The evaluator may take written notes during the interview or group discussion.

Signature Risks & Benefits: There are no risks to you or your child’s safety. You may opt to review the notes taken at any time.

I understand that I or my child has the right to stop participating in the interview or refuse to respond to any questions at any time.

Grievance Procedure: If I have any concerns or am dissatisfied with any aspect of this evaluation you may report my grievances anonymously if desired to the UNICEF directly by emailing to Aye Myint Than Htay at the following email address: amthtay@unicef.org

Questions: Please feel free to ask the evaluator any questions before signing the consent form or at any time during or after the study.

Principal evaluator: [Full Name]

I agree for

- myself

- My Child

to participate in the Evaluation of the Bring Back Learning Programme:

- Focal Discussion Group

- Case study discussion

Consent Statement I, ______________, give permission for my child, _______________ to participate in the evaluation titled , “Evaluation of the Bring Back Learning Programme”. The evaluation has been explained to me and my questions answered to my satisfaction. I understand that my child’s right to withdraw from participating or refuse to participate will be respected and that his/her responses and identity will be kept confidential and will not be shared with identifying information.

I give this consent voluntarily.

Parent/Guardian Signature: _________________________________ _______________________

Facility Supervisor/Head Signature ________________________________________

Signature Investigator Signature: _________________________________

Signature Date: _____________

Ensure one copy is retained by the parent/guardian and one copy by the investigator/enumerator.

## Form 3: Facilitator (Teacher) Focal Group Discussion (FGD) Introduction and General Guidelines

For use with Tools 3

Introduction

I would like to thank you all for coming, My name is ............................................................................. and I am undertaking an independent evaluation of the Bringing Back Learning Programme (BBL) on behalf of UNICEF. Your input will help us in evaluating and determining recommendations for future changes and expansions to the programme which could benefit many children throughout Myanmar.

You are kindly requested to provide answers about the topic based on your current experience and personal opinion of this programme.  Do not worry about giving your opinion with full transparency; all names will be kept anonymous. There are no right or wrong answers, and you are free to ask for clarification at any time if you do not understand the question. Also, please be assured that the answers you give today will not have any implications for continuing to benefit from the programme. Our discussion will take about 60 to 90 minutes at the most. We want this to be a group discussion, so feel free to participate without waiting to be called on. However, we would appreciate it if only one person speaks at a time. Be assured that all of you will have equal opportunity to express your opinions and please be respectful to opposing attitudes/statements expressed by another participant.  There is a lot we want to discuss, so at times I may move the discussion along a bit.

The discussion taking place will be kept confidential, and your names will be kept anonymous. You can withdraw from the discussion at any time.

1. Ask all participants to turn their phones on silent – indicating that they are allowed to leave temporarily if there is an urgent call.

2. If audio recorded please inform the participants.

3. Ask participants to introduce themselves before you start Questions The moderator will use four types of questions as needed; open-ended, follow-up, probing and prompted questions. In some cases, the moderator will follow a sequence that consists typically of four parts.

1. Starting with the main question and listening for its answer.

2. Then s/he will follow up and inquire about the answer.

3. And probe to clarify.

4. If necessary, they prompt (cue or aide) the probing questions.

Additional Guiding notes for Investigators/Enumerators/Moderator(s)

- Notice body language and expressions as relevant.

- Make sure to listen to participants, non-judgmentally and intervene if others are judging them, reminding them of the respect for other opinions.

- Encourage that only one person talks at a time, and remind people and the interpreter not to go too long in between translation, as you will lose a lot of the detail.

- It can be helpful sometimes, especially in one on one interviews, to put a question in the form of a role play. For example, you might say something like, “imagine I’m the head of a school, what would you say to me?”

- Use neutral comments and encourage the quieter people to contribute – “Anything else?”, “does anyone else have something to add?”, “How about this side of the group?”

- Explain to interpreters the importance of translating sentence-by-sentence and not summarizing what people say. Interviewers should help interpreters by asking only one short question at a time and by reminding them about confidentiality of the discussions.

- keep focus group discussions (FGD) confidential from anyone outside the group

## Form 4: Child / Parent Focal Group Discussion (FGD) Introduction and General Guidelines

For use with Tools 4

Introduction

I would like to thank you all for coming, My name is ............................................................................. and I am undertaking an independent evaluation of the Bringing Back Learning Programme (BBL) on behalf of UNICEF. Your input will help us in evaluating and determining recommendations for future changes and expansions to the programme which could benefit you and many other children throughout Myanmar.

You are kindly requested to provide answers about the topic based on your own experiences while studying and learning during the past two years.  Do not worry about giving your opinion with full transparency; all names will be kept anonymous.

There are no right or wrong answers, and you are free to ask for clarification at any time if you do not understand the question.

Our discussion will take about 30 to 40 minutes at the most. We want this to be a group discussion, so feel free to participate without waiting to be called on. However, we would appreciate it if only one person speaks at a time. Be assured that all of you will have equal opportunity to express your opinions and please be respectful to opposing attitudes/statements expressed by another participant.

The discussion taking place will be kept confidential, and your names will be kept anonymous. You can withdraw from the discussion at any time and you are not required to answer or address a topic or question if you do not want to.

1. Ask all participants to turn their phones on silent – indicating that they are allowed to leave temporarily if there is an urgent call.

3. Ask participants to introduce themselves before you start Questions The moderator will use four types of questions as needed; open-ended, follow-up, probing and prompted questions. In some cases, the moderator will follow a sequence that consists typically of four parts.

1. Starting with the main question and listening for its answer.

2. Then s/he will follow up and inquire about the answer.

3. And probe to clarify.

4. If necessary, they prompt (cue or aide) the probing questions.

Additional Guidelines notes for Children

Welcome the children to the discussion or Case Study

Explain the purpose of the discussion in simple terms and allow for children to ask questions or investigate further. (e.g. to learn about their experiences, opinions, suggestions, etc.)

Set some ground rules

- FGD: Take turns when you talk, there is no rush and we would like to hear everyone’s opinion,

- FGD: Respect each other's opinions, listening carefully, and only one person speaks at a time.

- FGD/Case Study:

  - The discussion is voluntary

  - You are not required to answer every or any question.

  - If you wish to withdraw please do so.

  - If you would like to stop the discussion please let us know and we can end.

Icebreaker

Start with an icebreaker question to help the children feel comfortable and get to know each other. For example, "What is your favourite animal and why?"

Main Discussion

Encourage children to give detailed answers and provide real-life examples based on their experiences or observations.

Conclusion

Summarize the main points discussed during the session and thank the children for their participation.

Finally, allow the children to ask any questions they might have or share any additional thoughts.

Additional Guiding notes for Moderator(s)

- Notice body language and expressions as relevant.

- Make sure to listen to participants, non-judgmentally and intervene if others are judging them, reminding them of the respect for other opinions.

- Encourage that only one person talks at a time, and remind people and the interpreter not to go too long in between translation, as you will lose a lot of the detail.

- It can be helpful sometimes, especially in one on one interviews, to put a question in the form of a role play. For example, you might say something like, “imagine I’m the head of a school, what would you say to me?”

- Use neutral comments and encourage the quieter people to contribute – “Anything else?”, “does anyone else have something to add?”, “How about this side of the group?”

- Explain to interpreters the importance of translating sentence-by-sentence and not summarizing what people say. Interviewers should help interpreters by asking only one short question at a time and by reminding them about confidentiality of the discussion

- Adhere to the Ethical Guidelines for conducting interviews / FGD with children (Form 5)

- keep focus group discussions (FGD) confidential from anyone outside the group

## Form 5: Ethical Guidelines for conducting Interviews/FGD with children

Appropriate for Tools 4 and 6

- Participation is safe : Risks are considered both before and during FGD processes to ensure that children are kept safe.

- This includes ensuring that processes do no harm / further traumatise children (for example not asking children questions about their abuse in open forums); prevent children from being exposed to risks as a result of their participation (for example be subjected to stigma or discrimination as a result of their involvement); and ensuring their emotional, psychological and physical safety during participation processes.

- This also includes careful consideration of confidentiality and anonymity, and circumstances in which it is necessary to break confidentiality, such as where abuse is disclosed.

- Participation is voluntary, Consent / assent is always sought both from children and their caregivers (where available). Children know that they can withdraw from FGD processes at any time, without any negative consequences.

- Children are informed about the purpose of their participation in FGDs. The purpose is understood and felt as meaningful and relevant for them. They are made aware of how their views and opinions will be used and any feedback that will be given to them, in order to make an informed decision regarding whether to participate.

- The use of FGDs with children is meaningful and necessary. Careful consideration is always be given as to whether it is relevant and appropriate to conduct FGDs children, and if information is already known and can be found from other sources or if other data collection methods are more appropriate. Where FGDs are conducted with children, the data obtained is used to inform policy and programmes.

- Participation is Inclusive and non-discriminatory. All children, including those who are marginalised, are able to participate equally, and where necessary special measures are in place to ensure that children who are marginalised can participate fully in FGD processes

- Participation is developmentally appropriate, gender sensitive and culturally relevant. Participation should be an enjoyable and stimulating experience

- Participation is ensured by professionals having the required competencies. They must have the necessary experience and sensitivity to apply developmentally, age, gender and culturally sensitive processes for children. 8) In all situations the best of interest of children is the paramount consideration

- keep focus group discussions (FGD) confidential from anyone outside the group

## Form 6: Introduction Letter to Key Informant Interviews (KII)

For use with Tools 1 and 2

Introduction letter

Evaluation of the Bring Back Learning Programme in Myanmar

Key Informant Interview

Dear……

UNICEF Myanmar has managed the Bringing Back Learning (BBL) Programme since April 2021.  The BBL Programme is currently being reviewed by an independent evaluator.

This evaluation will assess the Bringing Back Learning programme over the entire project period and across different funding, from June 2021 to June 2023. The results of the evaluation will help inform BBL programme’s main implementing partners and stakeholders including donors of the project BBL and provide valuable insights into future programming to help achieve the ultimate goal in which no child in Myanmar is left behind.

It is therefore important to understand your perception about aspects of the BBL and what factors may play a critical role for successes. It is equally important to understand the challenges and how they may be addressed in the future.

The interview will take between 60 and 90 minutes depending on your inputs.   You participation in the interview is voluntary and your decision to participate or not will not be recorded anywhere. You may choose to ignore a question or ask for further clarification as needed. The interview will be referenced anonymously and is been administered by the independent evaluator. All information will be kept confidential, so please feel free to express your views.

## Tool 1: Implementation Partner (IP) KII

Note:  Estimate 2-2.5 hours per IP.  Recommend all relevant staff from an IP attend at once.

Evaluator / Investigator Name:

Organisation Name:

Project name:

Name (Optional):

Position (Optional):

Time in your current position (Optional):

Email (Optional):

Gender:  <Select from>: Male, Female, Transgender, gender neutral, non-binary, Other.

General Introduction Question

Question: Please tell me about your role and experience with the BBL to date

Relevance (Discuss):

- (Q1) In what has your BBL project has been relevant towards providing learning opportunities to 3-18 year olds within the community? (anticipated areas to cover below)

  - Equip education spaces with WASH facilities and other materials to prevent the spread of COVID-19

  - Provide learning opportunities focused on literacy, numeracy, social-emotional learning and life skills for children and adolescents – especially through NFPE, EXCEL, reading enrichment, and open learning.

  - Integrate Mental Health & Psychosocial Support (MHPSS) and child protection into education activities

  - Identify and recruit qualified facilitators/educators to ensure continuity of learning

  - Support facilitators/educators to conduct learning assessments that support children to learn at the right level

  - Conduct outreach to communities so that children most affected by vulnerabilities (such as girls, children with disabilities) are better able to access education

Raising awareness of the importance of re-engaging children in learning.

- (Q2) Has your approach been flexibly adapted to different communities/locations (how/why)?

- (Q3) Describe how the approach aligns with your organisations policies and practice (thematic area of expertise)?

- (Q4) Has the BBL targeted regions/communities impacted by the crisis and are there communities which require assistance which are not currently receiving assistance?

Coherence:

- (Q5) Describe whether the BBL complements and fits in with community level activities to advocate home and community level learning among children?  Is it viewed as an intermediary to return children to formal education (DFA MoE or CSO schools?)

- (Q6) Do you have examples of where the BBL overlaps, aligns with or complements other programmes?

Efficiency:

- (Q7) Was the budget defined adequately and did it make adequate provisions for all important goals, including addressing gender and inclusion related specific objectives/activities?

- (Q8) Were funds and activities delivered in a timely manner?

  - If not, what were the bottlenecks encountered and have banking issues affected financial disbursement?

- (Q9) Have resources (human resources, time, expertise, supplies, transportation, funds etc.) been allocated and used effectively?

- (Q11) Which activities/inputs have been most effective and why?

- (Q11) Looking forward, do you think there are opportunities to use resources more effectively or redirect the approach?

- (Q13/Q14) Have beneficiaries and target groups been involved in decision making during implementation, and if so how?

- (Q14) Have Community, parents/caregivers, community workers, natural community leaders, local organizations, facilitaors/educators, community structures, and other stakeholders been involved in the programme?

Effectiveness:

- Do you think the BBL programme has been effective in achieving its goals of re-engaging children to learn at the community level (why/how)?

- (Q16) What do you think are the major factors that have led to achievement or non-achievement of the BBL’s objectives (most significant activities and why)?

- (Q18) Would you suggest any changes to the programme strategy or management to improve achievement of expected outcomes and impacts?

Sustainability: Do you think the gains made under the BBL programmes will be sustainable when the programme has concluded?

- (Q21) Have you developed / applied a realistic and effective exit strategy?

- (Q22) Do you think the BBL strategy can be scaled up in the future? What would be required (financial, institutional, environmental, technical, and social).

- (Q23) What recommendations would you have for sustainability of the BBL?

- (Q24/Q25) What do you think are the key lessons and recommendations learnt which education sector overall can build on in designing similar projects in the future?

Gender, Equality, Disability and Social Inclusion: Do you think the BBL programme has adequately understand and address the needs of the most vulnerable in the community?

- (Q26) Which activities/aspects have supported a) gender, b) disability, c) Ethnic Children) d) Children from Poor Households?

- (Q28) Did the project budget make adequate provisions for all important goals, e.g. addressing gender and inclusion related specific objectives/activities? (Efficiency)

- (Q29) What factors (activities etc.) of BBL have worked well to achieve results for a) gender (Girls and Boys), b) disability, c) Ethnic Children) d) Children from Poor Households? (Effectiveness and Impact)

- (Q26) Can the BBL be further improved (changed) to better address gender, disability, and other requirements for social inclusion?

- (Q27) Have representatives from women’s groups, OPDs, and other groups for marginalized communities been involved in understanding the needs and response of BBL (how)? (Relevance)

- (Q30) What evidence exists that any gains toward GEDSI will be sustained? What recommendations are there for future projects for sustainable efforts toward GEDSI? (Sustainability)

- (Q16) Discuss the strengths and weaknesses of the BBL Programme

- Strengths

- Weaknesses

- Challenges / Barriers and how (if at all) these were overcome

- (Q16/Q23) Evidence for improvement in learning outcomes

Final Questions:

- Would you like to say any final words before we close?

- Itemize supporting evidence (documents, reports)

## Tool 2: Centre Head KII

Note: Estimate less than 1 hour.  Some Centre Heads may wish to have Facilitators attend

Note:  Each response should be explained (why), justified (evidence) and followed with sub questions where appropriate

Evaluator / Investigator Name:

Implementation Partner name:

Learning Centre name:

State:

District:

Township:

Name (Optional):

Position (Optional):

Time in your current position (Optional):

Email (Optional):

Gender:  <Select from>: Male or Female

General Introduction Question

Question 1: Please tell me about your role and experience with the BBL to date

Relevance:

- (Q2) Describe the type of support you and your centre have received through the BBL?

(Specific teaching and learning materials (textbooks, stationery); Stipends to support cost of education (transportation, buying uniforms, etc.); Temporary learning spaces (physical spaces for learning); Support for transportation to/from education spaces; Training for educators / Facilitators / facilitators)

- (Q2/Q9) Has the training, support and resources you have received been sufficient to help you to reach more children?  Which have been most effective?

- (Q1) Do you think the BBL has helped you to ensure that children attending your centre are receiving an education?

Coherence:

- (Q5) Do you think the BBL complements and fits with the community activities to advocate home and community level learning among children?  If so how?

- (Q15) Do you think the BBL has contributed to reengagement of children to learning at community level?

- (Q5) Are children returning to school (DFA MoE or CSO) and if so has the BBL helped bridge the gap in learning during closure?

Efficiency:

- (Q7) Have you had sufficient training, materials and support for example to help address gender and inclusion related specific objectives/activities?

- (Q8) Were supplies, funds and activities delivered in a timely manner? If not, what were the bottlenecks encountered? Has this affected you in any way?

- (Q10) Were there examples where support, materials or training could have been better?

- (Q13) Have you been asked for feedback from the implementation partner?  If so, how was this gathered and was it used?

- (Q19) Are you measuring learning outcome and graduation rates and has the BBL positively influenced these?

- (Q13)  Do you submit data to the implementation partner concerning enrolment, attendance and learning outcomes? Have you received feedback on this data (how is data captured/stored)?

- (Q14) Has the Community, natural community leaders and local organizations and other stakeholders been involved in the BBL?

Effectiveness and Impact

- (Q16) What have been the biggest challenges you have faced through the BBL?

Sustainability

- (Q21) Do you think the gains from the BBL will be sustained when the programme ends?  Which gains and why?  What are the barriers and opportunities?

- (Q23) What do you think needs to be done to ensure the gains from the BBL are sustained at the programmes end?

Gender, Equality, Disability and Social Inclusion

- (Q26/Q28) Do you think the BBL has addressed the needs of vulnerable children? How?

  - Gender

  - Children with Disabilities

  - Children from Ethnic Backgrounds

  - Children from Poor Families

- (Q27) Have representatives from women’s groups, OPDs, and other groups for marginalized communities been involved in understanding the needs and response of BBL? (Relevance)

- (Q29) What could the BBL be doing to better address the needs of:

  - Girls

  - Boys

  - Children with disabilities

  - Children from poorer families

Change Story (Case study):

Do you have any special cases of children, Facilitators or yourself whose lives may have been changed by the BBL Programme, with particular emphasis on Marginalised children from poorer families, with disabilities or from ethnic groups (refer case study form)?

Final Questions:

- Would you like to say any final words before we close?

- Itemize supporting evidence (documents, reports)

## Tool 3: Facilitators FGD

Note: Estimate to take approximately 1 hour.  Some Centre Heads may wish to attend

Note: There are 5 topics.  It is suggested that no more than 15 minutes be spent on each topic

Note:  Each response should be explained (why), justified (evidence) and followed with sub questions where appropriate

Evaluator / Investigator Name:

Learning Centre Name:

Supporting Implementation Partner Name:

State:

District:

Township:

For each Teacher attending:

Time in your current position (Optional):

Gender:  <Select from>: Male or Female

Employment type: <full time, part time, casual>

Relevance:

Topic 1: (Q13) Discuss your personal involvement in the BBL programme

- (Q9) Your own capacity development and teaching needs.  What you have learnt and gained from the programme

- (Q13) Opportunities for consultation and feedback

- (Q14) Engagement with the community, community leaders, local organizations

Topic 2: (Q1/Q15) Discuss whether you think the BBL has helped you to reach children and engage them in learning (how and why)?

Inputs may include: Specific teaching and learning materials (textbooks, stationery); Stipends to support cost of education (transportation, buying uniforms, etc.); Temporary learning spaces (physical spaces for learning); Support for transportation to/from education spaces; Training for educators / Facilitators / facilitators).

- Overcoming the challenges of the Twin Crisis Situation (Covid19 and the Coup)

- (Q5) Meeting community Needs

- (Q5) Facilitating and encouraging out of school and home learning

- (Q15) Re-engaging children in learning at the community level

- (Q15) Bridging the gap towards re-entering DFA MoE or CSO Schools

Topic 3: (Q16) Discuss the strengths and weaknesses of the BBL Programme

- Strengths

- Weaknesses

- Challenges / Barriers and how (if at all) these were overcome

- (Q16/Q23) Evidence for improvement in learning outcomes

Topic 4: The Sustainability of the BBL Programme

- (Q22) Aspects of the BBL programme that will be sustained after its conclusion and why

- (Q23) Aspects that are at risk of not being sustained, why and what needs to be done to ensure they can be sustained?

Topic 5: Discuss how the BBL has helped address Gender, Equality, Disability and Social Inclusion noting what has been done and what more can be done

- (Q26) Gender

  - Key Issues

  - (Q29) What has been done

  - (Q29) What more should be done

- (Q26) Disability

  - Key Issues

  - (Q29) What has been done

  - (Q29) What more should be done

- (Q26) Ethnic Children and Children from Poor Families

  - Key Issues

  - (Q29) What has been done

  - (Q29) What more should be done

- (Q27) Discuss Involvement from women’s groups, OPDs, and other groups for marginalized communities

Change Story (Case study):

Do you have any special cases of children, Facilitators or yourself whose lives may have been changed by the BBL Programme, with particular emphasis on Marginalised children from poorer families, with disabilities or from ethnic groups (refer case study form)?

Final Questions:

Final Comments: Would you like to say any final words before we close?

## Tool 4: Parents, Caregivers, Community Members of the Parent Committee and Students FGD

Note: Estimate to take less than 45 minutes.  Some Centre Heads or Facilitators may wish to attend

Note: There are 5 topics.  It is suggested that no more than 10 minutes be spent on each topic

Note:  Each response should be explained (why), justified (evidence) and followed with sub questions where appropriate

Note: Where possible responses should be contextualised to a child’s circumstances.  For example, in the case of a volunteering information about a disability then it is important to note the child’s response to the topics below.

Evaluator / Investigator Name:

Implementation Partner name:

Learning Centre name:

State:

District:

Township:

For each student attending:

Gender:  <Select from>: Male or Female

Age:

Current Grade attending:

    - (Q1-Q4) Discuss how your life changed during Covid19 and after the February 2021 coup and the challenges you faced in learning

    - (Q15 – Q20) Discuss the opportunities and support has the BBL Programme given to you and whether it has helped or supported your learning?

NOTE: Special focus on issues of Gender, Children with Disability, Poor households and Ethnic Children

      - Support to learning at home during Covid19 / Conflict

      - Support through teaching and mentoring

      - Access to learning materials and resources

      - Stipends to support cost of education (transportation, buying uniforms, etc.)

      - Participation in community activities and learning opportunities outside of school

    - (Q15 – Q20) Discuss the challenges or barriers you still face towards learning and what would be needed to further help or assist you to towards achieving your learning goals?

NOTE: Special focus on issues of Gender, Children with Disability, Poor households and Ethnic Children

    - (Q21-Q25) Discuss your goals and plans for next year and at the completion of your study

    - Further Comments

## Tool 5: Donor and UNICEF KII

Selected questions and topics from Tool 1: Implementation Partner (IP) KII

## Tool 6: Case Study Form.  Parents/Guardians and Students

Note/guidance: Signed authorisation from the child’s guardian/parent (consent for 2.0) should be obtained to include any detailed information in the final report.  If signed authorisation is not obtained then identification details must be omitted in the final report.

NOTE: Special focus on issues of Gender, Children with Disability, Poor households and Ethnic Children and the issues which are specific to these children and how the BBL programme has assisted them.

Evaluator / Investigator Name:

Implementation Partner name:

Learning Centre name:

State:

District:

Township:

Gender:  <Select from>: Male or Female

Age:

Current Grade attending

Question 1: Describe the situation of the child.

- Family composition:

- Father/mothers job/work (if any):

- Child job/work (if any):

Question 2: What was your, the child’s and the parent/guardian’s circumstance before the BBL began.  Please describe noting the challenges and barriers (with reference to Covid19 and the military coup).

Question 3: What has been the positive change as a result of the BBL intervention?  How did the BBL result in you attending learning or gaining access to learning?

Question 4: Have you encountered any difficulties since the BBL intervention began and did you overcome those?

Question 5: What do you intend to do when completing learning at the learning centre?

## Tool 7: Site Observation Form

The following facility observation form is recommended as it allows for nuanced narrative descriptions along key aspects of facilitator and facility assessment criteria.

Evaluator / Investigator Name:

Implementation Partner name:

Learning Centre name:

State:

District:

Township:

Learning Centre: ___________________________________

Peer/Observer: __________________________________

Date and Time ____________________________

Number of children attending    M____, F______

Description of disability if appropriate_____________________

Number of computers/laptops for children__________________

Number of tablets for children________________

Description of Centre (noting indoor and outdoor facilities and activities and linkages to other learning centres such as Early Childhood Development or Primary Schools)_________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

Describe the Means of assessing learning Progression:

(Tick: A=Good, B=Fair, C=Not good)

| ID | Theme | A) Good | B) Fair | C) Not Good |
| --- | --- | --- | --- | --- |
| 1 | Internet availability |  |  |  |
| 2 | Ramps for Children with Disabilities |  |  |  |
| 3 | Toilet facilities for girls |  |  |  |
| 4 | Toilet facilities for boys |  |  |  |
| 5 | Handwashing facilities with soap |  |  |  |
| 6 | Handwashing practices for children |  |  |  |
| 7 | Facilitator Use active participation in learning process with children |  |  |  |
| 8 | Remedial learning interaction with children with disabilities |  |  |  |
| 9 | Outdoor play facilities |  |  |  |
| 10 | Adequate provision of learning materials such as books |  |  |  |
| 11 | Adequate provision of writing materials such as pads/papers/pens/pencils |  |  |  |
| 12 | Engaging posters, materials on the walls |  |  |  |
| 13 | Attendance record books |  |  |  |

Strengths observed:

Suggestions for improvement:

Overall impression of the Learning Facility and Facilitator

Structure of Final Report

Preliminary Material

Table Of Contents

List Of Tables

List Of Figures

Acknowledgements

Definitions

Acronyms

Executive Summary

Summary of Responses to the Evaluation Questions

1	Background And Context

1.1	Structure Of The Final Report

1.2	Background And Context

1.3	Impact Of Recent Events On Education

1.4	Learning Challenge

1.5	Impact Of Recent Events On Donor Support And Funding

1.1	Bringing Back Learning (BBL)

2	Purpose, Objectives, Scope and Methodology Of The Evaluation

2.1	Evaluation Purpose, Objectives And Scope

2.2	Overview Of Methodology And Approach

2.3	Data Protection Protocol And Evaluation Ethics

2.4	Limitations And Risk To The Evaluation

3 	BBL Main Findings and General Discussion

4.	Response to Evaluation Questions

4.1. Relevance

4.2. Effectiveness

4.3. Efficiency

4.4. Impact

4.5. Sustainability

4.6  Gender, Equity, Disability, Social Inclusion

5. Conclusions, Lessons Learned and Recommendations (Phase I & Phase II)

5.1 Conclusions

5.2. Lessons learned

5.3  Recommendations

Annex 1.	Terms Of Reference

Annex 2.	Groups Interviewed

Annex 3.	Bbl Context Timeline

Annex 4.	Result Framework – Bringing Back Learning (Bbl)

Annex 5.	Bbl Programme Data

Annex 6.	Evaluation Data

Annex 7.	GEDSI Analysis summary with recommendation

- List of Partners and Programmes

List of Partners and Programmes

| Organisation | Project |
| --- | --- |
| BDA | Bring Back Learning to Primary Children through Short Term-Home Base Learning materials, Psychosocial Support and WASH Hygiene Promotion in Monywa Township |
| KBC | Bring Back Learning to Children |
| KBC | Improve Education access and Bring back learning activities for conflict-affected childen and adolescens in Kachin, Shan State and Sagaing Region |
| KBC SM | Bring Back Learning to Children |
| MBC | Bring Back Learning to Children and Adolescents |
| METTA | Bring Back Learning to Children |
| MLRC | Capacity building to NGO partners on NFE_Bring Back Learning to Children |
| TdH | Bring Back Learning of children from the crisis-affected township of Hlaingtharya, Yangon Region by providing Open Learning assistance and EXCEL (Extended and Continuous Education and Learning) curriculum |
| WVI-M | Bring Back Learning to Children |
| KMSS | Providing learning opportunities to children |
| SF | Bringing Back Learning to the Children of Myanmar |

Additional Ethics Material

UNICEF (2022) UNICEF Proposal to DFAT, Bringing Back Learning to the Children of Myanmar, Submitted by, UNICEF Myanmar, February 2022

UNESCO (2022) Myanmar Joint Response Framework for The Education Sector 2022-2025, March 2022

UNSDG (2021) United Nations Country Results Report Guidelines for UN Country Teams, United Nations Sustainable Development Group (UNSDG), December 2021.  Available at: https://unsdg.un.org/sites/default/files/2022-05/UNCT-Results-Report-Guidelines-050522.pdf.  (Accessed on 13/02/2023)

OECD Guidelines for Project and Programme Evaluations, Organisation for Economic Co-Operation and Development (OECD), 2009.

OECD, DAC Guidelines and Reference Series Quality Standards for Development Evaluation, Organization for Economic Co-Operation and Development (OECD), 2010.

Chappell, Bill; Diaz, Jaclyn (1 February 2021). Myanmar Coup: With Aung San Suu Kyi Detained, Military Takes Over Government. NPR. Archived from the original on 8 February 2021. Retrieved 8 February 2021.  Available at: https://www.npr.org/2021/02/01/962758188/myanmar-coup-military-detains-aung-san-suu-kyi-plans-new-election-in-2022.  Accessed on 20/01/2023.

Ostwald K., Myint T. (2021) Myanmar: Pandemic in a Time of Transition, in Victor V. Ramraj (ed.), Covid-19 in Asia: Law and Policy Contexts (New York, 2021; online edn, Oxford Academic, 21 Jan. 2021). Available at: https://doi.org/10.1093/oso/9780197553831.003.0023. (Accessed 12/02/2023).

Traill, Ashwini Deshpande, Khaing Thandar Hnin, and Tom (2020). Myanmar's response to the COVID-19 pandemic. Brookings.  Available at: https://www.brookings.edu/blog/future-development/2020/12/01/myanmars-response-to-the-covid-19-pandemic/.  Accessed on 20/01/2023

Source: World Bank.

World Bank (2021) Myanmar's Economy Hit Hard by Second Wave of COVID-19: Report. World Bank. Available at: https://www.worldbank.org/en/news/press-release/2020/12/15/myanmars-economy-hit-hard-by-second-wave-of-covid-19-report.  (Accessed on 20/01/2023)

Projected from the 2019 national inter-censal survey (refer publication below).

MoIP (2015) The Republic of the Union of Myanmar, The 2019 Myanmar Population inter-censal survey – Key Findings, Department of Population, (Ministry of Immigration and Population (MoIP).  Available at: https://myanmar.unfpa.org/sites/default/files/pub-pdf/the_2019_inter-censal_survey_key_findings_english.pdf.  (Accessed on 20/01/2023).

MoIP, The Republic of the Union of Myanmar

World Bank, Achieving Learning for All, (World Bank Group, 2013)

World Bank.  An Analysis of Poverty in Myanmar, December 2017, Part 2, Poverty Profile, (Myanmar Ministry of Planning and Finance, World Bank Group, 2017)

OOSC pp6, Source: DBE data (20 March 2017)

The existing basic education system structure is undergoing a reform cycle restructuring the previous/current five years of primary education, four years of middle school and two years of high school (5-4-2) to a KG+12 structure.  Inclusion of Kindergarten in the formal education structure means that children start in grade 1, one year later than in the previous structure (from age 5 to age 6).

GoM (2016) The Government of the Union of Myanmar Ministry of Education National Education Strategic Plan 2016-21, The Government of the Union of Myanmar (GoM), Ministry of Education (MoE)

Adapted from: MyEQIP (2020) Myanmar Education Quality Improvement Program (My-EQIP) Gender and Ethnicity in Myanmar Education - Study Report (DRAFT), For the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) Committee, Submitted 12 August 2020

OOSC, Myanmar Report on Out of School Children Imitative, (The Republic of Myanmar, Ministry of Education, Department of Education Research Planning and Training, 2018)

OOSC pp5, http://www.mmpeacemonitor.org/research/monitoring-archive

The Straits Times (2020) Myanmar Confirms first two Coronavirus Cases, 24 March 2020. Available at:   https://www.straitstimes.com/asia/se-asia/myanmar-confirms-first-coronavirus-cases. (Accessed on 26/01/2022)

The UN raised concerns about Myanmar's vulnerability to the pandemic due to its weak healthcare infrastructure following poor investment over six decades of military rule, as well as ongoing internal conflict.

Source: UCA News (2021) UN raises concerns over Myanmar's Covid-19 situation. Available at: https://www.ucanews.com/news/un-raises-concerns-over-myanmars-covid-19-situation/88991.  (Accessed on 26/01/2022)

Deshpande A.T., Hnin K.T. (2020). Myanmar's response to the COVID-19 pandemic. Brookings, December 2020.  Available at: https://www.brookings.edu/blog/future-development/2020/12/01/myanmars-response-to-the-covid-19-pandemic/.  (Accessed on 26/01/2022)

Education in Emergencies (EiE) Sector Provisional Strategy, July 2021

UNICEF (2021) Bringing Back Learning to the Children of Myanmar UNICEF Education Programme Response Plan to the Current Crisis in Myanmar, June 2021

UNICEF (2018) Myanmar Report on Out of School Children (OOSC), The Republic of the Union of Myamar, Ministry of Education (MoE), Department of Education Research, Planning and Training, UNICEF, UNESCO Institute of Statitics (UIS).  Available at: https://themimu.info/sites/themimu.info/files/documents/Report_Out-of-School_Children_Initiative_Mar2018_ENG.pdf.  (Accessed on 10/02/2023)

UNESCO (2022) Myanmar Joint Response Framework for The Education Sector 2022-2025, March 2022

UNICEF (2022) Evaluation of UNICEF's response to the L2 emergency in Maynmar, Draft Evaluation Report, Baker J, Kyuu A.A, Aiello M.

The Myanmar Facilitators’ Federation has reported that more than 125,000 Facilitators from a total of more than 430,000 have been suspended and that no more than a quarter of Myanmar’s more the 12 million learners have enrolled for the new school year

UNICEF (2022). Evaluation of UNICEF’s response to the L2 emergency…

UNICEF (2022) Education Cluster Strategy Myanmar 2022-2025, Save the Children, UNICEF. Available at: https://themimu.info/sites/themimu.info/files/edu_public/Education_Cluster_Strategy_2022-2025.pdf. (Accessed on 10/02/2023)

https://www.usnews.com/news/world/articles/2021-05-22/more-than-125-000-myanmar-Facilitators-suspended-for-opposing-coup. (Accessed 20 December 2022).

UNDP (2021) Impact of the Twin Crisis on Human Welfare in Myanmar, United Nations Development Programme (UNDP).  Available at: https://www.undp.org/press-releases/pandemic-and-political-crisis-could-result-half-myanmars-population-living-poverty-2022-undp-says.  (Accessed on: 10/02/2023)

UNICEF (2022). Evaluation of UNICEF’s response to the L2 emergency…

Ministry of Education, UNESCO International Institute for Educational Planning and UNICEF. (2018). Myanmar Report on Out-of-School Children Initiative (OOSCI).

11% of children reach the minimum SDG 4.1 proficiency level.

UNICEF & SEAMEO. (2020). SEA-PLM 2019 Main Regional Report: Children’s learning in 6 Southeast Asian countries. Bangkok, Thailand: United Nations Children’s Fund (UNICEF) & Southeast Asian Ministers of Education Organization (SEAMEO) – SEA-PLM Secretariat.

Ibid…

UNESCO (2022) Myanmar Joint Response Framework for The Education Sector 2022-2025, March 2022

(2021) Myanmar Interim Emergency Response Plan: June to December 2021, June 2021.  Available at: https://reliefweb.int/report/myanmar/myanmar-interim-emergency-response-plan-june-december-2021-overview

Not published.

EiE (2021) Education Cluster’s EiE provisional strategy, June 2021 to May 2022, June 2021

(2022) Education Cluster Strategy Myanmar 2022-2025.  Available at: https://themimu.info/sites/themimu.info/files/edu_public/Education_Cluster_Strategy_2022-2025.pdf. (Accessed on 26/01/2022)

Source: Ibid… pg. 7.

The Myanmar Education Cluster is co-led by Save the Children and UNICEF. It is supported at national level by a Cluster Coordinator, Information Management Officer, and Coordination Specialist, through funding of the co-lead agencies. The Education Cluster has a Strategic Advisory Group comprised of the co-lead agencies, two International Non Government Organisations (INGOS) and a National NGO (NNGO). The Education Cluster currently has six active Sub-National Coordination Groups. These groups coordinate responses in the respective States/Regions.

Reported in interviews with UNICEF, January 2023.

As reported by UNICEF and DFAT in interviews (February 2023)

UNICEF (2022) UNICEF Proposal to Department of Foreign Affairs and Trade (DFAT) Bringing Back Learning to the Children of Myanmar, UNICEF, February 2022

UNCT principle of engagement, and UNCT guidance for programme review

In non-government-controlled areas (NGCAs), education is provided through a range of non-state education service providers such as monastic schools and ethnic education working groups and departments.

The terms, community libraries, hubs, community learning centres, are interchangeably used in this proposal document.

The age limit would normally be 8 years old but due to lost learning and overaged learners, the BBL Programme increased the upper age limit to children who are 10 years old.

UNSDG (2021) United Nations Country Results Report Guidelines for UN Country Teams, United Nations Sustainable Development Group (UNSDG), December 2021.  Available at: https://unsdg.un.org/sites/default/files/2022-05/UNCT-Results-Report-Guidelines-050522.pdf.  (Accessed on 13/02/2023)

UNICEF (2022) UNICEF Proposal to DFAT, Bringing Back Learning to the Children of Myanmar, Submitted by, UNICEF Myanmar, February 2022

UNICEF (2022) UNICEF Theory of Change, Zero Draft.  Submitted for this evaluation 20/01/2022.

Partners with expertise in the respective areas; e.g., Myanmar Literacy Resource Centre (MLRC) for non-formal primary education, and Myanmar Book Aid and Preservation Foundation (MBAPF) for reading activities

UNICEF Proposal to DFAT, Bringing Back Learning to the Children of Myanmar, Submitted by, UNICEF Myanmar, February 2022

UNICEF (2022) UNICEF Proposal to DFAT, Bringing Back Learning to the Children of Myanmar, Submitted by, UNICEF Myanmar, February 2022

Ibid..

Source: UNICEF

According to consultations held so far with CSOs that are supporting community libraries, e.g. Myanmar Book Aid and Preservation Fund and Succor Foundation, there are about 157 active community libraries across different States and Regions in Myanmar. Of these, about 100 have been tentatively identified as potential hosts of the planned community learning hubs and these are located across the country. Townships where these 100 community libraries are located will therefore be deliberately targeted.

Regions/States are: Mon, Ayeyarwady, Bago (East), Bago (West), Chin, Kachin, Kayah, Kayin, Magway, Mandalay, Nay Pyi Taw, Rakhine, Sagaing, Shan (East), Shan (North), Shan (South), Tanintharyi, Yangon

UNICEF (2019) Every Child Learns, UNICEF Education Strategy 2019-2030. Available at: https://www.unicef.org/media/59921/file/UNICEF-education-strategy-2019-2030-data-analytics.pdf

The first batch of numeracy and literacy materials, with 30 weeks of lessons per grade for grades 1 to 4 are due to be released in April 2022, with the remaining ones, including for grade 5 due by the end of July 2022

Source: UNICEF (2022) Bring Back Learning to the Children of Myanmar, Presentation to the Advisory Committee Meeting, 17 October 2022

UNICEF (2021) Guidance for Civil Society Organizations on Partnership with UNICEF, UNICEF Division of Data, Analytics, Planning and Monitoring.  Available at: https://www.icvanetwork.org/uploads/2021/12/Guidance-for-Civil-Society-Organizations-on-Partnership-with-UNICEF.pdf. (Accessed on 30/01/2023)

Ibid…

Source: UNICEF Data supplied 04/02/2023.  Refer annex 6.

Using an exchange of 1 USD = 2119 Kyat (09/02/2023)

USD equivalent contributions at exchange rate 2119 are estimates only based on exchange rate as of 05/02/2023.  Source: https://www.xe.com/currencyconverter/convert/?Amount=1&From=USD&To=MMK.

Source: UNICEF Financial figures 04/02/2023. Refer annex 6.

Source: UNICEF MCO

1 USD = 2120 Kyat as of 03/02/2023.  Source: https://www.xe.com/currencyconverter. Location exchange rates and exchange rates on different dates may vary considerably from this figure.

Regions include: Sagaing (13 townships); Chin (4 townships); Ayeyarwardy (10 townships); Mandalay (2 townships); Magway (12 townships); Bago (6 townships) as depicted on the map below.

OECD Guidelines for Project and Programme Evaluations (Organisation for Economic Co-Operation and Development (OECD), 2009.

OECD DAC Guidelines and Reference Series Quality Standards for Development Evaluation, (Organization for Economic Co-Operation and Development (OECD), 2010.

In Myanmar, other types of marginalization to consider include but are not limited to: ethnic minority groups, IDPs, and stateless populations.

UNICEF (2018 Revised Evaluation Policy of UNICEF, [E/ICEF/2018/14]. Available at : https://www.unicef.org/evaluation/documents/revised-evaluation-policy-unicef-2018. (Accessed on 01/02/2023)

UNEG (2016) UNEG Norms and Standards for Evaluation. Available at: https://www.betterevaluation.org/tools-resources/uneg-norms-standards-for-evaluation-2016. (Accessed on 01/02/2023).

UNEG (2014) Integrating Human Rights and Gender Equality in Evaluation - Towards UNEG Guidance.  Available at: http://www.uneval.org/document/detail/980. (Accessed on 01/02/2022)

UNEG (2020) UNEG Ethical Guidelines for Evaluation. Available at: https://www.alnap.org/system/files/content/resource/files/summary/UNEG_Ethical_Guidelines_for_Evaluation_2020.pdf. (Accessed on 01/02/2023.)

UNICEF (2021) UNICEF Procedure on Ethical Standards in Research, Evaluation, Data Collection and Analysis. Available at: https://gdc.unicef.org/resource/unicef-procedure-ethical-standards-research-evaluation-data-collection-and-analysis.  (Accessed on 01/02/2023)

UNICEF (2017) UNICEF Adapted UNEG Evaluation Reports Standards. Available at: https://www.unicef.org/evaluation/media/816/file/UNICEF-Adapted-UNEG-Evaluation-Report-Standards.pdf.  (Accessed on: 01/02/2023)

OECD Guidelines for Project and Programme Evaluations, Organisation for Economic Co-Operation and Development (OECD), 2009.

OECD, DAC Guidelines and Reference Series Quality Standards for Development Evaluation, Organization for Economic Co-Operation and Development (OECD), 2010.

Appreciative Inquiry was developed in the 1980s by D. Cooperrider and colleagues at the Case Western Reserve University in Ohio as a research tool to organizational change with focus on strengths rather than focussing on the weaknesses. It is based on the belief that people and organizations will be drawn towards constructive actions in the future by affirming positive moments of their past (Michael, S. (2005) “The Promise of Appreciative Inquiry as an Interview Tool for Field Research” Development in Practice, Vol. 15, No. 2 (Apr., 2005), pp. 222-230). Cooperrider has identified five principles of Appreciative Inquiry: Constructionist, Simultaneity, Anticipatory, Poetic, and Positive stressing the importance of perceptions. Over the years, Appreciative Inquiry has developed and been adapted to different contexts, including development evaluations (see for instance www.betterevaluations.com).

UNICEF (2017) “Results-Based Management Handbook.”

UNEG (2015) “UNEG Handbook for Conducting Evaluations of Normative Work in the UN System.”

For introduction to the principles of Realist Evaluations see Better Evaluation “Realist Evaluation.” Accessed 28 December 2020.

For introduction of principles of mapping of causal paths see Copestake, J. et al (2019) “Attributing Development Impact - The Qualitative Impact Protocol (QuIP) Case Book.” Practical Action Publishing, Warwickshire.

Bamberger, M. InterAction, Introduction to mixed methods in impact evaluation (No. 3.), .).2012. Retrieved from website: http://www.interaction.org/sites/default/files/Mixed%20Methods%20in%20Impact%20Evaluation%20%28English%29.pdf

February 1st 2021.

SDG Indicator 4.5.1: Parity indices (female/ male, rural/ urban, bottom/ top wealth quintile and others such as disability status, indigenous peoples and conflict-affected, as data become available) for all education indicators on this list that can be disaggregated

Such as the experiences and benefits of having participated in the programme.

Refers to facilitators, educators, volunteers responsible for facilitating learning for children engaged through the BBL.

Adapted from: https://www.isu.edu/media/libraries/college-of-technology/pdfs/faculty-staff-docs/ClassroomObservationForm.doc

In addition to the evaluation teams own research, the Evaluation team will also rely partially on the informal UNICEF to ensure that all local and national data protection and privacy laws are respected.

United Nations Evaluation Group (UNEG)

From the OECD‐DAC Criteria for International development evaluation – website http://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

In Myanmar, other types of marginalization to consider include but are not limited to: ethnic minority groups, IDPs, and stateless populations.

Adapted from: UNICEF (2022) Evaluation of UNICEF’s response to the L2 emergency in Myanmar, Draft Evaluation Report, Lattanzio KIBS, December 2022

Schools in some areas remained open, such as in Rakhine, Mon and some of the other states.

UN News (2021). Security Council appeals for end to violence in Myanmar. https://news.un.org/en/story/2021/11/1105642

(UNDP, 2017)

Source: Terre Des Hommes (2021) Using Focus Group Discussions with children and adolescents A practical guide for maximising their effectiveness.  Available at:

https://www.tdh.ch/sites/default/files/tdh_pcm_series_guide_using_fgd_with_children.pdf.  (Accessed  on 15/03/2023)