FINAL REPORT ON THE POST INTRODUCTION EVALUATION OF THE PENTAVALENT VACCINE IN ZAMBIA

WHO/AFRO IST East & Southern Africa, WHO/Zambia,

UNICEF/Zambia, CDC, USAID, MOH Zambia

February 2-13, 2009

# Table of Contents

Acronyms	3

Executive Summary	4

Background	8

Context for the Post-Introduction Evaluation in Zambia	9

Rationale for the Evaluation	9

Objectives of the Evaluation	10

Evaluation group members	10

Methodology of the evaluation	10

Rationale for introduction of new vaccine	11

Description of introduction	12

Key Findings	13

Pre-implementation planning and training	13

Health Care Worker Knowledge	14

Advocacy, Communication and Acceptance	15

Coverage and reporting	15

Adverse Events Following Immunization	18

Monitoring and supervision	19

Cold chain capacity and management	20

Vaccine Management Storage and Wastage 	21

Waste management and injection safety	22

Lessons Learned for Future Vaccine Introductions	23

Training	23

Policy	23

Community Preparedness	23

Sustainability	23

Follow-up Actions	24

Appendices	25

Appendix I - Itinerary	25

Appendix II – Sites Visited	26

Appendix III – Team Members	27

Appendix IV - Recommendations	28

Appendix V - Key indicator table	30

Appendix VI - Data collection instrument	31

ACRONYMS:

| AD | Auto-Disable Syringes |
| --- | --- |
| AEFI | Adverse Events Following Immunization |
| AFRO | WHO Africa Regional Office |
| CDC | U.S. Centers for Disease Control and Prevention |
| CHT | County Health Team |
| DPT | Diphtheria, Pertussis and Tetanus Vaccine |
| DVMT | District Vaccine Management Tool |
| EPI | Expanded Programme on Immunization |
| GAVI | Global Alliance for Vaccines and Immunization |
| HBV | Hepatitis B Virus |
| HF | Health Facility |
| HepB | Hepatitis B |
| HF | Health Facility |
| HCW | Health Care Worker |
| Hib | Haemophilus influenzae type b |
| ICC | Inter-Agency Coordinating Committee |
| ISS | Immunization Services Support |
| MDG | Millennium Development Goal |
| MLM | Mid-Level Manager |
| MOH | Ministry of Health |
| MSF | Médecins Sans Frontières |
| NGO | Non-Governmental Organization |
| PIE | Post Introduction Evaluation |
| RED | Reaching Every District |
| UCI | Universal Childhood Immunization |
| UNICEF | United Nations Children’s Fund |
| USAID | United States Agency for International Development |
| VVM | Vaccine Vial Monitor |
| WHO | World Health Organization |

Executive Summary

Hepatitis B virus (HBV) infection and Hib related diseases are important public health problems in Zambia.  Zambia submitted its application to GAVI for pentavalent vaccine that includes both HBV and Hib antigens in 2001. However, due to vaccine production failure, the Ministry of Health decided in January 2003, to introduce liquid-lyophilised tetravalent, DTP+Hib in January 2004 and switch to liquid-lyophilised pentavalent, DTP-HepB+Hib in 2005. Following the availability of the fully liquid formulation late in 2006, the country eventually switched to the fully liquid formulation in February 2007.

A post introduction evaluation (PIE) is recommended by WHO for all countries that have introduced a new vaccine, ideally within 6-12 months of introduction.  The PIE in Zambia was specifically aimed at assessing the programmatic impact of switching from the liquid-lyophilised to fully liquid pentavalent vaccine.  The Zambia PIE evaluation team was composed of representatives from:  WHO, UNICEF, CDC, USAID and the Ministry of Health (MOH).  Four provinces were selected based on criteria of good, medium and poor coverage performance and diversity of population size. Within each province, two districts (eight total) were selected and within each district, three health facilities (HFs) were selected based on similar criteria. Observation visits and interviews were conducted at national, district and health facility levels, and interviews with caregivers on exit from immunization sessions were also conducted.  In total, 24 HFs were evaluated during the trip.  The key findings and recommendations are presented in the table and list below.

Key Findings

| Strengths | Areas for Improvement |
| --- | --- |
| Pre-implementation, Planning and Training |  |
| • A plan for switch in vaccine formulations was distributed at the time of switch. • Training for the liquid penta vaccine was done before switch at all levels by cascade. • Trainings went well. • Consistent instructions given for continuation of liquid vaccine for subsequent doses. • Vaccine well accepted by all stake-holders. | • Training manuals not readily available at the sites. • Minimal training for liquid penta done as training performed for lyophilized vaccine. • Not all members of the health facilities were trained. |
| Health Care Worker Knowledge |  |
| • Generally adequate information provided to parents after penta vaccination in many facilities. • Very good communication with parents regarding when to return. | • Insufficient information provided to parents about which side effects of vaccination to return for. • Some HCWs did not know all five antigens in pentavalent vaccine • Some HCWs did not know what diseases the Hib vaccine prevents leading to inadequate communication with parents on vaccine and its use • Lack of handwashing in between clients. |
| Advocacy, Communication and Acceptance |  |
| • Adequate health education messages provided to community about penta vaccine. • Excellent acceptance of vaccine by community and health care workers. | • Lack of awareness by mothers of the clinical symptoms prevented by vaccines |
| Coverage and Reporting |  |
| • Facilities completed tally sheets/monthly summary sheets. • Good completeness of reporting • HFs record outreach and static immunization reports separately. | • Poor ability to calculate and monitor coverage and drop-out at HF level • Coverage and drop-out data not used to guide immunization activities • Coverage often exceeded 100%, likely due to CSO underestimate of target populations. • Many instances of Penta3 exceeding Penta1 (negative drop-out) • Outreach data not reported separately to higher levels and not being used to guide vaccine programs. • Monthly immunization records from HFs are not reported to districts in a timely manner |
| Adverse Events Following Immunization |  |
| • Facilities had copies of AEFI reporting forms and guidelines. • AEFI procedure in place. | • HFs not aware of what AEFIs to expect and report |
| Monitoring and Supervision |  |
| • Facilities receiving frequent supervisory visits • Written recommendations are provided | • Supervisory visits not identifying and correcting many obvious problems regarding coverage, vaccine management and cold chain. • No single designated book for recommendations and follow-up. |
| Cold Chain Capacity and Management |  |
| • Refrigerators all functioning. • Twice daily monitoring of temperatures at HF level, including weekends at HF level • Generally adequate cold chain space at HF level. • Thermometers present either inside or outside of fridges | • Insufficient cold chain capacity at central level; some limited capacity for cold chain and dry storage at province and district level as well. • No standardized protocol to address how often to monitor temperatures during power failures • No freeze-watch monitors. • Stock registries not well maintained • Some provinces and districts not recording temperatures on weekends. |
| Vaccine Management, Storage and Wastage |  |
| • Districts had staff members trained in vaccine management. • No gap between switch from lyophilized and liquid penta. • Stock-outs rare at all central and HF levels | • Vaccines in VVM stage 3 and 4 observed at some districts and HFs • Poor knowledge among facility staff regarding VVM stages • No standardized method for vaccine forecasting • Wastage not calculated at any level • Occasional stock-outs at district level due to poor forecasting. • Inaccurate target populations used by districts to forecast vaccine need • Some expired vaccine at province and HF levels |
| Waste Management and Injection Safety |  |
| • Clean wastage sites • No syringes on ground. • Safe injection practices followed | • Wastage sites not fenced off. • Some pits were shallow. • No wastage reports on site |

Key Recommendations

- For future vaccine introductions, adequate resources should be mobilized for the required pre-implementation training of a large number of health workers who will be working with the new vaccine

- The AEFI monitoring system should be assessed and strengthened prior to introduction of new vaccines.  Training of HCW should include the specific side effects that require medical follow-up and the importance of continued monitoring after introduction.

- Build and sustain optimal communication on vaccines and vaccination between health workers and parents to increase awareness of mothers and boost demand.

- Further exploration into the reasons for national pentavalent coverage estimates to drop from 100% and 97% in 2005 and 2006 to 88% in the first half of 2008; specifically to identify if this is an artefact of data reporting or estimation procedures or is a true drop in coverage.

- Consider supplementary sources of target population estimates to better understand and approximate the true immunization coverage in each catchment area and engage relevant national authorities to resolve the frequent occurrence of coverage >100%.

- Improve quality of training and supportive supervision at all levels including: instruction on how to calculate, analyze and use immunization coverage and drop-out data to guide immunization activities; and vaccine and cold chain management

- Vaccine and cold chain management practices need to be strengthened particularly vaccine forecasting, maintenance fridges and freezers, procedures to follow in case of power failure, and supportive supervision

- An additional cold room should be purchased for the central store to increase the cold storage capacity for existing and future vaccines.

- Strengthen waste disposal management at health facility level to protect communities from the dangers of used injection equipment

Background

Zambia is a landlocked country in Southern Africa with an estimated 2009 population of 12, 939,233 million. The country is divided into 9 provinces and 72 districts.

The EPI programme immunization in Zambia commenced in 1975, and in 1984 the Ministry of Health adopted the goal of universal childhood immunization.  All children up to 5 years are eligible for vaccination. However, the priority is to vaccinate all children with all doses of available antigens before the first birthday.

Zambia submitted its application to GAVI for pentavalent vaccine in 2001. Following the approval, GAVI committed itself to supplying the pentavalent vaccine in third quarter of 2002 but this was later changed to the third quarter of 2003 due to vaccine production failure. Following consultations with the GAVI Vaccine Provision Project, implemented by UNICEF, WHO and the Vaccine Fund, the Ministry of Health decided in January 2003, to introduce liquid-lyophilised tetravalent, DTP+Hib in January 2004 and switch to liquid-lyophilised pentavalent, DTP-HepB+Hib in 2005. Following the availability of the fully liquid formulation late in 2006, the country eventually switched to the fully liquid formulation from February 2007.

Routine immunization coverage has generally been high. Some of the key activities that could have contributed to this achievement include the training staff at all levels on EPI in 2002, the first in 10 years. This was followed by introduction of the Reaching Every District (RED) approach in pilot districts in 2003, and training on the Hib vaccine in 2003. By 2008, all 72 districts had started implementing RED and supportive supervision was intensified.

The quality of the routine immunization coverage data was confirmed by an external Data Quality Audit (DQA) commissioned by GAVI in 2003, in which Zambia achieved a verification factor of 0.79 and received awards for increasing routine coverage in subsequent years, particularly DTP3 coverage among children under the age of one.

Fig 1: Routine Immunization Coverage in Zambia 1999-2007 DTP3/Pentavalent 3

The coverage for pentavalent 3 during January-June 2008 is shown in figure 4 below:

Fig 2: Map of Zambia showing pentavalent3 coverage, Jan-Jun 2008

CONTEXT FOR THE POST INTRODUCTION EVALUATION

Rationale for the Evaluation

A post introduction evaluation (PIE) is recommended by WHO for all countries that have introduced a new vaccine.  Ideally, a PIE should be conducted within 6-12 months of introduction, (a) to allow enough time for programme scale up, collect data and develop potential long-lasting problems due to introduction, and (b) early enough to correct any major problems related to the introduction.  The PIE for Zambia was conducted two years after the switch from liquid-lyophilised to fully liquid pentavalent.

Objectives of the Evaluation

The main objective of the evaluation was to assess the programmatic impact of the switch from liquid-lyophilised to fully liquid pentavalent on the immunization programme.  Specifically, the evaluation looked at issues related to:

- Pre-implementation planning and training

- Health care worker knowledge

- Advocacy, communication and acceptance

- Coverage and reporting

- Adverse events following immunization (AEFI) reporting

- Monitoring and supervision

- Cold chain capacity and management

- Vaccine management, storage and wastage

- Waste management and injection safety

At the national level, it is intended that the findings be used to recommend corrective action in areas where disruption to service, or less than optimal implementation, are occurring, so that the benefits of the new antigens are reaching as much of the population as possible.

At regional and global levels, the findings are to be used to ensure that future countries introducing new antigens are aware of, and avoid, the potential pitfalls of introducing a new vaccine or switching to a different formulation of the new vaccine.  The findings will furthermore be used to revise introduction guidelines, stimulate discussion with global partners on the issues surrounding the introduction of new vaccines in developing country situations, and eventually to influence the upstream formulation of vaccine presentations to avoid the most serious of possible problems.

Evaluation Group Members

The PIE evaluation group was composed of representatives from WHO/AFRO IST East and Southern Africa, WHO/Zambia, UNICEF Zambia, CDC, USAID and the MOH Zambia.

Methodology of the evaluation

Prior to arrival, eight Districts within four Provinces were selected based on the level of performance, to include good, medium and poor performing Districts and to obtain geographical spread throughout the country.  Within each District, 3 HFs were chosen, also based on high and low performance, resulting in the total selection of 24 HFs.  The evaluation group was divided into four teams to visit the eight Districts; the teams comprised one external evaluator and two national evaluators.  Each of the four teams evaluated one Province and two Districts. The Districts selected were Lusaka, Chongwe, Ndola, Masaiti, Mansa, Mwense,  Mumbwa and Kabwe.  The teams visited the Province and District Health Offices, as well as three HFs per District.  The HFs were selected, in consultation with District staff, based on their EPI performance.   The cold stores at National, District and HFs level were also evaluated.  Mothers were interviewed and observations were made during immunization sessions in the HFs.  In total, 24 HFs were visited during the 5-day field data-collection trip.  A map of the HFs visited in included in figure 3 below.

Fig 3: Map of Zambia showing districts selected for PIE

A detailed itinerary of the PIE activities is found in Appendix I.  On the first day of the PIE, the evaluation group met and were briefed on the history and status of the EPI in Zambia and had the opportunity to brief the MOH on the purpose and objectives of the PIE.  In addition, revisions were completed of the generic data collection instruments to make them appropriate to the country situation.  The group then divided into the 4 teams and visited the selected Provinces, Districts and HFs over the following days. Data was collected from interviews and observations at all health administrative levels, i.e. national, Province, District, HFs, and from the caregivers interviewed on exit.  The remaining days consisted of data compilation and analysis through discussions of the field teams with other EPI staff in the MOH, WHO, USAID and UNICEF.  A final presentation was prepared during this time.

Rationale for introduction of new vaccine

Hepatitis B virus (HBV) infection and Hib related diseases are important public health problems in Zambia.  Sero-prevalence studies among different segments of the Zambian population have shown that the prevalence of Hepatitis B infection markers vary from 6.5% in pregnant women, 6% in haemophiliacs and 12% among blood donors.

According to data at the Hib Sentinel Surveillance Site at UTH in Lusaka Zambia, Hib accounted for about 25% of bacterial meningitis cases seen in the paediatric wards at the University Teaching Hospital in 2002 alone.

Local data and sub-regional evidence indicate that HBV infection is endemic, and Hib related diseases (mainly meningitis and pneumonia) are a major concern for the MOH in the country.

In view of the regional evidence of high disease burden of Hib related disease and the WHO recommendation, the Government of Zambia, MOH decided to introduce the tetravalent and pentavalent vaccines in national routine EPI with the GAVI Fund support starting in February 2004 and September 2005 respectively.

## Description of introduction

The first new vaccine to be introduced into Zambia’s EPI programme was Hib in a tetravalent combo with DTP, DTP+Hib in 10-dose vials, in February 2005. Pentavalent vaccine, DPT-HepB+Hib, was later introduced in September 2005 using the liquid-lyophilised formulation in a 2-dose vial presentation and administered at 6, 10, and 14 weeks.

The fully liquid pentavalent vaccine requires greater space then the DPT vaccine, 12.9 cm3 per 10 doses than the traditional DPT which occupies 2.5cm3 per 10 doses and DTP+Hib which takes up 13.72 cm3 per 10 doses.  An assessment of the cold storage capacity and its management at the national level was conducted in 2003, using the Effective Vaccine Store Management (EVSM) tool. The assessment revealed a number of shortcomings at national level, both in terms of management and of buildings and equipment. The report also alluded to the lingering concern about vaccine storage capacity in view of the plan to introduce pentavalent vaccine, future measles campaigns and the intention to increase TT coverage from target of 40% in 2003 to 80% in a bid to eliminate maternal and neonatal tetanus. The report clearly highlighted the need to carry out detailed calculations to establish whether storage capacity will remain adequate over the next few years.

The EPI in Zambia introduced safe injections in routine immunisation using auto-disable (AD) syringes with accompanying safety boxes in 2003. GAVI support ended in 2005 but the government has taken over the financing of safe injection supplies. There has been extensive training on safe injection practices over the years but the last injection safety study was conducted in 2001 to justify the proposal to GAVI in 2002.

Zambia was one of 5 countries in Africa that was invited by GAVI to switch from liquid-lyophilised to fully liquid pentavalent when the latter formulation became available late in 2006. The ICC took a decision to switch and formulations were switched from liquid-lyophilised in 2-dose vials to fully liquid pentavalent in 1-dose vials in February 2007.  Cascade training on liquid-lyophilised pentavalent was started from the national level through the HF level. Revised recording and reporting forms were distributed to all facilities and the “Field Guide for Introduction of New Vaccines in Zambia” which was produced in 2004.

With the introduction of both tetravalent and pentavalent vaccines, all EPI forms were revised and reprinted.

These include:

- Immunization schedules and child health cards

- Vaccine stock forms and cards

- Vaccination tally sheets, vaccination registers, and computer programs

- New informational materials for parents and training material for health care workers

This process was initiated so that forms were distributed by the time the tetravalent and pentavalent vaccines were introduced in February 2004 and September 2005 respectively.

An official launch of the liquid-lyophilised pentavalent was conducted in Mazabuka in 2005 in the presence of the Minister of Health, the WHO and UNICEF Representatives, and other ICC members.  The media was involved and the launch of the pentavalent vaccine was a high level advocacy event.  Launch ceremonies were also conducted in the Districts.

Key Findings

## Pre-implementation planning and training

Early and effective planning is essential prior to introduction of new vaccines. As the introduction of new vaccines has implications on the vaccination schedule, cold chain capacity, distribution plans, training of health workers and key messages for community acceptance, there is need for the country to prepare adequately. Zambia, with the support from the Interagency Coordinating Committee (ICC), made the decision to switch from the lyophilised DPT-HepB+Hib vaccine (pentavalent) to the liquid one dose DPT-HepB-Hib vaccine in 2006. The Child health Technical working group in collaboration with partners assessed the feasibility to undertake the switch and developed a plan to facilitate a smooth transition. Training guidelines were prepared to facilitate cascade training of health workers at provincial, district and health facility levels early 2007. Funding was sourced from UNICEF, and MoH basket funds.

Strengths

The Child Health Technical working group developed a detailed national plan for the switch in vaccine presentations with guidance from the ICC. Subsequently cascade trainings were conducted to orient health workers on the switch prior to vaccine introduction. Participants at the trainings were provided with handouts and CDs containing information on the liquid pentavalent. The national level supported the provincial and district trainings.

The provincial and district staff were advised to allow the remaining stocks of the DPT-HepB+Hib to be fully exhausted before switching to the liquid formulation. Consistent instructions were given to health workers for continuation of the liquid vaccine for subsequent doses. This ensured smooth introduction of the liquid pentavalent vaccine.  Health Facilities did not report any interruption of immunization services as there was no gap between arrival of the liquid pentavalent vaccine and phasing out of excess lyophilised pentavalent vaccine.  96% of health facilities visited reported a smooth transition to liquid pentavalent.

Areas for Improvement

Even though there was a national plan for introducing the liquid pentavalent vaccine, district-specific plans with concrete activities and timelines for implementation were not evident at the lower levels. There was minimal training on the switch because more training was done for the lyophilized vaccine. Training on the switch was not provided to all relevant staff members of the Health Facilities and those staff members trained had to subsequently train the rest of the Health Facilities. Training manuals were not readily available at the sites and not all members of the health facilities were trained.

The plan for continuation in the use of the remaining lyophilized DPT-Hib-HepB stock was conveyed verbally, and not through a written plan.  A written plan provides information for health workers document how the transition from lyophilized pentavalent to the liquid formulation would take place

Recommendations

- Adequate training materials should be developed and distributed to all health facilities for future new vaccine introductions or programmatic changes

- Adequate resources should be mobilized for pre-implementation training of a large number of health workers on new vaccine

- For future introductions, District specific plans should be developed clearly highlighting how the switch to new vaccine would be undertaken.

- Future new vaccine introductions or programmatic changes should utilize a chronogram of pre-introduction activities that is distributed as a template to all levels in advance.  County-specific planned activities should be reviewed by the national team with the Partners prior to initiating the introduction activities.

- A clear, written policy regarding the procedure for existing vaccine stocks should be prepared and communicated to HCWs at all levels.

- Training should be provided to a broader audience at the Health Facility level.

## Health Care Worker Knowledge

Zambia received USD 100,000 for the introduction of liquid-lyophilised tetravalent vaccine in 2003. This grant was utilized on training and other activities related to new vaccine introduction. Training and introduction of liquid-lyophilised and fully liquid pentavalent vaccines in September 2005 and February 2007 were funded from GAVI ISS funds.   Health care worker knowledge was assessed during the PIE.  Their knowledge reflects the quality of the training programme in addition to the quality of supervision they received, their baseline pool of knowledge and their self-directed learning.

Strengths

Health care workers demonstrated a good general knowledge of EPI practices. HCWs provided adequate information, such as scheduling and side effects, to parents after pentavalent vaccination at 23 of 24 Health Facilities (96%). There was very good communication with parents regarding when to return for subsequent vaccinations. Eighteen of 21 (86%) of HCWs knew that Hep B vaccine prevents hepatitis B infection.

Areas for Improvement

Appropriate communication to parents regarding which side effects of vaccination require medical attention was often not observed.  HCWs at 6 (24%) of facilities did not know all the five antigens contained in pentavalent vaccine. HCWs at 9 of 24 facilities (37%) did not know that the Hib vaccine prevents both meningitis and pneumonia, leading to inadequate communication with parents on the vaccine and its use.  Handwashing in between clients was rarely observed.

Recommendations

- Train HCW adequately on key components of pentavalent vaccine, including the side effects that require medical follow-up.

- Reinforce key messages to parents on the vaccines and diseases they prevent by providing job aids for health workers

- Encourage hand washing / sanitizing between administration of immunizations

## Advocacy, Communication and Acceptance

Advocacy and communication for the introduction of pentavalent vaccine was coordinated by the national EPI programme utilizing radio, newspaper, posters and daily health talks at HF and outreach sites.  District and HF staff facilitated social mobilization activities in their communities for the new vaccine. There was strong advocacy for the liquid-lyophilised pentavalent leading to very good acceptance by the community. In consequence, there was no need for additional advocacy for the fully liquid formulation since it was the same vaccine.

Strengths

The introduction of the liquid-lyophilised pentavalent vaccine was preceded at the national and district levels by high profile launches.  Health centres used posters and clinic talks. Adequate health education messages were provided to the community about the pentavalent vaccine in many facilities. The pentavalent vaccine was well accepted by the community.

Areas for Improvement

There was a lack of awareness by mothers of clinical symptoms prevented by the vaccine.

Recommendations

- Print and distribute already developed information leaflets for health care workers and parents that address frequently asked questions concerning vaccines and the diseases they prevent.

- Reinforce IEC materials for routine immunization in general, such as posters.

- Sustain optimal communication on vaccines and vaccination between health workers and parents

## Coverage and reporting

In 2003, the year prior to introducing Hib-containing vaccine, three-dose DPT3 coverage was 85%; this coverage increased to 100% in 2005 and 97% in 2006 after introducing Hib containing vaccine (Figure).  Liquid pentavalent vaccine was introduced in February 2007; national Penta3 coverage for the first half of 2008 decreased to 88%.   It is not clear if this decrease in coverage is a true decrease or an artifact of the methodology in reporting or calculating coverage.  The team also heard report that supplementary adjustment factors were calculated to address the underestimates of the population using CSO figures. However, Zambia is undergoing an update of its HMIS system which could impact reporting procedures and possibly help to resolve the issue of population estimates.

Strengths

All HFs completed tally sheets and monthly summary sheet and had good completeness of reporting; 7 out of 7 districts (100%) had >95% completeness of reporting.

Twenty of 20 (100%) HFs record outreach and static immunization reports separately and some distinguished vaccinations given to infants inside and outside their catchment areas.  HF reported a decrease in missed vaccination opportunities as they no longer asked mothers to return at a later date when other children were being vaccinated to avoid wastage.  New HMIS will include reporting of penta drop-out.

Areas for Improvement

Coverage data was not consistently available; there was not a consistent use of standard immunization charts and data were not readily available.  The recent change in HMIS forms may have added to some disorganization or difficulty in locating the requested figures.

The ability to calculate coverage at several HFs was poor; Four of 24 HFs (17%) did not know the correct formula.  Coverage exceeded 100% in 9/23 (39%) of HFs (Figure) and coverage ranged from 76 to 230% across the sites.  This is likely due to CSO figures underestimating target populations.  Coverage rates exceeding 100% limit the usefulness of coverage estimates and may give a false sense of reaching all children.

There was limited evidence that coverage data were used to guide program activities.  In some areas, this may be related to the limited usefulness of coverage figures that exceed 100%.  However, despite this, there was little indication that coverage data, including data on distinguishing outreach and static vaccinations rates, were used to identify gaps in service delivery and plan for corrective action.

Summarizing and monitoring DPT1 or Penta1 and Penta1-Penta3 drop out was not being conducted in 2008 and 7 of 24 HFs did not know the correct formula for drop-out. However, these data are being collected as part of the new HMIS system.  Ten of 17 (59%) of HF had less then 10% drop-out with drop-out ranging from -42 to +30.

There were multiple instances of DPT3 being substantially greater than DPT1; 5/17 (29%) of HF had negative drop-out.  In some cases this may be explained by vaccinating children outside of the catchment area and by re-starting immunization services after cession due to program constraints (i.e., stock-out or loss of staff).  However, consistently substantial negative drop-out may indicate a problem with correctly recording or tabulating data.  For example, the summary reports from the first 2 quarters of 2008 in one HF showed a -10% Penta1-Penta3 drop-out while a cursory review of registries revealed a 45% drop-out rate.

Timeliness was not usually documented.  When it was collected, timeliness rates were low.  Three of five districts reported that the received <90% of reports on time.

Recommendations

- Nation-wide guidance through refresher training and supervisory visits should address improving data quality, how to calculate, analyze and use immunization coverage and drop-out data to guide immunization activities.  Specifically,

  - Improve data quality starting with the fundamentals of understanding the purpose of and organizing the various required forms, accurately recording data and calculating coverage and drop-out figures.

  - Special emphasis and detail should be given to the calculation and analysis of Penta1-Penta3 drop-out figures since this is a recently introduced indicator.  Assessment of calculation and use of drop out figures should be included in the supervisory check-list (if it does not currently exist).

  - Instruction, including examples, of how to use both coverage and drop-out figures to guide immunization strategies.

- Districts should investigate reasons for having frequent reports of DPT3 substantially higher than DPT1 (negative drop-out rates) among relevant HFs to ensure these data are accurate.

  - Investigation could include reviewing registries and monthly tallies and reporting forms for selected months with DPT3 substantially higher than DPT1.  If HF distinguishes vaccinations administered to children inside vs outside the catchment area, a separate drop-out rate could be calculated using only children in the catchment area.

- The frequent occurrence of coverage >100% limits the ability to monitor program implementation.  In addition to CSO-based coverage, HF should consider supplementary sources of target population estimates to better understand and approximate the true immunization coverage in their catchment area.  Such analyses include:

  - Use of ‘head counts’ or community registries to get at the true number of children <1 in the catchment area.

  - If data are available, calculate and monitor coverage from the ‘in-catchment’ children.

  - Compare annual trends in CSO-based coverage to that of supplementary sources.

- Improve the use and analysis of outreach-specific data.  Monitor the proportion of total vaccinations given through outreach and determine if these data appropriately reflect vaccination strategies and resources.

- Timeliness should be emphasized during supervisory visits to reinforce that the data are important to the national program. Districts should have a mechanism in place to track and respond to HFs not reporting on time.

- Use the existing inter-health center quarterly meetings to review immunization data and discuss immunization strategies with all HFs staff and community partners.

  - Meetings could feature successful strategies used in high performing HFs and obstacles and recommendations for improving program performance in low performing HFs.

## Adverse Events Following Immunization

Since the introduction of liquid pentavalent vaccine, no adverse events have been reported at any level.

Strengths

All levels were aware of AEFI procedures and HF had copies of AEFI reporting forms and guidelines.  A total of 20 (95%) out of 21 HF reported having AEFI procedures in place.

Areas for Improvement

HFs were often not aware of what AEFIs to expect and report.  For example, they could not name the types of adverse events that are reportable.

Recommendations

Training and education on the awareness of types of expected reactions and types and response to adverse events occurring after immunization should be conducted.

## Monitoring and supervision

There is clear indication that a supervisory system at all levels is in place, ensuring high performance of EPI in Zambia.  The main step forward for supervision is to improve the quality and follow-up of visits.   Supervision is intended to complement training activities and observe and trouble shoot barriers to translating national policy to the HF level.

Strengths

There was evidence of supervisory visits occurring throughout the health system.  Of the HFs visited, 100% reported receiving at least one supervisory visit in the last six months and many received more visits, up to once per week.  Written recommendation resulting from visit were provided by supervisors at 18/19 (95%) of HFs.

Areas for Improvement

The quality of supervision could be improved as multiple problem areas were identified by the evaluation team that had not been corrected through supervisory visits, including coverage calculations, vaccine forecasting, and cold chain issues. Although written recommendations were provided, the entries were difficult to locate as they were often documented in visitors log books which are not designed for indicating follow-up recommendations and status.

Recommendations

- Improve supervision by establishing nation-wide use of standard supervisory logbooks to record observations and recommendations from supervisory visits

  - The logbooks should record observations and recommendations from supervisory visits and should include a column which indicates the status and evidence describing whether the recommendation has been met.

- Ensure that the supervisory check list is updated to include issues related to the new vaccine and other priority areas identified during this evaluation.

  - Update supervisory check list to ensure that immunization coverage and drop-out are correctly calculated and analyzed, data are being used to guide immunization activities (ie, if supervisor identifies large drop-out they should ask what is being done about it), review monthly reporting form to ensure no children >1 year are receiving pentavalent vaccine, monitor timeliness.

  - Consider synchronization of supervisory visits to reduce burden at all levels.

## Cold chain capacity and management

The cold chain in Zambia consists of a national store in Lusaka, 9 Provincial, 72 District and 1732 Health Centre stores.  The National Cold Store is equipped with three cold rooms and 16 refrigerators. The central cold chain is powered by the Zambia National Electricity Supply Company (ZESCO) with a standby generator that serves as a back-up. Vaccines at all other levels (Provinces, districts and Health centres) are stored in refrigerators. Transportation of vaccines from the national store to the provinces is done by two EPI trucks and from provinces to district by vehicles. The health facilities usually collect their vaccines by MOH or hired vehicles. The Zambian cold chain benefited from routine equipment replacement shortly before the switch from lyophilized to fully liquid pentavalent.

Strengths

Adequate storage at the time of the switch was reported by sixty-seven percent (16/24) of the HFs and only 29% had a change in frequency of vaccine delivery after the switch.

Ninety-two percent of the HFs use electricity as their source of power while 4% each use solar and kerosene. 100% of HFs had a thermometer either inside or outside of their fridge; 96% (23/24) HF had thermometers outside the fridges. Temperatures were recorded daily, including holidays and weekends, in 96% (23/24) of HFs. Most of the facilities visited have the correct temperature range of (2-8oC). This translates into 4/6 province, 7/10 districts and 12/15 HFs. Although all the 24 the health centres are without backup generators, 96% said they had plan for power outage.

Areas for Improvement

Cold chain capacity at the central level was observed to be grossly inadequate leading to stocking with vaccines beyond capacity which is a potential threat to maintaining vaccine potency. As such, the minimum condition of storing vaccines has not been adhered to and the Central level has had to request for a delay in delivery of shipment.  Some of the provinces and districts have limited storage capacities as well. Some of the provinces and districts did not have adequate space between vaccines.

Temperatures at Province and District levels are measured daily but not consistently during weekends and public holidays. At the HF level, 20% had no thermometer inside the fridges.

Although health facilities have coping strategies, there is no standard protocol across facilities as to what to do in case of power failure. Plans for power failure were found to be limited to not frequently opening the refrigerators during blackouts; no mention was made about checking temperature every hour.

There are no freeze-watch monitors at any level and stock registers are not generally well maintained.

Recommendations

- A check list for EPI supervisory visits should include refrigerator and freezer maintenance, and appropriate placement of vaccines in refrigerators.

- Freeze-watch monitors should be provided to all levels of the cold chain.

- The EPI should come up with a standardized protocol that staff is expected to follow in case of power failure.

- One additional cold room should be purchased for the central store in order to reduce the congestion.

## Vaccine Management, Storage and Wastage

To ensure potent vaccine is available for administration to the people of Zambia, vaccine must be ordered correctly and in a timely manner.  The number of vaccine doses discarded should be collected and wastage calculated to determine vaccine need and other programme issues.  Vaccines and related supplies (e.g. safety boxes, syringes, and vaccine carriers) should be stored in good condition to maintain potent vaccine and working equipment.

Stock management in Zambia requires that vaccine is requested from the lower levels, i.e. Province, district and HF, from the higher level, i.e. Central level. Requisitions are expected on a monthly basis from HFs, and quarterly from central cold stores.  No more than one month’s supply should be stored at a HF. Stock-outs are sentinel events that indicate a problem in vaccine logistics.

Strengths

All the districts had staff members trained in vaccine management and no stock-out was experienced in the last six months at the national level. Since the policy was to for HFs to exhaust their existing stocks of lyophilized before switching vaccine formulations, gaps in vaccine supply during the switch from lyophilized to fully liquid pentavalent were rare.

Ninety-two percent (22 of 24) of HFs reported no vaccine or supply stockout in the past six months.

At the time of the switch, no change occurred in the frequency of vaccine deliveries at provincial, district and HF levels. This is due to sufficiency of the storage capacities at these levels as a result of routine cold chain replacement prior to the switch. Dry immunization supplies such as safety boxes, AD syringes, reporting forms, etc. are stored in a clean and orderly manner in 95% (21/22) of HFs.

The stock control method in place is first expired first use. There were no expired pentavalent vaccines at the central level. Only two HFs (8%) had vaccine expirations within the last six months.

Areas for Improvement

A significant proportion of vaccines including pentavalent were observed to be in VVM stage II.  The explanation is unknown, but vaccines were reportedly received from the national level in stage II and a check at the central store confirmed a high proportion of pentavalent in VVM stage II. HCWs were often observed to have a poor understanding of the different VVM stages. One out of 8 districts and 2 of 22 HFs had vaccine vials in VVM stage III and IV. One of 4 provinces and 3 of 23 HFs had expired vaccines in their refrigerators. In total 5/23 or 22% of HFs had either expired vaccine or vaccine VVM in stage III or IV in their refrigerators.

While some staff responsible for ordering vaccine do so appropriately, upon questioning it was apparent that many staff do not use optimal ordering techniques and are unable to accurately forecast their vaccine need. Most of the HFs do not have any standardized method for forecasting vaccine needs, including accounting for the 25% buffer stock. It was observed that requisitions for vaccine are based on previous quantity ordered and not necessarily on need. Due to poor forecasting, stocks-out in the last six months occurred in 1/4 province and 3/8 districts.

With the exception of the central level, vaccine wastage is not estimated at provincial, district and HF levels. All these rely on guidelines on wastage provided by the central stores.

Dry stores were generally well maintained, but in some cases, storage was done amongst other pharmaceuticals thereby making it difficult for appropriate removal.

Recommendations

- Train the health staff handling vaccines on vaccine management with emphasis on VVM.

- Spot-checks of vials should occur regularly at all levels to monitor the progression of vaccine to VVM stage II and identify any vials in stage III.

- Develop and implement comprehensive vaccine management strategy including use of the District Vaccine Management Tool (DVMT)

- Develop a simple, standardized method of vaccine forecasting at the national level .

- Conduct vaccine management training with focus on forecasting vaccine requirements.

- Supplement training with supportive supervision to ensure that the training was adequate; assist staff to implement their newly acquired techniques.

## Waste management and injection safety

Safe immunization practices are a key component of effective immunization programmes.  Safe injection practices minimize preventable morbidity in the recipients, such as abscesses, and in the HCWs, such as needle-stick injuries. Appropriate waste management protects the community from dangers from by-products of the immunization programme.

Strengths

All HCWs interviewed had a clear procedure to dispose of waste.  The primary method of disposal was either incineration or burial pits. Out of the 24 HFs visited, 10 each use incinerators and only one buries without burning. Clean disposal sites were observed in 23 of 24 HFs (96%). None of HFs had wastage report onsite.

There were no reported stock-outs for syringes or other injection supplies except for a province, two districts and one HF.

Safe injection practices were followed in 6 of the 7 HFs where vaccination sessions were observed. AD syringes are used in all HFs visited.

Areas for improvement

Seventeen of 24 (71%) of waste disposal sites were not fenced off. Some of the pits were found to be shallow. Some of the pits were used for disposal of other wastes other than injectable wastes. At three of 24 (13%) HFs, waste was transferred to another site and occasionally delays in wastage collection occurred.

Recommendations

- All pits should be of adequate depth

- To improve safety, all incinerators and burial pits should be fenced off.

Lessons learned for future vaccine introductions

The PIE offers an opportunity for other countries to improve their upcoming introductions based on the experiences of countries such as Zambia, who have been evaluated.  The lessons learned from Zambia fall into three categories: Training, policy and community preparedness.  They lessons are as follows:

## Training

- Training prior to new vaccine introduction ensures preparedness at all levels

- Distribution of training and written guidelines specific to the new vaccine is important to a successful introduction

- Training only one focal point per site may lead to gaps in knowledge

## Policy

- New vaccine introduction provides an opportunity to update national documents and existing policies

- The switch from lyophilized to liquid pentavalent increases cold chain requirements, particularly at the national level, reinforcing the need to assess capacity prior to introduction

## Community Preparedness

- Effective launching for lyophilized vaccine decreases the need for extensive social mobilization in preparation for the switch to fully liquid vaccine

## Sustainability

A good step towards financial sustainability in Zambia is the creation of a budget line for the EPI programme. The said budget line is used for purchasing vaccines and paying for other operational expenses.  All the traditional vaccines are paid for by the government of Zambia except BCG which is paid for by JICA. Zambia is already co-financing its pentavalent vaccine under the new vaccines financing policy in GAVI Phase II. However, the country is paying the co-financing amount above the minimum co-financing requirement applicable to Zambia. Any further new vaccine introduction in the country with GAVI support, for example pneumococcal or rotavirus vaccines, would have to be co-financed from the onset. Therefore, MOH needs to ensure that resources are mobilized well in advanced of any further new vaccine introduction to ensure the sustainability of the pentavalent vaccine and any new vaccines to be introduced.

## Follow-up Actions

As a result of this PIE, several actions still need to be accomplished for the recommendations to be fully considered, and acted upon, if deemed appropriate.  These follow-up actions are:

- Share PIE report with ICC and follow up on recommendations through inclusion of key activities in 2009 plans

- Continue to strengthen financial sustainability

- Maintain coverage gains

- Investigate cost-effectiveness of outreach sessions

- Conduct multi-disciplinary training for all levels using the revised RED guidelines as a basis

- Ensure proposed modifications to forms and charts are carried out and revised versions disseminated

- Monitor coverage during 2009 to determine impact of 2008 census figures

- Continue quarterly supervisory visits and use PIE recommendations for targeted support

- Conduct cold chain assessment and mobilize funds for gaps

- Conduct spot checks on vials at central store level

## Appendix I - Itinerary

## February 2

## Introductions to WHO Representative (PIE evaluation group)

## Briefing on PIEs (MOH, PIE Evaluation group, partners)

## Review and adaptation of PIE tool (MOH, PIE Evaluation group, partners)

## Introduction to Deputy Minister of Health (PIE evaluation group)

## February 3

    - PDA training

## Teams travel to field

## February 4-8

## Data collection in the field

## February 7-8

## Teams return from the field

## February  9

## Review findings and summaries with each field team and larger evaluation group

## February 9-11

## Data consolidation and analysis

## Finalization of findings and recommendations for final report (PIE Evaluation Teams, MOH  and partners)

## Report Writing

## February 12

## Report writing

## Summary of findings and recommendations presented to the Ministry of Health and ICC members

## Appendix II – Sites Visited

- Province: Central

  - District: Kabwe

    - Health facility: Natuseko

    - Health facility: Mahatma Ghandi

    - Health facility: Makululu

  - District: Mumbwa

    - Health facility: Nangoma mission hosp

    - Health facility: Bulungu

    - Health facility: Nakanjoli

- Province: Lusaka

  - District: Lusaka

    - Health facility: Chawama:

    - Health facility: M’tendere Health Centre

    - Health facility: Chipata

  - District: Chongwe

    - Health facility: Chongwe

    - Health facility: Kanakantapa

    - Health facility: Chalimbana

- Province: Luapula

  - District: Mansa

    - Health facility: Central

    - Health facility: Nsonga

    - Health facility: Butungwa

  - District: Mwense

    - Health facility: Stage II

    - Health facility: Mutango

    - Health facility: Mambilima

- Province: Copperbelt

  - District: Ndola

    - Health facility: New Masala

    - Health facility: Ndeke Urban

    - Health facility: Pamodzi

  - District: Masaiti

    - Health facility: Mishikishi

    - Health facility: Kafulafuta

    - Health facility: Masaiti Council

## Appendix III – Team Members

Team Lead: Mutale Mumba, WHO/AFRO/IST-ESA

Technical Support: Belem Matapo, WHO, Zambia

- Province: Lusaka

Site Visit Team Members

    - Pa Lamin Beyai, WHO/AFRO/IST-ESA (current UNDP, Ghana)

    - Penny Kalesha, MoH, Zambia

    - DunganI Cheembo, MoH, Zambia

Province/District Level Officers

    - Pauline Miyoba – Assistant MCH Coordinator

    - DunganI Cheembo – Logistics Officer

    - Christopher Sinkala – EPI Technician

    - Mastard Nyirenda – Ag DHIO

    - Penelope Kalesha – Child Health Specialist

    - Cecilia Sichinga – MCH Coordinator

- Province: Central

Site Visit Team Members

    - Jennifer Rosen, CDC

    - Obert Silwimba, MoH, Zambia

    - Josephine Simwinga, MoH, Zambia

Province/District Level Officers

    - Mildred Mwangala – CCS, MOH, Zambia

    - Maureen Simuchimba – CCS, MOH, Zambia

    - Wake Stanley – EPI Technicia

- Province: Luapula

Site Visit Team Members

    - Karen Hennessey, CDC

    - Mary Kaoma, HSSP/USAID

    - Abrahams Mwenamwenge, WHO

Province/District Level Officers

    - Agness M Mwenge – MCH Coordinator

    - West Sikanyika – Cold Chain Officer

    - V B Musopelo – District Cold Chain Officer

- Province: Copperbelt

Site Visit Team Members

    - Flint Zulu, UNICEF, Zambia

    - Helen Mutambo, WHO, Zambia

    - Elicah Kamiji, MoH, Zambia

Province/District Level Officers

    - Angela Ikowa – MCH Coordinator

Appendix IV: Recommendations

| Recommendation | Responsible party (lead agency 1st) | Timeframe |
| --- | --- | --- |
| Pre-implementation Planning and Training |  |  |
| For future vaccine introductions, adequate resources should be mobilized for pre-implementation training of a large number of health workers on new vaccine | MOH & Partners |  |
| For future vaccine introductions, training should be provided to a broader audience at the Health Facility level. | MOH |  |
| Health Care Worker Knowledge |  |  |
| Train HCW adequately on key components of pentavalent vaccine, including the side effects that require medical follow-up. | MOH |  |
| Advocacy, Communication and Acceptance |  |  |
| Sustain optimal communication on vaccines and vaccination between health workers and parents | MOH |  |
| Coverage and Reporting |  |  |
| Consider supplementary sources of target population estimates to better understand and approximate the true immunization coverage in each catchment area | MOH/CSO | Dec 09 |
| Improve use and analysis of outreach-specific data | MOH/WHO/UNICEF | Immediate |
| Monitoring and Supervision |  |  |
| Improve quality of training and supportive supervision all levels including: instruction on how to calculate, analyze and use immunization coverage and drop-out data to guide immunization activities; vaccine stock and cold chain management | MOH/WHO/UNICEF |  |
| Emphasis of timeliness of immunization data reporting at all levels during supervisory visits | MOH | Immediate |
| Use the existing inter-health center quarterly meetings to review immunization data and discuss immunization strategies with all HFs staff and community partners. | MOH | Immediate |
| Training and education on the awareness of types of expected reactions and types and response to adverse events occurring after immunization should be conducted. | MOH/WHO/UNICEF | Dec 09 |
| Improve quality of supportive supervision at HF level including the establishment of nation-wide use of standard supervisory logbooks to record observations and recommendations from supervisory visits | MOH | Immediate |
| Cold Chain Capacity and Management |  |  |
| Check list for EPI supervisory visits to include refrigerator and freezer maintenance, and appropriate placement of vaccines in refrigerators. | MOH | Jul 09 |
| Freeze-watch monitors should be provided to all levels of the cold chain. | MOH & Partners | Dec 09 |
| Create a standardized protocol that staff is expected to follow in case of power failure. | MOH/UNICEF/WHO | Immediate |
| An additional cold room should be purchased for the central store | MOH & Partners |  |
| Vaccine Management, Storage and Wastage |  |  |
| Train health staff on vaccine management with emphasis on VVM. | MOH/WHO/UNICEF | Dec 09 |
| Spot-checks of vials should occur regularly at all levels to monitor progression of vaccine to VVM stage II and identify vials in stage III. | MOH | Immediate |
| Develop and implement comprehensive vaccine management strategy including use of the District Vaccine Management Tool (DVMT) | MOH/WHO/UNICEF | Oct 09 |
| Develop a simple, standardized method of vaccine forecasting at the national level . | MOH/WHO/UNICEF | Jul 09 |
| Conduct vaccine management training with focus on forecasting vaccine requirements. | WHO/UNICEF | Dec 09 |
| Waste Management and Injection Safety |  |  |
| Ensure all pits are of adequate depth | MOH | Immediate |
| Ensure all waste disposal sites are fenced off. | MOH | Immediate |

| PRE-IMPLEMENTATION PLANNING &VACCINE INTRODUCTION: How prepared were the facilities for the new vaccine, and how well did it incorporate into the existing EPI program structure? |  |
| --- | --- |
| % reporting provision of training materials for the switch | 78 (18/23) |
| % reporting satisfaction with training | 92 (22/24) |
| % reporting smooth transition | 96 (23/24) |
| HCW KNOWLEDGE & PRACTICE: Do healthcare workers provide appropriate information to caregivers? |  |
| % reporting adequate information/instructions for caregivers during immunization sessions | 96 (23/24) |
| VACCINE COVERAGE AND REPORTING: Is coverage reported adequately and how much of the target population is receiving the new vaccine? |  |
| % able to calculate coverage correctly | 83 (20/24) |
| Range of fully liquid penta 3 coverage rates (%), 2008† | 76 to 230 |
| Range of fully liquid penta 3 drop-out rates (%), 2008† | − 42 to + 30 |
| MONITORING & SUPERVISION: How closely are the overall EPI program and health facilities supervised? |  |
| % of sites reporting >1 supervisory site visits in last 6 months | 100 (24/24) |
| % receiving written copy of supervisory visit | 95 (18/19) |
| COLD CHAIN MANAGEMENT: How sufficient is cold chain capacity and maintenance? |  |
| % of clinics reporting adequate cold store space at the time of the switch | 67 (16/24) |
| % with thermometer outside and/or inside refrigerator | 100 (24/24) |
| Among sites with refrigerators, % with daily temperatures reported on logs including holidays and weekends weeweekends and holidays, with temperatures consistently between 2-8°C | 96 (23/24) |
| VACCINE MANAGEMENT & STORAGE: How well is the current stock of vaccine maintained? |  |
| % with refrigerators containing only VVM stage 1 or 2 and non-expired vaccines | 78 (18/23) |
| % reporting no vaccine or supply stock-out in last 6 months | 92 (22/24) |
| VACCINE WASTAGE: How much vaccine is wasted? |  |
| % with wastage reports on site | 0 (0/24) |
| INJECTION SAFETY: Do healthcare workers perform safe vaccination practices? |  |
| % of sites with > 2 unsafe practices observed | 14 (1/7) |
| WASTE MANAGEMENT: How safely and effectively is vaccine waste material disposed of? |  |
| % with observed clean disposal site | 96 (23/24) |
| % with observed closed off disposal site | 29 (7/24) |

Appendix V: Key Indicators

† All represent coverage over 12 months except for 2 to 4 sites showing coverage over 6 months

Appendix VI: Data Collection Instrument

QUESTIONNAIRE - CENTRAL/REGIONAL/DISTRICT

This questionnaire was conducted at (check 1 and name level)

Central: _____________________

Region: ______________________

District: ______________________

Name (s) and title (s) of person(s) interviewed (please list all that you interviewed with): EPI Manager/person responsible for vaccinations (or their deputy) should be interviewed

Name________________________ Title _______________________

Name________________________ Title _______________________

Name________________________ Title _______________________

Contact details of most senior person:

Telephone __________________

e-mail address _______________________

Date of introduction of lyophilized pentavalent vaccine: 		______

Date of introduction of fully liquid pentavalent vaccine: 		______

Documents to ask for at beginning of interview:

Copy of national vaccine schedule (central level only)

Training materials/reference documents utilized during switch of vaccines

Immunization policy guidelines for vaccine management

Media campaign/social mobilization materials (brochures, posters, pamphlets, etc)

Central / Regional / District Questionnaire

Cells in light grey indicate that they are only asked at certain levels of the health service

| BACKGROUND INFORMATION |  |
| --- | --- |
| - Date of introduction of lyophilized pentavalent vaccine: | (DD/MM/YYYY) _____ / _____/ ______ |
| - Date of introduction of fully liquid pentavalent vaccine | (DD/MM/YYYY) _____ / _____/ ______ |
| - What is the population of children less than five years of age in this country/Region/ district | Number of children < 5 years of age ______________ Source/Year____________ |
| Central level interviews only - Did the switch take place in all regions at once or on a phased basis | - National introduction (all regions and districts at once) Phased introduction (explain) _______________________ |
| Central level interviews only - Why was the decision made to switch formulations? |  |
| Central level interviews only - What is the national EPI schedule Note: Ask for a copy of the schedule for all EPI vaccines (central level only) | Copy of schedule received Yes No |
| Central level interviews only - What is the schedule for the pentavalent vaccine ? Note: Insert age that dose should be given | Schedule: Dose 1 ___________ Dose 2___________ Dose 3___________ Dose 4___________ |
| Central level interviews only - If the schedule for pentavalent vaccine is different than WHO’s recommended schedule what is the rational for the change? Note: See WHO recommendations in PIE manual | Penta schedule as per WHO recommendations Yes No If no reason for difference ________________________ |
| - What are the antigens included in pentavalent vaccine? Note: Diphtheria, Pertussis, Tetanus, Hepatitis B, Haemophilus influenzae type b (Hib) |  |
| - What disease(s) does Hib vaccine prevent? Note: Hib vaccine prevents some, not all, meningitis and pneumonia. |  |
| PRE-IMPLEMENTATION PLANNING AND VACCINE INTRODUCTION PROCESS |  |
| - Did you develop a plan for the switch in vaccine presentations? | Yes. If yes, please provide a copy at time of interview No. If no why not? |
| - Please describe staff training in preparation for the switch in pentavalent vaccine presentation. Prompts:Was it conducted before or after vaccine introduction? How soon before/after? What method i.e. cascade? Region by region? Who conducted the training? |  |
| - How was the training financed? |  |
| - Were there any problems with the training? | Yes No. If yes, please describe |
| - What educational and reference materials were provided to participants at time of training? Ask for samples |  |
| - What instructions were given for a child who had already started their vaccinations e.g. had received one or two doses with lyophilized vaccine? |  |
| - What policy was established for the remaining quantities lyophilized pentavalent vaccine after the switch? Prompt: Was vaccine kept in district/facility cold chain? Phased out through use? Destroyed? Sent to province/national level? Given to another district? |  |
| - How well was the fully liquid pentavalent vaccine accepted? If there were any issues please comment for each group. Prompt: by the community, health care workers, others | Well accepted Not well accepted Health care workers Professional Societies Community Government Media |
| VACCINE COVERAGE |  |
| - How do you calculate vaccine coverage? What formula do you use? What sources of data do you use? | Their formula:___________________ Formula: Correct formula Incorrect formula Did not know |
| - What was lyophilized penta1 and lyophilized penta3 vaccine coverage in the year before the switch? NOTE: Have them calculate coverage without assistance or prompting, using immunization monitoring chart. If not calculated correctly, calculate coverage with them. Use this as a teaching opportunity. NOTE: Use year before switch or closest administrative period (January to June 30, 2006) | Did the interviewee calculate coverage correctly? Yes, No, Report the CORRECT coverage: Penta1 (lyophilized) _________ year _________ # immunized:____________________ Target population:________________ Penta3 (lyophilized) __________ year _________ # immunized:___________________ Target population:________________ |
| - How do you calculate vaccine drop-out rate? | Formula: Correct Incorrect Did not know |
| - What was lyophilized penta3 drop-out? NOTE: Have them calculate drop-out rate without assistance or prompting. If not calculated correctly, calculate drop-out with them. Use this as a teaching opportunity. Calculate drop out rate: Penta1-Penta3 x 100 = _____% Penta1 (January to June 30, 2006) | Did the interviewee calculate drop-out correctly on his/her own? Yes, No, Report the CORRECT drop-out (lyophilized penta):____________% |
| - What was liquid penta1 and liquid penta3 vaccine coverage? Note: Use latest administrative period available (January to December 2008) (January to June 30, 2008) | Did the interviewee calculate coverage correctly? Yes, No Report the CORRECT coverage: Penta1 (liquid) _________ year _________ # immunized:____________________ Target population:________________ Penta3 (liquid) __________ year _________ # immunized:___________________ Target population:________________ Complete? Yes, No, |
| - What was liquid penta3 drop-out? (January to June 30, 2008) | Did the interviewee calculate drop-out correctly? Yes, No, Report the CORRECT drop-out (liquid penta):____________% |
| - Is coverage of liquid penta1 vaccine higher or lower than lyophilized pentavalent vaccine? Is coverage of liquid penta3 vaccine higher or lower than lyophilized pentavalent vaccine? | Penta1 (liquid) coverage Higher Lower No change Penta3 (liquid) coverage Higher Lower No change |
| - Is the dropout rate for liquid pentavalent vaccine higher or lower than lyophilized pentavalent vaccine? | Penta (liquid) drop out rate versus Penta (lyophilized) drop out rate Higher Lower No change |
| - In the last 6 months, what proportion of Provinces/districts/health facilities sent monthly immunization summary forms on time? How complete was the data? | % of regions/districts/health facilities submitting reports monthly on time ______ Estimated completeness of data _________% (of reports received how many have all information completed) |
| COLD CHAIN MANAGEMENT |  |
| - Discuss any changes you had to make in the cold chain before the switch Note: The volume of the fully liquid vaccine is greater than the volume of the lyophilized vaccine. Try and separate cold chain expansion / replacement of equipment that is part of normal cold chain rehabilitation versus changes specifically for the switch. |  |
| - Were there any problems with the cold chain system following the switch? If yes, what were the problems and how have the problems been addressed? Prompts: Frozen vaccine, malfunctioning refrigerators, power supply |  |
| - Do you use freezewatch monitors during vaccine transportation? | Yes No |
| VACCINE MANAGEMENT, STORAGE & LOGISTICS |  |
| - Do you have immunization policy guidelines for vaccine management? If yes, have they been updated to include the liquid pentavalent vaccine? Please provide a copy at time of interview | Yes No |
| - How do you forecast vaccine need? Did the estimated needs change with the switch in vaccine formulation? |  |
| - Please describe how vaccines are transported to the regions/districts/health facilities. |  |
| - For the old lyophilized vaccine how often did you receive and send out vaccine shipments and supplies from your level of the health service to the next level? |  |
| Did the frequency of deliveries change with the switch to liquid pentavalent vaccine? If yes, by how much? Note: Specify the change in logistics e.g. hiring extra trucks, using larger trucks, hiring extra staff, using extra petrol, other supplies etc. |  |
| - Have you had any stock-outs of the liquid pentavalent vaccine since introduction? What was the reason? Note: Probe for the real reason for the stock out. Shortage of vaccine or management problems. |  |
| - Did you have any stock-outs of any other vaccine in the past 6 months. If yes, which vaccines and what was the reason? |  |
| - Did you have a gap between finishing lyophilized pentavalent vaccine stock and receiving the liquid pentavalent vaccine? If yes, for how long. | Yes No If yes, how many weeks: _____ |
| MONITORING AND SUPERVISION |  |
| - Have you or a member of your staff or a partner organization made supervisory visits, to the districts/health facilities since the switch? If so, how often and by whom? | Yes No How often: ________ By whom: ___________________ |
| - How do supervisors give feedback to sites visited? Prompts: Discuss improvements at time of visits? Complete supervisory checklist? Send site visit report? Conduct follow up visits with poorly performing sites? |  |
| Question for Districts only - Have you received a supervisory visit since liquid pentavalent vaccine introduction? If yes, when and by whom? | Yes No When: _______________ By whom: ________________________ |
| WASTE MANAGEMENT & INJECTION SAFETY |  |
| Question for Central only - Describe the waste disposal system at each level of the health service. |  |
| - Did you have to make changes to your waste disposal system for introduction of liquid pentavalent vaccine? If yes explain. |  |
| - What are the key safety and immunization waste management messages that you provide to staff regarding the liquid pentavalent vaccine? Prompts: Written injection safety or waste management policy (ask for copy), auto-disposable syringes only, bury, problems adhering to policies |  |
| VACCINE WASTAGE |  |
| - What was the lyophilized pentavalent vaccine wastage rate? | lyophilized pentavalent wastage rate _____________ |
| - What is the liquid pentavalent vaccine wastage rate? | Liquid pentavalent wastage rate (this admin period) _________ |
| - Has the liquid pentavalent vaccine wastage rate changed when compared to the lyophilized pentavalent vaccine wastage rate | Pentavalent (liquid) wastage rate versus Pentavalent (lyophilized) wastage rate Increased Decreased No change |
| ADVERESE EVENTS FOLLING IMMUNIZATION (AEFI) |  |
| - Do you have a system and written protocol to track AEFI for all vaccines? Please describe the procedure. If no system why not? |  |
| - Have you had any reported AEFI since the switch? If yes, how many cases and how was it handled? |  |
| ADVOCACY & COMMUNICATION |  |
| For central and regional interviews only - Did you have any media or community awareness around the switch in vaccine formulation? Prompt: If no why not? If yes, what did it involve, was it successful, did it get much media coverage, what were the associated costs?? |  |
| - Did you prepare or distribute any health education material for the community on the liquid pentavalent vaccine? If yes what, and when and what was the associated cost? Prompts: Posters, Brochures, Flyers what were the main messages, were they distributed before or after vaccine introduction? Please ask for copies of any materials |  |
| SUSTAINABILITY |  |
| For central interviews only - Is there a budget line for immunization in the national budget? |  |
| - How are traditional vaccines paid for? Note: List all sources that pay for the vaccine |  |
| For central and regional interviews only - How is pentavalent vaccine paid for? |  |
| For central and regional interviews only - Do you plan to introduce any more new vaccines in the future? If yes which one(s) and when? Note: If they say no this is an opportunity to mention new vaccines such as pneumococcal vaccine, rotavirus vaccine and HPV that will be available in the future. |  |
| GENERAL IMPRESSIONS |  |
| - What costs or savings were involved in the switch to fully liquid pentavalent vaccine? Prompt: Cold chain, transport, wastage, communications materials, training, media, unexpected costs (specify) |  |
| - What effect has the introduction of the fully liquid pentavalent vaccine had on your EPI program? In your opinion was it a smooth process or problematic? Please explain | Please check one that best describes the introduction: Very smooth no problems Smooth, minor problems. Please explain Somewhat smooth, some major problems. Please explain Not smooth at all, Some major problems. Please explain |
| - Other countries may have to switch formulations in the future. Is there any advice that you would give them to ensure a smooth switch? |  |

The following questions require observation of the vaccine storage areas at the Central /Regional /District levels

| OBSERVATION OF VACCINE STORAGE AREA |  |
| --- | --- |
| - Are all refrigerators clean and properly functioning? | Y N |
| - Is there a thermometer inside the refrigerator? | Y N |
| - Is the temperature inside the refrigerator between +2 º and +8º C | Y N |
| - Is there a thermometer outside the refrigerator? | Y N |
| - Is there a log of refrigerator temperatures? | Y N |
| - Is the temperature recorded in the log consistently between +2 º and +8º C. | Y N |
| - How often are temperatures recorded? | Twice daily Daily No records Other (specify) ____________________ |
| - Are temperatures monitored and recorded on weekends and holidays? Note: Check specifically for the most recent weekend and holiday period | Y N Sometimes |
| - Are all vaccines arranged as “First expiry First out”? | Y N Not applicable, all vaccines have same expiration date |
| - Did you observe any expired vaccines? | Y N |

(For vaccines with a VVM)

| - Did the VVMs that you observed indicate that vaccine is useable i.e. stage 1 or 2 | Yes, all vaccines useable No some vaccines stage 3 or 4 (unusable) Specify vaccine and proportion unusable ___________________ |  |
| --- | --- | --- |
| For vaccines with a VVM) - Are vaccines with VVM stage 2 arranged so they are used first? |  | Y N Not applicable, no stage 2 |  |
| - Are there spaces between the vaccine boxes/trays to allow air circulation? |  | Y N |  |
| - Is there any remaining stock of liquid lyophilized pentavalent vaccine in the refrigerator? |  |  |  |
| - Is injection equipment stored in good condition (space, temp, organization, etc) |  | Y N |  |
| - Was the last batch of vaccines and injection equipment received bundled i.e. were there adequate syringes and needles and safety boxes for the number of vaccines supplied? Note: Look at stock list to get this information. |  | Y N |  |
| NOTES |  |  |  |
| Add any comments here |  | If you were unable to visit the cold store or dry store area, please mention reason. |  |

QUESTIONNAIRE HEALTH FACILITY

This questionnaire was conducted at

Health Facility Name: ________________________

Type of Health Facility (check one):

Health Center/Clinic      Health Post/Outpost       Other (specify) ____________________

Name (s) and title (s) of person(s) interviewed (please list all that you interviewed with): EPI Senior Nurse/Healthcare Worker responsible for vaccinations (or their deputy) should be interviewed

Name________________________ Title _______________________

Name________________________ Title _______________________

Name________________________ Title _______________________

Contact details of most senior person:

Telephone __________________

e-mail address _______________________

Documents to ask for at beginning of interview:

Training materials/reference documents utilized at pentavalent vaccine training

Immunization policy guidelines for vaccine management

  - Logbooks, monitoring forms, tally sheets, etc

  - Monthly coverage report

  - written guidelines for vaccine management

  - supervisory book (site visit book)

  - Wastage report

  - AEFI report (if applicable)

Health Facility Questionnaire

| PRE-IMPLEMENTATATION PLANNING |  |
| --- | --- |
| - Date of introduction of lyophilized pentavalent vaccine in this health facility | (MM/YYYY) _________/ ______ |
| - Date of switch to fully liquid pentavalent vaccine in this health facility | (MM/YYYY) _________/ ______ |
| - Please describe staff training to prepare for the switch. Prompts: Was it conducted before or after vaccine introduction? How soon before/after? What method i.e. cascade? Region by region? Who conducted the training? |  |
| - Were there any problems with the training? Prompts: Were topics adequately covered? Were all staff in the facility trained? | Yes No. If yes, please describe |
| - Were you provided with any introduction guidelines or paper copies of any training materials regarding the switch? Ask to see samples | Key Indicator: guidelines/training materials provided? Yes No |
| - Overall were you satisfied with the training provided? If no, why not | Key Indicator: satisfaction with training? Yes No If no specify reason _______________________________ |
| - What effect has the switch to the liquid pentavalent vaccine had on your routine immunization program? Prompts: Improved day to day management of immunization. Increased or decreased demand for services. Increased /decreased work load | Positive Negative Same Expand ___________________________________________ |
| - What did you do after the switch if a child came in who had already received one or two doses of lyophilized vaccine? |  |
| VACCINE COVERAGE |  |
| - What is the size of the target population for your area? Age <1 year? Age <5 years? | Target population: Age <1 year:__________ Age <5 years:_____________ |
| - How do you record and summarize immunization administration of all vaccines for your reports? NOTE: consider a spot check for the summary report | tally sheets log books monthly summary sheet other:___________ |
| - How do you calculate vaccine coverage? What formula do you use? What sources of data do you use? | Their formula:___________________ Formula: Correct formula Incorrect formula Did not know Source of data:_________________ |
| - What was lyophilized penta1 and lyophilized penta3 vaccine coverage in the year before the switch? NOTE: Have them calculate coverage without assistance or prompting, using immunization monitoring chart. If not calculated correctly, calculate coverage with them. Use this as a teaching opportunity. NOTE: Use January to December 2006 | Did the interviewee calculate coverage correctly on his/her own? Yes, calculated coverage correctly No, did not calculate coverage correctly Report the CORRECT coverage: Penta1 (lyophilized) _________ year _________ # immunized:____________________ Target population:________________ Penta3 (lyophilized) __________ year _________ # immunized:___________________ Target population:________________ |
| - How do you calculate vaccine drop-out rate? What formula do you use? | Their formula:___________________ Formula: Correct formula Incorrect formula Did not know |
| - What was lyophilized penta3 drop-out (use same year as for question #12)? NOTE: Have them calculate drop-out rate without assistance or prompting. If not calculated correctly, calculate drop-out with them. Use this as a teaching opportunity. Use January to December 2006 Calculate drop out rate: Penta1-Penta3 x 100 = _____% Penta1 | Did the interviewee calculate drop-out correctly on his/her own? Yes, calculated correctly No, did not calculate correctly Report the CORRECT drop-out (lyophilized penta):____________% |
| - What was liquid penta1 and liquid penta3 vaccine coverage? Note: Use latest administrative period available Use January to December 2008 | Did the interviewee calculate coverage correctly on his/her own? Yes, calculated coverage correctly No, did not calculate coverage correctly Report the CORRECT coverage: Penta1 (liquid) _________ year _________ # immunized:____________________ Target population:________________ Penta3 (liquid) __________ year _________ # immunized:___________________ Target population:________________ |
| - What was liquid penta3 drop-out (use same year as for question 15)? Use January to December 2008 | Did the interviewee calculate drop-out correctly on his/her own? Yes, calculated correctly No, did not calculate correctly Report the CORRECT drop-out (liquid penta):____________% |
| - Is coverage of liquid penta1 vaccine higher or lower than lyophilized pentavalent vaccine? Is coverage of liquid penta3 vaccine higher or lower than lyophilized pentavalent vaccine? | Penta1 (liquid) coverage Higher Lower No change Penta3 (liquid) coverage Higher Lower No change |
| - Is the dropout rate for liquid pentavalent vaccine higher or lower than lyophilized pentavalent vaccine? | Penta (liquid) drop out rate versus Penta (lyophilized) drop out rate Higher Lower No change |
| - How often do you report immunization data to the district? Ask to see a report |  |
| - How many days a week does your site perform outreach immunization sessions i.e. immunization sessions not conducted at the health facility? Note: Assess whether outreach data is recorded separately |  |
| - Is outreach data recorded separately? | recorded separately not recorded separately |
| - Did you have to make any changes to outreach sessions when you introduced the liquid pentavalent vaccine Did you require more vaccine carriers? More trips to collect vaccine from health facility? | Changes? yes no More vaccine carriers? yes no More trips? yes no |
| COLD CHAIN MANAGEMENT |  |
| - Where do you store your vaccines and what power source is used for refrigeration? |  |
| - If there is an interruption in your power supply what do you do? (includes lack of kerosene) |  |
| - Was your cold storage capacity enough at the time you switched to liquid pentavalent vaccine? List any changes you had to make Prompts: may have increased space due to reduced wastage, increased frequency of delivery, new equipment etc | Key Indicator: problems with capacity? Yes No List changes |
| - Please describe any problems with the cold chain in the past 6 months and how they were resolved. Prompts. Power supply problem, fuel shortage, equipment breakdown, frozen vaccine vials, temperature fluctuation. | Key Indicator: problems other than cold space? Yes No |
| VACCINE MANAGEMENT, STORAGE, & LOGISTICS |  |
| - Do you have written guidelines for vaccine management and if so, do the guidelines include the liquid pentavalent vaccine? Ask to see a copy |  |
| - Please describe how vaccines are transported to your health facility Prompts: Who orders, how is need determined, Has need increased since introduction of the new vaccine? How often are vaccines delivered? |  |
| - For the old lyophilized vaccine how often did you receive vaccine and supplies? |  |
| - Did the frequency of deliveries change with the switch to liquid pentavalent vaccine? If yes, by how much? Note: Specify the change in logistics e.g. more frequent trips, using extra petrol, other. |  |
| - What did you do with remaining quantities of lyophilized pentavalent vaccine after the switch? Prompts: Was vaccine kept in district/facility cold chain? Phased out through use? Destroyed? Sent to province/national level? Given to another district? |  |
| - Did you have a gap between finishing lypholized pentavalent vaccine and receiving the fully liquid pentavalent vaccine? If yes, for how long? |  |
| - Have you had vaccine expirations in the last 6 months? If yes, what did you do with the expired stock? |  |
| - Have you had stock outs of the liquid pentavalent vaccine or any other vaccine, syringe or safety box in the last 6 months? If yes, what and how long did it last? | Key Indicator: vaccine or supply stock out? Yes No |
| MONITORING AND SUPERVISION |  |
| - How many times in the past 6 months have you received a supervisory visit from district or regional level or from a partner agency? Ask to see the supervisory book | Key Indicator: One or more visits? Yes No Number of visits ___________ Is there a written copy of the visit? Yes No (ask to see report) |
| - If yes, who visited, and what were the problems identified? | Who visited _______________________________ (job title) Problems identified _________________________________ |
| HEALTH CARE WORKER KNOWLEDGE: |  |
| - What antigens are included in pentavalent vaccine? | Tick if mentioned – don’t prompt but can tell afterwards Diphtheria Pertussis Tetanus Haemophilus Influenzae type B (Hib) Hepatitis B (Hep B) List others mentioned __________________________ |
| - What disease(s) does the Hib component of pentavalent vaccine prevent? Interviewer: Hib vaccine prevents some, not all, meningitis and pneumonia. | Interviewer : Quote exact response given |
| - What disease(s) does the Hepatitis B component of pentavalent vaccine prevent? | Interviewer : Quote exact response given |
| - What information do you provide to parents before and after vaccination with pentavalent vaccine? | Tick if mentioned – don’t prompt but can tell afterwards Vaccine Schedule/When to return Normal side effects? What side effects they should return for Bring vaccination card Other health messages (specify) _____________________ Two or more mentioned? Yes No Key Indicator: HCW providing adequate information to parents? Yes No |
| WASTE MANAGEMENT AND INJECTION SAFETY |  |
| - How do you dispose of used syringes, needles, and safety boxes? Prompts: Burn in incinerator or pit and bury; bury without burning, transport to another site. |  |
| - Have you experienced any problems with your waste disposal system? Prompts: No fuel for burning, incinerator not working, For pneumococcal vaccine glass syringes. Observe site |  |
| VACCINE WASTAGE |  |
| - How do you determine how much of the pentavalent vaccine has been used and wasted at the end of an immunization session? Ask for wastage report | Key Indicator: wastage report on site? Yes No |
| - What was the lyophilized pentavalent vaccine wastage rate? | lyophilized pentavalent wastage rate _____________ |
| - What is the liquid pentavalent vaccine vaccine wastage rate? | Liquid pentavalent wastage rate (this admin period) _________ |
| - Has the liquid pentavalent vaccine wastage rate changed when compared to the lyophilized pentavalent vaccine wastage rate? Note: Calculate using administrative periods. Would expect a decrease as went from a two dose to a single dose vial. If wastage not calculated ask whether they think wastage has changed. | Key Indicator: Pentavalent (liquid) wastage rate versus Pentavalent (lypholized) wastage rate Increased Decreased No change |
| ADVERESE EVENTS FOLLOWING IMMUNIZATION |  |
| - Have you had any reported AEFI since the switch? If yes how many cases and how was it handled? Ask to see report | Yes No |
| - If no AEFI what would you do if you had an AEFI? | Key Indicator: AEFI procedure in place? Yes No |
| ADVOCACY, COMMUNICATION & ACCEPTANCE |  |
| - Did you provide any health education messages or materials to the community about the switch to fully liquid pentavalent vaccine? Prompts: Posters, Brochures, health education sessions to community leaders, public meetings etc. | Yes No If yes, was there any cost associated? |
| - Did you experience any resistance from the community or encounter any problems regarding the switch to fully liquid pentavalent vaccine? |  |
| GENERAL IMPRESSIONS |  |
| - What costs and or /savings were involved in the switch to fully liquid pentavalent vaccine? Prompt: cold chain, transport, wastage, communications materials, training, media, unexpected costs (specify) | Y N If yes, specify:_____________________________________ |
| - What effect had the introduction of the fully liquid pentavalent vaccine had on your facility? In your opinion was it a smooth process or problematic? | Please check one that best describes the introduction: Very smooth no problems Smooth, minor problems. Please explain Somewhat smooth, some major problems. Please explain Not smooth at all, Some major problems. Please explain Key Indicator: Smooth transition (A & B)? Y N |
| - Have you any other comments to add regarding the switch to fully liquid pentavalent vaccine? |  |

The following questions require observation of the vaccine storage areas at the Health Facility Level

| OBSERVATIONS AT VACCINATION SESSION |  |
| --- | --- |
| - Are (all) vaccines reconstituted correctly? (E.g. measles, BCG) | Y N |
| - Are vaccines stored/handled properly during the session? e.g. clean, organized, vaccine vials outside carrier are in foam pad etc | Y N |
| - Are good injection techniques observed (e.g. pentavalent intramuscular thigh) | Y N |
| - Are auto-disposable syringes used? | Y N |
| - Are needles recapped? | Y N |
| - Are needles and syringes disposed of in a safety box? | Y N |
| - Is correct use of the open multi-dose vial policy observed? | Y N |
| - Summary – were 2 or more unsafe practices observed? | Y N Key Indicator |
| OBSERVATION OF VACCINE STORAGE AREA |  |
| - Are all refrigerators clean and properly functioning? | Y N |
| - Is there a thermometer outside the refrigerator? | Y N |
| - Is there a thermometer inside the refrigerator? | Y N |
| - Is the temperature inside the refrigerator between +2 º and +8º C | Y N |
| - Is there are log of refrigerator temperatures? | Y N |
| - If yes, has temperature consistently between +2 º and +8º C in the last 2 months? | Y N |
| - How often are temperatures recorded? | twice daily daily No records Other (specify) ___________________ |
| - Are temperatures monitored and recorded on weekends and holidays? Note: Check specifically for the most recent weekend and holiday period | Y N Sometimes |
| - Are vaccines arranged as “First expiry First out”? | Y N |
| - Did you observe any expired vaccines? | Y N |
| (For vaccines with a VVM) - Are any vaccines currently in the refrigerator expired or with VVM stage 3 or 4? | Y N Key Indicator |
| (For vaccines with a VVM) - Are vaccines with VVM in stage 2 arranged so that they are used first? | Y N Not applicable, no stage 2 |
| - Are there spaces between the vaccine boxes/trays to allow air circulation? | Y N |
| - Is there any remaining stock of liquid lyophilized pentavalent vaccine in the refrigerator? |  |
| - Are there other medical supplies/reagents stored in the refrigerator with the vaccines? If yes, what sorts of other supplies? | Y N |
| HEALTH COMMUNICATION |  |
| - Are any posters or other literature about the new vaccine noted in the health facility? | Y N |
| STOCK ROOM |  |
| - Is injection equipment stored in good condition (space, temp, organization, etc) | Y N |
| WASTE DISPOSAL |  |
| - Observe how used needles and syringes are being disposed | Safety box Open bucket Other ___________________ Not observed |
| - Observe how used safety boxes are being disposed of (If not observed, ask how waste is disposed of) Note: Specify whether box is emptied and reused or destroyed with contents inside. | Incinerator Pit-burned Pit-exposed Pit-buried Above ground area Not observed |
| Were discarded needles and syringes observed on the ground outside the facility? Describe any other observation of the disposal site | Y N Key Indicator: Waste disposal site clean and closed off? Y N |
| NOTES |  |
| Interviewer – compare questionnaire responses from clinic visit to observed practice noted above and summarize any discrepancies. | If you were unable to visit the cold store or dry store area, please mention reason. |

QUESTIONNAIRE FOR MOTHER OR CAREGIVER

Region: _________________District: _____________________Health Facility Name: ____________________________

Health Facility Level: Person(s) to interview: Mothers or caregivers whose child has just received the new vaccine (can also talk to a group of mothers waiting to be vaccinated to get their impressions)

Interviewer Note: Please modify as appropriate for the type of new vaccine introduced

“I would like to ask you a few questions about the vaccines your child received today. The answers you give will help us learn more about new vaccines being used.”

| - What injection(s) did your child receive today? | Interviewer: record mothers exact response (vaccines, diseases, or general wellbeing) |
| --- | --- |
| - Do you know when to bring your child for his/her next vaccination? | yes (answer correct) yes (answer incorrect) no Interviewer: If answer is no or yes but incorrect, please advise mother of when next vaccination is due |
| - Do you know any reaction that your child may get following his/her vaccination today? | yes (answer correct) Heard from ___________ yes (answer incorrect) Heard from ___________ no Interviewer: If answer is no or yes but incorrect please advise mother of potential side effects e.g. mild redness, pain, mild swelling at injection site, mild fever, Drowsiness and irritability. |
| - Do you have an immunization card for your child with you today? | Card present yes no If yes: May I please see it? Record vaccines that were received today Pentavalent OPV Measles BCG Other (specify)________________________ Note if there is a space to record pentavalent vaccine |
| - Other comments or observations |  |

Zambia’s Proposal to GAVI for Pentavalent Vaccine, April 2001.

Field Guide for Introduction of New vaccines in Zambia, 2004.

Trip Report by Andrew Garnett on the Zambia EVSM assessment, 21-25 July 2003.