| Maharashtra State Report FINAL Oct 13, 2014 |  |  |
| --- | --- | --- |
|  | JALNA | END TERM EVALUATION OF CHILD RIGHTS PROJECT |
| WARDHA |  |  |
|  | YAVATMAL |  |

# Submitted By:                                                                        Submitted To:

# An ISO 9001:2008 Organisation

# ANNEXURES

### ANNEXURE 1: Key Child Protection Legislation and Schemes in India

#### Juvenile Justice Act

The JJA is a central legislation that forms the primary legal framework for juvenile justice in India. It broadly deals with two categories of children viz. children in need of care and protection (CNCP) and children in conflict with the law (CNCL). The JJA has been enacted in India in conformity with relevant international protocols such as United Nations Standard Minimum Rules for the Administration of the Juvenile Justice 1985 (Beijing Rules) and is based on the CRC. The Act requires states to set up the necessary infrastructure and protocols for ensuring that provisions are implemented and justice for children is delivered quickly, so that their childhood and rights are not violated. It focuses on safeguarding the best interests of children in CNCP and CNCL categories. One of the JJA’s key principles is that the best interest of the child is preserved in the family setting and as such the family is primarily responsible for providing care and protection of children, and that institutionalisation of a child should be the last resort. The Government of India (GoI) provides financial assistance to State Governments/Union Territory (UT) Administrations for the establishment and maintenance of various homes, salary of staff, food, clothing, etc. for vulnerable children.

#### Child Marriage Act

The Prohibition of Child Marriage Act, 2006 came into force on 1 November 2007.  The Child Marriage Prohibition Officer (CMPO) and District Collector are responsible for sensitisation and awareness creation in the community on the harmful effects of child marriage and the law. It is also the community’s responsibility to make use of the law whose basic premise is: To make a child go through a marriage is an offence. A child or minor is a person up to 18 years of age in the case of girls and 21 years of age in the case of boys.

#### Child Labour Act

The Child Labour (Prohibition and Regulation) Act, 1986 does not specifically prohibit the work of children in agriculture; but restricts the maximum number of working hours in a day for children to six hours including time spent waiting for the work. The Act is limited to children up to 14 years of age and does not provide protection to children in the 15-18 years age group who work in exploitative conditions. On the other hand, the JJA pertains to children in need of care and protection, including working children below 18 years. The project recognises the disconnect between these two legislations and has advocated for raising of the age bar from 14 years to 18 years (e.g. Rajasthan) and amending the Child Labour Law to include prohibition of child labour in agriculture (e.g. Maharashtra).

#### Integrated Child Protection Scheme

The Integrated Child Protection Scheme (ICPS) under the Ministry of Women and Child Development (MWCD) was introduced in 2009. ICPS is a centrally sponsored scheme aimed at building a protective environment for children in difficult circumstances, as well as other vulnerable children, through Government-CSO partnerships. The ICPS mandates establishment of service delivery structures and statutory support services for vulnerable children at various levels including state, district, block and community.

#### National Child Labour Project

The National Child Labour Project is implemented by the Ministry of Labour. The scheme serves to rehabilitate child labourers by funding Project Societies in select districts to open up special schools/rehabilitation centres. These centres provide non-formal education, vocational training, supplementary nutrition, stipends, etc. to children withdrawn from employment.

### ANNEXURE 2: Education Legislation and Schemes in India

#### Right to Education Act

The Right of Children to Free and Compulsory Education (RTE) Act, 2009 came into effect April 1, 2010. The Act mandates government and local authorities to provide and ensure admission, attendance and completion of elementary education by all children aged 6-14 years. RTE provides for specific provisions for disadvantaged groups, such as child labourers, migrant children, children with special needs, or those who have a “disadvantage owing to social, cultural, economical, geographical, linguistic, gender or such other factor.”

RTE focuses on the quality of teaching and learning, which requires accelerated efforts and substantial reforms.

#### Sarva Shiksha Abhiyan

Sarva Shiksha Abhiyan (SSA) has been operational since 2000-2001 to provide for a variety of interventions for universal access and retention, bridging of gender and social category gaps in elementary education and improving the quality of learning. SSA interventions include inter alia, opening of new schools and alternate schooling facilities, construction of schools and additional classrooms, toilets and drinking water, provisioning for teachers, periodic teacher training and academic resource support, textbooks and support for learning achievement. With the passing of the RTE Act, changes have been incorporated into the SSA approach, strategies and norms.

The Integrated Child Development Services (ICDS) is a programme for early childhood development under the Ministry of Women and Child Development. The programme comprises six components including delivery of pre-school non-formal education for children aged 3-6 years. Other services under the scheme include supplementary nutrition; immunisation; health check-up; referral services; and nutrition and health education. The targeted beneficiaries under the scheme are children (0-6 years), pregnant and lactating mothers, and women (15-45 years). Services, including pre-school education, are primarily delivered from the Anganwadi Centre (AWC) by Anganwadi Workers (AWWs).

### ANNEXURE 3: Project Logical Framework

| Consolidated results matrix of progress in Child Rights in Cotton Areas- Gujarat, Maharashtra and Rajasthan, 2009.015.UNI.IN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Results/ Outcomes/ Outputs | Indicators | Baselines |  |  | Targets |  |  | Progress as on December 2011 |  |  | Progress as on 31.12.2012 |  |  | Progress as on 31.12.2013 |  |  | Remarks |
|  |  | Guj | Mah | Raj | Guj | Mah | Raj | Guj | Mah | Raj | Guj | Mah | Raj | Guj | Mah | Raj |  |
| Strategic Result In cotton and cotton seed production areas children in the age group of 6 to 14 years are not working and are in school | Children in age group 6-14 years who are out of school[1] are reduced from X% to Y% | 15% | 7.90% | 7% | 5% | 4% | 3% | To be determined through the end line survey | To be determined through the end line survey | To be determined through the end line survey | 6% | 3.7% | 6.1% | 0.8% | 0.5% | 3% | Rajasthan: This is as per Government of Rajasthan Child tracking system Maharashtra: This is as per Government of Maharashtra figures based on DISE 2013-14 and SDP 2014-15 Gujarat- DISE data - in 2013 there are only 21,694 out of school children against the total population of children 2,816,761 |
| Outcome 1 Child protection structures in place addressing child labour issues | Child protection structures are established and operational at the state and district levels. | CWC, JJB established but not functional. |  |  | All structures established and operational |  |  | CWCs/JJBs functional |  |  | All structures established and operational | All structures established and operational | All structures established and operational | All structures established and operational | All structures established and operational | All structures established and operational |  |
|  |  | SCPS, DCPU, SJPU not established and not functional |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | State and District level Task Force (DLTF) on Child Labour established, Plans developed, and implementation monitored | 0 DLTF | 0 DLTF | 0 DLTF | 6 DLTF | 3 DLTF | 2 DLTF | 6 DLTF | 3 DLTF | 2 DLTF | 6 DLTF | 3 DLTF | 2 DLTF | 6 DLTF | 3 DLTF | 2 DLTF | Gujarat, Maharashtra and Rajasthan- target achieved in 2011 |
| 1.1 Child Protection structures under labour and Integrated Child Protection Scheme/Juvenile Justice in place, functioning at state, district, and panchayat level | Notifications/Resolutions are issued by the State Governments for establishment of child protection structures at state and district level | 0 Notif/ Resol | 3 Notif/ Resol | 3 Notif/ Resol | 1 Notif/ Resol | 7 Notif/ Resol | 6 Notif/ Resol | 01 Notification issued | 7 Notif/Resol | 6 Notif/Resol | 1 Notif/Resol | 7 Notif/Resol | 8 Notified | 1 Notif / Resol | 7 Notif / Resol | 11 Notifications | Gujarat, Maharashtra and Rajasthan- target achieved in 2011. Rajasthan- Five more notifications issued. |
|  | SCPS and DCPU established and meetings carried out on schedule | 0 | 0 | SCPS- 0 | 1 SCPS | 1 SCPS | SCPS- 1 | SCPS-1 | MoU for ICPS signed and SPSU established. | SCPS -1 | target achieved in 2011 | 1 SCPS | 1 SCPS | target achieved in 2011 | 1 SCPS | 1 SCPS |  |
|  | SCPS and DCPU established and meetings carried out on schedule | 0 | 0 | DCPU- 0 | 26 DCPUs | 35 DCPUs | DCPS- 2 | DCPU – 6 | 0 | DCPU- 2 | DCPU- 26 | DCPU - 11 | 2 DCPU | DCPU- 26 | DCPU - 35 | DCPU- 2 |  |
|  | DLTF established | 0 | 0 | 0 | 6 DLTF | 3 DLTF | 2 DLTF | 0 | 0 | DLTF - 3 | DLTF - 6 | DLTF - 3 | DLTF - 3 | DLTF - 6 | DLTF - 3 | DLTF-2 |  |
|  | CWC, JJB, notified and appointed | 26 not operational | 0 | Notified CWC -2 | 26 CWC operational | 35 CWCs newly appointed | Appointed CWC -2 | CWCs - 26 | 35 CWCs newly appointed | CWC- 2 | target achieved in 2011 | CWCs - 35 | 2 CWC | target achieved in 2012 | CWCs - 35 | 2 CWC |  |
|  | CWC, JJB, notified and appointed | 0 | 0 | JJB-2 | JJB-6 | JJB-3 | JJB-2 | JJBs - 26 | JJB-3 | JJB-2 | JJB-6 | JJB-3 | 2 JJB | JJB-26 | JJB-3 | 2 JJB | Gujarat- All districts in the State have Juvenile Justice Boards. |
|  | SJPUs notified at district level, and CWPOs designated at police station level | 0 | 0 | 0 | 26 SJPU | 35 SJPU | 2 SJPU | 26 SJPUs | 35 SJPU | 2 SJPU | 22 SJPUs | 35 SJPU | 2 SJPUs | 26 SJPUs | 35 SJPUs | 2 SJPUs |  |
|  | Village Child Protection Committees formed and informed on child labour and out of school children. | 0 | 0 | 0 | 3,450 VCPC | 170 VCPC | 1,329 VCPC | 2,497 VCPC | VCPC formation pending registration of SCPS and DCPUs and awaiting notification from DWCD. | 294 VCPC | 3,450 VCPCs | 185 VCPCs | 1,100 VCPC | 3,450 VCPCs | 1,576 VCPCs | 1,329 VCPCs |  |
|  | Child Labour Task Force established at district level involving concerned Departments with clear delineations of roles, responsibilities and accountabilities of all Task Force members | 0 | 0 | 0 | 6 DLTF | 3 DLTF | 2 DLTF | 6 DLTF | 2 DLTF | 2 DLTF | 6 LTF | 3 DLTF | 2 DLTF functioning | 6 DLTF | 3 DLTF | 2 DLTF | Gujarat, Maharashtra and Rajasthan- DLTFs are established and functional. |
|  | Members of CP structures are trained to plan, implement, and monitor programs to address child labour and OOSC issues. | 0 | 280 | 0 | 6,900 members | 400 members | 84 members | 4,400 members | 200 members | 84 members | 6,000 members | 400 members | 84 members | 7,000 members | 3,733 members | 125 members |  |
| 1.2 Monitoring systems to track and target children at risk established and maintained | Database is maintained at village level with information on working children | 0 | 0 | 0 | 3,450 villages | 2,288 villages | 1,329 villages | 848 villages | 850 villages | 640 villages | 3,450 villages | 2,288 villages | 1,100 villages | 3,450 villages | 2,288 villages | 1,329 villages |  |
| 1.3Civil society alliance established and actively partnering government efforts for reducing child labour | NGOs working with District Administration for planning and review of child labour interventions | 0 | 0 | 0 | 21 NGOs | 17 NGOs | 10 NGOs | 21 NGOs | 15 NGOs | 3 NGOs | 21 NGOs | 17 NGOs | 10 NGOs | 15 NGOs | 17 NGOs | 10 NGOs | Gujarat- The number of NGOs was reduced from 21 to 15 in 2013 to concentrate on building capacities and strengthening systems at cluster, block and district level, with limited engagement around community mobilization. |
| 1.4 State and district action plans against child labour developed | State and district level child labour action plans developed. | 0 | 0 | 0 | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan | 1 State Action Plan |  |
|  | Monitoring and review of the implementation of child labour action plans at district level | 0 | 0 | 0 | 6 District Action Plans | 3 District Action Plans | 2 District Action Plans | 04 District Action Plans | 2 District Action Plans | 2 District Action Plans | 6 District Action Plans in place | 3 District Action Plans | 2 District Action Plans | 6 District Action Plans | 3 District Action Plans | 2 District Action Plans | Gujarat, Maharashtra and Rajasthan- District Action Plans are jointly formed with the State Governments to eradicate child labour in their respective States. |
| 1.5 Advocacy platforms strengthened for the amendment of the Child Labour Law to include prohibition of child labour in agriculture | District level consultation meetings held to provide recommendations for amendments to the CLPRA. Not Applicable for Gujarat and Rajasthan | Not Applicable | 0 | Not Applicable | Not Applicable | 4 meetings | Not Applicable | Not Applicable | 1 meeting (World Day against Child Labour observed in June 2011) | Not Applicable | Not Applicable | 3 meetings | Not Applicable | Not Applicable | 4 meetings | Not Applicable |  |
| Outcome 2 Quality education available for all children 6-14 years | Proportion of children of 06-14 years enrolled in schools | 85% | 92.10% | Dungarpur- 86.4% ( Girls) 90% (Boys) Udaipur-77.8% Girls91.1 Boys | 95% | 96% | 90% boys and girls are enrolled | figures to be established after the completion of the ongoing survey | figures to be established after the completion of the ongoing survey | figures to be established after the completion of the ongoing survey | 98.6% | 99.4% | 96% | 95.7% | 99.5% | 97% | Gujarat Source DISE 2012-13. Maharashtra: This is as per GoM figures based on DISE 2013-14 and SDP 2014-15 Rajasthan: Government data sources |
|  | # of teachers and head teachers aware of how to improve the quality of Education in their schools | 12,154 teachers/head teachers | 0 | 0 | 39,000 teachers/head teachers | 3,300 teachers/head teachers | 12,000 teachers/head teachers | 62,000 teachers/head teachers | 1,091 teachers/head teachers | 5,500 teachers/head teachers | 77,423 teachers/head teachers | 10,800 teachers/head teachers | 8,500 teachers/ head teachers | 63,000 teachers/head teachers | 10,800 teachers/head teachers | 12,000 teachers/head teachers | Maharashtra Elementary schools in all the project blocks of Yavatmal and 100% blocks of Wardha and Jalna have been oriented. To improve learning levels and other parameters, the need to orient all the teachers in the schools on quality education aspects was felt. As such, the original plan to orient one teacher in each school was revised and all the teachers were oriented. This led to a manifold increase to the number of teachers trained. Hence the actual numbers are higher than the target. |
| 2.1 All elementary schools in the project areas providing quality, child friendly education | # of teachers /head teachers/academic support team informed on the elements of child friendly schools | At least 10,000 teachers trained | nil | 0 | 35,000 Head teachers/ teachers/ academic resource teams | 3,300 Head teachers/ teachers/ academic resource teams | 200 academic resource members | 46,000 teachers/head teachers | 1,091 teachers/head teachers | 0 | 47,567 teachers/head teachers | 10,800 teachers/ head teachers | 8,700 Head teacher/ Teacher/ Academic Resource Team | 47,567 teachers/ head teachers | 10,800 teachers/head teachers | 200 | Maharashtra The rationale for increased coverage vis-à-vis the target is same as given above. Of these, 3475 teachers and head teachers have developed a CFS action plan. |
|  | Standards and guidelines of child friendly schools developed. Standards and guidelines for child friendly schools adopted by the state government for replication | 0 | 0 | 0 | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Guidelines available | Gujarat, Rajasthan and Maharashtra- The Guidelines were available in the three States in 2011 itself. |
|  | # of schools demonstrating elements of child friendly schools | 4397 schools | 0 | 0 | 10,930 schools | 3,300 schools | 4,000 schools | 10,930 Schools | 250 schools | 1,604 schools | 10,930 Schools | 3,413 schools | 2,500 schools | 9,889 schools | 3,475 schools | 4000 schools | Maharashtra The no. of schools covered includes all schools which have incorporated child friendly elements (as given in the Narrative Report). Gujarat- The total number of schools has been reduced by the Government. Please see end of project report for details. |
| 2.2 Special training programme for child labourers and other out-of school children upto 14 years in place for mainstreaming children into formal education | A STP package developed | 0 | 0 | 0 | Package developed | Package developed | Package developed | Package developed. | Package developed | Package developed | Package developed. | Package developed. | Package developed. | Package developed. | Package developed. | Package developed |  |
|  | Percentage of 06-14 years out of school children attend STPs | 0 | 0 | 0 | 81% | 50% | 17% | 64% | 0 (STPs were introduced by the state government only in 2012 in Maharashtra) | 44% | 75% | 28% | 70% | 70% | 100% | 70% | Rajasthan: Civil society intervention was successful in enrolling more children. In addition, tracking by child protection systems, and police check posts ensured that many children were unable to go to Gujarat hence enrolled in schools Maharashtra As per government data, there were 5,841 OOSC children in the 3 districts in 2013-14; all of these children are currently attending STP (100%). Gujarat- After OOSC identified, some communities migrated and some children also became over aged hence could not reach the target of earlier identified children |
| 2.3 SMCs and PRIs monitor and support attendance and infrastructure improvement of schools | Number of schools that have school development plans in coordination with SMCs | 0 | 0 | 0 | 9,863 schools | 3,300 schools | 4,000 schools | 5,800 schools | 4,797 schools | 1,327 schools | 10,930 schools | 4,718 schools | 4,000 schools | 9,851 schools | 4,718 schools | 4,000 schools | Gujarat: Number of schools has been reduced by government. Maharashtra: In partnership with Government, UNICEF has strengthened SMCs to monitor school attendance and infrastructure. 744 SMCs (of the 4718) have received handholding support to monitor school attendance & infrastructure improvement. |
|  | Number of SMCs monitoring the school attendance and infrastructure improvement | 0 | 0 | 0 | 9,863 SMCs | 3,300 SMCs | 3,200 SMCs | 5,800 SMCs | 0 SMCs | 1,500 SMCs | 10,930 SMCs | 2,765 SMCs | 2,500 SMCs | 9,851 SMCs | 4,718 SMCs | 4,000 SMCs | Rajasthan- The government has made it mandatory that the SMCs should develop School Development Plans (SDPs). As such, the environment was conducive to reach out to more SMCs and ensure that need based quality SDPs are developed and monitored by the SMCs. UNICEF, through this project could support 4,000 SMCs for this particular output. Maharashtra: In partnership with Government, UNICEF has strengthened SMCs to monitor school attendance and infrastructure. 744 SMCs (of the 4718) have received handholding support to monitor school attendance & infrastructure improvement. Gujarat- since the schools got merged; the number of SMCs got reduced. Secondly- KGBVs are also part of the schools but the SMCs of schools in that village also take responsibility of KGBVs so there are no separate SMCs for KGBVs. |
| 2.4 Models of School readiness programme established for 03-05 year old children (output revised and made more specific) | State specific standards/ norms and package school readiness programme available | 0 | 0 | 0 | Developed standards and package | Developed package | Specific standards/norms and package developed | State specific standards/norms and package developed | Specific standards/norms and package developed | Specific standards/norms and package developed | Developed standards and package | Developed standards and package | Developed standards and package | Developed standards and package | Developed standards and package | Developed standards and package |  |
|  | Percentage of AWCs implementing the school readiness programme | 33% | 0 | 0 | 87% | 80% | 50% | 79% | 0% | 0% (Process of implementing the school readiness program initiated) | 106% | 58% | 87% AWC | 106% | 120% | 87% AWC | Maharashtra covered more AWWs on the request of the Government. Gujarat: In Gujarat achievement was more than the targets due to two reasons- 1) Number of AWCs increased 2) the provisioning of quality ECE led to increased awareness among the community so more number of children got enrolled in AWC. |
|  | Percentage of 3-5 year old children enrolled in early learning programmes enter class I at an appropriate age | Not Applicable | Not Applicable | Not Applicable | Not Applicable | At least 90% | 80% | Not Applicable | figures to be established after the ongoing survey. | Not Applicable | Not Applicable | 90.30% | 60% | Not Applicable | 93.90% | 60% | Rajasthan: ECE still remains a challenge with ICDS (who have the mandate of ECE) due to low skills of the Anganwadi workers. The second challenge is that the Anganwadi workers are not yet trained on school readiness programmes. Maharashtra: Children enrolled (3-5 yrs): State - 91 %. Jalna - 98.7% ; Wardha - 85.4%; Yavatmal - 97.5% (source MPR Oct 2013) |
|  | Percentage of 3-5 year olds registered in AWCs and attending early learning programmes | 26% | Not Applicable | Not Applicable | 48% | Not Applicable | Not Applicable | To be established after the Monitoring Survey results in December 2012 | Not Applicable | Not Applicable | 19.7% | Not Applicable | Not Applicable | 19.7% | Not Applicable | Not Applicable | Gujarat-The progress as of 2012 is being repeated as the data from Government sources is awaited. Will be updated asap. |
| 2.5 Evidence based advocacy for effective targeting and utilization of resources for education of excluded children | Secondary data analyzed and shared with government and stakeholders for effective utilization of targeted resources. Not Applicable for Gujarat and Rajasthan | Not Applicable | 0 | 0 | Not Applicable | 1 report | Not Applicable | Not Applicable | Profiling of OOS children completed and data shared with government | Not Applicable | Not Applicable | 1 report on OOS children, the work that started in 2011 | Not Applicable | Not Applicable | 1 report on OOS children available | Not Applicable |  |
|  |  | Not Applicable | 0 | Not Applicable | Not Applicable | 2 policy briefs | Not Applicable | Not Applicable | 0 | Not Applicable | Not Applicable | 2 policy briefs | Not Applicable | Not Applicable | 2 policy briefs | Not Applicable |  |
| Outcome 3 Families and communities take collective action for protection and development of children | Children in the age group of 6-14 are attending schools increased from X% to Y% | 85% | 92.10% | Dungarpur- approx. 88% Udaipur- 84% | 95% | 96.00% | Dungarpur 90% Udaipur- 90% | To be established after the monitoring survey results in December 2012 | To be established after the monitoring survey results in December 2013 | To be established after the monitoring survey results in December 2014 | 94.60% | 96.30% | 90.10% | 94.60% | *** | 97.00% | Gujarat: Source DISE data Maharashtra: Data awaited from the Government. Rajasthan: Data from CSO and panchayat level child protection structures in both districts |
| 3.1 Families aware of harm caused by sending children to work and instead send their children to school | No. of villages reached with information on harms of child labour, importance of education and age of school enrolment | 0 | 0 | 0 | 3,450 villages | 2,288 villages | 2,500 villages | 848 villages | 850 villages | 640 villages | 3,450 villages | 2,288 villages | 2,500 villages | 3,450 villages | 2,288 villages | 2,500 villages |  |
|  | Community based structures (SMCs/PRIs/Gram Sabhas,/CPCs/, CBOs) promote enrolment of out of school children | 0 | 0 | 0 | 13,000 community based structures | 4,978 community based structures | 2,560 community based structures, | 2,200community based structures | 1450 community based structures | 2,000 community based structures | 10,350 community based structures | 4725 community based structures | 4,074 community based structures( VCPC , SMC and SHG) oriented on the | 10,350 community based structures | 6,359 community based structures | 6,831 community based structures( PLCPC, VLCPC , SMC and SHG) oriented on the | Rajasthan The strategy was slightly revised in line with the changing needs of the community. The project had proposed establishment of new community based structures and working with them. With time, it was felt prudent to include the community groups which were existent in the villages, in addition to forming new ones, and build their capacities so that a larger organized community force can be established. As such, the capacities of the existing community based structures along with the newly formed ones were developed. Gujarat- SMCs numbers reduced because of the merging of schools. These SMCs also cater to the functioning of KGBVs. |
| 3.2 Adolescents, especially girls and women networked and empowered to monitor and tackle child rights violations and protect children’s rights, especially the right to education and to protection | # of adolescent girls’ groups formed | 0 | 0 | 0 | 3,450 groups | 2,288 groups | 500 groups | 1,723 groups | 382 groups | 1,600 groups | 3,450 Groups | 1540 groups | 1,600 groups | 3,450 Groups | 2,247 groups | 1,825 groups | Rajasthan The existing adolescents of the civil society partners in project areas were also capacitated to have a larger critical mass of trained adolescents. This has been done with the objective of sustaining the results of the project in the long run. Maharashtra: In terms of the number of groups, close to 98% of the target has been achieved. This is because in smaller villages that have fewer number of adolescent girls, there is one AGG for 2 villages. However the number of girls reached exceeds the target. |
|  | No. of adolescent girls and women (including SHGs) trained on CP and importance of education SHG not applicable for Gujarat | 0 | 0 | 0 | 6,900 adolescent girls | 70,000 adolescent girls, 80,000 women | 5,000 members | 3,400 Adolescent Girls trained | 10,766 adolescent girls trained, 1,800 women informed | 44,250 members | 6,000 adolescent girls trained | 48,000 adolescent girls trained, 72770 women informed | 44,250 members | 7,000 adolescent girls trained | 71,055 adolescent girls trained, 85000 women informed | 54,250 members | Rajasthan The actuals were higher than the target. The reasons given for output 3.1 applies here as well. |
|  | Number of cases of child labour/ out of school children/ child marriages addressed successfully and documented. | 0 | 0 | 0 | 20 case studies | 50 case studies | 25 case studies | 10 case studies | 30 case studies | 150 case studies | 20 case studies | 75 case studies | 350 case studies | 35 case studies | 75 case studies | 225 case studies additional | Rajasthan: Many more case studies were documented due to the high awareness about child rights issues. |
| 3.3 Community leaders, including PRIs take active role in monitoring child rights issues and take action for preventing child labour | Community leaders including PRI members informed on child rights issues and need for prevention of child labour/out of school children | 0 | 0 | 0 | 17,500 community leaders | 10,556 community leaders | 11,000 community leaders | 4,400 community leaders | 4,200 community leaders | 10,844 community leaders | 16,000 community leaders | 11375 community leaders | 11,000 community leaders informed | 40,000 community leaders | 14,775 community leaders | 20,000 Community leaders |  |
|  | Gram Sabha meetings and other forums to discuss issues related to child labour and education | 0 | 0 | 0 | 240 meetings | 2,413 meetings | 3,000 meetings | 100 meetings | 1,700 meetings | 3,000 meetings | 250 meetings | 3,951 meetings | 3,000 meetings | 250 meetings | 5,671 meetings | 3,000 meetings |  |
| 3.4 Advocacy on child labour free farming with farmers and through media | Farmers meetings Not Applicable for Rajasthan | 0 | 0 | Not Applicable | 12 | 1,508 farmers meetings | Not Applicable | 0 | 0 (preparatory work for meetings inititated in 600 Gram Panchayats) | Not Applicable | 10 meetings | 1,600 meetings | Not Applicable | 42 meetings | 1,600 meetings | Not Applicable |  |
|  | Media reports on child labour Not Applicable for Gujarat | Not Applicable | Not Available | 2-3 per annum | Not Applicable | 24 reports | 500 reports per annum | Not Applicable | 9 reports | 500 reports | Not Applicable | 95 reports | 690 reports | Not Applicable | 100 reports | 610 reports |  |
| Outcome 4 Enhanced access to social protection schemes for vulnerable families (out of school and children without parental care) | X% of vulnerable families take benefit from at least one social protection scheme in the project period | 0 | Not Available | 47% in Dungarpur and 41.7% in Udaipur | 90% | 10% | 57% in Dungarpur and 51.7% in Udaipur | Figures to be established after the ongoing survey. | Figures to be established after the ongoing survey. | Figures to be established after the ongoing survey. | 91.00% | 68.00% | 89.8% Dungarpur and 93.9 Udaipur | 74.00% | 83.00% | 96% Dungarpur and 98% Udaipur | Maharashtra: The figures are based on information sourced from district administration. The percentage of vulnerable families including OOSC was linked to social protection schemes. Gujarat: using the first two years of the project, 415,000 vulnerable families had been identified and linked with social protection schemes through the government’s ’Gareeb Kalyan Melas’. Later the strategy was further refined to address families with specific vulnerabilities such as those with OOSC, child labourers and children without appropriate parental care. On the basis of this definition, the data of vulnerable families was then ”filtered” on the basis of this revised definition. As a result of this re-strategizing, a total of 21,651 families (74 per cent) have been linked to at least one social protection scheme out of the 29,267 families identified. The families which were left out for linkages did not have necessary documents to stand eligible for social protection schemes. |
| 4.1 Social protection schemes mapped, reviewed and recommended [11] for revisions to explicitly target vulnerable families, including those having children engaged in child labour and migrants | Relevant social protection schemes mapped. | 0 | 0 | 0 | 600 schemes | 90 schemes | 50 schemes | A compendium of all SPS disseminated in four districts covering 7,500 villages. | 0 (assessment initiated for 90 social protection schemes but not yet complete) | 25 schemes | 600 Schemes | 90 schemes completed. | 200 schemes mapped and listed | 600 schemes | 90 schemes completed. | 200 schemes mapped and listed | Rajasthan: The state government requested UNICEF to provide support in the State Girl Child Policy. One of the objectives of the policy is to be able to provide a conducive environment for the children especially girls. As this project works closely to provide a protective environment to children, especially girls, through this project UNICEF mapped schemes to support in this work. As such, the actuals are higher than the target. |
|  | At least one social protection scheme reviewed and recommendations submitted to the government for revisions. Not Applicable for Gujarat | Not Applicable | 0 | 0 | Not Applicable | 1 (Bal Sangopan Yojana) | 1 (Palanhar scheme) | Not Applicable | 1(Bal Sangopan Yojana) scheme assessed and reviewed. Amendments in the process of finalisation. | 1 (Palanhar scheme) | Not Applicable | 1(Bal Sangopan Yojana) scheme assessed and reviewed and amendments submitted to government. | 1 (Palanhar scheme; 80 % of the recommendations incorporated) | Not Applicable | 1(Bal Sangopan Yojana) scheme assessed and reviewed and amendments submitted to government. | 1 (Palanhar scheme; 80 % of the recommendations incorporated) |  |
| 4.2 Increased awareness among families on social protection schemes | Community based structures (Gram Sabhas/PRIs/CPCs/CBOs) disseminate information about the social protection schemes at least twice each year | 0 | 0 | 0 | 3,450 community based structures | 1,695 community based structures | 2,568 community based structures | 3,048 community based structures | 600 community based structures | 2,000 community based structures | 3,450 community based structures | 4,725 community based structures | 4,074 community based structures( VCPC , SMC and SHG) | 3,450 community based structures | 6,359 community based structures | 6,831 community based structures( PLCPC, VLCPC , SMC and SHG) oriented on the | Maharashtra: Information dissemination during panchayat planning process, community based meetings that were held around village micro planning exercise, formation of CPCs and special Gram Sabhas lead to coverage of 6395 community based structures. |
|  | % of villages where families were reached with information on social protection schemes. | 0 | 0 | 0 | 100% | 100% | 70% | 25% | 40% | 42% | 100% | 100% | 82% | 100% | 100% | 100% |  |
| 4.3 Systems set up to monitor and link vulnerable families to social protection schemes [12] | Database established and maintained on vulnerable families and social protection schemes | 0 | 0 | 0 | 3,450 village databases | 1 district level data base | 1,329 village level database | 848 village databases | 1 district level data base is in the process of development | 640 village level databases | 3,450 village databases | 1 district level data base developed. | 1,100 village level databases | 3,450 village databases | 1 district level data base developed. | 1,329 village level | Maharashtra: The database is operational and being used by District Administration for online monitoring |
|  | Vulnerable families who have been registered in social protection schemes increases from X% to Y% | 0 | Not available | 80% in Dungarpur and 75% in Udaipur | 100% | 10% | 90% in Dungarpur and 85% in Udaipur | None. | 187 vulnerable families (% will be reported in 2013) | Figures to be established after the ongoing survey. | 67.24% vulnerable families linked to social protection schemes. | 840 families from project area (% will be provided in 2013) | 89.8% Dungarpur and 93.9 Udaipur | 74% vulnerable families linked to social protection schemes. | 83% (3,106 families) | 96% Dungarpur and 98% Udaipur | Rajasthan: The relaxation in the eligibility and provisions under the scheme (as a result of advocacy by UNICEF and partners) led to more than planned vulnerable families availing social protection schemes. Maharashtra Increase in percentage of families registered in social protection schemes to be taken from endline. Gujarat-The strategy of identifying vulnerable families was refined to include families of OOSC, child labourers and children without appropriate parental care. Hence, the data of vulnerable families was ”filtered” on the basis of this revised definition. |

### ANNEXURE 4: Project Budget

Table 1: Project’s Final Financial Report (2009-2014)

| Expense head | Provided budget | Actual expenditure | Diff (Provided - Actual) | % of budget | % of actual expenditure |
| --- | --- | --- | --- | --- | --- |
| IKEA Foundation transfer in EUR | 1,34,46,577 |  |  |  |  |
| Outcome 1 | 8,93,518 | 12,33,123 | -3,39,605 | -28% | 9% |
| Outcome 2 | 36,64,387 | 42,82,991 | -6,18,604 | -14% | 30% |
| Outcome 3 | 29,56,960 | 29,73,648 | -16,688 | -1% | 21% |
| Outcome 4 | 7,40,478 | 9,30,719 | -1,90,241 | -20% | 6% |
| Partnership with NGOs/ implementing agencies in the state, including their field monitoring costs | 14,42,506 | 18,45,072 | -4,02,566 | -22% | 13% |
| Project Implementing Staff- Child Protection specialist, district level coordinators | 9,95,577 | 12,17,505 | -2,21,928 | -18% | 8% |
| Documentation | 40,000 | 54,450 | -14,450 | -27% | 0% |
| Costs for communication and advocacy at field level, including production of printing and electronic materials and dissemination meetings | 1,22,556 | 69,356 | 53,200 | 77% | 0% |
| Midline and endline evaluation surveys for Gujarat, Maharashtra and Rajasthan through a centrally managed third party evaluation | 3,44,688 | 2,04,194 | 1,40,494 | 69% | 1% |
| Technical support from Delhi (Child Protection, Social Mobilisation, Partnership, Advocacy and Communication and Monitoring and Evaluation)* | 1,35,0423 | 14,07,263 | -56,840 | -4% | 10% |
| Planning phase baseline survey | 1,34,359 | 1,34,359 | 0 | 0% | 1% |
| Sub-total | 1,26,85,452 | 1,43,52,680 | -16,67,228 | -12% |  |
| Indirect cost-6% | 7,61,127.12 |  |  |  |  |
| Total | 1,34,46,579.12 | 1,43,52,680 |  |  |  |
| Provided Budget-Actual Expenditure | -9,06,100.88 |  |  |  |  |
| Variance | -7% |  |  |  |  |
| Sub-total | 1,26,85,452 | 1,43,52,680 | -16,67,228 | -12% |  |
| Indirect cost-6% | 7,61,127.12 |  |  |  |  |
| Total | 1,34,46,579.12 | 1,43,52,680 |  |  |  |
| Provided Budget-Actual Expenditure | -9,06,100.88 |  |  |  |  |
| Variance | -7% |  |  |  |  |

Table 2: Maharashtra Financial Report for the period (1.07.2009-28.02.2014)

| Project reference: 2009.015 (SC090454) |  |
| --- | --- |
| Currency: EUR | Year 1 |
| Period: | 2009-2014 |
| Opening balance |  |
| Income: |  |
| - IKEA Foundation transfer in EUR |  |
| - Other sources |  |
| Total income |  |
| Outcome 1: Child protection structures in place addressing child labour issues | 327,900 |
| Outcome 2: Quality education available for all children 6-14 years | 942,686 |
| Outcome 3: Families and communities take collective action for protection and development of children | 1,364,461 |
| Outcome 4: Enhanced access to social protection schemes for vulnerable families (out of school and children without parental care) | 109,190 |
| Partnership with NGOs/implementing agencies in the state, including their field monitoring costs | 1,096,968 |
| Project Implementing Staff- Child Protection specialist, district level coordinators | 485,983 |
| 7. Documentation | 20,000 |
| Sub-total | 4,347,188 |
| Exchange rate: EUR/local currency | 1.36037=1 USD |

Table 3: Budget and Financing Plan - Maharashtra

| BUDGET AND FINANCING PLAN |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Maharashtra |  |  |  |  |  |  |  |  |  |
| Currency: EUR | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |  |  |  |
|  | 2009 | 2010 | 2011 | 2012 | 2013 | IF |  | other | Grand Total |
|  |  |  |  |  |  | 2009-2013 |  | 2009-2013 |  |
| Opening balance |  | - | - | - |  | - |  | - |  |
| Secured income: |  |  |  |  |  | - |  | - |  |
| IKEA Foundation | 472 | 581,281 | 1,095,192 | 1,484,919 | 1,335,321 | 4,497,185 |  |  | 4,497,185 |
| - Other sources | - | - | - |  | 110,835 |  |  | 110,835 | 110,835 |
|  |  |  |  |  |  |  |  |  | - |
| Total income | 472 | 581,281 | 1,095,192 | 1,484,919 | 1,446,156 | 4,497,185 |  | 110,835 | 4,608,019 |
|  |  |  |  |  |  |  |  | - |  |
|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |  |  | - |
|  | 2009 | 2010 | 2011 | 2012 | 2013 |  | 2014 |  |  |
| Expenditure | IF | IF | IF | IF | IF |  | IF | Grand Total |  |
| Out come 1 | 445 | 70,076 | 86,147 | 106,472 | 35,052 |  | 29,708 | 327,900 |  |
| Out come 2 |  | 91,262 | 152,784 | 345,273 | 283,293 |  | 70,075 | 942,686 |  |
| Out come 3 |  | 184,406 | 89,147 | 603,995 | 482,135 |  | 4,778 | 1,364,461 |  |
| Out come 4 |  | - | 45,470 | 15,971 | 47,749 |  | - | 109,190 |  |
| Partnership with NGOs |  | 179,677 | 558,440 | 103,817 | 255,034 |  | - | 1,096,968 |  |
| Project implementing staff |  | 22,958 | 101,212 | 205,339 | 156,474 |  | - | 485,983 |  |
| Documentation |  | - | - | 20,000 | - |  | - | 20,000 |  |
| Sub-Total | 445 | 548,379 | 1,033,200 | 1,400,867 | 1,259,737 |  | 104,561 | 4,347,188 |  |
| Recovery Costs @6% | 27 | 32,903 | 61,992 | 84,052 | 75,584 |  | 6,274 | 254,558 |  |
| Total costs | 472 | 581,281 | 1,095,192 | 1,484,919 | 1,335,321 |  | 110,835 | 4,497,185 |  |
| Closing balance |  |  |  |  |  |  |  |  |  |
| Exchange rate EUR/local currency: | 1 Euro= 1.3149 USD |  |  | for 2012 |  |  |  |  |  |
| Exchange rate EUR/local currency: | 1 Euro= 1.36037 USD |  |  | for 2013 and 2014 |  |  |  |  |  |

### ANNEXURE 5: Project from Human Rights Lens

The project seeks to build a protective environment for children in which their rights to quality education, participation and to protection against exploitation and abuse are fulfilled. In this way, the project supports the following Articles of the CRC.

#### Article 4 (Protection of rights)

Governments have a responsibility to take all available measures to make sure children’s rights are respected, protected and fulfilled. When countries ratify the Convention, they agree to review their laws relating to children. This involves assessing their social services, legal, health and educational systems, as well as levels of funding for these services. Governments are then obliged to take all necessary steps to ensure that the minimum standards set by the Convention in these areas are being met. They must help families protect children’s rights and create an environment where they can grow and reach their potential. In some instances, this may involve changing existing laws or creating new ones. Such legislative changes are not imposed, but come about through the same process by which any law is created or reformed within a country.

#### Articles related to Component 1

# Article 32 (Child labour)

The government should protect children from work that is dangerous or might harm their health or their education. While the Convention protects children from harmful and exploitative work, there is nothing in it that prohibits parents from expecting their children to help out at home in ways that are unsafe and inappropriate to their age. If children help out in a family farm or business, the tasks they do be safe and suited to their level of development and comply with national labour laws. Children's work should not jeopardise any of their other rights, including the right to education, or the right to relaxation and play.

# Article 35 (Abduction, sale and trafficking)

The government should take all measures possible to make sure that children are not abducted, sold or trafficked.

#### Articles related to Component 2

# Article 28 (Right to education)

All children have the right to a primary education, which should be free. For children to benefit from education, schools must be run in an orderly way – without the use of violence. Any form of school discipline should take into account the child's human dignity. Therefore, governments must ensure that school administrators review their discipline policies and eliminate any discipline practices involving physical or mental violence, abuse or neglect. The Convention places a high value on education. Young people should be encouraged to reach the highest level of education of which they are capable.

# Article 29 (Goals of education)

Children’s education should develop each child’s personality, talents and abilities to the fullest. It should encourage children to respect human rights and their own and other cultures. It should also help them learn to live peacefully, protect the environment and respect other people. Children have a particular responsibility to respect the rights of their parents, and education should aim to develop respect in them for the values and culture of their parents.

#### Articles related to Component 3

# Article 42 (Knowledge of rights)

Governments should make the Convention known to adults and children. Adults should help children learn about their rights, too.

#### Articles related to Component 4

# Article 26 (Social security)

Children – either through their guardians or directly – have the right to help from the government if they are poor or in need.

### ANNEXURE 6: Project Results Matrix

| Results/Outcomes/Outputs/Indicators | Targets | Progress as on 31.12.2012 | Current Status (as of March 2014) | Remarks |
| --- | --- | --- | --- | --- |
| Strategic Result In cotton and cotton seed production areas children in the age group of 6 to 14 years are not working and are in school |  |  |  |  |
| Children in age group 6-14 years who are out of school are reduced from X% to Y% | 4% | 3.7% | 0.5% | This is as per Government of Maharashtra figures based on DISE 2013-14 and SDP 2014-15 |
| Outcome 1 Child protection structures in place addressing child labour issues |  |  |  |  |
| Child protection structures are established and operational at the state and district levels. | All structures established and operational | All structures established and operational | All structures established and operational |  |
| State and District level Task Force (DLTF) on Child Labour established, Plans developed and implementation monitored | 3 DLTF | 3 DLTF | 3 DLTF | Target achieved in 2011 |
| 1.1 Child Protection structures under labour and Integrated Child Protection Scheme/Juvenile Justice in place, functioning at state, district, and panchayat level |  |  |  |  |
| Notifications/Resolutions are issued by the State Governments for establishment of child protection structures at state and district level | 7 Notif/Resol | 7 Notif/Resol | 18 Notif/Resol: SOPs for CWCs; SOPs for missing children to be used with Track Child; Bal Sangopan Yojana; Adoption of State Child Policy; ICPS and DWCD coordination | Target achieved in 2011 |
| SCPS and DCPU established and meetings carried out on schedule | 1 SCPS | 1 SCPS | 1 SCPS |  |
| SCPS and DCPU established and meetings carried out on schedule | 35 DCPUs | 11 DCPUs | 35 DCPUs (1 per district) |  |
| DLTF established | 3 DLTF | 3 DLTF | 3 DLTF | DLTFs are established and functional |
| CWC, JJB, notified and appointed | 35 CWCs newly appointed | 35 CWCs | 35 CWCs |  |
| CWC, JJB, notified and appointed | 3 JJBs | 3 JJBs | 3 JJBs | Target achieved in 2011 |
| SJPUs notified at district level, and CWPOs designated at police station level | 35 SJPU | 35 SJPU | 35 SJPU | Target achieved in 2011 |
| Village Child Protection Committees formed and informed on child labour and out of school children. | 170 VCPC | 185 VCPCs | 1,576 VCPCs (please see comment) |  |
| Child Labour Task Force established at district level involving concerned Departments with clear delineation of roles, responsibility and accountability of all Task Force members defined | 3 DLTF | 3 DLTF | 3 DLTF | DLTFs are established and functional |
| Members of CP structures are trained to plan, implement, and monitor programs to address child labour and out of school children issues. | 400 members | 400 members | 3,733 members |  |
| 1.2 Monitoring systems to track and target children at risk established and maintained |  |  |  |  |
| Database is maintained at village level with information on working children | 2,288 villages | 2,288 villages | 2,288 villages |  |
| Number of children at risk tracked through village-level databases, desegregated by social group, gender, OOS, and child labour |  |  |  |  |
| 1.3 Civil society alliance established and actively partnering government efforts for reducing child labour |  |  |  |  |
| NGOs working with District Administration for planning and review of child labour interventions. | 17 NGOs | 17 NGOs | 17 NGOs |  |
| 1.4 State and district action plans against child labour developed |  |  |  |  |
| State and district level child labour action plans developed. | 1 State Action Plan, | 1 State Action Plan, | 1 State Action Plan, | Target achieved in 2011. District Action Plans are jointly formed with the State Governments to eradicate child labour in their respective States. |
| Monitoring and review of the implementation of child labour action plans at district level | 3 District Action Plans | 3 District Action Plans | 3 District Action Plans |  |
| 1.5 Advocacy platforms strengthened for the amendment of the Child Labour Law to include prohibition of child labour in agriculture |  |  |  |  |
| District level consultation meetings held to provide recommendations for amendments to the CLPRA. | 4 meetings | 3 meetings | 4 meetings |  |
| Outcome 2 Quality education available for all children 6-14 years |  |  |  |  |
| Proportion of children of 06-14 years enrolled in schools | 96% | 99.4% | 99.5% | This is as per GoM figures based on DISE 2013-14 and SDP 2014-15 |
| Number of teachers and head teachers aware of how to improve the quality of Education in their schools | 3,300 teachers/head teachers | 10,800 teachers/head teachers | 10,800 teachers/head teachers | Elementary schools in all the project blocks of Yavatmal and 100% blocks of Wardha and Jalna have been oriented. To improve learning levels and other parameters, the need to orient all the teachers in the schools on quality education aspects was felt. As such, the original plan to orient one teacher in each school was revised and all the teachers were oriented. This led to a manifold increase to the number of teachers trained. Hence the actual numbers are higher than the target. |
| 2.1 All elementary schools in the project areas providing quality, child friendly education, |  |  |  |  |
| Number of teachers /head teachers/academic support team informed on the elements of child friendly schools | 3,300 Head teachers/ teachers/ academic resource teams | 10,800 teachers/head teachers | 10,800 teachers/head teachers | The rationale for increased coverage vis-à-vis the target is same as given above. Of these, 3,475 teachers and head teachers have developed a CFS action plan. |
| Standards and guidelines of child friendly schools developed Standards and guidelines for child friendly schools adopted by the state government for replication | Guidelines available | Guidelines available | Guidelines available | Target achieved in 2011. |
| # of schools demonstrating elements of child friendly schools | 3,300 schools | 3,413 schools | 3,475 schools | The number of schools covered includes all schools which have incorporated child friendly elements (as given in the Narrative Report). |
| 2.2 Special training programme for child labourers and other out-of school children up to 14 years in place for mainstreaming children into formal education |  |  |  |  |
| A STP package developed | Package developed | Package developed | Package developed | Target achieved in 2011 |
| Percentage of 06-14 years out of school children attend STPs. | 50% | 28% | 100% | As per government data, there were 5,841 OOSC children in the 3 districts in 2013-14; all of these children are currently receiving STP (100%). |
| 2.3 SMCs and PRIs monitor and support attendance and infrastructure improvement of schools |  |  |  |  |
| Number of schools that have school development plans in coordination with SMCs | 3,300 schools | 4,718 schools | 4,718 schools | In partnership with Government, UNICEF has strengthened SMCs to monitor school attendance and infrastructure. 744 SMCs (of the 4718) have received handholding support to monitor school attendance & infrastructure improvement. |
| Number of SMCs monitoring the school attendance and infrastructure improvement | 3,300 SMCs | 2,765 SMCs | 4718 SMCs | In partnership with Government, UNICEF has strengthened SMCs to monitor school attendance and infrastructure. 744 SMCs (of the 4718) have received handholding support to monitor school attendance & infrastructure improvement. |
| 2.4 Models of School readiness programme established for 03-05 years children (output revised and made more specific) |  |  |  |  |
| State specific standards/norms and package school readiness programme available | Developed package | Developed standards and package | Developed standards and package | Target achieved in 2011 |
| Percentage of AWCs implementing the school readiness programme | 80% | 58% | 120% | Maharashtra covered more AWWs on the request of the Government. |
| Percentage of 3-5 year old children enrolled in early learning programmes enter class I at an appropriate age | At least 90% | 90.30% | 93.90% | Children enrolled (3-5 yrs): State - 91 %. Jalna - 98.7% ; Wardha - 85.4%; Yavatmal - 97.5% (source MPR Oct 2013) |
| 2.5 Evidence based advocacy for effective targeting and utilization of resources for education of excluded children |  |  |  |  |
| Secondary data analyzed and shared with government and stakeholders for effective utilization of targeted resources. | 1 report | 1 report on OOS children, the work that started in 2011 | 1 report on OOS children available |  |
|  | 2 policy briefs | 2 policy briefs | 2 policy briefs |  |
| Number of Kasturba Gandhi Balika Vidyalaya (KGBV) established for girls from SC, ST and minorities in Maharashtra |  |  |  |  |
| What has been the budget allocation and utilisation for education of excluded children? |  |  |  |  |
| Outcome 3 Families and communities take collective action for protection and development of children |  |  |  |  |
| Children in the age group of 6-14 years are attending schools increased from X% to Y% | 96.00% | 96.30% | Data awaited from the government |  |
| 3.1 Families aware of harm caused by sending children to work and send their children to school |  |  |  |  |
| No. of villages reached with information on harmful effects of child labour, importance of education and age of school enrolment | 2,288 villages | 2,288 villages | 2,288 villages |  |
| Community based structures (SMCs/PRIs/Gram Sabhas,/CPCs/, CBOs) promote enrolment of out of school children | 4,978 community based structures | 4,725 community based structures | 6,359 community based structures |  |
| Number of Adolescent Animators to mobilise CBOs |  |  | 2,000 Deepshikha Prerikas |  |
| How many Out of School Children are enrolled in school due to efforts of CBOs |  |  | 4,944 |  |
| 3.2 Adolescents, especially girls and women networked and empowered to monitor and tackle child rights violations and protect children’s rights, especially the right to education and to protection |  |  |  |  |
| # of adolescent girls’ groups formed | 2,288 groups | 1,540 groups | 2,247 groups | In terms of the number of groups, close to 98% of the target has been achieved. This is because in smaller villages that have less number of adolescent girls, there is one AGG for 2 villages. However the number of girls reached exceeds the target. |
| No of adolescent girls and women (including SHGs) trained on CP and importance of education SHG not applicable for Gujarat. | 70,000 adolescent girls, 80,000 women | 48,000 adolescent girls trained, 72,770 WSHG members informed | 71,055 adolescent girls trained, 85,000 WSHG members informed |  |
| Number of cases of child labour/ out of school children/child marriages addressed successfully and documented. | 50 case studies | 75 case studies | 75 case studies |  |
| Number of cases of child labour/ out of school children/ child marriages that have been addressed successfully. Please note, Annual Report states "In Yavatmal and Jalna districts of Maharashtra, 47 early marriages stopped and 693 working children rescued and mainstreamed into schools" |  |  | 1,919 CL, 4,944 CM, 168 OOSC |  |
| 3.3 Community leaders, including PRIs take active role in monitoring child rights issues and take action for preventing child labour |  |  |  |  |
| Community leaders including PRI members informed on child rights issues and need for prevention of child labour/out of school children. | 10,556 community leaders | 11,375 community leaders | 14, 775 community leaders |  |
| Gram Sabha meetings and other forums to discuss issues related to child labour and education | 2,413 meetings | 3,951 meetings | 5,671 meetings |  |
| 3.4 Advocacy on child labour free farming with farmers and through media |  |  |  |  |
| Farmers meetings | 1,508 farmers meetings | 1,600 meetings | 1,600 meetings |  |
| Media reports on child labour | 24 reports | 95 reports | 100 reports |  |
| Outcome 4 Enhanced access to social protection schemes for vulnerable families (out of school and children without parental care) |  |  |  |  |
| X% of vulnerable families take benefit from at least one social protection scheme in the project period (provide details) | 10% | 68.00% | 83% | The figures are based on information sourced from district administration. The percentage is of vulnerable families, including OOSC, linked to social protection schemes. |
| 4.1 Social protection schemes mapped, reviewed and recommended for revisions to explicitly target vulnerable families, including those having children engaged in child labour and migrants |  |  |  |  |
| Relevant social protection schemes mapped. | 90 schemes | 90 schemes completed. | 90 schemes completed. |  |
| At least one social protection scheme reviewed and recommendations submitted to the government for revisions. Not Applicable for Gujarat | 1 (Bal Sangopan Yojana) | 1 (Bal Sangopan Yojana) scheme assessed and reviewed and amendments submitted to government. | 1 (Bal Sangopan Yojana) scheme assessed and reviewed and amendments submitted to government. |  |
| 4.2 Increased awareness among families on social protection schemes |  |  |  |  |
| Community based structures (Gram Sabhas/PRIs/CPCs/CBOs) disseminate information about the social protection schemes at least twice each year | 1,695 community based structures | 4,725 community based structures | 6,359 community based structures | Information dissemination during panchayat planning process, community based meetings that were held around village micro planning exercise, formation of CPCs and special Gram Sabhas lead to coverage of 6395 community based structures. |
| % of villages where families were reached with information on social protection schemes. | 100% | 100% | 100% |  |
| 4.3 Systems set up to monitor and link vulnerable families to social protection schemes |  |  |  |  |
| Database established and maintained on vulnerable families and social protection schemes | 1 district level data base | 1 district level data base developed. | 1 district level data base developed. | The database is operational and being used by District Administration for online monitoring. |
| Number of databases on vulnerable families and social protection schemes operational |  |  | 1 district level data base developed and operational. |  |
| Vulnerable families who have been registered in social protection schemes increases from X% to Y% | 10% | 840 families from project area (% will be provided in 2013) | 83% (3,106 families) | Increase in percentage of families registered in social protection schemes to be taken from endline. |
| Indicators in red are as per the revised proposal submitted to IKEA Foundation in July 2012. |  |  |  |  |

### ANNEXURE 7: List of Secondary Documents

| Type of document | Hard copy/soft copy | Name | Language | Author/Institution | Dated |
| --- | --- | --- | --- | --- | --- |
| Child protection structures in place addressing child labour issues |  |  |  |  |  |
| Policy | Hard copy | Child Policy 2013 - An informative effort at structured, comprehensive and planned development for child development | Marathi | Maharashtra State Commission for Protection of Child Rights |  |
| Training Manual | Hard copy | Training workshop for SJPU (Under the Juvenile Justice (Care and protection of children) Act, 2000 | Marathi | Joint purview of DWCD, GoM and UNICEF, Mumbai | 15 Dec. 2012 |
| Training Manual | Hard copy | Training workshop for Protection Officers on "Protection of Women from Domestic Violence Act 2005" | Marathi | DWCDO, Yavatmal | 17 Mar. 2013 |
| Booklet | Hard copy | Child Rights and Child Protection Reference Reading | Marathi | Vikasganga Samajsevi Sanstha, Ghatanji, Yavatmal |  |
| Booklet | Hard copy | These are your rights! | Marathi | Save the Children | 2011 |
| Handbook | Hard copy | Working with adolescent girls….Focusing on issues of gender relations, child protection and education….Handbook for prerikas…..that has been prepared (For prerikas working in project on Child protection and education under UNICEF in the districts of Yavatmal, Wardha and Jalna in Maharashtra) | Marathi | UNICEF |  |
| Handbook | Hard copy | Working with adolescent girls - Addressing issues related to gender, child protection and education - Handbook for Prerikas (as part of UNICEF IKEA partnership for district Wardha, Yavatmal & Jalna, Maharashtra) | Bilingual (English and Marathi) | UNICEF |  |
| Pledge | Hard copy | Sample pledge document to be signed/sworn by community members at the village level (Child marriage is marriage of girls under 18 years of age and boys under 21 years of age and that they will not allow child marriage) | Marathi |  |  |
| Letter | Hard copy | Congratulatory letter to be given to elected Chairman/Vice-chairman/member of VCPC signed by Block Coordinator | Marathi |  | 2012-13 |
| Booklet | Hard copy | VCPC | Marathi |  |  |
| Government Resolution | Hard copy | Related to establishing VCPCs and providing their information to the DWCDO | Marathi | Krishna Rathod, DWCDO, Yavatmal | 6 Feb. 2013 |
| Database | Hard copy | Database on working children | Marathi | Vikasganga Samajsevi Sanstha, Ghatanji, Child Rights Protection Project |  |
| Guide | Hard copy | Meena in the Community (For volunteers, Gram Pradhan, Panchayat members, SHG members, NGO, NCC, NSS, Nehru Yuva Kendra) | Marathi | UNICEF | 2008 |
| Guide | Hard copy | Gram Panchayat Microplanning: Ready and illustrated guide to community led Gram Panchayat Planning process | Marathi | YASHADA and UNICEF | April 2013 |
| Information booklet | Hard copy | Gram Panchayat Comprehensive Information Compendium: Gram Panchayat Booklet (In which GPP data is entered) | Marathi | Government of Maharashtra |  |
| Information booklet | Hard copy | Gram Panchayat Comprehensive Information Compendium: Family Booklet (In which GPP data is entered) | Marathi | Government of Maharashtra |  |
| Information booklet | Hard copy | Gram Panchayat Comprehensive Information Compendium: Mehsuli Village Booklet (In which GPP data is entered) | Marathi | Government of Maharashtra |  |
| Letter and enclosure | Hard copy | Proposed amendments to the Juvenile Justice (Care and Protection of Children) Act 2000 | English | Nilima Mehta (Mumbai Working Group on Juvenile Justice) | 27 Feb. 2012 |
| Case study booklet | Hard copy | Case studies of child protection structures addressing child marriage and child labour | English | UNICEF |  |
| Final Report | Hard copy | Promoting Protection and Education Rights of Children in Cotton Areas of Maharashtra (Pre-final draft) | English | UNICEF | Sept. 2013 |
| Sample training schedule | Hard copy | Training details for ICPS in Maharashtra (Rough first draft) | English | UNICEF |  |
| PPT Slides Handout | Hard copy | Promoting Protection and Education Rights of Children in Cotton Areas of Maharashtra | English | UNICEF | June 2013 |
| Guidelines | Hard copy | Assessment and Implementing Guidelines for Bal Sangopan Yojana (BSY) - Submitted to DWCD, GoM, 2012 | English | Expert Group on Bal Sangopan Yojana, UNICEF |  |
| Booklet of GRs | Hard copy | Elimination of Child Labour: Government Resolutions issued by various departments under the State Action Plan | Marathi | YASHADA, Department of Labour (GoM) |  |
| Booklet | Hard copy | Juvenile Justice (Care and Protection of Children) Act, 2000, included in Amendment 2006 | Marathi | Balprafulta (A Child Rights Advocacy Initiative) |  |
| Booklet | Hard copy | Child Protection: A Compilation | Marathi | Balprafulta (A Child Rights Advocacy Initiative) |  |
| CD | Hard copy | Training on Child Protection: Comprehensive Guide | Marathi | UNICEF |  |
| District Action Plan | Hard copy | District Action Plan, 2014 | Marathi | DCPU, Yavatmal |  |
| Handbook | Hard copy | Child Protection Resources Handbook | Marathi | DCPU, Yavatmal and MSCPS |  |
| Handbook | Hard copy | Preventive Strategies for Child Protection - Practical Guidance to Form and Strengthen Child Protection Committees | English | UNICEF |  |
| Contents checklist | Hard copy | Contents of Information Kit for JJB (This kit exists and UNICEF has shown it to State Coordinator) | English | UNICEF |  |
| Contents checklist | Hard copy | Contents of Information Kit for CWC (This kit exists and UNICEF has shown it to State Coordinator) | English | UNICEF |  |
| SOP | Hard copy | SOP for CWC | Marathi | DWCD and UNICEF |  |
| Newsletter | Hard copy | Ujjwal (For CWC members); Vol 14 | Marathi | Balprafulta, UNICEF, Resource Cell for Juvenile Justice, DWCD | Dec. 2010 |
| Recommendations | Hard copy | Recommendations to strengthen Child Protection Instruments and Structures: Submitted to DWCD, GoM, 2012 | English | Resource Group on Child Protection and ICPS, UNICEF |  |
| Guidelines | Soft copy | Maharashtra Guidelines for Child Protection Committees (CPCs) (Draft) | English | DWCD, MSCPS, Research & Documentation Centre, YASHADA, Save the Children and UNICEF |  |
| Project structure map | Soft copy | Maharashtra IKEA project structure | English | UNICEF |  |
| NGO and consultant list | Soft copy | IKEA Maharashtra NGOs and consultants list | English | UNICEF |  |
| Details of training | Soft copy | Details of training in the year 2013 | English | UNICEF |  |
| Guidelines | Soft copy | Revised job description for MSCPS | English | UNICEF |  |
| Quality education available for all children 6-14 years |  |  |  |  |  |
| Guideline | Hard copy | Kasturba Gandhi Balika Vidyalaya Guidelines | Marathi | School Education & Sports Dept., Mantralaya, Mumbai, Government of Maharashtra, Maharashtra Prathmik Shikshan Parishad, Mumbai |  |
| Register | Hard copy | Sample of school attendance register from AWC 2160 | Marathi |  |  |
|  | Hard copy | Sample of family information register | Marathi |  |  |
| Case study booklet | Hard copy | Case studies on "Model AWW; volunteer; school; SMC, AWC"; Case studies on child labourers; children in need of care and protection; OOSC"; Case studies on "A village; beneficiaries of social protection schemes; child marriage" | Marathi | Vikasganga Samajseva Sanstha, Ghatanji, Child Rights Protection Project, Yavatmal district |  |
| Case study booklet | Hard copy | Case studies on "Irregular students; AWW; child labourers" | Marathi | Vikasganga Samajseva Sanstha, Ghatanji, Child Rights Protection Project, Yavatmal district |  |
| Booklet | Hard copy | What is a boy? What is a girl? | Marathi | Kamla Bhasin (Bharat Gyan Vigyan Samuday) | March 2007 |
| Book | Hard copy | Balshikshankram (2007) - For children at PSE level | Marathi | MSCERT, Pune |  |
| CD | Hard copy | Songs and stories for the AWW | Marathi | MSCERT and UNICEF |  |
| Training module | Hard copy | Training module for Anganwadi Supervisors - First stage | Marathi | MSCERT and UNICEF |  |
| Training module | Hard copy | Training module for Anganwadi Supervisors - Second stage | Marathi | MSCERT and UNICEF | 15-20 Oct, 2012 |
| Training module | Hard copy | Training module for Anganwadi Supervisors - Third stage | Marathi | MSCERT and UNICEF | 15-20 Jan, 2013 |
| Training module | Hard copy | Training module for Anganwadi Supervisors - Fourth stage | Marathi | MSCERT and UNICEF | 15-20 Apr, 2013 |
| Handbook | Hard copy | Handbook for Child Education - Introduction to environment and science experience | Marathi | MSCERT and UNICEF |  |
| Handbook | Hard copy | Handbook for Child Education - Language experience | Marathi | MSCERT and UNICEF |  |
| Handbook | Hard copy | Handbook for Child Education - Art experience, creativity and development of aesthetic vision | Marathi | MSCERT and UNICEF |  |
| Handbook | Hard copy | Handbook for Child Education - Preparation for reading, writing and counting | Marathi | MSCERT and UNICEF |  |
|  | Hard copy | Handbook for Child Education - Bodily and cognitive development | Marathi | MSCERT and UNICEF |  |
| Database | Hard copy | Status of Elementary Education in Maharashtra - State and Districts Profiles; District Information System for Education (DISE), 2011-12 | Marathi | School Education and Sports Department, Government of Maharashtra and UNICEF | Sept. 2012 |
| Database | Hard copy | Status of Elementary Education in Maharashtra - State and Municipal Corporation Profiles; District Information System for Education (DISE), 2011-12 | Marathi | School Education and Sports Department, Government of Maharashtra and UNICEF | Sept. 2012 |
| Database | Hard copy | Status of Elementary Education in Maharashtra - State and Districts Profiles; Unified - District Information System for Education (U-DISE), 2012-13 | Marathi | School Education and Sports Department, Government of Maharashtra | Sept. 2012 |
| Database | Hard copy | Status of Elementary Education in Maharashtra - State and Municipal Corporation Profiles; Unified - District Information System for Education (U-DISE), 2012-13 | Marathi | School Education and Sports Department, Government of Maharashtra | Sept. 2012 |
| Case study booklet | Hard copy | Case studies on quality education | English | UNICEF |  |
| Stickers | Hard copy | Stickers with slogans: "My children go to school, do yours?"; "Children in our house go to school and not to work in the fields."; "Now, you must definitely study!" | Marathi | UNICEF |  |
| Form | Hard copy | PSE - Form to compile information on AWC | Marathi |  |  |
| MPR (Monthly Progress Report) | Hard copy | Form 1 – Rajmata Jijau Mother-Child Health and Nutrition Mission, Yavatmal district | Marathi | ICDS | Dec. 2013 |
| MPR (Monthly Progress Report) | Hard copy | Form 1 – Rajmata Jijau Mother-Child Health and Nutrition Mission, Yavatmal district | Marathi | ICDS | Feb. 2014 |
| Booklet | Hard copy | Let us make the school child-friendly: CFS Programme | Marathi | UNICEF, MPSP and Education Department, Yavatmal |  |
| Checklist | Hard copy | Let us make the school child-friendly | Marathi | UNICEF |  |
| Sample schedule | Hard copy | Monthly schedule of ECE activities for AWW | Marathi |  |  |
| Booklet | Hard copy | Children's sexual exploitation: Their safety - Our responsibility | Marathi | DWCD, UNICEF, FACSE (Forum Against Child Sexual Exploitation) |  |
| Handbook | Hard copy | Training for School Management Committee member (2013-14) (Phase - 1) | Marathi | MPSP (Maharashtra Prathmik Shikshan Parishad) |  |
| Handbook | Hard copy | Training for School Management Committee member (2013-14) (Phase - 2) | Marathi | MPSP (Maharashtra Prathmik Shikshan Parishad) |  |
| Handbook | Hard copy | Training Handbook for SMC members | Marathi | School Education and Sports Department, Government of Maharashtra and MPSP |  |
| Handbook | Hard copy | Volunteer Handbook - SSA | Marathi | School Education and Sports Department, Government of Maharashtra, MPSP and UNICEF | Sept. 2012 |
| Handbook | Hard copy | Training material | Marathi | School Education and Sports Department, Government of Maharashtra, MPSP and UNICEF | Sept. 2012 |
| Booklet | Hard copy | Training material | Marathi | CORO, MPSP, MSCERT and UNICEF | Sept. 2013 |
| Advocacy Booklet | Hard copy | Education is my right | Marathi | School Education and Sports Department, Government of Maharashtra, MPSP and UNICEF |  |
| GR | Hard copy | Related to implementation of MRM programme in the year 2013-14 for girls education programme | Marathi | MPSP | June 6, 2013 |
| GR | Hard copy | Related to infrastructure improvement and maintenance in the year 2013-14 | Marathi | MPSP | May 16, 2013 |
| GR | Hard copy | Related to school grant in the year 2013-14 | Marathi | MPSP | May 16, 2013 |
| Plan | Hard copy | Sample School Development Plan format (Year 2014-15) | Marathi | MPSP |  |
| Article | Hard copy | From Evidence to Impact - Use of DISE data to achieve "Right to Education" in schools | English | UNICEF | March 2013 |
| Article | Hard copy | Kasturba Gandhi Balika Vidyalaya - A transformative space for girls | English | UNICEF | April 2013 |
| Data profile | Hard copy | Block profile - Based on DISE, 2011-12 | English | UNICEF, MPSP |  |
| GR compilation | Hard copy | GRs and notifications for evaluation in Maharashtra | English | UNICEF |  |
| Strategy document | Hard copy | Child-friendly schools - Strategy in 3 districts in Maharashtra, UNICEF-IKEA project | English | UNICEF |  |
| Families and communities take collective action for protection and development of children |  |  |  |  |  |
| Handbook | Hard copy | Handbook for Prerika (Part 1) – Deepshikha Programme for Adolescent Girls | Marathi | UNICEF | July 2009 |
| Handbook | Hard copy | Handbook for Prerika (Part 2) – Deepshikha Programme for Adolescent Girls | Marathi | UNICEF | July 2009 |
| Enhanced access to social protection schemes for vulnerable families (out-of-school children and children without parental care) |  |  |  |  |  |
| Database | Hard copy | Database on beneficiaries of social protection schemes | Marathi | Vikasganga Samajsevi Sanstha, Ghatanji, Child Rights Protection Project |  |

### ANNEXURE 8: List of Research Tools

- IDI with policy level respondents

- FGD with policy level respondents

- IDI with programme/implementation level respondents

- FGD with programme/implementation level respondents

- IDI with community level respondents

- FGD with community level respondents

- FGD with children (6-14 years)

### ANNEXURE 9: Project Partners

In Maharashtra, the NGO partners and consultants are as follows:

#### Consultants

# Outcomes (1, 3 and 4)

- GN Sharma , State Consultant, Social Mobilisation (currently with UNICEF Delhi)

- Santosh Shinde, State Consultant, CP

- Paresh Jayshree Manohar, District Consultant, Yavatmal

- Naseem Md, District Consultant, Wardha

- Dnyanesh Renguntwar, District Consultant, Jalna

- Tanaji Patil

- Namrata Kilpady

# Outcome 2

- Siddesh Wadkar - RTE

- Meena Srinivasan - Quality

- Sneha Madiath - Equity

#### NGO Partners

# Outcomes (1, 3 and 4)

Yavatmal

- Vikasganga SamajSevi Sanstha

- Janseva Gramin Vikas Va Shikshan Pratishthan

- Gramin Samasya Mukti Trust

- Srujan

- Yuva Ved Manch

- Priyadarshini Mahila Gramin Kalyan Sanstha

- Navvidya Bahuudeshiya Sanstha

Wardha

- Yuva Rural Association

- Pragati Bahuudeshiya Sanstha

- Sadbhavna Gramin Vikas Sanstha

- ISSUE: Indian Social Service Unit of Education

- Dharamitra

Jalna

- SACRED

- SWARAJ

- Jai Ambe

- MADAN Bahuudeshiya Sanstha

- MSSM

Outcome 2

- QUEST - Support to KGBVs

- CORO for Literacy - Support to Meena Raju Manch

- Akshara - Support to Gender Resource Center

### ANNEXURE 10: Project’s Alignment with Ethical Principles

An effort to demonstrate alignment with ethical principles of the project has also been presented.

- The Principle of Non-maleficence: Research must not cause harm to the participants in particular and to people in general.

It is not anticipated that harm has been caused to any respondent as a result of participating in the project or in the evaluation. No such cases of harm caused as a result of either project implementation or the subsequent evaluation have come to light. Ethical safeguards to protect all participants, the research team, as well as communities participating in the evaluation were ensured by the research team. For example, all respondents were explained their rights as research participants in the evaluation as outlined above in line with internationally recognised ethical guidelines. The evaluation and the project both engaged the community through active NGOs who were rooted in the community and thus aware of the ground realities as well as maintained community linkages. This point is further addressed in the sections below namely “the principle of beneficence” and “the principle of justice”.

- The Principle of Beneficence: Research should also make a positive contribution towards the welfare of people.

UNICEF as the commissioner of this study is an organisation that serves to uphold the human rights of children.  The project as well as the evaluation of the same; both endeavour to strengthen the protective environment for children as well as address the issue of out of school children in the project states and in India more broadly. Therefore both the project and the evaluation were carried out towards this end in anticipation that it will make a positive contribution to the welfare of people, particularly children. In this spirit the project and the evaluation seek to uphold the principle of beneficence.

- The Principle of Autonomy: Research must respect and protect the rights and dignity of participants.

The autonomy of each respondent was acknowledged by obtaining their informed consent to participate in the study as well as their right to withdraw from the study. The study also recognised children as rights holder therefore supporting the right of children to be involved in research about issues of concern to them.

- The Principle of Justice: The benefits and risks of research should be fairly distributed among people.

The principle of beneficence has been discussed above. Since children are the foundation of any society, any direct benefits that improve their welfare are also absorbed by society and therefore the benefits of research extend to the wider population. Considered from another perspective, key stakeholders are also study participants especially service providers where it is envisaged that research findings will be used to improve service delivery, which suggesting improvements to their working environment.

The community is also a key stakeholder in both the project and the evaluation. Benefits from project implementation particularly under component 3 of the project and any recommendations taken forward arising from the evaluation should benefit the community. Potential risks that may ensue are if recommendations are followed up with the introduction of bureaucratic procedures that create an additional burden of administration that is not supported by adequate resources required to sustain such new processes thus taking away from the actual time of service delivery personnel to deliver services to children as direct beneficiaries. The evaluation however seeks to provide learnings and recommendations that will be used to further strengthen the protective environment for children and address the issue of out of school children by demonstrating efficiency and sustainability that should serve to address these potential challenges. Therefore, the principle of justice is deemed to be upheld.

### ANNEXURE 11: Composition of CP structures

#### a. MSCPS

The First Members of the Governing Body of the Society include:

- Principal Secretary, Women & Child Development - President

- Commissioner, Women & Child Development – Vice President

- Principal Secretary, Finance – Member

- Principal Secretary, Education – Member

- Principal Secretary, Labour – Member

- Principal Secretary, Social justice – Member

- Principal Secretary, Home – Member

- Principal Secretary, Law & Judiciary – Member

- Principal Secretary, Health - Member

- Principal Secretary, Planning – Member

- Deputy Inspector General (DIG), Maharashtra –Member

- Chairperson, State Advisory Board - Member

- Collectors of Districts – Mumbai, Mumbai  Sub, Thane,  Raigad,  Ratnagiri, Sindhudurg, Pune, Satara, Sangali, Solapur, Kolhapur, Nashik, Dhule, Nandurbar, Jalgaon, Ahmednagar, Amravati, Akola, Washim, Yavatmal, Buldhana, Nagpur, Bhandara, Gondia, Chandrapur, Gadchiroli, Wardha, Aurangabad, Jalna, Parbhani, Hingoli, Beed, Nanded, Usmanabad, Latur - Members

- Member Secretary – Deputy Commissioner, Women & Child Development.

- Executive Secretary– Programme Manager, Maharashtra State Child Protection Society

- Representatives from Development partners–

    - Representative of UNICEF, Mumbai

    - Representative of  Childline – Member

The bodies and authorities of the MSCPS are:

- Governing Body

- General Body

- State Child Protection Society(SCPS)

- District Child Protection Unit (DCPU)

- State Adoption Resource Agency (SARA).

#### b. DCPU

The DCPU functionaries comprise of the District Child Protection Officer (DCPO), Protection Officer (Institutional Care), Protection Officer (Non-Institutional Care), Legal cum Probation Officer, Counsellor, Social workers (2), Accountant, Data analyst, Assistant cum data entry operator, Outreach workers (5). Members of the DCPU include:

- District Magistrate/Collector  - Chairperson

- District Women and Child Development Officer (DWCDO) - Secretary

- District Child Protection Officer (DCPO) – Member

- Chairperson/ Member of District Advisory Board – Member

- Superintendent of Police – Member

- District Health Officer – Member

- District Labour Officer – Member

- District Technical Education Officer – Member

- District Social Welfare Officer – Member

- District Education Officer  - Member

- District Planning Officer – Member

- Chairperson, District Child Welfare Committee – Member

- Chairperson, District Juvenile Justice Board - Member

- In-charge District Special Juvenile Police Unit – Member

- Representative of  Special Adoption Agency  - Member

- Representative of Child Line – Member

- Representative of District Legal Services Authority – Member

### ANNEXURE 12: Components of JJB Kit

- JJ Act, 2000, as amended by the Juvenile Justice (Care and Protection of Children) Amendment Act 2006 and Rules 2007.

- Compilation of select case laws

- International and national instruments on Juvenile Justice

- Child protection and Juvenile justice system for Juveniles in conflict with the law (Hindi)

- Handbook for activists on Juvenile Justice

- Criminal Law: Law for Activists Series, Volume 1

- Findings and recommendations of the TISS study on the JJB.

- Ujjwal newsletters

- Compilation of contacts of district authorities, members of JJBs, CWCs, children’s institutions and social work colleges of Maharashtra, policy of the Bal Sangopan Yojana (BSY) and schemes of Social Welfare Department, Government of Maharashtra

### ANNEXURE 13: Components of CWC Kit

- Information on bare acts including JJA, Child Labour (Prohibition and Regulation) Act, Immoral Traffic (Prevention) Act, Bonded Labour System (Abolition) Act, Hindu laws, Family Courts Act, Protection of Women from Domestic Violence Act, Bombay Prevention of Begging Act, Guardians and Wards Act

- Booklets on a). Conventions, policies, plan b). Government resolutions, guidelines and protocol and c). Contacts

- Brochure on WCD schemes

- CD with soft copies of all materials

- SOPs for CWCs

### ANNEXURE 14: Role of Child Protection Structures

| Child Protection Structure | Roles of Child Protection Structures |
| --- | --- |
| State Level |  |
| State Child Protection Society | Fundamental unit for implementation of ICPS. SCPS supports and monitors performance of District Child Protection Societies. They ensure effective implementation of JJA. It also ensures effective implementation of other legislations and policies for child protection. Members: Principal Secretaries of line departments; Director/ Commissioner Women and Child Development; Programme Manager (Child Protection); Programme Manager (Training, IEC; & Advocacy) Other Members: Programme Officer (CNCP); Programme Officer (JCL); Programme Officer (Training); Programme Officer (IEC & Advocacy) |
| State-level Child Labour Task Force | Please note, not a mandatory structure under ICPS Members: Commissioner; Secretary; and other members |
| District Level |  |
| District Child Protection Unit/Society (DCPU/DCPS) | DCPU/S established in each district as fundamental unit for implementation of ICPS. The DCPU/S shall coordinate and implement all child rights and protection activities at district level. ICPS mandates that DCPU/Ss ensure setting up of District, Block and Village level Child Protection Committees for effective implementation of programmes and discharge of functions Senior Members: District Magistrate/Collector; Chairperson/Member of District Advisory Board; District Child Protection Officer (DCPO) Other members: Superintendent of Police; Representative of Childline; Representative of District Legal Services Authority; Protection Officer (Institutional care and non-institutional care - max 3); Legal cum Probation Officers; Counsellor; Social Workers (x2); Outreach Workers (x3) |
| District-level Child Labour Task Force | Not a mandatory structure under ICPS Key Representative: Chairperson/ District Collector |
| Child Welfare Committee | CWC established in each district under ICPS. It is the final authority to dispose of cases for care, protection, treatment, development and rehabilitation of children in need of care and protection and to provide for their basic needs and protection of human rights. CWC has the same powers as a metropolitan magistrate or judicial magistrate of the first class. The probation officer in charge of the case must also submit regular reports of the child’s progress. CWC can hold people accountable for the child such as in the case of child labour, the employers are fined or made to give bonds to the children. Key Representative: Comprised of Chairperson and four members. |
| Juvenile Justice Board | JJBs should be established in each district to deal with matters relating to juveniles in conflict with the law. Members: Metropolitan Magistrate/ Judicial Magistrate of the first class; Social Worker |
| Special Juvenile Police Unit (SJPU) | JJA provides for setting up Special Juvenile Police Units in every district and city to coordinate and upgrade police interface with children. All police officers, designated as juvenile/child welfare officers in the district or city, are members of the SJPU Members: Juvenile/ Child Welfare Police Officers (CWOs); Statutory requirement of two paid social workers in each SJPU supporting the unit appointed by DCPS (one female and one with expertise in child protection) |
| Block and Village Level |  |
| Block Level Child Protection Committees | Under ICPS, every block (ward in a city) should have a Child Protection Committee under the Chairpersonship of the block/ward level elected representative (Head of the Block Committee) with the Block Development Officers as the Member Secretary to recommend and monitor the implementation of child protection services at block level. The committee could include a member of the DCPS, one ICDS functionary, representatives of education and health departments, Chairpersons of the Village Level Child Protection Committees as well as respected community members and civil society representatives |
| Block Child Labour Task Force | Please note, not a mandatory structure under ICPS |
| Village Child protection Committees | VLCPC established in each village under Chairpersonship of village level elected representative (Head of Gram Panchayat) to recommend and monitor the implementation of child protections services at village level VCPC Committee Members: two child representatives, a member of the DCPS, Anganwadi workers, school teachers, auxiliary nurse midwives, as well as respected village members and civil society representatives |

### ANNEXURE 15: CFSS Approach and the RTE Framework

CFSS has three guiding principles of child-centeredness, democratic participation and inclusiveness and five major components that include: learning environment, school environment, improved learning outcomes through development of teacher support, community, civil society partnership and policy and systems.

The Right of Children to Free and Compulsory Education (RTE) Act, 2009 was implemented in Maharashtra on April 1, 2010. A set of rules known as the Maharashtra Rules was also brought out with a GR issued to the effect on Oct 11, 2011 to ensure uniform and smooth implementation of the RTE Act. Maharashtra was the first state to implement Continuous and Comprehensive Evaluation (CCE) in all schools in keeping with the RTE Act. In this way, the policy environment was created at the state and district levels to provide education to all children between the ages of 6-14 which is an essential prerequisite before improving the quality of education.

After making education mandatory, the thrust of work in this sub-outcome was focused on training teachers, the service providers of education, in child-friendly pedagogy as per the child-friendly mandate of the RTE. Articles 3,16,17,29 and 30 of the RTE provide the framework for making schools child-friendly and are summarised as follows:

- The state must provide free elementary education up to the age of 14 in a nearby school to all children including children with special needs.

- Admissions should take place without interviews, donations or any selection process.

- Children who have never attended school or have dropped out must be admitted to age- appropriate classes and provided special training to help them to catch up with other children in the class.

- A child cannot be detained in any class up to Class 8, and cannot be asked to leave the school.

- Children cannot be subject to corporal punishment or mental harassment. Discipline must be applied in a positive manner.

- Children's mental and physical abilities must be given maximum scope for development.

- Learning must be facilitated through exploration and activities in a child-friendly manner.

- Learning should be free of worry, fear, stress, and should allow free expression.

- Continuous and comprehensive evaluation of all children must take place in a stress-free manner.

### ANNEXURE 16: CFS Checklist

Area 1 of the Action Plan: RTE Compliance

A – This happens regularly in my school in a satisfactory manner

B – This happens in my school, but it needs some strengthening

C – I would like to initiate this activity in my school

D – I may want to take up this activity later, but not right now

NA – This is not applicable in my school

| No. | Area | RTE Article No |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Area 1: RTE |  | A | B | C | D | NA |
| 1.1 | No discrimination for admission and participation in school processes (Caste, Class, Gender, Disability, Religion, Language, etc.) | 8(c),9(c) |  |  |  |  |  |
| 1.2 | Transfer certificate and birth certificate not compulsory for admission to schools | 5 |  |  |  |  |  |
| 1.3 | Age appropriate admission given | 4 |  |  |  |  |  |
| 1.4 | Delivering special training to all children admitted under 1.3 |  |  |  |  |  |  |
| 1.5 | All children entitled to free education till completion of elementary education even after fourteen years | 4 |  |  |  |  |  |
| 1.6 | No physical punishment or mental harassment | 17,4,8(e), 9(g) |  |  |  |  |  |
| 1.7 | Timely disbursement of entitlements at school level: free text books, work books, uniform transportation, library, sports equipment, mid day meal |  |  |  |  |  |  |
| 1.8 | Provisions for CWSN utilized (Therapy, availability of resource teacher, aids and appliances supplied where necessary, Home based care for multiple disabilities and severe disability) | 3(2) |  |  |  |  |  |
| 1.9 | Completion certificate issued to all children completing elementary education (even after fourteen years) |  |  |  |  |  |  |
| 1.10 | Cumulative Pupil Record maintained | 9(d) |  |  |  |  |  |
| 1.11 | Agenda and minutes of monthly SMC meeting recorded |  |  |  |  |  |  |

Area 2 of the Action Plan: School Environment

A – This happens regularly in my school in a satisfactory manner

B – This happens in my school, but it needs some strengthening

C – I would like to initiate this activity in my school

D – I may want to take up this activity later, but not right now

NA – This is not applicable in my school

|  | Area 2: School Environment | RTE Article | A | B | C | D | NA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Display of commitment to development of Child Friendly School in a visible location |  |  |  |  |  |  |
| 2.2 | Greenery in school (trees/ potted plants as space available) |  |  |  |  |  |  |
| 2.3 | Cleanly maintained campus, common areas | 9(f) |  |  |  |  |  |
| 2.4 | Dustbin in each class and used by students and teachers |  |  |  |  |  |  |
| 2.5 | Toilets kept clean with water and soap for hand washing |  |  |  |  |  |  |
| 2.6 | Mirror and comb available | 9(f) |  |  |  |  |  |
| 2.7 | First Aid Kit with medicines within expiry period for common illnesses available |  |  |  |  |  |  |
| 2.8 | Playground/or space for playing be available and in use |  |  |  |  |  |  |
| 2.9 | Sports Kit used at least once a week |  |  |  |  |  |  |
| 2.10 | Mid-day Meals served on time |  |  |  |  |  |  |
| 2.11 | Code of conduct for students developed in consultation with students |  |  |  |  |  |  |
| 2.12 | Code of conduct for teachers developed in consultation with SMCs |  |  |  |  |  |  |
| 2.13 | School display board regularly updated with relevant information (Funds available, SMC meeting decisions, enrollment, etc.) |  |  |  |  |  |  |

Area 3 of the Action Plan: Learning Environment

A – This happens regularly in my school in a satisfactory manner

B – This happens in my school, but it needs some strengthening

C – I would like to initiate this activity in my school

D – I may want to take up this activity later, but not right now

NA – This is not applicable in my school

|  | Area 3: Learning Environment |  | A | B | C | D | NA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Bulletin board regularly updated with informative/ interesting matter (important dates, student birthdays, joke) |  |  |  |  |  |  |
| 3.2 | School assembly activities with opportunities for all children to lead | 29(2)(g) |  |  |  |  |  |
| 3.3 | Some design ideas for using school building as learning aid such as: -Height measuring scale painted on classroom wall, meter scale painted on bench, -Hopscotch court/snake and ladder board etc painted in veranda | 9(f) |  |  |  |  |  |
| 3.4 | Clock, posters/charts or any other educational displays at the eye level of children |  |  |  |  |  |  |
| 3.5 | Use of a variety of seating arrangement as per requirement of the activity (groups, etc.) | 29(2)(g) |  |  |  |  |  |
| 3.6 | TLM/ SLM accessible to children and in use (e.g. reading cards, charts, reading books, globe, Mathematics and English kit, etc.) | 29(2)(e) |  |  |  |  |  |
| 3.7 | Establishment and/or activation of learning corners, exploratory corner | 29(2)(e) |  |  |  |  |  |
| 3.8 | Easy and regular access to library books | 29(2)(e) |  |  |  |  |  |
| 3.9 | Active child cabinet or Meena-Raju Manch |  |  |  |  |  |  |
| 3.10 | Board/ Space for free expression by children | 29(2)(g) |  |  |  |  |  |
| 3.11 | Feedback box for students suggestion, problems, on working of school, teaching etc. | 29(2)(g) |  |  |  |  |  |
| 3.12 | Functional computers and timetable of use |  |  |  |  |  |  |

Area 4 of the Action Plan: Classroom Processes

|  | Area 4: Child Friendly classroom processes |  | A | B | C | D | NA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Respecting the mother tongue of students, and accepting its use in school at the primary level |  |  |  |  |  |  |
| 4.2 | Daily lesson plan with child-centered activities |  |  |  |  |  |  |
| 4.3 | Using the first name of children to address students in the class | 29(2) (g) |  |  |  |  |  |
| 4.4 | Encouraging students to work in mixed groups | 29(2) (g) |  |  |  |  |  |
| 4.5 | Encouraging children to ask questions and share opinions | 29(2)(e) |  |  |  |  |  |
| 4.6 | Encouraging and displaying students’ free expression in written/artistic form | 29(2)b |  |  |  |  |  |
| 4.7 | Promoting self study habits through open book exercises, studying using LEP activity cards, supervised study, asking open ended questions to children etc. | 29(2)(e) |  |  |  |  |  |
| 4.8 | Encouraging and positive remarks to be recorded for every child in CCE | 29(2)h |  |  |  |  |  |

### ANNEXURE 17: List of Government Resolutions (GRs) issued under the project for child protection (Outcomes 1, 3 and 4)

| S. No. | Outcome of the Programme | Date of GR | Content of GR | Purpose |
| --- | --- | --- | --- | --- |
| 1 | 1 | 30/11/09 | SOPs for CWCs | Strengthening JJ System |
| 2 | 1 | 5/6/2010 | Setting up of Vishakha Committee in Children’s’ Homes | Strengthening ICPS |
| 3 | 1 | 2/25/2011 | Setting up Children's Management Committees in Homes | Strengthening Protection |
| 4 | 1 | 3/3/2011 | Appointment of Counsellors in Children’s’ Homes | prevent sexual harassment |
| 5 | 1 | 3/29/2011 | Increase in sitting allowance for CWCs | Strengthening CWCs and JJ System |
| 6 | 1 | 4/7/2011 | Collector to nominate persons to various District level Committees for child protection and CWC | Strengthening JJ System |
| 7 | 1 | 4/8/2011 | Regarding care and protection of 0-6 years children - Regularising SAA | Alternative Care |
| 8 | 1 | 5/27/2011 | Related to increase in allowance to SJPU for repatriation | Strengthening JJ System |
| 9 | 1 | 17/08/11 | State Plan of Action on Child Labour adopted | Elimination of Child Labour |
| 10 | 1 | 18/08/11 | Formation of MSCPS and appointment of SPSU | ICPS Roll out |
| 11 | 3 | 19/09/11 | 5% reservation in Children's Homes for rehabilitation of Working Children | Rehabilitation and Alternative Care |
| 12 | 1 | 10/26/2011 | Appointment of High Court Committee for Monitoring and supervision of Children’s Homes | Strengthening JJ system |
| 13 | 1 | 12/22/2011 | Comprehensive Care Plan for children in Institutions | Strengthening CP systems and standards of care in Institutions |
| 14 | 1 | 12/22/2011 | Registration and licensing of Homes | Strengthening JJ Systems |
| 15 | 1 | 12/29/2011 | Appointment of Divisional Committees for Monitoring and Supervision of Homes | Strengthening JJ Systems |
| 16 | 1 | 05/01/12 | GR for Implementation of the State Plan of Action on Child Labour and Role of DWCD | Prevention of CL and Strengthening CP |
| 17 | 1 | 1/23/2012 | Procedures in relation to CWC: Sitting place, record keeping and documentation | Strengthening JJ Systems |
| 18 | 1 | 5/2/2012 | Crisis Management Protocols and closure of Homes | Strengthening JJ Systems |
| 19 | 3 | 17/05/12 | Role of Rural Development Department in implementing State Plan of Action on Child Labour | Role of PRIs in child labour elimination |
| 20 | 1 | 7/17/2013 | ICPS and DWCD Coordination | Strengthening JJ Systems |
| 21 | 3 | 3/06/13 | Authorities for monitoring Child Marriage: Gram Sevak and AWW | Prevention of Child Marriage |
| 22 | 4 |  | Bal Sangopan Yojna | Strengthening Social Protection |
| 23 | 4 | 14/11/2013 | Adoption of State Child Policy | Strengthening Social Protection |
| 24 | 3 | 3/10/2011 | Role of ZP level for Implementation of Special Gram Sabhas on children's issues | Communities and families and PRI play a role in Child Protection |

### ANNEXURE 18: List of GRs related to Education

| Date of issue | Place | Number | Issuing institution | Name | Content | Attached forms/appendices |
| --- | --- | --- | --- | --- | --- | --- |
| 11th October, 2011 | Mantralaya, Mumbai | PRE-2010/C.R.-211 (B)/PE-1 | School Education and Sports Department | Maharashtra Right of Children to Free and Compulsory Education Rules, 2011 | Brings into force the RTE Act, 2009 with effect from April 1, 2010. Includes list of rules for the following: 1) special training for teachers 2) duties of state govt. and local authority 3) responsibilities of schools and teachers 4) school management committee 5) teachers 6) curriculum and completion of elementary education 7) protection of rights of children | Appendix II, Form I - Self declaration cum application for grant of recognition of school; Form II - Recognition certificate for the school under sub rule (4) of rule 11 of Right of Children to Free and Compulsory Education Rules, 2011 for the purpose of section 18 of the Right of Children to Free and Compulsory Education Act, 2009; Form III - Certification for student that he/she has received elementary education up to 8th standard as per the RTE. |
| 24th May, 2012 | Mantralaya, Mumbai | PRE 2012/CR 74/PE 1 | School Education and Sports Department | 25% admission in unaided school for weaker section and disadvantaged group children 2012-13 | Describes the manner of reservation of seats for admission, in respect to elementary education, for the children belonging to disadvantaged group and children belonging to weaker section and for matters incidental thereto namely 1) short title, application and duration 2) definitions 3) provisions for reservation of seats 4) manner of reservation of seats 5) general conditions 6) monitoring of admission 7) procedure for reimbursement | Form-1 - Form for admission against free seats in entry level classes for academic year 2012-13 Form-2 - Application form for the admission under free ship quota Form-3 - Registration slip to be issued to parents Form-4 - Return to be submitted to the education officer after completion of admission process Form-5 - Quarterly statement of the attendance of the children admitted on the free seats |
| 15th March, 2013 | Mantralaya, Mumbai | PRE-2012/CR-112/PE 1 | School Education and Sports Department | 25% admission in unaided school for weaker section and disadvantaged group children 2013-14 | Describes the procedure for admission in class 1 or pre-school for at least 25% of the strength of that class at the entry level for the children belonging to disadvantaged group and weaker section and for matters incidental thereto including the name, definitions, procedure to be followed by school, certificates to be accompanied, fees, acknowledgement, communication of rejected application, general conditions, monitoring of admission, procedure for reimbursement, grievances and redressal | Form-I (Rule 3.1) - Notice to be published and displayed by the school Form-II (Rule 4) - Application form to be submitted by the parent or guardian Form-III (Rule 8) - Acknowledgement for the receipt of application and documents (to be issued by school) Form-IV (Rule 10 (C)) - Result of draw of lottery held on __ in the presence of admission committee Form-V (Rule 12 (2)) - Application for claim of reimbursement (1st installment) Form-V (Rule 12 (2)) - Application for claim of reimbursement (2nd installment) |
| 7th March, 2012 | Mantralaya, Mumbai | PRE 1411/(175/11)/PE-5 | School Education and Sports Department | Academic authority | Describes the powers and duties of the Academic Authority (MSCERT, Pune) and the Maharashtra State Bureau of Textbook Production and Curriculum Research | NA |
| 10th May, 2010 | Mantralaya, Mumbai | 2009/PRE 292/PE 1 | School Education and Sports Department | No detention of children in same class; No board examination till completion of the elementary education | No child that is given entry into a school can be kept behind and cannot be removed until his primary education is completed. | NA |
| 11th June, 2010 | Mantralaya, Mumbai | PRE/2010/215/PE 1 | School Education and Sports Department | School admission (Age proof, extended period of admission, screening procedure and capitation fee, parents responsibility | Age of child for entry into school; documents required for entry into school; entry into age-appropriate class; right to change schools; time period of entry into school during the school year; giving donation for school admission is forbidden; entry of children with special needs; duties of parents | NA |
| 14th June, 2010 | Mantralaya, Mumbai | PRE-2010/213/PE 1 | School Education and Sports Department | Acquiring minimum qualifications for teachers | Those teachers who are already at their posts and do not possess a B.Ed. Degree have to obtain a B.Ed. degree through their own expense by 31st Mar, 2014; These teachers should be given adequate facilities to obtain the title of a qualified teacher by 31st Mar, 2014; unqualified teachers have to obtain the prescribed qualifications, in any conditions, in the above 5 years (2009-2014); if any individual teacher, as per his/her consideration, has applied for training, then they should be provided with facilities for training in that year itself through a letter. | NA |
| 16th June, 2010 | Mantralaya, Mumbai | PRE-2010/291/PE-1 | School Education and Sports Department | No detention of children in same class | Ensuring that the child gains adequate skills in that class will be the responsibility of that teacher/subject teacher/principal or school | NA |
| 17th June, 2010 | Mantralaya, Mumbai | PRE 2010/217/PE 1 | School Education and Sports Department | School Management Committee and School Development Plan | Roles and responsibilities of the school management committee | Appendix-A: Guiding principles for preparing the school development plan |
| 18th June, 2010 | Mantralaya, Mumbai | PRE-2010/225/PE-1 | School Education and Sports Department | Maintaining the PTR | MIS information is available and it should be verified with schools; rules for teacher deployment | Appendix-A and Appendix-B: Necessary teacher posts in schools and currently agreed upon posts in schools as per GR; Appendix-C: Schedule |
| 1st March, 2011 | Mantralaya, Mumbai | PRE-2010/589/PE-1 | School Education and Sports Department | Physical punishment and mental harassment (no corporal punishment and expulsion) | The forms of physical punishment and mental harassment included are listed. | NA |
| 24th July, 2007 | Mantralaya, Mumbai | BHA-2006/138/K-3 | School Education and Sports Department | Constitution of SCPCR | Specifies the members of the SCPCR | NA |
| 13th February, 2013 | Mantralaya, Mumbai | 1112/258/2012/PE-3 | School Education and Sports Department | Elementary cycle | Defines the different levels of education | NA |
| 1st March, 2011 | Mantralaya, Mumbai | PRE 2011/114/PE-1 | School Education and Sports Department | Availability of neighbourhood schools | There will be provision for children to go to school between grades 1-5 within 1 km of their home and between grades 6-8 within 3 kms of their home. Where such provisions are not made available, they will be provided with a means of transport. | NA |
| 23rd August, 2013 | Mantralaya, Mumbai | RTE 2013/91/PE-1 | School Education and Sports Department | Teacher eligibility test (TET) | TET will be made compulsory as per the RTE; accompanying instructions | NA |
| 31st December, 2013 | Mantralaya, Mumbai | RTE 2013/20/PE-1 | School Education and Sports Department | Responsibility of local authority | Specifies the roles of teachers and the level of education in the various types of schools run by different institutions like government, local bodies like the Zilla Parishad, Mahanagarpalika, Nagarpalika, boards etc, and private institutions (aided or unaided). | NA |

### ANNEXURE 19: Bal Sangopan Yojana

The Bal Sangopan Yojana covers any situation that inhibits the capacity of the family to take care of the child. The family in such situation falls under the umbrella of the scheme. The reasons may include HIV, loss of family breadwinner, natural calamities, etc. It includes circumstances that compel children to be at economic risk and to be trafficked. For example, if the breadwinning family members have contracted TB, then the BSY can be availed of for sending the child to school. If the family has fallen into debt, then the aid of rupees 425/- can be drawn upon by the family. In this process, families interact with the Probationary Officer (PO) and NGOs and are thus brought into contact with institutional support structures. These support structures can then link families to other schemes (like agricultural schemes), thus ensuring that families and children are being safeguarded against the effects of poverty.

February 7, 2014

Ministry of Women and Child Development (2007). Study on Child Abuse India 2007

Child Friendly Schools. Strategy in 3 districts in Maharashtra. UNICEF-IKEA Project.

Feb 2013, UNICEF.Let’s make our schools child-friendly: Teacher’s Handbook. p.6

Extracted from "Let's Make Our School Child-Friendly"; Teachers' Handbook (Translation of "Karuya Shala Balsnehi", a handbook for teachers on an action plan for Child Friendly Schools) (Feb 2013, UNICEF)