# Annexes

The Formative Evaluation Of The HighScope® Curriculum Reform  Programme

(February to December, 2014 )

28 January, 2015

Submitted by:

http://manitouinc.com/

UNICEF Office for the Eastern Caribbean Area

UNICEF Office for the Eastern Caribbean Area

1st floor,

UN House

Marine Gardens

Christ Church

BARBADOS

Formative Evaluation of the HighScope Curriculum Reform Programme in Antigua and Barbuda, Dominica and St. Kitts and Nevis completed between February and January 2014.

Evaluation conducted and submitted by:

Manitou Incorporated

1008 Main Street

Suite #201

Peekskill, New York, 10566

Please see website http://manitouinc.com/ for office telephone and fax numbers

Lead Evaluator: Tristi Nichols, Ph.D. (tnichols@manitouinc.com)

Expert in Early Childhood Development, Jennifer Greene, Ph.D. (jennifer@manitouinc.com)

Associate Evaluator: Mrs. Sarah Boeckmann (sarah@manitouinc.com)

The report was commissioned by UNICEF Office for the Eastern Caribbean Area

UNICEF Office for the Eastern Caribbean Area

1st Floor,

United Nations House

Marine Gardens

Christ Church

Bridgetown, BARBADOS

UNICEF Staff Contacts:

Frederic Unterreiner

Chief, Monitoring and Evaluation

Oladimeji Olowu

Planning, Monitoring & Evaluation Specialist

Wycliffe Otieno, Ph.D.

Chief of Education

Shelly-Ann Harper

Early Childhood Development Specialist

Contents

Annex 1: 	Country Summaries	76

Country Summary: Antigua and Barbuda	77

Country Summary: Dominica	83

Country Summary: St. Kitts and Nevis	89

Annex 2: 	Terms of Reference	93

Annex 3: 	Methodology	100

Annex 4:	Stakeholder Feedback on Recommendations By Country	114

Annex 5:  	Evaluation Plan Matrix	135

Annex 6:	List of Documents Consulted	150

Annex 7: 	List of Stakeholders	154

Annex 8: 	Samples of Main Instruments Used (and permission slip)	158

Annex 9:  Sample List of Materials for Each Interest Area	175

Annex 10: List of Training Efforts	177

Annex 11:   UNICEF-Adapted OECD Evaluation Criteria	180

Annex 12:   Evaluation Firm and Team Profiles	182

Annex 1: 	Country Summaries

## Country Summary: Antigua and Barbuda

Antigua and Barbuda is a 442.6 sq km (Antigua is 280 sq km; Barbuda is 161 sq km) twin-island Small island Developing State (SIDS) with a population of 91, 295 located in the northern section of the Eastern Caribbean chain of islands. Antigua and Barbuda is considered a high income country with a GDP (PPP) of $1.61 billion (2013 estimate) and a per capita GDP (PPP) of $18,400 (2013 estimate).

Economic Context

Tourism dominates Antigua and Barbuda's economy, accounting for nearly 63% of GDP and 58% of total employment. In contrast, agriculture contributes roughly 7% to employment. Overall employment is 11%. The countries agricultural production is focused on the domestic market and constrained by a limited water supply and a labor shortage stemming from the lure of higher wages in tourism and construction. In 2009, Antigua's economy was severely hit by the global economic crisis and suffered from the collapse of its largest private sector employer, a steep decline in tourism, a rise in debt, and a sharp economic contraction between 2009 and 2011. Antigua has not yet returned to its pre-crisis growth levels. After taking office in 2004, the SPENCER government adopted an ambitious fiscal reform programme and was successful in reducing its public debt-to-GDP ratio from approximately 130% in 2010 to 89% in 2012. As of 2012, Antigua and Barbuda’s debt was 89% of GDP.

Contribution of Tourism to Antigua and Barbuda’s Economy

| 2013 Data from World Travel and Tourism Council | Antigua and Barbuda | Dominica | St. Kitts and Nevis |
| --- | --- | --- | --- |
| Direct Contribution to GDP | 16.4% of GDP | 10% of GDP | 6.2% of GDP |
| Total Contribution to GDP | 62.9% of GDP | 32% of GDP | 22.5% of GDP |
| Employment Direct Contribution | 16.8% of total employment | 9.1% of total employment | 6.1% of total employment |
| Employment Total Contribution | 57.8% of total employment | 29.1% of total employment | 21.4 of total employment |

Government Context

Antigua and Barbuda is part of the British Commonwealth and has a parliamentary system of government. Antigua and Barbuda’s political parties include:

- Antigua Labor Party or ALP [Gaston Browne]

- Barbuda People's Movement or BPM [Trevor Walker]

- Barbuda People's Movement for Change [Arthur Nibbs]

- Barbudans for a Better Barbuda [Ordrick Samuel]

- United Progressive Party or UPP [W. Baldwin Spencer]

Since March 24, 2004 through the time of data collection, the Prime Minister was Winston Baldwin Spencer of the UPP. However, as with all the countries included in this formative evaluation, Antigua and Barbuda were anticipating pending elections during data collection in the end of April 2014.   As of June 13, 2014, Gaston Browne of the ALP is the country’s new prime minister, returning ALP to power after a 10 year drought. Browne is a one-time banker who campaigned on turning around Antigua and Barbuda’s struggling economy and is now the country’s youngest prime minister. The Labor Party won 14 of the 17 seats in a landslide over the United Progressive Party led by Baldwin Spencer. Spencer, 63, was seeking a third, five-year term for his party, which many felt had struggled to govern the Eastern Caribbean nation amid a hobbling financial crisis, high unemployment and rising crime rate.

Crime continues to be a problem in Antigua and Barbuda, and the government has responded with increased community policing, the reintroduction of roadblocks, and stiffer fines for firearms violations. The United Nations Development Programme’s 2012 Caribbean Human Development Report reported that Antigua and Barbuda suffers from a high rate of property crimes, such as robberies, with a lower violent crime rate. Long term evidence of participation in the HighScope curriculum positively affecting participation in crime makes these high crime rate relevant.

As data collection was done with officials from the previous government, at this stage it is unknown how the shift in government from UPP to ALP will affect the implementation and expansion of HighScope in Antigua and Barbuda.

Geography/Physical Context

Antigua and Barbuda are low-lying islands comprised of limestone and coral with some higher volcanic areas. The highest point above sea-level is 402 meters. Antigua and Barbuda are approximately 33 kilometres apart. Despite this short distance there are policy and infrastructure differences between the two islands which influence the implementation of HighScope. In contrast to St. Kitts and Nevis which has model centres on both islands, the HighScope curriculum is not currently being implemented in Barbuda. According to government officials, a primary challenge with government-led expansion of HighScope in Barbuda is the absence of Junior Secondary Schools on the island. Junior Secondary school was recently eliminated in Antigua when universal secondary education was introduced. This elimination of Junior Secondary schools freed up classroom space in primary schools for preschools such as Villa and Green Bay which are now implementing HighScope in that space in Antigua.  Barbuda did not have any Junior Secondary Schools which means that there is no existing space to introduce government-run centres.

Early Childhood Education Sector

For 2013, the total number of students enrolled in an ECE programme was 2,195 in 72 institutions.  Fifty-one percent of those children enrolled were female, and 48.6% were male. This includes the small number of centres which are daycare only, with a preschool unit.   The exact numbers are outline below.

| 2012 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total Boys | Total Girls | Overall Total | % Female | % Male | Total Schools | Total Staff |
| Daycare Only | 107 | 87 | 194 | 44.8% | 55.2% | 15 | 50 |
| Combination Day Care and Preschool | 614 | 629 | 1243 | 50.6% | 49.4% | 44 | 213 |
| Standalone Preschool | 598 | 659 | 1257 | 52.4% | 47.6% | 29 | 143 |
| Overall Total | 1319 | 1375 | 2694 |  |  | 88 | 406 |
| 2013 |  |  |  |  |  |  |  |
|  | Total Boys | Total Girls | Overall Total | % Female | % Male | Total Schools | Total Staff |
| Daycare Only | 32 | 30 | 62 | 48.4% | 51.6% | 8 | 21 |
| Combination Day Care and Preschool | 556 | 478 | 1034 | 46.2% | 53.8% | 37 | 180 |
| Standalone Preschool | 534 | 565 | 1099 | 51.4% | 48.6% | 27 | 104 |
| Overall Total | 1122 | 1073 | 2195 |  |  | 72 | 305 |

Source: ECD Unit Antigua

How many schools are currently using the HighScope Curriculum?

Five schools in Antigua and Barbuda are currently using the HighScope Curriculum.

Three (3) HighScope Model Schools

- Simon Bolivar (government run-preschool only)

- Beginners Academy (private-combined daycare/crèche and preschool)

- Eleven Hour Sunshine (private-combined daycare/crèche and preschool)

Two (2) Government Schools where HighScope has been expanded

- Villa (government run-preschool only)

- Green Bay (government run-preschool only)

Pre-Primary Enrollment Data from UNESCO

| Net enrolment rate, pre-primary, both sexes (%) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 64.0 | 72.0 | .. |
| Dominica | 76.7 | .. | .. | .. |
| Saint Kitts and Nevis | .. | 77.9 | .. | .. |
| Net enrolment rate, pre-primary, female (%) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 63.4 | 68.8 | .. |
| Dominica | 82.1 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Net enrolment rate, pre-primary, male (%) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 64.6 | 75.2 | .. |
| Dominica | 71.5 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Net enrolment rate, pre-primary, gender parity index (GPI) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 98 | 92 | .. |
| Dominica | 1.15 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Data Source: UIS/ISU from http://data.uis.unesco.org/ |  |  |  |  |

| Gross enrolment ratio, pre-primary, both sexes (%) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 84.3 | 82.7 | 88.6 | .. |
| Dominica |  | 104.9 | 101.9 | 95.0 | .. |
| Saint Kitts and Nevis |  | 90.0 | 95.6 | .. | .. |
| Gross enrolment ratio, pre-primary, female (%) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 81.7 | 84.0 | 85.8 | .. |
| Dominica |  | 106.0 | 107.0 | 97.2 | .. |
| Saint Kitts and Nevis |  | 88.1 | 103.4 | .. | .. |
| Gross enrolment ratio, pre-primary, male (%) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 87.0 | 81.4 | 91.4 | .. |
| Dominica |  | 103.8 | 97.0 | 92.9 | .. |
| Saint Kitts and Nevis |  | 91.9 | 88.1 | .. | .. |
| Gross enrolment ratio, pre-primary, gender parity index (GPI) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 0.94 | 1.03 | 0.94 | .. |
| Dominica |  | 1.02 | 1.10 | 1.05 | .. |
| Saint Kitts and Nevis |  | 0.96 | 1.17 | .. | .. |
| Data Source: UIS/ISU from http://data.uis.unesco.org/ |  |  |  |  |  |

## Country Summary: Dominica

Dominica is a 261 sq. km. Small island Developing State (SIDS) with a population of 51,538 (July 2014 est.) located in the northern part of the Eastern Caribbean chain of islands, one-third of the way between Puerto Rico and Trinidad and Tobago. Dominica is considered an upper middle income country with a GDP (PPP) of $1.015 billion (2013 est) and a per capita GDP (PPP) of $14,300 (2013 est).

Economic Context

While tourism plays an important role in Dominica’s economy, accounting for nearly 32% of GDP and 29% of total employment it is not as dominant a contributor as in Antigua and Barbuda.  Tourism has increased since Dominica began to market itself more strongly as an eco-tourism destination due to its mountainous terrain and attractions such as rainforests and sulfur hot-springs.

Contribution of Tourism to Dominica’s Economy

| 2013 Data from World Travel and Tourism Council | Antigua and Barbuda | Dominica | St. Kitts and Nevis |
| --- | --- | --- | --- |
| Direct Contribution to GDP | 16.4% of GDP | 10% of GDP | 6.2% of GDP |
| Total Contribution to GDP | 62.9% of GDP | 32% of GDP | 22.5% of GDP |
| Employment Direct Contribution | 16.8% of total employment | 9.1% of total employment | 6.1% of total employment |
| Employment Total Contribution | 57.8% of total employment | 29.1% of total employment | 21.4 of total employment |

Both agriculture and industry contribute more to total employment than does tourism, 40% and 32% respectively. Overall employment is 23% (2000 est). Dominica’s major exports are bananas, soap, bay oil, vegetables, grapefruit and oranges. Because of its dependence on agriculture the Dominican economy remains highly vulnerable international economic developments and climatic conditions. For example, when Hurricane Dean struck the island in August 2007 it caused damage equivalent to 20% of GDP.  In 2012 weak demand and an outbreak of banana leaf disease negatively impacted the nation’s banana industry hurting Dominica’s attempts to recover from the global economic crisis.

In 2003, the government began a comprehensive restructuring of the economy - including elimination of price controls, privatization of the state banana company, and tax increases - to address an economic and financial crisis and to meet IMF requirements. In 2009, the economy contracted as a result of the global recession and to date growth remains anemic. The debt burden has declined from 78% of GDP in 2011 to approximately 70% in 2012, one of the lowest levels in the Eastern Caribbean.

Government Context

The Commonwealth of Dominica is a parliamentary democracy. The major political parties are:

- Dominica Freedom Party or DFP [Judith Pestaina]

- Dominica Labor Party or DLP [Roosevelt Skerrit]

- Dominica United Workers Party or UWP [Hector John]

The current head of state is President Charles A. Savarin.  The Prime Minister is Roosevelt Skerrit of the DLP. The most recent elections were held in September 2009, the next are expected in 2018.

Geography/Physical Context

Dominica’s geography was unique among the three data collection sites, because of its rugged mountainous terrain and dense rainforest.   Steep hills, winding roads, and periods of heavy rainfall increase travel times and make it very challenging for the one staff member monitoring all 90 preschools and daycares on a regular basis.

Early Childhood Education Sector

For 2013-2014 school year, the total number of students enrolled in a preschool programme in Dominica was 1,773 at 74 institutions (six of which were unregistered).   This represents data for preschools only, and for daycares, only basic data is available.  Forty-seven percent of those children enrolled were female, 53% were male.

| 2011-2012*** |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Type of Center | Boys | Girls | Total | % Female | % Male | Total Schools |
| Preschools (registered and unregistered) | 863 | 870 | 1848 | 47% | 47% | 73 |
| Daycares | 103 | 116 | 219 | 53% | 47% | 15 |
| Overall Total | 966 | 986 | 2067 | 48% | 47% | 88 |
| 2012-2013** |  |  |  |  |  |  |
| Type of Center | Boys | Girls | Total | % Female | % Male | Total Schools |
| Preschools (registered and unregistered) | 962 | 886 | 1848 | 48% | 52% | 73 |
| Daycares | 110 | 105 | 215 | 49% | 51% | 13 |
| Overall Total | 1072 | 991 | 2063 | 48% | 52% | 86 |
| 2013-2014* |  |  |  |  |  |  |
| Type of Center | Boys | Girls | Total | % Female | % Male | Total Schools |
| Preschools (registered and unregistered) | 939 | 834 | 1773 | 47% | 53% | 74 |
| Daycares |  |  |  |  |  | 16 |
| Overall Total |  |  |  |  |  | 90 |

* Dominica Database of Registered ECE Facilities 2013-2014 as at January 2014

** Dominica Education Planning Unit, 2012

***Dominica Education Planning Unit, 2012

How many schools are currently using the HighScope Curriculum?

There are 24 schools in Dominica using the HighScope Preschool Curriculum.

The four (4) Model HighScope centres that were the focus of the evaluation are:

- Mahaut

- Grand Fond

- Social Centre

- S.W.O.R.D

The two (2) additional centres implementing the HighScope curriculum that began at the same time as the model centres and are where two TOT’s completed their training are:

- Bagatelle

- Canefield

Four (4) additional centres implementing the HighScope curriculum and are physically attached to primary schools that started after the pronouncement on universal preschool access in 2012 include:

- Campbell

- Pichelin

- Roseau

- Trafalgar

14 other preschools that are also implementing the HighScope curriculum. They are considered “private schools” but most are in primary school buildings.

- Bense

- Castle Bruce

- Grand Bay

- Jones Beaupierre

- Good Hope

- Petite Soufriere

- Dublanc

- Delices

- Colihaut

- Petite Savanne

- Tete Start

- Vieille Case

- St. Joseph

- Morne Riviere

Pre-Primary Enrollment Data from UNESCO

| Net enrolment rate, pre-primary, both sexes (%) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 64.0 | 72.0 | .. |
| Dominica | 76.7 | .. | .. | .. |
| Saint Kitts and Nevis | .. | 77.9 | .. | .. |
| Net enrolment rate, pre-primary, female (%) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 63.4 | 68.8 | .. |
| Dominica | 82.1 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Net enrolment rate, pre-primary, male (%) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 64.6 | 75.2 | .. |
| Dominica | 71.5 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Net enrolment rate, pre-primary, gender parity index (GPI) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 0.98 | 0.92 | .. |
| Dominica | 1.15 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Data Source: UIS/ISU from http://data.uis.unesco.org/ |  |  |  |  |

| Gross enrolment ratio, pre-primary, both sexes (%) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 84.3 | 82.7 | 88.6 | .. |
| Dominica |  | 104.9 | 101.9 | 95.0 | .. |
| Saint Kitts and Nevis |  | 90.0 | 95.6 | .. | .. |
| Gross enrolment ratio, pre-primary, female (%) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 81.7 | 84.0 | 85.8 | .. |
| Dominica |  | 106.0 | 107.0 | 97.2 | .. |
| Saint Kitts and Nevis |  | 88.1 | 103.4 | .. | .. |
| Gross enrolment ratio, pre-primary, male (%) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 87.0 | 81.4 | 91.4 | .. |
| Dominica |  | 103.8 | 97.0 | 92.9 | .. |
| Saint Kitts and Nevis |  | 91.9 | 88.1 | .. | .. |
| Gross enrolment ratio, pre-primary, gender parity index (GPI) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 0.94 | 1.03 | 0.94 | .. |
| Dominica |  | 1.02 | 1.10 | 1.05 | .. |
| Saint Kitts and Nevis |  | 0.96 | 1.17 | .. | .. |
| Data Source: UIS/ISU from http://data.uis.unesco.org/ |  |  |  |  |  |

## Country Summary: St. Kitts and Nevis

St. Kitts and Nevis is a 751sq km island Small island Developing State (SIDS) with a population of 73,449 (est. July 2014) located in the center of the Eastern Caribbean chain of islands, halfway between Puerto Rico and Trinidad and Tobago. St. Kitts and Nevis is considered a high income country with a GDP (PPP) of $952 million (2013 est) and a per capita GDP (PPP) of $16,300 (2013 est).

Economic Context

Since the 1970s, tourism has replaced sugar as the traditional mainstay of the economy.  Tourism currently contributes 23% to GDP and represents 6% of total employment. Roughly 200,000 tourists visited the islands in 2009, but reduced tourism arrivals and foreign investment led to an economic contraction in 2009-2012, and the economy returned to growth only in 2013. Like other tourist destinations in the Caribbean, St. Kitts and Nevis is vulnerable to damage from natural disasters and shifts in tourism demand.

Contribution of Tourism to St. Kitts and Nevis’ Economy

| 2013 Data from World Travel and Tourism Council | Antigua and Barbuda | Dominica | St. Kitts and Nevis |
| --- | --- | --- | --- |
| Direct Contribution to GDP | 16.4% of GDP | 10% of GDP | 6.2% of GDP |
| Total Contribution to GDP | 62.9% of GDP | 32% of GDP | 22.5% of GDP |
| Employment Direct Contribution | 16.8% of total employment | 9.1% of total employment | 6.1% of total employment |
| Employment Total Contribution | 57.8% of total employment | 29.1% of total employment | 21.4 of total employment |

In terms of agriculture, following the 2005 harvest, the government closed the sugar industry, after several decades of losses. To compensate for lost jobs, the government has embarked on a program to diversify the agricultural sector and to stimulate other sectors of the economy, such as export-oriented manufacturing and offshore banking. The government has made notable progress on reducing its public debt—from 154% of GDP in 2011 to 83% in 2013—although it is still one of the highest in the world.

Government Context

St. Kitts and Nevis is part of the British Commonwealth and is a parliamentary democracy. The major political parties in the country include:

- Concerned Citizens Movement or CCM [Vance Amory]

- Nevis Reformation Party or NRP [Joseph Parry]

- People's Action Movement or PAM [Shawn Richards]

- Saint Kitts and Nevis Labor Party or SKNLP [Dr. Denzil Douglas]

Dr. Denzil Douglas has been the Prime Minister since 1995. The most recent elections were held in January 2010 and the next are expected in 2015. The Douglas administration has made economic development, the reduction of public debt, and crime prevention its priorities.

Geography/Physical Context

The dominant physical feature of St. Kitts and Nevis which influences the implementation of HighScope is the existence of the two islands and the policy differences that result from the distance.

Early Childhood Education/Pre-Primary Sector

Nevis

| Type of Preschool | Total Preschools | Males | Females | Total | % Female | % Male |
| --- | --- | --- | --- | --- | --- | --- |
| 2011-2012 |  |  |  |  |  |  |
|  |  | Boys | Girls | Total |  |  |
| Government | 4 | 79 | 87 | 166 |  |  |
| Private | 6 | 82 | 124 | 206 |  |  |
|  | 10 | 161 | 211 | 372 | 57% | 43% |
| 2012-2013 |  |  |  |  |  |  |
|  |  | Boys | Girls | Total |  |  |
| Government | 4 | 86 | 76 | 162 |  |  |
| Private | 6 | 83 | 107 | 190 |  |  |
|  | 10 | 169 | 183 | 352 | 52% | 48% |
| 2013-2014 |  |  |  |  |  |  |
|  |  | Boys | Girls | Total |  |  |
| Government | 4 | 103 | 81 | 184 |  |  |
| Private | 6 | 75 | 51 | 126 |  |  |
|  | 10 | 178 | 132 | 310 | 43% | 57% |

| Children 0-5 Enrolled in Early Learning Programmes in St. Kitts | 2011-2012 |  |  | 2012-2013 |  |  | 2013-2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Boys | Girls | Total | Boys | Girls | Total | Boys | Girls | Total |
|  | 1,367 | 1,343 | 2,710 | 1,574 | 1,431 | 3,005 | 1,699 | 1,568 | 3,267 |
|  | % Male | % Female |  | % Male | % Female |  | % Male | % Female |  |
|  | 50% | 50% |  | 52% | 48% |  | 52% | 48% |  |

How many schools are currently using the HighScope Curriculum?

In St Kitts, there are 36 preschools implementing the curriculum with the exception of one Montessori preschool.  In Nevis, 10 preschools are implementing the curriculum with the exception of the Montessori preschool.

Pre-Primary Enrollment Data from UNESCO

| Net enrolment rate, pre-primary, both sexes (%) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 64.0 | 72.0 | .. |
| Dominica | 76.7 | .. | .. | .. |
| Saint Kitts and Nevis | .. | 77.9 | .. | .. |
| Net enrolment rate, pre-primary, female (%) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 63.4 | 68.8 | .. |
| Dominica | 82.1 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Net enrolment rate, pre-primary, male (%) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 64.6 | 75.2 | .. |
| Dominica | 71.5 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Net enrolment rate, pre-primary, gender parity index (GPI) |  |  |  |  |
|  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda | .. | 0.98 | 0.92 | .. |
| Dominica | 1.15 | .. | .. | .. |
| Saint Kitts and Nevis | .. | .. | .. | .. |
| Data Source: UIS/ISU from http://data.uis.unesco.org/ |  |  |  |  |

| Gross enrolment ratio, pre-primary, both sexes (%) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 84.3 | 82.7 | 88.6 | .. |
| Dominica |  | 104.9 | 101.9 | 95.0 | .. |
| Saint Kitts and Nevis |  | 90.0 | 95.6 | .. | .. |
| Gross enrolment ratio, pre-primary, female (%) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 81.7 | 84.0 | 85.8 | .. |
| Dominica |  | 106.0 | 107.0 | 97.2 | .. |
| Saint Kitts and Nevis |  | 88.1 | 103.4 | .. | .. |
| Gross enrolment ratio, pre-primary, male (%) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 87.0 | 81.4 | 91.4 | .. |
| Dominica |  | 103.8 | 97.0 | 92.9 | .. |
| Saint Kitts and Nevis |  | 91.9 | 88.1 | .. | .. |
| Gross enrolment ratio, pre-primary, gender parity index (GPI) |  |  |  |  |  |
|  |  | 2010 | 2011 | 2012 | 2013 |
| Antigua and Barbuda |  | 0.94 | 1.03 | 0.94 | .. |
| Dominica |  | 1.02 | 1.10 | 1.05 | .. |
| Saint Kitts and Nevis |  | 0.96 | 1.17 | .. | .. |
| Data Source: UIS/ISU from http://data.uis.unesco.org/ |  |  |  |  |  |

Annex 2: 	Terms of Reference

TERMS OF REFERENCE: UNICEF Office for the Eastern Caribbean Area

| Position | Evaluator(s) – Evaluation of the HighScope Curriculum Programme |
| --- | --- |
| Duration | 4 months (1st September to 30th December 2013) |
| Grade | L3/L4 |
| Duty Station | Bridgetown, Barbados, Eastern Caribbean Area |
| Supervisor | Monitoring & Evaluation Specialist in Barbados. |
| Programme Component | PCR1 / IR1, as part of the 2013 IMEP and in support to the 2014 MTR |

- Background and Context

It is widely acknowledged that there are numerous weaknesses in early childhood systems in the Eastern Caribbean that impede the effective fulfilment of the Convention on the Rights of the Child (CRC) and national socio-economic advancement. One of these, is the curriculum. Efforts to address the weakness in this area began in 2004 with the development of the CARICOM Learning Outcomes for Early Childhood Development in the Caribbean: A Handbook for Practitioners. The regulations were developed by CARICOM Member States and early childhood specialists with the objective of standardizing quality holistic education across the region for the improved facilitation of the CARICOM Single Market Economy (CSME). The corresponding Curriculum Resource Guide encouraged reforming current adult-directed Caribbean preschool programmes to incorporate more child-centred and interactive practices.

The goal of the HighScope Curriculum Reform Programme is two-fold: (i) To improve the learning environments and quality of developmental and educational programmes in a total of thirteen preschool settings in Antigua and Barbuda, the Commonwealth of Dominica, Grenada, and St. Kitts and Nevis; and to subsequently showcase the participating centres as “models” in the use of a child-directed curriculum. (ii) These models would inform wider curriculum implementation plans and serve as teacher training demonstration sites for both the participating countries and for the greater Eastern Caribbean sub-region.

In 2006, the HighScope Curriculum Reform Programme was introduced with the objective of upgrading the learning environments of the 13 preschool settings by providing an adequate supply of learning materials to enhance the children’s developmental process and facilitate the training of the teachers in the use of a child-directed curriculum.   The programme was established through collaboration between UNICEF ECA and the four target countries and was funded by the Government of Italy under the larger “Capacity Building for Life Skills and Early Childhood Education” project. The HighScope Curriculum Reform Programme was one element of the umbrella project’s Early Childhood Education component, which also included initiatives for mainstreaming policy and creating a structured approach to early childhood programming. The project’s funding was obtained in 2006 and expired on December 31, 2008.

Whilst the Government of Italy’s participation in the HighScope Curriculum Model Programme concluded at the end of the 2008 calendar year, the programme continued with additional funds obtained by UNICEF ECA. The new funding provided the four target countries’ with the national capacities to expand and effectively sustain the use of the HighScope Preschool Curriculum. In July 2010, two Early Childhood representatives from each of the four countries were enrolled in High Scope’s Training of Trainers (TOT) certificate programme. Upon completion of the training, the participants became certified to teach and support other individuals in implementing and using the HighScope Preschool Curriculum. It is credible to note that a third practitioner from Antigua and Barbuda used her own resources to also become certified in the interactive approach.

The four countries participating in the HighScope Curriculum Reform Programme (Antigua & Barbuda, Grenada, St. Kitts and Nevis, and Dominica) are currently at different stages of acceptance and support for the model.

- Objectives of the Consultancy

UNICEF, as part of its programme policy, evaluates pilot programmes/projects, to learn lessons and make appropriate improvements before they are approved for adoption on a wider scope. A documentation of the results of this pilot programme will also go a long way in providing hard-evidence to support the advocacy and full-adoption in the model countries and other Caribbean countries.

An initial assessment of the evaluability of the programme, indicate that the baseline situations in the model countries and centres were properly documented through Programme Quality Assessments (PQAs) and detailed progress monitoring reports exist to support a credible evaluation. However, given the number of years during which the programme has been implemented (about four years), the focus will be more on the processes and outputs of the curriculum reform process, and learning lessons that will support a scale-up of the programme, rather than outcomes or impact.

As such, the objectives of this evaluation are as follows:

i - Asses the results achieved to date, identify the intended and any unintended results and bring all the evidence available to qualify and quantify the outputs (and if possible the outcomes) at the individual, household, school and community levels.

ii - Identify the opportunities and constraints the programme has faced and draw lessons and good and bad practices from them

iii -  Review the operational effectiveness of the pilot including cost of implementation

iv - Identify requirements and implications (institutional capacity, Maintaining HighScope Certified Trainer status, financial support etc.) for possible mainstreaming and implementing an interactive, child-centred curriculum on a national scale in the model countries and other Caribbean countries.

This formative evaluation is therefore being implemented based on the need of partners in the Ministry of Education in the model countries as well as UNICEF’s mandate. The evaluation will be adding value through the use of the findings and recommendations for: (a) evidence-informed advocacy for national Governments to adopt an interactive curriculum model based on this or other model, including models co-implemented with or borrowing the positive elements of the current programme (b) draw lessons that will help the success  of the current mainstreaming efforts,  and (c) documentation of the Caribbean experience in the adoption of the HighScope Curriculum and its positive outcomes for children.

- Major Duties and Responsibilities / Scope of Work

The evaluation will focus on the HighScope experience in two countries (St. Kitts & Nevis and Antigua & Barbuda) and focus on the following points:

- Relevance

- How relevant is the HighScope Curriculum Reform Programme, as part of the efforts of Governments, to improve access to ECD for all, to the learning environments and quality of educational programmes in the model countries?

- How appropriate have been the resources allocation and the monitoring system established in support of the implementation of the HighScope Curriculum Reform Programme?

- What current and possible additional prospects does the HighScope Curriculum Reform Programme offer to promote the development of the child’s personality, (talents and mental and physical abilities) to their fullest potential as specified in the convention on the Rights of the Child?

- What objections have arisen on the relevance of the HighScope Curriculum Reform programme? How were they dealt with? Are there any anecdotal or observable changes in the opinion or views of the stakeholders e.g. Ministry of Education (MoE)/ECD staff, parents etc

B.	 Effectiveness

- What is the progress made so far, towards achieving the initial planned outputs and outcomes? Has the programme been effective in influencing: (i) access to quality ECD; (ii) demand for ECD and (iii) change, development, holistic child growth and development?

- How are the children who have passed through the programme since 2009 performing in primary school?

- Were the activities, planned under the HighScope Curriculum Reform Programme, sufficient (in quantity and quality) to achieve the outputs?

- What is the stakeholders’ (both duty bearers and rights-holders) own perception and appreciation of the results of the HighScope Curriculum Reform Programme? What do they like or dislike? What do they want to change? What are the teachers and parents saying about the programme?

- What have been the major constraints in the implementation of the curriculum?

- What partnerships were or have been established to support the HighScope Curriculum Reform Programme implementation, and how adequate and effective have these been in facilitating the realization of its objectives?

- Has the external environment in any way affected the internal management of HighScope Curriculum Reform Programme? If yes, how?

- Are the originally identified assumptions still valid? Has the programme included strategies to reduce the impact of identified risks?

- Efficiency

- Are there any inefficiency issues with regards to how the programme is implemented or coordinated?

- How can one categorize the relationship between project costs and the results achieved?

- Have the synergies created among various providers’ services contributed to the overall efficiency of the program?

- How have the duty bearers and rights holders been interacting? Is there any potential efficiency gain to make?

- How does the program compare to other comparable initiatives?

- Have any measures been taken during the implementation of the project, to address cost/effectiveness issues? (any budget constraints?)

- Has the use of HighScope lessons learned from other countries helped reduced errors during implementation and helped deliver quality services, faster?

- Impact

- Were the selected indicators used to monitor the programme Specific, Measurable, Achievable and Relevant enough to determine the outputs and outcomes? Do they need to be revised?

- Has it been feasible to collect data on selected indicators?

- Are there any observed unintended direct or indirect results at the school level? At the household level (children, parents caregivers)?

- Is there any observable evidence of the contribution of the HighScope Curriculum Reform Programme to short, medium or long term Educational achievement/improvements in the selected children,  communities etc.? Is there any benefits to programme staff? What are the student grades saying?

- Is there any difference in the way the programme affects girls compared to boys? Based on socio-economic status, who is benefiting more? The poorest?  The richest?

- Sustainability

- What are the current strengths and weaknesses (design, coordination, management and monitoring) of the HighScope Curriculum Reform Programme and their capacity to contribute to or hinder the overall sustainability of the pilot programme or other curriculum reform programmes with a similar design?

- What has been the buy-in from the duty-bearers and rights-holders and what leadership or supportive roles have they played?

- What are the institutional capacity development efforts needed to ensure effective and efficient management, monitoring and evaluation of the HighScope Curriculum Reform Programme –in keeping with the established system?

- What type of monitoring and evaluation system should be established to support the rollout of the HighScope Curriculum Reform Programme on a national basis in the model or other countries e.g. required tools, training of staff, processes and procedures?

- Has parents involvement and support to the HighScope programme been considered as a way to ensure sustainability?

Methodology and Evaluation process

The Evaluation will be conducted in accordance with the evaluation principles (openness, transparency, participation, etc.) and standards using the usual Evaluation criteria (relevance, efficacy, effectiveness, impact, sustainability). It will also adopt an equity-focused approach to evaluation as defined by UNICEF guidance for Equity-focused Evaluations. This will require the consultant to closely work with the UNICEF M&E section at key phases of the evaluation process so as to ensure Equity focused Evaluation standards are fully met in the final evaluation report.

It is proposed that an Evaluation Reference Group made up of the Regional UNICEF M&E Adviser, the Chief of M&E and PME specialist in UNICEF Barbados, the Permanent Secretaries and Chief Education Officers in the Ministry of Education in St. Kitts & Nevis, Antigua & Barbuda and Dominica, be established.

Given its nature and the information it seeks, it is proposed that a mix of the following methodologies be adopted, subject to discussion with the consultant of choice and stakeholders:

| Methodology | Data sources |
| --- | --- |
| 1. Desk review of key documents and reports | -Project proposals, Monitoring reports, Baseline reports etc. from MoE |
| 2.In-depth interviews with key informants (rights-holders and duty-bearers) | -Project staff, Parents/Caregivers, Families in St. Kitts & Nevis and Antigua & Barbuda -Policy/decision makers in MoE, -UNICEF, HighScope |
| 3.Focus group discussions with rights-holders | -Parents/caregivers, Community members |
| 4.School-based surveys in a representative sample of model centres in St. Kitts & Nevis and Antigua & Barbuda and Dominica covering the target group of children and the control group | -Parents/caregivers and families in St. Kitts & Nevis and Antigua & Barbuda and Dominica |
| 5.Review of the operational cost for the pilot and what it means in case of scaling up | -Project document including budgets, Monitoring reports, Current expenditures |

Stakeholder participation both on the side of the duty bearer (Early Childhood Education officials, teachers, parents, caregivers etc.) and on the side of the rights-holder (parents, caregivers, children? Etc.) will be fundamental in this evaluation. Therefore, stakeholders’ participation will be an integral component of evaluation design, planning and conduct (information collection, development of findings, evaluation reporting, results dissemination, etc.) The Evaluation is estimated to cover 16 weeks, from 1st July to 31st October, 2013.

- Deliverables

The Consultant will prepare:

| # | Deliverable | Proposed Completion Timeline | Payment | Estimated Person-days |
| --- | --- | --- | --- | --- |
| 1 | A detailed draft evaluation work plan (with questionnaires, etc.) within 2 weeks of the signing of the contract | September 10th | 10% | To be defined from the technical proposal received |
| 2 | A final evaluation work plan within one (1) week of receiving UNICEF, HighScope Educational research Foundation and Ministry of Education’s comments on the draft work plan | Latest September 20th | 20% | To be defined from the technical proposal received |
| 3 | Interim report presenting progress and initial findings from the evaluation/field work | Latest October 20th | 20% | To be defined from the technical proposal received |
| 4 | A draft evaluation report 3 weeks before the end of the consultancy, in accordance with standards identified in the UNICEF/UNEG Evaluation Policy/Guidance.) | Around November 30th | 30% | To be defined from the technical proposal received |
| 5 | A final evaluation report (with a complete executive summary) that meets UNICEF standards for good evaluation reports within two (2) weeks of receiving UNICEF’s, HighScope Educational research Foundation and Ministry of Education’s comments on the draft report. Two PowerPoint presentations (one for stakeholders and one for policy makers) will also be submitted as part of the final deliverables. A presentation to key stakeholders (exit meeting at the end of the consultancy work) | Around December 15th Around December. 27th | 20% | To be defined from the technical proposal received |

The consultant will regularly report to the technical committee comprising the staff from UNICEF (M&E unit), the HighScope Educational Research Foundation and Ministry of Education in in St. Kitts & Nevis and Antigua & Barbuda and Dominica. This will be an opportunity to provide updates, discuss constraints and if needed, obtain the additional support needed to complete the work with the expected quality and in a timely manner.

- Competencies

The evaluation will be carried out by an experienced consultant/consulting firm who is expected to have in its employment persons with skills in Evaluation, together with personal and professional ethics and integrity, and basic skills in human rights and gender equality analysis.

- Qualifications

- Education: Master’s degree in Early Childhood or Development, Education. A good understanding of the education sector as well as policy, gender and children’s issues.

- Experience: Minimum eight (8) years of relevant experience. A proven record in education or social science research, or Evaluation. Experience producing high quality evaluation reports on time

- Strong analytical skills.  Demonstrable capacity to apply UNICEF Evaluation standards, Human-rights, Result-based Management, Gender and equality principles. Knowledge of international evaluation guidelines and quality standards.

- Languages: Fluency in English is required (both written and oral) with excellent writing skills.

- Duration:  1st September  to December 30th, 2013  (4 months)

- Official Travel / Work Arrangement

The consultant/consulting team, depending on whether they are based in Barbados or outside Barbados, will work in collaboration with UNICEF and its Government partners. They will be required to travel for consultations in St. Kitts & Nevis, Antigua & Barbuda and Dominica, in the process of data collection/verification and in sharing preliminary or final results with the various stakeholders. Details of travel itinerary and costs should be included in the technical and financial proposals.

- Proposal

Interested individual and firms will be expected to submit a technical and financial proposal.

- Payment schedule: Payments in check or bank transfer, will be made based on the satisfactory and timely submission of deliverables identified in (5.) above

- Conditions of Service

Prior to commencing the contract, the following conditions must be met:

A Corporate Entity will be required to submit samples of previous relevant work, a Certificate of Incorporation for the Company as well as a profile of the individual(s) who would be undertaking the assignment.

An Individual Consultant will be required to submit samples of previous relevant work, a statement of good health, accompanied by a recent Medical Certificate which indicates that the Consultant is fit for work and travel.  In addition, the Consultant is required to certify in the Health Statement that he/she is covered by medical/health insurance. The statement includes confirmation that he/she has been informed of any inoculation required for the country or countries to which travel is authorized. He/she takes full responsibility for the accuracy of the statement.

- Recourse

UNICEF reserves the right to withhold all or a portion of payment if performance is unsatisfactory, if work/outputs is incomplete, not delivered or for failure to meet deadlines. Performance indicators against which the satisfactory conclusion of this contract will be assessed include: timeliness/quality of submission and responsiveness to UNICEF and counterpart feedback.

- Property Rights

UNICEF shall hold all property rights, such as copyright, patents and registered trademarks, on matter directly related to, or derived from, the work carried out through this contract with UNICEF.

- How to apply

Proposals should be sent by e-mail to bridgetown@unicef.org with a copy to ainniss@unicef.org  no later than Friday 23rd August, 2013, indicating “Evaluation of HighScope Curriculum Programme” in the subject line of the email. The proposal package should include the following:

- A cover letter

- A detailed curriculum vitae or background of the corporate entity in English

- A duly completed United Nations Personal  History form  (p11) for individual contractors

- A technical proposal explaining the methodological approach to achieving the results of this consultancy

- A financial proposal or expected cost, with a detailed budget (including travel and DSA, if required)

Proposals may also be sent to:

Representative

UNICEF Office for the Eastern Caribbean Area

1st floor, UN House

Marine Gardens

Christ Church

BARBADOS

ONLY SUITABLE PROPOSALS WILL BE ACKNOWLEDGED

Annex 3: 	Methodology

This part presents the overall methodology used for this evaluation.  In compliance with the UNEG Evaluation and Global Evaluation Reports Oversight System (GEROS) standards, this part of the report presents the following:

- The purpose and objectives of the formative evaluation.  The section elaborates on how this evaluation fits into the UNICEF ECA Country 2012-2016 programme cycle;

- The Organization for Economic Cooperation and Development (OECD)- Development Assistance Committee(DAC) evaluation criteria used;

- Site (and subsequently stakeholder) sampling;

- Information sources, including the use of monitoring data;

- Data collection methods;

- Evaluation phases and schedule;

- The extent of stakeholder participation and role(s);

- Assessing Data Quality;

- The incorporation of the United Nations (UN)/UNICEF’s frameworks into the formative evaluation design and analysis (i.e., human rights-based approach to programming (HRBAP), human rights frameworks, CRC, United Nations Committee on the Elimination of Discrimination against Women (CEDAW), Convention on the Rights of Persons with Disabilities (CRCD), and equity-focused evaluation);

- Ethical safeguards used; and

- A transparent discussion of the formative evaluation limitations.

3.0	The Purpose of the Formative Evaluation

As the participating countries are currently embracing HighScope in their own unique way, UNICEF planned the opportunity to learn and draw lessons from this pilot intervention.  First, UNICEF has a policy for evaluating programmes and projects in order “to support planning and decision-making, and to provide a basis for informed advocacy–aimed at promoting the well-being of all children, everywhere.”    Second, the results of this formative evaluation are intended to support a child-centred, interactive curriculum, of which the HighScope Curriculum is an example.    Finally, in line with this Evaluation Policy, a formative evaluation was commissioned for several purposes, specifically:

- A comprehensive documentation of the results of this programme will offer hard evidence to support advocacy for HighScope’s full-adaptation in the model countries, and possibly in other Caribbean countries; and

- Based on the results, the evaluation will provide lessons which may help the success of the current mainstreaming effort.

Finally, this evaluation contributes to efforts outlined in the UNICEF Eastern Caribbean Multi-Country Programme Action Plan: 2012 – 2016.  Currently, the key priorities are to provision evidence for policy-level decision-making in the areas of ECD, gender equality, and strengthening administrative data collection in the education sector.

3.1	Formative Evaluation Objectives and Approach

The formative evaluation concentrates on how and how well the programme is being implemented; it describes how the programme operates, the services it delivers, and the current benefits of these services.  Based on Terms of Reference, the objectives of this evaluation are to:

- Assess the [programme] results achieved to date and identify the intended and any unintended results.

- Identify the opportunities and constraints the programme has faced and draw lessons and good and bad practices from them.

- Review the operational effectiveness of the pilot, including cost of implementation.

- Identify requirements and implications (notably institutional capacity, maintaining HighScope Certified Trainer status, financial support) for possible mainstreaming and implementing an interactive, child-centered curriculum on a national scale in the model countries and other Caribbean countries.

The approach used throughout this evaluation effort is participatory, consultative, and focused on understanding what is valued by all key stakeholders.  This approach is consistent with a formative evaluation.  Other characteristics of this type of evaluation approach include: (1) involving a range of participants to share their views during the process, (2) understanding the overlapping realities of those implementing early childhood development initiatives in the Caribbean, and (3) encouraging stakeholders to proactively engage in identifying sustainable solutions and recommendations.  The variation of data sources is intended to capture the diversity of perspectives and to support data credibility and accuracy.

3.2	OECD-DAC Evaluation Criteria

Figure 1: OECD DAC Evaluation Criteria

The evaluation team addressed 30 questions from the Terms of Reference (see annex 2), which are all categorised under the five standardized evaluation criteria recognised by the OECD, namely relevance, effectiveness, efficiency, sustainability, and to a limited extent impact (see figure).  The key evaluation questions falling under each criteria are integrated within the findings section.

This evaluation is focused on learning, taking into consideration contextual factors, and sharing what is considered most important according to key programme stakeholders. The OECD-DAC criteria, however, represent a framework for an evaluation of scaled, fully implemented development assistance programmes and not for pilot-scale programmes, such as the HighScope Curriculum Reform Programme.  Hence, it is for this reason that questions related to Impact cannot be answered with specificity.  The other OECD-DAC evaluation criteria, Coverage, Connectedness, and Coherence, are designed to enhance the quality of the evaluation of humanitarian action, and are therefore not appropriate to this evaluation context.

3.3	Methodology

3.3.1	Sampling and Time Period Parameters

In three of the four participating countries, the sampling frame for the model learning centres is 10.  The stakeholder sampling rationale includes those who were directly involved in the delivery of the HighScope Curriculum (e.g., school-level stakeholders) as well as the network of actors indirectly supporting overall programme implementation (e.g., Ministry of Education senior officials, UNICEF, HighScope Educational Foundation, and UNICEF).   This evaluation only covers the five-year period from 2008 to 2012 when UNICEF invested in HighScope Curriculum Reform Programme.

It should be recognized, however, that the original situation since 2008 has changed significantly.    Namely, in 2007, each participating country agreed to implement the HighScope Curriculum  in three “model” learning centres with the intention of “inform[ing] wider curriculum implementation plans and serv[ing] as teacher training demonstration sites for both the participating countries and for the greater Eastern Caribbean sub-region.” The stakeholders from each participating country drew attention to the fact that the HighScope Curriculum  had already been replicated extensively in other learning centres.  In light of this development, it not only became necessary to understand the adaptation of the HighScope model within each participating country‘s context, but also its evolution since 2008.

Given the evolution of HighScope in each participating country, the evaluation team agreed to “visit” one or two non-model learning centres, where the HighScope Curriculum  had been newly implemented, in addition to the ten model centres.  With a time constraint during data collection, the data from these supplemental “visits” is not comprehensive.  The “visits” mainly included brief interviews with the Head Teacher/Supervisor, and to some extent, photographs taken of the premises.  The evaluation team did not conduct any observations or ask teachers to fill out any surveys.   Any relevant data was used to substantiate findings from the ten model learning centres.

3.3.2	Data Sources

The data sources came from a mixture of stakeholders, including:

- Children who had experienced the programme;

- Children currently in the programme;

- Parents whose children had experienced the programme;

- Parents whose children were currently in the programme;

- Early childhood educators from model learning centres;

- Early childhood educators at the kindergarten level;

- Primary school principals and early childhood educators at the primary school levels in Dominica only;

- The Ministry of Education senior level personnel;

- The Ministry of Education ECD Unit personnel;

- UNICEF personnel; and

- HighScope Educational Foundation staff.

Similarly, the data sources consisted of:

- Document reviews HighScope-related materials, including scholarly articles written about HighScope, and HighScope training, including video, materials;

- Basic records on student attendance and disaggregated data of pupils from 2008 through 2013;

- Learning centre income;

- Learning centre expenses;

- Teacher survey data; and

- Previously undertaken studies, including but not limited to the Costing Study, UNESCO, and UNICEF Multi-Indicator Cluster Surveys (MICS).

The evaluation also made use of the monitoring data (statistics) routinely collected and stored in databases maintained by the Ministry of Education, ECD Units in each participating country.  The tools used to garner (learning centre-level) performance data at different levels are fully described in the effectiveness section of this report.

3.3.3	Data Collection Methods

As part of the mixed methods evaluation design, quantitative methods were limited to surveys of early childhood educators and supervisor and from six Training of Trainers (ToTs) who took part in the training certificate programme.  An instrument was used to collect systematically learning centre enrolment, staffing, income, and expenses.   As ten model learning centres constituted the entire sample, the key elements of the instruments were:

- The number of children enrolled (disaggregated by gender);

- The number of teachers working at each learning centre;

- Teacher demographic information (e.g., their age, educational background, number of years’ experience teaching, and gender);

- Frequency of use of the HighScope materials and coaching support received;

- School fee rates;

- Available budget data that illustrated the expenditures for programme implementation (books, teaching / learning materials, school building maintenance, teacher and administrators salaries, meal services provided, student transportation provided, communications, and any other training received); and

- Infrastructure characteristics of each preschool setting.

The qualitative data presented in this report was collected from interviews with key stakeholders, classroom observations and focus group discussions. The data collection instruments, including question guides for different stakeholder groups, focus guides for parents, observation checklists, educator surveys, and ToT surveys may be found in annex 8.

3.4	Evaluation Phases and Schedule

A mixed methods evaluation design was used in this evaluation and carried out in three phases: (1) Desk and Definition Phase; (2) Field Phase; and (3) Production Phase.  Figure 2 details the different phases and indicates the precise methodologies used as well as the timing of stakeholder consultations.

Figure 2: Formative Evaluation Methodology

3.4.1	Desk and Definition Phase

The first phase of the evaluation involved an extensive review of programme documents, including HighScope materials purchased from the website.  Annex 6 presents the list of major documents consulted.  The inception report followed an Evaluation Plan Matrix that UNICEF provided to the Manitou, Inc. evaluation team of two females.  This Evaluation Plan Matrix enabled those who wished to follow the overall evaluation process to do so without getting too concerned with small details.  The Evaluation Plan Matrix for the HighScope Curriculum Reform Programme is located in annex 5 of this document.

Given that the formative evaluation process is focused on understanding and sharing, it was intended for the degree of stakeholder participation in the evaluation process would be inclusive and robust.  Stakeholders from the school-level to the senior officials within the Ministries of Education were present at a stakeholder meeting.  The inception report was shared with all stakeholders, and three meetings were held, one in each participating country, providing the education sector stakeholders (from teachers to principals to senior officials from the Ministry of Education) the opportunity to voice their concerns about and offer feedback on the evaluation scope and process. This consultation resulted in a five-week delay in the launch of the field phase.  The evaluation Team Leader participated via Skype.

The preparation of instruments for the field phase took into consideration the elements that the HighScope Educational Foundation encourages, including in all assessments of HighScope.  Further, Manitou, Inc.'s Child Development and Education Expert, Dr. Jennifer Greene, conducted a detailed review and provided insightful, significant feedback on all instruments.  Once revised, instruments were shared with UNICEF and all of the education sector stakeholders for their review and feedback.

3.4.2	Field Phase

Primary data sources collected during the second phase included the collection of primary data elaborated in the Data Sources Section.  In line with the UNEG guidelines, the Manitou, Inc. evaluation team consistently consulted a wide range of parents, among others who benefitted from the intervention, including grandparents and the parents of children with special needs.  Open discussions with teachers and Head Teachers/Supervisors about working with children with disabilities were encouraged throughout the evaluation.  The deliberate steps taken to ensuring data quality during the field phase was including the evaluators consulting the ECD Unit staff about the best and most culturally appropriate measures to take to ensure strong credibility and data quality.

Finally, interviews with the HighScope Foundation stakeholders and relevant UNICEF staff were strategically undertaken at the end of the data collection phase.  The HighScope Foundation stakeholders had unique perspectives about the HighScope adaptation process from the onset, as their Early Childhood Specialist and Trainer(s) provided technical assistance to several officers in the ECD Units within country Ministries of Education.  These stakeholders were consulted to confirm background information but also to elicit their support in data interpretation, specifically in authenticating what could be considered an adaptation to the HighScope Curriculum .  Interviews with the UNICEF stakeholders focused on documenting overall trends in curricula in early childhood development within the Caribbean region and verifying the extent of funding invested in the programme since 2008.  Annex 7 has the list of stakeholders.

3.4.3	Production Phase

The final phase included data analysis from all of the instruments used (see text box).  Annex 8 presents samples of the different forms used.  A systematic content analysis was undertaken of data from each stakeholder group, including: (1) classroom observations, (2) focus group discussions with parents, (3) teacher perceptions about the HighScope Curriculum  and working with children/parents, (4) Head Teacher/Supervisor’s general perspectives about delivering HighScope and working with the parent community, (5) the ideas from the ECD Unit (from each participating country) about sustaining the current efforts, and (6) strategic reflections from senior officials from

Data Collection Instruments Used

- A semi-structured Interview Guide for Ministry of Education Stakeholders.

- A Classroom Observation Guide.

- A Parent - Focus Group Discussion Guide.

- A Teacher Questionnaire.  This instrument also includes a set of questions about their background in teaching.

- A Teacher single semi-structured Interview Guide.

- A Head Teacher or Supervisor Questionnaire.

- The School Building and Administration Questionnaire. - This instrument is sub-divided into four parts:

- The indoor and outdoor infrastructure of the setting;

- The enrollment and admissions statistics and procedures;

- The costs and the income to support operations; and

- The monitoring and evaluation system.

the Ministry of Education about mainstreaming HighScope and what it would look like 20 years ahead.  Qualitative data analysis also involved triangulating data sources from interviews and observations, and this process was iterative.  Ultimately, emergent themes were identified and then key patterns or ideas were validated.

Quantitative data analysis included: (1) the assessment of frequency values for the effective use of HighScope materials and coaching support that teachers received; (2) the assessment of frequency values for the training that TOT’s provided; (3) calculations of teacher demographics; (4) in-depth reviews of financial and student enrollment data, which are intended to determine the true costs of delivering the HighScope Curriculum; and (5) a summary of country – level education sector statistics.  Such analyses highlight the degree to which the capacities of duty bearers (ToTs and Teachers) and other key players have been sufficiently strengthened in order to fulfil their obligations and responsibilities.

Qualitative interview and observation data were summarized into one document, and standard qualitative data analysis techniques of content analysis and clustering of responses took place.  The approach to data interpretation may best be characterised as inclusive at every stage.

When the draft report was completed, all stakeholders had access to the document and were asked formally to provide comments and feedback.  This information was considered and integrated into the finalised document submitted to UNICEF.  The close of the evaluation process included the Manitou, Inc. evaluation team, provided a final formal presentation of the evaluation findings to key stakeholders.  Three meetings were held, one in each participating country with the education sector stakeholders (from teachers to principals to senior officials from the Ministry of Education), and the intent was to:

- receive a confirmation of the findings;

- provide an agreement with the proposed recommendation; and

- develop action items for recommendations implementation, including who is responsible for implementing the recommendation and the time allotted to completing the recommendation.

The result of these evaluation activities was a written response, or a Management Response, to the evaluation findings and an articulated planning document which includes future steps.  The preliminary document is located in annex 4.

3.5	Stakeholder Participation in the Evaluation

As evidenced, stakeholder groups at every level were included in the evaluation and consulted at the Desk and Production phase, Field phase, and at the Production phase.   Not only did programme stakeholders facilitate communication between the evaluation team and the learning centres, but also they shared country-level data with the evaluation team.  Prior to returning to Manitou, Inc.’s headquarters in New York, the evaluation team debriefed participating ECD Unit staff and informed them of expected next steps within the evaluation process.  Stakeholder involvement in the evaluation process was purposefully planned to facilitate buy-in and to sustain future efforts.

During the stakeholder meetings, an introductory-level orientation was delivered on the following topics:

- Evaluation: “What is evaluation?”; “Why evaluate?”, “What can be expected from evaluations?”

- UNICEF Frameworks: Rights-Based Programming Approaches and Equity-focused evaluation methods.

However, additional stakeholder participation substantiated efforts and further strengthened stakeholder capacity in programme evaluation and in data analytical frameworks would have been made.  Due to budget constraints, it was not feasible to allocate more time than originally planned.

3.6	Assessing Data Quality

Bias limitations were effectively restricted with:

- The presence of and support from the UNICEF personnel facilitating access to all key stakeholder groups;

- The presence of school-level stakeholders throughout the data collection process;

- Conventional interviewing techniques, where at the close of every interview, the evaluators systematically summarized key points with the respondent to verify what was discussed;

- Triangulation; and

- The presence of school-level stakeholders during the final presentation meetings.

All such stakeholder involvement contributes to other evaluation criteria used as benchmarks for assessing the soundness of methodologies and best practices.  They include “Credibility, or the confidence in the 'truth' of the findings; Dependability, or showing that the findings are consistent and could be repeated; and Confirmability, or the extent to which the findings of a study are shaped by the respondents”.

3.7	Incorporation of UN Frameworks

Throughout every stage of the evaluation process (from design to data analysis and reporting) the evaluation team integrated HRBAP, equity concerns, and gender equality.  During the Desk and Definition phase, a specific instrument, the Formative Evaluation Plan Matrix, was used to identify precisely: (1) how gender equality and the equity concerns would be explored; and (2) the relevant duty-bearers and rights holders, to provide the relevant information.  The evaluation methodology, from sampling to data collection procedures, reflects the key principles of: (1) inclusion; (2) participation; and (3) observance of power relations.

Data interpretation includes a review of the evidence through an equity lens, examining how the HighScope Curriculum  benefits all children, and especially disadvantaged and children and children with disabilities.    The findings are presented with an equity focus, using human-rights language, including the extent to which:

- The implementation of the HighScope Curriculum reflects the CRC, CEDAW conventions, the CRPD, equity-focus, among other internationally-agreed instruments.

- Gaps exist in the ToC, where: (1) rights holders (teachers) are not in a position to fully claim their rights; and (2) duty bearers (parents) are fulfilling their responsibilities.

- The issue of equity and costs must be considered in order to deliver an efficient ECD service;

- Duty bearers (teachers), being at the forefront of service delivery, are in need of training in the area(s) of how to deal with children with disabilities; and

- The child assessment systems require dimensions in measuring student outcomes for all children.

The extent to which how the HighScope Curriculum was accessed by boys and girls and how it affected them was also assessed.  Finally, all enrollment information is also disaggregating by gender and year of enrollment.

3.8	Ethical Safeguards

The underlying rationale for protecting programme participants, especially children, is that evaluations can potentially negatively affect the interests of some stakeholders.  As a result of participating in the evaluation, it is possible that unforeseen risks or burdens may fall on the participating stakeholders.  However, with the proper protocols in place(e.g., confidentiality and informed consent), the evaluation team effectively engaged in standard ethical safeguards which are in keeping with conventional evaluation practices within educational settings.  These safeguards and policies included:

- Evaluators issued the confidentiality clause prior to conducting all interviews and explained that no individual would be singled out or quoted and that instead their information would be compiled with information from others. That an individual’s comments would not be able to be identified and tied back to that person so they should feel free to speak freely.

- All documents which asked for enrollment and financial information were marked as Confidential.  The learning centre cost and expenditure information was respected.

- All parents were requested to sign a “permission slip” in order for their child(ren) to participate in any observation or appear in any video or photographs. (Please see annex 8 for a copy of the permission slip used).  The informed consent was returned before the evaluators arrived at the preschool for data collection.  The children whose parents noted on the permission slip that they “did not agree” were not included in observations, videos, or photographs.  These precautionary steps were taken as protection for dignity and welfare of children and parents.

3.9.	Limitations

The limitations during the data collection process are provided in a transparent discussion below:

- Institutional memory is limited, which was beyond the control of the evaluation team.  It was therefore not feasible to:

    - Review if UNICEF managed or adjusted the programme according to human rights and gender monitoring of monitoring processes; and

    - Address the GEROS standard of how ethical the initial design of the programme was and the balance of costs and benefits to participants.

- In Dominica, Chickungunya prevented access to the children and teachers.   In all of the observed centres, only half of the children were present, thereby altering the context in which the HighScope Curriculum  was delivered.   This limitation was unforeseen and beyond the evaluation team’s control.

- There is only data from parents who are active in their children’s lives and responsive to their children’s educational needs.  The parent focus group discussions (FGDs) were voluntary, and the parents who attended and contributed data were self-selected.  Those who were comparably less active and responsive were least likely to participate in parent FGDs, and so their input and voices are absent from the database.

    - This limitation was unexpected.  However, this limitation could have been minimized with additional time scheduled in each participating country (see the next limitation for further explanation).

- While collecting the data, the time frame within each participating country was limited due to budget restrictions, The implication is that the information gathered therefore represents “snapshots” of how the programme was implemented.

      - While this limitation could have been addressed with a larger evaluation budget dedicated to travel and lodging, one of the challenges of undertaking evaluation work in the Caribbean is the high costs of travel, lodging, and meals.  The region is a vacation destination, and so there are very few amenities for social service-related business travel.

- The data collected may be subjected to “social desirability,” where programme stakeholders (excluding the children) may have presented their best rather than their usual behavior.  For example, each learning centre was aware of the day the evaluation team was  coming.

- Only limited financial data from schools and monitoring data on the schools from the Ministry of Education was available.  This limitation was unforeseen and beyond the evaluation team’s control.

- The two evaluators were cultural outsiders, so may they could not have fully understand all of the inter-island and cultural innuendos that took place the way evaluators from the Caribbean region would have.

- There was no attempt to construct a counterfactual or contribution/attribution analysis, because such an analysis would not have been applicable to this evaluation context.

Annex 4:	Stakeholder Feedback on Recommendations By Country

Country: Antigua and Barbuda

| Stakeholder Feedback on Recommendations by Country | Agree / Disagree Not Applicable | Action to Be Taken | Person(s) or Department(s) Responsible |  | Timeframe | Additional Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Recommendation 1a | The Government of Antigua and Barbuda and Barbuda should prioritize the drafting of legislation to render the Standards for the Regulation of Early Childhood Services in Antigua and Barbuda (under the Education Act) into law within 12 months. Rendering “The Standards” into law would ensure that all services for children are consistent and would also effectively support the expansion of the HighScope Preschool Curriculum. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Standards for the Regulation of Early Childhood Services in Antigua and Barbuda and Barbuda (under the Education Act) should be reviewed first, because so much time has passed since the Standards were established. After the review, the next step would be for the language to be drafted into legal language so that it can be officially gazetted. | Ministry of Education, Chief Education Officer, Legal Affairs, Cabinet |  | Next 6 to 12 months | There was broad agreement on this recommendation across the stakeholders. It was agreed that the drafting of the needed legislative language for Standards for the Regulation of Early Childhood Services in Antigua and Barbuda and Barbuda (under the Education Act) should happen as quickly as possible. One group disagreed partially. The point was that at this point The Standards having been waiting so long that an intervening step should be to review them first. This same group pointed out that grassroots advocacy and support for this process would help prevent the Ministry of Education from stalling or running out of steam. |  |
| Recommendation 1b | The Commonwealth of Dominica should continue with current plans and efforts to finalise a document to outline and standardize the government’s contribution to early childhood learning centres and shift that a guidance document into policy language effective immediately. |  |  |  |  |  |  |
| Antigua and Barbuda | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable |  |
| Recommendation 2 | The Government of Antigua and Barbuda and St. Kitts and Nevis should establish a succession plan to fill upcoming vacancies created from retiring Early Childhood Unit staff by 2015. Establishing a succession plan would ensure that sufficient and adequate human resources are available to effectively support the continuation and expansion of the HighScope Curriculum. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | They agreed that in-service training should be on-going to prepare a new Early Childhood Development Unit staff. Specifically the formal succession process to replace the Early Childhood Unit head should start at least 6 months before Mrs. Earla Musgrave-Esdaille retires and should include shadowing before full employment. |  | Ministry of Education, Supervisor of retiree | Should begin 6 to 8 months before retirement date | The stakeholders also noted the importance of potential replacements within the Early Childhood Development Unit or the Ministry of Education being trained on an on-going basis, so that the new staff are prepared to replace retirees. |  |
| Recommendation 3 | The Commonwealth of Dominica should continue with current plans and efforts to reinforce the current Early Childhood Unit with additional officers who are entrusted with supporting the implementation and expansion of the HighScope Curriculum, among other obligations, including monitoring. |  |  |  |  |  |  |
| Antigua and Barbuda | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable |  | Not Applicable |
| Recommendation 4 | The Ministry of Education’s Early Childhood Units in all countries should use the HighScope Programme Quality Assessment (PQA) at least once annually, starting in 2015. The use of PQA would effectively highlight areas for improvement and document progress, supporting the research-based, quality monitoring as well as expansion efforts. |  |  |  |  |  |  |
| Antigua and Barbuda | Partial agreement (Agree for all early learning centres currently implementing the HighScope Curriculum) | The administration of the Programme Quality Assessment system should take place at least one time per year in each learning centre. Administrating the instrument two times per academic year would be ideal. | Early Childhood Development Unit |  | 2 times per year, at the beginning and at the end of the academic year starting for the September 2015 academic year. | There was not 100% agreement on this point. Those stakeholder groups that agreed said that yes the Programme Quality Assessment system should be used` two times per year. One stakeholder group, pointed out that this step cannot be taken until “The Standards” are fully gazetted and functional. In addition, stakeholders pointed out that it is not fair to use the Programme Quality Assessment on the private preschools not using HighScope curriculum because it is not applicable to their current programmes. |  |
| Recommendation 5 | The Ministry of Education in all countries should deliver more practical training in adult – child interactions in particular within the next 12 months (in 2015). Training would strengthen the implementation of the HighScope Curriculum. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Could take the form of in-service training. | Early Childhood Development Unit Staff to deliver training |  | Over the next 12 months | None. |  |
| Recommendation 6 | The Ministry of Education in Antigua and Barbuda and the Commonwealth of Dominica should continue with planned efforts to provide training in the area of conflict resolution. The Ministry of Education in St. Kitts and Nevis should provide “further training” in conflict resolution in 2015. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Provision of training in conflict resolution. | Early Childhood Unit |  | On-going | None. |  |
| Recommendation 7 | The Ministry of Education in all countries should invest resources into teacher training in the areas of dealing with children with disabilities (i.e., learning, behavioral and emotional, social, physical disabilities, and visual and hearing impairments). This input would strengthen the equity focus in the delivery of the HighScope Curriculum. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Provision of supplemental training to early childhood educators teachers in the area(s) of special needs of children with disabilities. | Ministry of Education, with support from UNICEF |  | September 2015 for additional training for teachers, and afterwards on-going | As of the last term of the 2013-2014 school year there is one special needs specialist attached to Early Childhood Unit who provides support to both public and private preschools intermittently. The specialist is part of the Special Needs Unit within the Ministry of Education that provides support to all early learning centres and schools. It was also pointed out that there is no infrastructure in place in government schools for physically handicapped children |  |
| Recommendation #8 | The Ministry of Education in all countries should consider alternate fee strategies which support both efficiency and equity, facilitating access to the most vulnerable families. This change would effectively ensure that the teachers in the private sector receive payment for services delivered. The different rates should take effect before the 2015-2016 academic year. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Despite agreement on this recommendation in principle, there were mixed opinions about the actions needed to address this recommendation (see Additional Comments). | Ministry of Education and Ministry of Social Transformation |  | Begin from September 2015 | There was not uniform agreement on the actions for this recommendation. Instead the stakeholders present offered a range of solutions including: (1) paying salaries for private sector teachers; (2) supporting low income students directly through payment of school fees; or (3) providing the schools with direct support (such as rent and utility costs). One group mentioned that private schools using the HighScope Curriculum could receive an added incentive from the government to support access for low income kids. This would be done in cooperation with the Ministry of Social Transformation. |  |
| Recommendation 9 | The Ministry of Education in all the participating countries should continue as planned with the implementation of the training area of Child Assessment. A robust monitoring and evaluation system, a culture of results-based management and practical skills in Monitoring & Evaluation, are key to identifying children’s accomplishments and future development needs. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Implementation of training in the area of child assessment. | Supervisors, Early Childhood Unit, Planning Unit of the Ministry of Education |  | From January 2015 | None. |  |
| Recommendation #10 | The ministries of education should institutionalise a formal, systematic assessment process, such as the use of the COR, without delay. In the absence of assessment practices, the Training of Trainers are likely to need of supplemental training. Though there are multiple on-line courses available in using and instituting the Child Observation Record (COR) system, it may be more cost-efficient to work with the HighScope Foundation staff to deliver the training directly to multiple stakeholders at the same time. Should the Ministries of Education in participating countries wish to explore the use of the COR as their robust assessment system, UNICEF should provide support through the technical assistance. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Further actions are needed to integrate the Child Observation Record (COR) system through the Training of Trainers system. | Ministry of Education, Early Childhood Unit, Teacher Training Department, UNICEF and the HighScope Research Foundation |  | January 2015 and on-going afterward. | The following efforts were mentioned for action to consider in the future: (1) Full and part time scholarships for teachers, (2) professional development training for private and public sector teacher possibly in the form of a professional development day (this might be difficult for private schools). (3) Training of Trainers to create a broader base of trained people. |  |
| Recommendation #11 | Putting into practice a formal and comprehensive child assessment system, which enables parents and teachers to identify, work on, and document children’s learning and development would be an effective and efficient management system for tracking student achievement and progress. The Ministry of Education in all the participating countries should develop a tracking system starting from the level of ECD. The system would be used for HighScope Curriculum “roll out” and “scaling up”. |  |  |  |  |  |  |
| Antigua and Barbuda | Agree | Despite agreement on this recommendation in principle, there were mixed opinions about the actions needed to address this recommendation. | Teachers, Ministry of Education (specifically Department of Measurement and Evaluation within Ministry of Education) Early Childhood Unit, HighScope Foundation, UNICEF |  | September 2015 | Whole-hearted agreement. There is a need for a holistic system to track the preschool students from preschool through secondary school. |  |

Country: St. Kitts and Nevis

| Stakeholder Feedback on Recommendations by Country | Agree / Disagree Not Applicable | Action to Be Taken | Person(s) or Department(s) Responsible |  | Timeframe | Additional Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Recommendation 1a | The Government of Antigua and Barbuda and Barbuda should prioritize the drafting of legislation to render the Standards for the Regulation of Early Childhood Services in Antigua and Barbuda (under the Education Act) into law within 12 months. Rendering “The Standards” into law would ensure that all services for children are consistent and would also effectively support the expansion of the HighScope Preschool Curriculum. |  |  |  |  |  |  |
| St. Kitts and Nevis | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | The stakeholders in St. Kitts and Nevis pointed out that the “White Paper” specifically lays out support for the HighScope Curriculum in the country. |  |
| Recommendation 1b | The Commonwealth of Dominica should continue with current plans and efforts to finalise a document to outline and standardize the government’s contribution to early childhood learning centres and shift that a guidance document into policy language effective immediately. |  |  |  |  |  |  |
| St. Kitts and Nevis | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable |  |
| Recommendation 2 | The Government of Antigua and Barbuda and St. Kitts and Nevis should establish a succession plan to fill upcoming vacancies created from retiring Early Childhood Unit staff by 2015. Establishing a succession plan would ensure that sufficient and adequate human resources are available to effectively support the continuation and expansion of the HighScope Curriculum. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Once the retirees declare their intention to retire, then new recruits should be shadowing the current staff, so that there is effective overlap. |  | Ministry of Education, Supervisor of retiree | At least 12 months before retirement date | One group expressed concern about movement within the Early Childhood Development sector/unit. It was felt that more professional development would facilitate smooth succession planning. Stakeholders pointed out that in-service training is not a succession plan and felt that facilitating access to HighScope certification should be part of the budget. |  |
| Recommendation 3 | The Commonwealth of Dominica should continue with current plans and efforts to reinforce the current Early Childhood Unit with additional officers who are entrusted with supporting the implementation and expansion of the HighScope Curriculum, among other obligations, including monitoring. |  |  |  |  |  |  |
| St. Kitts and Nevis | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable |  | Not Applicable |
| Recommendation 4 | The Ministry of Education’s Early Childhood Units in all countries should use the HighScope Programme Quality Assessment (PQA) at least once annually, starting in 2015. The use of PQA would effectively highlight areas for improvement and document progress, supporting the research-based, quality monitoring as well as expansion efforts. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Ms. Jacqueline Morris and Ms. Florence Mooving-Smithen supported that training to begin using the Programme Quality Assessment which is already planned between now and January 2015 in both St. Kitts and Nevis. Stakeholders pointed out that teachers in all schools will need access to the Programme Quality Assessment documents. These documents are copy written by HighScope Foundation and need to be purchased from the Foundation. | Early Childhood Development Unit |  | To begin in next 6 months | It was agreed that the administration of the Programme Quality Assessment would take place in all learning centres at least one time per academic year. |  |
| Recommendation 5 | The Ministry of Education in all countries should deliver more practical training in adult – child interactions in particular within the next 12 months (in 2015). Training would strengthen the implementation of the HighScope Curriculum. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Components of implementation for teachers include in-service training, sharing of best practices and the use of a monitoring checklist to ensure effectiveness. | Early Childhood Development Unit |  | It is currently on-going and should continue | After unveiling of the Manitou Inc. produced video for stakeholders, it was suggested that this and similar media could be used to further inform parents about elements of HighScope and adult-child interaction. |  |
| Recommendation 6 | The Ministry of Education in Antigua and Barbuda and the Commonwealth of Dominica should continue with planned efforts to provide training in the area of conflict resolution. The Ministry of Education in St. Kitts and Nevis should provide “further training” in conflict resolution in 2015. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Provision of training in conflict resolution. | Early Childhood Unit |  | On-going | None. |  |
| Recommendation 7 | The Ministry of Education in all countries should invest resources into teacher training in the areas of dealing with children with disabilities (i.e., learning, behavioral and emotional, social, physical disabilities, and visual and hearing impairments). This input would strengthen the equity focus in the delivery of the HighScope Curriculum. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Provision of training to preschool teachers in the area(s) of special needs of children with disabilities. | Early Childhood Unit and Ministry of Education, with support from UNICEF |  | Timeline is 2016 school year and forward | None. |  |
| Recommendation #8 | The Ministry of Education in all countries should consider alternate fee strategies which support both efficiency and equity, facilitating access to the most vulnerable families. This change would effectively ensure that the teachers in the private sector receive payment for services delivered. The different rates should take effect before the 2015-2016 academic year. |  |  |  |  |  |  |
| St. Kitts and Nevis | Partial Agree | According to Ms. Jacqueline Morris, the Early Childhood Development Unit has recommended that fees should be increased this year as they have not increased in 20 years. In addition the unit also recommended that a sliding scale be implemented. The current fees are EC$15 per week. The recommended increase would be a maximum of EC$25 per week for those who can pay. Then there would be a sliding scale downward for those who have difficulty paying the full amount. The remainder would be subsidized by the Ministry of Social and Community Development identifies those children who are low income. Apparently this has already been recommended to the government several years in a row with no success. | Ministry of Education Ministry of Social and Community Development |  | This will start in the September 2015 academic school year | Stakeholder groups passionately discussed whether or the government should pay private sector teachers’ salaries. It appeared that there was broader agreement on the government supporting learning centres’ costs for low income families rather than supporting the schools themselves or paying teachers’ salaries. There was also a debate about whether or not it is appropriate for the Ministry of Education to implement a sliding scale for students of different income levels. |  |
| Recommendation 9 | The Ministry of Education in all the participating countries should continue as planned with the implementation of the training area of Child Assessment. A robust monitoring and evaluation system, a culture of results-based management and practical skills in Monitoring & Evaluation, are key to identifying children’s accomplishments and future development needs. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Implementation of training in the area of child assessment. | Supervisors, Early Childhood Unit, Planning Unit of the Ministry of Education |  | From January 2015 | It was mentioned that the Child Observation Record (COR) system is part of the HighScope Preschool Curriculum would be appropriate. The stakeholders would like to go forward with instituting training on the COR system and with implementing this particular child assessment system. |  |
| Recommendation #10 | The ministries of education should institutionalise a formal, systematic assessment process, such as the use of the COR, without delay. In the absence of assessment practices, the Training of Trainers are likely to need of supplemental training. Though there are multiple on-line courses available in using and instituting the Child Observation Record (COR) system, it may be more cost-efficient to work with the HighScope Foundation staff to deliver the training directly to multiple stakeholders at the same time. Should the Ministries of Education in participating countries wish to explore the use of the COR as their robust assessment system, UNICEF should provide support through the technical assistance. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Further actions are needed to integrate the Child Observation Record (COR) system through the system. | Ministry of Education, Early Childhood Unit, UNICEF and the HighScope Research Foundation |  | Currently, this is ongoing. | The Child Observation Record (COR) system is part of the HighScope Preschool Curriculum would be appropriate. Future efforts should explore instituting the Child Observation Record (COR) system in nursery and daycare centres. |  |
| Recommendation #11 | Putting into practice a formal and comprehensive child assessment system, which enables parents and teachers to identify, work on, and document children’s learning and development would be an effective and efficient management system for tracking student achievement and progress. The Ministry of Education in all the participating countries should develop a tracking system starting from the level of ECD. The system would be used for HighScope Curriculum “roll out” and “scaling up”. |  |  |  |  |  |  |
| St. Kitts and Nevis | Agree | Despite agreement on this recommendation in principle, there were mixed opinions about the actions needed to address this recommendation. | Statistics Office, Education Planning Division (within the Ministry of Education |  | September 2015 | Stakeholders would like to put in place a centralized data processing system for child data that starts at the early childhood level. |  |

Country: Dominica

| Stakeholder Feedback on Recommendations by Country | Agree / Disagree Not Applicable | Action to Be Taken | Person(s) or Department(s) Responsible |  | Timeframe | Additional Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Recommendation 1a | The Government of Antigua and Barbuda and Barbuda should prioritize the drafting of legislation to render the Standards for the Regulation of Early Childhood Services in Antigua and Barbuda (under the Education Act) into law within 12 months. Rendering “The Standards” into law would ensure that all services for children are consistent and would also effectively support the expansion of the HighScope Preschool Curriculum. |  |  |  |  |  |  |
| Dominica | Not Applicable | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable |  |
| Recommendation 1b | The Commonwealth of Dominica should continue with current plans and efforts to finalise a document to outline and standardize the government’s contribution to early childhood learning centres and shift that a guidance document into policy language effective immediately. |  |  |  |  |  |  |
| Dominica | Agree | Finalize the necessary document into appropriate policy language. It was suggested by stakeholders that consultants could be brought in to perform this task within 3 months. | Ministry of Education |  | June 2015 | The stakeholder group concluded that they want written copies of the fees (EC$50 per month) that parents are required to pay so that they can post them in the early learning centres. |  |
| Recommendation 2 | The Government of Antigua and Barbuda and St. Kitts and Nevis should establish a succession plan to fill upcoming vacancies created from retiring Early Childhood Unit staff by 2015. Establishing a succession plan would ensure that sufficient and adequate human resources are available to effectively support the continuation and expansion of the HighScope Curriculum. |  |  |  |  |  |  |
| Dominica | Not Applicable | Not Applicable |  | Not Applicable | Not Applicable | Not Applicable |  |
| Recommendation 3 | The Commonwealth of Dominica should continue with current plans and efforts to reinforce the current Early Childhood Unit with additional officers who are entrusted with supporting the implementation and expansion of the HighScope Curriculum, among other obligations, including monitoring. |  |  |  |  |  |  |
| Dominica | Agree | There is a need to increase the size of the Early Childhood Development Unit by at least one staff member. There is pending legislation that would increase the size of the unit to 4-5 people including separate staff to oversee day-care centres and early learning centres. As of June 2014 this document needed to be shifted into policy language. New Recommendation: Mrs. Veda George’s title should be changed to “Education Officer for Early Childhood Development.” Stakeholders also recommended that in adding staff to the Early Childhood Development Unit, those doing the hiring should look within the Ministry of Education for qualified staff. Further, offer scholarships to those who need additional qualifications. | Ministry of Education, Cabinet. |  | 2015 Financial Year. |  | None. |
| Recommendation 4 | The Ministry of Education’s Early Childhood Units in all countries should use the HighScope Programme Quality Assessment (PQA) at least once annually, starting in 2015. The use of PQA would effectively highlight areas for improvement and document progress, supporting the research-based, quality monitoring as well as expansion efforts. |  |  |  |  |  |  |
| Dominica | Agree | There is a need to procure Programme Quality Assessment materials for all learning centres for teachers to implement the system. These materials are copywritten by the HighScope Research Foundation and need to be purchased. Additionally, stakeholders felt teachers should not conduct Programme Quality Assessments in their own early learning centres. | Ministry of Education, Early Childhood Development Unit. |  | Programme Quality Assessment should be administered annually starting in the 2015-2016 school year. | None. |  |
| Recommendation 5 | The Ministry of Education in all countries should deliver more practical training in adult – child interactions in particular within the next 12 months (in 2015). Training would strengthen the implementation of the HighScope Curriculum. |  |  |  |  |  |  |
| Dominica | Agree | The provision of training should include early childhood, Grade 1 and Kindergarten teachers in order to create a smooth transition for children leaving preschool learning centres. | Early Childhood Development Unit Staff to deliver training |  | January 2015 | Well-trained staff is essential for HighScope’s success. |  |
| Recommendation 6 | The Ministry of Education in Antigua and Barbuda and the Commonwealth of Dominica should continue with planned efforts to provide training in the area of conflict resolution. The Ministry of Education in St. Kitts and Nevis should provide “further training” in conflict resolution in 2015. |  |  |  |  |  |  |
| Dominica | Agree | Provision of training in conflict resolution. | Early Childhood Unit |  | January 2015 | It was also mentioned that the provision of conflict resolution training to parents would also be beneficial. Future efforts should explore what options are available are therefore needed. |  |
| Recommendation 7 | The Ministry of Education in all countries should invest resources into teacher training in the areas of dealing with children with disabilities (i.e., learning, behavioral and emotional, social, physical disabilities, and visual and hearing impairments). This input would strengthen the equity focus in the delivery of the HighScope Curriculum. |  |  |  |  |  |  |
| Dominica | Agree | The provision of introductory training to early childhood educators in the area(s) of special needs of children with disabilities. | Early Childhood Development Unit & Special Education Unit |  | February 2015. Every child should be assessed in September each year. | Even with this special needs specialist attached to Early Childhood Unit They have enough staff to assess special needs children. However, there are insufficient staff persons to provide relevant on-going support to students. Preschool teachers will probably be frontline on this and therefore would benefit greatly from this type of training. |  |
| Recommendation #8 | The Ministry of Education in all countries should consider alternate fee strategies which support both efficiency and equity, facilitating access to the most vulnerable families. This change would effectively ensure that the teachers in the private sector receive payment for services delivered. The different rates should take effect before the 2015-2016 academic year. |  |  |  |  |  |  |
| Dominica | Agree | Despite agreement on this recommendation in principle, there were mixed opinions about the actions needed to address this recommendation (see Additional comments). | Ministry of Education, School-Level stakeholders |  |  | It was mentioned by teacher stakeholders that they would like additional support in collecting minimum mandated school fees of EC$50 per month from parents. After unveiling of the Manitou Inc. produced video for stakeholders it was suggested that this and similar media could be used to further sensitize parents about the importance of early childhood education and encourage payment from parents. This recommendation has strong implications for Dominica’s indigenous population(s). |  |
| Recommendation 9 | The Ministry of Education in all the participating countries should continue as planned with the implementation of the training area of Child Assessment. A robust monitoring and evaluation system, a culture of results-based management and practical skills in Monitoring & Evaluation, are key to identifying children’s accomplishments and future development needs. |  |  |  |  |  |  |
| Dominica | Agree | Implementation of training in the area of child assessment. | Supervisors, Early Childhood Unit, Planning Unit of the Ministry of Education |  | To begin with the 2015-2016 school year | None. |  |
| Recommendation #10 | The ministries of education should institutionalise a formal, systematic assessment process, such as the use of the COR, without delay. In the absence of assessment practices, the Training of Trainers are likely to need of supplemental training. Though there are multiple on-line courses available in using and instituting the Child Observation Record (COR) system, it may be more cost-efficient to work with the HighScope Foundation staff to deliver the training directly to multiple stakeholders at the same time. Should the Ministries of Education in participating countries wish to explore the use of the COR as their robust assessment system, UNICEF should provide support through the technical assistance. |  |  |  |  |  |  |
| Dominica | Agree | Further actions are needed to integrate the Child Observation Record (COR) system through the Training of Trainers system. | Ministry of Education, Early Childhood Unit, UNICEF and the HighScope Research Foundation |  | Starting in the academic year of 2015-2016. | None. |  |
| Recommendation #11 | Putting into practice a formal and comprehensive child assessment system, which enables parents and teachers to identify, work on, and document children’s learning and development would be an effective and efficient management system for tracking student achievement and progress. The Ministry of Education in all the participating countries should develop a tracking system starting from the level of ECD. The system would be used for HighScope Curriculum “roll out” and “scaling up”. |  |  |  |  |  |  |
| Dominica | Agree | The Education Management Information System (EMIS) already in place should be expanded to include childrens’ records at the early childhood level. | Teachers, Ministry of Education, Statistics and Planning offices |  | On-going, finalized September 2015. |  |  |

Annex 5:  	Evaluation Plan Matrix

| OECD-Adapted | Key Substantive Areas | Evaluation parameters (overall questions) |  | Evaluand (object of the evaluation) |  | Field Research questions | Mixed Methods | Data Sources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation Criteria |  |  |  |  |  |  |  |  |
| Relevance - What is the overall relevance of this intervention in relation to national priorities and child conventions? | Political | To what extent is there alignment with national strategic or development plan in the education sector? |  | Government Level |  | What is the relevant ministry stakeholder’s understanding of HighScope within the frame of their country’s policy environment (includes improving access to ECD for all)? | Face to face Interviews | Ministry of Education: Principal Education Officer(s); Early Childhood Coordinator; Education Officer Early Childhood |
|  |  | What is the policy environment for HighScope specifically in each island country? |  | Government Level |  | Are resources at policy - level made available for HighScope®? If so, how appropriate are earmarked funds? What is policy on national level M&E system? | Document Review | Official documents; Education Legislation; Budgets |
|  | Unicef Institutional | To what extent is there congruence with the Convention on the Rights of the Child? |  | Government Level |  | What are stakeholder sentiments/perspectives about HighScope current and possible additional prospects to promote the development of the child’s personality, (talents and mental and physical abilities) as per the Convention on the Rights of the Child and how it relates to the island country? | Face to face Interviews | Ministry of Education (see above) |
|  |  |  |  | Unicef Level |  |  | Skype Interviews | Unicef Education/M&E Officer(s) |
|  |  |  |  | School Level |  |  | Face to face Interviews | School administrator (principal) |
|  | Change in opinion(s) about HighScope® Reform Programme | To what extent have opinions about the programme changed? |  | Government Level |  | What objections have arisen on the relevance of HighScope, and how were these objections dealt with? | Face to face Interviews | CEO/ ECD staff |
|  |  |  |  | School Level |  |  | Focus Group Discussions | School Principals and Teachers |
|  |  |  |  | Parent Level |  |  |  | Parents |
|  | Economic, cultural, political, and social Context | What are the other economic, cultural, political, social contextual factors influencing this programme in each island nation? |  | Country Level |  | What external influences may have a significant role within the programme environment? How were they dealt with? | Document review | Recent Development effectiveness indicators (i.e., tourism income, employment, poverty reduction strategies, and investments) |

| OECD-Adapted | Key Substantive Areas | Evaluation parameters (overall questions) |  | Evaluand (object of the evaluation) |  | Field Research questions | Mixed Methods | Data Sources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation Criteria |  |  |  |  |  |  |  |  |
| Effectiveness - Institutional Level What progress or short-term results have been achieved? | Implementation of HighScope® Reform Programme- Strategy Implementation of HighScope® Reform Programme- Strategy | Effectiveness: The extent to which the intervention’s equity-focused results were achieved, or are expected to be achieved. |  | Institutional Level (across schools) |  | How are the most vulnerable / children identified in the community? | Data Review. Information available to identify children (i.e. use of disaggregated data by gender, disability, age group and geographic location). | School attendance records; Administrative records for identifying and selecting children who qualify for enrollment. |
|  |  | What are the institutional functions that facilitate child participation? What (if any) core programme elements to address equity issues exist? What is missing? |  | Institutional Level (across schools) |  | What is done to ensure that the most vulnerable / children complete the HighScope® curriculum? | Data Review. (See above). | School enrollment and attendance records. |
|  |  |  |  |  |  |  | Face to face interviews | School principal(s) and/or other stakeholders. |
|  |  | How have the supported schools made HighScope “their own”? What are the strategies in place? [This adaptation will be assessed across the countries] |  | Institutional Level (across schools) |  | What partnerships were or have been established to support the HighScope? How effective have these been in facilitating the realisation of its objectives? | Face to face interviews | School principal(s) and/or other stakeholders. |
| Effectiveness - Institutional Level What progress or short-term results have been achieved? |  |  |  |  |  |  |  |  |
|  |  | How have supported schools been effective at influencing (a) access; (b) demand; and (c) change in child growth and development? |  | Institutional Level (across schools) |  | Has access changed over time? Are there increasing demands for services? Are the HS values becoming more prominent in the community? | Face to face interviews | School principal(s) and/or other stakeholders. |
|  |  | How comprehensive are the programme’s chosen modalities for M&E? |  | Institutional Level (across schools) |  | (1) exploring if monitoring data is used in managerial decisions to improve programme implementation (including whether they are selected indicators used to monitor the programme Specific, Measurable, Achievable and Relevant (SMAR) enough to determine the outputs. | Data Review. | The tools used (if available); guidelines; and other documents. |
|  |  |  |  |  |  |  | Face to face interviews –examining frequency of monitoring and reporting, and overall preparedness in M&E. | School administration and staff |
|  |  | How comprehensive are the programme’s chosen modalities for M&E? |  | Institutional Level (across schools) |  | (2) identifying if the indicators selected to monitor the programme meet key standards – including if the indicators are “SMAR”?) (3) do indicators need revisions? | Data Review. | Indicators (if available) |
| What progress or short-term results have been achieved? | Implementation of HighScope® Reform Programme- Strategy | How sustainable is the M&E function in each school? |  | Institutional Level (across schools) |  | Are funds appropriated for this function. If so, are they sufficient? | Data Review. | Budget information |
|  |  |  |  |  |  | What is needed to create a robust and sustainable system? | Face to face Interviews. | School Principals and Teachers |

| OECD-Adapted |  |  |  | Key Substantive Areas |  |  |  | Evaluation parameters (overall questions) |  |  |  |  |  |  |  | Evaluand (object of the evaluation) |  |  |  |  |  |  | Field Research questions |  |  |  | Mixed Methods |  |  | Data Sources |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Effectiveness - School Level What progress or short-term results have been achieved? |  |  | Effectiveness - What school-level results have been achieved to date? Here, the focus is on the curriculum, instruction, visible practice, and relationships with the children. The sufficiency of the programme to achieve desired outputs is also examined. |  |  | Effectiveness of the education system in place: Physical Environment |  |  |  |  |  |  |  | School Level |  |  |  |  |  |  | To what extent are the most vulnerable (including girls) getting support within the school’s physical environment? To what extent does the school’s physical environment facilitate or hinder learning? (Looking at child Safety; Sanitation (toilettes); food safety (if needed); protection from the elements (rain and floods)? |  |  |  | Observations of interactions inside and outside of |  |  | Children (boys and girls ages 3-5 years). |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | School survey. |  |  | Exterior, playgrounds, and building resources (kitchen, bathrooms). |  |
| Effectiveness - School Level What progress or short-term results have been achieved? |  |  | Effectiveness - What school-level results have been achieved to date? |  |  | Effectiveness of the education system in place: Pedagogical Environment |  |  |  |  |  |  |  | School Level |  |  |  |  |  |  | To what extent are the most vulnerable getting support within the school’s pedagogical environment? To what extent does the school’s pedagogical environment facilitate or hinder learning? (Looking at child safety; girls’ safety (as needed); child friendly spaces; child-centered curricula used; academic expectations fulfilled)? |  |  |  | Observation of interactions inside classrooms and responsiveness to pedagogy, and relationships with other children. |  |  | Children (boys and girls ages 3-5 years). |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Face to face interviews about routine, benefits and difficulties of curricula and materials used. |  |  | School Administrators and Teachers |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data review. |  |  | Classroom-pupil ratio; Textbook-pupil ratio; materials used for instruction. |  |
| Effectiveness - School Level |  |  | Effectiveness - What school-level results have been achieved to date? |  |  | Effectiveness of the education system in place: Teacher-Student interactions. |  |  |  |  |  |  |  | School Level |  |  |  |  |  |  | To what extent are the most vulnerable children getting support through teacher-student interactions? To what extent are the teacher-student relations facilitating the HighScope® elements (open communications, engagement, and mutual respect)? |  |  |  | Observations of interactions inside classrooms and teachers – children relationships. |  |  | Children (ages 3-5 years) and teachers working together. |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Data review. |  |  | Promotion and completion rates - disaggregated for boys and for girls. |  |
| Effectiveness - School Level |  |  | Effectiveness - What school-level results have been achieved to date? |  |  | General Perceptions about the HighScope® Programme |  |  |  |  |  |  |  | Government Level |  |  |  |  |  |  | What are the perceptions and appreciation of what can be changed? What can be improved? |  |  |  | In-depth interviews |  |  | CEO and ECD staff |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | School Level |  |  |  |  |  |  |  |  |  |  |  |  |  | School Principals and Teachers |  |
|  |  |  | Effectiveness - What school-level results have been achieved to date? |  |  | Effectiveness of the training input provided by Unicef N.B. This is not in the ToR but is needed. |  |  |  |  |  |  |  | School Level |  |  |  |  |  |  | To what extent are the teachers trained to be teacher-trainers effectively strengthening capacity in their respective schools? What are the results of this Unicef input? What are the challenges so far? |  |  |  | Short survey on skills and materials use. |  |  | Trained teachers |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Focus group discussions about challenges and existing opportunities available for professional development. |  |  | Trained teachers |  |
|  |  |  | Context |  |  | What are the risks and protective factors influencing the effective implementation of HighScope®? This includes challenges and constraints. |  |  |  |  |  |  |  | School Level |  |  |  |  |  |  | Are there any factors that hinder or help the duty bearers to deliver? |  |  |  |  |  |  | School Administrators and Teachers |  |
| Effectiveness – Parent Level |  |  |  |  |  | Effectiveness of the education system in place: Parent reflections |  |  |  |  |  |  |  | Parent Level |  |  |  |  |  |  | To what extent is this programme meeting their needs? |  |  |  | Focus group discussions about their expectations, perceived benefits and costs. |  |  | Select group of parents from each school. |  |
| OECD-Adapted |  | Key Substantive Areas |  |  |  | Evaluation parameters (overall questions) |  |  |  |  |  | Evaluand (object of the evaluation) |  |  |  |  |  |  |  |  | Field Research questions |  |  |  | Mixed Methods |  |  | Data Sources |  |  |  |  |
| Evaluation Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Efficiency – What resources / inputs have been used? |  | Financial Resources Use |  |  | What are the resources used to implement the programme? |  |  |  |  |  | School Level |  |  |  |  |  |  |  |  | What are the resources in place in general? |  |  |  | Data review. |  |  | Cost of programme per school; |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cost per rights-holder (child served, parents (if possible), caregivers, etc.); and |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Portion of overall budget spent on staff costs, workbooks/supplies, and other programme components. |  |  |  |  |
|  |  |  |  |  | Does the programme use resources to achieve expected equity-focused results? If so, what are they? |  |  |  |  |  | School Level |  |  |  |  |  |  |  |  | To what extent are programme resources used in the most economical manner to achieve expected equity-focused results? |  |  |  | Data review. |  |  | School budget Information. |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | In-depth interviews about cost-saving methods used. |  |  | School Administrators and Teachers |  |  |  |  |
|  |  | Team Interaction (Human Resources) |  |  | How are human resources used? Are the methods cost-effective? |  |  |  |  |  | School Level |  |  |  |  |  |  |  |  | What is the internal team interaction like? |  |  |  | In-depth interviews |  |  | School Administrators and Teachers |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | How are resource-related decisions made? Is there potential for efficiency gains? |  |  |  | In-depth interviews about resource-saving / sharing methods used |  |  |  |  |  |  |  |
| Efficiency – What resources / inputs have been used? |  | Team Interactions with External Partners |  |  | What are the external partnerships supporting management? |  |  |  |  |  | School Level |  |  |  |  |  |  |  |  | What are the external interactions with suppliers / other schools? |  |  |  | In-depth interviews about resource-saving / sharing methods used |  |  | School Administrators and Teachers. |  |  |  |  |
|  |  | Context |  | Effects of external environment on the programme |  |  |  |  |  | School Level |  |  |  |  |  |  |  |  |  | How has the external environment helped/hindered the programme implementation? |  |  | Observations. |  |  |  | External factors influencing the costs of different ratios produced. |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Have HighScope® lessons learned been used? If so, in what way? (Reducing errors, delivering faster, or expanded delivery will be examined) |  |  | In-depth interviews about resources use and sharing of experiences with other schools |  |  |  | School Administrators and Teachers. |  |  |  |  |

| OECD-Adapted |  | Key Substantive Areas |  | Evaluation parameters (overall questions) |  |  | Evaluand (object of the evaluation) |  |  |  | Field Research questions |  | Mixed Methods | Data Sources |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact – What are the short-term positive and negative effects? |  | Effects on the most vulnerable / children | What have been the positive and negative effects from exposure to HighScope? |  |  |  | School Level |  |  |  |  |  | Children who have been promoted (2nd and 3rd graders now) Teachers who have seen the children be promoted Parents |
|  |  |  |  |  |  |  |  |  |  |  | Is there any difference in the way the programme affects girls compared to boys? Based on socio-economic status, who is benefiting more? The poorest? The richest? | Interviews about how the children who have passed through the programme are doing. |  |
|  |  | Effects on the teachers | Are there any benefits to Unicef sponsored programme support for the Training of Trainers (ToT)? |  |  |  | School Level |  |  |  | Describe the difference in this professional development compared to other opportunities experienced? | Interviews | Trained Teachers |

| OECD-Adapted |  | Key Substantive Areas |  | Evaluation parameters (overall questions) |  |  |  | Evaluand (object of the evaluation) |  |  |  | Field Research questions |  | Mixed Methods | Data Sources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sustainability - Is HighScope likely to continue without Unicef support? |  | Continuation of Activities |  | To what extent is there a perceived sense of accountability to education within the communities, where the HighScope® Curriculum Reform Programme is implemented? |  |  |  | Government Level |  |  |  | What is their perceived duty (buy-in) at country-level capacity to continue delivering and improve upon HighScope? | Interviews about wanting and needing to continue the efforts. | Ministry of Education |
|  |  |  |  |  |  |  |  | School Administrator Level |  |  |  |  |  | School Administrators and Teachers |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Interviews looking specifically at their involvement and support for its continuation. | Ministry of Education and School |
|  |  |  |  |  |  |  |  | Teacher Level |  |  |  |  |  | Administrators and Teachers |
|  |  |  |  |  |  |  |  | Parent Level |  |  |  |  |  | Parents |
|  |  |  |  |  |  |  |  | Child Level |  |  |  |  |  | Children (ages 3-5 years old in particular) |
|  |  | Links between Programme Design and Sustainability |  | What are the strengths and weaknesses of the HighScope® design? |  |  |  | Government Level |  |  |  | How do weaknesses and strengths contribute to sustainability? | Interviews | Ministry of Education |
|  |  |  |  |  |  |  |  | School Level |  |  |  |  |  | School Administrators and Teachers |
|  |  | Replicability |  | What is the likelihood that programme objectives will be expanded? |  |  |  | Government Level |  |  |  | What would be needed in order for the strategy to be more widely replicated or adapted? (Management, leadership, M&E system) | Focus Group Discussions | Ministry of Education and School |
|  |  |  |  |  |  |  |  | School Administrator Level |  |  |  |  |  | Administrators and Teachers |
|  |  |  |  |  |  |  |  | Teacher Level |  |  |  |  |  | Parents |

NB1: Definitions are from the Unicef adapted OECD Evaluation Criteria.

NB2: The impact of HighScope® Curriculum Reform would be reflected in the children’s progressive learning, While the terms of reference calls for the observed unintended direct or indirect results at the household level (children, parents, and caregivers), it is not possible to address this component without a counterfactual (which would require baseline data) and a robust assessment measuring household-level changes. However, some specific evidence will be collected that may be attributed to the contributions of the HighScope® Curriculum Reform Programme to short, or medium term improvements in the selected children’s families. Further, a review of the way the programme affects girls compared to boys would also be performed.

Annex 6:	List of Documents Consulted

Airasian, P. (2000). Assessment in the classroom: a concise approach, 2nd Edition. New York: McGraw-Hill.

Bamberger, M. and Segone. M UNICEF (2011) How to design and manage Equity-focused evaluations.

Accessed at: http://www.unicef.org/evaluation/index_60809.html

Campbell, F.A., Ramey, C.T., Pungello, E., Sparling, J., & Miller-Johnson, S. (2002) "Early childhood education: Young adult outcomes from the Abecedarian Project." Applied Developmental Science 6: 42-57.

CARICOM. (2008) Regional Guidelines for Developing Policy, Regulation and Standards in Early Childhood Development Services. Page 8.  Accessed at:

http://www.caricom.org/jsp/community_organs/cohsod_education/early_childhood_development_guidelines.pdf

Charles, Jacqueline, “Browne becomes new Prime Minister of Antigua, Youngest Ever.” The Miami Herald, June 13, 2014.

Charles, L. (2012) The Cost Of Providing Early Childhood Services In Antigua and Barbuda.

Charles, L (2011). Investment and Financing Strategies for Early Childhood Development in the CARICOM Region.

Charles, M. M. (2011) UNICEF Eastern Caribbean Office.  The HighScope Curriculum Reform Programme: A Child-Directed Preschool Curriculum at Work in the Eastern Caribbean.

CIA World Factbook (2014). Dominica Country Profile. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html. Accessed June 17, 2014.

CIA World Factbook (2014). Antigua and Barbuda Country Profile. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html. Accessed June 17, 2014.

CIA World Factbook (2014). Saint Kitts and Nevis Country Profile. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html. Accessed June 17, 2014.

Culkin, M. L., Howes, C., Kagan, S. L. and Yazejian, N. (2001) The Relation of Preschool Child-Care Quality to Children's Cognitive and Social Developmental Trajectories through Second Grade. Child Development, 72: 1534–1553; Reynolds, A. J., Temple, J.

Convention of the Rights of the Child (CRC).

Dart, J. (2009).  Six Normative Approaches to Evaluation.

Accessed at: http://www.clearhorizon.com.au/wp-content/uploads/2009/01/dart-six_normative_approaches.pdf

DESA. (2014) World Statistics Pocketbook 2014 edition Small Island Developing States Series V, No. 38/SIDS Special Issue.

Epstein, A.S. Essentials of Active Learning in Preschool: Getting to Know the HighScope Curriculum, 1st Edition." High/Scope Educational Research Foundation. 2007.

Freedom House (2013). Freedom in the World Report 2013: Antigua and Barbuda http://www.freedomhouse.org/report/freedom-world/2013/antigua-and-barbuda#.U6A_q_ldWSo

Freedom House (2013). Freedom in the World Report 2013: Dominica http://www.freedomhouse.org/report/freedom-world/2013/dominica-0#.U6LhfPldV5I Accessed June 18, 2014.

Freedom House (2013). Freedom in the World Report 2013: St. Kitts and Nevis http://www.freedomhouse.org/report/freedom-world/2013/st-kitts-and-nevis#.U6LgdPldV5I

Government of Antigua and Barbuda (2008). The Education Act, No. 21 of 2008.

Government of Antigua and Barbuda, Ministry of Education (2008) Standards for the Regulation of Early Childhood Services in Antigua and Barbuda under the Education Act.

Government of Dominica, Education Planning Unit, (2012).

Government of St. Kitts and Nevis. The Education Act No. 9 and No. 17.

Government of St. Kitts and Nevis, Ministry of Education. (2008) White Paper on Education Development and Policy 2009-2019:  Raising the Standard, Maximising Resources, Aligning With best Practices – Promoting Success for All.

Guba, E. G., & Lincoln, Y. S. (1989). Fourth generation evaluation. Newbury Park, CA, Sage Publications.

HighScope. (2014) Eastern Caribbean and UNICEF: Capacity Building for Early Childhood Education Formative Evaluation with the HighScope Educational Research Foundation: Final Evaluative Report.

HighScope. (2014). Preschool Child Observation Record. Accessed from: http://www.highscope.org/Content.asp?ContentId=113

National Scientiﬁc Council on the Developing Child. (2004). Young children develop in an environment of relationships. Working Paper No. 1. Page 1.

Retrieved from http://www.developingchild.net

Overseas Development Institute. (2006) Evaluating humanitarian action using the OECD-DAC criteria: An ALNAP guide for humanitarian agencies.  London: United Kingdom.

OECD (1991).  The DAC Principles for the Evaluation of Development Assistance, OECD (1991),

OECD (1986). Glossary of Terms Used in Evaluation, in 'Methods and Procedures in Aid Evaluation'

OECD (2000) Glossary of Evaluation and Results Based Management (RBM) Terms

Organisation of Eastern Caribbean States (OECS). (2012) 2012 – 2021 OESC Education Sector Strategy.

OECS. (2013) OECS EDUCATION SECTOR STRATEGY 2012-2021.

Accessed at: http://www.oecs.org/edmu-documents.

Heckman, J. (2000) “Policies to Foster Human Capital, ”JCPR Working Papers 154, Chicago, IL: Northwestern University/ University of Chicago Joint Center for Poverty Research.

Karoly and Bigelow, The Economics of Investing in Universal Preschool in California, p. xxix.

Learning Outcomes for Early Childhood development in the Caribbean Curriculum Resource Guide. http://www.open.uwi.edu/sites/default/files/Learning_Outcomes_Handbook.pdf

Peisner-Feinberg, E. S., Burchinal, M. R., Clifford, R. M., Culkin, M. L., Howes, C., Kagan, S. L. and Yazejian, N. (2001) The Relation of Preschool Child-Care Quality to Children's Cognitive and Social Developmental Trajectories through Second Grade. Child Development, 72: 1534–1553

Q-Finance Country Profile: Dominica http://www.qfinance.com/country-profiles/dominica Accessed June 18, 2014.

Reynolds, A , Temple, J., Robertson, D. and Mann, E. (2002) “Age 21 Cost-Benefit Analysis of the Title I Chicago Child-Parent Centers,” Educational Evaluation and Policy Analysis, vol. 24, no. 4, pp. 267-303.

Reynolds, A., Temple, J., Robertson, D., and Mann, E. (2001) Long-term effects of an early childhood intervention on educational achievement and juvenile arrest: A 15-year follow-up of low-income children in public schools. Journal of the American Medical Association, May 9, 285 (18): 2339-46

Ramey, S. and Ramey, C. (2000) “Early Childhood Experiences and Developmental Competence,” in Sheldon Danziger and Jane Waldofogel, eds., Securing the Future (New York, NY: Russell Sage Foundation, pp. 132-137.

Schweinhart, L. J., Montie, J., Xiang, Z., Barnett, W. S., Belfield, C. R., & Nores, M. (2005). Lifetime effects: The HighScope Perry Preschool study through age 40. (Monographs of the HighScope Educational Research Foundation, 14). Ypsilanti, MI: HighScope Press.

Schweinhart, L. & Heckman, J. (2010) The Cost-Benefit Analysis of the Preschool Curriculum Comparison Study. Final Report to the John D and Catherine T. MacArthur Foundation.

Schweinhart, L. & Weikart, D. P. (1997) Lasting differences: The HighScope® Preschool Curriculum Comparison study through age 23 (Monographs of the HighScope Educational Research Foundation, 12). Ypsilanti, MI: HighScope® Press.

Schweinhart, L. J., & Heckman, J.J. (2010) The Cost-Benefit Analysis of the Preschool Curriculum Comparison Study. Final Report to the John D and Catherine T. MacArthur Foundation.

UNDP. http://web.undp.org/evaluation/handbook/ch7-2.html

United Nations. (1959) DECLARATION OF THE RIGHTS OF THE CHILD.  Adopted by UN General Assembly Resolution 1386 (XIV) of 10 December 1959, paragraph 7.

UNESCO. http://data.uis.unesco.org/

UNICEF. E/CN.17/2010/9 (2011) Review of the implementation of the Mauritius Strategy”, submitted to the Commission on Sustainable Development

UNICEF. (2011) Eastern Caribbean multi-country Programme Eastern Caribbean.  Country programme document 2012-2016, paragraph 36.  Accessed at: http://www.unicef.org/about/execboard/files/Eastern_Caribbean_multicountry_2012-2016_20_Oct_2012.pdf

UNICEF. (2013) Eastern Caribbean multi-country Programme Country Programme Document.

UNICEF. (2013) E/ICEF/2013/14. Revised Evaluation Policy of UNICEF.

UNICEF. (2014) TERMS OF REFERENCE: UNICEF Office for the Eastern Caribbean Area.

UNICEF. (2009) PBA SC/2005/0712-01.  UNICEF Final Report for the Government of Italy: Eastern Caribbean Education Sector Capacity Building for Lifeskills and Early Childhood Education, page 3.

Vogler, P., Crivello, G. and Woodhead, M. (2008) Early childhood transitions research: A review of concepts, theory, and practice. Working Paper No. 48. The Hague, The Netherlands: Bernard van Leer Foundation.

Williams, S. (2009) HighScope Resource.  Establishing Curricula in the Caribbean: HighScope Helps Meet the Region’s Early Childhood Challenges. Spring.

World Travel and Tourism Council (2014) “Travel and Tourism Economic Impact 2014: Antigua and Barbuda”

http://www.wttc.org/research/economic-impact-research/country-reports/a/antigua-and-barbuda/

World Travel and Tourism Council (2014) “Travel and Tourism Economic Impact 2014: Dominica”

http://www.wttc.org/research/economic-impact-research/country-reports/d/dominica/

World Travel and Tourism Council (2014) “Travel and Tourism Economic Impact 2014: St. Kitts and Nevis”

http://www.wttc.org/research/economic-impact-research/country-reports/s/saint-kitts-and-nevis/

The World Bank, http://www.worldbank.org/en/results/2013/09/19/education-young-poor-children-Dominican-Republic.

The World Bank. (2012) Education Indicators. Accessed at: http://data.worldbank.org/indicator/SE.PRE.ENRR?order=wbapi_data_value_2012+wbapi_data_value&sort=asc

Annex 7: 	List of Stakeholders

Antigua and Barbuda

Ministry of Education

- Michael Browne, Minister of Education

- Earla Esdaille - Director ECD Unit

- Embler Spencer - Curriculum Officer ECD Unit (not sure this is correct title)

- Alvacea Burton - Education Officer Zone II

- Idona George - Education Officer Zone I

- Charmaine A. Meade - Education Officer Secondary Schools

- Emil Michael - Education Officer Zone IV

- Desiree Antonio - Education Officer Zone III

- Clare Browne - Deputy Director of Education

- Jacintha Pringle - Director of Education

- Valerie Mussington - Permanent Secretary for Education

HighScope Teachers and Supervisors

- Veronica Haywood   - Head Teacher and Supervisor at Simon Bolivar Preschool

- Amanda Christian, Teacher Simon Bolivar

- Charisa Hazelwood    -  Teacher at Beginners Academy

- Bernadette Hazelwood – Supervisor at Beginners Academy

- Kay Bailey    - Supervisor and Director at Eleven Hour Sunshine Preschool

- Hester Samuel   - Head Teacher at Eleven Hour Sunshine

- Denise Pryce -  Supervisor and Teacher at Green Bay Preschool

- Rosebelle Payne   - Teacher at Villa Preschool

HighScope Parents

- Simon Bolivar Parent Focus Group: 13 participants (12 female, 1 male)

- Eleven Hour Sunshine Parent Focus Group: 12 participants (11 female, 1 male)

- Beginners Academy Parent Interviews

- Cerelyn Richards   - Past HighScope parent who also works at Beginners Academy with the Daycare kids.

- Richell George Cole   - Parent of HighScope student at Beginners Academy

Dominica

Ministry of Education

- Marcella Powell - Education Permanent Secretary

- Veda George, ECD Unit

HighScope Teachers and Supervisors

- Patricia Bruno – Teacher at Mahaut Preschool

- Eva Leslie Smith – Teacher at Mahaut Preschool

- Josette Jean-Baptiste – Head Teacher and Supervisor at Mahaut Preschool

- Abigail Jean-Baptiste – Teacher at Mahaut Preschool

- Jannice Dejan – Head Teacher and Supervisor at Grand Fond Preschool

- Danielle Cuffy – Teacher at Grand Fond Preschool

- Patricia Noel - Supervisor and Head Teacher at S.W.O.R.D. Preschool

- Fanny Rapha - Teacher at S.W.O.R.D. Preschool

- Debra Charles – Head Teacher and Supervisor at Social Centre Model School

- Makisha Riley Mitchell – Teacher at Social Centre Model School

- Martha Isles – Teacher at Social Centre Model School

- Sharon Samuel – Teacher at Social Centre Model School

- Valda Frederick – Teacher at Social Centre Model School

- Albena Mulcare – Teacher at Social Centre Model School

HighScope Parents

- Mahaut Preschool Parent Focus Group: 10 participants (3 male, 7 female).

- Grand Fond Parent Focus Group: 11 participants (10 female, 1 male).

- S.W.O.R.D. Parent Focus Group: 13 participants (all female)

- Social Centre Model School Parent Focus Group: 10 participants (2 male, 7 female)

Focus Group with Primary School Teachers and Principals

| Name | School | Position |
| --- | --- | --- |
| Shakina Derival | Bagatelle Primary | K & 1 teacher |
| Doreen Ulatt | Trafalgar Primary | Principal |
| Maurice Lusite | Bagatelle Primary | Principal |
| Leon Leconate | Kelleb John Laurent Primary | K teacher |
| Victoria Roberts | Mahaut Primary | Principal |
| Lyndonna Benjamin | Mahaut Primary | K teacher |
| Evans James | Grand Bay | Principal |
| Marcia Defoe | Grand Bay | K teacher |
| Verne | Kelleb John Laurent | Principle |
| Lydia Joseph Philip | Grand Fond Primary | K teacher |
| Karen Richards | Massacre/Canefield Primary | K teacher |
| Brenda Coupel | Warner Primary | K teacher |
| Elizabeth Xavier David | Massacre/Canefield Primary | Principal |

Director of the Social Centre

- Mrs. Norma Cyrille   -  Social Centre Director

Grand Fond Primary School

- Hatty Leslie, Principal

St. Kitts and Nevis

Ministry of Education

- Honorable Nigel Carty  - Minister of Education

- Lornette Queely-Connor -  Permanent Secretary on Nevis

- Clarice Cotton - Chief Education Officer on St. Kitts

- Vanta Walters - Former National Director, Early Childhood Development on St. Kitts

- Jacquelyn Morris - National Director, Early Childhood Development on St. Kitts

- Florence Smithen - Education Officer on Nevis

- Nadine Natta - Resource Teacher on St. Kitts

- Valery Dolphin - Resource Teacher on St. Kitts

- Rosalind Warner-Otto - Resource Teacher on St. Kitts

- June Wallace - Resource Teacher on St. Kitts

- Palsy Wilkin - Principal Education Officer on Nevis

- Dawnny Lanns - Coordinator Early Childhood Education on Nevis

HighScope Teachers and Supervisors

- Yasmine Powell, Supervisor of McKnight Daycare Centre

- Michelle Isaac, Teacher of McKnight Daycare Centre

- Tanisha Hanley, Teacher of McKnight Daycare Centre

- Haddiya Jeffers, Teacher of McKnight Daycare Centre

- Zelda James, Teacher of McKnight Daycare Centre

- Celicia Jordan, Teacher of McKnight Daycare Centre

- Sophia Johnson, Teacher McKnight Daycare Centre

- Jasmine Harris, Supervisor Cayon Daycare Centre

- Octacia Jeffers, Teacher of Cayon Day Care Centre

- Tobesea Connonier, Teacher of Cayon Day Care Centre

- Kimmoy Charles, Teacher of Cayon Day Care Centre

- Walisia Dias,  Teacher of Cayon Day Care Centre

- Delicia Anthony, Teacher of Cayon Day Care Centre

- Moneshia Rawlins,  Teacher of Cayon Day Care Centre

- Brenda Smithen-Williams, Head Teacher / Supervisor of Charlestown Primary School

- Malinda Liburd, Teacher of Charlestown Primary School

- Gillian Hendrickson, Teacher of Charlestown Primary School

- Marigold Wilkonson, Teacher of Charlestown Primary School

- Nekisha Marshall, Teacher of Charlestown Primary School

- Serena Clarke, Teacher of Charlestown Primary School

- Velona Claxton, Teacher of Charlestown Primary School

HighScope Parents

- McKnight Daycare Centre Parent Interviews: 6 participants (2 males and 4 females)

- Cayon Day Care Centre Focus Group: 30 participants: (8 males, 22 females)

- Charleston Primary School parent Focus Group: 13 participants (8 males, 5 females)

Primary School Teachers

- Marissa Caines - Kindergarten Teacher, Dr. William Connor Primary School (St. Kitts)

- Lenette Roper - Kindergarten Teacher, Charleston Primary School (Nevis)

- Verna Grant - Kindergarten Teacher, Charleston Primary School (Nevis)

Kindergartners

- Deonté Libyrd, male (5 years old), Charleston Primary School (Nevis)

- Tejaneh David, female (6 years old), Charleston Primary School (Nevis)

- T’shanika Wells, female (6 years old), Charleston Primary School (Nevis)

- Jarden Robertson, male (5 years old), Charleston Primary School (Nevis)

Annex 8: 	Samples of Main Instruments Used (and permission slip)

Classroom Observation Form

Prior to your visit, confirm from teacher is what the regular routine.

| Name of school: | Number of children observed: Girls_______ Boys________ |
| --- | --- |
| Number of Teachers: | Class Observation Time: 30 minutes_____ 1 Hour______ More than one Hour______ |

Is there text on walls: ____ Yes 	____ No

How many walls? ____ 1 ____ 2  ____ 3  ____ 4

Is the text used during lesson: ____ Yes 	____ No

Work designed and created by children is on display? ____ Yes 	____ No

Daily Routine

The classroom has a consistent daily routine? (Compare what teacher says to what you observe)

____ Yes 	____ No ____ To Some Degree

The children are aware of the daily routine?

____ Yes 	____ No   ____ To Some Degree

Children have an appropriate amount of time for each part of the day?

____ Yes   ____ No  ____ To Some Degree

Children are actively engaged and appear focused as they carry out the activities in each part of the day?

____ Yes   ____ No  ____ To Some Degree

The daily routine includes children

| Planning (and indicating plans to adults) | Yes | No | To Some Degree | Not Observed |
| --- | --- | --- | --- | --- |
| Carrying out their plans (work time, choice time, free play) | Yes | No | To Some Degree | Not Observed |
| Recalling and discussing their activities | Yes | No | To Some Degree | Not Observed |
| Engaging in small group activities | Yes | No | To Some Degree | Not Observed |
| Engaging in large group activities | Yes | No | To Some Degree | Not Observed |
| snacks or meals (with participation and interaction) | Yes | No | To Some Degree | Not Observed |
| Participating in cleaning-up | Yes | No | To Some Degree | Not Observed |
| Nap or rest | Yes | No | To Some Degree | Not Observed |

Teacher – Child Interaction

Did the teacher include interactive activities (songs, games, role-play)

____ Yes   ____ No

| Children’s separation from home and daily entry are handled with sensitivity and respect | Yes | No | To some degree | Not observed |
| --- | --- | --- | --- | --- |
| Adults create a warm and caring atmosphere (address comments to children, attend to children who are upset, positive attention, children go to adults for help, call teachers by name) | Yes | No | To some degree | Not observed |
| Adults share control of conversations with children (asking open ended questions, seek children’s ideas, listen without interrupting) | Yes | No | To some degree | Not observed |
| Adults participate as partners in children’s play (assume roles suggested by children and follow cues) | Yes | No | To some degree | Not observed |
| Adults encourage children’s ideas, suggestions and efforts | Yes | No | To some degree | Not observed |
| Adults encourage and support children’s strengths and interests | Yes | No | To some degree | Not observed |
| Adults encourage children to explore and use materials and their own developmental level and pace | Yes | No | To some degree | Not observed |
| Adults encourage children to do things for themselves | Yes | No | To some degree | Not observed |
| Adults encourage children to interact with and turn to one another for assistance throughout the day | Yes | No | To some degree | Not observed |
| Adults involve children in resolving conflict | Yes | No | To some degree | Not observed |

Social Skills and Self-Expressions of Emotion

Children are involved in social activities? Social Activities--Physical and/or verbal activities involving attention to one's behavior in relation to other children and adults, such as showing objects to others (e.g., show and tell), reporting your “news” (e.g., telling others about the park you visited last night), sharing materials, borrowing materials, seeking or giving help or information, planning or making decisions, talking to others, asking questions, making demands, carrying on a conversation, telling jokes, requesting permission to do something, conflict resolution, etc.	____ Yes 	____ No

Children express positive or negative emotions? ____ Yes 	____ No

Children listen to, watch or participate in physical and/or verbal communication of attitudes and/or feelings. ____ Yes 	____ No

Self-Sufficiency

Children take part in tasks involving attention to physical and bodily needs. This refers to toileting, washing hands or face, bathing, washing/brushing hair, brushing teeth, dressing, eating, sleeping, etc.

____ Yes 	____ No

Children take part in caring for the class room.  Refers to helping with chores such as setting up snack or clean up ____ Yes 	____ No

Sensory and Motor Skills

Did you observe children using gross motor skills? Gross Motor--Active movement using legs, arms, head, and/or body: Such activities would include: running, climbing, jumping, swinging, swimming, rough-housing, throwing, sliding, riding a bike, baseball, soccer, football, leapfrog, ring-around-the-rosie, chasing games, hiding games, teasing games, calisthenics, gymnastics, using a trampoline, building with large wooden or plastic blocks, giant tinker toys, crates, etc.++    ____ Yes   ____ No

Did you observe children using fine motor skills? Fine Motor--Active movement using hands, feet, fingers, toes. Such activities would include: stringing beads, sewing/lacing cards, table games, puzzles, peg boards, dice, playing with play dough, clay, sand, water, rice, or beans, sorting, arranging, handling small object building with Legos, bristle blocks, other small blocks, small tinker toys; doing woodworking, carpentry, etc.++

____ Yes   ____ No

Pre-academic

Use of teaching aids during the lesson: ____ Yes 	____ No

Use of small or large group methodology during the lesson: ____ Yes 	____ No

Children’s use of any reading skills (if applicable) (Reading--Activities involving visual recognition/auditory discrimination of letters, and use of books, such as looking at books independently, attempting to sound out words, learning to look or looking at books right-side-up and in proper sequence (i.e., beginning to end), learning to "read" or "reading" in the direction of the written language, following the words in a book while listening to the story narrated on a recording, forming letters with play dough, etc.)

____ Yes 	____ No

Children’s use of any writing skills (if applicable)?    ____ Yes 	____ No

Children’s use of any math skills (if applicable)? ____ Yes 	____ No

Children’s use of any sensory exploration or examination of objects or materials skills (if applicable)

____ Yes 	____ No

Children’s understanding of any community environmental skills (if applicable)?

____ Yes 	____ No

Children’s participation in any religious activities (if applicable)? Religious Activities--The child listens/watches, listens to instructions for, or participates in religious activities such as lessons, singing, praying, attending chapel, etc.    ____ Yes 	____ No

TEACHER [TOT] Survey Form

Demographic Information

Confirm that this teacher has provided this training….

| Country : | Number of students in his/her classroom(s):______ Female_______ Male_________ |
| --- | --- |
| Name of School: |  |
| Name of Teacher: |  |

Training Information

1. For how long have you been providing ToT HighScopes trainings?

______________(in months or years)

2. Roughly, how	many trainings sessions have you provided?___________

3. Have 	you provided coaching assistance from a school stakeholder? (Circle only one)

______NO ________YES

4. For how long have you been providing ToT HighScopes trainings?

______________(in months or years)

5. Roughly, how	many times have you provided coaching assistance?___________

Training Effectiveness – Materials Use

As a ToT, we understand that you have been trained through the UNICEF – supported intervention.  For the next series of questions, please use the following five‐point scale to respond	 to the questions:

Perceptions of Effectiveness of Training Delivery and Pedagogy

| (1) | (2) | (3) | (4) | (5) |
| --- | --- | --- | --- | --- |
| Strongly Disagree | Disagree | Neither Agree nor Disagree | Agree | Strongly Agree |

- I typically show the teachers I train how and what to do in order to master course content. ____

- My training goals and methods address a variety of student learning styles._____

- Sharing my knowledge and expertise with the teachers I train is very important to me._____

- I give the teachers I train negative feedback when I see their performance is unsatisfactory._____

- The teachers I train have the opportunity to direct or provide input into their learning experience.____

Improvements

In your view, what could be done to further support teachers to implement HighScopes?

What could be improved to further support your ability to be a more effective ToT of HS?

TEACHER Survey Form

Demographic Information

Confirm if this teacher has received training.  If not, skip to teacher characteristics section.

| Country : | Number of students in his/her classroom(s):______ Girls_________ Boys_________ |
| --- | --- |
| Name of School: |  |
| Name of Teacher: |  |

Training Information

1. Have	you taken part in any ToT HighScopes trainings? [Check only one please]

______NO ________YES

2. How	many trainings sessions have you attended?___________

3. Have 	you received coaching assistance from a school stakeholder?

______NO ________YES

5. How	many times have you received coaching assistance?	___________

Training Effectiveness – Materials Use

For the next series of questions, please use the following five‐point scale to respond	 to the questions:

| (1) | (2) | (3) | (4) | (5) |
| --- | --- | --- | --- | --- |
| Almost Never | Seldom | Every Month | Every Week | Every Day |

- How often do you apply the information you learned in your classroom?  _____[Please insert code for each Question]

- How often do you apply the coaching support applied? ____

- How often do you use the tools provided?  ______

- How often do you use the programme quality assessment (PQA) form (documenting anecdotal notes for children, observing child behavior, child strengths and weaknesses)? [May need to show the form to the respondent]_____

- How often do you engage in curriculum planning and assessment for each child? ____

- How often do you share this information with the parents? ________

Perceptions of Training Effectiveness

| (1) | (2) | (3) | (4) | (5) |
| --- | --- | --- | --- | --- |
| Strongly Disagree | Disagree | Neither Agree nor Disagree | Agree | Strongly Agree |

- The information I have learned has helped me to be a more effective teacher. ____ [Insert code]

- In my view, the coaching support has helped me to be a better teacher. _____

- The tools that have been provided to me support my ability to teach the children.  _____

- The PQA has made my work as a teacher more structured and consistent.____

- The task of curriculum planning / assessment has made me to be a more competent teacher.____

- Sharing information with the parents makes me feel like a stronger teacher.____

Improvements

- What could be improved to further support your ability to be a more effective teacher?

Teacher Characteristics Data

As part of our evaluation, we are gathering information about the adults who work with the children we are observing.

- First, what is your age (in years)?

________ AGE

- What is your gender? [Please check one]

________ MALE _________ FEMALE

- How many years have you been working with 3- to 5-year-old children?

________ NUMBER OF YEARS WORKING WITH 3- TO 5-YEAR-OLD CHILDREN

- How many years have you been working at this school?

________ NUMBER OF YEARS WORKING IN THE SETTING

- Place a checkmark in front of the highest grade or educational level you have completed [Check One Please].

| ______________ No Schooling | ______________ Senior High |
| --- | --- |
| ______________ Preprimary | ______________ Some college/less than Bachelor’s degree |
| ______________ Primary | ______________ First stage University (Bachelor’s degree) |
| ______________ Junior High | ______________ Second stage University (Master’s, Ph.D.) |
|  | ______________ Not definable by level |

- Apart from HighScope, did you attend a teacher training programme?

______NO (GO to Question 27) ______YES (continue)

- At what level of education did you attend the teacher training Program?

________ SECONDARY EDUCATION

________ VOCATIONAL EDUCATION

________ TERTIARY EDUCATION

- How many years of teacher training did you attend?

________ NUMBER OF YEARS OF TEACHER TRAINING

- Are you certified or licensed?

______NO (GO to Question 30) ________YES (continue)

- Are you certified for preprimary education? [If relevant]

______NO 	________YES

- Are you certified for primary education? [If relevant]

______NO	________YES (continue)

- For each of the following, check the appropriate column to indicate if you have received additional specialized training in that area, and the length of the specialized training:

| TOPIC | Brief (1 day to 1 week) | Long (More than 1 week) |
| --- | --- | --- |
| Social Development Skills |  |  |
| Language Development in Children |  |  |
| Motor Development |  |  |
| Psychology of Primary Education |  |  |
| Cognitive Development |  |  |
| Development of Motivation for Learning in Preschoolers |  |  |
| Creativity in Preschoolers |  |  |
| Readiness Skills |  |  |
| Reading and Writing Skills |  |  |
| Music and Games for Preschoolers |  |  |
| Science Methods |  |  |
| Mathematics Methods |  |  |
| Health and Safety of Preschoolers |  |  |
| Assessment Procedures for Preschoolers |  |  |
| Play and its Development |  |  |

- Any other certificate or degree not mentioned?__________________________________

Thank you very much for taking the time to fill out this questionnaire.

School FORM-Part I (Infrastructure)

Indoor Facilities

Issue Confidentiality Protocol.  (Excluding the toilets, bathrooms, and kitchen) how many rooms are available for use by the target children? __________

How many of the available rooms do the children actually use on a regular basis? ___________

For the number of rooms recorded above, approximately how many children are typically in each room at one time?

What is the primary purpose for which each room is used (e.g., classroom, music room, gross motor room, etc.)?

|  | Number of Children | Primary Purpose for the room | Square footage |
| --- | --- | --- | --- |
| ROOM 1 |  |  |  |
| ROOM 2 |  |  |  |
| ROOM 3 |  |  |  |

In what ways (if any) is the setting furnished/structured for use by children and aligned with HighScopes? (Circle or check one only)

| Child-sized tables and chairs | Yes | No | To Some Degree |
| --- | --- | --- | --- |
| Child-sized toilets and sinks | Yes | No | To Some Degree |
| An area for large group activities | Yes | No | To Some Degree |
| Shelves low enough for children to reach out and get (non-dangerous) materials safely | Yes | No | To Some Degree |
| Materials are varied, manipulative, open-ended and appeal to multiple senses | Yes | No | To Some Degree |
| Materials reflect the home and community cultures of program children | Yes | No | To Some Degree |
| Examples:_______________________________________________________________ |  |  |  |
| Multi-cultural materials are integrated into the classroom | Yes | No | To Some Degree |
| Examples:_______________________________________________________________ |  |  |  |
| Materials depict a wide range of non-stereotyped role models | Yes | No | To Some Degree |
| Materials are plentiful | Yes | No | To Some Degree |
| Child initiated work is on display | Yes | No | To Some Degree |
| Materials are labeled in a manner understood by children (pictures, photos, simple words) | Yes | No | To Some Degree |
| The space is divided into interest areas | Yes | No | To Some Degree |
| Interest areas have names easily understood by children | Yes | No | To Some Degree |
| Interest areas are clearly defined and marked (by low shelves, furniture, carpeting etc.) | Yes | No | To Some Degree |
| Interest areas have enough space for many children to play at once | Yes | No | To Some Degree |
| Children can move freely from one interest area to another | Yes | No | To Some Degree |
| Interest areas with compatible activities are adjacent | Yes | No | To Some Degree |

Which of the following does the school have? (Circle or check one only)

| Fire Alarm System (Electric Or Manual which includes an extinguisher) | Yes | No |
| --- | --- | --- |
| Kitchen |  | Yes | No |
| Running Water/Tap Water |  | Yes | No |
| Flush Toilet Facilities (Indoor) |  | Yes | No |
| Toilettes for those with Disabilities |  | Yes | No |
| Separate Toilettes for boys and girls |  | Yes | No |
| Telephone In Working Order |  | Yes | No |
| Refrigerator In Working Order |  | Yes | No |
| Electricity/Some Type Of Lighting System |  | Yes | No |
| Fan |  | Yes | No |
| Air Conditioner Or Other Type Of Cooling System |  | Yes | No |
| First Aid Supplies |  | Yes | No |
| Transportation In Working Order (as needed) |  | Yes | No |
| Flood Prevention Materials |  | Yes | No |

Outdoor Facilities

Does the facility have an outdoor play area on the property?

____ Yes 	____ No

If yes, is the outdoor play area easily accessible from the indoor space?

____ Yes 	____ No

If yes, is a portion of the outdoor play area covered?

____ Yes 	____ No

If no, is there an outdoor play area within walking distance of the setting?

____ Yes 	____ No

Is the outdoor play area located in:

____ A Sports Field ____ A Private Park/Playground

____ A Public Park/Playground ____Other, Specify: _______________

What is the approximate size of the outdoor play area (sq ft)? ___________________

How often do the children have outdoor play time?

____ Once per day 			____ Multiple times per day

____ Once per week		____ Multiple times per week (but less than daily)

____ Less than once per week	____ No outdoor play area accessible

Is there a variety of stationary and portable equipment and materials for various types of play? (take pictures)

____ Yes 	____ No

Is there equipment available in the outdoor play area that allows children to:

|  | Is there equipment is available in the outdoor play area that allows children to: |  |  |
| --- | --- | --- | --- |
| Climb | Yes | No | Some Degree |
| Swing | Yes | No | Some Degree |
| Jump over objects | Yes | No | Some Degree |
| Catch and throw | Yes | No | Some Degree |
| Running | Yes | No | Some Degree |
| Walk up and down steps | Yes | No | Some Degree |
| Ride a tricycle/bike | Yes | No | Some Degree |

Are there hazardous issues in the outdoor play area? (ex. trash, broken equipment?)

____ Yes 	____ No

Is there an indoor play area/large muscle room separate from the classroom for the children to use?

____ Yes 	____ No

What is the approximate size of the indoor play area/large muscle room (sq ft)?___________________

******

THANK YOU FOR YOUR HELP!

School FORM-Part II - (Enrollment and Admissions Policy)

Enrollment

Please fill in the relevant information regarding enrollment. Issue Confidentiality Protocol.

|  | 2009-2010 |  | 2010-2011 |  | 2011-2012 |  | 2012-2013 |  | 2013-2014 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enrolment | M | F | M | F | M | F | M | F | M | F |
| Applicants | M | F | M | F | M | F | M | F | M | F |
| Dropouts* | M | F | M | F | M | F | M | F | M | F |
| Completed | M | F | M | F | M | F | M | F | M | F |

* dropouts are defined by each school – we have to find this out

**This information must be disaggregated by gender for the last since the beginning.

HighScope programmes have different policies regarding the children they admit.

Does the selection of the children for this setting’s pre-primary class(es), ages 3 to 5, based on any criteria?  _______Yes _______No (Mark or Check only one)

If you marked “yes”, please mark all the criteria that are applicable:

| No. | Check Here | Criteria |
| --- | --- | --- |
| a. |  | Age |
| b. |  | CHILD SPEAKS (OR UNDERSTANDS) DOMINANT LANGUAGE OF SETTING |
| c. |  | CHILD'S ABILITY TO CARE FOR SELF (DRESSING, EATING, TOILETING, WASHING, ETC.) |
| d. |  | READINESS TESTS. Please explain. |
| e. |  | DEVELOPMENTAL SKILLS TESTS (COGNITIVE, LANGUAGE, MOTOR, SOCIAL, ETC.) ____ ____ Please explain. |
| f. |  | SPECIAL NEEDS OF THE CHILD. Please explain. |
| g. |  | Other. Specify:__________________________ |

Please use this additional room for your explanation about the above.

Are there any particular categories of children or families who are targeted for recruitment or given priority for enrollment at your setting?

_______ No (GO to ADMISSIONS POLICY) _______Yes (continue)

| No. | Check Here | Criteria |
| --- | --- | --- |
| a. |  | LOW-INCOME/DISADVANTAGED FAMILIES |
| b. |  | HIGH RISK CHILDREN |
| c. |  | HIGH-INCOME FAMILIES |
| d. |  | HANDICAPPED CHILDREN |
| e. |  | SINGLE-PARENT FAMILIES |
| f. |  | WORKING PARENTS |
| g. |  | STUDENT PARENTS |
| h. |  | MEMBERS OF SPONSOR GROUP (E.G., EMPLOYEES OF SPONSOR) |
| i. |  | OTHER, SPECIFY: __________________________________ |

The data from this section will be analyzed and will generate:

(i) an analysis of rights-based approaches implemented.

Admissions Policy

Do you have written guidelines or written policies guiding admissions?

Does this setting maintain and update records for any of the following?

| No. | Check Here | Criteria |
| --- | --- | --- |
| a. |  | BACKGROUND INFORMATION (Enrollment Application) FOR EACH CHILD |
| b. |  | ATTENDANCE RECORDS |
| c. |  | MEDICAL RECORDS |
| d. |  | DEVELOPMENTAL TESTS |
| e. |  | EVALUATIONS |
| f. |  | FOOD PROGRAM (includes allergies) |
| g. |  | BEHAVIOR OBSERVATIONS |
| h. |  | OTHER, SPECIFY: _______ |

Licensing/Registration

In this setting, how many children are you licensed/registered to serve? [Take picture of License]  _______ NUMBER OF CHILDREN

******

THANK YOU FOR YOUR HELP!

School FORM-Part III (Fee Structure & Management)

I am going to read you a list of places and people that are often sources of funding for HighScope programmes. For each one, please tell me if you receive funding or in-kind resources from that source for the 2013-2014 school year. Issue Confidentiality Protocol.

INCOME

The checklist for the budget information to be collected. Only for this past school year of 2013-2014 (circle or check one. The ones checked “yes”, obtain the income amount for the 2013-2014 school year. Use extra paper if needed.

|  |  | Income Area |
| --- | --- | --- |
| Yes | No | a. PARENT FEES |
| Yes | No | b. AGENCY |
| Yes | No | c. FOUNDATION/ORGANIZATION |
| Yes | No | d. Other |

| Income Area | Amount Received for the 2013-2014 school year – this can be financial or in-kind |
| --- | --- |
| a. Parent FEES |  |
| b. AGENCY |  |
| FEDERAL/NATIONAL |  |
| MUNICIPAL OR LOCAL |  |
| COMMUNITY SERVICE |  |
| FOUNDATION/ORGANIZATION |  |
| c. PRIVATE FOUNDATION |  |
| BUSINESS ORGANIZATION |  |
| COMMUNITY GROUPS |  |
| OTHER PRIVATE INDIVIDUALS |  |
| RELIGIOUS ORGANIZATION |  |
| FUND RAISING EVENTS |  |
| d. OTHER, SPECIFY: ________________________________ |  |
| Total |  |

Expenditures

Staffing

| Expenditure Area | Number Total | Number Full-Time | Number Part Time | Paid Amount (Mark currency) | Volunteer Yes/No | Person Not There |
| --- | --- | --- | --- | --- | --- | --- |
| Director/Principal |  |  |  |  |  |  |
| Assistant Director/Principal |  |  |  |  |  |  |
| Bookkeeper/Accountant |  |  |  |  |  |  |
| Secretary/clerk |  |  |  |  |  |  |
| Nurse |  |  |  |  |  |  |
| Lead/head teacher |  |  |  |  |  |  |
| Teacher |  |  |  |  |  |  |
| Assistant Teacher |  |  |  |  |  |  |
| Other Teacher/Intern |  |  |  |  |  |  |
| Driver |  |  |  |  |  |  |
| Cook/Food Handler |  |  |  |  |  |  |
| Janitor or Building Maintenance person |  |  |  |  |  |  |

Roughly, what is teacher turnover over the past three years?____________(in percent)

Materials (workbooks, supplies, and other programme components)

| Materials | Number of Units | Amount Spent/Value |
| --- | --- | --- |
| Furniture |  |  |
| Books |  |  |
| Workbooks |  |  |
| Supplies (paints, glue, crayons) |  |  |
| Other |  |  |

Services

MEALS: Do you provide meals or snacks for any of the children for whom you provide care?

______NO (Skip to TRANSPORTATION questions) _______YES (continue on)

Which meals or snacks do you provide? (Mark or Check all that apply)

| ______ a. BREAKFAST | ______ d. MORNING SNACK |
| --- | --- |
| ______ b. LUNCH | ______ e. AFTERNOON SNACK |
| ______ c. DINNER | ______ f. BEDTIME SNACK |

Are these meals included in the tuition or do the parents pay extra for them? [Mark the one that applies]

________ PARENTS PAY EXTRA ________ INCLUDED IN TUITION

TRANSPORTATION: Do you provide transportation to and from children's homes?

______NO (Questionnaire is COMPLETED) _______YES (continue on)

Is transportation included in the tuition or do the parents pay extra for it?

[Mark the one that applies]

_______ PARENTS PAY EXTRA _______ INCLUDED IN TUITION

How much does this transportation service cost annually?

Running costs (rent, utilities, and other)

******

THANK YOU FOR YOUR HELP

PARENT FGD

Introductions.  My name is Tristi Nichols and Sarah Boeckmann.  We have been hired to understand better how the HighScope programme that you all use for your children is meeting your needs and any other ideas you may wish to share with us today.  Let’s go around the circle and introduce ourselves. Confidentiality Clause Provided.

Enrollment

How did you find out about the HS programme?

What influenced your decisions to enroll your child?

Expectations – Your Child

What were your overall expectations from this programme? [Keep open – later probe in the following areas:]

- Preacademic skills--Child learns basic concepts, improves small muscle coordination, and begins to master skills necessary for reading, writing, and arithmetic.

- Motor/physical skills--Child improves his/her coordination, balance and agility through large muscle activities.

- Self-expression skills--Child learns to express him/herself creatively through arts and crafts, music, dance, and/or imaginative play.

- Language skills--Child learns to express his/her thoughts and feelings verbally in a clear and appropriate manner.

- Social skills with peers--Child learns to share and cooperate with other children, to respect them and to understand their feelings.

- Social skills with adults--Child learns to listen to, cooperate with, and respect adults.

- Self-sufficiency skills--Child learns to be independent and to care for him/herself and his/her belongings in a responsible manner.

- Self-assessment skills--Child learns to assess his/her own abilities and behaviors, begins to take pride in his/her accomplishments, and develops a sense of self-confidence.

The Permission Slip Used

The instruments can be made available with a request to the Manitou, Inc. Evaluaton Team.

Permission Slip

PERMISSION FOR CLASSROOM VIDEO TAPING

PERMISSION SLIP

Student’s Name: _____________________________________________________________

School: ______________________________________________________________________

I am the legal parent/legal guardian of the child named above. I understand that the Formative

Evaluation of the HighScope Programme will be videotaping in my child's class by independent consultants from Manitou, Inc. My decision is indicated by my check mark and signature below.

Please check the appropriate circle and sign below.

O  I DO give permission to include my child’s voice and image on tape as s/he participates in a class conducted at ________________________

O I DO NOT give my permission to include my child’s voice and image on tape as s/he participates in a class

Signature of Parent/Guardian________________________________ Date__________

Head Teacher Interview FORM

Introduction Information

| Country : | Number of students in his or her preschool:_____ Boys: _____ Girls: _____ |
| --- | --- |
| Name of School: |  |
| Name of Teacher: |  |

Introductions. Issue Confidentiality Protocol.

Background Information.  How long have you been administering this HS programme?

Please tell us about what are the unique responsibilities as the Supervisor / Head Teacher of the HS programme? For instance, what role does leadership play for a Head Teacher? [Probe: areas related to programme management, instructional leadership, community relations).

And…..what kinds of induction or training do Head Teachers or Supervisors receive related to these responsibilities?

Now, we have looked at your job as Head Teacher or Supervisor.  Now I would like your opinion about what the HS programme brings to your preschool and community?  If you can, please give me an example where you think that HS has “worked”?

Just so that we can recognize how much effort is being invested into the management of a HS programme, tell us a little bit about yourself and the team dynamics here.  Give us examples of some of the most important “best practices” or qualities that you and your HS preschool team believes is essential for the programme to be successful. [Probe: The TEAM….follows the HS standards, …..receives respect from parents, ….is adaptable to children’s changing needs..)

Of those key qualities, please describe any challenges that you and your team may have.

Now thinking critically, in addition to the human and financial resources that you have, what else would be needed to continue the HS on a sustainable basis.

Annex 9:  Sample List of Materials for Each Interest Area

Materials Procured from Discount Supply (USA)

- Classic Rubber Unit							 	220 Pieces

- Mini Dinosaurs								128 Pieces

- Wooden Cubes (1inch)							   90 Pieces

- Fabulous Farm Animals							100 Pieces

- Lacing Beads  								1 Jar

- Unifix Cubes									100 Pieces

- Magna Tiles (32 Pieces)							1 Set

- Lego Education System							1 Set

- Colorations Glue Stick (30)						     	1 Box

- Simply washable Tempera 							6 Containers

- Foam Table- top Unit Blocks						1 Set

- Big Bright Animal Beads							1 Set

- Colorations White Chalk (100 Pieces)					1 Set

- Decorate Your Own Puppy (12)						1 Set

- Whirling Wooden Tops (24)					                    	1 Set

- Alias Rolling Pins (6)							     	1 Set

- New Born Dolls (4)							     	1 Set

- Blue Magnetic Board (20)						     	1 Set

- Reversible Lap Board (20)						     	1 Set

- Pretend Play People (Mummy, Daddy, Son, Daughter)			1 Set

- Dry Erase Markers Colorations (48)					     	1 Set

- Magnetic Wand(20)							     	1 Set

- Sand Art Sun Pendant (12 with 6 funnels0				     	1 Set

- Super Sand Art Figures (12 with 8 funnels)			                    	1 Set

- White Chalk								     	1 Set

- Wooden Wood Chimes (12 Pieces)					2 Sets

- Coloured ABC Beads (600 Pieces)				                    	1 Set

- Wooden ABC Beads (600 Pieces)					      	1 Set

Materials Procured Locally for Preschools [In Dominica]

- 1 rug

- 1 child-size accordion

- 1 frying pan

- 2 small pots

- 4 small plastic bowls

- 2 large plastic bowls

- 1 set wooden mixing spoons

- 1 set spatulas

- 5 plastic plates

- 4 plastic cups

- 1 abc ice tray

- 1 plastic baby bottle

- 2 plastic strainers

- 1 set funnels

- 2 plastic juice squeezers

- 1 set hangers

- 1 set magnetic numbers

- 3 packets jumbo crayons

- 2 picture books

- 1 set hair curlers

- 2 child-sized sunglasses

- 2 small cradle and doll sets

- 5 small baskets

- 2 medium baskets (for storage)

- 1 medium plastic container (for storage)

Annex 10: List of Training Efforts

The table details key areas in which training was provided by country and year.  This impressive list is not comprehensive but it demonstrates the scope of the training efforts undertaken by the ECD Units in participating countries.

Table 1: Training Efforts of the ECD Units By Country and Year

| Country | Year | Topics Covered | Participants |
| --- | --- | --- | --- |
| Dominica | 2010 | Arranging the Learning Space Establishing a Learning Environment | School-level stakeholders |
| Dominica | 2011 | Anecdotes and Small Group Time Learning Environment – Selecting and labeling materials Large Group Time | School-level stakeholders |
| Dominica | 2013 | Introduction to Lesson Planning Active Learning The Indoor Learning Environment | School-level stakeholders |
| Antigua | 2010 | Monthly workshop provided to all centres/ institutions. Brain Development Active Learning Daily Routine. | School-level stakeholders |
| Antigua | 2011 | Active Learning Brain Development Adult-Child Interaction Strategies Daily Routine Planning Time Work Time The Learning Environment Small Group Time Large Group Time | School-level stakeholders |
| Antigua | 2012 | Observation and Anecdotal Record Taking Introductions to the Key Developmental Indicators Lesson Planning | School-level stakeholders |
| Antigua | 2013 | Active Learning Brain Development Adult-Child Interaction Strategies Daily Routine Planning Time Work Time Learning Environment Small Group Time Large Group Time | School-level stakeholders |
| St. Kitts | 2012 | Active Learning The Plan-Do-Review Adult Child Interaction Conflict Resolution Anecdotes, KDI, Small Group Time Large Group Time Language, Literacy and Communication Mathematics in Preschool | School-level stakeholders |
| St. Kitts | 2012 | Special Education Workshop on Autism and other Developmental Disabilities in Young Children Staff Orientation and Development (on-going) | Selected School-level stakeholders |
| St. Kitts | 2013 | Active Participatory Learning Planning Time Small Group Time Child Observation Record (COR) First Aid Certificate Course Leadership Training (on-going) | School-level stakeholders |
| St. Kitts | 2014 | Clinical Supervision Role Playing Workshops (with teachers and parents) | Teachers and Parents |
| Nevis | 2010 - 2011 | General training in HighScope Curriculum Anecdotes and Lesson Planning (on-going) | School-level stakeholders |
| Nevis | 2011 | Active Learning Small Group Time Adult Child Interaction | School-level stakeholders |
| Nevis | 2012 | Greeting Time Message Board Indoor Learning Environment Outdoor Learning Environment | School-level stakeholders |
| Nevis | 2013 | PQA | School-level stakeholders |
| Nevis | 2014 | Conflict Resolution Scaffolding Small Group Time | School-level stakeholders |

Annex 11:   UNICEF-Adapted OECD Evaluation Criteria

| OECD Definition of the Evaluation Criteria | Unicef Adaptation of the Evaluation Criteria |
| --- | --- |
| Relevance: The extent to which the expected results of the intervention address the rights and needs of worst-off groups, reduce inequities, and are consistent with equity-focused development priorities at global, national or local level. | - What is the relevance in relation to the equity approach, as well as foundation strategies such as the Human Rights-based Approach to Programming and gender mainstreaming the Core Commitments for Children in Humanitarian Action (CCCs), and, in the case of Unicef-supported interventions, the Medium Term Strategic Plan)? - What does the literature and current experience suggest about the appropriateness of the current or proposed strategy? If successfully implemented, would this likely address some of the key issues of worst-off groups? |
| Effectiveness: The extent to which the intervention’s equity-focused results were achieved, or are expected to be achieved. | - Are the service delivery systems reaching worst-off groups? - What are the main constraints on supply? - What are the main constraints on demand? - Which programmes/strategies are most and least effective? - What factors explain success? |
| Efficiency: A measure of how economically resources/inputs (funds, expertise, time, equipment, etc.) are converted to equitable results | - Does the programme use resources in the most economical manner to achieve expected equity-focused results? - Are any economical alternatives feasible? - How cost-effective are the public systems for reaching worst-off groups? - How do costs for reaching worst-off groups compare with average public services costs? - How do costs for reaching worst-off groups compare with alternative systems to deliver services to worst-off groups? |
| Impact: Positive and negative, primary and secondary long-term effects produced by a development intervention, directly or indirectly, intended or unintended, for the worst-off groups as well as inequities between best-off and worst-off groups. | - What are the results of the intervention – intended and unintended, positive and negative – including the social, economic, and environ mental effects on the worst-off groups? - How do the results affect the rights and responsibilities of worst-off individuals, communities and institutions ? - To what extent have results contributed to decreased inequities between the best-off and the worst-off groups? |
| Sustainability: The continuation of benefits to the worst-off groups after major development assistance has been completed. Sustainability the probability of continued long-term benefits for the worst-off groups. | - Is the intervention and its impact on the worst-off groups likely when external support is withdrawn? - Are inequities between best-off and worst-off groups likely crease, remain stable, or decrease when external support is withdrawn? - Will the strategy be more widely replicated or adapted? Is it likely to go to scale? |

Annex 12:   Evaluation Firm and Team Profiles

The Firm

Manitou, Inc. is a small, woman-owned and minority-owned firm based in Peekskill (located in the New York Metropolitan Area), operating since 1999. Manitou, Inc. has significant experience administering small and large evaluation projects over short time periods.

The Team Leader

Dr. Tristi Nichols: With advanced formal training in programme planning and evaluation from Cornell University, Dr. Tristi Nichols has been continuously involved in a wide-ranging international evaluation practice over the past fourteen years.  Dr. Nichols is leading the field in developing a framework measuring gender equality, which will be presented in a chapter entitled “Measuring, Conducting, and Interpreting Findings of Evaluations of International Development Interventions Aimed at Fostering Democracy: An Elaboration of Gender Inequality and Ecological Concerns.” This peer-reviewed work will be published through Guilford Press in the Fall 2013. Dr. Nichols has extensive experience evaluating programs that address violence against women, is fluent in English and Portuguese, and has a good working knowledge of French.

Early Childhood Development Curriculum Expert Consultant

Dr. Jennifer Greene:  With an established global reputation as a programme evaluation Thought Leader and practitioner, Dr. Greene is currently, a Professor of Educational Psychology at the University of Illinois at Urbana-Champaign.  While she has published hundreds of works in area of education evaluation, one of her most recent contributions was:  Greene, J.C. (2012). Values-engaged evaluation. In Marco Segone (ed.), Evaluation for equitable development results. New York: UNICEF.

Evaluation Specialist

Sarah Boeckmann: Ms. Boeckmann has five years of progressive experience conducting field research focused on sub-Saharan Africa, as well as conducting desk and literature reviews for the World Bank, including a recent comprehensive case study of social accountability in fragile and conflict-affected States.

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html. Accessed June 17, 2014.

World Travel and Tourism Council “Travel and Tourism Economic Impact 2014” http://www.wttc.org/site_media/uploads/downloads/antigua_and_barbuda2014.pdf. Accessed June 14, 2014.

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html. Accessed June 17, 2014

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html. Accessed June 17, 2014

“Browne becomes new Prime Minister of Antigua, Youngest Ever.” The Miami Herald, June 13, 2014, Jacqueline Charles, http://www.miamiherald.com/2014/06/13/4175779/antigua-prime-minister-baldwin.html#storylink=cpy, Accessed June 17, 2014

Freedom House, Freedom in the World Report 2013: Antigua and Barbuda: http://www.freedomhouse.org/report/freedom-world/2013/antigua-and-barbuda#.U6A_q_ldWSo

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html.

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/do.html Accessed June 18, 2014.

World Travel and Tourism Council “Travel and Tourism Economic Impact 2014”

http://wttc.org/site_media/uploads/downloads/dominica2014.pdf

Q-Finance Country Profile: Dominica http://www.qfinance.com/country-profiles/dominica

Freedom House, Freedom in the World Report 2013: Dominica

http://www.freedomhouse.org/report/freedom-world/2013/dominica-0#.U6LhfPldV5I

CIA World Factbook.

https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html.

CIA World Factbook.

https://www.cia.gov/library/publications/the-world-factbook/geos/ac.html.

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/do.html.

World Travel and Tourism Council “Travel and Tourism Economic Impact 2014”

http://wttc.org/site_media/uploads/downloads/st_kitts_and_nevis2014.pdf

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/do.html

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/do.html

CIA World Factbook. https://www.cia.gov/library/publications/the-world-factbook/geos/do.html

Freedom House, Freedom in the World Report 2013: St. Kitts and Nevis http://www.freedomhouse.org/report/freedom-world/2013/st-kitts-and-nevis#.U6LgdPldV5I

Revised and updated in 2010.

These four countries were selected as they were, at the time, the priority countries under UNICEF ECO’s Multi-Country Programme.

The 13 participating preschool settings consisted of three in Antigua, three in Grenada, three in St. Kitts and Nevis, and four in Dominica.

Please note that the Core Commitments for Children in Humanitarian Action does not apply to this formative evaluation.

E/ICEF/2013/14. (2013). Revised Evaluation Policy of UNICEF. Paragraph 14.

UNICEF. (2014) TERMS OF REFERENCE: UNICEF Office for the Eastern Caribbean Area.

Note that the language of the first objective has been modified slightly to better suit the elements of a formative evaluation.  Specifically, the remaining part of the sentence “bringing all the evidence available to qualify and quantify the outputs (and if possible the outcomes) at the individual, household, school, and community levels.” was omitted, as this would imply that information gathered is for the purpose of quantifying inter-mediate outcomes.  The focus of this formative evaluation, however, is on the quality of programme implementation, taking into account context, among other considerations.  Outcome data and even higher-level (or impact-related) information is currently unavailable.  An analysis of outcome-level results would be unsubstantiated.

Dart, J. Six Normative Approaches to Evaluation.  Accessed at: http://www.clearhorizon.com.au/wp-content/uploads/2009/01/dart-six_normative_approaches.pdf

All definitions for the Evaluation Criteria which inform the structure of this report were derived  from: The DAC Principles for the Evaluation of Development Assistance, OECD (1991), Glossary of Terms Used in Evaluation, in 'Methods and Procedures in Aid Evaluation', OECD (1986), and the Glossary of Evaluation and Results Based Management (RBM) Terms, OECD (2000).

Overseas Development Institute. (2006) Evaluating humanitarian action using the OECD-DAC criteria: An ALNAP guide for humanitarian agencies.  London: United Kingdom, page 18.

This sampling frame was predetermined by UNICEF in the Request for Proposals (RFP) announcement from August 2013.

UNICEF. (2014) TERMS OF REFERENCE: UNICEF Office for the Eastern Caribbean Area.

Data sources took the form of observations.  It is estimated that 362 children were observed while taking part in a specific activity. Please note that this number should be interpreted broadly, as all of the children were observed in group settings and not individually.  The number of observed children does not reflect the total number of children enrolled in the model learning centres.

General questions were presented to a total of four kindergarten students who had experienced the HighScope preschool programme in Nevis and in Dominica.

A total of thirteen parents (five males - 4 fathers and 1 grandfather – and 8 females) were also interviewed directly. 118 parents took part in Focus Group Discussions (FGDs).

A total of 23 interviews were conducted with teachers (and supervisors) and some of whom were implementing the HighScope Curriculum inside and outside the model schools and some of whom were teaching kindergarten classes.

Information was elicited from two kindergarten teachers.  The discussions were focused on understanding better how the children leaving the HighScope model preschool were transitioning to the next level.

Information was elicited from two kindergarten teachers.  The discussions were focused on understanding better how the children leaving the HighScope model preschool were transitioning to the next level.

A total of seven senior officials from the Ministry of Education were interviewed in addition to the staff from the ECD Units working in all of the participating countries.

A total of four UNICEF personnel took part in the evaluation process.  Three UNICEF personnel were actively involved throughout the evaluation process.  One staff member provided education-related expertise to the evaluation team.

A total of six ECD ToTs were surveyed.

A total of ten instruments were filled in.

Thirty-two observation forms were filled-in, indicating that multiple observations were conducted of different classroom activities.

Eight focus group discussions (FGDs) were held with parents exclusively, and one FGD was facilitated with first grade teachers and principals in Dominica only.

This information was accessed at www.HighScope.org. Permission was sought from Dr. Tomoko Wakabayashi at twakabayashi@highscope.org and the Senior Early Childhood Specialist, Shannon Lockhart at SLockhart@highscope.org.

The data from the classroom observation guide was also coded and categorised into a scoring system.

Guba, E. G., & Lincoln, Y. S. (1989). Fourth generation evaluation. Newbury Park, CA., Sage Publications.

UNEG. (2011) Integrating Human Rights and Gender Equality in Evaluation-Towards UNEG Guidance, page 15; and Bamberger, M. and Segone. M UNICEF (2011) How to design and manage Equity-focused evaluations, page 50.

Bamberger, M. & Segone, M. (2012) How to design and manage Equity-focused evaluations.  UNICEF Evaluation Office, New York, NY.