Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu

United Nations Trust Fund for Human Security Project

Reference: CN09-025

Summative/Terminal Evaluation Report

November 2015

Table of Contents

Acknowledgements	v

Abbreviations	vi

Executive Summary	1

1. Introduction	4

1.1 Project description	4

1.2 Country context	4

1.3 Expected results	5

1.4 Theory of change	5

1.5 Beneficiaries	6

1.6 Project strategy	6

1.7 Project partners	7

1.8 Project sites	8

1.9 Project timeline	9

1.10 Evaluation report structure	10

2. Evaluation Objectives and Methodology	11

2.1 Purpose of Evaluation	11

2.2 Evaluation Objectives	11

2.3 Scope of the Evaluation	11

2.4 Evaluation Process	12

2.5 Evaluation Methodology	12

2.6 Evaluation Limitations	13

2.7 Ethical Issues	13

3. Logical Framework	14

4. Evaluation Findings	16

4.1 Relevance	16

4.2 Effectiveness	25

4.3 Efficiency	41

4.4 Impacts	43

4.5 Sustainability	44

4.6 Cross-cutting concerns	47

5. Lessons Learned	49

6. Conclusions	51

7. Recommendations	53

Annex A: Map of project sites	56

Annex B: Logical Framework	57

Annex C: Fund utilization	67

Annex D: Bibliography	68

Annex E: List of people interviewed	71

Annex F: List of sites visited	73

Annex G: Data collection instruments	74

Annex H: Terms of Reference	78

Index of Questions	87

List of tables

Table 1.7: Non-UN executing partners and roles	7

Table 1.8: Project site locations	8

Table 1.9: Important project dates	9

Table 3.1: Components conducted by agencies in project sites and withdrawn locations	15

Table 4.1.1.1: UNTFHS Community Resilience objectives and support to other development frameworks	17

Table 4.1.4.1: Selected human security threats and two area councils per province	22

Table 4.2.5.1: Organizations that conducted disaster risk reduction and management activities by community	30

Table 4.2.5.2: Overlap of area councils between different UNDP projects in Vanuatu	32

Table 4.2.7.1: Food security training and support dates	34

Table 4.2.7.2: Farming materials provided to communities	35

Table 4.2.7.3: Food preservation training	37

Table 4.2.8.1: Cooperatives established in project sites	38

Table 4.2.9.1: WASH interventions	39

Table 7.1 Recommendations	53

List of maps

Map 4.2.5.1: Map of V-CR, PRRP and V-CAP project sites	33

Annex A: Map of project sites with hazard risks	56

# Acknowledgements

This report is the product of a summative/terminal evaluation of the Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu (a United Nations Trust Fund for Human Security project) conducted between July and October 2015. The UNICEF Multi-Country Office in Fiji commissioned this external evaluation to examine the extent to which the programme fulfilled the goals to support human security in Vanuatu. I am grateful for all the support that has been provided throughout this period.

In particular, I would like to thank all the community members, community mobilizers, chiefs and area secretaries for their hospitality, time and thoughts. The strength of their insights is an invaluable contribution to this work. Also, I am grateful to the implementing partners that explained the work they had done and the impact that it had on people’s lives.

I would also like to thank Roslyn Arthur and Rebecca Olul from UNICEF; Donald Wouloseje, Matthew Hardwick and David Malakay from UNDP; and Runte Likiafu from FAO for their time and facilitating my work in the country.

All comments have been helpful in providing additional information and clarifications. Feedback is an invaluable step in the process, and has helped to strengthen the findings and recommendations of the report. I thank all those that took time to read through the report and provided comments.

Finally, I am grateful to UNICEF for making the funds available for this evaluation, as well as the technical and logistical support provided throughout the evaluation process.

It is strongly hoped that the initiatives begun in this programme will continue to address human security needs in Vanuatu. The project activities helped people during Cyclone Pam. More support, however, will be required to ensure that people prepare and are knowledgeable about the adverse effects of climate change and the impacts on their lives. The information and recommendations presented here seek to build on this and strengthen security for all.

David Gullette, PhD

# Abbreviations

ADB	Asian Development Bank

BNPL	Basic Needs Poverty Line

CBO	Community-Based Organization

CDC	Community Disaster Committee

DAC	Development Assistance Framework

DLA	Department of Local Authorities

DRM	Disaster Risk Management

DRR	Disaster Risk Reduction

FAO	Food and Agriculture Organization

FPL	Food Poverty Line

HDI	Human Development Index

HFA	Hyogo Framework for Action

INGO	International Non-Governmental Organization

JICA	Japan International Cooperation Agency

MDG	Millennium Development Goal

MIA	Ministry of Internal Affairs

MTR	Mid-Term Review

NAB	National Advisory Board on Climate Change and Disaster Risk Reduction

NACCC	National Advisory Council on Climate Change

NDMO	National Disaster Management Office

NGO	Non-Governmental Organization

OECD	Organisation for Economic Co-operation and Development

PICTs	Pacific Island Countries and Territories

PRRP	Pacific Risk Reduction Project

TWG	Technical Working Group

UN 	United Nations

UNCTAD	United Nations Conference on Trade and Development

UNDAF	United Nations Development Assistance Framework

UNDP	United Nations Development Programme

UNICEF	United Nations Children’s Fund

UNTFHS	United Nations Trust Fund for Human Security

UPR	Universal Periodic Review

USB	Universal Serial Bus

USD	United States Dollar

V-CAP	Vanuatu Coastal Areas Project

V-CR	Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu

VNSO	Vanuatu National Statistics Office

VUV	Vanuatu Vatu

WASH	Water, Sanitation and Hygiene

# Executive Summary

Project description

The ‘Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu’ (V-CR) project, funded by the United Nations Trust Fund for Human Security (UNTFHS) addressed challenges in remote communities abilities to prepare for and increase their resilience against natural hazards and risks from climate change. The project comprised four main components: disaster risk reduction (DRR) and disaster risk management (DRM); governance and decision making; food and nutrition security; and water security. A fifth component was included focusing on knowledge management. These components contributed towards strengthening the communities’ overall human security.

UNTFHS granted the project over USD 2.9 million dollars. The United Nations Children’s Fund (UNICEF) as the lead agency, together with the United Nations Development Programme (UNDP) and the Food and Agriculture Organization (FAO), implemented project activities in 12 communities (two in each province). The intended number of people to benefit from the project was almost 40,000 people.

The three-year project began in 2010. Due to staffing issues and logistical challenges, the project was extended until August 2015. External consultants conducted a mid-term review in 2014 and included a number of recommendations to facilitate implementation and completion of project activities.

Project evaluation

UNICEF commissioned this summative/terminal evaluation to examine the successes and challenges of the V-CR project, particularly those following the Mid-Term Review (MTR). It utilizes the Organisation for Economic Co-operation and Development’s Development Assistance Criteria: relevance, effectiveness, efficiency, impacts and sustainability. UNICEF has added that the evaluation also examine cross-cutting concerns.

The evaluator conducted fieldwork to some of the project sites and spoke with project stakeholders and UN staff in Port Vila, the capital, to obtain a wide variety of views and understand resilience issues in the communities. The evaluation was conducted from July to October 2015. Fieldwork was conducted in late August and early September 2015.

It is important to note that this evaluation was conducted after Cyclone Pam, which devastated many parts of Vanuatu in March 2015. Some activities may have had a greater impact that was not visible after the cyclone. Other issues arose after the cyclone which may have undone some of the work and weakened communities’ overall resilience. This evaluation attempts to make clear such issues.

Major findings

Relevance

The project identified communities at risk of a range of natural hazards and threatened by the adverse effects of climate change. Project activities strengthened knowledge and skills through trainings and practical exercises. Additional efforts focused on building capacities among local authorities and councils to integrate DRR issues into local development plans and budgeting. Other initiatives focused on strengthening food and nutrition security, and water security, so that communities can become more self-sufficient while addressing challenges for communities to meet basic needs. There were ways to make the project more relevant, such as including education throughout the other components, but overall it addressed a range of complex issues in many communities.

Effectiveness

Relevant project activities helped to promote effective results. The project designers, however, had originally identified area councils and not individual communities, which meant that much larger populations which could not be managed with the human and financial resources allotted through this grant. The designers also attempted to include many remote communities without fully addressing significant logistical issues. This resulted in some activities or full components being withdrawn from some communities. Furthermore, weak coordination mechanisms also created further challenges to ensure the activities had their maximum impact. Despite these challenges, people highlighted the benefits of the project activities for their communities and noted their effectiveness in their ability to survive Cyclone Pam.

Efficiency

The lack of joint coordination and logistical challenges limited opportunities for project activities to be more financially efficient. As noted above, the difficulty to reach some places meant that some activities or whole components were withdrawn from those communities. Had the United Nations (UN) agencies jointly implemented some activities, costs could have been reduced and may have increased the likelihood that fewer activities or components would have been withdrawn from communities.

Impacts

The overall impact was positive and community members expressed their appreciation for the project initiatives. The potential impact was limited, again, due to the broad geographical coverage and the lack of joint coordination and implementation. If fewer communities had been chosen, more activities may have been successfully implemented. Outside of formal coordination mechanisms with state counterparts and other organizations, UN agencies had few joint meetings to discuss project issues. Closer coordination was made more challenging as the head offices of each of the UN agencies were located outside of Vanuatu. These issues lessened the potential positive impact that may have been passed on to communities through enhanced implementation mechanisms and planning.

Sustainability

Comprehensive training sessions, practical demonstrations and exercises in the communities, and, when possible, monitoring and feedback missions helped to make many interventions sustainable. The skills were put into use to prepare for and withstand Cyclone Pam. Community members praised the usefulness of the interventions to protect them and said they would continue to work to integrate them into their own activities. Limited engagement with provincial-level authorities, however, may have omitted a potential sustainability mechanism. Had they been more involved, communications between the community, province and national levels would have been strengthened and DRR needs may be more readily acknowledged and included into provincial budgets.

Cross-cutting issues

Cross-cutting concerns – such as the inclusion of women and persons with disabilities, or general approaches, such as equity or human right based approach – were included in the project, but often addressed not in a direct or deliberate manner. The inclusion of women, in particular, was highlighted in the project proposal, but the logframe indicators did not include explicit criteria to ensure the participation of women, which resulted in lower numbers of women engaged in activities. Civil society organizations, including community-based organizations, were included in the projects, but there were few opportunities to build capacities to ensure that they were able to promote cross-cutting issues through their ongoing work.

Conclusions

The project overall achieved its main goals and people were positive about the knowledge and skills they acquired. An important issue to consider in future programming is to ensure that as many sectors as possible are represented in the DRR activities. For example, education activities, targeting schools and young people, could have been included and would helped to spread resilience messaging and directly engage more people in the project. Also, logistical challenges and joint planning are important, particularly as transportation networks are unreliable or non-existent. This created significant challenges to implement activities and conduct monitoring on their development. These are important issues to address, but the project had an important impact in preparing people against natural hazards and other risks.

Main recommendations

The main recommendations serve to strengthen approaches for future programming, particularly when addressing DRR and climate change issues. The recommendations are divided by the evaluation criteria. In brief, the project could have been more relevant by conducting more research during the inception phase and ensuring that the project activities supported intergovernmental plans, such as the Hyogo Framework for Action (HFA), as well as addressing more formally the interaction between formal and traditional governance approaches. While the project was effective it could have strengthened its coordination and management of project activities. Education could have been included throughout the components to strengthen engagement and awareness. Delays and logistical challenges need to be examined in order to make such projects more financially efficient. Greater impact could be had through ensuring the involvement of women in positions of authority and responsibility. Further impacts could be had through strengthened monitoring and reporting. Project initiatives could be more sustainable through developing a sense of volunteerism and having a repository of knowledge resources in communities in order to share and use them. Also, inclusivity supported through specific equity and human rights-based approaches can integrate cross-cutting issues more thoroughly into project activities.

# 1. Introduction

This section provides an overview of project and its goals, as well as the context in which the project was being implemented. It discusses the roles of the partners and some of the major events throughout the duration of the project.

In this report, ‘community’ refers people living in an area and may be one of several communities that form a village. In some of the project sites, villages are divided into separate communities based on different church affiliation or other forms of identity. A community can be a few households that are set apart from other communities within the general village territory. In some places the term ‘location’ is used to indicate both the area council and corresponding communities.

## 1.1 Project description

This main purpose of the project was to enhance short- and long-term community resilience and coping capacities in 12 locations that are exposed to natural hazards and at risk of the effects of climate change. Advancing the concept of human security, the project sought to provide a holistic approach to strengthening disaster risk reduction (DRR) and disaster risk management (DRM) through training, improving governance to promote action at all levels, food security and water security.

Project designers based initiatives on the commitment of the Pacific Leaders Niue Declaration (August 2008), the United Nations (UN) Secretary General’s message to the Pacific Leaders in Niue and the UN Pacific climate change scoping study (July 2009). A further set of consultations (20-23 July 2010) provided further ideas and refined project activities.

The project had a budget of USD 2,921,122 to be shared by the three UN agencies – UNICEF (lead agency), UNDP and FAO – to implement projects over three years.

## 1.2 Country context

Vanuatu is an archipelago of 83 islands in the south-west Pacific Ocean with a land area of 12,200 square kilometres. It has a population of 280,054 people. Vanuatu has a low human development index (HDI) of 0.616. According to the 2014 HDI report, Vanuatu ranked 131 out of 187 countries. The gender development index, or the female to male HDI ratio, is 0.900 (0.581 for women contrasting with 0.646 for men). The unemployment rate is around 4.6 per cent of the labour force in the formal sector. Roughly 13 per cent of the country lives in poverty. Vanuatu is a lower middle income country with a gross domestic product per capita of VUV 295,000 (USD 3,062). The World Bank ranks Vanuatu at 131 out of 187 countries in terms of income inequality, indicating that inequality is a serious challenge.

## 1.3 Expected results

The expected project results were:

- Twelve (12) selected communities (in the original project proposal this referred to area councils) supported and empowered to identify threats/needs and formulate sustainable interventions within the first 6 to 12 months of the project, and thereafter implement and monitor the interventions (Component 1: Disaster Risk Reduction and Management);

- All six provincial governments and 12 selected communities have capacity to ensure that local development, local-level governance, decision making and the public sector performance enhance community resilience and coping mechanisms during and beyond the project period (Component 2: Governance and Decision Making);

- At least 75% of households (6,000) in the selected communities have enhanced food and nutrition security before and after adverse effect of climate change and natural disasters (Component 3: Food and Nutrition Security);

- At least 75% of households (6,000) in the selected communities have enhanced capacity to and access safe and secure water sources before and after adverse effect of climate change and natural disasters (Component 4: Water Security);

- Information system, threat monitoring and communication systems established in the selected communities within the first 12 months of the project and thereafter maintained (Component 5: Knowledge Management).

## 1.4 Theory of change

The project designers highlighted expected outputs for each component. (No explicit theory of change section was included in the project proposal.)

Component 1: Disaster Risk Reduction and Management – Training of leaders and community members, as well as identification of local ‘champions’ would contribute to the development of comprehensive preparedness plans, response mechanisms and mitigation and adaptation measures. The communities at risk to natural hazards as well as threatened by the adverse effects of climate change would be able to develop plans and promote gender-balanced decision-making methods and forums to promote the resilience of their communities.

Component 2: Governance and Decision Making – The project designers identified the need to build the capacity of community and area council leaders to take action on DRR and climate change issues. As part of this work, the project was to ‘document the interface between traditional and formal forms of leadership so as to develop at least six (6) effective engagement strategies to ensure that governance, decision-making and public sector performance enhance community resilience and coping mechanisms’ (see Section 4.1.5). This was to promote greater gender balance in leadership.

In addition, civil servants were to be trained in order to mainstream community resilience and coping mechanisms into provincial government policies, planning and budgeting formulation. This would introduce standardization into planning and management of policies, and would ensure that resilience issues and coping mechanisms would be a key feature to ensure that initiatives are continued beyond the end of the project.

Component 3: Food and Nutrition Security – Project designers sought to increase the food production and availability through diversified farming. This would make communities more resilient through enabling people to have more access to food and food production processes, and loose fewer nutrients through crop loss. If a disaster were to strike, communities would have greater stores of a variety of food and have greater possibility to provide for themselves.

Component 4: Water Security – Project activities would examine existing and potential water sources to determine sustainability to identified threats and hazards. Based on the findings, communities would develop plans and infrastructure put in place to maintain water and sanitation facilities. This will promote resilience and human security as many communities lack clean water.

Component 5: Knowledge Management – The initiatives included in this component intended to go beyond the usual way in which people and organizations conceptualize knowledge management, which is to ‘expedite and improve the way [they] communicate and transfer knowledge both internally and externally’. It included the strengthening and establishment of evacuation centres. It also focused on promoting and establishing regular reporting mechanisms and annual reviews. This would help to provide a communication link between national and local levels, and advance awareness of resilience issues and opportunities.

## 1.5 Beneficiaries

The project identified 39,711 people (20,254 men and 19,457 women), living in the 12 area councils to benefit from the project. Through capacity-building training, 318 government and non-government actors would also benefit. The estimation on indirect beneficiaries ranged from 30,000 people to the whole population, based on the influence and actors at all levels. The private sector was also considered to benefit through the provision of goods and services for the project.

## 1.6 Project strategy

Project designers grounded the project in the UNTFHS concept of human security. They developed the project to be implemented through line ministries, departments and non-governmental organizations. Capacity-building training would be provided to ensure that implementation and sustainability of the project activities. The project was also aligned with government priorities (see Section 4.1.1) and harmonized with donor-funded and regional projects. This alignment was highlighted through actor mapping and identification of development priorities.

## 1.7 Project partners

UNICEF was the lead UN agency and implemented jointly with UNDP and FAO. See Table 3.1 for UN agency engagement at the community level.

UNICEF oversaw Component 4: Water Security and Component 5: Knowledge Management. This involved facilitating and implementing activities, as well as collaboration with state bodies to conduct activities.

UNDP oversaw Component 1: Disaster Risk Reduction and Management, Component 2: Governance and Decision Making, and some elements under Component 3: Food and Nutrition Security. This involved supporting and conducting trainings, work in the communities and collaborating with state bodies and international non-governmental organizations to implement some activities.

FAO worked through the Office of the Registrar of Cooperatives and Business Development Services and the private sector to implement activities under Component 3: Food and Nutrition Security.

Non-UN executing partners and their roles are described in Table 1.7.

### Table 1.7: Non-UN executing partners and roles

| Counterparts | Role |
| --- | --- |
| State bodies |  |
| Department of Agriculture and Rural Development (Ministry of Agriculture) | Supported agricultural training and interventions in the project communities as well as monitoring |
| Department of Geology, Mines and Water Resources (Ministry of Lands and Natural Resources) | Worked together with UNICEF to support water source assessment and identify necessary infrastructure maintenance or establishment |
| Department of Local Authorities (Ministry of Internal Affairs) | Provided project oversight and monitoring through Project Coordinator |
| National Disaster Management Office | Supported training of community members, provided support to develop template for community disaster coordination and climate change adaptation plans |
| Office of the Registrar of Cooperatives and Business Development Services | Supported strengthening and establishment of cooperatives in communities and monitoring |
| Vanuatu National Statistics Office | Provided technical support in development of initial community profile study |
| Six provincial local governments | Briefed on projects and received (or are expected to receive) proposals from area councils that support continued disaster risk reduction and management proposals to strengthen communities’ resilience |
| Area secretaries | Formal leaders of the area councils received training and included project initiatives with expectation to continue the work of the project and facilitate greater resilience in the communities |
| Non-state bodies |  |
| Traditional leaders | Traditional leaders were trained and often took on critical roles in their communities (such as on community disaster councils) to promote resilience and development |
| Community mobilizers | Positions created through this project to promote awareness of DRR and climate change adaptation issues, and to facilitate the implementation of project activities |
| Civil society |  |
| Non-government organizations (NGOs), community women’s and youth groups, community- and faith-based organizations | Community-level organizations and bodies were included through training, participation in and implementation of project activities |
| Academic and research bodies |  |
| Vanuatu Agricultural Research and Technical College | Provided seeds to be used in agricultural training and farming methods activities |
| International NGOs |  |
| CARE International | Implemented DRR and climate change adaptation activities in several communities under Component 1 (See Table 4.2.5.1) |
| Live & Learn | Implemented DRR and climate change adaptation activities in several communities under Component 1 (See Table 4.2.5.1) |
| Private sector |  |
| Entani Company Limited | Developed an agreement with women from Imaio (Tafea Province) to see handicrafts at the entrance to Yasur Volcano |
| Salome Kalo | Conducted food preservation training in the communities |

The Ministry of Health was identified in the original project proposal as a strategic state partner, but was not engaged in activities.

## 1.8 Project sites

Previous documents listed the names of islands, area councils and villages together without explanation or administrative difference as project sites. The original project proposal noted that activities were to take place in area councils. This created confusion as some area councils have many villages and could not realistically be taken into consideration under this project. Thus, project coordinators focused on specific villages within the selected area councils. This information is not clearly stated in project documents. Table 1.8 identifies the specific communities that were included in this project. (See Annex A for a map of project sites.)

### Table 1.8: Project site locations

| Province | Island | Area Council | Communities |
| --- | --- | --- | --- |
| Malampa | Ambrym | West Ambrym | Baiap |
|  | Ambrym | North Ambrym | Wilit Konkon |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga |
| Sanma | Santo Espiritu | South Santo 1 | Ipayato |
|  | Santo Espiritu | North West Santo | Olpoe |
| Shefa | Emae | Emae | Fononge Marae |
|  | Efate | Tanvasoko | Blacksands |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu |
|  | Tanna | Whitesands | Imaio |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel |

## 1.9 Project timeline

As noted above, project designers began work in 2010. Table 1.9 provides an overview of the main events during the implementation of the project.

### Table 1.9: Important project dates

| 31 March 2010 | UNICEF, UNDP and FAO submitted project Concept Note to United Nations Trust Fund for Human Security (UNTFHS) |
| --- | --- |
| 17 June 2010 | Human Security Unit (HSU) of the Office for the Coordination of Humanitarian Affairs, which manages the UNTFHS, approved project Concept Note for three years. HSU encouraged UNICEF, UNDP and FAO to address 12 points during the development of the project proposal |
| 10 December 2010 | Implementing partners submitted final project proposal submitted to UNTFHS |
| 8 February 2011 | UNTFHS approved project |
| 1 August 2011 | Start of project (as dated in the First Progress Report August 2012) |
| 24 September – 2 October 2011 | Inception mission comprising members of UNICEF, UNDP and FAO visited Vanuatu to finalize the implementation and funding arrangements for the project |
| September 2011 – May 2012 | Initial visits to identify Community Mobilizers in all 12 project area councils |
| August 2012 | First Progress Report |
| September – November 2012 | Baseline survey was conducted in all 12 project area councils |
| March – April 2013 | Training of Trainers workshop (84 representatives) – 2 week workshops for the northern and southern islands |
| 12-16 August 2013 | Lead Farmer training for six project sites in northern islands (held in Luganville, Espiritu Santo Island) |
| 11-15 November 2013 | Lead Farmer training for six project sites in southern islands (held in Tagabe, Efate Island) |
| December 2013 | Third Progress Report |
| March – April 2014 | First Governance Training for Shefa and Tafea Provinces |
| 9 April 2014 | Government of the Republic of Vanuatu requests a no-cost extension until 31 July 2015 |
| May – June 2014 | Mid-Term Review |
| December 2014 | Fourth Progress Report |
| 31 July 2015 | End of project, some activities still ongoing |
| August – October 2015 | Final/Terminal Evaluation, some activities still ongoing |

## 1.10 Evaluation report structure

This evaluation is divided into three parts. The first part focuses on the evaluation development and implementation. Chapter 2 discusses the evaluation objectives and methodology. Chapter 3 discusses the logical framework (logframe) and changes that were made. A full description of the final logframe can be found in Annex B.

The second part describes the evaluation findings. Chapter 4 discusses the results of the project according to the evaluation criteria: relevance, effectiveness, efficiency, impacts, sustainability and cross-cutting issues. The questions included in the terms of reference are provided at the beginning of each section. The questions have been given individual codes and are referenced throughout Chapter 4 where they are relevant to issues discussed. The question codes are indexed at the end of the report in order to easily locate them if required.

The third part provides an analysis of the evaluation findings. Chapter 5 discusses the lessons learned from the project and the impact this has for other projects and programmes. Chapter 6 provides conclusions from the project. Chapter 7 lists the recommendations from the evaluation based on each of the evaluation criteria.

# 2. Evaluation Objectives and Methodology

This section provides information on the evaluation objectives and methodology. The evaluation was based on the plan described in the Inception Report.

## 2.1 Purpose of Evaluation

The purpose of this summative/terminal evaluation is to assess the extent to which the project contributed to the intended purpose ‘to demonstrate enhanced short- and long-term community resilience and coping capacity to at least six categories of adverse effects of climate change and natural disasters, with special attention to women, children and other vulnerable groups, in Vanuatu and to draw lessons learned in applying the human security concept to the rest of the Pacific Island Countries and Territories’.

## 2.2 Evaluation Objectives

The objectives of this evaluation are ‘learning orientated with the objective of understanding what worked well to inform scale-up and/or replication of successful elements of the Project throughout Vanuatu and the rest of the Pacific Island Countries and Territories’.

This evaluation builds on the findings of the Mid-Term Review (MTR) and other documents published during the course of the project. In addition, it will provide a useful guide to government counterparts, implementing partners and civil society organizations in their efforts to support communities to prepare and respond to hazard risks and disasters.

## 2.3 Scope of the Evaluation

The evaluation examines the project development in relation to the 12 project sites, in particular since the MTR. This includes examining programme interventions, changes to the logical framework, successes and challenges. However, some project sites were removed as a result of the MTR recommendations or due to an agreement between project coordinators and UN agencies that work could not be conducted in some areas due to logistical reasons. (Project sites that have been withdrawn have been indicated by component in Table 3.1.)

The primary focus of this evaluation is on:

- Targeted groups (beneficiaries) – all community members in project sites;

- Service providers – community leaders, local and national state bodies.

The evaluation examines the relevance, efficiency, effectiveness, impact sustainability and cross-cutting concerns of the project and the extent to which it built resilience among the target groups and stakeholders. This evaluation follows the Organisation for Economic Co-operation and Development’s (OECD) Development Assistance Committee’s (DAC) criteria. Cross-cutting concerns, however, is not considered within the DAC criteria and is understood in this evaluation to mean the extent to which the project integrated aspects of gender and human rights issues into the activities.

## 2.4 Evaluation Process

The evaluation was implemented in three phases.

Phase 1: Desk review and evaluation design (August 2015) – The evaluator conducted a desk review (see Annex D for the Bibliography) of documents related to the Community Resilience Project and related strategic documents, plans and conflict context documents. The findings from the desk review and evaluation design were included in an Inception Report. An Inception Report presentation to the National Steering Committee, which reports to the National Advisory Board on Climate Change and Disaster Risk Reduction (NAB), was scheduled, but due to timing conflicts, the meeting was cancelled. The Inception Report was discussed with stakeholders to inform them of the intentions of this evaluation and to receive feedback.

Phase 2: Interviews and field site visits (August-September 2015) – The evaluator interviewed project stakeholders in Port Vila and selected project sites (see Annex E for a list of interviews). The evaluator visited sites and spoke with community residents and duty bearers (see Annex F for project sites visited). This provided valuable information and first-hand accounts about interventions and changes brought to the people in those areas.

Phase 3: Report preparation (September-November 2015) – After the field site visits, the evaluator prepared a draft report which was shared with stakeholders for feedback and comments. The feedback and comments were incorporated into the final version of the report.

## 2.5 Evaluation Methodology

The evaluator used four main sources of information to assess the programme. As there were already reports, surveys and monitoring tools gathering up-to-date data, the evaluator did not create additional tools. A list of guiding questions for UN staff and for stakeholders and beneficiaries was drawn up to identify main areas for discussions (see Annex G for guiding questions).

The main sources of information were from:

- Documents – Documents related to the Community Resilience Project and other development issues related to project;

- Interviews – Interviews with staff, strategic partners and beneficiaries for more context on local issues, broader awareness of the programme’s details and personal experiences of change;

- Participatory feedback sessions – Opportunities to gather views from groups of target groups / beneficiaries to promote their voices through the evaluation about project activities and contribute to lessons learned;

- Field site visits – Based on an anthropological approach, there is a high importance to conduct field site visits. Although not enough time is available to conduct detailed field research and the extent to which participant-observation techniques are possible is extremely limited, the evaluator’s strong research and ethnographic experience helped to elicit valuable insights into the implementation and significance of these interventions.

## 2.6 Evaluation Limitations

There are three main limitations to the evaluation. First, the evaluation relies on proper documentation and reporting of issues. Any discrepancies in the reporting will, unfortunately, be reflected in the evaluation.

Second, the evaluator was not able to visit all the project sites. Attempts were made to visit as many project sites as possible without the possibility of lengthy delays in any one place. Many of the project sites are in remote locations and travel is sometimes uncertain. The evaluator requested implementing partners’ guidance on which area councils to visit. The project sites selected reflect a range of different hazard risks so that the impacts of project activities could be understood in different local contexts.

Third, during some interviews there was potential interference from stakeholders. For example, some stakeholders translated and interpreted answers of beneficiaries for the evaluator, or answered on a person’s behalf during an interview. In these cases, the evaluator made a point of asking the question again and getting an answer from the person. This was noted most when speaking with women. It is possible that the evaluator, a man, may have made the women uncomfortable, and that they were sitting in the presence of other men from their communities.

There were some language challenges. The evaluator did not speak Bislama or French. This was not a major problem and was overcome, often with the assistance of someone to translate. In some communities, some people did not speak Bislama, English or French, and this slowed down the conversation as answers were translated several times. Translation has the potential to create misunderstandings. However, there were no major issues detected during this evaluation.

## 2.7 Ethical Issues

The evaluator considered a range of ethical issues and applied the following approaches:

- All people interviewed for this evaluation were informed about the purpose of the work, the interest to interview them and consent was sought before beginning the interview. The informants were also asked for permission to quote them and use their names in the report.

- Children were not interviewed during this evaluation.

- Information was analysed and findings reported impartially and as accurately as possible.

As for the Community Resilience Project (V-CR), the evaluator considers it to have been designed in an ethical way. The project was based on a rights-based approach and does not exclude groups of people. It did not, however, include gender quotas for objective of output indicators so as to ensure gender parity in the participation of activities.

# 3. Logical Framework

The logical framework (logframe) was developed based on the findings of the original consultation workshop conducted by UNICEF with government counterparts and development partners in 2010. The logframe contained four main components through which most activities were implemented:

- Disaster Risk Reduction and Management;

- Governance and Decision Making;

- Food and Nutrition Security;

- Water Security.

There was a fifth component on Knowledge Management. However, this component could have been distributed throughout the other components. Costs for specific requirements, such as the MTR and summative/terminal evaluation could have been covered through a pooled fund or covered by one of the other components.

One issue in the original version of the logframe was that 12 communities were identified for interventions, but implementation was meant to take place at the area council level, which incorporates a number of communities. This created confusion and challenged the ability of agencies to manage implementation effectively across the whole area council.

After the MTR in 2014, a number of changes were made to the logframe resulting in some of the project sites being withdrawn from some components or had specific outputs removed See Table 3.1). Some components were withdrawn from sites due to their remoteness and challenges in shipping materials and conducting monitoring there. In some cases, however, the agencies may not have clearly explained the changes and implications of changes to communities. In Blacksands, for example, the Area Secretary was told in 2014 that project activities would no longer be implemented there. In a discussion with the Area Secretary, he noted his confusion as some activities had been conducted or were meant to be completed, but he understood that all activities were now being withdrawn from the community. This has led to frustration in the community about the lack of implementation and shrinking expectations that some activities will be completed.

An updated version of the logframe has been included in Annex C. Based on the changes to the project following the MTR, only four outputs are ongoing or partially completed and one has been withdrawn.

Table 3.1 provides a list of components conducted by agencies in projects sites and locations where they were withdrawn.

### Table 3.1: Components conducted by agencies in project sites and withdrawn locations

| Project sites |  |  |  | Component 1: Disaster Risk Reduction and Management | Component 2: Governance and Decision Making | Component 3: Food and Nutrition Security | Component 4: Water Security | Component 5: Knowledge Management |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Province | Island | Area Council | Villages (Communities) |  |  |  |  |  |
| Malampa | Ambrym | West Ambrym | Baiap | UNDP | UNDP | FAO | UNICEF | UNICEF |
|  | Ambrym | North Ambrym | Wilit | UNDP | UNDP | FAO | UNICEF | UNICEF |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | UNDP | UNDP | UNDP | Withdrawn | UNICEF – Withdrew Output 5.1 |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | UNDP | UNDP | FAO | UNICEF | UNICEF |
| Sanma | Santo Espiritu | South Santo | Ipayato | UNDP | UNDP | FAO | UNICEF | UNICEF |
|  | Santo Espiritu | North West Santo | Olpoe | UNDP | UNDP | Withdrawn | UNICEF | UNICEF |
| Shefa | Emae | Emae | Fononge Marae | UNDP | UNDP | FAO | UNICEF | UNICEF |
|  | Efate | Tanvasoko | Blacksands | UNDP | UNDP | Withdrawn | UNICEF – Partial implementation | UNICEF – Withdrew Output 5.1 |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | UNDP | UNDP | UNDP | UNICEF | UNICEF |
|  | Tanna | Whitesands | Imaio | UNDP | UNDP | UNDP | UNICEF | UNICEF |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | Vanuatu Red Cross | UNDP | FAO | UNICEF | UNICEF |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | UNDP | UNDP | Withdrawn | UNICEF | UNICEF |

# 4. Evaluation Findings

This section provides the findings from the evaluation and is broken down into the six assessment areas: relevance, effectiveness, efficiency, impact, sustainability and cross-cutting concerns. The guiding questions, included in the Terms of Reference (Annex H), are provided at the beginning of each section and are referenced throughout the text. The guiding questions codes (for example, ‘R1’ or ‘EF2’) are included in parentheses at the end of the paragraph or section (in the case where an explanation runs over several paragraphs) in which answers have been provided. Answers to questions are not limited to their specific sections. Therefore, some answers are related to several different questions (from the same and other sections).

## 4.1 Relevance

R1: To what extent did the Project, as it was implemented, address threats to human security in the selected communities? R2: To what extent was the project considered to be relevant and useful by communities and local governments? R3: How well aligned was the Project to national priorities of the Government of Vanuatu? R4: Are there any critical emerging issues that are not within the scope of the Project?

The project supported government action plans and addressed natural hazard risks and threats from climate change in the project sites. The need for such a project and its value to communities was evidenced by people’s ability to prepare and survive Cyclone Pam. The numerous challenges in the communities demand a strong response from state bodies and international organizations. All the project activities contributed to improved resilience and human security. There were some areas that could have been included, such as education, which would have made the project more inclusive of young people and children. This is an area that should be examined for future programming.

Relevance – ‘The extent to which the objectives of a development intervention are consistent with beneficiaries’ requirements, country needs, global priorities and partners’ and donors’ policies. Note: Retrospectively, the question of relevance often becomes a question as to whether the objectives of an intervention or its design are still appropriate given changed circumstances.’

4.1.1 Supporting development frameworks

The relevance of the project was demonstrated by its support for a number of strategic development processes in Vanuatu. Table 4.1.1 provides details on which frameworks and processes the project supported. (R3)

### Table 4.1.1.1: UNTFHS Community Resilience objectives and support to other development frameworks

| - UNTFHS Community Resilience Objectives | Vanuatu Priorities and Action Agenda 2006-2015 | Pacific UNDAF Outcomes (2008-2012) | Pacific UNDAF Outcomes (2013-2017) | Millennium Development Goals |
| --- | --- | --- | --- | --- |
| - Objective 1: Ten selected communities supported and empowered to identify threats/needs and formulate sustainable interventions within the first six to 12 months of the project, and thereafter implement and monitor interventions (Component 1: Disaster Risk Reduction and Management) | National Strategic Priority 1: Private Sector Development and Employment Creation National Strategic Priority 4: Primary Sector Development, Environment, Climate Change, and Disaster Risk Management | Outcome 1: Pacific island countries develop and implement evidence-based, regional, pro-poor and National Sustainable Development Strategies (NSDS) to address population, poverty, and economic exclusion issues, stimulate equitable growth, create economic opportunities and quality employment, and promote sustainable livelihoods Outcome 4: The mainstreaming of environmental sustainability and sustainable energy into regional and national policies, planning frameworks and programmes; and Pacific communities sustainably using their environment, natural resources and cultural heritage | Outcome 1.1: Improved resilience of PICTs, with particular focus on communities, through integrated implementation of sustainable environmental management climate change adaptation/mitigation, and disaster risk management Outcome 3.1: Inclusive economic growth is enhanced, poverty is reduced, sustainable Decent Work is improved and increased, livelihood opportunities and food security are expanded for women, youth and vulnerable groups and social safety nets are enhanced for all citizens | 1, 7, 8 |
| - Objective 2: All six provincial governments and 10 selected communities have capacity to ensure that local development, local-level governance, decision-making and public sector performance enhance community resilience and coping mechanisms during and beyond the project period (Component 2: Governance and Decision-Making) | National Strategic Priority 3: Good Governance and Public Sector Reform | Outcome 2: National and regional governance systems exercise the principles of inclusive good governance, respecting and upholding human rights; and resilient Pacific island communities participating in decision-making at all levels | Outcome 2.1: By 2017, all women and girls, men and boys will contribute to national development and citizenship to national development and citizenship through opening channels to decision making, improved access to social services, strengthened livelihoods and greater economic security; and together with children and other vulnerable groups, benefit from strengthened protection systems that respond to and prevent violence against them, in line with international standards. Outcome 5.1: Regional, national, local and traditional governance systems are strengthened and exercise the principles of good governance, respecting and upholding human rights, especially women’s rights, in line with international standards | 8, Millennium Challenge |
| - Objective 3: At least 75% of households (6,000) in the selected communities have enhanced food and nutrition security before and after adverse effects of climate change and natural disasters (Component 3: Food and Nutrition Security) | National Strategic Priority 1: Private Sector Development and Employment Creation National Strategic Priority 4: Primary Sector Development, Environment, Climate Change, and Disaster Risk Management | Outcome 1: Pacific island countries develop and implement evidence-based, regional, pro-poor and National Sustainable Development Strategies (NSDS) to address population, poverty, and economic exclusion issues, stimulate equitable growth, create economic opportunities and quality employment, and promote sustainable livelihoods | Outcome 3.1: Inclusive economic growth is enhanced, poverty is reduced, sustainable Decent Work is improved and increased, livelihood opportunities and food security are expanded for women, youth and vulnerable groups and social safety nets are enhanced for all citizens | 1, 8 |
| - Objective 4: At least 75% of households (6,000) in selected communities have enhanced capacity and access to safe and secure water sources before and after adverse effects of climate change and natural disasters (Component 4: Water Security) | National Strategic Priority 4: Primary Sector Development, Environment, Climate Change, and Disaster Risk Management | Outcome 3: Strengthened equitable social and protection services through support to the development of evidence-based policies and enabling environments; and improved capacity to deliver affordable, quality, basic social services with strengthened safety nets and emphasis on equality, inclusiveness and access | Outcome 1.1: Improved resilience of PICTs, with particular focus on communities, through integrated implementation of sustainable environmental management climate change adaptation/mitigation, and disaster risk management | 7 |

In addition, this project came at an important moment to strengthen disaster risk reduction efforts, as the United Nations noted that in 2011 Vanuatu was ‘off track’ on achieving Millennium Development Goal (MDG) 7, which included improving sustainable access to safe drinking water and basic sanitation. (R3)

The project design, however, did not explicitly address issues raised in Hyogo Framework for Action national progress reports. If this had been done, additional components or complementary elements, such as education, could have been included and would have increased the comprehensive nature of the project and its probable impact. (R3)

4.1.2 Site selection

There was general agreement among stakeholders that the site selection did identify area councils that were remote and whose populations were threatened by natural hazards and the adverse effects of climate change. Cherol Ala, the Director of the Department of Local Authorities, stated during an interview for this evaluation that she used two criteria to select project sites: 1) a study indicating the hazard risks for each location; and 2) area councils where few projects had been conducted before. In each of the six provinces, two area councils were selected, providing broad geographical coverage. Indeed, some of the area councils selected, such as West Coast Santo (Sanma Province), are remote and logistically difficult to reach. Little work had been done in some of these places and raised their potential as project sites. (R1, R2)

However, no other indicators were used to justify potential project sites locations during the project design. In particular, poverty indicators were not used. The Vanuatu National Statistical Organization (VNSO) notes that in 2010 noted that incidence of basic needs poverty, as measured by the Head Count Index, indicated that 11 per cent of households or 13 per cent of the population lived in poverty. In a report on child poverty in Vanuatu, the authors indicated that 17 per cent of children lived below the Basic Needs Poverty Line in 2006 and that there were strong regional differences. UNICEF noted that 25.2 per cent of children in Vanuatu may have been living in severe deprivation of one or more dimensions of child poverty, and 4.9 per cent of children may have been living in severe deprivation of two or more dimensions. Another indicator hinting at the lack of nutritional food is the high rate of stunting in Vanuatu, which was 26 per cent of children under 5 years of age in 2013. That was over double the rate for East Asia and the Pacific. (R1)

Poverty in Vanuatu Poverty in Vanuatu is quantified by examining consumption levels, which focus on the Basic Needs Poverty Line (BNPL) and the Food Poverty Line (FPL). The BNPL comprises two components: ‘the cost of a minimum food basket, and an amount of expenditure for “essential” non-food basic needs’. In a joint report by the VNSO and UNDP, separate calculations were made for the two urban centres, Port Vila and Luganville, and rural areas. The FPL ‘has an absolute base (2,100 kilocalories/day per adult equivalent) with items that make up those calories derived from the actual consumption patterns of the lowest three deciles in each of the three areas’. Analysts were able to examine a number of issues related to poverty based on the above criteria from the 2010 Household Income and Expenditure Survey. Based on this information, the VNSO and UNDP produced a report on poverty and hardship. The data, however, was not disaggregated by province. Thus, the category ‘rural’, which comprises over three-quarters of the population, does not provide sufficient information to understand poverty rates in different parts of the country. Wadan Lal Narsey challenged the VSNO’s methods for quantifying poverty. In particular, Narsey criticized the use of the food energy intake methods employed by the VSNO in the construction of the FPL, as well as the multiplier method used to develop the Non-Food Poverty Line and Basic Needs Poverty Line values. Based on his calculations, he noted that ‘more appropriate values for the food poverty lines and non-food poverty lines would give opposite indications: the incidence of poverty is higher in rural areas than urban areas. Moreover, the share of poverty alleviation resources that should be going to rural areas (74%) is totally reversed from that indicated implicitly by the ADB/UNDP report, a mere 33%. Rural areas (a mere 33%). [sic] This has major policy implications for poverty alleviation guidelines in Vanuatu.’ Thus, further work must be done to examine the methods used to quantify poverty and provide more disaggregated poverty data to be able to understand the extent of poverty in the country. This will enable future projects to develop more sensitive criteria for project site locations.

Another issue was that in three provinces, both project sites were located on the same island: Ambae Island (Penama Province), Ambrym Island (Malampa Province) and Espiritu Santo Island (Sanma Province). While the hazard risks were different for each of the sites, more selection criteria would provide more details to judge which area councils would be best served by this project. From a practical point of view, having both sites on the same island did not facilitate implementation of activities or logistics. Sites were separate from each other and did not have any land or air connection. (R1)

The purpose to target remote area councils with few or no project conducted in them is a good approach. Project implementation delays and a lack of coordination and reporting may have contributed to other organization being unaware of V-CR activities in certain areas. The MTR of this project indicated ‘extensive water improvement plans involving a World Bank funded project and a Japanese funded de-salinization plant are slated for Seratamata, Ambae’. A Japan International Cooperation Agency (JICA) desalination plant was established on Aniwa Island (Tanna Province), where V-CR water security activities were conducted. The needs on Aniwa Island are quite great and these activities complemented each other. Nonetheless, it highlights that greater partner mapping needs to be done in order to ensure that duplication of efforts is avoided. (R1)

Moreover, logistical challenges meant that remote sites were difficult to travel to and created problems in the procurement and shipping of materials to those sites. For example, due to the challenges getting to Olpoe (Sanma Province), FAO was not able to conduct its activities under Component 3 in Olope (Table 3.1). (R1, EC2, EF1, I1)

Given these challenges and the three-year timeframe, some people interviewed during this evaluation suggested that working in 12 area councils was too ambitious to be able to complete all the components. Many sites are in need of similar interventions. The choice of sites for this project was good, but this initiative could be replicated in other areas. Nonetheless, there is common agreement among all stakeholders that communities have been better prepared and are able to recover more effectively to hazard risks and disasters.  (R1, EC2, EF1)

These issues were not taken into consideration during the design of the project. The initial scoping mission (2011) and the baseline survey (2012) did not provide any findings that challenged the original project site selection. These types of issues could have been raised during these activities to ensure that the proposed location sites would benefit the most from this project. (R1)

4.1.3 Project activities

At the community level, community members interviewed for this evaluation noted that activities supported human security in their areas. The communities faced a number of challenges in each of these areas and the interventions did address key concerns in the communities. (R1, R2, S1)

Logistical challenges to implement these activities, however, meant that some project sites were removed from components (Table 3.1), selected initiatives were chosen for specific sites and there were delays in procurement. Procurement of some goods can only be done in Port Vila, the capital, and Luganville, the second largest city. Further challenges were encountered in shipping the materials to the project sites. This has caused challenges and resulted in delays in some sites. (EC1, EC2, EC3, EF1)

4.1.4 Disaster risk reduction and management

Climate change and existing hazard risks create significant challenges for many island countries and territories. Disaster risk reduction and management formed a critical component of this project to protect and promote human security. A consultation process took place in 2010 to identify hazard risks and, thus, to select project sites. Extensive consultations were conducted with government bodies, non-governmental organizations and international development organizations in Vanuatu. This helped to identify a number of sites which have significant hazard risks and vulnerability to natural disasters (see Table 4.1.4.1). (R1)

### Table 4.1.4.1: Selected human security threats and two area councils per province

| Province | Selected Human Threat |  |  |  | Selected Areas/Local Councils |
| --- | --- | --- | --- | --- | --- |
| 1. TORBA | 1. Cyclone 1 |  |  |  | Mere Lava |
|  | 2. Rising sea level 1 |  |  |  | Loh Island |
| 2. SHEFA | 3. Cyclone 2 |  | Floods 1 |  | Marae and Finonge |
|  | 4. Tsunami 1 |  |  |  | Black Sands |
| 3. TAFEA | 5. Volcanic eruption 2 |  |  |  | White Sands |
|  | 6. Drought/Shortage of water 2 |  |  |  | Aniwa or Anaichom |
| 4. SANMA | 7. Earthquake 1 | Tsunami 2 |  |  | West Coast |
|  | 8. Floods 2 |  |  |  | Sarakata |
| 5. MALAMPA | 9. Volcanic eruption 1 |  |  |  | West Ambrym |
|  | 10. Earthquake 2 |  |  |  | North Ambrym |
| 6. PENAMA | 11. Rising sea level 2 |  |  |  | East Ambae – Lolowai Sarakata |
|  | 12. Drought/Shortage of water 1 |  |  |  | West Ambae |

Project designers noted, ‘Rising sea levels causes soil salinity and contamination of underground water and the changing precipitation causes storms and floods and both lead to soil erosion, reduced food production, destruction of infrastructure and depletion of fresh water lenses.’ Further, volcanic emissions cause acid rain which destroys crops and contaminates water supplies. (R1)

Access to and communications with the project sites is highly challenging. Some communities, such as Ipayato (Sanma Province), flooding and poor infrastructure maintenance mean that they can be isolated during bad weather. Some communities do not have radio or mobile communication. This increases the need to address risk hazards and prepare for disasters in these communities. (R1)

This was particularly evident when Tropical Cyclone Pam struck the islands. On the evening of 13 March 2015, Tropical Cyclone Pam, a category 5 cyclone, struck Vanuatu, killing 16 people. There was extensive damage. Around 166,000 people were affected on 22 islands, 15,000 homes were destroyed and 75,000 people were in need of emergency shelter. President of Vanuatu, Baldwin Lonsdale, who was attending the Hyogo Framework for Action 2 conference in Sendai, Japan, said, “After all the development that has taken place, all this development has been wiped out.” (R1)

Some sites had limited food supplies after the cyclone as the fruit crop was largely damaged by the rain. In some places, such as Baiap (Malampa Province), it took one month for aid to arrive. This highlighted the vulnerability of these places and the necessity to promote disaster risk reduction and management activities. (R1, R4)

4.1.5 Governance and decision making

In addition to strengthening disaster risk preparedness, UNDP also provided support to strengthen governance capacities. Initiatives supported Vanuatu’s efforts to strengthen its decentralization policy through the promotion of skills and knowledge for area secretaries and other community leaders to improve local-level decision-making processes. Training during workshops also focused on strengthening budgeting and administration issues to continue to promote community-based participation and leadership. (R2, R3, EF1, I1, S1, S2)

Although not explored in detail in the project proposal, the project sought to develop strategies to incorporate both traditional (‘kastom’) and formal (outlined by the constitution and laws) forms of governance in Vanuatu (see Section 1.4). There have been initiatives to highlight the strengths of kastom governance and its role after independence in 1980. This UNTFHS project sought to strengthen the role of area secretaries and promote the engagement with kastom governance. (R2, S1, S2)

At the same time, there was a concern to improve gender equality, both in kastom and formal forms of governance. Women’s limited role in this sphere has been an issue and continues to be a challenge to ensure more equitable development in the communities. Work conducted at the time of this evaluation is focusing on strengthening the work of the Department of Women’s Affairs. (R2, S1, S2, CC1, CC2, CC3)

Project staff have developed area council templates to aid decision-making processes were developed, but it is not clear how many were approved. Moreover, there was no further explicit attempt to document or map the interface between traditional and formal forms of governance. It focused less on the integration of these two forms of governance, but did seek to enhance opportunities for community consultation and feedback. (R2, S1, S2, S3, CC1, CC2, CC3)

4.1.6 Food and nutrition security

Food and nutrition security was another important aspect for the project communities. The original project proposal noted that over 80% of populations in PICTs live within 1.5 kilometres of the ocean or within river basins, the increasing coastal inundation, soil salinity and erosion threaten fresh water and food security. This is the case for many communities in Vanuatu and threatens their ability to grow food. (R1)

Furthermore, according to research on food insecurity, Vanuatu has not achieved the MDG 1c goal: to halve the proportion of people who suffer from hunger. Advances in this area have been undermined by the effects of Tropical Cyclone Pam. (R1, R3)

Another challenge is that land that could be used for planting food is used to plant coconut trees to produce copra. The United Nations Conference on Trade and Development (UNCTAD) estimated that over 60 per cent of the rural population is involved in coconut production. Coconut and copra goods account for around 30 per cent of total exported goods. The global demand for coconut and copra products is helping to keep prices high and result in greater income for rural families. The devastation caused by Cyclone Pam has meant that some communities have lost large number of coconut trees. These could take up to 18 months to grow back and produce fruit. The focus on developing this cash crop means some farmers prioritize land for coconut production instead of for subsistence farming. Together with this, some communities have little knowledge or skills in keeping kitchen gardens. These limitations increase the potential for food insecurity. (R1, R4, EC3)

Cyclone Pam also provided other lessons for the communities. First, the cyclone wiped out the fruit crop in many communities. The cyclone destroyed Aniwa Island’s (Tanna Province) celebrated oranges. This has resulted in a lack of essential vitamins for the community members, but also deprives them of a money-generating opportunity to sell their oranges on other islands. Community members on Aniwa Island worry that it could take several years for the oranges to grow back. (R1, R4, EC3)

Second, due to the scale of the disaster, it took the government two weeks or more to reach remote communities with basic supplies and aid. While the root crops were not damaged and edible, communities quickly ran out and some noted that they had become hungry before the first government relief efforts reached them. Weak transportation links and limited resources mean that communities need to be prepared to become self-reliant in the event of similar disasters. Thus, this component does play an important role in promoting resilience in communities. (R4, EC3)

4.1.7 Water security

Access to clean water sources is a challenge in many places in Vanuatu. The World Health Organizations stated that a person needs from 50 to 100 litres of water per day ‘to ensure that most basic needs are met and few health concerns arise’. In Baiap (Malampa Province), for example, many families rely on 6,000 litre poly tanks for water storage and use. However, in some cases as many as nine families use one poly tank. If the average household size in Vanuatu is 4.8 people and each requires around 50 litres of water per day, then those families have less than three days of water supply, if the tank is full. In dry periods, or when weather patterns change (particularly during an El Niño year such as 2015), people cannot be certain that they will have enough water for their basic needs. (R1, R2, R4, I1)

4.1.8 Knowledge management

There has been a lack of resources for communities to know how to prepare themselves against hazard risks and what to do in the event of a disaster. The main focus of this component was to establish and make operational rural disaster stations, identify and strengthen evacuation centres and undertake quarterly participatory project monitoring (Output 5.1). Project activities did help communities to find safe places to shelter, if available, such as traditional shelters and concrete structures, such as community halls, health centres and schools. (R1, EC1, EF3, I1)

As a result of the activities, more reporting was done on the accomplishments and needs of the communities. This was an important aspect as little or incomplete information exists on many communities. The information and data gathered will provide decision makers with essential details to enable more targeted interventions to promote resilience. (R1, S3)

## 4.2 Effectiveness

EC1: To what extent were the Project’s objectives achieved? EC2: What were the major factors that influenced the achievement or non-achievement of the objectives/goals? EC3: Are there any unexpected outcomes of the Project either positive or negative that had not been planned for?

The project was effective in developing essential knowledge and skills that promoted preparedness and resilience against natural hazards and disasters. It promoted improved governance approaches to address DRR issues and built food and water security capabilities. Some issues, such as the geographical scope and internal coordination mechanisms, perhaps limited the overall effectiveness of the project. If these issues had been addressed during the inception phase, the project activities could have been refined and greater benefits through activities may have been achieved in the communities. Overall, however, the project was effective and helped to raise awareness of vulnerabilities for projects that followed.

Effectiveness – ‘The extent to which the development intervention’s objectives were achieved, or are expected to be achieved, taking into account their relative importance.’

4.2.1 Planning and coordination

In 2010 there was a consultation workshop in which UN agencies worked with state counterparts and other development partners to refine areas for intervention. The consultation process also contained a mapping session which examined provincial-level hazard risks and identified two area councils in each province for potential project implementation. The work clearly identified a range of issues that hinged on strengthening human security through addressing hazard risks. (EC2, R1, R2, R3)

The consultation session, and perhaps also due to a lack of more detailed community-level information, resulted in a project designed for area councils. This, however, overlooked the challenges at implementation in multiple communities in the targeted area councils. Some area councils are small, with only a few communities, but others have many people spread out and have poor road networks or are infrequently reached by flights or ships. Thus, the identification of area councils, as opposed to specific communities, and the ability to access the proposed sites was an issue from the beginning and was not addressed until the MTR in 2014. (EC1, EC2, EC3)

There were also challenges in project coordination. The project proposal described the coordination structure as

(i) [the] National Advisory Council on Climate Change (NACCC) that provides overall oversight, coordination and policy guidance, (ii) NACCC Technical Working Group (TWG) that provides multi-sector technical guidance and coordination (iii) Director of Local Authorities (DLA) in Ministry of Internal Affairs (MIA), as Project Director, and with assistance from a full-time Project Manager, will report project progress to the NACCC; (iv) Provincial Secretary Generals, assisted by Provincial Disaster Coordinators or Provincial Planners, will coordinate project activities at Provincial level; (v) Areas Secretaries or Administrators, assisted by full-time Project Community Mobilizers, will coordinate project activities at Area Council level with existing community committees taking implementation for various project components.

Although comprehensive, there were a number of issues with the coordination structure. First, the NACCC (which became the National Advisory Board on Climate Change and Disaster Risk Reduction, NAB, in 2012) had regular updates on the project (although it was not always quarterly). The MTR authors noted, however, ‘it appears to date that V-CR has had limited interactions with the NAB and no formal V-CR presentations during NAB meetings in the past two years. […Without] the linkage to the NAB there are challenges in delivery of a coordination and lessons learnt in relation to climate change in Vanuatu.’ Interviews with respondents for this evaluation have said that more meetings with NAB took place after the MTR. Furthermore, there were additional calls for NAB to be acknowledged as the National Steering Committee for the project. It is not clear to what extent the TWG contributed to multi-sector technical guidance and coordination. (EC2)

The limited role the NACCC and NAB played in the project was also complicated by the lack of a dedicated project manager/coordinator. Ben Tabi, Principle Development Planning Officer from the Department of Local Authorities, was appointed as V-CR Project Coordinator in addition to his other duties. David Malakay took over as Project Coordinator in 2014. While it is not uncommon for people to take on project coordination roles in addition to their other work, it does mean that the amount of time devoted to this project was reduced. (EC2)

The role of provincial Secretary Generals and Disaster Management Offices was also limited. Project Coordinators briefed Secretary Generals, or Assistant Secretary Generals, in the provinces on the project and the survey conducted in 2012. After this, however, there seems to be limited engagement of provincial figures. Some provincial-level officials were aware of the V-CR project, but did not know any details. (EC2, S2)

This was partly the result of staff turnover, but there was little engagement of the provincial level throughout the project. The MTR recommended ‘Should the V-CR scale back on provincial and Area Council level committees (due to their limited functionality), it is recommended that the V-CR keep the Secretary Generals of the provinces apprised of project work plans and development, in order to promote cooperation with government stakeholders and improve the efficiency of project delivery.’ It does not appear that this was done, or at least not done in each province. The DLA has encouraged area secretaries to put in any incomplete V-CR activities into their budgets and send them to the provincial authorities for consideration. This will help to build a sense of ownership at the local level. However, if provincial authorities are not aware of the V-CR project and its goals, important resilience interventions in area council budgets may be overlooked. (EC1, EC2, EC3, S1, S2)

Community mobilizers were an important resource of the project. Their continued engagement with the community, through established community disaster risk reduction committees or their participation in other projects, is crucial to continuing to strengthen communities’ resilience. The project, however, did not consider the use of UN volunteers as community mobilizers. This was perhaps a missed opportunity. In order to support their work, community mobilizers received a small wage through the project, but many have continued to work for free after the conclusion of the project. Nonetheless, this could have been an opportunity to develop a sense of volunteerism at the community level and encourage other people to take conduct activities and maintain a strong community sense of preparedness. The community mobilizers are seen as the focal points in their communities to promote disaster preparedness actions and are supported by the community disaster committees (CDCs). Thus, community participation is largely a result of actions taken by the CDCs and community mobilizers. There has been limited or no engagement of volunteers or special initiatives by other groups in the communities to promote disaster preparedness and raise awareness of hazard risks through this project. (EC2, R2, I1, S1, S2)

4.2.2 Scoping survey

In 2012 UN agencies and government counterparts conducted a baseline survey in project sites. The baseline survey tool sought detailed information, but was ‘[…] not obviously designed to fully capture the V-CR’s expected project deliverables’. There were also issues with the implementation of the survey, which may have led to poor data collection. The information collected did help to initiate activities, particularly for Water, Sanitation and Hygiene (WASH) initiatives. In 2014 UNDP contracted CARE International and Live & Learn to conduct community-level DRR activities in 11 project sites (see Table 4.2.5.1). (EC1, EC2, EC3, S3)

4.2.3 Structures of authority

The project promoted strengthening and establishing CDCs and communities’ awareness of hazard risks and preparedness measures for natural disasters. While women and youth were incorporated into the activities and have been more active among some chiefs’ councils and in area councils, the project proposal and logframe had few requirements about women’s participation. Component 2.1.3 (Governance and Decision-Making) sought an indicator of having ’12 female candidates (2 per province) successful in provincial council elections’. Increasing women’s participation in government bodies is important, but was an overambitious attempt to establish gender equality that was beyond the scope of this project. (EC2, EC3, R4, I1, S1, CC1, CC2, CC2)

There is a broader question about whether the project had fully identified the issues of working through various structures of authority and to what extent women and youth would be recognized as having authority relating to DRR and resilience issues. Women played an important role in CDCs, cooperatives and other aspects of the project. However, the question is whether women have become recognized as leaders within their communities, especially in relation to DRR and resilience initiatives. This evaluation has not been able to establish that women have taken on a more prominent role in their communities through this project. This is not a suggestion that women and youth should supplant kastom governance, but allow them to be recognized as focal points that are authorized to take decisions on specific issues within the framework of tasks identified by the CDC. The community mobilizers, to a certain extent, do fill this role, but they are mainly men. Stipulations in the logframe could have been made to ensure that more women were community mobilizers. Furthermore, including the Department of Women’s Affairs into the project would have provided support and technical guidance into ways to promote women’s involvement at the community level. (EC2, EC3, R2, R4, EF1, I1, S1, S2, CC1, CC2, CC2)

Another aspect that may not have been fully considered was the role of churches in the communities. The project had activities to engage faith-based organizations. Churches play an important role and have significant authority within the communities. In order to unite communities across church affiliations more focus could have been provided to working with church leaders, perhaps through the facilitation of the Vanuatu Christian Council, project initiatives cold have created opportunities for church to collaborate formally with the CDCs and ensure that churches also became DRR and resilience leaders in their communities. (EC2, EC3, R2, R4, EF1, I1, S1, S2, CC1, CC2, CC2)

This is not a suggestion that community mobilizers, women and youth supplant kastom governance, but to allow them to take on roles with recognized responsibilities and become an important voice in their communities to drive resilience initiatives. (EC2, R2, EF1, I1, S1, S2, CC1, CC2, CC3)

4.2.4 Project management and administration

The project proposal did not identify an inter-agency management structure. All three UN agencies have head offices outside of Vanuatu. UNDP and UNICEF’s main offices are located in Suva, Fiji, and FAO’s office is located in Apia, Samoa. The lack of an internal management and communication system established at the beginning of the project contributed to delays and isolated work plans. (EC2)

High turnover of staff and national- and provincial-level counterparts led to additional challenges in implementation and addressing issues. Staff to oversee components and a contracted Project Coordinator were not brought on until almost one year after the project began. Few people that were involved with the project at the beginning were involved at the end. The lack of a shared document drive means that important documents may have been lost when people left their positions. (EC2)

4.2.5 Disaster risk reduction and management

CDC members expressed their satisfaction with trainings they received in 2012 and said that it provided necessary support, particularly during Cyclone Pam. The knowledge they received and continued work in developing hazard maps and plans in the communities have helped to raise awareness. (EC1, R2, EF1, I1, S1, S2, CC2)

While UNDP has extensive experience in disaster risk reduction, UNICEF has also supported the Hyogo Framework for Action (2005-2010) through promoting improved protection and developing resilience for women and children at national and local levels. This would have also supported the findings of the ‘National progress report on the implementation of the Hyogo Framework for Action [HFA]’ and outlined in the National Disaster Management Office (NDMO) report ‘Education on natural Disaster Preparedness for Sustainable Development’. Both documents were available before the initiation of this project and could have been reviewed during the project development stage. Therefore, UNICEF could have combined efforts with UNDP to support education initiatives, and facilitated Vanuatu’s achievements in complying with its HFA commitments. (EC2, R2, E1, I1, S1, S2, S3, CC2, CC3)

This would have also increased the likelihood that project initiatives would have been sustainable after the completion of the project. UNICEF has games, such as Riskland, that can be adapted to be a helpful resource for children to learn about protecting themselves and others. UNICEF focused instead of WASH and knowledge management components of the V-CR project. (EC2, R2, E1, I1, S1, S2, S3, CC2, CC3)

UNICEF also supported an Education in Emergencies Officer at the Ministry of Education for two years. Although the position was filled after the official start of the V-CR project, this person could have been an important resource to provide technical guidance and adapt and refine initiatives at the community level. According to the project development process documents shared with this evaluator there was no consultation done with education officials in Vanuatu. This is a gap that could have been addressed, especially as delays in staffing and implementation meant that education could have been incorporated into Component 1. UNICEF’s engagement into promoting DRR in schools and engaging the Ministry of Education may have provided greater effectiveness, impact and sustainability to project initiatives. (EC2, R2, E1, I1, S1, S2, S3, CC2, CC3)

Due to delays with the project, the strengthening and establishment of CDCs did not take place until mid-2014. UNDP contracted CARE International and Live & Learn, two international non-governmental organizations (INGOs), to conduct this work (see Table 4.2.5.1). As these activities were conducted towards the end of the project, it reduced the amount of time that was allotted to working with community members, preparing for disasters and establishing disaster management plans through community mapping exercises. The timeframe is a significant factor as an organization new to an area must take more time to understand the specific hazard risks that the communities face, the specific context in those communities, build trust with the communities, conduct a thorough mapping exercise and ensure through monitoring that roles and responsibilities are being carried out for the sustainability of the initiatives. (EC2, EC3, EF3, I1, S1, S3)

### Table 4.2.5.1: Organizations that conducted disaster risk reduction and management activities by community

| Project sites |  |  |  | Organizations working with communities |
| --- | --- | --- | --- | --- |
| Province | Island | Area Council | Communities |  |
| Malampa | Ambrym | West Ambrym | Baiap | Vanuatu Christian Council – not under contract CARE International |
|  | Ambrym | North Ambrym | Wilit Konkon | Vanuatu Christian Council CARE International |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | CARE International |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | CARE International |
| Sanma | Santo Espiritu | South Santo 1 | Ipayato | World Vision – not under contract Live & Learn |
|  | Santo Espiritu | North West Santo | Olpoe | Live & Learn |
| Shefa | Emae | Emae | Fononge Marae | Live & Learn |
|  | Efate | Tanvasoko | Blacksands | Live & Learn |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | CARE International –not under contract |
|  | Tanna | Whitesands | Imaio | Live & Learn |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | Red Cross – not under contract |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | CARE International |

At the time of the MTR, the authors noted that four area councils – North Ambrym, West Ambrym, South Santo 1 and Loh – had all had disaster management plans developed. It was recommended that UNDP focus on developing plans for the other eight areas. Although Live & Learn was contracted to cover Tafea Province, Aniwa was not included in their grant agreement. In other places, such as South Santo 1, where World Vision had already done extensive work and developed community and area council reports, it was not clear that there was a clear distinction, at least in Ipayato community, between the work that World Vision had done and the ways in which Live & Learn were able to complement this. (EC1, EC2, EC3, R1, EF1, EF2, I1, S1, S2)

The allocation of project sites to the two INGOs was unclear. CARE International had been working in Tafea Province for a number of years, particularly in addressing DRR issues, and had established good relations with the communities there. However, they were contracted by UNDP to conduct activities in other areas where they had never worked. Staff were confident in their abilities to conduct the work, despite the short timeframe and the new project sites. Nonetheless, in their area council disaster management plans, CARE International highlighted that such activities should be conducted over a longer period of time. Thus, the quality of what they may achieve may not be as strong as in other communities where they have an established presence. Furthermore, as CARE International did not have ongoing activities or plans or funding to continue their activities in those communities, they recommended that UNDP to monitor the work in the committees. (EC1, EC2, EC3, R1, EF1, I1)

Travel to the communities was scheduled to take place during the cyclone season. This created additional challenges. Furthermore, in December and January it is often difficult to organize activities as people prepare for Christmas and have a number of social events during this time. Due to delays, Live & Learn were only able to carry out a second site visit in some communities after Cyclone Pam. The training may not have been effective given the circumstances after the cyclone. (EC1, EC2, EC3, EF1)

Another issue that arose was whether the two INGOs were meant to strengthen and establish area council disaster management plans or community disaster management plans. CARE International developed area council disaster management plans and developed reports for individual communities (or a majority of them) within the area councils. Live & Learn had understood that they were meant to develop community disaster plans. Live & Learn has experience in implementing DRR activities, but usually as an integrated component of ecosystems adaption projects and food projects. After further discussions with UNDP, it was agreed to provide area council disaster management plan, but that would focus primarily on the project communities. (EC1, EC2, EC3, R1, EF1, I1, S1)

CARE International developed an area council disaster management plan template and shared it with the Vanuatu Red Cross and NDMO. The template was not reviewed in time before CARE International planned to begin work in the project communities and was not able to incorporate changes that were suggested later. UNDP requested that Live & Learn utilize templates developed by the Vanuatu Red Cross and NDMO. (EC1, EC2, EC3, EF1)

Thus, the community disaster management plans, which serve to a certain extent as community mapping resources, have been completed, but are based on different templates and have different approaches. This will create a challenge for other projects to utilize them in the future. (EC1, EC2, EC3)

There is potential for overlap between UNDP projects that focus on some aspect of DRR or resilience. The Pacific Risk Reduction Project (PRRP) and Vanuatu Coastal Areas Project (V-CAP) share some sites, particularly in Tafea and Torba Provinces (see Table 4.2.5.2 and Map 4.2.5.1). Delays in the V-CR project meant that the baseline and groundwork for other projects did not exist. Instead, the work on the PRRP and V-CAP projects has retroactively informed what kind of information should be sought in the V-CR project sites. (EF2)

### Table 4.2.5.2: Overlap of area councils between different UNDP projects in Vanuatu

| Project | Provinces |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Malampa | Penama | Sanma | Shefa | Tafea | Torba |
| V-CR | West Abrym, North Ambrym | East Ambae, West Ambae | South Santo 1, North West Santo | Emae, Tanvasoko | Aniwa, Whitesands | Loh, Mere Lava |
| PRRP |  |  | South Santo 1, North West Santo |  | Aniwa, Whitesands |  |
| V-CAP | South East Malekula, West Epi | Central Pentecost | South Santo 2 |  | Aneityum, Aniwa, Futuna | Hiu, Loh, Toka, Megua and Metoma |

#### Map 4.2.5.1: Map of V-CR, PRRP and V-CAP project sites

4.2.6 Governance and decision making

It would be an overestimation to state that the project was able to bridge divides between kastom and formal forms of governance. The project was designed to ‘involve top-down policy guidance, technical guidance and financial support’, while also providing ‘bottom-up dialogue with the view of identifying Pacific-tailored tools, guidelines, regulations and legislation for short-term and long-term community coping capacity and resilience’. However, with a stronger focus on community-level activities, the project missed an opportunity to strengthen the flow of information and communication between local and national levels. For example, provincial disaster management officers were not included in the trainings or engaged directly as part of the project. Thus, some provincial disaster management officers were unaware of the project goal and uncertain how they should or could assist with ensuring the maintenance of the resilience measures developed in the communities. (EC1, EC2, S1, S2, CC3)

4.2.7 Food and nutrition security

Many communities have food and nutrition security issues. Project activities sought to improve the availability, variety and resilience of crops to the communities. Many people noted to the evaluator that this was a particularly important aspect of the project. Table 4.2.7.1 provides information on the dates of trainings held outside and in the communities, Field Days (during which crops harvested were presented to demonstrate their growth and to talk about the methods), and any follow-up mission dates. It should be noted that due to the challenges of working in Olpoe (Sanma Province), it was removed from the project activities for Component 3: Food and Nutrition Security. (EC1, R1, EF1, I1, S1, S2, S3)

### Table 4.2.7.1: Food security training and support dates

| Project sites |  |  |  | Regional Training dates | Local training support dates | Field Day date(s) | Follow-up mission dates |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Province | Island | Area Council | Communities |  |  |  |  |
| Malampa | Ambrym | West Ambrym | Baiap | 11-15 November 2013 | 18-19 August 2014 | 13 October 2014 | 18-19 August 2014 |
|  | Ambrym | North Ambrym | Wilit | 11 -15 November 2013 | 21-22 August 2014 | No | 21-22 August 2014 |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | 12-16 August 2013 | 20-22 October 2014 | 10 June 2014 | 20-22 October 2014 |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | 12-16 August 2013 | 30 Sept – 3 October 2014 | 30 Sept – 3 October 2014 | 30 Sept – 3 October 2014 |
| Sanma | Santo Espiritu | South Santo | Ipayato | 12-16 August 2013 | 13-14 August 2014 | 13-14 August 2014 | 13-14 August 2014 |
|  | Santo Espiritu | North West Santo | Olpoe | No | No | No | No |
| Shefa | Emae | Emae | Fononge Marae | 11-15 November 2013 | 12-13 August 2014 | 12-13 August 2014 | 3-5 October 2014 |
|  | Efate | Tanvasoko | Blacksands | 11-15 November 2013 | 12-13 August 2014 | No | 12-13 August 2014 |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | 11-15 November 2013 | 3-4 Sept 2014 | No | 3-4 Sept 2014 |
|  | Tanna | Whitesands | Imaio | 11-15 November 2013 | 1-3 October 2014 | No | 1-3 October 2014 |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | 12-16 August 2013 | 1-3 October 2014 | 1-3 October 2014 | 1-3 October 2014 |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | 12-16 August 2013 | 13-15 October 2014 | No | 13-15 October 2014 |

The project also provided seeds and farming equipment to the communities. Table 4.2.7.2 provides information on the types of crops planted in each community and farming equipment provided. It is important to note that no follow-up missions were conducted following Cyclone Pam. Thus, there is no full account as to what extent the crops have been damaged and what additional support is required to promote food and nutrition security in the communities. (EC1, R1, EF1, I1, S1, S2, S3)

### Table 4.2.7.2: Farming materials provided to communities

| Project sites |  |  |  | Type of crop(s) planted (species) | Type of farming equipment provided | Damaged by Cyclone Pam (Y/N) | Total loss of crops due to Cyclone Pam (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Province | Island | Area Council | Communities |  |  |  |  |
| Malampa | Ambrym | West Ambrym | Baiap | Manioc Kamala Yams – [died] | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
|  | Ambrym | North Ambrym | Wilit | Manioc Kamala Yams | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | Manioc Taro Yam Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | Navia Yam Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
| Sanma | Santo Espiritu | South Santo | Ipayato | Navia Yam Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
|  | Santo Espiritu | North West Santo | Olpoe | No | No | No information | No visit after Cyclone Pam |
| Shefa | Emae | Emae | Fononge Marae | Yams Kamala Manioc | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
|  | Efate | Tanvasoko | Blacksands | Manioc Yams Kamala Taro | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | Manioc Yams Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
|  | Tanna | Whitesands | Imaio | Manioc Yams Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | Manioc Yams Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | Manioc Yams Kamala | Spades Forks Hoes | Yes | No visit after Cyclone Pam |

There were several challenges with this intervention. Some of the seeds provided by the Vanuatu Agricultural Research and Technical College did not grow well. There are a number of reasons for this, but primarily the seeds were not transported to the community and planted within a recommended period of time. Other reasons included the seeds did not adapt to the local conditions or insufficient water in the soil. In other places, particularly near volcanoes, the volcanic ash and acid rain killed some of the plants that had grown. (EC1, EC2, EC3, R1, I1)

Communities near volcanoes asked for high tunnels (or polytunnels) to protect the plants. Community members said that they did not have the money to purchase the required materials. In communities where they had high tunnels, such as in Imaio where CARE International had provided one through a separate project, the high tunnel blew away during Cyclone Pam. High tunnels and other protective materials may have been more effective than testing out new seed varieties if there was insufficient soil and water information available. (EC1, EC2, EC3, R1, I1)

Another issue that some communities reported was the presence of different varieties of insects. Community members noted that after Cyclone Pam they had found different types of insects present which were damaging their crops. Such developments suggest that protective materials may be a good investment for future food security initiatives. (EC1, EC2, EC3, R1, I1)

FAO also supported a food preservation training, which was conducted by Salome Kalo, an entrepreneur, in 2014. She conducted training on food preservation techniques using solar dryers and a hands-on demonstration on how to build the dryers. Training sessions were conducted in all but two sites, Olpoe (Sanma Province) and Mere Lava (Torba Province) because of their remote location and logistical challenges (see Table 4.2.7.3 for more information on the project sites). (EC1, R1, EF1, I1, S1, S2, S3)

### Table 4.2.7.3: Food preservation training

| Project sites |  |  |  | Training conducted (Y/N) | Monitoring (Y/N) | Solar dryer damaged during Cyclone Pam (Y/N) |
| --- | --- | --- | --- | --- | --- | --- |
| Province | Island | Area Council | Communities |  |  |  |
| Malampa | Ambrym | West Ambrym | Baiap | Yes | No | No |
|  | Ambrym | North Ambrym | Wilit | Yes | No | No |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | Yes | No | No |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | Yes | Yes | Yes |
| Sanma | Santo Espiritu | South Santo | Ipayato | Yes | Yes | No |
|  | Santo Espiritu | North West Santo | Olpoe | No | No | No |
| Shefa | Emae | Emae | Fononge Marae | Yes | No | No |
|  | Efate | Tanvasoko | Blacksands | Yes | No | No |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | Yes | No | No |
|  | Tanna | Whitesands | Imaio | Yes | Yes | No |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | Yes | No | Yes |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | No | No | No |

The training sessions covered four areas, including dryer construction, food preservation, food hygiene and value added through production. Solar dryers were made from local materials with only a few parts that needed to be procured from an ironmonger. In three of the project sites she was able to see the first attempts to build the solar dryers and preserve food. She also worked with the communities to understand the fast income-generating potential of the preserved foods when sold to the local markets. The initial results were positive and people were engaged in the activity. (EC1, R1, EF1, I1, S1, S2, S3)

Following the training sessions, Kalo discovered that some of the participants were unable to train others on all the methods. She received requests to do hold training sessions. The strong potential of this project was limited and needed further inputs, such as more manuals and monitoring, to ensure that the activity was sustainable. (EC1, EC3, EF1, I1, S1, S2)

4.2.8 Cooperatives

Cooperatives were strengthened or established to promote food security and provide a small income. The process usually involves a six-month probationary period before they are given official approval by the Office of the Registrar of Cooperatives and Business Development Services for it to continue. However, due to the need to approve the cooperatives in the project sites to enable UNDP and FAO to fund them, the Cooperative Office agreed to fast-track applications (see Table 4.2.8.1 for a list of cooperatives established). This was good for the cooperatives, but did not allow time to see if the establishment of the cooperative and their focus were sustainable. There are positive views, however, that the cooperatives in the project sites are sustainable. (EC1, R1, EF1, I1, S1, S2, S3)

### Table 4.2.8.1: Cooperatives established in project sites

| Project sites |  |  |  | Cooperative type |
| --- | --- | --- | --- | --- |
| Province | Island | Area Council | Communities |  |
| Malampa | Ambrym | West Ambrym | Baiap | Savings and loan – focusing on copra |
|  | Ambrym | North Ambrym | Wilit Konkon | Savings and loan – focusing on livestock |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | Pig farm |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | Poultry |
| Sanma | Santo Espiritu | South Santo 1 | Ipayato | No information |
|  | Santo Espiritu | North West Santo | Olpoe | Retail shop |
| Shefa | Emae | Emae | Fononge Marae | Handicrafts |
|  | Efate | Tanvasoko | Blacksands | Savings and loan – has not been funded |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | Retail shop |
|  | Tanna | Whitesands | Imaio | Retail shop Handicrafts (joint partnership with Entani Company Limited ) – yet to open |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | Savings and loan |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | Site removed by FAO, due to difficulty to access it |

Some communities established savings and loan cooperatives. This is a new business type for Vanuatu, but it is an older approach in other countries. Accessing finance from banks and financial institutions is hard and the interest rates are too high. Interest rates from financial institutions – it depends on the type of loan you are applying for. The interest rate is often 15 per cent, but ranges from 13 to 20 per cent. For most cooperatives it is 10 per cent interest. (EC1, R1, EF1, I1, S1, S2, S3)

A fixed amount of money VUV 400,000 (nearly USD 3,500) was allotted for each cooperative in order to help with its establishment and purchase of any necessary items or materials. The fixed amount, however, did not allow for community members to establish more costly cooperative businesses that may have contributed to food security and livelihood development. For example, some communities wanted to establish cooperatives to facilitate fishing in the local waters. The cost of inputs, such as a boat, motor, nets, refrigerators and freezers (as well as generators to power them), were prohibitive under the allotted amount. (EC1, EC2, EC3)

For those cooperatives that want to sell copra or other goods, they will have difficulty reaching markets. Shipping is infrequent and dictated by the weather. Any perishable goods may not make it to markets. (EC2, EC3)

4.2.9 Water security

Many communities do not have sufficient clean water for drinking and cleaning purposes. This is a challenge throughout Vanuatu. An important focus of this component was to provide training in basic plumbing and maintenance to be able to utilize effectively existing infrastructure. UNICEF also supported the installation of new fixtures (see Table 4.2.9.1). Other support also focused on conducting an assessment of water needs. Due to a number of issues, this assessment was carried out towards the end of the project and was ongoing during the evaluation field mission. (EC1, EC2, EC3, R1, R2, EF1, I1, S1, S2)

### Table 4.2.9.1: WASH interventions

| Project sites |  |  |  | Water security measures |
| --- | --- | --- | --- | --- |
| Province | Island | Area Council | Communities |  |
| Malampa | Ambrym | West Ambrym | Baiap | - 2 x 6,000 litre tanks; - WASH committee, plumbers and sanitation training completed; - Water safety and security plan completed |
|  | Ambrym | North Ambrym | Wilit Konkon | - 2 x 6,000 litre tanks in Konkon village. Co-funded Wilit direct gravity fed water supply with Rotary Club; - WASH committee, plumbers and sanitation training completed; - Water safety and security plan completed |
| Penama | Ambae | East Ambae (Lungei Tagaro) | Lolowai (Seratamata) | - Site removed. Other agencies installed bore hole at Seratamata and desalination unit at Lolowai |
|  | Ambae | West Ambae (Walaha area – Nduindui) | Nanako Navitora Vatiwaga | - Gutters repaired on existing water tanks; - WASH committee, plumbers and sanitation training completed |
| Sanma | Santo Espiritu | South Santo 1 | Ipayato | - WASH committee, plumbers and sanitation training completed; - Water safety and security plan completed; - Direct gravity-fed water system repaired and spring sources protect by building secure dam |
|  | Santo Espiritu | North West Santo | Olpoe | - WASH committee, plumbers and sanitation training completed; - Direct gravity-fed water system repaired |
| Shefa | Emae | Emae | Fononge Marae | - Water safety and security plan completed; - 2 x 6,000 litre tanks installed before Cyclone Pam; - WASH committee, plumbers and sanitation training completed |
|  | Efate | Tanvasoko | Blacksands | - 2 x 10,000 litre water tanks installed |
| Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu | - WASH committee, plumbers and sanitation training completed; - Water safety and security plan completed; - 2 x 6,000 litre tanks installed; - Gutters repaired to feed existing tanks (damaged by Cyclone Pam and now being rehabilitated) |
|  | Tanna | Whitesands | Imaio | - Reticulated water system rehabilitated (later damaged by Cyclone Pam); - Installed 2 x 6,000 litre tanks as holding tanks; - Installed 9 tap stands in community; - Completed water committee plumber and sanitation trainings |
| Torba | Loh | Loh | Vipaka Rinura Telaklak Lungharigi | - 4 x 1,100 litre tanks and 3 x 6,000 litre tanks installed; - Repair of cutters on existing catchment; - Plumbers, water committee training and sanitation training completed |
|  | Mere Lava | Mere Lava | Aot Tasmat Levatmise Lekwel | - 4 x 1,100 litre tanks installed; - Water committee plumbers, and WASH training completed |

Community members noted how important the training and installation of new fixtures was for them. They noted, however, that much more is required in order to provide more security. Many of the poly tanks seen during the field mission were not full and would only provide a limited amount of water for many family members (see Section 4.1.7). The assessment should provide a more comprehensive picture to enable better targeting of activities in the future. (EC1, EC2, EC3, R1, R2, EF1, I1, S1, S2)

4.2.10 Knowledge management

A main focus of the project proposal was to strengthen or establish disaster shelters. This was not achieved during the project, but work was conducted to identify buildings or structures that could be used during a disaster. Since Cyclone Pam, no work has been done to assess whether those buildings and structures withstood the cyclone or were damaged in some way. In some community, many traditional-style houses (made with palm fronds and other natural materials) were destroyed. Furthermore, no training or materials were provided to help community members assess whether the buildings or structures were still safe following a disaster. This is an area that could be examined further in future programming. (EC1)

The concept of ‘human security’ as described by the UNTFHS was not found to be widely understood or recalled if it had been described in trainings. Few materials were developed to remain with government partners or in the communities to explain the concept and provide guidance on how to strengthen human security beyond the timeframe of the project. (EC1, R1)

Another important point was that there was a high turnover of staff in government bodies and in UN agencies. This, combined with the lack of a dedicated repository of documents, meant that much information was incomplete or may have been lost. In other cases, electronic versions of documents were corrupted or contained viruses. For example, in Imaio (Tafea Province), the community mobilizer had viruses on his universal serial bus (USB) drive and on his computer. He had saved the documents on his smartphone and was able to transfer to those. However, if there had been a central repository of documents, these could have been easily backed up and would have provided a full overview of reports and activities conducted in all project sites. (EC1, EC2, EC3)

## 4.3 Efficiency

EF1: Has the Project reached the expected numbers and type of beneficiaries (i.e. individuals/communities/institutions/organizations/groups, etc.) within the expected timeframe? EF2: To what extent has the Project reduced duplication among participating UN Agencies, reduced transaction costs and maximized synergies among national partners? EF3: What were the gains and losses caused by deviation of the Project from the original project proposal?

A lack of a project management plan, staff hiring delays and logistical challenge created efficiency issues for the project. UN agencies largely worked separately which precluded the opportunity to plan joint missions, which would have reduced overall transportation costs. Other activities were delayed or were unable to be implemented in some communities due to their remoteness and challenges to reach them. Thus, not all people expected were reached by the project.

Efficiency – ‘A measure of how economically resources/inputs (funds, expertise, time, etc. are converted to results.’

Some ambitious plans were not feasible within this project due to logistical, management and coordination challenges. One of the main issues that emerged was the original focus was on areas councils. UN agencies were not able to cover entire area councils as the communities were spread far apart and sometimes logistically difficult to reach, but also there were not enough resources to carry out activities on such a level. The complexity of this level of implementation contributed to delays. The transition to focus on individual communities meant that not all people targeted as beneficiaries in the project proposal were reached. This more limited approach, however, was likely more effective and allowed UN agencies and partners to attend to specific community issues in more detail. (EF1, EF3)

The actor mapping during the consultation process in 2010 was sufficient to identify ongoing activities and reduced the possibility of duplication. In some cases, UNDP was able to identify other partners working in some of the project sites, such as the Vanuatu Red Cross, and build on their initiatives for this project. The V-CR project provided some lessons learned for the implementation of the Pacific Regional Risk Project (PRRP) and the design of the Vanuatu Coastal Areas Project (V-CAP), both of which were ongoing during this evaluation. There are possibilities, however, that the limited coordination and reporting may have created a situation where other partners were not aware of the V-CR project and implemented activities in the same communities. In Ipayato (Sanma Province), for example, World Vision implemented a project there on DRR and DRM issues after the V-CR project had begun. (EF1, EF2, R1, I1)

Within the project, there was little duplication between agencies. Each agency oversaw its own component. Only Component 3: Food and Nutrition Security was conducted by FAO and UNDP. However, the agencies split the sites between them and activities were conducted through the Office of the Registrar of Cooperatives and Business Development Services. Thus, there was no overlap between agencies on specific activity types. (EF2)

Yet, the agencies’ individual focus areas may have missed an opportunity to increase project efficiency. For example, beyond the initial scoping mission, UN agencies did not actively seek to combine missions to communities or to identify ways to implement jointly activities. Such efforts could have reduced complicated travel arrangements and logistics expenditures. It is, of course, difficult to say whether delays to one activity or unexpected changes in transportation or shipping connections between islands would not have created more challenges for the implementation. However, combining project initiatives and work plans would most likely have caused significant delays to any particular agency or component. In fact, it may have increased the visibility of the project and its goals as agencies worked together and implemented activities together. This is an area where inter-agency coordination outside of NAB presentations and reporting, as well as and joint financial mechanisms could have identified potential collaboration benefitting all agencies. (EF2)

The challenges to reach the communities, lack of coordination and, ultimately, the withdrawal of some activities or whole components from communities led to some frustration. Some people were bewildered and dissatisfied with the way in which some activities or whole components were not implemented in their communities. In some cases, as in Blacksands (Shefa Province), created confusion between the Area Secretary and community as to why project initiatives were not conducted. An improved joint communication should be provided to communities so they are able to monitor the progress of activities and raise questions to UN agencies about implementation of specific components. (EF1, EF3, EC1, EC2, I1)

As for fund utilization, in the final annual report, most of the agencies had spent over half of their allotments for each component with activities increasing in the final year. See Annex C for the final fund utilization chart. This is not unusual as project activities usually increase towards the end of the project, but the delays suggest that a more even implementation throughout the project could have been achieved. Note, however, that no cost-benefit analysis was conducted at this project. This evaluation has not attempted to conduct such an analysis. An attempt to do so would need to consider the shift from area councils to communities. This would indicate that the original expected output for money would be far less now after few people would have been reached through the project. (EF3, S1)

## 4.4 Impacts

I1: How and to what extent has the Project contributed to enhance short- and long-term community resilience and coping capacity, with a particular focus on the most vulnerable?

Disaster preparedness and methods to strengthen resilience, particularly in areas at risk of natural hazards and threatened by climate change, were important measures and had a noted positive impact by community member. Some issues emerged that reduced the overall impact of the project. An overambitious geographical scope created significant logistical challenges and resulted in some activities being withdrawn from some communities. The project also did not address communication issues between UN agencies or facilitate collaboration between state partners. There was a lack of communication and collaboration between state departments at all levels, which led to more sectoral and less integrated approach to address communities’ needs. Activities could have had a stronger impact on the role of women and their engagement in community activities.

Impacts – ‘Positive and negative, primary and secondary long-term effects produced by a development intervention, directly or indirectly, intended or unintended.’

Trainings and workshops provided an important opportunity to learn new techniques and skills. Many community mobilizers and CDC members highlighted how they have conducted trainings in other communities to teach others what they learned. Such kinds of outreach work are important for the broader impact and continued sustainability of the project. (I1, R2, EC2, EF1, S2)

The strengthening and establishment of CDCs has been an important impact that has long-lasting significance for communities. They have a structure to discuss and initiate activities to promote preparedness and protection against hazard risks. Their continued engagement and decisions have an important effect on preparedness and resilience issues. The importance of the CDCs has been strongly noted after Cyclone Pam. (I1, R2, EC1, S2)

There is a challenge, however, as there was insufficient monitoring of outreach activities. As the project produced few resources to remain in the communities, people conducting outreach activities must draw on their memories. Accuracy of advice may diminish over time and without updates, new views on protection and resilience will not be communicated to the vulnerable. (I1, R2, EC1, S2)

The lack of monitoring also highlights additional challenges in establishing and maintaining communication channels. The project did not establish effective communication mechanisms between national-level government departments or include the provincial level in activities. Outside of the NAB and any working groups, the evaluator found little communication between departments on issues related to the project or similar areas of joint concern. This suggests that government resources will not be joined together to reduce costs and strengthen approaches to addressing DRR or more broad resilience issues in these communities. Moreover, the limited engagement with provincial bodies means that there is a potential gap in the line of support and communication between the communities and government bodies. (I1, EC2, EF3, CC2)

The provision of seeds, tools and knowledge sharing have had an important positive impact on communities. Some community members continue to use demonstration plots. The seeds and produce have been shared with other community members so that they may grow the plants for their own households. This is contributing to improving food security. (I1, R2, EF1, S2)

The lack of selection criteria of participants for the food security workshop, however, meant that mostly men attended. Women’s limited involvement may reinforce their constrained participation in decision-making forums and in becoming respected leaders, particularly on farming. Many women are engaged in farming, but their work and recognition are often understated. By not making clear selection criteria and ensuring women’s participation, the project did not make a strong contribution to women’s empowerment. (I1, R2, EC2, EF1, S1, CC1, CC2, CC3)

## 4.5 Sustainability

S1: To what extent has capacity (human and financial resources) been built in the area councils and communities to effectively increase human security through local-level planning and disaster risk management? S2: To what extent has the project promoted national ownership? S3: To what extent have standardized methodologies been developed, documented and endorsed?

Project activities have proven their sustainability and necessity by helping people to survive Cyclone Pam. The knowledge and skills developed during training and community-based activities facilitated preparedness measures and actions during and after the cyclone. Community members are also able to maintain water infrastructure and have new methods to grow food, which was witnessed during the evaluation mission. Other methods could have been applied to ensure greater community-wide engagement in DRR activities and facilitate strengthened communication and collaboration between communities and state bodies at all levels.

Sustainability – ‘The continuation of benefits from a development intervention after major development assistance has been completed. The probability of continued long-term benefits. The resilience to risk of the net benefit flows over time.’

The continued existence of CDCs, cooperatives and other community-based organization is an important indicator to the continued benefit of the project. This means that skills and knowledge are being used and contributing to the resilience of the communities. Ensuring that people, in particular state officials, have the capacity to fulfil their roles is essential to ensure that additional work will be conducted and support requested to address ongoing and emerging needs. Thus, the DLA’s encouragement to area secretaries to include unfinished project activities into their budgets and submitting it to the provincial level is a positive step to promote sustainable actions. (S1, S2, R2, I1)

Through discussions with CDC members and community mobilizers, communities have taken ownership of project initiatives. Their continued efforts are demonstrated through their efforts to protect life during Cyclone Pam. However, support from the provincial-level bodies and departments could have been strengthened further but were not fully integrated into the project. This is a challenge as communities need continued support and guidance from provincial-level bodies to ensure that they have the right information and knowledge to strengthen further their preparedness measures and resilience mechanisms. (S2, R1)

There was a suggestion that a training of trainers workshop could be conducted to enable area secretaries to train the 74 area councils in the northern provinces. While developing outreach components are highly recommended, the lack of financial resources, transportation and printed and electronic materials to share with other area councils would be significant challenges to conducting effective training. Such initiatives could be included in funding proposals by area councils to the provinces. (S1, S2, S3, EF1, I1)

The training in agricultural methods has had a lasting impact and some communities, such as Imaio (Tafea Province), were experimenting with different techniques that they learned to see what works best. In some communities, members of schools and faith-based organizations also attended trainings and are using these skills in their own areas. The challenge remains whether the provincial agricultural extension stations will be able monitor their progress and continue to support the communities’ ability to increase their food security. (S1, EC1, EC2, I1)

Cooperatives also seem to be sustainable and contributing to improving members’ household budgets. For some, however, the long-term sustainability is a concern. Cooperatives that seek to produce goods and sell them, this may be a challenge. Establishing access to markets and finding buyers may be a problem for communities not on the same island as the market. Shipping times and routes are not fixed and changeable due to weather. Low commodity prices, such as for copra, may make shipping costs too great to offer a reasonable return. This should not deter cooperatives from developing such a business, but there should also be a secondary approach, such as a savings and loan scheme, that will keep the cooperative solvent if there are periods where goods are not sold, particularly for seasonal goods. This seems to have been done in both sites in Ambrym Island (Malampa Province). However, in future monitoring, the Office of the Registrar of Cooperatives and Business Development Services should ensure that the savings and loan component is functioning to support the business model. (S1, R1, R2, EC2, I1)

Migrant labour does not seem to be a challenge for many communities. Although anecdotal evidence suggests some young people do want to travel to Port Vila or abroad for work, the number of people that do migrate seems to be small. Migration also seems to be limited by strict migration policies in the region. Thus, project initiatives should continue without lacking people to conduct necessary activities, such as convene CDCs and conduct other resilience-building measures. There is a concern in some communities whether young people will want to continue farming. This evaluation was not able to establish the extent of this issue, but conversations with community members does not suggest that this is a significant issue. (S1)

There are four areas, however, that could have been strengthened through the project that would have supported greater human capacity and sustainability of the project initiatives. First, the project did not promote volunteerism at the community level. Community mobilizers are good, but without volunteers and without developing a sense of commitment and duty towards their communities, people may regard community resilience as purely the work of community mobilizers and the CDCs. (S1, S2, EC2, EF1, I1)

Second, the project worked with area secretaries and with community governance structures. It also included engaging women and faith-based organizations. The challenge is whether women, youth and faith-based organizations will continue to be engaged and whether the project could have been designed in a way that created shared responsibility among community members and assign them authority, irrespective of whether they are formal members of the CDCs. For example, church leaders may not be part of CDCs, but their strong role in the communities would be important in promoting disaster preparedness and resilience techniques on an everyday level. (S1, S2, EF1, I1, CC2)

Third, few materials related to DRR and resilience were left in communities for people to refer to and continue to train others. The central, public resource was a disaster map, which charted hazard risks and evacuations points for communities. In some cases, however, the disaster map was damaged or destroyed during Cyclone Pam. The lack of basic materials, such as large sheets of paper, has limited CDCs and community members’ ability to create new maps or improve on what previously existed. Moreover, not all project sites received reports for their communities. This was not done for every project site and may contribute to gaps in their preparedness. The lack of an agreed upon standardized template for reporting is another challenge. Different sets of information may create challenges for state bodies, UN agencies INGOs in adequately addressing resilience issues in the future across the project sites. Furthermore, not having a central repository for all documents, as well, creates the possibility that some of the details and knowledge may be lost. (S1, S2, S3, R1, R2, EC2)

Fourth, while provincial secretaries (or their deputies) were briefed about the project, the provincial government bodies, including the disaster management office, were largely not included in the project. Thus, few government officials at the provincial level have a good understanding of the project goals and what the outputs should be. The DLA has encouraged area secretaries to include incomplete activities in budgets to be reviewed at the provincial level. However, there is a risk that without prior knowledge of the project, its goals and importance to communities, important activities may go unfunded. (S1, S2, R3, E2, EF1, I1)

In addition, the limited inclusion of provincial level structures has created a gap in communication and support for promoting resilience at the community level. The provincial bodies, in particular the disaster management offices, will not be able to align the goals of the V-CR project with other initiatives and funding to ensure that the project activities are sustainable and continue to promote awareness and resilience at the community level. This creates a risk that community may need to be self-sufficient in identifying their needs and communicating them to the provincial and national levels. It also means that they may need to develop funding proposals to address food and water security issues. With coordinated communication between national and local levels, the needs of the communities will be better monitored and addresses issues that weaken resilience. (S1, S2, R3, EF1, I1)

A frequent challenge heard during the evaluation field mission was that there is a lack of human and financial resources to conduct regular monitoring of DRR issues and resilience mechanisms in communities. This is a challenge, in particular, for remote communities that do not have regular transportation links to other parts of the country. The project worked to create better communication links, in particular through the provision of high frequency radios in Loh (Torba Province) and Olpoe (Sanma Province). It is beyond the scope of this project to establish a fund or financially support a dedicated position to conduct regular monitoring missions. This is an issue that requires greater input from state bodies and international organizations working on DRR. (S1, S2, EC1, EC2, EC3, EF1, I1)

## 4.6 Cross-cutting concerns

CC1: To what extent has gender and disability been taken into consideration? CC2: To what extent has civil society been engaged in the community mobilization? CC3: To what extent has equity and human rights been taken into consideration?

Cross-cutting concerns emerged most clearly through the inclusivity of project activities. Trainings and activities were open and sought to benefit all community members. On the whole, the cross-cutting concerns were addressed, but often not directly or in a deliberate manner.

There were some specific issues which possibly limited the impact of cross-cutting intentions. For example, there was a lack of explicit quotas and selection criteria to ensure equal participation of women in the project. This was particularly noticeable in agricultural activities for lead (model) farmers, where few women were selected to participate. In general, women did participate and highlighted that the knowledge gained and opportunities provided were a benefit. During community feedback sessions, however, it was the men that answered most frequently and women had to be encouraged by the men to speak. This gave the impression that there had not been a significant change in everyday gender relations and attitudes. Although this project was not designed explicitly to address gender issues, but did promote the increased participation of women and youth in activities, there were missed opportunities to ensure that gender was given a more central consideration. (CC1, EC3)

Disabilities were also not directly addressed in the project. Some communities noted that they had developed plans to ensure the protection of persons living with disabilities during disaster evacuations. There will few visible efforts to accommodate the needs of persons living with disabilities into other components. According to data collected during the 2009 census, around 12 per cent of the total population reported a disability. ‘While about 6% of children younger than 5 years of age had a disability, it was more than half of the population at age 60 years and older.’ Given the increasing needs of older generations, poor or limited infrastructure and challenges in receiving basic services, project activities could have built in specific methods to promote the contribution of persons living with disabilities and to address their needs through skills development. (CC1)

The engagement of civil society partners, beyond the community-based organizations (CBOs), was limited. CBOs did benefit through their participation in trainings and being supported to take part in decision-making forums. The project did not, however, directly facilitate connections between civil society groups at community, provincial and national levels or create support networks to further activities in the project sites. While this was not part of the project proposal, it could have been developed through activities to promote greater sustainability. (CC2)

Equity and human rights were integrated into the governance component of the project. Components were developed to promote community-wide resilience, but specific issues related to equity were not elaborated throughout the project. For example, equity in disaster preparedness or addressing hazard risks was not discussed as a topic or elaborated through activities. Governance issues examined ways to promote improved local governance, but did not advance equitable approaches within it to ensure that all community members had a voice and were able to have their voices heard. The project did not engage the Department of Women’s Affairs to obtain input and feedback on activities and to ensure how these could have more gender sensitive and equitable. There were no criteria to select participants for the food security workshop. Thus, few women attended the event, even though a large number of women are engaged in farming activities in their communities. Gender issues are one such example. The lack of a detailed approach indicates that there were missed opportunities to promote equity across the components. (CC3)

Human rights were also not explicitly outlined in the project proposal. The project did seek to improve resilience through mechanisms to protect people and make them more self-reliant. Nonetheless, education was one area that the project did not focus on, even to implement DRR awareness classes in schools. Such interventions are important is it increases the sustainability of activities and involves children in their own protection and that of their communities. Promoting the role of education is important, in particular, as Vanuatu only ‘noted’ many education-related recommendations during the second review of the Universal Periodic Review (UPR). The need to promote education for all and to include DRR messaging into curriculum and activities, as practised in other regions, such as Central Asia and the southern Caucasus, is an important aspect to strengthening resilience. (CC3)

# 5. Lessons Learned

This section outlines lessons learned from this evaluation for the effective design and implementation of future DRR and disaster risk management (DRM) activities that promote human security. In addition, it provides general information that would be useful for those planning, implementing or evaluating activities. Building on the lessons of this programme and other work will strengthen approaches to promote human security and overall resilience.

The lessons learned were developed from the desk literature review and the field work. This examines both the strengths of the programme and the opportunities to capitalize on to enhance the work started in this programme. These are the overall views that the evaluator learned through the discussions with stakeholders, beneficiaries and programme staff.

Lesson 1: Detailed coordination is essential for implementation

The project suffered significant delays due to a lack of coordination at all levels – local and national. During the inception period, it is essential to develop a coordination plan among all stakeholders, staffing plan and clear define roles and responsibilities related to specific components. This then can be mapped onto an implementation plan of activities. When inputs are coming from agencies’ offices located in other countries, it increases the challenges to coordinate effectively and may need a temporary technical working group to convene and draft such plans.

Lesson 2: Defining target site is required to refine activities and delivery

A long inception period allowing for detailed research and planning for target locations is essential. This project suffered from an overestimation about what could be achieved within area councils. A detailed baseline assessment validated by the design team and conducted during the inception period could have highlighted challenges and offered recommendations to refine the project while ensuring the DRR and DRM initiatives are well established and could serve the surrounding communities.

Lesson 3: DRR activities need to be cross-cutting

Strengthening preparedness and overall resilience to natural hazard risks and disasters needs to be grounded in a cross-sectoral approach. For example, it must include technical coordination as well as developing education approaches to include children in the process. Bringing DRR lessons into schools is an important mechanism to promote sustainability and to have children become leaders in the community through advocating preparedness. A communication specialist can also help to ensure that DRR and human security messages are streamlined across the different components. This would also ensure that products – such as reports, maps and other materials – are designed for and remain in villages so that community members can refer to them and use them to prepare for disasters and aid their recovery. A cross-sectoral approach will also promote equality and equity in methods and preparedness activities.

Lesson 4: Establish linkages between human security and intergovernmental plans, such as the Hyogo Framework for Action, to the local context

Closer links to inter-governmental frameworks and initiatives are important to ensure a coordinated approach and regional support. This project did highlight its support of national goals and plans; however, it did not refer to the Hyogo Framework for Action. Identifying links to this broader framework would also serve to attract funding from donors interested in supporting such frameworks.

Lesson 5: Project initiatives need to feed into cluster coordination to facilitate relief efforts

Project activities promote resilience at the community level, but they do not necessarily translate into enhanced coordination and communication mechanism between agencies and non-UN partners during the launch of a humanitarian appeal following a disaster. A strong role by national stakeholders, such as the Department for Local Authorities, is essential to ensure better communication links between all levels and ensures that information from community focal points reach the other partners. UNICEF, also, can strengthen education activities in the components. It would have allowed UNICEF to coordinate messages and actions to affected communities and between partners. After Cyclone Pam, it does not appear that the Early Recovery Cluster was activated. Nonetheless, UNDP, which heads this cluster, could have created links to help Early Recovery Coordinators and Advisors how to draw on the ongoing activities in the communities, resilience mechanisms in place and opportunities to support communities’ recovery after the disaster.

Lesson 6: Project management can be strengthened through technical support

In situations where there is minimal staff and present in country, short-term technical support can provide enhanced capacities for programme management and oversight of activities. In this project, there were areas where additional human resources in specific areas, such as DRR, education and governance could have strengthened the work of all stakeholders. This technical expertise together with the findings from a detailed baseline study in the inception phase would help to identify approaches and methods that meet communities’ needs. The addition of such skills can contribute to improved coordination.

Lesson 7: One UN principles should be built into projects

Delays and administrative challenges are a challenge to any project. Instituting joint programming models, such as the One UN approach, should be integrated into project development. This is particularly important when UN agencies’ offices are located in other countries. This slows down administrative and financial approvals, and creates complications when multiple agencies are involved in a joint programming model is not in place. Joint implementation also facilitates improved effectiveness and efficiency of activities.

# 6. Conclusions

Community members appreciated the skills and knowledge that they received. They saw the benefit of it when it was put to the test during Cyclone Pam. The largest cyclone of its kind and people were killed. There were few reports of injuries or casualties from the project sites. The broad approach – which included DRR, governance, food and nutrition security, and water security – helped to build and create capacities to address risks to natural hazards and promote resilience.

In this sense, the project results have been a success. Project design and implementation, however, indicate that there are a number of challenges that need to be taken into account. Implementing stakeholders noted these issues during evaluation meetings. While project implementation crescendos in the final part of the project, usually in the final year as it was with this project, there were missed opportunities to ensure better implementation and more thorough delivery, such as with DRR and DRM activities, throughout the duration of the project.

The project initially stalled due to a lack of coordination and clear establishment of roles and responsibilities, as well as an absence of technical support at all levels. Additional challenges were met with activities being approved by UN agencies’ main offices in other countries. An internal coordination and management structure was not developed (or at least not included in the project proposal). A similar management structure to other projects was applied, but this should have been clarified at the beginning of the project and clearly communicated to stakeholders. This has been a significant factor for the project and has served as a lesson to projects developed afterwards.

The intention to reach remote communities at risk of a range of natural hazards was a positive focus of the project. The project consultation ensured that many people would be reached and would benefit from efforts to strengthen their resilience. The geographical scope was ambitious and overlooked significant logistical challenges. In promoting a bigger number of communities, the project lost some quality of the activities. Delays and logistical limitations meant that activities had to be trimmed down or were not conducted in some sites.

An opportunity was missed to increase sustainability and community interaction by not including education into the activities. This would have increased ownership of the activities and made children more active within their communities. It would have also supported recommendations for Vanuatu’s commitments to the HFA and other such intergovernmental plans.

Tremendous logistical challenges and challenges of dealing with offices with regional headquarters in other countries and budgeting systems could have been streamlined in order to allow for activities to be conducted on time for increased effectiveness and efficiency.

Through a counterfactual approach, the following statements can be made:

- If better coordination had taken place, improved and joint implementation could have reducing costs and made activities more efficient.

- If provincial-level authorities had been more closely involved, strengthened communication between communities, province and national levels would have been in place, which would have also provided greater opportunities to highlight communities’ needs to improve their resilience and may have received more effective support from all levels.

- If planning had been less ambitious and a solid baseline assessment conducted, it would have allowed agencies and state counterparts to refine activities.

- If project implementation had happened earlier and opportunities had allowed for more monitoring, some activities would have had a greater impact and been more sustainable.

There were no unexpected findings during the evaluation mission. Conducting this evaluation after Cyclone Pam there were limited expectations as to the extent material inputs had remained undamaged. Fortunately, there had not been extensive damage visible in the communities visited and community members had been able to fix anything that had been broken with the water security instalments.

Despite these issues, the project did implement needed activities in remote communities. Community members were positive of the activities and have noted improvements in their abilities to prepare and respond to natural hazards. It is important that such activities continue and that good approaches and innovations are noted and disseminated to other communities.

# 7. Recommendations

The recommendations below are drawn from interviews and observations made during field site visits, documents reviewed and the findings of the MTR. These are divided into six areas of focus examined in the evaluation:

- Relevance;

- Effectiveness;

- Efficiency;

- Impacts

- Sustainability;

- Cross-cutting concerns.

The methodology used to identify the recommendations is based on a two-step process. First, the findings of the evaluation are used to identify what changes would have the greatest contribution to the overall outputs. Second, the recommendations are presented in a way that would have the greatest overall contribution to strengthening the programme’s impact. Together with the lessons learned in Section 5, these recommendations should be taken into consideration for ongoing and future programming.

Each recommendation is addressed to an organization (or organizations), identifies joint responsibilities, and is given a priority level and timeframe in which the recommendation should be addressed. The timeframe has three periods:

- Short term – within half a year;

- Medium term – within a year;

- Long term – more than a year.

### Table 7.1 Recommendations

| No. | Recommendation | Organization(s) | Responsibilities | Priority | Timeframe |
| --- | --- | --- | --- | --- | --- |
| Relevance |  |  |  |  |  |
| 1 | Develop a standardized community mapping assessment to determine resilience and vulnerability characteristics. | State counterparts, NAB members, NGOs and UN agencies | Determine resilience and vulnerability of communities based on a wide variety of indicators and refine activities to address specific needs. | High | Short term |
| 2 | Support engagement and interaction of different modes of governance to facilitate joint promotion of goals. | State counterparts, NGOs and UN agencies | Develop plans and approaches to address the engagement of traditional (kastom) and formal governance approaches. | High | Long term |
| 3 | Integrate goals and lessons learned from intergovernmental plans. | State counterparts, NGOs and UN agencies | Ensure that the project design addresses intergovernmental frameworks, such as the Sendai Framework for Disaster Risk Reduction (2015-2030). | High | Long term |
| Effectiveness |  |  |  |  |  |
| 4 | Establish an inter-agency coordination mechanism. | UN agencies | Define roles and responsibilities to facilitate implementation and effectiveness of activities. | High | Short term |
| 5 | Ensure education initiatives are included throughout DRR activities. | UN agencies | Maximise the effectiveness, impact and sustainability of DRR initiatives through inclusion of education activities and other inclusive measures. | High | Short term |
| 6 | Maintain and establish connections with state bodies at all levels. | UN agencies | Facilitate communication, awareness and planning between community and national levels to strengthen development gains. | High | Medium term |
| 7 | Establish a unified project management and financial system. | UN agencies | Strengthen joint approach to limit administrative and logistical challenges. | Medium | Long term |
| Efficiency |  |  |  |  |  |
| 8 | Implement comprehensive approach that meets needs of communities. | UN agencies | Ensure broad-based and comprehensive response to resilience needs in communities, which may necessitate a limited geographical coverage. | High | Medium term |
| 9 | Conduct a cost-benefit analysis of activities. | UN agencies | Identify economic efficiency of activities to determine value for future projects. | Low | Long term |
| Impacts |  |  |  |  |  |
| 10 | Strengthen monitoring and reporting mechanisms. | State counterparts, NGOs and UN agencies | Ensure regular monitoring is conducted and reporting standardized to understand changes and impact in project activities, while ensuring that interventions are conflict sensitive. | High | Medium term |
| 11 | Promote the role of women in all aspects of programming. | State counterparts, NGOs and UN agencies | Enhance mechanisms to ensure women’s participation and identification of roles with responsibilities and authority. | High | Medium term |
| Sustainability |  |  |  |  |  |
| 12 | Develop knowledge resources in communities to build skills and promote outreach. | State counterparts, NGOs and UN agencies | Ensure that knowledge resources contribute to ongoing and future activities, and can be used as centres for outreach to other communities. | Medium | Long term |
| 13 | Foster a sense of volunteerism and community participation. | NGOs and UN agencies | Promote concept of volunteerism and develop a network of volunteers in communities to address collectively DRR issues. | Medium | Long term |
| Cross-cutting concerns |  |  |  |  |  |
| 14 | Promote inclusion, in particular women, youth and persons living with disabilities. | State counterparts, NGOs and UN agencies | Facilitate community-wide effect through promoting inclusive methodologies and contributions to resilience. | High | Short term |
| 15 | Identify and develop an equity and human rights-based approach, including standards for all activities. | UN agencies | Ensure that approaches and activities promote equity and human rights, and identify contributions to resilience and human security. | High | Medium term |

# Annex A: Map of project sites

#### Annex A: Map of project sites with hazard risks

# Annex B: Logical Framework

Based on the information provided, the outputs have been ranked according to whether they have been completed or not. A simple colour code has been applied to provide a quick understanding of the achievement of outputs. Logframe indicators were not updated following the recommendations of the MTR. Thus, it would be unfair to provide the ranking according to the original output indicators. In order to take into consideration the change in indicators from the focus on the area council to the community level, a blue colour code is used to highlight achievements of activities and on which no additional action was taken during the project or achievement of activities based on revised activities:

|  | Completed according to original output indicators |
| --- | --- |
|  | Achieved activities and no additional action was taken during the project, or achieved activities based on revised activities |
|  | Ongoing, partially complete or unclear completion rate against indicator |
|  | Not completed or withdrawn |

| Main objectives | Main outputs | Output indicators | Results | Status |
| --- | --- | --- | --- | --- |
| - Objective 1: Ten selected communities supported and empowered to identify threats/needs and formulate sustainable interventions within the first six to 12 months of the project, and thereafter implement and monitor interventions (Component 1: Disaster Risk Reduction and Management) | 1.1: Leaders, managers, household heads, men, women, youth, boys and girls in the 10 area councils identify human security risks, hazards, vulnerabilities and capacities and develop comprehensive preparedness, response, mitigation and adaptation plans, with special reference to governance and decision-making, water, food and nutrition, and knowledge management | 1.1.1: 12 area council reports by July 2012 1.1.2: 12 area councils have plans by December 2012 | 11 disaster response plans were reviewed and finalized (Loh was covered by Vanuatu Red Cross). 11 of Community Disaster and Climate Change Committees established and formalized. Activity conducted at level of villages (communities) not area councils. |  |
|  | 1.2: Household heads, men, women, youth, boys and girls in the 10 area councils have knowledge and skills to respond to, mitigate and adapt to the identified risks and hazards | 1.2.1: 50% (15,384 people; one woman and two youth per household) covered by December 2012 | 2013 – Training of Trainers workshops – 84 people attended from all project sites, comprising women, youth, area secretaries and some provincial secretary generals (on average 7 people from each area, but no disaggregated lists). Awareness-raising activities conducted in project sites. There have not been monitoring updates. Original indicator was not updated after MTR. |  |
|  | 1.3: Champions from the 10 area councils advocate and provide support and leadership to communities for preparedness, response, mitigation and adaptation | 1.3.1: 50 champions (five per area council) identified and trained by December 2012. | 12 Community Mobilizers trained as Community Climate Change Champions. They served as interface between UNDP and government counterparts in communities. Communities also received trainings to build their knowledge and skills in responding to climate change. Technical Committees consisting of Community Climate Champions were established in 12 sites (these committees meet fairly regularly). They have all developed their first work plans with the intension to implement the plans with the support of the Area Secretaries and provincial government. |  |
|  | 1.4: Income-generating activities promoted to build physical, institutional, social and economic means | 1.4.1: Microfinance schemes established by June 2013; 1.4.2: Percentage of communities participating in the scheme. Baseline: TBD Target: 50% by 2013 | 2013 – Training on income-generating activities held in Port Vila for three southern provinces and in Luganville. On behalf of UNDP, the Office of the Registrar of Cooperatives and Business Development Services supported the establishment and development of cooperatives in four locations (the remaining project sites were covered by FAO under Component 3 (Output 3.4). Income-generating activities ongoing in West Ambae (poultry farm), Aniwa and Tanna both have a retail shop. In a pilot project together with the private sector Entani Company Limited, the same cooperative on Tanna will set up tourism stalls at the entrance of the Yasur Volcano. Two other communities (Loh and Wilit) established their own cooperative with information gained from the Training of Trainers workshop without any further support. |  |
|  | 1.5: Area councils have access to dedicated premises to conduct council business as a demonstration | 1.5.1: Two area council community centres constructed by June 2013; 1.5.2: Day-to-day operations sustained in the 12 area councils | No area council buildings were constructed. 10 Area Council Centres were equipped with laptop computers and generators to facilitate daily administrative tasks. Of the 10 sites, six were in need of solar improvements and were provided with solar power equipment. Communication links have been established with two of the most remote communities (Olpoe and Loh) through the installation of a high frequency (HF) radio. |  |
| - Objective 2: All six provincial governments and 10 selected communities have capacity to ensure that local development, local-level governance, decision-making and public sector performance enhance community resilience and coping mechanisms during and beyond the project period (Component 2: Governance and Decision-Making) | 2.1: Interface between traditional and formal forms of leadership documented and engagement strategies developed to incorporate both forms of governance, including gender balance in community leadership | 2.1.1: Six engagement strategies developed/ improved; 2.2.2: Provincial council members endorse engagement strategies; 2.2.3: Gender activities and female community leaders supported with at least 12 (two per province) being elected into provincial councils by end of project | UNDP, through communication to UNTFHS in 2014, amended this to focus on capacity building of area councils and area secretaries. 2014 two trainings focused on governance, administration and budgeting, as well as encouraging development concepts at the community level. April 2014 – 22 area secretaries, provincial project officers, women representatives and youth representatives (18 men and 5 women) for two southern provinces in Lenakel (Tanna Island). Trained area secretaries were expected to share their knowledge with other area secretaries. No further monitoring has been done to assess this. September 2014 – 33 area secretaries (24 men and 9 women) from northern provinces received training in Luganville. Those trained supported the Community Mobilizer and area council secretaries to coordinate activities in the project sites. The Project Coordinator conducted monitoring in the project sites. It is not clear whether a suggestion to travel to each of the 74 Area Councils to conduct further trainings was conducted. Area Council templates were developed during both trainings – not clear of how many were finalized and approved. Trainings included area council secretaries, chiefs, women and youth. Indicator 2.2.3 was unachievable. Gender issues were covered as part of DRR/CCA training. The reports by CARE International provide more information on gender issues at the community level. |  |
|  | 2.2: Leaders, managers and members of faith-based and other organizations/groups have knowledge and skills to mainstream building community resilience and coping capacity at all times | 2.2.1: 318 persons (13 per provincial council, 20 per area council) trained by 2013 2.2.2: 12 preparedness drills conducted by 2013 Partially - 12 area secretaries and all 12 communities have knowledge and skills to mainstream resilience | Two governance trainings were completed with participants from the 11 project sites (including area council secretaries, chiefs, women and youth). Action plans were subsequently developed for each project site, including around DRR/CCA. (Loh was not covered). Through CARE International and Live & Learn, disaster simulation exercises were conducted in 11 sites (93 women, 123 men, 20 boys, seven girls and four people living with disabilities actively participated). Vanuatu Red Cross conducted a simulation exercise in Loh. |  |
|  | 2.3: Provincial councils, area councils and institutions have plans, procedures and processes that mainstream community resilience and coping capacity at all times | 2.3.1: Annual plans, procedures and processes at area and provincial levels reviewed; 2.3.2: Community resilience and coping capacity mainstreamed into at least five provincial sector plans by December 2012 | Three provincial governments have taken steps to integrate and mainstream coping capacities into their development plans. Plans and procedures will be documented and monitored over time to gauge progress on the measures to prepare for and adapt to natural disasters. |  |
| - Objective 3: At least 75% of households (6,000) in the selected communities have enhanced food and nutrition security before and after adverse effects of climate change and natural disasters (Component 3: Food and Nutrition Security) | 3.1: Flood- and landslide-prone farmland stabilized for food production | 3.1.1: Percentage of households with knowledge of appropriate land use patterns. Baseline: TBD Target: 75% by 2013 | August 2013: Lead Farmer training for northern provinces, including 11farmers (9 men and 2 women) from 5 sites in three provinces; 3 agricultural officers from 3 provinces. November 2013: Lead Farmer training for southern provinces, including 17 farmers (9 men and 2 women) from 5 sites in 3 provinces; 3 Agricultural Officers from 3 provinces. Blacksands was omitted, as community members do not have access to land for cultivation. (Evaluator noted that there were some small gardens, but was not able to establish if these had been developed through the UNTFHS project.) |  |
|  | 3.2: Increased food production and availability | 3.2.1: Percentage of households adopting diversified farming Baseline: TBD Target: 75% by 2013 | Resilient crops previously distributed for cultivation at project sites were harvested and redistributed to households for cultivation. |  |
|  | 3.3: Household heads, caregivers and other adults practice appropriate food processing, storage and preparation methods to minimize crop, food and nutrient losses | 3.3.1: Percentage of households practicing methods minimizing food and nutrient losses Baseline: TBD Target: 75% by 2013 | A consultant was hired to conduct community-level training on food processing, storage and preparation methods in Ambae (2 sites), Santo (1 site), Mere Lava (1 site), Aniwa and Tanna. |  |
|  | 3.4: Women empowered and men cooperate for food production, processing, preparation and marketing | 3.4.1: Percentage of households marketing surplus foods. Baseline: TBD Target: 75% by 2013 | Training conducted on 12 sites, involving lead farmers (Output 3.1) as well as women community members. About 80% of participants were women. On behalf of FAO, the Office of the Registrar of Cooperatives and Business Development Services supported the establishment and development of cooperatives in seven locations (the remaining project sites were covered by UNDP under Component 1 (Output 1.4). There were eight sites, but Mere Lava was removed as it was too remote and difficult to set up a cooperative there. |  |
|  | 3.5: Local council pre-positions emergency supplies for vulnerable groups, especially women, children, elderly and people living with disabilities and HIV/AIDS | 3.5.1: Supplies in stock at a predetermined central warehouse | This activity has been reprogrammed because of the lack of facilities at the area council sites for prepositioning. |  |
| - Objective 4: At least 75% of households (6,000) in selected communities have enhanced capacity and access to safe and secure water sources before and after adverse effects of climate change and natural disasters (Component 4: Water Security) | 4.1: Household and water catchment area safety and security plans developed and implemented | 4.1.1: 12 area council water safety and security plans produced by December 2012; 4.1.2: 12 water systems functional by 2013; 4.1.3: Percentage of households with access to safe and secure water sources. Baseline: TBD Target: 75% by 2013 | (a) Seven sites (Aniwa, Imaio, Baiap, Willit and Konkon, Emae, Loh and Mere Lava) have developed WSSPs following trainings conducted by DGMWR. UNICEF purchased 20 smartphones for the DGMWR and use Akvo Flow, a survey system. Rapid assessment forms used after disasters (e.g. cyclones) were uploaded onto the phones and were used to conduct a WASH assessment after tropical cyclones, such as Cyclone Pam, and to conduct water source mapping across the whole country. (b) 7 water systems are functional in Aniwa, Imaio, Baiap, Willit and Konkon, Emae, Loh and Mere Lava. 22 community participants (9 women and 13 men) were trained on basic plumbing, water management and sanitation on Emae. 13 community members from Wilit (6 women and 7 men) and 15 community members (5 women and 10 men) from Baiap participated in the water safety and security training conducted in Baiap. (c) 70% of target households have access to water systems installed or upgraded by the project. These include gravity-fed water systems in Imaio and Wilit and rainwater harvesting in Aniwa, Baiap, Mere Lava and Loh and Emae. Planned water security measures at schools and health clinics in the project sites were not able to be completed as Cyclone Pam disrupted activities. WASH in schools (with wider coverage) is being taken up through a UNICEF-supported project implemented by Oxfam. Construction materials for water systems were purchased and delivered to the remaining three project sites (Ipayato, Olpoe and West Ambae). West Ambae was completed before Cyclone Pam. The cyclone delayed activities in Ipayato and Olpoe were delayed, but completed in July and August 2015. Printing of some paper materials has not been completed. |  |
|  | 4.2: WASH operation and maintenance (O&M) systems standardized nationwide | 4.2.1:National guidelines published and disseminated by 2012 | WASH O&M guidelines have been drafted and are under discussion with the DGMWR and the Ministry of Health (MoH). |  |
| - Objective 5: Information system, threat monitoring and communication systems established in the selected communities within the first 12 months of the project and thereafter maintained (Component 5: Knowledge Management) | 5.1: Rural disaster stations established and operational, evacuation centres identified and strengthened and quarterly participatory project monitoring undertaken | 5.1.1: 12 area councils have information systems by 2012; 5.1.2: 12 risk monitoring and stations established by 2012; 5.1.3: Monthly Project Monitoring Tool; 5.1.4: Quarterly monitoring meetings held | 10 project sites have identified at least one building (either a private home or a public building) that communities can use during disasters (particularly cyclones). Loh evacuation centre strengthened. Blacksands and Seratamata were removed from the project activities. Communities are being encouraged through community-level training to construct ‘cyclone houses’ in their communities to provide secure shelter during cyclones. Communities have traditional cyclone houses that are built using local materials. They proved resilient during previous cyclones. Some communities survived Cyclone Pam in these traditional houses and are being encouraged to build more of them. With the development of the monthly project monitoring tool, the Integrated Village Information Management System (IVIMS) IVIMS is now active, with community representatives monitoring project activities and resilience indicators in their communities. Through this process, each community conducted an initial baseline assessment of each household. The assessment is being conducted on a quarterly basis (although it may vary in some communities) to assess the status of each household against agreed indicators. Some communities lost their maps and information during Cyclone Pam. Quarterly meetings (although it may vary in some places) in the communities are held and feed into the monthly monitoring tool. |  |
|  | 5.2: Participatory project annual reviews undertaken | 5.2.1: Mid-year and annual reviews held | MTR conducted in 2014. Project Coordinator was hired in 2014 for one year. |  |
|  | 5.3: An independent project evaluation undertaken | 5.3.1: End-of-project evaluation undertaken by September 2014 | MTR conducted 2014. Summative/Terminal Review conducted in 2015. |  |
|  | 5.4: Project outputs documented and disseminated | 5.4.1: Project proposal and multi-year work plan published by August 2012; 5.4.2: Project reports produced as scheduled; 5.4.3: Public relations and communication materials published | The multi-year work plan has been completed and revised to reflect the extension and MTR recommendations. Plans are underway to develop information materials, including flyers for each project component, which will be shared with partners and other agencies involved in DRR/CCA. A post-project photo essay will be completed in 2015. MTR and project reports have been produced and shared. The Department of Agriculture and Rural Development produces a quarterly newsletter, Talemaot, providing foods security information, including activities conducted through UNTFHS. Adventist and Development Relief Agency has been contracted to lead the development of WASH in emergencies information materials that will be easily accessible to the communities. Work on this is still in progress. After MTR quarterly NAB meetings were held. |  |

# Annex C: Fund utilization

|  | Total fund allocation and cumulative utilization by agency (US$) August 2011 to 1 December 2014 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNTFHS Project in Vanuatu | UNICEF |  |  | UNDP |  |  | FAO |  |  |
| Description | Budget | Utilization | % | Budget | Utilization | % | Budget | Utilization | % |
| Component 1: Disaster Risk Reduction and Management | 169,000 | 54,424 | 32% | 460,500 | 497,640 | 108% | 0 | 0 |  |
| Component 2: Governance and Decision-Making | 0 | 0 | 0 | 223,000 | 34,175 | 15% | 0 | 0 |  |
| Component 3: Food and Nutrition Security | 41,000 | 2,699 | 7% | 0 | 0 | 0 | 414,865 | 292,579 | 71% |
| Component 4: Water Security | 395,000 | 283,262 | 72% | 0 | 0 | 0 | 0 | 0 |  |
| Component 5: Knowledge Management | 297,200 | 34,787 | 12% | 0 | 0 | 0 | 0 | 0 |  |
| Component 6: Programme support component | 729,456 | 614,686 | 84% | 47,845 | 64,571 | 135% | 0 | 0 |  |
| Subtotal: Direct Project costs | 1,631,656 | 973,193 | 60% | 683,500 | 596,386 | 93% | 414,865 | 292,579 | 71% |
| PSC 7% of direct project costs | 114,215 | 68,124 | 60% | 47,845 | 38,044 | 80% | 29,041 | 20,481 | 71% |
| TOTAL | 1,745,872 | 1,041,317 | 60% | 731,345 | 634,430 | 87% | 443,906 | 313,060 | 71% |

# Annex D: Bibliography

Below are project documents reviewed during this evaluation.

CARE International, ‘West Ambrym Area Council Disaster Management Plan’ (1 February 2015).

CARE International, ‘Mere Lava Area Council Disaster Management Plan’ (28 June 2015).

CARE International, ‘North Ambrym Area Council Disaster Management Plan’ (28 June 2015).

CARE International, ‘West Ambae Area Council Disaster Management Plan’ (28 June 2015).

Daniel, J., ‘Action Plan Imaiao’ (2013).

Daniel, J., ‘Imaiyo Community (Tanna) Action Plan’ (2013).

Daniel, J., ‘Imaio Water System Plan’ (2013).

Daniel, J., ‘Imaio Community Cyclone Respond Plan’ (2013).

Daniel, J., ‘Imaio Community Evacuation Plan’ (2013).

Daniel, J., ‘Imaio community participants to Climate change Resilient and Adaptation workshop at Crystal Blue Lagoon’ (2013).

Daniel, J., ‘Imaio Cooperative Action Plan’ (2013).

Daniel, J., ‘Imaio Community Project 3 Month Detail Implementation Plan. Component: Cooperative and Savings an Loan (as from July-October 2013)’.

Daniel, J., ‘Time line blong building ol haoses’ (2013).

Daniel, J., ‘Traditional Knowledge on growing crops’ (2013).

Daniel, J., ‘Wok Plan blong wota: Imaio community’ (2013).

Hardwick, M., ‘Sanma Provincial Consultation – MTR’ (8 May 2014).

Hardwick, M., ‘Photos of Imaio, Tanna Water System Upgrade’ (10 June 2014).

Hardwick, M., ‘Ipayato Site Consultation (South Santo) – MTR’ (11 May 2014).

Jonas, M., ‘Governance Training for Northern Provinces’ (2014).

Live & Learn, ‘Community Disaster Plan: Blacksands’ (2015).

Live & Learn, ‘Community Disaster Plan: Finonge’ (2015).

Live & Learn, ‘Community Disaster Plan: Imaio’ (2015).

Live & Learn, ‘Community Disaster Plan: Ipayato’ (2015).

Live & Learn, ‘Community Disaster Plan: Marae’ (2015).

Live & Learn, ‘Community Disaster Plan: Olpoe’ (2015).

Mael, H. S., ‘Climate Change and Agriculture in Vanuatu: A study of crops and farming system’, FAO, (September 2013).

Rural Water Supply Section, Department of Geology, Mines and Water Resources, ‘Village Plumbers’ Training Report’ (2015).

O’Callaghan, B. and M. Hardwick, ‘Community resilience and coping with climate-change and natural disasters in Vanuatu. United Nations Trust Fund for Human Security. Reference: CN09-025. Mid-Term Review’ (2014).

Sammy, E., ‘Drinking Water Safety Plan: Imayo Water Supply Tanna’ (November 2013).

Sammy, E., ‘Drinking Water Safety Plan: Aniwa Rainwater Harvesting’ (November 2013).

UNDP, ‘Vanuatu Community Resilience to Climate Change and Natural Disaster – Training of Community Representatives’ (4-15 March 2013).

UNDP, ‘Field Trip Report: Ambae, Mere Lava’ (20 March 2013).

UNDP, ‘Field Trip to VARTC – (Vanuatu Agriculture Research and Technical Centre)’ (16 May 2013).

UNDP, ‘Governance Training Program Report: Tafea and Shefa Provincial Council Training Report’ (7-11 April 2014).

UNDP, ‘Governance Training Program – Field Trip Report’ (9 April 2014).

UNDP, ‘Vanuatu Community Resilience to Climate Change Project: Feasibility Report for Establishing Livelihoods Projects in Aniwa, West Ambae, Tanna, and South Santo’ (2014).

UNDP, ‘Field Trip Report: Ambrym’ (9 December 2014).

UNDP, ‘Field Trip Report: Ambae, Mere Lava’ (16 February 2015).

UNDP, ‘Field Trip Report: Ambrym’ (9 December 2014).

UNICEF, ‘National Project Management Team Meeting’ (29 May 2012).

UNICEF, ‘Project Minutes of Meeting’ (13 July 2012).

UNICEF, ‘Minutes of Meeting’ (27 August 2012).

UNICEF, ‘Minutes of Coordination Meeting’ (4 September 2012).

UNICEF, ‘Minutes of Coordination Meeting’ (14 September 2012).

UNICEF, ‘Project Coordination Group Meeting’ (15 October 2012).

UNICEF, ‘Minutes of Meetings’ (26 March 2013).

UNICEF, ‘UNTHFS Coordination Meeting / Teleconference’ (5 November 2013).

UNICEF, ‘Vanuatu Mid-Term Review Meeting’ (9 December 2013).

UNICEF, ‘UNTHFS Project Management Team Meeting Minutes’ (22 April 2014).

UNICEF, ‘UNTFHS Draft MTR Report Review: Minutes of Meeting (teleconference)’ (20 June 2014).

UNICEF, UNDP, FAO, ‘Community resilience and coping with climate-change and natural disasters in Vanuatu, 2011-2013’ (2010).

UNICEF, UNDP, FAO, ‘Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu: Third Progress Report to the United Nations Trust Fund for Human Security (December 2012 – November 2013)’ (2013).

UNICEF, UNDP, FAO, ‘Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu: Fourth Progress Report to the United nations Trust Fund for Human Security (November 2013 – November 2014)’ (2014).

Vanuatu Department of Agriculture and Rural Development, ‘Vanuatu Climate Change and Coping Mechanism – Lead Farmers Training Report for Six Project Sites in the North’, 12-16 August 2013).

Vutinamoli, J., ‘Ambrym WAHS Workshop – Malampa Province (10-24 August 2013).

# Annex E: List of people interviewed

| No. | Date | Person(s) | Position | Organization | Location |
| --- | --- | --- | --- | --- | --- |
| 1 | Thursday, 13 August 2015 | Roslyn Arthur | UN Affairs Officer | UNICEF | Port Vila, Vanuatu |
| 2 | Thursday, 13 August 2015 | Cherol Ala | Director | Department of Local Authorities | Port Vila, Vanuatu |
| 3 | Thursday, 13 August 2015 | David Malakay | Procurement Associate for the Vanuatu Coastal Adaptation Project (former Project Coordinator for the UNTFHS WASH project) | UNDP | Port Vila, Vanuatu |
| 4 | Thursday, 13 August 2015 | Minifereti Nainoca | Environment Team Leader | UNDP | Port Vila, Vanuatu |
| 5 | Friday, 14 August 2015 | Mark Vurobaravu | Principal Agriculture Technical Officer | Department of Agriculture and Rural Development | Port Vila, Vanuatu |
| 6 | Friday, 14 August 2015 | Mathias Bule | Information Officer | Department of Agriculture and Rural Development | Port Vila, Vanuatu |
| 7 | Friday, 14 August 2015 | Runte Likiafu | Assistant FAO Representative | FAO | Port Vila, Vanuatu |
| 8 | Monday, 17 August 2015 | Donald Wouloseje | Programme Officer | UNDP | Port Vila, Vanuatu |
| 9 | Monday, 17 August 2015 | Matthew Hardwick | Community Adaptation Panning Specialist | UNDP | Port Vila, Vanuatu |
| 10 | Tuesday, 18 August 2015 | Binson Henry | Business Development Officer | Office of the Registrar of Cooperatives and Business Development Services | Port Vila, Vanuatu |
| 11 | Tuesday, 18 August 2015 | Sowany Joseph Matou | Chief Executive Officer (former Director of the Department of Cooperatives) | Entani Company Limited | Port Vila, Vanuatu |
| 12 | Tuesday, 18 August 2015 | Karldon Sam | Manager for Training, Promotion and Research | Office of the Registrar of Cooperatives and Business Development Services | Port Vila, Vanuatu |
| 13 | Wednesday, 19 August 2015 | Christina Bare-Karae | Education Consultant | UNICEF | Port Vila, Vanuatu |
| 14 | Friday, 21 August 2015 | Erickson Sammy | Acting Director | Department of Geology, Mines and Water Resources | Port Vila, Vanuatu |
| 15 | Friday, 21 August 2015 | Paula Feehan Sonia Zavesky | Programme Manager Programme Manager | ActionAid | Port Vila, Vanuatu |
| 16 | Saturday, 22 August 2015 | Craig Lind | Research Fellow | Department of Social Anthropology, University of St. Andrews | Port Vila, Vanuatu |
| 17 | Sunday, 23 August 2015 | Pierre Simon | Chief | Baiap SDA | Baiap, West Ambrym, Vanuatu |
| 18 | Monday, 24 August 2015 | Abel Merani | Registered Nurse | Baiap Health Clinic | Baiap, West Ambrym, Vanuatu |
| 19 | Tuesday, 25 August 2015 | Hilson Toaliu | WASH Officer | UNICEF | Port Vila, Vanuatu |
| 20 | Tuesday, 25 August 2015 | Roslyn Arthur | UN Affairs Officer | UNICEF | Port Vila, Vanuatu |
| 21 | Wednesday, 26 August 2015 | Micah Kensley | Provincial Disaster and Climate Change Officer | Sanma Province | Luganville, Vanuatu |
| 22 | Wednesday, 26 August 2015 | Shirley Johnson | Branch Officer, Sanma Province | Vanuatu Red Cross | Luganville, Vanuatu |
| 23 | Wednesday, 26 August 2015 | Philip Panpan | Food Security Officer, Acting Provisional Agriculture Officer | Department of Agriculture and Rural Development, Sanma Province | Luganville, Vanuatu |
| 24 | Thursday, 27 August 2015 | Leon Macreveth | Area Secretary | South Santo Area 1 Council | Namuru, Vanuatu |
| 25 | Thursday, 27 August 2015 | Ravutia Vatimoli | Community Mobilizer |  | Ipayato, Vanuatu |
| 26 | Sunday, 30 August 2015 | Helen Corrigan | Senior Program Manager | Australia High Commission | Port Vila, Vanuatu |
| 27 | Monday, 31 August 2015 | Charlie Damon | Vanuatu Program Manager | CARE International | Port Vila, Vanuatu |
| 28 | Monday, 31 August 2015 | Anjali Nelson | REDD+ Regional Program Advisor | Leave & Learn | Port Vila, Vanuatu |
| 29 | Tuesday, 15 September 2015 | Asenaca Ravuvu Ruci Yauvoli | Assistant Resident Representative Programme Associate | UNDP | via Skype |
| 30 | Wednesday, 7 October 2015 | Salome Kano | Entrepreneur |  | Via Skype |

# Annex F: List of sites visited

| Dates | Project sites |  |  |  |
| --- | --- | --- | --- | --- |
|  | Province | Island | Area Council | Communities |
| 23-25 August 2015 | Malampa | Ambrym | West Ambrym | Baiap |
| 27 August 2015 | Sanma | Santo Espiritu | South Santo 1 | Ipayato |
| 1-2 September 2015 | Tafea | Aniwa | Aniwa | Ikaukau Isavai Imatu |
| 2-4 September 2015 |  | Tanna | Whitesands | Imaio |
| 5 September 2015 | Shefa | Efate | Tanvasoko | Blacksands |

# Annex G: Data collection instruments

Below are questions developed for various project stakeholders. These questions will invite discussion and will be complemented by other questions during the interview based on the focus of conversation.

Questions for stakeholders/beneficiaries in targeted communities – key informant interviews and participatory feedback sessions

- How have the activities improved awareness of disaster risk reduction issues?

- How have the activities raised awareness of the effects of climate change to your community?

- What types of initiatives have you been a part of to improve your community’s ability to prepare and respond to natural hazards?

- Which activities have worked well, which need improvement (go through each component)? Why?

- How did Cyclone Pam affect your community? Do you think that the initiatives conducted in this project helped? If yes, how? How did you respond? What did you do differently than before?

- What more do you think could have been done to improve your community’s ability to prepare and respond to natural hazards?

- Will you be able to continue the project initiatives? Which initiatives are the most important to you and/or your community? Why?

- Do you feel that you have the support from other organizations and state officials? How have they helped?

Questions for state counterparts

- In what way have you and your organization been involved in the project?

- How have you and your organization benefited from your participation in the project?

- What do you think were some of the successes and challenges of the project?

- Which activities have worked well, which need improvement (go through each component)? Why?

- Do you think that the recommendations from the mid-term review were helpful? Did they help to strengthen the project?

- How did the project support your work to address challenges and threats from natural hazards?

- How has this project encouraged your organization or other state bodies to respond to challenges and threats from natural hazards?

- Did this project help during the response to Cyclone Pam? Please give specific examples.

- Do you feel there is greater communication between stakeholders as a result of this project?

- If you were planning for this type of project again, what would you do differently?

Questions for implementing partners

- How effective was the project to strengthen communities’ abilities to prepare and respond to the effects of natural hazards and climate change?

- What is the history of your organizations work in the targeted communities? How has this project contributed to your work?

- What were some of the successes and challenges of this project? Please give specific examples.

- Which activities have worked well, which need improvement (go through each component)? Why?

- Do you think that the recommendations from the mid-term review were helpful? Did they help to strengthen the project?

- Do you think that your own organization’s capacity has been built through this project? If yes, how?

- How was your organization involved in the preparations for and response to Cyclone Pam? Did the project initiatives have a noticeable positive impact on the communities’ abilities to prepare and respond to the cyclone? Please give specific examples?

- Do you feel that the state bodies are supportive of the work that has been done? If yes, in what way?

- Is there greater communication and understanding between stakeholders as a result of this project?

- If you were planning for this type of project again, what would you do differently?

Questions for project staff

Outputs

- Why were certain interventions chosen for this output? What were the reasons for integrating such interventions into the programme?

- How do these interventions build on previous activities?

- How were the locations for these activities chosen?

- How did you identify local partners to implement activities? Were any of these new partners? If so, why were they chosen? If not, why did you chose to work with previous local partners?

- What have been some of the successes of the activities so far? Please cite specific examples.

- What have been some of the challenges to implement the activities so far? Please cite specific examples.

- What has been done to address challenges? Please cite specific examples.

- Which activities have worked well, which need improvement (go through each component)? Why?

- How have state partners provided assistance or not facilitated the process of implementation?

- Do you feel that the activities that you are implementing represent a comprehensive approach in the targeted communities? Please explain. Please cite specific examples. If no, what else could you be doing? Why was this not included into the project?

- Do you think that the recommendations from the mid-term review were helpful? Did they contribute to strengthening the project outputs and outcomes?

Objective and Impact

- What were the processes for supporting activities for objective and impact indicators?

- What have been the successes and challenges in meeting the indicator goals?

- Do you think that the recommendations from the mid-term review were helpful? Did they help to strengthen the project?

Programme Coherence

- Do you think that the activities represent a comprehensive approach by partners to assist communities in this project?

- What have been the responses of stakeholders and beneficiaries regarding the activities? Did they request additional activities be included? Were these feasible requests within the project framework?

- How do you think your activities contributed to resilience?

- Do you feel there is greater communication between stakeholders as a result of this project?

- If you were planning for this type of project again, what would you do differently?

# Annex H: Terms of Reference

UNICEF Pacific

TERMS OF REFERENCE FOR CONSULTANT

Final Evaluation of the Community resilience and coping with climate change and natural disasters in Vanuatu Project

Requesting Section: 	WASH

Date/updated date:	July 2015

Programme Area and Specific Project involved: 	WASH UNTFHS SC110398

*******************************************************************************************************************************

From 2011 to 2015, the United Nations Trust Fund for Human Security funded the Community resilience and coping with climate change and natural disasters in Vanuatu project (the Project) undertaken jointly by UNICEF, UNDP, FAO and the Government of Vanuatu. The overall objective of the Project was to ‘demonstrate enhanced short and long term community resilience and coping capacity to at least six categories of adverse effects of climate change and natural disasters, with special attention to women, children and other vulnerable groups, in Vanuatu and to draw lessons learned in applying the human security concept to the rest of Pacific island countries and territories’.

On behalf of and in cooperation with its partners in the Project, UNICEF is seeking a national or international consultant to undertake a joint final evaluation of the Project. The evaluation must use participatory methodology and be learning oriented.

- Purpose and Objective

The purpose of the evaluation is to document the achievements, constraints, challenges and lessons learned of the Project. The evaluation is being carried out at this time as the project has been completed.

The evaluation is learning oriented with the objective of understanding what worked well to inform scale up and/or replication of successful elements of the Project throughout Vanuatu and the rest of the Pacific Island Countries and Territories. As such the primary audience of the evaluation is the Vanuatu Government and UN agencies that participated in the Project. Potential donors for climate change mitigation and disaster risk reduction programmes are a secondary audience.

- Context

Vanuatu is consistently ranked as one of the most vulnerable countries to natural hazards including tropical cyclones, earthquakes, tsunamis and volcanos. Climate change brings new threats such as coastal erosion and ground water contamination as well as increasing the frequency and severity of meteorological hazards, particularly tropical storms and droughts.

In March 2015, Vanuatu was directly hit by the Category 5 Cyclone Pam. The first such event since formal meteorological records began in Vanuatu. The people of Vanuatu are very resilient, but anecdotal reporting is beginning to be collected that those communities that had been reached by disaster risk reduction programming were better prepared and recovered faster than other communities. This evaluation will add to the growing body of knowledge around the effectiveness of community based resilience programming in Vanuatu and the Pacific more broadly.

The specific parameters of the Project were:

- Twelve selected communities supported and empowered to identify threats/needs and formulate sustainable interventions within the first six to 12 months of the project, and thereafter implement and monitor the interventions. (Component 1: Disaster Risk Reduction and Management)

- All six provincial governments and 12 selected communities have capacity to ensure that local development, local level governance, decision making and the public sector performance enhance community resilience and coping mechanisms during and beyond the project period. (Component 2: Governance and Decision-Making)

- At least 75% of households (6,000) in the selected communities have enhanced food and nutrition security before and after adverse effects of climate change and natural disasters. (Component 3: Food and Nutrition Security)

- At least 75% of households (6,000) in the selected communities have enhanced capacity to and access safe and secure water sources before and after adverse effects of climate change and natural disasters. (Component 4:Water Security)

- Information system, threat monitoring and communication systems established in the selected communities within the first 12 months of the project and thereafter maintained. (Component 5: Knowledge Management)

A mid-term review (MTR) of the Project took place in June 2014 which found that project implementation had not achieved outcomes that may be expected mid-way through the project. The project design deemed to be too ambitious and there have been challenges in clarifying management arrangements and some elements were not yet delivering outcomes. As a result of the MTR, the project ceased support to two sites, Saratamata and Blacksands, where there will be substantial investments by other donors in future projects.

- Scope of Work:

The consultancy is to carry out this evaluation of the Project in relation to the 10 project site area councils targeted since the MTR. It is expected to cover Project components implemented by UNICEF, UNDP, FAO and the Government of Vanuatu. It should consider the entire timeframe of the project from 2011 to 2015. Fieldwork should be carried out at appropriate locations. Locations worst affected by Tropical Cyclone Pam, in particular on Tanna, should not be considered for field work as those communities are still recovering. However, as there is anecdotal reporting that communities that engaged with the project were more resilient to Cyclone Pam, efforts should be made to consult with moderately affected communities.

- Evaluation Criteria and Questions:

Relevance:

- To what extent did the Project, as it was implemented, address threats to human security in the selected communities?

- To what extent was the Project considered to be relevant and useful by communities and local governments?

- How well aligned was the Project to national priorities of the Government of Vanuatu?

- Are there any critical emerging issues that are not within the scope of the Project?

Effectiveness

- To what extent where the Project’s objectives achieved?

- What are the major factors that influenced the achievement or non-achievement of the Project’s objectives/goals?

- Are there any unexpected outcomes of the Project either positive or negative that had not been planned for?

Efficiency

- Has the Project reached the expected number and type of beneficiaries (i.e., individuals/ communities/ institutions/ organizations/ groups etc) within the expected timeframe?

- To what extent has the Project reduced duplication among participating UN Agencies, reduced transaction costs and maximized synergies among national partners?

- What were the gains and losses caused by deviation of the Project from the original project proposal?

Impact:

- How and to what extent has the Project contributed to enhance short and long term community resilience and coping capacity, with a particular focus on the most vulnerable?

Sustainability:

- To what extent has capacity (human and financial resources) been built in area councils and communities to effectively increase human security through local level planning and disaster risk management?

- To what extent has the project promoted national ownership?

- To what extent have standardized methodologies been developed, documented and endorsed?

Cross-cutting concerns

- To what extent has gender and disability been taken into consideration?

- To what extent has civil society been engaged in the community mobilization?

- To what extend has equity and human rights been taken into consideration?

- Evaluation Methodology

This summative evaluation process will take an utilisation-focused approach with the objective of informing scale up and/or replication of successful elements of the Project throughout Vanuatu and possibly other Pacific Island Countries and Territories. It will use mixed methods to collect evidence including the following:

- A desk review of documents related to the Project such as relevant project documentation, including background material used in project formulation, inception workshop report, approved project proposal , program log frame, Results and Resources Framework, annual budgets and work plans, consolidated progress reports, program Baseline Report, Community profiling reports, Partner Coordination Committee minutes as available and other technical reports and documents as relevant, project monitoring reports, including back to office reports, Training Reports, UNDAF, Joint programming and program Guidelines and policies and the 2013 midterm review report of the project.

- Key informant interviews including with members of the program Implementation Team at national, Provincial and area/field levels; key UN Agency staff, the Inter Agency Program Group (IPG) and Human Security Focal Points, representatives of Government at national, regional and local level; partner NGOs, civil society community leaders and other relevant persons.

- Participatory feedback sessions with communities to capture the voice and opinions of the ultimate beneficiaries of the project in regards to its impact on their lives. Opportunities for men, women, boys and girls to participate in feedback sessions wherever possible noting that this will require sensitive handling at the community level.

- Ethical Considerations

The UNICEF Procedure For Ethical Standards In Research, Evaluation, Data Collection And Analysis which conform to UN Ethical Guidelines are applicable and the contractor must ensure compliance with all relevant provisions. In particular, the proposal must include a section identifying anticipated or actual ethical issues throughout the programme as well as the measures and methods anticipated or adopted to address or mitigate against these issues.

- Evaluation Management

The overall responsibility for commissioning the evaluation will be led by UNICEF in consultation with an Evaluation Reference Group with representatives from each of the agencies involved in the Project including the Vanuatu Department of Local Authority, UNICEF, UNDP and FAO. The Evaluation Reference Group is responsible for quality assurance of the evaluation and will be formally consulted in regards to the Inception Report and Final Report (please see work schedule below), including all relevant provisions regarding ethical standards.

The consultant will be responsible for arranging their own travel. The Evaluation Reference Group will facilitate introductions to relevant government bodies and agencies to arrange appropriate entry into communities. The consultant will also set up and conduct interviews, provide qualitative and quantitative data analysis findings, recommendations and lessons learned to the required standards. Throughout the evaluation process, the consultant will be responsible for ensuring the quality of the data collected as well as ensuring that all data collection activities are in compliance with the ethical standards.

- Work Schedule

The evaluation consultancy shall be 30 working days over a period of 35 to 50 working days (depending on the timing of field visits) commencing no later than 31 July 2015.

| Weeks | Activities | Deliverable |
| --- | --- | --- |
| 1 - 2 | - Desk review - Update the mapping of all agencies and projects currently active or planned related to disaster risk reduction and climate change adaptation presented in Annex 1 of the Project Document - Preparation of inception report - Submission of inception report to the Evaluation Reference Group allowing a minimum of three working days for feedback and comment | Electronic copy of the inception report including schedule of and structured questions for key informant interviews and community feedback sessions; and an outline (table of contents) of final report |
| 3 - 5 NOTE: These three working weeks can occur over a period of up to 6 calendar weeks as travel to communities may be difficult to schedule. | - Key informant interviews - Participatory community feedback sessions - Travel - Analysis and documentation of information - Preparation of draft report - Submission of draft report to the Evaluation Reference Group | Electronic copy of draft report as per the table of contents agreed in the inception report. Powerpoint presentation of draft findings/recommendations delivered in person or via conference call with the evaluation management group. As per Ethical procedures, the report must include a section identifying anticipated or actual ethical issues throughout the project as well as the measures and methods adopted to mitigate against these issues. |
| 6 | No action by consultant. Draft report is reviewed commented on by Pacific Enable evaluation reference group. Consultant is not paid for these days. | None |
| 7 | - Revise draft report incorporating comments from the Evaluation Reference Group - Submit final report | Electronic copy of the final evaluation report |

- Payment

30% of the consultancy fee upon submission of the inception report

70% upon the submission of the final report

Travel costs and travel allowance should be included in the overall cost of the contract.

- Qualifications or Specialized Knowledge/Experience Required:

Qualifications

- A relevant university degree

Work experience

- At least 5 years of experience in international development work or related fields

- Demonstrated and documented Experience of conducting and leading evaluations of integrated projects and programs, including participatory methodologies

- Experience working with UN and Government agencies, and with communities

Skills and knowledge

- A demonstrated understanding of human security, resilience and disaster risk reduction

- Knowledge of political, economic and social developments trends in Vanuatu will be an asset

- Demonstrable analytical skills and strong interviewing and drafting/report writing skills

- Excellent coordination and team working skills

Language

- Fluency in spoken and written English

- Understanding of the Bislama language is an advantage

- General Conditions of Contracts for the Services of Consultants / Individual Contractors

1. Legal Status

The individual engaged by UNICEF under this contract as a consultant or individual contractors (the “Contractor”) is engaged in a personal capacity and not as representatives of a Government or of any other entity external to the United Nations. The Contractor is neither a "staff member" under the Staff Regulations of the United Nations and UNICEF policies and procedures nor an "official" for the purpose of the Convention on the Privileges and Immunities of the United Nations, 1946. The Contractor may, however, be afforded the status of "Experts on Mission" in the sense of Section 22 of Article VI of the Convention and the Contractor is required by UNICEF to travel in order to fulfill the requirements of this contract, the Contractor may be issued a United Nations Certificate in accordance with Section 26 of Article VII of the Convention.

2. Obligations

The Contractor shall complete the assignment set out in the Terms of Reference for this contract with due diligence, efficiency and economy, in accordance with generally accepted professional techniques and practices.

The Contractor must respect the impartiality and independence of UNICEF and the United Nations and in connection with this contract must neither seek nor accept instructions from anyone other than UNICEF. During the term of this contract the Contractor must refrain from any conduct that would adversely reflect on UNICEF or the United Nations and must not engage in any activity that is incompatible with the administrative instructions and policies and procedures of UNICEF. The Contractor must exercise the utmost discretion in all matters relating to this contract.

In particular, but without limiting the foregoing, the Contractor (a) will conduct him- or herself in a manner consistent with the Standards of Conduct in the International Civil Service; and (b) will comply with the administrative instructions and policies and procedures of UNICE relating to fraud and corruption; information disclosure; use of electronic communication assets; harassment, sexual harassment and abuse of authority; and the requirements set forth in the Secretary General's Bulletin on Special Measures for Protection from Sexual Exploitation and Sexual Abuse.

Unless otherwise authorized by the appropriate official in the office concerned, the Contractor must not communicate at any time to the media or to any institution, person, Government or other entity external to UNICEF any information that has not been made public and which has become known to the Contractor by reason of his or her association with UNICEF or the United Nations. The Contractor may not use such information without the written authorization of UNICEF, and shall under no circumstances use such information for his or her private advantage or that of others. These obligations do not lapse upon termination of this contact.

3. Title rights

UNICEF shall be entitled to all property rights, including but not limited to patents, copyrights and trademarks, with regard to material created by the Contractor which bears a direct relation to, or is made in order to perform, this contract. At the request of UNICEF, the Contractor shall assist in securing such property rights and transferring them to UNICEF in compliance with the requirements of the law governing such rights.

4. Travel

If UNICEF determines that the Contractor needs to travel in order to perform this contract, that travel shall be specified in the contract and the Contractor’s travel costs shall be set out in the contract, on the following basis:

- UNICEF will pay for travel in economy class via the most direct and economical route; provided however that in exceptional circumstances, such as for medical reasons, travel in business class may be approved by UNICEF on a case-by-case basis.

- UNICEF will reimburse the Contractor for out-of-pocket expenses associated with such travel by paying an amount equivalent to the daily subsistence allowance that would be paid to staff members undertaking similar travel for official purposes.

5. Statement of good health

Before commencing work, the Contractor must deliver to UNICEF a certified self-statement of good health and to take full responsibility for the accuracy of that statement. In addition, the Contractor must include in this statement of good health (a) confirmation that he or she has been informed regarding inoculations required for him or her to receive, at his or her own cost and from his or her own medical practitioner or other party, for travel to the country or countries to which travel is authorized; and (b) a statement he or she is covered by medical/health insurance and that, if required to travel beyond commuting distance from his or her usual place or residence to UNICEF (other than to duty station(s) with hardship ratings “H” and “A”, a list of which has been provided to the Contractor) the Contractor’s medical/health insurance covers medical evacuations. The Contractor will be responsible for assuming all costs that may be occurred in relation to the statement of good health.

6. Insurance

The Contractor is fully responsible for arranging, at his or her own expense, such life, health and other forms of insurance covering the term of this contract as he or she considers appropriate taking into account, among other things, the requirements of paragraph 5 above. The Contractor is not eligible to participate in the life or health insurance schemes available to UNICEF and United Nations staff members. The responsibility of UNICEF and the United Nations is limited solely to the payment of compensation under the conditions described in paragraph 7 below.

7. Service incurred death, injury or illness

If the Contractor is travelling with UNICEF’s prior approval and at UNICEF's expense in order to perform his or her obligations under this contract, or is performing his or her obligations under this contract in a UNICEF or United Nations office with UNICEF’s approval, the Contractor (or his or her dependents as appropriate), shall be entitled to compensation from UNICEF in the event of death, injury or illness attributable to the fact that the Contractor was travelling with UNICEF’s prior approval and at UNICEF's expense in order to perform his or her obligations under this contractor, or was performing his or her obligations under this contract in a UNICEF or United Nations office with UNICEF’s approval. Such compensation will be paid through a third party insurance provider retained by UNICEF and shall be capped at the amounts set out in the Administrative Instruction on Individual Consultants and Contractors. Under no circumstances will UNICEF be liable for any other or greater payments to the Contractor (or his or her dependents as appropriate).

8. Arbitration

- Any dispute arising out of or, in connection with, this contract shall be resolved through amicable negotiation between the parties.

- If the parties are not able to reach agreement after attempting amicable negotiation for a period of thirty (30) days after one party has notified the other of such a dispute, either party may submit the matter to arbitration in accordance with the UNCITRAL procedures within fifteen (15) days thereafter. If neither party submits the matter for arbitration within the specified time the dispute will be deemed resolved to the full satisfaction of both parties. Such arbitration shall take place in New York before a single arbitrator agreed to by both parties; provided however that should the parties be unable to agree on a single arbitrator within thirty days of the request for arbitration, the arbitrator shall be designated by the United Nations Legal Counsel. The decision rendered in the arbitration shall constitute final adjudication of the dispute.

9. Penalties for Underperformance

Payment of fees to the Contractor under this contractor, including each installment or periodic payment (if any), is subject to the Contractor’s full and complete performance of his or her obligations under this contract with regard to such payment to UNICEF’s satisfaction, and UNICEF’s certification to that effect.

10. Termination of Contract

This contract may be terminated by either party before its specified termination date by giving notice in writing to the other party. The period of notice shall be five (5) business days (in the UNICEF office engaging the Contractor) in the case of contracts for a total period of less than two (2) months and ten (10) business days (in the UNICEF office engaging the Contractor) in the case of contracts for a longer period; provided however that in the event of termination on the grounds of impropriety or other misconduct by the Contractor (including but not limited to breach by the Contractor of relevant UNICEF policies, procedures, and administrative instructions), UNICEF shall be entitled to terminate the contract without notice. If this contract is terminated in accordance with this paragraph 10, the Contractor shall be paid on a pro rata basis determined by UNICEF for the actual amount of work performed to UNICEF’s satisfaction at the time of termination. UNICEF will also pay any outstanding reimbursement claims related to travel by the Contractor. Any additional costs incurred by UNICEF resulting from the termination of the contract by either party may be withheld from any amount otherwise due to the Contractor under this paragraph 10.

11. Taxation

UNICEF and the United Nations accept no liability for any taxes, duty or other contribution payable by the consultant and individual contractor on payments made under this contract. Neither UNICEF nor the United Nations will issue a statement of earnings to the consultant and individual contractor.

Prepared by Section Chief:			Approved by Deputy Representative **

Name/Title:					Name:

Date:						Date

** All Programme TORs to be approved by Deputy Representative and Operations TOR to be approved by Operations Manager.

(To be added to terms and conditions for Studies and Evaluations)

ETHICS FOR SAFEGARDING THE INTERESTS/RIGHTS OF CHILDREN AND WOMEN IN RESEARCH

NON-DISCRIMINATION

When consultants conduct interview/focused group research/survey that involves third party, consultants shall ensure that selection of participants and the processes and methods used serve to correct, not reinforce, patterns of exclusion. This requires attention to socio-economic barriers including gender and age discrimination as well as the different ways and capacities in which children and women express themselves.

PARTICIPATION

Consultants shall ensure that the purposes and processes of the research are fully explained, using alternative forms of communication where necessary and making reference to any implications for participants of time, cost and the possible influence of the outcomes. The way information is conveyed must be appropriate to the context and to the child capabilities when child is involved.

INFORMED CONSENT

Consultant shall ensure that the participants know their right to refuse or to withdraw from the research at any time and obtaining verbal or written consent without coercion. Parental consent is not an adequate standard in light of the rights of the child and consent should be ongoing negotiation process with child.

IDENTIFICATION OF RISKS

Consultant should be mindful of the risks involving children and women in the research. Consultant should withhold information where that information may place them at risk and take necessary measures to protect them from placing themselves at risk.

CONFIDENTIALITY

Consultants shall offer conditional anonymity and confidentiality to all participants and explain to participants the limitation of confidentiality and possible intervention based on what is in their best interests. Consultant is fully responsible for identifying the follow-up action and referrals to be made in case confidentiality is broken.

MISUSE OF INFORMATION

Consultants are fully responsible for considering the short and long term consequences of the research from the different perspectives of participants, policy-makers, researchers and UNICEF.

# Index of Questions

CC1, 24, 28, 29, 44, 47, 48, 87

CC2, 24, 28, 29, 30, 43, 44, 46, 47, 48, 87

CC3, 24, 29, 30, 34, 44, 47, 48, 87

EC1, 22, 25, 26, 27, 28, 29, 31, 32, 34, 35, 36, 37, 38, 39, 40, 41, 42, 43, 45, 47, 87

EC2, 21, 22, 25, 26, 27, 28, 29, 30, 31, 32, 34, 36, 39, 40, 41, 42, 43, 44, 45, 46, 47, 87

EC3, 22, 24, 25, 26, 27, 28, 29, 30, 31, 32, 36, 37, 39, 40, 41, 47, 87

EF1, 21, 22, 23, 28, 29, 31, 32, 34, 35, 37, 38, 39, 40, 41, 42, 43, 44, 45, 46, 47, 87

EF2, 16, 31, 32, 41, 42, 87

EF3, 25, 30, 41, 42, 43, 87

I1, 23, 25, 28, 29, 30, 31, 32, 34, 35, 36, 37, 38, 39, 40, 42, 43, 44, 45, 46, 47, 87

R1, 16, 19, 20, 21, 22, 23, 24, 25, 26, 31, 32, 34, 35, 36, 37, 38, 39, 40, 42, 45, 46, 87

R2, 16, 19, 22, 23, 24, 25, 26, 28, 29, 30, 39, 40, 43, 44, 45, 46, 87

R3, 16, 19, 23, 24, 26, 46, 47, 87

R4, 16, 23, 24, 25, 28, 29, 87

S1, 22, 23, 24, 27, 28, 29, 30, 31, 32, 34, 35, 37, 38, 39, 40, 42, 44, 45, 46, 47, 87

S2, 23, 24, 27, 28, 29, 30, 34, 35, 37, 38, 39, 40, 43, 44, 45, 46, 47, 87

S3, 24, 25, 28, 30, 34, 35, 37, 38, 44, 45, 46, 87

List of Questions

| Relevance | R1: To what extent did the Project, as it was implemented, address threats to human security in the selected communities? R2: To what extent was the project considered to be relevant and useful by communities and local governments? R3: How well aligned was the Project to national priorities of the Government of Vanuatu? R4: Are there any critical emerging issues that are not within the scope of the Project? |
| --- | --- |
| Effectiveness | EC1: To what extent were the Project’s objectives achieved? EC2: What were the major factors that influenced the achievement or non-achievement of the objectives/goals? EC3: Are there any unexpected outcomes of the Project either positive or negative that had not been planned for? |
| Efficiency | EF1: Has the Project reached the expected numbers and type of beneficiaries (i.e. individuals/communities/institutions/organizations/groups, etc.) within the expected timeframe? EF2: To what extent has the Project reduced duplication among participating UN Agencies, reduced transaction costs and maximized synergies among national partners? EF3: What were the gains and losses caused by deviation of the Project from the original project proposal? |
| Impacts | I1: How and to what extent has the Project contributed to enhance short- and long-term community resilience and coping capacity, with a particular focus on the most vulnerable? |
| Sustainability | S1: To what extent has capacity (human and financial resources) been built in the area councils and communities to effectively increase human security through local-level planning and disaster risk management? S2: To what extent has the project promoted national ownership? S3: To what extent have standardized methodologies been developed, documented and endorsed? |
| Cross-cutting concerns | CC1: To what extent has gender and disability been taken into consideration? CC2: To what extent has civil society been engaged in the community mobilization? CC3: To what extent has equity and human rights been taken into consideration? |

Vanuatu National Statistics Office, ‘Live Population of Vanuatu’, http://www.vnso.gov.vu/ (accessed 15 August 2015). In the 2009 census, the country had a population of 234,023 (110,091 men and 114,932 women). Vanuatu National Statistics Office, ‘2009 National Population and Housing Census: Analytical Report Volume 2’ (2011), p. vii.

UNDP, ‘Explanatory note on the 2014 Human Development Report composite indices: Vanuatu’, p. 2.

Ibid., p. 4.

Vanuatu National Statistics Office, ‘Statistics Pocketbook 2013’, p. II.

Vanuatu National Statistics Office, ‘Vanuatu Household Income and Expenditure Survey 2010’ (2012), p. 33. For more information, see Section 4.1.2.

Vanuatu National Statistics Office, ‘Statistics Pocketbook 2013’, p. 1. Exchange rate used was US dollar 1 = Vanuatu vatu (VUV) 96.3473746786 from 31 December 2013, http://www.xe.com/currencytables/?from=VUV&date=2013-12-31 (accessed 15 August 2015).

UNDP, ‘Income Gini coefficient’, http://hdr.undp.org/en/content/income-gini-coefficient (accessed 15 August 2015).

UNICEF, UNDP, FAO, ‘Community resilience and coping with climate change and natural disasters in Vanuatu, 2011-2013’, Project Proposal submitted to the United Nations Trust fund For Human Security, Reference: CN09-025 (10 December 2010), p. 14.

UNICEF, ‘Report of Information and Knowledge Management: UNICEF ROSA’ (2008), p. iii.

Population figures taken from the 1999 population census.

UNICEF, UNDP, FAO, op cit., pp. 9-10.

This table has been compiled based on information from the UNTFHS project proposal, information from the Vanuatu National Statistical Office and personal interviews. Note that village names may differ from official or locally used names or spellings.

O’Callaghan, B. and M. Hardwick, ‘Community resilience and coping with climate-change and natural disasters in Vanuatu. United Nations Trust Fund for Human Security. Mid-term review’ (2014), pp. 5, 12 & 21-22.

For more information, see OECD DAC http://www.oecd.org/dac/ (accessed 4 October 2015).

OECD, ‘Glossary of Key Terms in Evaluation and Results Based Management’ (2002), p. 32.

Objective 5 of the Community Resilience Project has not been included here as it not a focus for development frameworks, yet remains a vital aspect ensuring that monitoring and evaluation work is done to promote lessons learned for Vanuatu and other countries. See also UNICEF, UNDP, FAO, op cit., pp. 9-10.

Government of the Republic of Vanuatu, ‘Priorities and Action Agenda 2006-2015’ (2006).

United Nations, ‘Pacific Sub-Region: United Nations Development Assistance Framework (UNDAF) (2008-2012): Mid-Term Review’ (2010).

United Nations, ‘Vanuatu: UNDAF Results Matrix 2013-2017’ (2013).

Communities are area councils.

United Nations, ‘United Nations Common Multi-Country Assessment for the Pacific Island Countries and Territories under the Fiji and Samoa Multi-Country Offices in preparation for the United Nations Development Assistance Framework for the Pacific Sub-Region (2013-17)’ (2011), p. 88.

Interview, Port Vila, Vanuatu, 13 August 2015.

Vanuatu National Statistics Office, ‘Vanuatu Household Income and Expenditure Survey 2010’ (2012), p. 33.

Social Policy Research Centre, ‘Child Poverty and Disparity Study in Vanuatu’ (2010), p. 3.

The seven dimensions are: food, water, shelter, sanitation, health, education and information.

Minujin, A., ‘Child Poverty in East Asia and the Pacific: Deprivation and Disparities, A Study of Seven Countries’, with D. Born and Sk. Dobson, UNICEF (2011), p. 12.

UNICEF, ‘State of the World’s Children 2015: Executive Summary. Reimagining the future: Innovation for Every Child’, p. 46.

Vanuatu National Statistics Office and UNDP Pacific Centre, ‘Vanuatu Hardship & Poverty Report: Analysis of the 2010 Household Income and Expenditure Survey’ (2012), p. 9.

Ibid., p. 9.

Ibid., p. 9.

Narsey, W. L., ‘Poverty Analysis in Vanuatu: A Critical Review and Alternative Formulation’, South Pacific Studies 33:1 (2012), p. 48.

O’Callaghan, B. and M. Hardwick, op cit., p. 38.

Ibid., p., 12.

UNICEF, ‘Debriefing on Community resilience and coping with climate change and natural disasters in Vanuatu 2011-2012’ (23 July 2010).

UNICEF, UNDP, FAO, op cit., p. 12.

Ibid., p. 8.

OCHA, ‘Vanuatu: Severe Tropical Cyclone Pam. Situation Report No. 1 (as of 15 March 2015)’.

ABC News, ‘Tropical Cyclone Pam: Vanuatu death toll rises to 16 as relief effort continues’, 22 March 2015, http://www.abc.net.au/news/2015-03-21/un-raises-vanuatu-cyclone-death-toll/6337816 (accessed 15 August 2015).

OCHA, ‘Vanuatu: Severe Tropical Cyclone Pam. Situation Report No. 12 (as of 26 March 2015)’.

Walker, P. and P. Farrell, ‘Cyclone Pam: 24 confirmed dead as Vanuatu president blames climate change’, The Guardian, 16 March 2015, http://www.theguardian.com/world/2015/mar/16/vanuatus-president-blames-climate-change-for-extreme-weather (accessed 15 August 2015).

See, for example, Huffer, E. and G. Molisa, ‘Governance in Vanuatu: In Search of the Nakamal Way’, State, Society and Governance in Melanesia, Discussion Paper 4 (1999); and Malvatumauri National Council of Chiefs, University of Queensland and AusAID, ‘Kastom Governance is for everyone: Vanuatu Kastom Governance Partnership 2005-2012’ (2012).

See, for example, Mial, A., ‘Reviving Fres Wota Women’s Council to increase women’s participation, improve safety and raise awareness of importance of language and Kastom’, in ‘Kastom Governance is for everyone: Vanuatu Kastom Governance Partnership 2005-2012’, Malvatumauri National Council of Chiefs, University of Queensland and AusAID (2012), pp. 36-38.

Research through La Trobe University relating to the Pacific Leadership Program (http://www.plp.org.fj/ - accessed 14 September 2015), is one such programme.

UNICEF, UNDP, FAO, op cit., p. 6.

FAO, IFAD, WFP, ‘The State of Food Insecurity in the World. Meeting the 2015 international hunger targets: taking stock of uneven progress’ (2015), p. 17.

UNCTAD, ‘Copra/Coconut’, National Stakeholder Workshop: Green Export Review – Vanuatu’, Port Vila, Vanuatu, 27-28 August 2014, http://unctad.org/meetings/en/Presentation/11_ditcted_010914_unctadRH_copra-coc.pdf (accessed 24 September 2015).

UN-Water Decade Programme on Advocacy and Communication and Water Supply and Sanitation Collaborative Council, ‘The Human Right to Water and Sanitation: Media Brief’ (n.d.), p. 2.

Vanuatu National Statistics Office, ‘Statistics Pocket Book 2013’, p. II.

OECD op cit., p. 20.

UNICEF, UNDP, FAO, op cit., p. 18.

O’Callaghan, B. and M. Hardwick, op cit., p. 14.

It is not clear whether people directly involved in the project were members of NAB. Although it is not clear when the website was last updated, but the list of contacts does not list anyone that was directly involved in the project as members of NAB (see http://www.nab.vu/contact-search, accessed 18 September 2015). Thus, if the NAB meetings did take place, it is not clear who presented the information.

UNICEF, UNDP, FAO, op cit., p. 8.

O’Callaghan, B. and M. Hardwick, op cit., p. 15.

O’Callaghan, B. and M. Hardwick, op cit., p. 23.

Ibid.

UNICEF, UNDP, FAO, op cit., p. 28.

UNICEF, ‘Disaster Risk Reduction (DRR)’, (n.d.), http://www.unicef.org/esaro/5484_disaster_risk_reduction.html (accessed 21 September 2015).

Napat, J., ‘Vanuatu: National progress report on the implementation of the Hyogo Framework for Action’, Vanuatu Meteorological Services (2009), pp. 10-11. Document can be accessed at: file:///H:/2_Temp/7504_Vanuatu[1].pdf (accessed 6 October 2015).

Esau, M., ‘Republic of Vanuatu: Final Report – Education on Natural Disaster Preparedness for Sustainable Development’, National Disaster Risk Management Office (2008), pp. 33-43. Document can be accessed at: http://www.preventionweb.net/files/3561_VANUATUFINALREPORTONENDPPROJECT.pdf (accessed 6 October 2015).

UNISDR, ‘Let’s learn to prevent disasters: educational kit and riskland game’, (n.d.), http://www.unisdr.org/we/inform/publications/2114 (accessed 21 September 2015).

In this report, ‘context’ refers to the specific economic, political and social issues that are present in a community, which need to be taken into consideration in order for development initiatives to ensure that the initiatives do no harm.

Information from meetings with CARE International and Live & Learn. Additional information from O’Callaghan, B. and M. Hardwick, op cit., p. 26.

After the initial training, the Area Secretary of Aniwa Area Council asked CARE International to help develop an area council disaster plan for Aniwa. This was in 2013, before UNDP contracted CARE International and Live & Learn to do this work in other sites.

See World Visioin, ‘Community Based Disaster Risk Management Project: Yumi mekem rere blong katem daon ol trabol we i isi blong i save happen long komuniti blong yumi’ (nd). The evaluator saw this report in Ipayato community and it contained information related to the community’s natural hazards and DRR planning.

CARE International, ‘Final Report to UNDP’ (June 2015), p. 5.

UNICEF, UNDP, FAO, op cit., p. 8.

Information provided by Mathias Bule, Information Officer, Department of Agriculture and Rural Development. See also, Department of Agriculture and Rural Development, Talemaot, Issue #8 (December 2014), p. 4.

Information provided by Mathias Bule, Information Officer, Department of Agriculture and Rural Development.

Exchange rate was USD 1 = VUV 114.387. Information from http://www.xe.com (accessed 5 October 2015).

OECD op cit., p. 21.

It is not clear, however, how the World Vision project was developed and to what extent the organization examined the work of other partners.

OECD op cit, p. 24.

‘In fact, women have always been active in plantations where the families own cattle or small animals. The reality is that it has always been the men who claim to be the farmers while in reality [sic], the whole family is responsible for the animals on the farm.’ Garae, L., ‘More young women show interest in farming’, 22 July 2015, http://dailypost.vu/news/more-young-women-show-interest-in-farming/article_d6db7953-6761-5608-b26d-219d885da589.html (accessed 27 September 2015). Respondents shared similar sentiments with the evaluator during the mission in Vanuatu.

OECD op cit., p. 36.

Jonas, M., ‘Governance Training for Northern Provinces’ (2014), p. 3. No similar suggestion was found for southern provinces. See, UNDP, ‘Governance Training Program – Report: Tafea & Shefa Provincial Council Training Report (7-11 April 2014)’.

CARE International produced reports for each community within the area council. Also, the World Vision ‘Community Based Disaster Risk Management Project’ also produced reports for each community and the province to serve as a knowledge base to build on project initiatives after the completion of the report.

Note that his is not a category included in the OECD approach. It was included in this evaluation to ensure that cross-cutting issues were separately examined.

Vanuatu National Statistics Office (VSNO), ‘2009 National Population and Housing Census: Analytical Report Volume 2’ (2011), p. xii. These figures, however, have been challenged in a later report. See VSNO and UNICEF, ‘Children, Women and Men with Disabilities in Vanuatu: What do the data say? (2014), p. 6. This report suggested the actual rate of disabilities could be from 5 per cent to 3.3 per cent of the total population. It is unclear why there is such a significant difference as data was taken from the 2009 census.

Equity refers to ‘All children have an opportunity to survive, develop and reach their full potential without discrimination, bias or favouritism. […] The equity-based approach in UNICEF’s programmes and policies seeks to understand and address the root causes of inequity so that all children, particularly those who suffer the worst deprivations in society, have access to education, health care, sanitation, clean water, protection and other services necessary for their survival, growth and development.’ UNICEF, ‘What does UNICEF mean by equity approach?’ (25 October 2011), http://www.unicef.org/about/partnerships/index_60239.html (accessed 1 October 2015).

Activity 2.2.2, UNICEF, UNDP, FAO, op cit., p. 28.

Support for the Department of Women’s Affairs was accepted by Vanuatu in its responses to recommendations and voluntary pledges, ‘UPR, 2RP: Responses to Recommendations & Voluntary Pledges, Vanuatu, Second Review, Session 18’ (2014) paragraph 99.22, p. 3.

UNICEF, ‘DRR in Education: Good Practices and New Approaches’ (2013), http://www.unicef.org/ceecis/DRR_Good_Practices_and_New_Appraoches.pdf (accessed 1 October 2015).

Information for Components 1, 2, 3 and 4 from 30 November 2014. Information for Component 5 from 31 December 2015. UNICEF, UNDP, FAO, ‘Community Resilience and Coping with Climate Change and Natural Disasters in Vanuatu: Fourth Progress Report to the United Nations Trust Fund for Human Security (November 2013 – November 2014)’ (2014), pp.11-21. Additional information obtained during interviews with project coordinators and from the MTR.

Communities are area councils.

Indictor revised from 12 to 10 area councils as agreed based on the findings of the MTR in 2014.

For information from one of the Mach 2013 Training of Trainers workshop, in which 42 people received training, see UNDP, ‘Training of Trainers (TOT) Workshop – Report 2013’.

UNDP, ‘Training of Trainers (TOT) Workshop – Report 2013’, p. 2.

In a feasibility report, Asif Chida noted that community members and stakeholders identified these cooperatives. Chida also noted that there is still ‘significant potential’ to operationalize savings and loans schemes. Chida, A., ‘Vanuatu Community Resilience to Climate Change Project: Feasibility Report for Establishing Livelihoods Projects in Aniwa, West Ambae, Tanna, and South Santo’, UNDP (2014), p. 3.

Indictor revised from 12 to 10 area councils as agreed based on the findings of the MTR in 2014.

UNDP, ‘Governance Training Program – Report: Tafea & Shefa Provincial Council Training Report’ (2014), pp. 15-16, 18.

Jonas, M., ‘Governance Training for Northern Provinces’ (2014), pp. 2 & 3.

O’Callaghan, B. and M. Hardwick, op cit., paragraph 104, p. 30.

Indicator revised as recommended by MTR.

For more information, see http://akvo.org/products/akvoflow/ (accessed 28 September 2015).

Communities will be the Area Councils.