## MR
EMR Tracker
Evaluation Management Response Document
Region: | MENAR
Office: | Lebanon
Evaluation Year: | 2018
Evaluation Title: | Evaluation of Immunisation Programme (EPI) in Lebanon (2013-2017)
Evaluation Report Sequence Number: |  | Lebanon/59/2018/616
Person In Charge For Follow Up to Management Response: |  |  | Lovemore Mhuriyengwe
Planned Use of the Evaluation
-
Allowed Editor(s): | Genevieve Begkoyian , Christopher Choueiri , Georges Haddad
Recommendations and Actions
No. | Recommendation/Action |  | Responsible Section (Action) | Responsible Person Name(Action) | Expected Completion (Action) | Mgt Response/ Implementation Stage | Reason/Action Taken
1 | The AWP should mention specific strategies to address families from lower-socio economic backgrounds. Although UNICEF staff acknowledged that residual costs were a constant barrier for accessing vaccines, the activities detailed in the AWPs from 2013 to 2017 do not incorporate any specific strategy for overcoming those challenges at a programmatic level. In that regard, UNICEF could support the MoPH in the analysis of out of pocket expenditures related to immunisation and the drafting of a National policy on free access to vaccine and to vaccination till full immunisation of the child. |  |  |  |  | Disagree | No more agree ( ref activities related to AIA in RWP 2019, and 2020) RWP 2019: 1B.3.3 Support of supplementary and accelerated immunization activities (Polio , MMR & Vit A) in addition to enhanced routine immunization activities (Schools, Nurseries-Borders centers-UNHCR Vaccination sites) activity 2020: activity A.1.B.3.1.1.a Support EPI points and UNRWA health centers in supplementary and accelerated immunization activity implementation. Accelerated immunization activities (AIA) in 2018 & 2019 have been specifically designed (i) to identify drop out and left out children in low coverage cadaster (ii) to focus on most vulnerable, unreachable and remote cadaster that were identified as "low coverage " cadaster in the2016 EPI survey . In addition, in cosnultation with PHC coordinator AIA were as well conducted in additional cadaster identifed as at risk cadasker. More than 1/2 million children were reached, 375,000 identified in need of immunization > 200,000 came back to immunization.
1 | Continue advocacy discussions with MoPH and main stakeholders |  | Chief child survival Health officer | Genevieve Begkoyian Farah Mazloum | 2019-03-29 | Completed | 1-Social Policy and H&N team met with World Bank to advocate for free immunization in contect of UHC 2-Systematic particpation in the EU MADAD steering committee, to confirm free / affordable vaccine services in conext of MADAD funded health projects 3-Supported MoPH in issuing decree for private doctors access to MoPH vaccine store, only if they provide for free and report against the children vaccinated to MoPH 4-Design the AIA approach in response to the measles outbreak - referring children to free vaccination at identified PHCs; in addition, to free on spot vaccination through mobile units in isolated areas. 5-2019 Measles campaign was jointly plan with WHO MoPH and other health stake holder. 6-Chief of HN meeting Director of PHC on a weekly basis, is member of the EPI technical Committee, and of the Health core working group, HN Staff are all part of the inter agency working group.
2 | Equity analysis on immunization |  | Chief Child Survival | Genevieve Begkoyian | 2021-06-30 | Underway | ToR updated for an immunization financing analysis, in link with the current context in Lebanon's multifacet crisis. To be finalized this week and to be launched and conducted during Q2
3 | Identify steps needed to draft a policy on free routine immunization in Lebanon |  | Chief Child Survival Health officer Social Policy staff | Genevieve Begkoyian Farah Mazloum | 2021-06-30 | Underway | based on the immunization financing analysis, and taking into consideration the introduction of COVIED 19 vaccines, we will engage in a policy dialogu with MoPH and the provate sector to dtrengthen the immunization programme and mitigate the impact of COVID 19 introuction on the immunization programme, and reduce the out of pocket expenditre of the most vulnerable to access free vaccination for the child and free COVID 19 vaccines for the priority target (Eldrely, etc.)
4 | Draft Policy that includes monitoring and accountability aspects (possible sanctions) |  | Chief Child Survival Health officer Social Policy Staff | Genevieve Begkoyian Farah Mazloum | 2021-06-30 | Underway | embedded within the two previous responses
5 | Draft action plan to implement Policy |  | Chief Child Survival + Social Policy staff | Genevieve Begkoyian | 2021-06-30 | Underway | embedded within the two previous responses
2 | Furthermore, there was little mention of specific strategies to address families with disabled children. In line with UNICEF global efforts, more should be done in Lebanon to work with the MoPH to ensure health professionals do not consider disability alone as a contraindication for immunization. |  |  |  |  | Agree | Capacity Building of nurses and paediatricians and GPs in all PHCs on disability and immunization and develop immunization guideline for disabled children to be distributed in all PHCs in Lebanon by end of 2020. Capacity building of data IT/ EPI staff on importance of quality disaggregation of immunization data for children with disability And UNICEF integrated technical support to assess barriers to EPI for children with disability (with Child protection/ Social policy, Education and C4D sectors)
1 | Establish a committee with main stakeholders |  | HN focal point on disability | Genevieve Begkoyian | 2021-04-30 | Underway | first consultation with pediatricians took place on 26-11-2020 to call for engaging the private pediatricians in the free access to routine vaccination of the child including monitoring and the use of the MERA application. Following the first consultation, during Q 1 an additional consultation, this needs follow up to define concrete next steps for larger engagement of pediatricians with routine immunization
2 | Review existing guidelines related to Routine immunization and disabled children |  | Health officer | Genevieve Begkoyian Farah Mazloum | 2020-12-30 | Completed | the focus in 2020 was to integrate all COVID 19 prevention within the guidelines and SOP of the immunization programmes to ensure vaccination in a covid 19 free environment (as per WHO IPC conducted trainings)
3 | Draft guidelines |  | Health officer | Genevieve Begkoyian Farah Mazloum | 2021-06-30 | Underway | Based on MERA data base, we are targeting defaulter children in routine immunization catch-up
4 | Finalize guidelines |  | Health Officer | Genevieve Begkoyian | 2021-06-30 | Underway | AIA eveluation is undergoing; this will support in proposing needed recommendations for way forward in Routine Immunization catch up
3 | Capacity building activities should be more closely documented and should be focused on providing Training of Trainer (ToT) activities rather than simply training. Hence, ToT should support greater sustainability across MoPH, at the central, district and local level, and provide MoPH with the knowledge and skills to run their own training as new staff are contracted, rather than UNICEF needing to repeat training sessions. |  |  |  |  | Partially agree | UNICEF agrees on the need for TOT (especially for sustainability aspect), however, to ensure the quality of trainings we are opting for trainings. UNICEF agrees on putting more time in documenting the trainings conducted (noting that most of them do include pre-post tests, however not well documented) . All trainings supported by UNICEF this year were mainly around AIA. UNICEF only contributed to the design and the update of training materials, that were all elaborated under the MoPH leadership. Training of EPI staff, of PHC staff , of community health workers were all done by PHC coordinators and District level staff, with only a technical contribution or facilitation from UNICEF
1 | Esnure all trainings conducted till end of 2020 include pre-post tests and are well documented |  | HN roving Officer + C4D officer + PRIME | Genevieve Begkoyian | 2020-12-31 | Completed | 1-First AIA training was conceived across sector coordination to integrate: (1) Social Behaviour change on Immunization (2)IYCF practice (3) Immunization data by health workers 2-Second AIA training was designed sing lessons learned and good pracice from 1st AIA training; inititally conceived as a TOT was finally conducted as a training as part of capacity building (as TOT was not yet feasible - due to turnover of staff among different stakholders) 3-In context of AIA scale-up and plan of mass measles campaign; ToT is planned and integrated in the approach
4 | UNICEF can support PHCs through the introduction of practices and policies which promote equality across nationalities, providing greater support to hamper any misconceptions about biased among Syrians or Lebanese. |  |  |  |  | Agree | UNICEF advocates with MoPH for quality service that ensures respect and integrity among all right holders from different nationalities, and support MoPH as well in data collection / reporting on gender and on children with disability. Guideline and training/ supportive supervision and technical support to PHC coordinator and Qada staff for them to cascade the capacity building at PHC level on good practices UNICEF can’t implement proper/un-biased patient treatment and PHCs level, but can continue advocacy efforts and support in Inter-personal communication skills training for health staff at PHCs by 2020
1 | Prepare trainings and agendas for all PHC staff on essential IPC skills to ensure respect and proper treatment of patients from all nationalities – abiding by MoPH PHC values |  | HN Roving officer + C4D Officer | Genevieve Begkoyian | 2019-10-30 | Completed | 1-The AIA plans were based on measles attack rate, low immunization coverage with a micro-plan organized at local level with no descremination among all children. 2-all outreach workers and vaccinators through AIA were trained on IPC that emphasized vaccination for all (no descremination) 3-As a result, AIA in 2018, reached 48% Lebanese and 52% non-Lebanese. 4- Still undergoing in context of COVID. IPC and PPE equipment an dtraining were reinforced in context of COVID 19 response. 84 PHC have been equipped with PPE to continue immunization and MNCAH.
2 | Conduct needed trainings for all PHCs |  | HN Roving Officer | Genevieve Begkoyian | 2020-01-31 | Completed | (1) AIA trainings were done to PHC staff identified by MoPH (2) Future trainings will take place
3 | Ensure effective compliant mechanism and evaluation of respectful service at PHCs |  | HN Roving Officer | Genevieve Begkoyian | 2020-10-31 | Completed | Completed, Grievance system exists at the MoPH. Put in place by the PHC.
5 | In order to target residual costs that hinder access to vaccination services, UNICEF could further support the MoPH in tackling the cost of vaccines through PHCs and other health facilities. UNICEF should encourage the MoPH to collaborate with all actors (including the private sector) involved in making sure that they are a still and clear strategy that effectively ensure that vaccination is free for all children under five. Furthermore, the evaluation team suggests that UNICEF conducts research into wastage to better understand the extent to which it impacts on effectiveness and efficiency. |  |  |  |  | Disagree | UNICEF will be working on previous mentioned recommendation of drafting immunization policy in Lebanon. Also, most of the PHCs under MoPH are under private sector and very few are purely public; this creates a challenge in having the PHCs agree on free immunization. UNICEF will continue to support MoPH in monitoring PHCs and ensure their abidance of free vaccination service as per MoPH circular
1 | 1. Waste management of vaccination commodities in all EPI points ( 130 points of collection) |  | CS roving in close coordination with CS field offi | Genevieve Begkoyian | 2020-06-29 | Completed | (1) All PHCs are equipped with safe disposal boxes (2) UNICEF implementing partner (Arc en Ciel) collects all vaccine wastage from all EPI points and segregates them for safe disposal - this will continue till end of December 2019 (3) UNICEF engaged with Solutions for safe disposal of expired drugs in Lebanon and outside Lebanon
6 | Wastage of vaccines remains an ongoing concern that prohibits effective vaccine management at the national level. Health professionals at the local and district levels shared initiatives to reduce wastage. One option worth exploring further is the redistribution of non-used unexpired vaccines through the MoPH |  |  |  |  | Partially agree | Part of EVM is that wastage is better controlled. At the same time, MoPH have shared a decree with private clinics that they can access routine immunization as long as the vaccine is provided free of charge.
1 | Waste management of vaccination commodities in all EPI points ( 130 points of collection |  | Health officer | Fraah Mazloum | 2021-06-30 | On-going | Ongoing vaccine waste management from all EPI points through AEC (IP)
7 | No evidence was shared proving that efforts are made to verify reported vaccination needs and consider cost effectiveness when procuring vaccines and equipment. The first step to achieve some progress in that direction is to be made on the accuracy and transparency of MoPH data records. UNICEF shall work with the Ministry to support their efforts, drawing on the lessons learnt from the successful experience of other countries in the region that have put forth such reforms |  |  |  |  | Disagree | No evidence was shared proving that efforts are made to verify reported vaccination needs and consider cost effectiveness when procuring vaccines and equipment. The first step to achieve some progress in that direction is to be made on the accuracy and transparency of MoPH data records. UNICEF shall work with the Ministry to support their efforts, drawing on the lessons learnt from the successful experience of other countries in the region that have put forth such reforms
1 | 1.Continuous UNICEF support to the scale up of the EPI registry and MERA application, |  | CS Chief with MoPH HN officer central to support M | Farah Mazloum | 2021-06-30 | Ongoing | Ongoing scale up and enhancement of MERA
2 | 2.Capacity building of EPI network staff on quality data collection |  | Health Officer | Farah Mazloum | 2020-12-30 | Completed | 651 staff were trained on MERA (from dispensaries, PHCs and community outreach workers).
3 | 3.Equity analysis of Immunization |  | HN Officer | Genevieve Begkoyian | 2019-12-30 | Not Started | Will be part of EQUIST data anlysis - under AUB LTA - based on wealth of data generated from MERA. PS: Has been postponed due to economic crisis, and now because of COVID
8 | One major issue regarding the efficiency of the procurement of vaccines remains on the choice between single and multi-doses. Further investigation, both with the MoPH and UNICEF Supply Division, is required to better understand the procurement choices despite the awareness that wastage is an ongoing concern. Efforts needs to be made by UNICEF to collect and review spending, such as budgets allocated for vaccine procurement. UNICEF shall conduct a thorough needs-cost analysis to support their choices of procurement. |  |  |  |  | Agree | Underway in close collaboration with SD Copenhagen, Monitoring of stock and forecast already done on a monthly basis with MoPH
1 | Supply chain system strengthening and capacity building of warehouse management |  | Chief child survival Health officer | Genevieve Begkoyian Farah Mazloum | 2020-12-30 | Completed | EVM assessment training has been conducted with 66 participants including the central warehouse managers, PHC network participants and UNRWA to build up the whole capacity building throughout the vaccine supply chain system. Following the training they will be conducting a national assessment
9 | Building on UNICEF’s global experience, UNICEF Lebanon could work more closely with MoPH to develop lessons learned approaches to their practices, with the introduction of workshops or seminars, encouraging shared dialogue. Examples of topics to be discussed may include the following – best practices in other countries, data record keeping practices at national and local levels, monitoring tools and activities. The objective of such workshops is to ensure that the MoPH is aware and has the tools to introduce policies and practices that have been deemed successful to overcome challenges in other countries |  |  |  |  | Partially agree | The MoPH has by all partners, been participating in a most of global meetings this year, including SAGE in Geneva
1 | In collaboration with MENARO, seizing all opportunity for the MoPH participation in regional or global training/ workshop |  | Chief Child Survival Health officer | Genevieve Begkoyian Farah Mazloum | 2020-12-31 | Completed | (1) MoPH participated in EQUIST training in New Delhi - India (Q1 2019) (2) MoPH particpated in the Tunis Private / Public Immunization MENA landscape workshop
10 | Given the role played by the private sector in achieving the objectives of the EPI, UNICEF could encourage the MoPH and support it in better understanding the provision of immunisation services by the private sector, including vaccine safety issues (e.g., integrity of the cold chain), whom the sector serves, how services are paid for, its contribution to coverage, and its integration with monitoring and surveillance |  |  |  |  | Agree | Given the role played by the private sector in achieving the objectives of the EPI, UNICEF could encourage the MoPH and support it in better understanding the provision of immunisation services by the private sector, including vaccine safety issues (e.g., integrity of the cold chain), whom the sector serves, how services are paid for, its contribution to coverage, and its integration with monitoring and surveillance
1 | Supportive supervision in collaboration with PHC coordinator in the EPI network |  | HN Roving Officer Health officer | Genevieve Begkoyian Farah Mazloum | 2020-12-30 | Completed | (1) UNICEF advocated for decree for free vaccination at private sector (2) UNICEF supporting MoPH to equip private sector with MERA in order to have better reporting from private sector on immunization activities in Lebanon (3) UNICEF particpated in all EPI steering committee in close collaboration along with private sector to advocate on princliple of free access to quality vaccines across EPI netwrok both public and private (4) UNICEF supported MoPH in involvement of private sector in measles campaign. Private sector confirmed their engagement in MCV vaccination for all 6 months -11 months children in Lebanon Ongoing and will continue as a core activity to ensure quality vaccine system