# REQUEST FOR PROPOSAL FOR SERVICES (RFPS)

# ANNEX I – STATEMENT OF WORK	 AND TERMS OF REFERENCE

1.	INTRODUCTION OF THE SECTION

The Knowledge Management, Implementation Research, and Strategic Results Area Monitoring (KMIRS) Unit provides technical leadership to strengthen monitoring and evaluation, research, and knowledge management to ensure that intervention packages in maternal, neonatal, and child health are evidence-based and contribute to influencing equity-focused policy and practice.

The objectives of the KMIRS Unit are as follows:

- To improve monitoring, evaluation and documentation of health programs supported by UNICEF;

- To provide technical support for monitoring and evaluation and implementation research to the health section and UNICEF Regional and Country Office programs;

- To conduct and commission strategic analyses or reviews that provide scientifically based overviews of key maternal, neonatal, and child health strategies in order to guide policy and practice;

- To publish and disseminate new findings and innovations in maternal, neonatal, and child health throughout UNICEF and beyond;

- To work jointly with international research and monitoring and evaluation working groups to advance evidence for MNCH interventions and strategies.

2.	BACKGROUND INFORMATION

While progress toward reducing childhood mortality has been made globally, the rate of progress among low-income countries, particularly in sub-Saharan Africa, has been slow in comparison.  Millions of children in sub-Saharan Africa continue to die from preventable causes – primarily neonatal disorders, diarrhea, pneumonia and malaria – for which low cost, high impact interventions and effective delivery strategies exist.

The Catalytic Initiative to Save a Million Lives (CI) is “an international partnership with the goal of strengthening health systems to accelerate progress on the health-related Millennium Development Goals (MDGs)” .  To achieve this objective, the CI seeks to “strengthen health systems by delivering life-saving health and nutritional services to disadvantaged children and pregnant women to dramatically reduce child and maternal mortality” in Africa and Asia.

As part of the CI, the Canadian International Development Agency (CIDA), through its Master Arrangement with UNICEF 2003-2013, supports the UNICEF Integrated Health Systems Strengthening (IHSS) program.   In consultation with CIDA, UNICEF selected six countries in sub-Saharan Africa (Ethiopia, Ghana, Malawi, Mali, Mozambique and Niger) to target matched funding from CIDA (CND $105 million) and UNICEF for planning, implementation, monitoring and evaluation of the IHSS program in these countries starting between 2007 and 2013.  From this amount, funding was received by the UNICEF Country Offices in the targeted countries, the UNICEF West and Central Africa Regional Office (WCARO), the UNICEF Eastern and Southern Africa Regional Office, and UNICEF Headquarters office to strategically support the scaling-up of IHSS activities and specific support to those countries listed above.

In alignment with the health policies and planning of each government, the overall aim of the IHSS program is to increase coverage of a limited package of proven, high impact, and low cost maternal and child health interventions in the targeted countries.

The two strategic objectives of the IHSS program are to:

- Strengthen health systems (including planning, implementation and monitoring/health surveillance);

- Support and build capacity of government and/or civil society organizations to train, equip, deploy, and supervise front-line health workers to deliver a limited package of proven, high impact and low cost health interventions.

Following UNICEF’s  organizational structure, the IHSS program has been implemented through UNICEF’s support at three levels: (1) at the country level (where the program is guided by agreements between UNICEF, the government departments and identified NGOs in the key documents called Country Program Action Plans and the annual work plans) with UNICEF Health or Young Child Survival and Development Officers or focal points responsible for managing programme planning and implementation; (2) at the regional level, with Health Advisors or focal points for Health, playing a key role in providing technical support, capacity building, networking as well as monitoring quality at the country level and (3) at New York Headquarters, with the Child Health and Emergencies Response Unit in conjunction with the Knowledge Management and Implementation Research and Strategic Results Areas Monitoring Unit providing overall coordination, guidance and technical support to the Regions and Countries.

The IHSS program includes support for the following interventions for children under 5 years of age and pregnant women through CIDA and UNICEF funds:

- Treatment for diarrhoeal disease with oral rehydration salts and zinc; antibiotics for pneumonia and antimalarials for malaria;

- Long-lasting insecticide treated bednets (LLIN) (for both pregnant women and children under 5);

- Vitamin A supplementation (only to fill gaps not being met by current and imminent efforts);

- Intermittent preventative treatment of malaria in pregnant women;

- Immunizations (only in order to fill gaps not met by current or imminent efforts);

- Use of Nevirapine (or equally effective drug) for PMTCT (this includes costs for the delivery and purchase of the drug.  Ancillary costs such as voluntary counselling and testing will not be covered under this grant);

- Tetanus immunization for pregnant women;

- Breastfeeding promotion and counselling.

UNICEF funds for IHSS may be used for interventions other than those above (e.g. treatment of acute malnutrition).  For descriptions of the IHSS interventions in each country please see the Annual Reports to CIDA at the following website (insert external FTP site).

# MORE INFORMATION

# For more information about the IHSS program in the targeted countries please visit the following FTP web site (XXXX).

3.	PURPOSE AND OVERVIEW OF THE PROPOSED WORK

The external evaluation will encompass separate evaluations of the IHSS program in Ethiopia, Ghana, Malawi, Mali, Mozambique, Niger, and one overall evaluation of the IHSS program across these six countries.

The purpose of the external evaluation is two-fold:

- Accountability: to evaluate the effect of the IHSS program on coverage of a limited package of proven, high impact, and low cost maternal and child health interventions in each country and for the six countries as a whole.

- To enable Evidence-Based Decision-Making: to inform program and policy decisions in the targeted countries and regionally.

The objectives of the external evaluation are as follows:

- To assess the effect of the IHSS program on strengthening the health system as per the indicators outlined under INDICATORS FOR EVALUATION OBJECTIVES 1 & 2 in the Annex.

- To assess the effect of the IHSS program on capacity of government and/or civil society organizations to train, equip, deploy, and supervise front-line health workers to deliver a limited package of proven, high impact and low cost health interventions as per the indicators outlined under INDICATORS FOR EVALUATION OBJECTIVES 1 & 2 INDICATORS FOR OBJECTIVE in the Annex.

- To assess the effect of the IHSS program on coverage of select maternal and child health and nutrition interventions, particularly integrated Community Case Management (iCCM) of diarrhea, malaria and pneumonia, which were supported by the IHSS program (interventions are outlined under Background Information and indicators are outlined under INDICATORS FOR OBJECTIVE 3 in the Annex).

Based on the effect of the IHSS program on improvements in coverage of select maternal and child health interventions, the external evaluation will estimate and report the number of additional lives saved by the IHSS program using the Lives Saved Tool (LiST).  Estimations of the number of additional lives saved will be provided for the overall IHSS package of interventions and disaggregated by groups of interventions (i.e. integrated community case management) and by individual interventions.

The external evaluation is at the request of CIDA pursuant to the terms of the grant agreement of the IHSS program set forth in Schedule A of the Master Arrangement signed between CIDA and UNICEF on February 5, 2003.

The primary audiences of the final external evaluation are the governments of the countries implementing the IHSS program and CIDA as the main supporting partner.    Other audiences of the external evaluation include UNICEF and development partners.

# SCOPE AND FOCUS

The scope of the external evaluation is focused on estimating the plausible effect of the IHSS program on coverage of interventions funded by the IHSS program, and estimating the additional lives saved by the program using LiST.  The external evaluation will consider any interventions not funded by the IHSS program but necessary in order to execute the LiST estimation and construct a robust plausibility argument to be within the scope of the external evaluation.

Plausibility for this evaluation is defined as “apparently true or reasonable, winning assent, a plausible explanation”.   As defined by the OECD-DAC attribution represents “the extent to which an observed development effect can be attributed to a specific intervention or to the performance of one or more partners taking account of other interventions, (anticipated or unanticipated) confounding factors, or external shocks”.  In assessing plausibility of attribution, the external evaluation will attempt to “rule out external factors [factors outside of the program]…which might have caused the observed effects”.

The scope of the evaluation is limited to plausible attribution due to the presence of one or more the following conditions in each of the targeted countries:

- non-existence of true comparison areas due to the national scale of the program or differences between intervention areas and potential comparison areas on observed and unobserved characteristics (this is the case in all target countries); and

- the infeasibility of a randomized intervention/control design due to political and ethical considerations (e.g. Ghana, Malawi, Mali, Mozambique, Niger).

The exception to the above is Oromia region in Ethiopia where the Institute for International Programs (IIP) at Johns Hopkins University (JHU) is working with in-country partners to conduct a randomized intervention/comparison impact evaluation of the IHSS program at the request of CIDA.  The external evaluation (described in this TOR) will utilize the results and findings, as available, of the evaluation conducted by JHU IIP to inform its evaluation of the overall IHSS program in Ethiopia.

Geographically the scope of the external evaluation includes the following areas:

- Ethiopia – five of ten regions (Amhara, Benshangul, Oromia, SNNPR and Tigray)

- Ghana – the three northern regions and all districts therein;

- Malawi – hard to reach areas in ten districts (however similar programs are operating through the Government of Malawi in all 28 districts)

- Mali – five of eight regions ( Kayes, Koulikoro, Mopti, Sikasso, and Ségou)

- Mozambique – thirty-three districts in phase 1 and 144 districts in phase 2; and

- Niger – all regions of rural Niger (the program is national).

Temporally the scope of the external evaluation includes the period 2000-2007 (secular trend) prior to the start of the IHSS program, the period 2007 to 2010 known as Phase I of the program, and the period 2010 to March 2013 known as Phase II of the program.  The above time periods are generally accurate however UNICEF will provide the external evaluator with detailed timelines for each country.

In Malawi, the Johns Hopkins University Institute for International Programs (JHU IIP) is partnering with WHO and UNICEF to conduct an evaluation of MNCH programs in all 28 districts supported under a SWAp (of which the CIDA/UNICEF funded IHSS program in 10 districts is a part) using a district level “evaluation platform approach”.  The scope of the JHU IIP evaluation includes all 28 districts and does not focus on the 10 districts implementing the IHSS program.  For this external evaluation, the bidder will incorporate, as appropriate and available, the findings of the JHU IIP evaluation but the scope will focus on the 10 districts (and “hard to reach areas” therein) implementing the IHSS program.

# EVALUATION CRITERIA

The external evaluation will be guided by the OECD-DAC and UNICEF evaluation criteria.   A focus will be on relevance, effectiveness, efficiency (as cost-effectiveness), impact, and sustainability.  According to OECD/DAC definitions:

Relevance represents “The extent to which the aid activity is suited to the priorities and policies of the target group, recipient and donor.”

Effectiveness represents “A measure of the extent to which an aid activity attains its objectives.”

Impact is “The positive and negative changes produced by a development intervention, directly or indirectly, intended or unintended.  This involves the main impacts and effects resulting from the activity on the local social, economic, environmental and other development indicators.  The examination should be concerned with both intended and unintended results and must also include positive and negative impact of external factors, such as changes in terms of trade and financial conditions.”

Sustainability “is concerned with measuring whether the benefits of an activity are likely to continue after donor funding has been withdrawn.  Projects need to be environmentally as well as financially sustainable.”

# EVALUATION QUESTIONS

The external evaluation will answer questions within the evaluation’s scope and based on the framework of the OECD/DAC evaluation criteria.  The following section outlines key research questions.  The research questions may be refined by the external evaluator and UNICEF as necessary during the inception phase of the evaluation to better suit the purpose and objectives of the evaluation. Whether the research question is mandatory or optional based on content of the CIDA Grant Agreement is indicated in the parenthetical following the research question.  Indicators relevant to the research questions are listed in the parenthetical following each question and are arranged in the Annex according to their evaluation objective.  Some questions do not have indicators from the CIDA Grant Agreement but are relevant to the overall purpose of the evaluation, in which case the relevant indicator in the Annex is indicated in the parenthetical.  The external evaluator may propose modifications to the indicators below or additional indicators as relevant to the evaluation questions.

RELEVANCE

- To what extent were the objectives of the program valid for the target group, Government, and CIDA?  On what basis were the objectives set? (Optional)

- To what extent did the program’s objectives reflect a health systems strengthening approach, including:

  - alignment with the health policies, planning and health surveillance of the Government? (Mandatory. Question relevant to indicator 1.1.1, 1.1.2, 1.2.3, 1.2.4.14-1.2.4.15) and

  - training, equipping, deploying and supervising front-line health workers to deliver the selected high impact and low cost health interventions?  (Mandatory. Question relevant to indicators 1.1.3-1.1.8 and 1.2.4-1.2.4.24)

- To what extent did the program’s objectives include a focus on women’s participation and a gender equality approach? (Mandatory. Question relevant to indicator 1.2.2).

# EFFECTIVENESS

- To what extent were the objectives related to health system strengthening (including policies, planning and health surveillance) and training, equipment, deployment, and supervision of front-line health workers, and a focus on achieved? (Mandatory. Question relevant to indicators 1.1.1, 1.1.2, 1.2.3, 1.2.4.14-1.2.4.24).

- To what extent were the objectives related to women’s participation and gender-equality achieved? (Mandatory. Question relevant to indicator 1.2.2).

- To what extent did coverage of the selected high impact and low cost interventions in the target populations increase?  What additional coverage is plausibly attributable to the program? (Mandatory. Question relevant to indicators 1.3.2.5-1.3.2.14 and 1.3.2.17-1.3.2.29).

- What aspects of the IHSS program worked?  Why did these aspects work? (Mandatory).

- What aspects of the IHSS program did not work? Why did these aspects not work? (Mandatory).

- What were the major factors influencing the achievement or non-achievement of the IHSS program objectives? (Mandatory).

# IMPACT

- Was a reduction in child mortality (may be modeled) observed amongst target populations?  If so, could the reduction in child mortality (or some portion thereof and specify) be plausibly attributable to the program?  Based on plausible attribution of coverage, how many lives were saved by the program?  (Mandatory. Question relevant to indicators 1.3.2.15-1.3.2.16).

SUSTAINABILITY

- What is the likelihood that results/benefits continue after CIDA/UNICEF's involvement ends? (Optional but bidders are encouraged to answer).

  - Are committed financial and human resources sufficient to maintain benefits and results? (Optional but bidders are encouraged to answer).

  - Is the external environment conducive to maintenance of results? (Optional but bidders are encouraged to answer).

  - Are gender equality results likely to endure after CIDA/UNICEF involvement in the investment ends? (Optional but bidders are encouraged to answer).

# METHODOLOGICAL CONSIDERATIONS

# EVALUATION PHASES

The evaluation will occur in three phases: Inception Phase, Execution Phase, and Delivery Phase.

During the Inception Phase the external evaluator, in consultation with UNICEF, will fully develop the methodology to be employed during the rest of the evaluation.

During the Execution Phase, new data acquisition (context only, see below), analyses, and report writing will occur. Answers to evaluation questions 1-11 will emerge during this phase.

During the Delivery Phase, draft reports will be reviewed and finalized.

The evaluation calendar (section 5.0) offers more details.

# USE OF EXISTING INFORMATION SOURCES

# The following section offers guidance on existing data sources UNICEF will provide to the external evaluator.  Tables 1-6 in the Annex synthesize this information by country, including type of data, level of aggregation, and periodicity of data collection, who is collecting the data, and who is providing technical support.  Bidders should note that they will not be required to collect new data apart from contextual information (see section 2.4.2.2).  It is not a mandate to include any particular methodology or data source unless a specific requirement is mentioned.

As part of the technical proposal, bidders are directed to explain what portions of the evaluation objectives would be examined through analyses of the existing sources of data in addition to the contextual data they will collect as necessary, and the method(s) they expect to employ.  The proposal should explain the rationale for the proposed method(s), in the understanding that the actual method(s) will be developed consultatively with UNICEF during the inception period of the evaluation.

UNICEF will provide the following data (as available) for each country from existing sources during the inception phase to facilitate full development of the evaluation plan.  Where any of the data below is not available during the inception phase of the evaluation, UNICEF will attempt to provide such data to the external evaluator during the execution phase.

# PROGRAM DOCUMENTATION:

IHSS Program plans

- UNICEF Country Office (CO) IHSS Annual Workplans and Planning Budgets;

- UNICEF WCARO workplans and budgets related to IHSS;

- UNICEF HQ workplans and budgets related to IHSS; and

- Government planning/budget documents related to IHSS; and

- Government policy documents related to IHSS interventions.

Program reports and related documents

- UNICEF CO Annual Reports to CIDA on progress of IHSS

- UNICEF CO presentations on progress of IHSS

- UNICEF Country Program Documents

- UNICEF Consolidated Appeals Process documents

- UNICEF Mid-Term Reviews

- UNDAF reports; and

- Government Health Sector Development Plans;

- Government health policy documents; and

- Other documents as deemed necessary by UNICEF.

Program implementation of iCCM (indicators 1.1.3-1.1.8 and 1.2.4-1.2.4.13):

- Tables with these data from administrative systems (Health Management Information Systems) or parallel administrative systems reported on a quarterly basis; and

- Reports with tables showing these data from sample surveys of community health workers for at least one point in time near endline;

Utilization (indicators 1.3.2.5, 1.3.2.8, 1.3.2.10-1.3.2.10.1, 1.3.2.11-1.3.2.11.1 and 1.3.2.12-1.3.2.12.3):

- Tables with these data from HMIS or parallel administrative systems reported quarterly.

Quality of care of iCCM (indicators to be decided)

- Tables with data on quality of care based on a review of registers from a sample of community health workers in terms of concordance of signs and symptoms with treatment for at least one point in time near endline (for all countries except Ethiopia where this will be done only for Oromia region); and

- Tables with data on quality of care based on case observation of a sample of sick children treated by community health workers (Oromia Ethiopia only) for at least one point in time near endline.

CONTEXTUAL DATA

UNICEF will provide the following contextual data:

Documentation of contextual factors (program timelines, program activities, policy changes that would impact coverage or child health, nutrition and/or mortality rates; epidemics, humanitarian crises, socio-economic factors, demographics, health care access, cause of death profile (if possible), HIV prevalence, and partner mapping (mapping of programs similar to IHSS or ones that would potentially mediate the impact of the IHSS or impact the outcomes targeted by the HIS; the interventions they are providing, their geographic scope, scale in terms of inputs (if available)).

Unless otherwise noted in Tables 1-6 in the Annex, the external evaluation institute will verify the contextual data provided by UNICEF through key informant interviews with UNICEF and MOH staff.

COVERAGE, PREVALENCE OF UNDERNUTRITION AND UNDER-FIVE MORTALITY RATE (indicators 1.3.2.5.1, 1.3.2.6, 1.3.2.7, 1.3.2.9, 1.3.2.9.1, 1.3.2.10.2, 1.3.2.10.3, 1.3.2.11.2.3, 1.3.2.12.4-1.3.2.12.8, 1.3.2.13-1.3.2.29)

UNICEF will provide reports on analysis of trends in coverage, prevalence of undernutrition and under-five mortality rates, plus estimates of the number of lives saved using LiST  for Malawi (JHU-IIP evaluation platform report), Niger (UNICEF/JHU IIP report only up to 2010), Oromia, Ethiopia (JHU IIP impact evaluation report).  No trend analyses will be provided for Ghana, Mali, and Mozambique.

UNICEF will provide (pending approval from relevant MOH) the raw datasets from all available household surveys (DHS, MICS, and SMART) for the 6 countries for the period prior to the program until endline.  The external evaluator will use these data to update analyses (i.e. adding the 2012 DHS for Niger), review existing analyses (i.e. for Malawi and Oromia, Ethiopia) and conduct new analyses (e.g. for Ethiopia, Ghana, Mali and Mozambique).  For Malawi, particular focus will be on the ten districts implementing the IHSS through CIDA/UNICEF funds.

NEW INFORMATION SOURCES:  COUNTRY VISITS

Key informant interviews with UNICEF and MOH staff to collect information on contextual factors, policies, partner mapping (as per 2.3.1.2) and indicators 1.1.1, 1.1.2, 1.2.3, 1.2.4.14-1.2.4.24) (see Tables 1-6).

As part of the technical proposal, bidders are directed to explain what portions of the evaluation objectives would be examined during the key informant interviews, and the methods they expect to employ.  Country visits may be proposed but are not required.  Bidders may use teleconference, videoconference, and/or web-based technology to conduct key informant interviews.  The proposal should explain the rationale and procedures for the method(s) selected.

It can be assumed that Country Offices will assist with identifying key informants, arranging key informant interviews and country visits (if selected as a method), and gathering documentation etc.  It cannot be assumed that they will provide or absorb other costs (local researchers, travel etc.).

ANALYTIC SPECIFICITY

UNICEF is conscious that there are two types of questions posed within the questions sets:

- Analytic/Descriptive Questions: Successful responses involve well organized narratives which weigh the evidence in order to quantify and qualify the effect of IHSS on health systems strengthening, support to front-line health workers, coverage of interventions and, ultimately, lives saved.

- Normative Questions:  Successful responses require the application of explicit and defensible criteria for weighing the evidence in terms of what has worked or not, and why.    For all normative questions, the evaluators must be clear what is to be considered as a “good” standard and what is to be considered as a “poor” or “not met” standard.  Where possible, UNICEF is looking for good practice benchmarking that will form the basis of quality design and assessment efforts in future IHSS programming.

The technical proposals should present the organization’s familiarity with relevant evaluation methods, analytical procedures and norms used in prior evaluative work.

ETHICAL ISSUES

Conventional ethical guidelines are to be followed during the evaluation.  Specific reference is made to the UNEG guidelines, but good practices not covered there are also to be followed.  Any sensitive issues or concerns should be raised with the evaluation management team as soon as they are identified.

On two particular issues:

- The evaluation may have contact with children as informants or objects of study.  In all contacts with children, the UNICEF ethical guidelines regarding issues like confidentiality and not exposing the child to danger must be respected.

- No participant other than UNICEF staff may be compelled to cooperate with the evaluation.  UNICEF will direct staff to participate where needed.

4.	EXPECTED DELIVERABLES AND TIME LINE

INTERIM WORK PODUCTS

- Detailed work plans and timelines for each country evaluation and overall evaluation in MS Word©;

- Detailed protocols for evaluations in each country and overall evaluation in MS Word©;

  - Plans for collection of contextual data (key informant interviews)

  - Plans for assessment of quality of existing data (particularly household survey data on coverage, undernutrition and child mortality)

  - analysis/re-analysis of existing data (particularly household survey data on coverage, undernutrition and child mortality)

  - Plans for synthesis of existing data;

- Draft tools for key informant interviews MS Word©;

- Progress Reports (bi-weekly to start; may reduce to monthly after the inception report phase) MS Word©;

- Presentation materials for advisory committee meetings MS Word© and MS Powerpoint ©.

- Records of routines devised and executed for data collection, data processing, quality assessment, data analysis and other activities, if requested in MS Word© or other agreed upon format.

FINAL PRODUCTS:

- Inception Report (end of phase 1)

- Seven final reports (1 for each country and 1 overall summary) (Outline and details to be developed with the advisory committee)

- Accompanying visual material (if any) in final edited form.

- Update to the UNICEF Evaluation Database in the required format

- Assessment of the evaluation methodology, including a discussion of the limitations.

- Seven self-contained PowerPoint presentations (1 for each country and 1 summary) of up to 25 slides and complete speaking notes that summarizes the final report.

- One feedback workshop in New York with an expected duration of 1 day exclusive of preparation time.

# Other Responsibilities of the Institute/Consultant(s)

The consultants will provide their own computers.  On an as-needed basis, consultants will be granted access to UNICEF data bases and necessary software to utilize them.

The bidding firm will be expected to handle the following responsibilities during country visits:

# Accommodation, food, travel and appropriate insurance of the contractor’s workers, both international and local.  This includes life and health insurance, incentives, hazard pay.

# Transport and accommodation of government and/or NGO staff who are/were involved in program work and who will be resource persons to the study.

# Copying of information in hard copy or electronic form.

# Hiring and travel of local translators, interviewers, drivers, watchmen, etc.

# Renting of office space, computers, tape recorders, information technology, outside of what UNICEF will make available at sites where it has existing offices

Consultants will be covered by the usual terms and conditions for consultant with regards to security and evacuation in emergencies.  Benefits and arrangements such as insurance should be clarified for participants in the team (particularly in emergencies, consider hazard pay, war risk insurance).

# TIME LINE

# The contract is expected to be signed in mid May 2012. There will be three phases (inception, execution, and delivery).  The execution and delivery phases will have two sub-phases: one for Ethiopia, Ghana and Niger and one for Malawi, Mali, Mozambique, and the summary of the 6 countries.  Final deliverables for Ethiopia, Ghana and Niger must be received by April 1, 2013.  Final deliverables for Malawi, Mali, Mozambique, and the summary of the 6 countries must be received by December 2, 2013.  Earlier delivery while maintaining quality standards will be favourably considered in the technical assessment.

5.	KEY SKILLS, TECHNICAL BACKGROUND, AND EXPERIENCE REQUIRED

The institution should preferably be either a university or a research organization and should adequately demonstrate the availability of high calibre expert/s in the evaluation of large-scale child health programs in developing countries with an expressed specialization in the area of epidemiology, statistics, and demography. The institution should preferably provide consultant/s with:

- a Masters or Advanced Degree (Ph.D. desirable) in epidemiology, statistics, or demography;

- at least 10 years of progressively responsible professional work experience at national and international levels in conceptualizing, designing and implementing evaluations and/or research of large-scale child health programs in developing countries;

- proven publication record, preferably peer reviewed papers and journals;

- advanced knowledge of household survey methods and analyses thereof;

- demonstrated ability to produce high quality evaluation and/or analytical reports;

- familiarity with the Lives Saved Tool;

- familiarity with UNICEF’s work and the countries included in the evaluation;

- excellent Spoken and written fluency in English and French;

- proficiency in various MS Office © applications (Excel, Word and Powerpoint).

Institutions providing consultant/s that demonstrate diversity with regard to gender and other forms of difference will be preferred.

The presence of a conflict of interest may lead to a request to withdraw the proposed team member and identify a replacement.  Of special concern would be persons who had a leadership role in UNICEF or outside of UNICEF and that were forceful advocates for a particular approach to IHSS.  That said, former staff members will be entertained as team members (but not as team leader) provided they meet the other principal criteria.

6.	UNICEF RESPONSIBILITIES

An external evaluation steering committee comprised of UNICEF HQ staff (Health Section, Evaluation Office, Statistics and Monitoring Section), UNICEF Regional staff (ESARO – Research and Evidence Group, WCARO – PM&E Group), UNICEF Country Office focal points, and CIDA focal points will be responsible for the following:

- Selection and orientation of the evaluation team

- Liaison with the evaluation team

- Collection of relevant internal materials

- Facilitation of new data collection--e.g. admin support for arranging country visits and video/teleconferences

- Coordination of stakeholders

- Securing agreement of country and regional offices for field visits

- Review and acceptance of intermediate and final products

- Authorizing payment

Important note:  UNICEF may elect to designate a project manager for the evaluation.  The project manager may share or have direct accountability for some or all of the steering committee items.

UNICEF Country offices

- Designation of a focal point for support.

- Liaison with and introduction of evaluators to national counterparts and other partners

- Organization of administrative and logistical support to evaluation team, including accompanying them on trips.

- Provision of documents for review; being key informants

- Review of reports for factual errors and omissions

7.	DURATION: The work is planned to start [11 May, 2012] over the period of [11 months]. (All the dates below will be entered in the FLS, so please provide realistic dates, please see the reference note below of this document to calculate days/date)

The tentative schedule of the contractual process is as follows:

|  | Weeks |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contractual Process Stages | 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| Confirmation from service provider to participate |  |  |  |  |  |  |  |
| Questions and clarification from service provider |  |  |  |  |  |  |  |
| Q&A from UNICEF to be shared with all potential service provider |  |  |  |  |  |  |  |
| Technical and price proposals received |  |  |  |  |  |  |  |
| Technical and Price evaluation completed by a Technical Team |  |  |  |  |  |  |  |
| Contract Review Committee if the cost is $100,000 or up. |  |  |  |  |  |  |  |
| Anticipated Institutional/ Corporate Contracts Award Date |  |  |  |  |  |  |  |

| S.N. | Contractual Processes | Date |
| --- | --- | --- |
| 1 | Confirmation from service provider to participate | By one week from the date of RFP sent out. |
| 2 | Questions and clarification from service provider | Within two weeks, mostly by middle of the RFP submission period. |
| 3 | Q&A from UNICEF to be shared with all potential service provider | Within two days from the last day of Q&A by service provider. |
| 4 | Technical and price proposals received no later than 23:59 NY time | By three to four weeks depending on the complexity and cost of the RFPS. |
| 5 | Bid opening | Following day of the proposal submission day (no public opening) |
| 6 | Technical and Price evaluation completed by a Technical Team | Within one week from the date of bids opened. |
| 7 | Contract Review Committee if the cost is $100,000 or up. | Two weeks from the date of contract package submitted to CRC secretariat. |
| 8 | Anticipated Institutional/ Corporate Contracts Award Date | Depending on the CRC outcome, 2 business days after the CRC minutes signed. |
| 9 | Delivery of products | By end of the contract (to be suggested by the section) |

8.	EVALUATION OF THE PROPOSAL

In making the final decision, UNICEF considers both technical and financial aspects. The Evaluation Team first reviews the technical aspect of the offer followed by the review of the financial offer of the technically compliant vendors.

a. Technical Proposal:

The technical proposal should address all aspects and criteria outlined in this Request for Proposal. However, all these requirements represent a wish list from UNICEF. The bidders are free to suggest/ propose any other solution. UNICEF welcomes new ideas and innovative approaches.

No price information should be contained in the technical proposal.

The technical proposal should minimize repeating what is stated in the TOR and should emphasize the conceptual thinking and methods the organization expects to utilize.

There is no minimum or maximum length.  If in doubt, ensure sufficient detail.

Bidders may be asked to provide additional information.

Ensure that the level of effort to be committed by the different team members in each phase is visible within the technical proposal.  That same information with additional cost data should feature in the financial proposal.

Keep in mind that the following specific items must be present, in addition to whatever other approaches and methods proposed:

- Presentation of a work plan in three phases (inception, execution, and delivery).

- A discussion with adequate detail for analysis/reanalysis of existing data to address Objectives 1-2.

- A discussion in adequate detail of the proposed method(s) for synthesizing existing and new data (context) for making plausibility arguments to address Objective 3.

- Plans for country visit(s) to each country to conduct key informant interviews to learn about the program and context.  Key informant interviews may be conducted by teleconference, video or other method in lieu of country visits.

All other contents are at the discretion of the bidder, and within these four items there is significant flexibility in how they could be accomplished.

Sample Guide Texts:

The technical proposal must be organised to the following table of contents:

- Bidder’s Corporate Profile, see next section below.

- Bidder’s relevant expertise and experience relating to this consultancy, see next section below.

- Composition of the Bidders proposed team to carry out the work including a summary (maximum one-page) CV of each member.

- Course development including:

  - actions, outputs and proposed methodologies.

  - expected time inputs of Bidders proposed team.

  - list of expected activities/inputs from others if not covered elsewhere in this RFP document.

- Course delivery including:

  - actions, outputs and proposed methodologies.  To also include:

  - expected time inputs of Bidders proposed team.

  - list of expected activities/inputs from others if not covered elsewhere in this RFP document.

- Report, materials and resources provided at the end of the consultancy.

- Timeline of proposed actions. The Bidder is free to propose a time table to suit their methodology, as long as the proposal clearly explains the sequence of activities and achieves the key dates detailed in this RFP (see section 1.3 and Annex 1).

- Any other comments, commitments, etc. that the Bidder wishes to make.

| The Technical Proposals will be evaluated against the following: |  |  |
| --- | --- | --- |
| REF | CATEGORY | POINTS |
| TE1 | Experience of Company and Personnel to be assigned to this contract - Mandatory. Demonstrated: - Strong experience in, and knowledge of, evaluation in the context of large-scale child health programs in developing countries - Specific experience in designing, managing and documenting evaluations and assessments of large-scale child health programs in developing countries. - Composition, range and depth of experience of proposed team (CVs of team members will be analysed) - Understanding of the work of the UN, UNICEF, and CIDA. - Financial stability of the company. - Fluency in English and French. | 35 |
| TE2 | Experience of Company and Key Personnel to be assigned to this contract – Preferred. Demonstrated: - Experience in managing and conducting evaluations of large-scale child health programs in sub-Saharan African countries. - Proven and demonstrable experience in conducting advanced analyses of intervention coverage and mortality data household surveys (e.g. DHS and MICS), and triangulation with data from administrative sources and contextual data - Fluency in English, French, and Portuguese. | 10 |
| TE3 | Proposed Methodology and Approach – Mandatory. Demonstrated: - Detailed proposal with methodology and strategy for achieving the objectives and criteria set out in the call for proposals, guided by Section 3 (Purpose and Overview of the Proposed Work) of the RFP and Section 1 of the Annex. - Realistic and timed plan of action. | 25 |
| Total Technical |  | 70 |
| Only proposals which receive a minimum of 50 points will be considered further. |  |  |

b. Price Proposal

Bidders must submit a firm-fixed price bid.  The quotation will not subject to revision unless officially invited to re-submit by UNICEF.  The proposer will suggest a payment schedule for the Contract, linked to unambiguous Contract milestones. The currency of the proposal shall be in US Dollars. Invoicing will be in US Dollars.  Payment will be effected by bank transfer in US Dollars.  The price should be broken down for each component of the proposed work, based on an estimate of time taken which needs to be stated.

The budget should be presented in 3 categories: personnel costs, project costs, overhead costs. Sub-headings within the categories may be done at bidder’s discretion.

Personnel Costs to include: Classification (i.e. job title/function) and rates for team members; duration of work for each.  A separate table showing expected level of effort per team member, by project phase, is expected.  If it is proposed to hire local researchers or other affiliated institutions, the costs and level of effort must be specifically identifiable in the proposal.

Project Costs to include:  cost of travel, including subsistence allowances, travel by air, train, road, etc., telecommunication and miscellaneous expenses.  For bidding purposes, bidders will employ the following 6 destinations (Ethiopia, Ghana, Malawi, Mali, Mozambique, and Niger) for travel, local research etc. costs.

Overhead, general and administrative expenses, fee to include:  institutional overhead, fee/profit over and above overhead.  The Cost Proposal must include detailed item-wise quotations, based on the terms of reference and other relevant documents. Please note that travel costs and subsistence rates (lodging, food, local transport, and incidentals) will be based on the lower of the rates proposed by the bidder or the official and prevailing United Nations rates.  Bidders are encouraged to submit economical travel and subsistence costs.  If information on prevailing UN rates is required, UNICEF will provide this information upon request.

All prices/rates quoted must be exclusive of all taxes as UNICEF is a tax-exempt organisation.

The total amount of points allocated for the price component is 30. The maximum number of points will be allotted to the lowest price proposal that is opened and compared among those invited firms/institutions which obtain the threshold points in the evaluation of the technical component. All other price proposals will receive points in inverse proportion to the lowest price; e.g.:

Max. score for price proposal * Price of lowest priced proposal

Score for price proposal X = ---------------------------------------------------------------------------

Price of proposal X

The Price Proposals will be evaluated against the following:

| Ref | CATEGORY | POINTS |
| --- | --- | --- |
| 1 | Price Proposal – Mandatory. - Fees for providing the services laid out in this RFP. Detailed breakdown of the price proposal should be for each component of the proposed work and in line with the technical proposal. The Price Proposal must be organised in such a manner that it reflects the inputs shown in the technical proposal and distinguishes between: - Fixed Costs (professional fees, support services, insurance, travel and subsistence, and Grand sub-Total for Fixed Costs); - Estimate Reimbursable Costs (provide well defined and itemized details for all estimate costs that the Bidders consider being reimbursable and a Grand sub-Total for Estimate Reimbursable Costs). - Institutional overheads (Institutional overheads as a percentage of the above) - Grand Total Note: Any travel cost, if there would be any, should be budgeted according to UN Travel Standards as a ceiling. All prices/rates quoted must be exclusive of all taxes as UNICEF is a tax-exempt organization. | 25 |
| 2 | Price Schedule – Mandatory. - Proposed payment schedule. - If applicable/offered discount payment terms. | 5 |
| Total Price |  | 30 |
| Total Technical and Price |  | 100 |

9.	ADDITIONAL INFORMATION

The Institution must have juridical personality and need to present a copy of certificate of incorporation or an institutional registration with the relevant authorities in the place where the institution has its legal address before a contract is awarded.

Interested institutions should send their proposal by email to NYHQPGRFPS@UNICEF.ORG and indicate how your institution learned about this RFP (i.e. UNICEF website, DevEx, etc.).

The UNICEF reference 2012-xxxx and bidding company name reference must appear in the file name of all submitted electronic bidding documents. For example:

- 2012-xxxx-COMPANY-BidSummary.pdf

- 2012-xxxx -COMPANY-Technical Proposal.pdf

- 2012-xxxx -COMPANY-Price Proposal.doc

Important Note:  Companies who intend to submit a response to this RFPS are requested to initiate the registration process by logging on to www.ungm.org and to complete the full vendor registration process within 90 days.

Due to the high volume of communications, we will not issue confirmation as to receipt of RFPS.

_____________________________________________________

FOR INTERNAL USE ONLY: (this information will be entered in SAP and will not be provided to the vendors)

* Target Value/Maximum Budget - $ ____________________

# Annex

The indicators relevant to the key research questions, objectives, and purpose of the external evaluation are listed below according to the relevant evaluation objective and Grant Agreement.  Mandatory indicators are followed by “Grant Agreement” or “this indicator not included in Grant Agreement but is necessary” in parentheticals.  Optional indicators are indicated by “optional” in parentheticals.

# INDICATORS FOR EVALUATION OBJECTIVES 1 & 2

Note: Indicators in this section have/will be collected at baseline and at least one other time before the end of the program.

    - Indications that knowledge and experience sharing is occurring with UNICEF, partner country Ministry of Health and other donors and that this information is integrated into Program activities, where appropriate (Grant Agreement 2007).

    - Indications of regular meetings between UNICEF at country-level and MOH, MOF, Ministry of Women, if applicable (Grant Agreement 2007).

    - Information on equity of coverage of trained and deployed health workers at the community level (Grant Agreement 2007).

    - Ratio of health workers per 1000 population (Grant Agreement 2007) (Grant Agreement 2007).

      - Ratio of community health workers per 1,000 children under five (this indicator not included in Grant Agreement but is necessary).

    - Numbers of training sessions and number of persons trained. Data will be gender               disaggregated and disaggregated by new and augmented workers, where possible (Grant Agreement 2007).

    - Percentage of CHWs receiving quarterly supervision (Grant Agreement 2007).

    - Per capita health expenditure (Grant Agreement 2007).

    - Number of stockouts by commodity relevant to the interventions listed in Section 1.3, Annex 1 of the CIDA Grant Agreement (Grant Agreement 2007).

    - Cooperation agreement signed by country and UNICEF (Grant Agreement 2007).

    - Data indicating that women are involved in country-level Program design and that UNICEF is facilitating a focus on participation of women and gender-equality issues (Grant Agreement 2007).

    - Information indicating alignment of the UNICEF program with national health systems and the national plans, including health surveillance (Grant Agreement 2007).

    - Number of additional trained and deployed front-line workers (for the interventions in Section 3 Annex 1 of Grant Agreement, disaggregated by gender, facility health workers and CHWs; and particularly for ones trained in IMCI and iCCM) (Grant Agreement 2007).

      - Ratio of facility health workers trained in IMCI per 1,000 under five population (this indicator not included in Grant Agreement but is necessary).

      - Proportion of facility health workers trained in IMCI (this indicator not included in Grant Agreement but is necessary).

      - Ratio of community health workers trained in iCCM per 1,000 under five population (this indicator not included in Grant Agreement but is necessary).

      - Proportion of community health workers trained in iCCM (this indicator not included in Grant Agreement but is necessary).

      - Ratio of community health workers trained in iCCM and deployed (providing iCCM) per 1,000 under five population (this indicator not included in Grant Agreement but is necessary).

      - Percentage of community health workers trained in iCCM who have seen a sick child in the previous 7 days (optional).

      - Percentage of community health workers trained in iCCM who have seen a sick child in the previous 3 months (optional).

      - Proportion of health posts that received at least 1 supervisory contact in the previous 3 months during which registers and/or reports were reviewed (optional)

      - Proportion of health posts that received at least 1 supervisory contact in the previous 3 months where a sick child consultation was observed or the sick child register was reviewed (optional)

      - Proportion of community health workers (or CHW posts) with no stock-out of key iCCM drugs lasting longer than 7 days (consecutively) in the last 3 months (report for each iCCM drug separately) (this indicator not included in Grant Agreement but is necessary).

      - Proportion of community health workers (or CHW posts) with all essential iCCM drugs available on the day of assessment (this indicator not included in Grant Agreement but is necessary).

      - Proportion of cases in community health workers iCCM registers whose recorded signs and symptoms, results of diagnostic testing, classification(s), treatment(s) and/or referral were all consistent (optional).

      - Proportion of cases in facility-based IMCI registers whose recorded signs and symptoms, results of diagnostic testing, classification(s), treatment(s) and/or referral were all consistent (optional).

      - Existence of a National Health Strategy related to the IHSS Program, particularly iCCM

        - Existence of a National M&E Plan that includes IHSS indicators, particularly related to iCCM, and is this linked to the National Health Strategy.

      - Goals and objectives of the IHSS in line with the National Health Strategy and are they time bound and measurable.

      - Indicators for IHSS have clear definitions, data sources with baselines and targets.

        - Indicators were selected in collaboration with national/international M&E partners.

        - Indicator data is linked to the National M&E system.

      - Data from the IHSS Program is disseminated properly and sensitive data maintained confidential.

      - Has the IHSS Program allocated sufficient financial resources for M&E?

      - The MOH possess the resources, procedures, skills, and experiences necessary for M&E data management and reporting for the IHSS Program.

        - Feedback is provided to Sub-reporting Entities on the quality of their reporting and on IHSS Program performance.

      - The MOH provides sufficient oversight, guidance and support to Sub-reporting Entities.

        - Reports submitted on time, complete, and mistake free.

      - The data collection and reporting systems enable the reporting of valid, accurate and high-quality data on numbers of People reached through the activities of the IHSS Program.

      - The data collection and reporting systems enable the reporting of valid, accurate and high-quality data on numbers of Commodities Distributed (e.g. antimalarials, antibiotics, ORS and zinc) through the activities of the IHSS Program.

      - The data collection and reporting systems enable the reporting of valid, accurate and high-quality data on numbers of Individuals Trained through the activities of the IHSS Program.

      - The data collection and reporting systems enable the reporting of valid, accurate and high-quality data on numbers of Service Points/Facilities/Organizations Supported through the activities of the IHSS Program.

# INDICATORS FOR OBJECTIVE 3

Note: The indicators will be provided as trends over time (before the start and at the end of the program) for both intervention and comparator areas (where comparator areas are available).

      - Vitamin A supplementation ratio: Number of vitamin A doses distributed per 1,000 children under five (disaggregated by all sources and by CI specifically) (Grant Agreement 2007).

        - Proportion of children 6-59 months of age who received at least one high dose vitamin A supplement in the last 6 months (and at least 2 doses in the last 12 months) (this indicator not included in Grant Agreement but necessary).

      - Proportion of children 12-23 months of age who received measles vaccine (Grant Agreement 2007).

      - Proportion of children 12-23 months of age who received the third dose of DPT or Pentavalent vaccine (Grant Agreement 2007).

      - Number of LLLNs distributed (disaggregated by all sources and by CI specifically) (Grant Agreement 2007).

        - LLIN distribution ratio: Number of LLINs distributed per 1,000 children under 5 years of age (this indicator not included in Grant Agreement but necessary).

      - Proportion of children under 5 years of age in households with LLIN available sleeping under an insecticide treated net the previous night (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age in households with LLIN available sleeping under undamaged insecticide treated net the previous night (this indicator not included in Grant Agreement but necessary).

      - Number of antimalarials distributed to children under five (disaggregated by facility-based providers and community health workers) (Grant Agreement 2007).

        - Malaria treatment utilization ratio: number of antimalarial treatments for malaria among children under five provided per 1,000 children under five (disaggregated by facility-based staff and community health workers) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with fever in the last 2 weeks whose mothers/caregivers sought care (disaggregate by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with fever in the last 2 weeks who received appropriate treatment (as per national policy) (disaggregate by provider) (this indicator not included in Grant Agreement but necessary).

      - Number of treatments of appropriate antibiotics (as per national policy) distributed to children under five (disaggregated by facility-based providers and CHWs) (Grant Agreement 2007).

        - Antibiotic treatment utilization ratio: Number of treatments of appropriate antibiotics (as per national policy) for ARI among children under five provided per 1,000 children under five (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with ARI symptoms in the last 2 weeks whose mothers/caregivers sought care (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with ARI symptoms in the last 2 weeks who received appropriate treatment  (as per national policy) (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

      - Number of ORS packets distributed (disaggregated by facility-based providers and community health workers) (Grant Agreement 2007).

        - Diarrhoea treatment utilization ratio: Number of treatments of ORS for diarrhoea among children under five provided per 1,000 children under five (disaggregated by facility-based staff and community health workers) (this indicator not included in Grant Agreement but necessary).

        - Diarrhoea treatment utilization ratio: Number of treatments of Zinc for diarrhoea among children under five provided per 1,000 children under five (disaggregated by facility-based staff and community health workers). (This indicator not included in Grant Agreement but necessary).

        - Diarrhoea treatment utilization ratio: Number of treatments of ORS and Zinc for diarrhoea among children under five provided per 1,000 children under five (disaggregated by facility-based staff and community health workers) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with diarrhoea in the last 2 weeks whose caregiver sought care (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with diarrhoea in the last 2 weeks who received ORS (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with diarrhoea in the last 2 weeks who received Zinc (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with diarrhoea in the last 2 weeks who received ORS and Zinc (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

        - Proportion of children under 5 years of age with diarrhoea in the last 2 weeks who received ORS and Zinc plus continued feeding   (disaggregated by provider) (this indicator not included in Grant Agreement but necessary).

      - Proportion pregnant women receiving IPT for malaria (at least two doses of SP) during their last pregnancy (Grant Agreement 2007).

      - Proportion of newborns protected against tetanus (Grant Agreement 2007).

      - U5 mortality rates based on most recent interagency joint estimates of underfive mortality (Interagency Child Mortality Estimation Group), DHS/MICS assessment (Grant Agreement 2007).

      - Numbers of lives saved (based on coverage using the Lives Saved Tool) (Grant Agreement 2007).

      - Proportion of women currently married or in union aged 15-49 years of age who are using (or whose partner is using) a contraceptive method (either modern or traditional) (this indicator not included in Grant Agreement but necessary).

      - Proportion of women that are currently married or in union 15-49 years of age that have an unmet need for contraception (this indicator not included in Grant Agreement but necessary).

      - Proportion of women who were attended at least once during pregnancy by skilled health personnel for reasons related to the pregnancy in the X years prior to the survey (this indicator not included in Grant Agreement but necessary).

      - Proportion of women who were attended at least 4 times during pregnancy by any provider (skilled or unskilled) for reasons related to the pregnancy in the X years prior to the survey (this indicator not included in Grant Agreement but necessary).

      - Proportion of births attended by skilled health personnel (doctor, nurse, midwife, auxiliary midwife) (this indicator not included in Grant Agreement but necessary).

      - Proportion % of births attended by semi-skilled health personnel (community health workers and TBAs trained in uncomplicated deliveries) (this indicator not included in Grant Agreement but necessary).

      - Proportion of newborns put to the breast within one hour of birth (this indicator not included in Grant Agreement but necessary).

      - Proportion of infants aged 0-5 months of age who are exclusively breastfed (this indicator not included in Grant Agreement but necessary).

      - Proportion of infants aged 6-8 months of age who breastfed and receive complementary food (this indicator not included in Grant Agreement but necessary).

      - Proportion of mothers who received postnatal care visit within two days of childbirth (this indicator not included in Grant Agreement but necessary).

      - Proportion of babies who received a postnatal care visit within two days of birth (this indicator not included in Grant Agreement but necessary).

      - Proportion of the population using improved drinking water sources (this indicator not included in Grant Agreement but necessary).

      - Proportion of the population using improved sanitation facilities (this indicator not included in Grant Agreement but necessary).

| TABLE 1. ETHIOPIA: EXISTING DATA FOR THE EXTERNAL EVALUATION OF THE IHSS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead Data Collector: | MOH/UNICEF/JHU IIP | UNICEF | NSO | NSO | NSO |
| Technical Assistance: | UNICEF/JHU IIP | UNICEF | JHU IIP(Oromia/Tigray) External Evaluator | JHU IIP (Oromia/Tigray) External Evaluator | JHU IIP(Oromia/Tigray) External Evaluator |
| Data Type and Source: | Program plans and reports: UNICEF – IHSS Annual Workplans/budgets, Annual Reports to CIDA and CPD/MTR/UNDAF iCCM Implementation Strength: MOH/UNICEF – Parallel HMIS; JHU IIP – Sample survey of CHWs (Oromia and Tigray) iCCM Utilization: MOH/UNICEF – Parallel HMIS; JHU IIP – Extracted from registers of CHWs and facilities (Oromia and Tigray) Quality of Care (iCCM) in Oromia and Tigray: JHU IIP – Sample CHWs for case observation, register review and case scenarios to CHWs | Context: External Evaluator – Key informant interviews and meetings with UNICEF staff UNICEF – Timeline of program activities, partner mapping, and tables with contextual data on rainfall patterns, altitude, epidemics and humanitarian crises, socio-economic factors, demographics, health care access, user fees, cause of death profile (if possible), HIV prevalence JHU IIP – Context documentation/ partner maps in Oromia and Tigray | Coverage: External Evaluator – Re-analysis of trends in coverage from household surveys. JHU IIP – Re-analysis of trends in coverage from household surveys in Oromia and Tigray Baseline trend: DHS 2000, DHS 2005 Endline: DHS 2011 | Undernutrition: External Evaluator – Re-analysis of trends in undernutrition from household surveys JHU IIP – Analysis of trends in undernutrition from household surveys in Oromia and Tigray Baseline trend: DHS 2000, DHS 2005 Endline: DHS 2011 | U5 Mortality: External Evaluator – Analysis of trends in U5MR and application of LiST based on coverage and undernutrition. JHU IIP – Impact evaluation in Oromia and Tigray (including trends in U5MR) Baseline trend: DHS 2000, DHS 2005 Endline: DHS 2011 |
| Level aggregation: | MOH – HMIS at national, regional, zonal, woreda JHU IIP – Surveys of CHWs in comparison woredas of two zones in Oromia and Tigray (CHWs providing iCCM for diarrhea and malaria) versus intervention woredas (CHWs providing iCCM for diarrhea, malaria and pneumonia) | UNICEF – Region JHU IIP – Oromia and Tigray (intervention and comparison areas) | External Evaluator – National (wealth quintiles, maternal education, sex of the child, urban rural), and region JHU IIP – Oromia and Tigray (intervention and comparison areas) | External Evaluator – National (wealth quintiles, maternal education, sex of the child, urban rural), and region JHU IIP – Oromia and Tigray (intervention and comparison areas) | External Evaluator – National (wealth quintiles, maternal education, sex of the child, urban rural), and region JHU IIP – Oromia and Tigray (intervention and comparison areas); Cause of death (national) |
| How it will be provided to the external evaluator: | MOH/UNICEF – Tables with data for implementation strength and utilization; JHU IIP – impact report for Oromia and Tigray (by November 2012) | UNICEF – Context (by June 2012); JHU IIP – impact report for Oromia and Tigray (by November 2012) | NSO – Raw data files JHU IIP – impact report for Oromia and Tigray (by November 2012) | NSO – Raw data files JHU IIP – impact report for Oromia and Tigray (by November 2012) | NSO – Raw data files JHU IIP – impact report for Oromia and Tigray (by November 2012) |

| TABLE 2. GHANA: EXISTING DATA FOR THE EXTERNAL EVALUATION OF THE IHSS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead Data Collector: | MOH/UNICEF | UNICEF | NSO | NSO | NSO |
| Technical Assistance: | UNICEF | UNICEF | External Evaluator | External Evaluator | External Evaluator |
| Data Type and Source: | Program plans and reports: UNICEF – IHSS Annual Workplans/budgets, Annual Reports to CIDA and CPD/MTR/UNDAF iCCM Implementation Strength: MOH – HMIS; UNICEF – Sample survey of CHWs (iCCM) as part of supplementary MICS in 2012 iCCM Utilization: MOH – HMIS; UNICEF – Extracted from registers of CHWs (iCCM) as part of supplementary MICS in 2012 Quality of Care: UNICEF – Register review of a sample of CHWs (iCCM) as part of supplementary MICS in 2012 | Context: External Evaluator – Context documentation through key informant interviews and meetings with UNICEF staff UNICEF – Timeline of program activities, partner mapping, and tables with contextual data on rainfall patterns, altitude, epidemics and humanitarian crises, socio-economic factors, demographics, health care access, user fees, cause of death profile (if possible), HIV prevalence | Coverage: External Evaluator – Analysis of trends in coverage form household surveys. Baseline trend: DHS 2003, Supplementary MICS 2007, DHS 2008 Endline: Supplementary MICS in 2012 | Undernutrition: External Evaluator – Analysis of trends in undernutrition from household surveys. Baseline trend: DHS 2003, Supplementary MICS 2007, DHS 2008 Endline: Supplementary MICS in 2012 | U5 Mortality: External Evaluator – Analysis of trends in U5MR and application of LiST based on coverage and undernutrition. Baseline trend: DHS 2003, Supplementary MICS 2007, DHS 2008 Endline: Supplementary MICS in 2012 |
| Level aggregation: | 3 northern regions and at district level therein | 3 northern regions and districts therein | Regional level (for DHS 2003 and DHS 2008; District level in the 3 northern regions for Supplementary MICS 2007 and Supplementary MICS in 2012 | Regional level for DHS 2003 and DHS 2008; District level in the 3 northern regions for MICS 2007 and Supplementary MICS in 2012 | Regional |
| How it will be provided to the external evaluator: | UNICEF – tables with data for implementation strength and utilization (by November 2012) | UNICEF – context files (by June 2012) | NSO – raw data files (by November 2012) | NSO – raw data files(by November 2012) | NSO – raw data files (by November 2012) |

| TABLE 3. MALAWI: EXISTING DATA FOR THE EXTERNAL EVALUATION OF THE IHSS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead Data Collector: | MOH/UNICEF/JHU IIP | UNICEF/JHU IIP | NSO | NSO | NSO |
| Technical Assistance: | UNICEF/JHU IIP | UNICEF/JHU IIP | JHU IIP | JHU IIP | JHU IIP |
| Data Type and Source: | Program plans and reports: UNICEF – IHSS Annual Workplans/budgets, Annual Reports to CIDA and CPD/MTR/UNDAF iCCM Implementation Strength: MOH/UNICEF – Parallel HMIS in all districts; JHU IIP – Sample survey of CHWs in all districts iCCM Utilization: MOH/UNICEF – Parallel HMIS in all districts; JHU IIP – Sample survey of CHWs in all districts Quality of Care (iCCM): JHU IIP – Review of registers during sample survey CHWs | Context: External Evaluator – Context documentation through key informant interviews and meetings with UNICEF staff UNICEF – Timeline of program activities, partner mapping, and tables with contextual data on rainfall patterns, altitude, epidemics and humanitarian crises, socio-economic factors, demographics, health care access, user fees, cause of death profile (if possible), HIV prevalence | Coverage: JHU IIP– Analysis of trends in coverage from household surveys as part of evaluation platform. Baseline: DHS 2000, DHS 2004 Midline: DHS 2010, DHS Malaria Indicator Survey 2012 Endline: MICS 2013 | Undernutrition: JHU IIP – Analysis of trends in undernutrition from household surveys as part of evaluation platform. Baseline: DHS 2000, DHS 2004 Midline: DHS 2010, DHS Malaria Indicator Survey 2012 Endline: MICS 2013 | U5 Mortality: JHU IIP – Analysis of trends in U5MR and application of LiST based on coverage and undernutrition as part of evaluation platform. Baseline: DHS 2000, DHS 2004 Midline: DHS 2010, DHS Malaria Indicator Survey 2012 Endline: MICS 2013 |
| Level aggregation: | MOH/UNICEF – HMIS at national, district JHU IIP – Surveys of CHWs at national and district | UNICEF – National, district and 10 hard to reach areas (IHSS focus areas) as available | JHU IIP – National (wealth quintiles, maternal education, sex of the child, urban rural), district, and groups of districts based on implementation strength (platform approach) | JHU IIP – National (wealth quintiles, maternal education, sex of the child, urban rural), district, and groups of districts based on implementation strength (platform approach) | JHU IIP – National (wealth quintiles, maternal education, sex of the child, urban rural), and groups of districts based on implementation strength (platform approach) |
| How it will be provided to the external evaluator: | UNICEF – tables with data for implementation strength and utilization (by November 2012); JHU IIP – report (by November 2012) *Note External Evaluation will focus on 10 districts implementing IHSS | UNICEF – context files (by June 2012) *Note External Evaluation will focus on 10 districts implementing IHSS | JHU IPP evaluation platform report (by November 2012). *Note External Evaluation will focus on 10 districts implementing IHSS | JHU IIP evaluation platform report (by November 2012) *Note External Evaluation will focus on 10 districts implementing IHSS | JHU IIP evaluation platform report (by November 2012) *Note External Evaluation will focus on 10 districts implementing IHSS |

| TABLE 4. MALI: EXISTING DATA FOR THE EXTERNAL EVALUATION OF THE IHSS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead Data Collector: | MOH/UNICEF | UNICEF/JHU IIP | NSO | NSO | NSO |
| Technical Assistance: | UNICEF | UNICEF/JHU IIP | External Evaluator | External Evaluator | External Evaluator |
| Data Type and Source: | Program plans and reports: UNICEF – IHSS Annual Workplans/budgets, Annual Reports to CIDA and CPD/MTR/UNDAF iCCM Implementation Strength: MOH – HMIS UNICEF – Survey of CHWs in 6 districts (2 districts of Kayes, 4 districts of Sikasso – 2 early implementers and 2 late implementers) iCCM Utilization: MOH – HMIS UNICEF – Extraction from registers during survey of CHWs Quality of Care (iCCM): UNICEF – Review of registers during sample survey CHWs | Context: External Evaluator – Context documentation through key informant interviews and meetings with UNICEF staff UNICEF – Timeline of program activities, partner mapping, and tables with contextual data on rainfall patterns, altitude, epidemics and humanitarian crises, socio-economic factors, demographics, health care access, user fees, cause of death profile (if possible), HIV prevalence | Coverage: External Evaluator – Analysis of trends in coverage from household surveys. Baseline: DHS 2001, DHS 2006, MICS 2010 Endline: DHS 2013 | Undernutrition: External Evaluator – Analysis of trends in undernutrition from household surveys. Baseline: DHS 2001, DHS 2006, MICS 2010 Endline: DHS 2013 | U5 Mortality: External Evaluator – Analysis of trends in U5MR and application of LiST based on coverage and undernutrition. Baseline: DHS 2001, DHS 2006, MICS 2010 Endline: DHS 2013 |
| Level aggregation: | MOH – HMIS at national, regional, district UNICEF – Surveys of CHWs in 6 districts (2 districts of Kayes, 4 districts of Sikasso – 2 early implementers and 2 late implementers) | UNICEF – National, regional, district (in the 6 districts conducting CHW survey) | National (wealth quintiles, maternal education, sex of the child, urban rural), and region | National (wealth quintiles, maternal education, sex of the child, urban rural), and region | National (wealth quintiles, maternal education, sex of the child, urban rural), and region |
| How it will be provided to the external evaluator: | UNICEF – Tables with data for implementation strength and utilization (by November 2012); | UNICEF – Context files (by June 2012) | NSO – Raw data (by November 2012) except for 2013 DHS (Sept 2013) | NSO – Raw data (by November 2012) except for 2013 DHS (Sept 2013) | NSO – Raw data (by November 2012) except for 2013 DHS (Sept 2013) |

| TABLE 5. MOZAMBIQUE: EXISTING DATA FOR THE EXTERNAL EVALUATION OF THE IHSS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead Data Collector: | MOH/UNICEF | UNICEF/JHU IIP | NSO | NSO | NSO |
| Technical Assistance: | UNICEF | UNICEF/JHU IIP | External Evaluator | External Evaluator | External Evaluator |
| Data Type and Source: | Program plans and reports: UNICEF – IHSS Annual Workplans/budgets, Annual Reports to CIDA and CPD/MTR/UNDAF iCCM Implementation Strength: MOH – HMIS UNICEF – Survey of CHWs iCCM Utilization: MOH – HMIS UNICEF – Extraction from registers during survey of CHWs Quality of Care (iCCM): UNICEF – Review of registers during sample survey CHWs and interviews with caregivers | Context: External Evaluator – Context documentation through key informant interviews and meetings with UNICEF staff UNICEF – Timeline of program activities, partner mapping, and tables with contextual data on rainfall patterns, altitude, epidemics and humanitarian crises, socio-economic factors, demographics, health care access, user fees, cause of death profile (if possible), HIV prevalence | Coverage: External Evaluator – Analysis of trends in coverage from household surveys. Baseline: DHS 2003, MICS 2008, DHS 2011 Endline: Coverage Survey 2013 | Undernutrition: External Evaluator – Analysis of trends in undernutrition from household surveys. Baseline: DHS 2003, MICS 2008, DHS 2011 Endline: Coverage Survey 2013 | U5 Mortality: External Evaluator – Analysis of trends in U5MR and application of LiST based on coverage and undernutrition. Baseline: DHS 2003, MICS 2008, DHS 2011 Endline: Coverage Survey 2013 |
| Level aggregation: | MOH – HMIS at national, regional, district UNICEF – Surveys of CHWs at national, regional, district | UNICEF – National, regional, district | National (wealth quintiles, maternal education, sex of the child, urban rural), and province | National (wealth quintiles, maternal education, sex of the child, urban rural), and province | National (wealth quintiles, maternal education, sex of the child, urban rural), and province |
| How it will be provided to the external evaluator: | UNICEF – Tables with data for implementation strength and utilization (by November 2012); | UNICEF – Context files (by June 2012) | NSO – Raw data (by November 2012) except for 2013 DHS (Sept 2013) | NSO – Raw data (by November 2012) except for 2013 DHS (Sept 2013) | NSO – Raw data (by November 2012) except for 2013 DHS (Sept 2013) |

| TABLE 6. NIGER: EXISTING DATA FOR THE EXTERNAL EVALUATION OF THE IHSS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead Data Collector: | MOH/UNICEF | UNICEF | INS | INS | INS |
| Technical Assistance: | UNICEF | JHU-IIP | UNICEF/JHU-IIP | UNICEF/JHU-IIP | UNICEF/JHU-IIP |
| Data Type and Source: | Program plans and reports: UNICEF – IHSS Annual Workplans/budgets, Annual Reports to CIDA and CPD/MTR/UNDAF iCCM Implementation Strength: MOHP – HMIS; UNICEF – Sample survey of CHWs and facilities iCCM Utilization: MOH – HMIS; UNICEF – Extracted from registers of CHWs and facilities Quality of Care: UNICEF – Register review of a sample of CHWs (iCCM) and facilities (IMCI) | Context: External Evaluator – Context documentation through key informant interviews and meetings with UNICEF staff UNICEF/JHU IIP– Timeline of program activities, partner mapping, and tables with contextual data on rainfall patterns, altitude, epidemics and humanitarian crises, socio-economic factors, demographics, health care access, user fees, cause of death profile (if possible), HIV prevalence | Coverage: INS/JHU IIP – Re-analysis of trends in coverage form household surveys. Baseline trend: DHS 1993, DHS 1998, sub-National 2000; SMART 2005 and DHS 2006 Middle trend: SMART 2006, 2007, 2008, 2009 & Endline: Child Mortality Survey 2010* (*External evaluator will update with DHS 2012) | Undernutrition: INS/JHU IIP – Re-analysis of trends in undernutrition from household surveys. Baseline trend: DHS 1993, DHS 1998, sub-National 2000, SMART 2005 and DHS 2006 Middle trend: SMART 2006, 2007, 2008, 2009 Endline: Child Mortality Survey 2010* (*External evaluator will update with DHS 2012) | U5 Mortality: HIS/JHU IIP – Re-analysis of trends in U5MR since 2000 (JHU working with INS) using DHS 2006, Child Mortality Survey 2010* INS/JHU IIP – Cause of death study among U5s using verbal autopsies (*External evaluator will update with DHS 2012) |
| Level aggregation: | HMIS at national, regional and district; Sample survey of CHWs and facilities at regional and national | Region and (district where relevant) | National (wealth quintiles, maternal education, sex of the child, urban rural and possibly by groups of districts according to strength of implementation) and regional | National (wealth quintiles, maternal education, sex of the child, urban rural and possibly by groups of districts according to strength of implementation), and regional | National (wealth quintiles, maternal education, sex of the child, urban rural and possibly by groups of districts according to strength of implementation) and regional Cause of death (national) |
| How it will be provided to the external evaluator: | UNICEF to provide tables with data for implementation strength and utilization (by November 2012) | UNICEF/JHU IIP report on context (by June 2012) mapping (November | UNICEF/JHU IIP to provide report on trends from 1992 through 2010 and LiST applications (by November 2012) | UNCIEF/JHU IIP to provide report on trends from 1992 through 2010 and LiST applications (by November 2012) | UNICEF/JHU IIP to provide report on trends 2000 to 2010 (by November 2012); Report on cause of death study (prelim May/June 2012 and full report end-2012) |

# References

UN Interagency Group for Child Mortality Estimation. Levels and Trends in Child Mortality. Report 2011. UNICEF, 2011.

Jones G, Steketee R, Black R, Bhutta Z, Morris S and the Bellagio Child Survival Study Group. 2003. How many child deaths can we prevent this year? The Lancet, vol 362: 65-71.

Canadian International Development Agency. The Catalytic Initiative to Save a Million Lives. http://www.acdi-cida.gc.ca/acdi-cida/acdi-cida.nsf/eng/NAD-1249841-JLG (last accessed August 28, 2011).

New Webster’s Dictionary and Thesaurus of the English Language. Danbury, CT. Lexicon

Publications, 1992.

OECD DAC Criteria. http://www.oecd.org/document/22/0,2340,en_2649_34435_2086550_1_1_1_1,00.html (last accessed February 17, 2012).

Habicht JP, Victora CG, Vaughan JP. Evaluation designs for adequacy, plausibility and probability of public health programme performance and impact. International Journal of Epidemiology

1999;28:10-18.

OECD. The DAC Principles for the Evaluation of Development Assistance, OECD (1991).

OECD. Glossary of Terms Used in Evaluation, in 'Methods and Procedures in Aid Evaluation', OECD (1986)

OECD. Glossary of Evaluation and Results Based Management (RBM) Terms, OECD (2000).

For more information on LiST please visit: http://www.jhsph.edu/dept/ih/IIP/list/.

See “UNICEF Evaluation Report Standards”  http://www.unicef.org/evaldatabase/index.html

The proposer shall provide a minimum of three (3) references to clients for whom the proposer has carried out similar scope of project.  UNICEF may contact references for feedback on consultants / services provided by your firm to support similar projects.  Include: Name and description of client company/organisation; Names of senior individuals in the client companies who were involved in the  Project (referred to) who are knowledgeable; Scope and scale of  Projects; Services provided to client.