UNICEF’s response to the South Sudan Humanitarian Crisis (2016-2018)

Part 2: Emergency Education, Child Protection & related issues

Inception Report

Final version: 15th February 2019

Table of Contents

1.	Introduction	3

2.	Context: the South Sudan crisis and UNICEF’s response	4

2.1	The South Sudan crisis	4

2.2	UNICEF and the wider response to the crisis	8

3.	Evaluation purpose, scope and approach	13

3.1	Purpose and scope	13

3.2	Evaluation approach	14

4.	Methodology and guiding questions	15

5.	Proposed structure for the Evaluation Report	18

6.	Evaluation and field mission schedules	20

Annex A	Terms of Reference	25

Annex B	Evaluation matrix	26

Annex C	Field interviews and focus groups: protocols & questions	31

Annex D	Proposed field-mission activities	35

Annex E	Problem statements & implied theories of change	38

# 1.	Introduction

1.1	The evaluation of UNICEF’s L3 response to the crisis in South Sudan in the period 2016-2018 was commissioned by the UNICEF Evaluation Office (EO) in New York. It is being conducted in two parts. Part One, completed in 2018, focused mainly on the child survival aspects (WASH, Health and Nutrition) of UNICEF’s response. This second part of the evaluation, to be undertaken mainly in 2019, will focus on the crisis-related Child Protection and Education components of the response, along with a number of cross-cutting issues. A synthesis report, combining findings from the two parts with some overarching analysis, will be produced once the second part of the evaluation is substantially completed.

The terms of reference for this Part Two of the evaluation are included in the Annex. This Inception Report sets out the evaluation team’s interpretation of the terms of reference and the proposed approach for the evaluation, including its scope, guiding questions and areas of focus. This approach is based on consultations held during an inception mission to Juba in November 2018, along with a preliminary review of data and documentation. For the sake of consistency, the approach is essentially similar to that adopted for Part One.

1.2	The evaluation team is led by James Darcy, an independent consultant, who was the team leader for Part One of the evaluation. He is joined by Francesca Ballarin, an independent specialist in child protection in emergencies, who is also experienced in education in emergencies; and by Sophie Busi, an independent consultant originally from South Sudan, whose particular focus will be on situation and programme monitoring, as well as on community engagement and local partnerships. A specialist in education in emergencies, Rui da Silva, joins the team from January 2019. Volker Huls, who was part of the Part One team, will also support Part Two remotely with document collation and data analysis.

James Darcy, Francesca Ballarin and Sophie Busi were joined on the inception mission by Jane Mwangi from the Evaluation Office. While not part of the evaluation team, Jane will continue to provide support and oversight to the evaluation process from New York.

1.3	For the more substantive fact finding and field work component of the evaluation, the team will undertake a mission to South Sudan in February/March 2019. They will review the relevant components of the country programme for the period January 2016 to December 2018, conducting internal and external consultations in Juba and a number of field locations. International team members will also visit the Regional Office in Nairobi to discuss the evaluation with UNICEF regional staff. A visit is planned to Geneva to consult the relevant global Clusters; and a writing workshop will be held, following which a draft evaluation report will be produced for review by the reference group for the evaluation by the end of April 2019. As in Part One, a workshop to discuss the draft findings and recommendations will be held in Juba (date to be decided), following which a revised draft will be produced for wider consultation. A final evaluation report will be produced by July 2019. See section 6 below for full schedule.

1.4	This Part Two evaluation overlaps to some degree with other evaluation and learning processes being conducted by the SSCO. In particular, an evaluation of the Back to Learning initiative is being conducted in parallel with the present evaluation. This evaluation differs from the BTL evaluation in some important respects. First, it is concerned mainly with UNICEF’s programmatic and coordination role in ‘emergency’ education in unstable and conflict-affected areas of the country. It is not looking at educational outcomes, but at UNICEF’s contribution to increasing access to (mainly primary) education and ensuring the quality of that education, in camps and unstable (conflict-affected) areas; together with some consideration of local system strengthening and resilience. On inter-sector links, the present evaluation has a primary focus on the links between emergency education and child protection. The provision of PSS is a particular point of convergence, including relevant training for teachers; and the ways in which child friendly spaces and youth centres relate to schools. The evaluation is also looking at vocational training, particularly with regard to the reintegration of children released from armed forces; and to a limited extent ALP, in the areas visited (see below).

Beyond these issues, the present evaluation is also concerned with harmonisation and future convergence of the emergency education work with the mainstream education agenda over time - with some reference to the prospects for return and reintegration of both IDPs and the externally displaced South Sudanese refugee population.

The timeframe covered by the present evaluation (2016-18) differs from that of the BTL evaluation (2015-17). Nevertheless, the L3 evaluation team will try to ensure that its work is properly harmonised with that of the BTL evaluation, in particular to avoid unnecessary duplication of key informant interviews and site visits.

Of the various other evaluations currently in process, it is important to mention that an evaluation of UNICEF’s work on child soldiers (CAFAAG) is currently underway. Again, the present evaluation will seek to harmonise its work with that evaluation, and to draw on its results as far as possible.

1.5	In this inception report, we begin by reviewing below the most salient features of the humanitarian crisis in South Sudan context UNICEF’s response to it. In the subsequent sections we set out the purpose, scope and approach of the evaluation, noting areas of particular focus. The methodology is then described, together with the schedule for the evaluation. The Annex contains the terms of reference, the evaluation matrix, and protocols for field-level interviews and focus group discussions

# 2.	Context: the South Sudan crisis and UNICEF’s response

## 2.1	The South Sudan crisis

UNICEF has worked in South Sudan since the country gained independence in 2011, and for many years prior to that in what was then the southern part of Sudan. UNICEF played a leading role in Operation Lifeline Sudan during the second Sudanese Civil War (1983-2005) and in the negotiation with the Sudanese government and SPLM of the Ground Rules for delivery of humanitarian assistance to all communities in need. Following the signing of the Comprehensive Peace Agreement in 2005, greater security and a return of many of those displaced in the war saw a gradual reduction in the need for humanitarian assistance. When the South Sudanese people voted overwhelming for independence in 2011, the new country of South Sudan was created in a mood of great optimism – matched by a very large investment of international funds.

The optimism did not last. In December 2013, a political power struggle broke out between President Kiir and his former deputy Riek Machar, following which a civil war broke out that continues to the present. While principally a conflict between the SPLM government and Machar’s SPLM-in Opposition (IO), fighting between several factions on multiple ‘fronts’ across the country makes the course of the conflict hard to read. The conflict has a strong ethnic dimension, fuelled by long-standing tensions between Dinka and Nuer tribal groups in particular, and politicians have been quick to exploit those divisions. But growing insecurity and violence across the country has affected all communities, with both government and opposition parties engaging in ethnically-targeted killing, rape, torture and forced displacement. As a 2018 report from the UN Commission on Human Rights in South Sudan makes clear, these acts constitute war crimes and crimes against humanity.

Mass displacement is one of the defining features of the current conflict. Despite a peace agreement signed in 2015, violence erupted again in July 2016 in Juba and spread across the Equatorias and to Unity state. The pace and scale of displacement subsequently escalated. In total around 4 million people have now been displaced from their homes, or about one third of the entire population. Of those, around half have fled to neighbouring countries as refugees. For both displaced and non-displaced people, the threat of violence is very real: the creation of fear is central to the way in which the conflict is being waged. This has strong age and gender aspects. As the 2018 human rights report records: ‘Conflict-related sexual violence is endemic. Rape… and other forms of sexual violence, targeting girls, boys, women and men, are often committed in front of children, humiliate the victims, their families and their communities and destroy the social fabric, leaving behind a traumatised people and the seeds of yet more violence.’ Girls are increasingly at risk of sexual violence, child marriage and exploitation. Recruitment of child soldiers continues, despite assurances from the parties to the conflict, although there have also been some recent (limited) releases of children.

All of this suggests that, from a humanitarian perspective, the protection agenda is paramount. Yet in this respect, children and their families are largely at the mercy of the warring parties, who have so far shown very little inclination to modify their behaviour in the face of international condemnation. The UN Chapter-VII mandated protection force (UNMISS) has ‘authority to use all necessary means to [1] protect United Nations personnel, installations and equipment [2] to deter violence especially through proactive deployment and active patrolling, [3] to protect civilians from threats, regardless of source, [4] to create conditions conducive to delivery of humanitarian assistance by international and national actors…’  [numbers added]. In reality, UNMISS’ role is largely confined to securing the various Protection of Civilian sites across South Sudan, the Security Council noting with concern that the extensive resources needed to protect civilians at the United Nations Protection of Civilians sites has limited UNMISS’s presence outside [those sites]…

The threats to children and their families across South Sudan derive from both the direct and indirect effects of conflict. South Sudan has been at war for most of the past sixty years, with no history of stable governance and little investment in infrastructure or systems. The effects of the current conflict have to be seen against this backdrop. As a service provider, the government and its ministries have very limited reach and capacity. Donors have not been willing to provide development assistance in a context of weak and unstable governance, high levels of corruption and widespread human rights abuse. Opportunities for development have been correspondingly few, despite the potential for agricultural expansion, and the economy of the country has largely collapsed. Vital revenues from oil production have fallen, agricultural production – particularly in the fertile southern states – has been severely disrupted, and inflation is rapidly eroding the value of the South Sudanese pound. Traditional livelihoods are being lost as a result of insecurity and displacement of farmers. The result is that millions of South Sudanese are now destitute and acutely food insecure.

Acute food insecurity has brought large parts of the country to the brink of famine – and indeed pockets of famine were seen in 2017. In southern Unity, around 100,000 were reported to be living in famine conditions. Over half of the population was suffering acute food insecurity by December 2017, an unprecedented situation. Levels of acute malnutrition are correspondingly high, with around 250,000 projected to suffer severe acute malnutrition in 2018. Coupled with poor sanitation, lack of health services and exposure to disease (particularly diarrheal disease – including cholera – and malaria), the situation is particularly dangerous for young children. New threats, including the risk that the Ebola virus will spread from the neighbouring Democratic Republic of the Congo, now compound existing threats to health.

Among the trends noted in the 2017 Annual Report, one of the most striking is the process of urbanisation related to forced displacement. As the report notes: Although South Sudan is traditionally a rural society, it is rapidly urbanizing, even if mostly involuntarily and in an unplanned manner. Since the last quarter of 2016, a large part of the population in the Greater Equatorias have either fled to seek refuge in Uganda or moved to the relative safety of urban areas within the region. In other parts of the country, people have continued to look for safety in the protection of civilians (PoC) sites located in urban centres. Returnees have come back to towns and cities where they have better access to security, food markets and basic services. While this trend sets the context for much of the current humanitarian agenda, it also highlights the challenges faced by those who remain in the countryside where such services are much harder to access and where little if anything exists by way of protection.

The situation for children deteriorated over 2017, with continued incidents of recruitment (despite assurances from the parties to the conflict), abuse, exploitation and other grave violations, with 3,220 documented grave violations affecting 77,000 children. This included more than 19,000 children recruited into armed groups (up from 17,000 in 2016) and more than 1,200 documented cases of sexual violence. Girls have been increasingly at risk of sexual violence, child marriage and exploitation.  Although underreported due to fear of retaliation and social stigma, gender based violence — including sexual violence, abductions, child marriage and forced marriage — is widespread. It has been fuelled by harmful traditional practices, the conflict and lack of access to adequate support services.

The on-going crisis has aggravated an already-difficult education situation. Some 1.8 million children are out of school across the country, and girls make up only 40 per cent of those accessing education. The deterioration of systems and services – together with chronic under-investment and household economies that are under increasing pressure – has led to insufficient school infrastructure, poor educational outcomes, and high numbers of out-of-school children. Girls are more likely than boys to be excluded from education, and in some parts of the country, over 75 percent of primary-aged girls are not in school. Children in rural areas and those affected by conflict and other emergencies are amongst the most educationally disadvantaged in the country. By mid-2017, more than 2 million primary-school aged children were estimated to be out of school, and close to 1.3 million were at risk of dropping out.

Some of the main constraints to access are on the supply side. Approximately one third of primary schools are damaged, occupied or closed due to the conflict and failure to pay teacher salaries. According to the 2017 Education Cluster Assessment, 26 percent of functional schools have been affected by attacks on education with the most commonly reported incidences being theft and looting by armed forces/groups. Quality of education is also a major concern: most primary schoolchildren attending school do not achieve foundational literacy, numeracy and life skills. Two thirds of teachers are untrained and there are major shortages of teaching and learning materials.  The Annual Education Census (AEC) 2016 revealed that more than half (58 per cent) of primary level teachers are untrained, impacting negatively on the quality of learning outcomes. The findings of the 2017 Education Cluster Assessment showed that teachers left schools mainly due to insufficient, delayed and unpaid salaries, as well as insecurity. School closures have led to greater numbers of unsupervised children and a concomitant rise in protection concerns, including an increased risk of harmful coping mechanisms, child marriage and escalating boys’ involvement in armed groups or crime. Yet the capacity of the Ministry of General Education and Instruction (MoGEI) to respond to the needs of children remained very limited throughout the evaluation period: during FY 2017/18, the government allocated only 2.1 percent of the budget to education, far below the 20 percent ‘Education for All’ target.

By the end of 2018, although the general situation of children and their families remains critical, some opportunities for progress present themselves. The current peace process, based on the agreement signed by the main parties to the conflict in September 2018,  brings some hope of sustained cessation of hostilities, reduction in conflict-related violence and greater access for the provision of basic services. But many uncertainties remain, including the question of return for those displaced (internally and externally) by the conflict. The South Sudan Humanitarian Response Plan for 2019 notes that ‘the scale and flow of such movements remain difficult to project.’ More generally with regard to the humanitarian situation, it concludes that ‘the cumulative effects of years of conflict, violence and destroyed livelihoods have left more than 7 million people or about two thirds of the population in dire need of some form of humanitarian assistance and protection in 2019 – the same proportion as in 2018.’

## 2.2	UNICEF and the wider response to the crisis

2.2.1	The lack of public services coupled with the factors described above have led to ever higher levels of dependence on international humanitarian assistance. Yet people’s access to humanitarian assistance has also been constrained, partly it seems as a matter of deliberate strategy – itself an issue of major protection concern:

Humanitarian aid has been deliberately blocked from reaching civilians perceived to be from the “other side” or on the basis of ethnicity... People are fleeing as a result, leaving behind ghost towns and unattended crops, further exacerbating the food crisis. Hunger, lack of access to health care and schools are used to break down the other side in this conflict. The rights to life, physical integrity, to adequate food, water, healthcare, adequate accommodation and education are constantly violated.

In many other cases, access to humanitarian assistance has been limited less directly, either by organisational security constraints in the face of conflict or criminality; or by logistical constraints, particularly during the rainy season when the challenges are compounded by lack of the infrastructure necessary to allow long-distance transport of goods by road. The 2017 UNICEF country office annual report notes that: ‘Lack of sustained access in 2016 hampered regular access to those most in need by restricting movement of UNICEF staff and impeding supplies delivery. 2017 was evidenced by a 25 per cent increase (1,140 humanitarian access incidents) from incidents reported in 2016. Attacks on humanitarian workers in 2017 resulted in the death of 25 aid workers. In 2017, OCHA recorded a total of 612 relocations of humanitarians in 54 incidents, over 100 bureaucratic access impediments and 451 violent attacks against humanitarian personnel and assets. All of which hampered timely humanitarian response.’ More recently, there has been a worrying rise in abductions of humanitarian staff.

2.2.2	While the humanitarian situation therefore remains critical, funding for the overall humanitarian response remains tight. The response of the HCT has been to refine its targeting, looking for cross-sector synergies and opportunities for greater efficiency ‘wherever possible’. ‘The Humanitarian Country Team will prioritize integrated response efforts that tackle people’s needs in priority areas holistically. This aims to keep affected communities at the centre of the response while maximizing synergies among humanitarian clusters for a more effective response. We plan to reduce reliance on air operations and increase the use of new tools like biometric registrations to carefully target assistance’. The 2019 HRP is reduced in scope compared to 2018, targeting 5.7 million people with an overall appeal of US$1.5 billion.

UNICEF’s own targets within these wider totals are to reach 1.8 million people with assistance in 2019, including 800,000 children.  The comparable figures for 2018 were much higher: the overall number of people targeted was 4.2 million, of which 2.4 million were children. Given that the funding requested was almost the same as for 2019, this points to a very different way of calculating of targets and programme coverage for 2019, and this difference requires explanation.

Education

2.2.3	The UNICEF response to the education needs in South Sudan has been consistently built on the assumption that investing in Education is key to the development of South Sudan. The outcome defined for 2016 to 2018 period was: ‘Children and adolescents aged 3-18 years, particularly girls and other vulnerable groups, have increased and more equitable access to quality basic education with learning outcomes in South Sudan by 2018’

To accomplish this outcome, UNICEF South Sudan was to be focused on delivering results in the following programme areas:

- National Systems Strengthening in Literacy and Numeracy in Early Grades, School Supervision, inspection, Leadership, Monitoring and Evaluation.

- Early Childhood Development

- Education in Emergencies

- Conflict-sensitive programming, integration of peace-building and life skills in Education

Three outputs (perhaps better described as ‘sub-outcomes’) were intended to contribute to achieve this outcome:

- Output 1 Strengthened national systems to provide basic education and alternative learning with life skills, peace-building and conflict-sensitive education for children and adolescents, including disadvantaged and excluded children, with measurable learning outcomes by 2018.

- Output 2 Increased support to government and partners to improve transition from ECD to primary and primary to secondary education by 2018.

- Output 3 Improved national, sub-national and community capacity to protect and provide quality basic education services to children and adolescents by 2018.

In the event, as described in the Part One evaluation report, the scope for strengthening national systems and working with government was limited during the evaluation period; and limited progress was possible under these headings, in part because of the re-escalation of conflict that followed the writing of the 2016-18 CPD and strategies.

2.2.4	This evaluation will focus on the emergency-related aspects of the intervention.

As well as co-leading the Education Cluster, UNICEF and its partners have supported various education initiatives throughout the evaluation period, including:

- Back to learning initiative (BTL) – this has been supported by UNICEF since 2015, under the theme ‘Inclusive and Equitable Access to Quality Education for Peace and Sustainable Development’.  The objective is to provide education services for children in humanitarian settings, and building the capacities of education personnel and community members to effectively deliver quality, age-appropriate learning opportunities and inclusive education services.   The BTL initiative addresses the most urgent education needs in conflict-affected and insecure states.  Apart from ensuring access to education by children, establishing or rehabilitating of classrooms and learning spaces, greater focus is placed on strengthening the capacity of local education authorities, teachers and PTAs/School management committees (SMCs) to deliver life skills, peace-building and psychosocial support.  The BTL initiative, the Accelerating Learning Programme and the specific focus on girl’s education have contributed to redressing some of the deep inequities that have been exacerbated by years of crisis, conflict, and displacement.

- Education in emergencies and peace-building – this is integrated into the BTL initiative, and the goal is to ensure that children affected by severe humanitarian crises have access to quality education in a safe and protective environment.

- Global Partnership for Education (GPE) programme was initiated to strengthen the investment in the recovery and developmental phases of education systems building. It has supported the construction of schools, development of national curriculum for both primary and secondary education, development and procurement of textbooks, teaching and learning materials, and capacity building of teachers, school development committees, education managers and supervisors – this has included enhancing teacher development facilities including the construction/rehabilitation/expansion of teacher training institutes and county education centers. Also, GPE continues to strengthen the capacity of the education ministry at various levels, including in planning, budgeting, leadership, IMS, etc.

Child protection

2.2.4	As reflected in its own strategy documents, the UNICEF response to child protection needs in South Sudan has been consistently built on two main components: (i) system building and capacity development, and (ii) providing critical child protection services. The intended outcome of the programme is that “South Sudanese children and adolescent at risk of or exposed to violence, exploitation and abuse have their risk reduced, mitigated and, where possible, their dignity and health restored by 2018”.

Two outputs contribute to achieve his outcome.

Output 1 System Building: Ministry of Gender, Child and Social Welfare, the Ministry of Health and the selected State ministries have laws, regulatory frameworks and service delivery systems in place to adequately improve children’s access to justice and birth registration services

Output 2 Child Protection Services: Key actors are able to provide improved core child protection and GBV services for children at risk of or exposed to violence, exploitation and abuse in emergency and non-emergency settings by 2018

Output 3 CP Programme & Technical Support: CP program results effectively implemented and technical support provided at national and state levels by CP sections.

The evaluation will focus on the emergency-related aspects of Outputs 2 & 3, of which the main sub-components are as follows:

- Psychosocial support:  dedicated psychosocial care to children with critical child protection challenges is provided, including children in schools, communities, and in child-friendly spaces, as well as during RRM missions.

- Community based child protection: strengthening community support groups to enhance the protection of children.

- Family tracing and reunification of separated and unaccompanied children

- Release and reintegration of children associated with armed groups and armed forces (CAFAAG): advocacy for the prevention of the recruitment and use of children by armed forces/groups; supporting the release and reintegration of children associated with armed forces/groups;

- Mine Risk Education: supporting the provision of mine risk education to protect children from landmines and explosive remnants of war for populations living in high risk areas.

- Monitoring and Reporting Mechanism on grave violation (MRM) In South Sudan:  co-chairing the UN Country Task Force on Monitoring and Reporting (CTFMR) on the six grave violations with UNIMISS.

- GBV mitigation: supporting risk mitigation efforts across UNICEF sectors and UNICEF-led clusters through: 1) trainings); 2) conducting safety audits to assess safety; and 3) development of cluster specific action plans to mitigate GBV.

- Clinical management of rape (CMR): providing trainings for clinical and non-clinical staff in various health facilities.

- Communities Care programme: promotes gender equitable social norms to support survivors of GBV & transform inequitable gender relations that drive GBV.

2.2.5	The programme has been implemented through four operational modalities aimed at increasing the capacity and reach of interventions: 1) static operations in stable areas; 2) outreach programmes; 3) mobile campaigns; and 4) the Integrated Rapid Response Mechanism. These approaches facilitated sustained service delivery in both secure and highly inaccessible locations.

Anticipated risks and operational challenges for implementing the programme were:

- Further deterioration of the conflict

- Access

- Deteriorating economy

- Lack of government commitment and political accountability

- Limited partner capacity

Part One of the present evaluation noted that ‘more than in any other ‘sector’, the gap between vulnerabilities and the ability of humanitarian agencies to reduce them is apparent in relation to child protection. This is not a matter of under-performance but a characteristic of the protection agenda as a whole, where both the ability and responsibility to protect lies so directly with the warring parties themselves. UNICEF has been consistent in its efforts to create a safer environment for children and provide remedial services for those exposed to violence or separated from their families. But insecurity and lack of access has at times severely disrupted those efforts.’

2.2.6	With regard to the ‘centrality of protection’, this is an agenda to which the IASC principals (including the UNICEF ED) have explicitly committed themselves. It also constitutes the second of three objectives in the South Sudan Humanitarian Response Plans for 2017 and 2018. Thus the 2017 plan ‘recognizes that South Sudan is first and foremost a protection crisis and underscores the centrality of protection of civilians to the response’. For UNICEF, as a key member of the South Sudan HCT, this implies obligations that go beyond its mandated child protection role and extend to its wider humanitarian role. The Part 2 evaluation will consider the extent to which UNICEF has successfully integrated wider protection concerns into its overall programme, both in its design and the way in which it is implemented. This will include a review of UNICEF’s advocacy on protection issues (including the denial of access to humanitarian assistance); and consideration of the extent to which its implementing partners have been able to ensure that protection concerns are properly reflected in the implementation of the programme. Besides concerns about violence, coercion and deliberate deprivation, this will include questions about the dignity and rights of those affected by the prevailing crisis.

The L3 Corporate Emergency designation

2.2.7	UNICEF’s Level 3 Corporate Emergency Activation Procedure (CEAP) was activated on 8 February 2014 for South Sudan. The L3 was declared for an initial three-month period. It was extended 10 times, bringing its total duration to 4 years 5 months.

As of June 2018, the L3 CEAP in South Sudan has been ‘deactivated’ and the transition made to L2 status. The explanatory memo from the Executive Director (25th June 2018) says that although the humanitarian situation continues to deteriorate, ‘UNICEF’s capacity to respond has been significantly strengthened over the past years and the Country Office has the requisite capacity to sustain the response. However, given the volatility of the situation along with the high level of humanitarian funding needs, our support to South Sudan remains an organizational priority. Therefore, I have approved the recommendation by Leila Pakkala, ESA Regional Director and Global Emergency Coordinator for the South Sudan crisis, and endorsed by Manuel Fontaine, EMOPS Director, to de-activate the South Sudan Level 3 Response on 30 June 2018 and transition to an L2 designation until 31 December 2018.’

The L2 designation was subsequently extended in December 2018 for a further six months, and will be reviewed at the end of June 2019.

# 3.	Evaluation purpose, scope and approach

## 3.1	Purpose and scope

3.1.1	Part Two of the South Sudan evaluation has a similar purpose to Part One. Building on the first part, it is intended to provide an independent assessment of UNICEF’s humanitarian response in South Sudan during the evaluation period; and evidence-based findings and recommendations to guide UNICEF’s on-going humanitarian response in South Sudan and its global programming.

The evaluation is thus intended to fulfil two functions:

(i) 	A summative accountability function, reflecting the need to account (internally and externally) for one of UNICEF’s largest and most life-critical country programmes, designated a corporate L3 priority and now entering its sixth year.

(ii) 	A formative learning function, reflecting the need to capture lessons from a programme of this duration and significance, to inform the country programme and UNICEF’s global programming and practice.

3.1.2	As described in more detail in the ToR (Annex A), the main intended audience for the evaluation includes:

- UNICEF South Sudan country management and staff responsible for the implementation of the new Country Programme 2019-2020;

- UNICEF SSCO cluster and coordination leads responsible for contributing to the HCT-led interagency humanitarian response in South Sudan;

- Staff in UNICEF East and Southern Africa Regional Office and HQ Divisions (EMOPS, PD, Supply, DHR and others) who are responsible for coordinating and supporting the L2 humanitarian response;

- The UNICEF Executive Board and concerned UN Member States;

- UNICEF’s donors in South Sudan

- UNICEF’s implementing and strategic partners.

Beyond UNICEF and its immediate stakeholders, the report should be of interest to the government of South Sudan and others who share responsibility and concern for the welfare of crisis-affected communities in the country. Ultimately, the evaluation is intended to benefit ordinary people affected by the crisis, and above all the children of South Sudan.

3.1.3	Having focused on the ‘child survival’ sectors (WASH, Health, Nutrition) in Part One of the evaluation, this second part will focus primarily on Emergency Education and Child Protection. In addition, it will consider a number of cross-cutting issues, including the ‘centrality of protection’ principle and how it is applied by UNICEF in South Sudan. The response to gender-based violence will be considered within this framework. The Part Two evaluation will build on and deepen the analysis of Part One with respect to a number of strategic issues, including resilience and the humanitarian-development nexus; programme balance and accountability; and questions of operational modality, including partnerships and the use of direct delivery (specifically the IRRM).

3.1.4	As noted in Part One of the evaluation, the two functions described above each demand rather different approaches. Accountability requires a relatively broad scope that covers UNICEF’s response as a whole over the review period, judged against certain basic criteria. Learning requires a narrower focus on specific sectors and topics of particular interest or concern, allowing greater depth of analysis. The Part One report included a brief review of the whole programme from an accountability perspective. In Part Two, that analysis will be further fleshed out with regard to Education and Child Protection; and the learning component will focus on specific issues within those sectors that appear to the evaluation team to warrant deeper consideration.

3.1.5	Part One of the evaluation concluded that while UNICEF has performed well (given the immense challenges involved) in many aspects of its programme over the evaluation period, the threats to children remain worryingly high. It suggests that UNICEF needs to continue to find better ways, with its partners, to increase coverage of basic services and to extend its reach in this regard. In Part Two of the evaluation, we will consider the specific threats to children’s safety, security and well-being and their access to basic education; the extent to which UNICEF and its partners have been able to mitigate those threats; and whether there may be ways of increasing the effectiveness, efficiency coverage and quality of the related programmes.

3.1.6	Just as the humanitarian-development distinction was often hard (and sometimes unhelpful) to draw in relation to the child survival sectors, so it is in relation to Education and Child Protection. In both cases, the focus will be on the emergency-related agenda (EiE, CPiE), but the evaluation will also consider the relationship between the emergency and developmental agendas, in theory and practice. Although the evaluation will consider the UNICEF response from January 2016 to date, particular emphasis will be placed on the recent and current response, including the question of whether lessons learned over the past two years are currently being applied. Recommendations will be made based on our understanding of the future challenges likely to face UNICEF and the wider humanitarian system in South Sudan.

## 3.2	Evaluation approach

3.2.1	This Part Two evaluation has three main phases: (i) an inception and initial fact finding phase, including preliminary visit to the SSCO in November 2018; (ii) the main fact finding mission to the country in Feb/March 2019; (iii) analysis, write up and presentation of findings, conclusions and recommendations, together with related in-house consultations (to July 2019).

The evaluation team will draw on the results presented in the Part One report in order to expedite some of the more factual and descriptive elements of the evaluation, as well as to deepen the analysis presented in Part One. Overall, the approach to the evaluation will be determined by what it takes to answer the questions set out in section 4 below with a reasonable degree of confidence.

3.2.2	The approach of the evaluation will be consultative, looking to identify lessons and ways forward in collaboration with the staff involved in the response, while maintaining independence of judgement and a willingness to challenge ‘accepted wisdom’. The accountability dimension of the evaluation, in particular, demands such independence. It is not intended that the evaluation should focus on individual responsibilities for actions taken; but the responsibilities and related actions of teams and offices will be considered, as will any apparent gaps in the framework of accountability.

3.2.3	The evaluation will be conducted in accordance with the UNEG Ethical Guidelines for Evaluation and UNICEF’s own guidelines on interviewing children and young people.  Clearance will be sought through an ethical review process for the use of the tools included in Annex C.

We note here in particular the following provisions from the UNEG guidelines:

Obligations to participants

19.	Evaluators shall respect people’s right to provide information in confidence and make participants aware of the scope and limits of confidentiality. Evaluators must ensure that sensitive information cannot be traced to its source so that the relevant individuals are protected from reprisals.

Respect for Dignity and Diversity

20.	Evaluators shall:

a.	Respect differences in culture, local customs, religious beliefs and practices, personal interaction, gender roles, disability, age and ethnicity, and be mindful of the potential implications of these differences …

b.	Keep disruption to a minimum while needed information is obtained, providing the maximum notice to individuals or institutions they wish to engage in the evaluation, optimizing demands on their time, and respecting people’s right to privacy.

As a general rule, views expressed by informants to the evaluation will not be attributed to the individuals or organisations concerned, other than to distinguish views expressed by internal (UNICEF) sources from those expressed by external sources.

# 4.	Methodology and guiding questions

4.1	Following the approach outlined above, the primary methods used in the evaluation will be key informant interviews (KIIs), both with UNICEF staff and those from other organisations; and documentary review, using mainly UNICEF materials; and related data analysis. These will be supplemented by field observations and consultation with affected communities and local partners. It is also proposed to conduct a short survey with UNICEF country staff, and a similar survey with in-country partners.

Guiding questions

4.2	 The overall guiding question for the evaluation is: How well has UNICEF responded to the short-medium term threats to children’s well-being and development in South Sudan in the period Jan 2016- May 2018? How well placed is it now to respond to likely future threats?

In this Part 2 evaluation, our particular concern is with short-term threats to children’s security, safety and well-being, i.e. their freedom from violence and fear, from coercion and deliberate deprivation; and with their ability to access at least basic (primary level) education or life skills training as appropriate. The main focus throughout will be on those threats that derive primarily from conflict and insecurity in South Sudan, and from the related deficits in basic government services. In other words, we are primarily concerned with emergency-related threats and the UNICEF response to them, rather than with developmental deficits. The evaluation will, however, consider the relationship between the shorter-term humanitarian response and the longer-term developmental agenda, including questions of synergy, consistency and convergence.

4.3	The evaluation team has devised a framework of guiding questions for the evaluation, building on those in the Terms of Reference. Together with sub-questions, criteria and potential evidence sources, they are set out in full in the Evaluation Matrix in Annex B. Here we list the main ‘top line’ questions.

A. Programme relevance and appropriateness to context and needs

A1. What have been the main threats to children's security, well-being and development in the period January 2016 to December 2018?

A2. How does this break down by time, location and demographic group (including camp, urban and rural populations; age group; gender)?

A3. What has been the scale, coverage and reach of UNICEF's L3 programme relative to needs/ vulnerability?

A4. Were the forms of intervention chosen by UNICEF the rights ones (sectors, sub-agendas), taking account of the roles and capacities of others? Were they adapted to changing needs?

A5. Were targets set proportionate to need, in light of other capacities? Funding and resourcing issues? Was appropriate adaptation made to targets as needs evolved? Were changes of target communicated and their rationale recorded?

B. Strategy and programme design

B1. What sectoral strategies exist, how clear are they and how strong is their logic?

B2. How well designed are the corresponding interventions? Involvement of partners in strategy and design? Consultation with communities?

B3. How well integrated have the various programme components been? Has the programme as a whole been coherent (particularly between EiE and CPiE)?

B4. Has UNICEF found the right balance in its programme between camp/PoC, static and outreach approaches?

C: Programme performance: results and effectiveness

C1. To what extent has UNICEF achieved its targets in each sector?

C2. How effective have UNICEF's interventions been, measured against stated objectives?

C3. What have been the outcomes from UNICEF and its partners’ interventions? What attributable direct and indirect effects have there been?

D. Programme quality: compliance with CCCs and other standards/principles

D1. To what extent did UNICEF deliver against its CCC commitments? Where it did not, what were the main reasons?

D2. How accountable have UNICEF and its partners been to affected populations? What has been extent / quality of community engagement?

D3. Has the response been consistent with core principles of humanitarian action?

D4. Has the UNICEF response been equitable? Have gender and human rights issues been properly addressed?

D5. Compliance with external sector-specific and general standards?

E. Performance on cross-cutting agendas

E1. How well has UNICEF mainstreamed protection (applying the ‘centrality of protection’ principle)? Including Do no Harm

E2. To what extent has UNICEF contributed to resilience of individuals, communities and systems in relation to CPiE, EiE, GBV and protection generally?

E3. How far has UNICEF met its WHS commitments? Other organisational commitments?

E4. How effective has the communications & advocacy part of UNICEF’s response been?

F: Data quality, needs analysis, programme monitoring, reporting

F1. How strong has been the situational and needs analysis underpinning UNICEF's programme and strategy decisions?

F2. How well has UNICEF monitored the delivery, quality & effectiveness of its programme?

F3. How well has UNICEF managed information and reported on its programme?

G: Operational modalities: C4D, partnerships, IRRM

G1. How well has the C4D function worked to ensure programme appropriateness, effectiveness and accountability?

G2. How well have UNICEF’s implementing partnerships worked? Does UNICEF have the right partnership model?

G3. How effective has UNICEF’s direct service delivery (CPiE, EiE) been through the IRRM mechanism?

H: Coordination and collaboration with others

H1. How well has UNICEF performed its roles as Cluster Co-Lead and AOR Focal Point?

H2. How well has UNICEF collaborated with others on these agendas (CPiE, EiE, GBV)?

J: Efficiency, timeliness, resourcing & programme support

J1. How timely has the delivery of UNICEF’s programme been?

J2. How well has the supply and logistics function supported the programme?

J3. How well have resource mobilisation, HR and other support functions worked?

J4: How efficient has the programme been?

Data gathering and analysis methods

4.4	Key informant interviews

These will be conducted with those individuals within and outside UNICEF judged to be best placed to help answer the questions above, together with the subsidiary questions set out in the evaluation matrix in Annex B. The guiding questions provide a framework within which questions can be asked, rather than a questionnaire to be followed for all interviewees. A semi-structured approach has been adopted, using selected questions from the list above to elicit broad responses. To date, around twenty interviews have been undertaken during the inception and initial fact finding phase of the evaluation. Subsequent interviews – some of which are follow-up interviews with individuals already consulted – will be used to try to elicit answers to the more specific questions set out in Annex B.

The majority of the proposed key informants are UNICEF staff involved (directly or indirectly) in the South Sudan response, from the Country Office and field offices; the Regional Office for Eastern and Southern Africa (ESARO) in Nairobi; and from UNICEF Headquarters in New York. Implementing partner organisations, both national and international (i.e. those with which UNICEF has concluded PCAs) will be interviewed, together with staff from other UN bodies, including UNMISS. The relevant Ministries and government departments will also be consulted, and the evaluation team will meet in Juba with major donors to UNICEF’s Education and Child Protection work.

4.5	Focus group discussions: communities, children and local partners

During the field visits, a limited number of group discussions will be held with local communities and partners. A protocol and guiding questions for these group discussions are included in Annex C. A specific protocol for consultation with children has been designed, but given the sensitivities involved, the evaluation team will be closely guided on this by local staff and partners.

4.6	Surveys

It is proposed to conduct two short web-based surveys. These will be directed at two main stakeholder groups: UNICEF staff (including relevant staff in field offices who because of time constraints were only reached to a very limited extent) and UNICEF partners. These aim to complement the field phase by seeking responses to key questions around accountability and learning as per the evaluation structure. It is proposed to conduct these surveys in March/April 2018.

4.7	Document review and data analysis

Analysis of key documents and the data they contain will form a core part of the evaluation. They will be used both as information sources in their own right and as a basis for triangulating information gained through key informant interviews. A reference library of documents has been compiled during the inception phase of the evaluation, and compilation continues. The reference library includes the following types of document:

- Overview and general analysis documents, mostly situational, from UNICEF and external sources

- UNICEF Country Programme documents and related files

- Documents related to the Level 3 Emergency status, including the respective justifications for extension and the Level 3 SSOPs for reference

- Needs assessments, both joint and UNICEF-specific

- Response Plans (HRP, but also cluster plans and UNICEF-specific plans)

- UNICEF HAC Appeals and SitReps

- UNICEF Programming documents, including work plans, sector-strategies, and related documents

- Implementation data extracted from the UNICEF Results Assessment Module (RAM)

- Documents related to the Operations function, including the CPMP and HR data

- Resource Mobilisation documents, including Consolidated Emergency Reports (CER)

- Supply and Logistics Data and relevant documents, including specific studies undertaken in South Sudan

- Monitoring tools, including KOBO platform, and data as required

- Relevant studies and evaluations, including the updated situation analysis

Evaluation limitations and quality assurance

4.8	The main limitation for the evaluation concerns the availability of historic evidence covering the whole period 2016-18. In some cases, data appears to be missing or incomplete, particularly for the earlier part of the period. A number of key UNICEF informants for the period are no longer in post in the SSCO, having since been re-deployed. Efforts will be made to follow up with such staff, particularly those who held pivotal positions in the UNICEF response.

The evaluation report will be reviewed under the UNICEF Global Evaluation Reports Oversight System (GEROS) to help ensure the quality and completeness of the final product.

# 5.	Proposed structure for the Evaluation Report

The following is proposed as a structure for the full evaluation report. This remains provisional at this stage, subject to further evolution during the writing phase.

- Preface

- Executive Summary

- List of abbreviations

1.	Introduction … 5pp

1.1	Background to the evaluation

1.2	The South Sudan context

1.3	Evaluation scope, approach and methods

2.	UNICEF’s L3 programme response 2016-18… 5pp

2.1	Overview of UNICEF’s response to date

2.2	UNICEF’s overall strategy and programme balance

2.3	Resourcing of the programme

2.4	UNICEF leadership and advocacy for children

3.	UNICEF and the Education response…15pp

Box: the Education-related CCCs

3.1	The Education (EiE) context: threats, vulnerabilities and needs

3.2	Needs assessment and data quality

3.3	UNICEF’s Education in Emergencies strategy: clarity, coherence, logic?

3.4	Designing and planning the response: coverage, focus and target setting

3.5	Implementing the strategy

- Delivery against targets

- Effectiveness against stated objectives

- Programme quality and the CCCs

- Programme efficiency: VFM, process

3.6	Monitoring and reporting

3.7 	UNICEF and the Education Cluster

3.8	Resilience, capacity building and future prospects

3.9	Conclusions and lessons arising

4.	UNICEF and the Child Protection Response…15pp

Box: the CP-related CCCs

4.1	The CP context: threats, vulnerabilities and needs

4.2	Needs assessment and data quality

4.3	UNICEF’s CPiE strategy: clarity, coherence, logic?

4.4	Designing and planning the response: coverage, focus and target setting

4.5	Implementing the strategy:

- Delivery against targets

- Effectiveness against stated objectives

- Programme quality and the CCCs

- Programme efficiency: VFM, process

4.5	Monitoring and reporting

4.7	UNICEF, the Protection Cluster and CP AoR

4.8	Resilience, capacity building and future prospects

4.9	Conclusions and lessons arising

5.	UNICEF, centrality of protection and GBV…5pp

5.1	UNICEF’s contribution to the overall protection agenda

5.2	Responding to gender-based violence

5.3	Applying the ‘centrality of protection’ principle in practice

6.	Operational modalities, partnerships and collaboration---5pp

6.1	UNICEF’s ‘mixed modalities’ approach

6.2	Collaboration with government bodies: national, local

6.3	Partnerships and collaboration with other UN agencies

6.4	Partnerships with CSOs: INGO and NNGO

6.5	The IRRM mechanism

6.6	C4D, community mobilisation and engagement

7.	UNICEF efficiency and programme support…5pp

7.1	Information management and data quality

7.2	Supply and logistics

7.3	Human resources and operational support

7.4	Support to Country office from RO and HQ

8.	Conclusions and recommendations…6pp

8.1	Overall conclusions

8.2	Specific conclusions

8.3	Recommendations

Annexes

# 6.	Evaluation and field mission schedules

The table below sets out the proposed schedule and outputs for the evaluation. Some of the dates at the back end of the process have yet to be finalised, as have the format and expected attendance for the findings and recommendations workshop.

| Phase 1: Inception and document review | Output | Due date |
| --- | --- | --- |
| Activity 1: Preliminary document review and inception mission to Juba. Scoping and briefing discussions with key SSCO staff and selected external informants. Initial discussion with ESARO staff. | Meeting Notes | 15th December 2018 |
| Activity 2: Drafting of inception report, including evaluation matrix, methodology and work plan; development of the data collection materials. | Draft inception report | 31st January 2019 |
| Activity 3: Consultation on draft report, followed by revision and agreement of inception report | Final inception report | 15th February |
| Activity 4: Document review and field mission planning | Team member notes | 25th February |
| Phase 2: Field mission, data gathering and analysis |  |  |
| Activity 5: Field-level data collection, validation and analysis | KII notes | 15th March |
| Activity 6: Further data gathering (surveys, KIIs, documentation) and data analysis | Survey results KII notes | End April |
| Activity 7: Drafting workshop (Geneva) | Plan for completion of evaluation | 9/10 May |
| Phase 3: Analysis, report writing, consultation and communication of results |  |  |
| Activity 8: Drafting of evaluation report | 1st draft main report | 14th June |
| Activity 9: Draft report shared for review by Reference Group | RG initial comments | 24th June |
| Activity 10: Workshop in SSCO to discuss findings and conclusions, and to validate recommendations | Meeting report | Mid July tbc |
| Activity 11: Revise evaluation report considering written feedback and comments from RG and validation W/shop | 2nd draft report | End July |
| Activity 12: Revised evaluation draft report shared for final comments (more widely) | Final comments on evaluation report | August/early Sept |
| Activity 13: Finalization of main evaluation report, summary evaluation report, PowerPoint, etc. | Final report | Sept |
| Activity 14: Approval of the final deliverables | Final version of all deliverables | TBC |
| Activity 15: Final dissemination events | Notes from events | TBC |

| Data Collection Mission: 24th February - 16th March 2019 Provisional schedule |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date/Time | Agenda Item | Attendees | Venue | Comments |
| Sunday 2th February |  |  |  |  |
| 16.00 | Arrival in Juba and check-in in Hotel | Evaluation Team | Hotel |  |
| Week 1 |  |  |  |  |
| Monday 23rd February |  |  |  |  |
| 09.00 - 09.30 | Security Briefing | Evaluation Team | Security Office |  |
| 09.30 - 10.30 | Review of agenda, logistics, etc | SPPME Team | Evaluation Team's Office |  |
| 10.30 - 12.30 | Meeting with the Education Team | Evaluation Team | Evaluation Team's Office |  |
| 12.30 - 14.00 | Lunch |  |  |  |
| 14.00 - 16.00 | Meeting with the CP Team | Ed Teams | Evaluation Team's Office |  |
| 16.00 - 18.00 | Courtesy Call with Rep and DepRep | Evaluation Team | Conference Room |  |
| 18.00 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel |  |
| Tuesday 26th February |  |  |  |  |
| 9.00 - 12.00 | POC site visit (Juba 3) | Evaluation Team | Juba 3 | 3 hrs allocated to visit to POC; allocation for travel time |
| 12.00 - 13.00 | Meeting with UNMISS staff dealing with civil protection, MRM | Evaluation Team | Juba 3 |  |
| 13.00 - 14.00 | Lunch | Evaluation Team | Juba 3 |  |
| 14.00 - 15.30 | Meeting with GBV Co-lead (UNFPA + IRC) | Evaluation Team | UNFPA Offices (UN Hs) | Location can be UNFPA Offices?? |
| 16.30 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel | 1.5 hrs mtg; allocation for travel |
| Wednesday 27th February |  |  |  |  |
| 9.00 | Travel to Bentiu | Evaluation Team |  | See separate worksheet with Bentiu Programme |
| Friday 1st March |  |  |  |  |
| 16.00 | Travel back to Juba | Evaluation Team | Hotel |  |
| Saturday 2nd March |  |  |  |  |
| 9.00 - 14.00 | Team Meetings | Evaluation Team | Hotel |  |
| Sunday 3rd March |  |  |  |  |
| 9.00 - 18.00 | Free time/analysis and drafting | Evaluation Team | Hotel |  |
| Week 2 |  |  |  |  |
| Monday 4th March |  |  |  |  |
| 09.00 - 10.00 | Meeting with Chief of Field Ops | Chief of Field Ops | Evaluation Team's Office |  |
| 10.00 - 11.30 | Education Cluster | Evaluation Team | Evaluation Team's Office |  |
| 11.30 - 13.00 | CP Cluster | Evaluation Team | Evaluation Team's Office |  |
| 13.00 - 14.00 | Lunch | Evaluation Team |  |  |
| 14.00 - 15.30 | Meeting with a PCA partner (Ed/CP) - international | Evaluation Team | CSO Office | SSCO to advise - different from those met during the Inception Meeting. |
| 16.00 - 17.30 | Meeting with a PCA partner (Ed/CP) - local | Evaluation Team | CSO Office | SSCO to advise - different from those met during the Inception Meeting. |
| 18.00 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel |  |
| Tuesday 5th March |  |  |  |  |
| 09.00 - 10.30 | Meeting with Ministry of Education | Evaluation Team | Education Ministry Offices | Relevant Dept/Staff |
| 11.00 - 12.30 | Meeting with Ministry of Social Welfare | Evaluation Team | Social Welfare Ministry Offices | Relevant Dept/Staff |
| 12.30 - 14.00 | Lunch | Evaluation Team |  |  |
| 14.00-15.00 | Meeting with the Gender Specialist | Evaluation Team | Evaluation Team's Office |  |
| 15.30 - 17.00 | Meeting with the Protection Cluster | Evaluation Team | UNHCR Offices | UNHCR Protection Cluster Lead + NRC co-lead |
| 18.00 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel |  |
| Wednesday 6th March |  |  |  |  |
| 9.00 | Travel to Yambio | Evaluation Team |  | See separate worksheet with Yambio's Programme |
| Friday 8th March |  |  |  |  |
| 4.00 p.m. | Travel to Juba | Evaluation Team | Hotel |  |
| Saturday 9th March |  |  |  |  |
| 9.00 - 14.00 | Team Meetings | Evaluation Team | Hotel | If there is an opportunity for other meetings, these can be slotted in for Sat (if possible) |
| Sunday 10th March |  |  |  |  |
| 9.00 - 18.00 | Free Day/analysis | Evaluation Team | Hotel |  |
| Week 3 |  |  |  |  |
| Monday 11th March | Travel to Wau | Evaluation Team (excl. JD) | Guest House | The Team except (James Darcy) will travel for the 3rd Mission to Wau. James will remain in Juba for subsequent interviews See separate programme for Wau |
| Monday 11th March |  |  |  |  |
| 09.00 - 10.00 | ECHO | Evaluation Team | ECHO Office |  |
| 10.30 - 11.30 | DFID | Evaluation Team | DFID Office |  |
| 12.00 - 13.00 | USAID |  |  |  |
| 13.00 - 14.00 | Lunch | Evaluation Team |  |  |
| 14.00 - 15.00 | Meeting with Resource Mobilization Specialist | Evaluation Team | Evaluation Team's Office |  |
| 15.00 - 16.00 | Meeting with Communications Team | Evaluation Team | Evaluation Team's Office |  |
| 16.00 - 17.00 | Meeting with Access Coordinator + IRRM Team | Evaluation Team | Evaluation Team's Office |  |
| 18.00 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel |  |
| Tuesday 12th March |  |  |  |  |
| 09.00 - 10.00 | Meeting with C4D Team | Evaluation Team | Evaluation Team's Office |  |
| 10.00 - 11.30 | Meeting with CFOs | Evaluation Team | Evaluation Team's Office | Up to 3 CFOs from locations not part of field missions |
| 11.30 - 12.30 | Meeting with Supply and Logistics Staff | Evaluation Team | Evaluation Team's Office |  |
| 12.30 - 14.00 | Lunch | Evaluation Team |  |  |
| 14.00 - 15.30 | Meeting with NGO partner working on overall Protection | Evaluation Team | UNICEF or Partner's Office |  |
| 15.30 - 17.00 | Free to allocate | Evaluation Team | Evaluation Team's Office |  |
| 18.00 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel |  |
| Wednesday 13th March |  |  |  |  |
| 09.00 - 10.00 | Meeting with Global Affairs Canada (former CIDA) | Evaluation Team | Partner's Office |  |
| 10.30 - 11.30 | Meeting with Norwegian Embassy | Evaluation Team | Partner's Office |  |
| 11.30 - 12.30 | Free to allocate | Evaluation Team | Evaluation Team's Office |  |
| 12.30 - 14.00 | Lunch | Evaluation Team |  |  |
| 14.00 - 15.00 | Free to allocate | Evaluation Team | Evaluation Team's Office |  |
| 15.00 - 16.00 | Free to allocate | Evaluation Team | Evaluation Team's Office |  |
| 16.00 - 17.00 | Free to allocate | Evaluation Team | Evaluation Team's Office |  |
| 18.00 - 20.00 | Evaluation Team Meeting/Dinner | Evaluation Team | Hotel |  |
| Thursday 14th March |  |  |  |  |
| 09.00 - 10.00 | Evaluation Team meeting with SSPME Chief |  |  |  |
| 10.00 - 12.00 | Debrief Meeting with SSCO | Evaluation Team | Conference Room |  |
| 16.00 | Evaluation Team departs for Nairobi |  |  |  |

# Annex A	Terms of Reference

TERMS OF REFERENCE

(draft 2.0: 16.11.2018)

| Title/PURPOSE | To conduct an evaluation of UNICEF’s Response to the Crisis in South Sudan focused on Education and Protection (Part2) |
| --- | --- |
| RECRUITING OFFICER | Evaluation Specialist, UNICEF Evaluation Office |
| CONTRACT MODALITY | Individual contracts |
| Location of Assignment | Home based with travel to South Sudan and Kenya (ESARO) and/or reporting to UNICEF New York (UNICEF House, 3 UN Plaza - 44th Street between 1st Ave and 2nd Ave) |
| Language(s) required | English |
| Duration of Contract | November – June 2019 |

Introduction

In March 2018, UNICEF’s Evaluation Office commissioned an evaluation of the organization’s response to the crisis in South Sudan. The evaluation’s time frame was from January 2016 to June 2018 and had two components. As part of the inception/scoping the team conducted an accountability-oriented review of the entire UNICEF programme. This involved an analysis of the overall Level 3 emergency response against a limited set of evaluation criteria (including relevance, coverage, coherence, resourcing, and achievement against targets). The second component was to conduct a more focused learning-oriented review of the child survival component of the response: WASH, nutrition and health. This involved analysing the sectors’ strategies, design, performance and efficiency as well as use of evidence, systems used for quality assurance, coordination and partnerships.

A workshop on the findings, conclusions and recommendations took place in late August 2018. During the workshop, participants from both RO and SSCO indicated that the evaluative work was of significant use to the organization, and the Evaluation Office was requested to evaluate the sectors that were not covered in detail during Part 1, namely child protection (as well as the centrality of protection) and education. These TORs describe the Evaluation Office’s plan for the Part 2 of the evaluation. It describes the purpose, objectives and scope, the potential questions it will seek to answer, and an indication of the approach and methods to be used. It also describes the governance arrangements, the requirements of various parts of the organization, the tasks, and the timeline for the evaluation, the budget and the desired profiles of the evaluation team members.

Context – protection and education in South Sudan

Despite the peace agreement, South Sudan remains volatile and faces a crisis of unprecedented proportions, with the lives of many children at risk. The crisis disproportionately affects women and girls, and inequalities persist between women, men, boys and girls in terms of education access, livelihood opportunities, protection and political processes. Peace talks have occasionally resulted in ceasefire agreements, but they have been systematically violated. The political, security and economic situation has deteriorated over the past two years, with a corresponding increase in violence, a significantly worsened humanitarian situation and massive violations of child rights. The fighting has two distinct, but at times interwoven, elements: a national political struggle, and intercommunal conflicts over land and cattle.  In addition, the conduct of armed hostilities, general criminality and banditry, due to the lack of rule of law, present another source of insecurity that long pre-dates the present conflict and is sometimes hard to distinguish from it.

Protection Environment

Part 1 of this evaluation has raised some challenges relating to the entire UNICEF’s approach to protection. The context in which UNICEF is operating is rife with protection risks – first, the government and opposition parties have engaged in ethnically-targeted killing, rape, torture and forced displacement, to mention some of the most severe human rights violations. As a 2018 report from the UN Commission on Human Rights in South Sudan makes clear, some of these acts constitute war crimes and crimes against humanity. Second, mass displacement is one of the defining features of the current conflict. Since 2015, spreading hostilities have resulted in 4 million South Sudanese people being displaced – internally and externally – including 2.4 million children.  Of the 2.1 million who sought refuge in neighbouring countries, more than a million are children.

For both displaced and non-displaced people, the threat of violence is very real: the creation of fear is central to the way in which the conflict is being waged. More than 15,000 children around the country remain separated from their parents or missing, since the conflict started.  Separated and unaccompanied children are more susceptible to violence, abuse and exploitation, which makes returning them to their parents an urgent priority.  UNMISS which is mandated to contribute to the protection of civilians has, in reality, partly done so due to limited resources, and has largely confined its role to securing the various Protection of Civilian (PoC) sites across South Sudan.  As a result, many locations with active conflict remain unprotected.

The space for humanitarian operations is shrinking. South Sudan has proved one of the most dangerous environments in the world for aid workers, particularly for civil society organizations. The looting of aid supplies has become endemic. The 2018 HRP noted one hundred ‘bureaucratic access impediments’ (including denials of access permission) from January-October 2017. Yet, the constraints on people’s access to humanitarian assistance appear in part to be a matter of deliberate strategy – and is in itself an issue of major protection concern. This cannot be characterized as simply a set of technical, operational or bureaucratic hurdles for the agencies concerned.

The compounding effects of widespread violence and sustained economic decline have further diminished the capacity of people affected to address threats to their health, safety and livelihoods. People in need of assistance and protection number currently seven million.  It is estimated that up to 85 per cent are children and women. In the ongoing conflict, children continue to suffer the most – the situation for children deteriorated over 2017, with continued incidents of recruitment (despite assurances from the parties to the conflict), abuse, exploitation and other grave violations, with 3,220 documented grave violations affecting 77,000 children. This includes more than 19,000 children recruited into armed groups (up from 17,000 in 2016).

Amid long-standing factors such as poverty, impunity, and widespread gender inequality, the current conflict and displacement has further heightened women’s and girls’ vulnerability to violence and exacerbated protection risks.   Girls are increasingly at risk of sexual violence, child marriage and exploitation. Although underreported due to fear of retaliation and social stigma, gender based violence — including sexual violence, abductions, child marriage and forced marriage — is widespread. It is fuelled by harmful traditional practices, the ongoing conflict and lack of access to adequate support services. According to UN Mission in South Sudan (UNMISS), all parties to the recent conflict have committed acts of rape and other forms of sexual violence against women and girls of different ethnic groups and foreign nationalities. Even in close proximity to the PoC sites, women have been killed or attacked when collecting firewood and food.   Sexual violence has been used as a weapon of war in the South Sudan conflict, with more than 1,200 documented cases of sexual violence In 2018, the highest recorded since the conflict started.

Education

Education has the potential to help children unlock a future that is peaceful and productive, and also provide the needed human resources to develop their country. However, the ongoing crisis has aggravated an already-difficult education situation. The deterioration of systems and services – together with chronic under-investment and household economies that are under increasing pressure – has led to insufficient school infrastructure, poor educational outcomes, and high numbers of out-of-school children. Girls are more likely than boys to be excluded from education, and in some parts of the country, over 75 percent of primary-aged girls are not in school. Children in rural areas and those affected by conflict and other emergencies are amongst the most educationally disadvantaged in the country. By mid-2017, more than 2 million primary-school aged children were estimated to be out of school, and close to 1.3 million were at risk of dropping out.  Also, approximately one third of primary schools are damaged, occupied or closed due to the conflict and failure to pay teacher salaries – according to the 2017 Education Cluster Assessment, 26 percent of functional schools have been affected by attacks on education with the most commonly reported incidences being theft and looting by armed forces/groups.

Quality is a particular concern: most primary schoolchildren attending school do not achieve foundational literacy, numeracy and life skills. Two thirds of teachers are untrained and there are major shortages of teaching and learning materials.  The Annual Education Census (AEC) 2016 revealed that more than half (58 per cent) of primary level teachers are untrained, impacting negatively on the quality of learning outcomes. The findings of the 2017 Education Cluster Assessment show teachers left schools mainly due to insufficient, delayed and unpaid salaries, as well as insecurity. School closures have led to greater numbers of unsupervised children and a concomitant rise in protection concerns, including an increased risk of harmful coping mechanisms, child marriage and escalating boys’ involvement in armed groups or crime. Yet, the capacity of the Ministry of General Education and Instruction (MoGEI) to respond to the needs of children remains limited – for example, during the FY 2017/18, the government allocated only 2.1 percent of the budget to education, well below the 20 percent ‘Education for All’ target.

UNICEF’s Response

Despite the numerous challenges, UNICEF has been at the forefront of providing multi-sector response to multiple humanitarian crises, and has continued to train frontline professionals and government staff on social protection, justice for children, maternal and child health and education; advocate for policies; and make the case for providing free essential social services to the people of South Sudan.  In 2017 for example, UNICEF helped deliver aid to 2.3 million people, of whom 2.1 million were children.

For education specifically, UNICEF and its partners continued to support various initiatives, including:

- Back to learning initiative (BTL) has been supported by UNICEF since 2015, under the theme ‘Inclusive and Equitable Access to Quality Education for Peace and Sustainable Development’.  The objective is to provide education services for children in humanitarian settings, and building the capacities of education personnel and community members to effectively deliver quality, age-appropriate learning opportunities and inclusive education services.   The BTL initiative addresses the most urgent education needs in conflict-affected and insecure states (see below under EiE section).  Apart from ensuring access to education by children, establishing or rehabilitating of classrooms and learning spaces, greater focus is placed on strengthening the capacity of local education authorities, teachers and PTAs/School management committees (SMCs) to deliver life skills, peacebuilding and psychosocial support.  The BTL initiative, the Accelerating Learning Programme and the specific focus on girl’s education have contributed to redressing some of the deep inequities that have been exacerbated by years of crisis, conflict, and displacement.

- Education in emergencies and peacebuilding – this is integrated to the BTL initiative, and the goal is to ensure that children affected by severe humanitarian crises have access to quality education in a safe and protective environment.  In 2018, the plan is to provide 500,000 children and adolescents with access to age-appropriate learning opportunities; establish 405 learning spaces providing a safe and protective learning environment; train 4,000 teachers, including ECD caregivers, and 1,200 PTA and School Management Committee members on social mobilization, conflict sensitive education, basic school management and school development.

- Global Partnership for Education (GPE) programme was initiated to strengthen the investment in the recovery and developmental phases of education systems building. It has supported the construction of schools, development of national curriculum for both primary and secondary education, development and procurement of textbooks, teaching and learning materials, and capacity building of teachers, school development committees, education managers and supervisors – this has included enhancing teacher development facilities including the construction/rehabilitation/expansion of teacher training institutes and county education centers. Also, GPE continues to strengthen the capacity of the education ministry at various levels, including in planning, budgeting, leadership, IMS, etc.

On Child Protection, Part I of the evaluation has noted that: more than in any other ‘sector’, the gap between vulnerabilities and the ability of humanitarian agencies to reduce them is apparent in relation to child protection. This is not a matter of under-performance but a characteristic of the protection agenda as a whole, where both the ability and responsibility to protect lies so directly with the warring parties themselves. UNICEF has been consistent in its efforts to create a safer environment for children and provide remedial services for those exposed to violence or separated from their families. But insecurity and lack of access has at times severely disrupted those efforts.

Overall, UNICEF continues to provide leadership and technical guidance on child protection programming in South Sudan, including to the Child Protection (CP) sub-Cluster at national and state levels, as well as all activated CP working groups, focusing on the following:

- Providing critical child protection services

- Family tracing and reunification of separated and unaccompanied children; strengthening community support groups to enhance the protection of children;

- Release and reintegration: UNICEF and partners continue to advocate for the prevention of the recruitment and use of children by armed forces/groups; supporting the release and reintegration of children associated with armed forces/groups;

- Psychosocial support:  UNICEF and partners continued to provide dedicated psychosocial care to children with critical child protection challenges, including children in schools, communities, and in child-friendly spaces, as well as during RRM missions.

- Mine Risk Education: supporting the provision of mine risk education to protect children from landmines and explosive remnants of war for populations living in high risk areas.

- Gender-based violence (GBV)

- UNICEF continues to play a leading role in supporting risk mitigation efforts across UNICEF sectors and UNICEF-led clusters through: 1) trainings); 2) conducting safety audits to assess safety; and 3) development of cluster specific action plans to mitigate GBV.

- Clinical management of rape (CMR): training has been provided for clinical and non-clinical staff in various health facilities.

- Communities care (Transforming lives and preventing violence programme): The UNICEF Communities Care (CC) program promotes gender equitable social norms to support survivors of GBV and to transform inequitable gender relations that drive GBV.

- Monitoring and Reporting Mechanism on grave violation (MRM) In South Sudan, UNICEF co-chairs the UN Country Task Force on Monitoring and Reporting (CTFMR) on the six grave violations with UNIMISS. The Task Force also includes various UN organizations and non-governmental organizations.

- System building – for key actors within the child welfare, legal systems and judiciary, lawmakers and law enforcement agents at national and decentralized levels.

Centrality of protection:

With regard to the ‘centrality of protection’, this is an agenda to which the IASC principals (including the UNICEF ED) have explicitly committed themselves, and is at the core of the United Nations “Rights Up Front” Plan of Action, and to the Responsibility to Protect.  It also constitutes the second of three objectives in the South Sudan Humanitarian Response Plans for 2017 and 2018. Thus the 2017 plan ‘recognizes that South Sudan is first and foremost a protection crisis and underscores the centrality of protection of civilians to the response’. For UNICEF, as a key member of the South Sudan HCT, this implies obligations that go beyond its mandated child protection role and extend to its wider humanitarian role. The Phase 2 evaluation will consider the extent to which UNICEF has successfully integrated wider protection concerns into its overall programme, both in its design and the way in which it is implemented. This will include a review of UNICEF’s advocacy on protection issues (including the denial of access to humanitarian assistance); and consideration of the extent to which its implementing partners have been able to ensure that protection concerns are properly reflected in the implementation of the programme. Besides concerns about violence, coercion and deliberate deprivation, this will include questions about the dignity and rights of those affected by the prevailing crisis.

Despite these commendable efforts, as well as work in the other sectors, Part 1 of the evaluation concludes that while UNICEF has performed relatively well in most aspects of its programme over the evaluation period, with the immense challenges of the operating environment, the threats to children remain worryingly high, and suggests that UNICEF needs to continue to find better ways, with its partners, to increase coverage of basic services and to extend its reach in this regard.

Purpose and Objectives

The South Sudan conflict has entered its fifth year in 2018, and the humanitarian crisis has continued to intensify and expand. An evaluation of the UNICEF response to the South Sudan humanitarian crisis (Part 1) was initiated from March 2018, using the rapid and timely evaluation approach.  The scope of Part 1 was limited and focused on the child survival component of the response: WASH, nutrition and health. There was a request to evaluate sectors not included in Part 1 (child protection and education). Thus, Part 2 will focus on these two sectors.

Part 2 of the evaluation has a similar dual purpose as phase one: (i) building on Part 1, to provide an independent assessment of UNICEF’s humanitarian response in South Sudan during the evaluation period, in order to promote accountability among key stakeholders; and (ii) to provide evidence-based learning and recommendations to guide UNICEF’s ongoing humanitarian response in South Sudan, the coordinated interagency response, and UNICEF’s global programming.

The specific objectives are as follows:

- To assess the extent to which UNICEF has contributed to the protection of the children in South Sudan over the evaluation period (2016 to end 2018), and to suggest ways to strengthen its future role in this area;

- To capture lessons from the education and child protection programme over the evaluation period, in order to inform implementation of the country programme and UNICEF’s global programming and practice.

The evaluation will be conducted in line with EO standards and sector-wide standards for independent evaluation of humanitarian action. Since the proposed approach emphasizes utility, rapidity and timeliness, the evaluators will clearly state the limitations this implies in terms of upholding standards of rigour, credibility, and independence.

Evaluation Users

The primary target users include the following the following UNICEF actors: (i)UNICEF SS country management responsible for the implementation of the new Country Programme 2019-2020; (ii) ESARO and HQ Divisions (EMOPS, PD, Supply, DHR, etc) that are responsible for coordinating and supporting the L2 humanitarian response; and (iii) UNICEF coordination leads: SSCO strategic managers and cluster leads responsible for contributing to the UNHCT-led interagency humanitarian response in South Sudan; UNICEF implementing partners; (iv) the government of South Sudan.  (v) People affected by the conflict, among them are intended beneficiary communities and their local representatives; South Sudan’s children, adolescents, and women; and their national government and representatives, etc. The Secondary users include: (i) the UNICEF Executive Board and interested UN Member States; (ii) donor agencies that provide resources to the South Sudan humanitarian response; (iii) strategic humanitarian partners, and other key implementing partners at the global, regional and country levels.

Evaluation Scope

Programmatic Scope

While child protection and education were considered in a limited manner during Part 1, Part 2 is expected to assess these components in more detail. As in Part 1, this will include a review of the appropriateness of the UNICEF strategy and programme designs in these sectors, including the delivery modalities for static groups, groups on the move, camps and hard to reach populations. Given that South Sudan is one of the countries most affected by attacks on education, a grave violation, and thus a central protection concern and education priority, the evaluation will assess the intersectorality of CP and Education, particularly in PSS provision, coordination (cluster/AoR and information management) and protecting education from attack and military occupation.

The evaluation will include a review of implementation by analysing coverage, results, effectiveness, quality and efficiency. It will also include a review of the quality and use of evidence, assessing how well the response has used previous evidence such as reviews and evaluations to inform or adapt current programming, and what systems are in place to monitor the situation and UNICEF’s performance. The analysis will take into consideration the generation / use of information as well as gender and equity issues. The evaluation will investigate UNICEF’s leadership of the education cluster and child protection areas of responsibility; their coordination with other actors, coherence with other sectors and implementation.

In addition to these sector-specific areas of focus, the evaluation will assess protection as a cross-cutting strategy, the extent to which UNICEF has integrated protection components to its programme design, and how protection has been mainstreamed in the response (both overall and in each sector), including in its advocacy.  As a humanitarian actor, UNICEF is committed to the protection principles outlined in the Humanitarian Charter and Minimum Standards in Humanitarian Response, and the humanitarian principles adopted in General Assembly Resolution 46/182 and General Assembly Resolution 58/114.  Additional data and evidence will be collected and triangulated for this purpose.

Temporal scope

Part 2 of the evaluation will cover the period of January 2016 to end 2018.

Geographic scope

The country of South Sudan. It is recognised that considerations of security and logistics may make it impossible to visit certain areas of the country for evaluation purposes, just as they have limited UNICEF’s own programme reach; but the scope of the evaluation remains country-wide. It is important to consider where UNICEF has not been able to programme, despite the existence of humanitarian needs, and why this was so.

Guiding Evaluation Questions

As in the previous phase, the overall guiding question will be as follows:

How well has UNICEF responded to (and mitigated against) the short-medium term protection threats to children and development (education) in South Sudan in the period Jan 2016- end 2018? How well placed is it now to respond to likely future threats?

During the inception phase, the evaluation questions will further be refined, based on questions used in Part 1 (see the Evaluation Matrix: https://www.unicef.org/evaldatabase/index_103550.html), and include some of the following:

| Key Area(s) of Focus | Suggested questions |
| --- | --- |
| Programme relevance and appropriateness to context and needs | - What have been the main threats to children's security, well-being and development in the period January 2016 to December 2018? - How does this break down by time, location and demographic group (including camp, urban and rural populations; age group; gender)? - What has been the scale, coverage and reach of UNICEF's L3 programme relative to needs/ vulnerability? - Were the forms of intervention chosen by UNICEF the rights ones (sectors, sub-agendas), taking account of the roles and capacities of others? Were they adapted to changing needs? - Were targets set proportionate to need, in light of other capacities? Funding and resourcing issues? Was appropriate adaptation made to targets as needs evolved? Were changes of target communicated and their rationale recorded? |
| Strategy and programme design | - What sectoral strategies exist, how clear are they and how strong is their logic? - How well designed are the corresponding interventions? Involvement of partners in strategy and design? Consultation with communities? - How well integrated have the various programme components been? Has the programme as a whole been coherent (particularly between EiE and CPiE)? - Has UNICEF found the right balance in its programme between camp/PoC, static and outreach approaches? |
| Programme performance: results and effectiveness | - To what extent has UNICEF achieved its targets in each sector? - How effective have UNICEF's interventions been, measured against stated objectives? - What have been the outcomes from UNICEF and its partners’ interventions? What attributable direct and indirect effects have there been? |
| Programme quality: compliance with CCCs and other standards/principles | - To what extent did UNICEF deliver against its CCC commitments? Where it did not, what were the main reasons? - How accountable have UNICEF and its partners been to affected populations? What has been extent / quality of community engagement? - Has the response been consistent with core principles of humanitarian action? - Has the UNICEF response been equitable? Have gender and human rights issues been properly addressed? - Compliance with external sector-specific and general standards? |
| Performance on cross-cutting agendas | - How well has UNICEF mainstreamed protection (applying the ‘centrality of protection’ principle)? Including Do no Harm? - To what extent has UNICEF contributed to resilience of individuals, communities and systems in relation to CPiE, EiE, GBV and protection generally? - How far has UNICEF met its WHS commitments? Other organisational commitments? - How effective has the communications & advocacy part of UNICEF’s response been? |
| Data quality, needs analysis, programme monitoring, reporting | - How strong has been the situational and needs analysis underpinning UNICEF's programme and strategy decisions? - How well has UNICEF monitored the delivery, quality & effectiveness of its programme? - How well has UNICEF managed information and reported on its programme? |
| Operational modalities: C4D, partnerships, IRRM | - How well has the C4D function worked to ensure programme appropriateness, effectiveness and accountability? - How well have UNICEF’s implementing partnerships worked? Does UNICEF have the right partnership model? - How effective has UNICEF’s direct service delivery (CPiE, EiE) been through the IRRM mechanism? |
| Coordination and collaboration with others | - How well has UNICEF performed its roles as Cluster Co-Lead and AOR Focal Point? - How well has UNICEF collaborated with others on these agendas (CPiE, EiE, GBV)? |
| Efficiency, timeliness, resourcing & programme support | - How timely has the delivery of UNICEF’s programme been? - How well has the supply and logistics function supported the programme? - How well have resource mobilization, HR and other support functions worked? - How efficient has the programme been? |

Approach and Methods

The methods for data collection and analysis will be proposed and developed by the evaluation team.  The approach of the evaluation will be consultative, looking to identify lessons and ways forward in collaboration with the staff involved in the response, while maintaining independence of judgement and a willingness to challenge ‘accepted wisdom’. The evaluation framework will be developed during the inception phase. As in Part 1, it is expected that the methods for data collection will include the following:

Document review and data analysis: This will involve assessing documentation and data available from the evaluation document repository and other sources; selecting a sample of key documents and sources for analysis; and conducting a detailed review to inform the analysis. It will make full use of Part 1 of the evaluation, and other UNICEF evaluative studies and lessons learned.

Key informant interviews and focus group discussions: This will involve sampling some key stakeholders; consulting an adequate range of key informants through in-depth interviews or participatory methods, such as focus group discussions; and analysis that looks for convergence or divergence of views. Specificities will be defined during the inception phase through a stakeholder analysis, but should include UNICEF staff, HCT, key clusters, development partners, implementing partners, and affected populations.  To the extent possible, child participation during the evaluation should be considered.

Field visits/Direct observation: This will involve case studies in a selection of 3-5 locations in South Sudan, including at least one location served by IRRM (if one is scheduled during the field work); preparation of a ‘community research tool’ to guide consultation; carrying out the field-based research using mixed methods; and preparing case study reports to contribute to evidence and share with Field Offices. Location of case studies will be dependent on access and security.

Online Survey for UNICEF donors and implementing partners:   During Part 1, a short survey with UNICEF country office staff, and a similar survey with in-country partners was undertaken.  It is proposed to also conduct a short survey with UNICEF country staff and partners working in these sectors.

Analysis and reporting: This will involve preparation during inception of an analytical framework and/or evaluation matrix, showing how UNICEF will be assessed; iterative analysis during data collection phase; presentation and discussion of preliminary findings during the country visit with SSCO and/or ESARO; and synthesis analysis and report drafting. The report will be a maximum of 50 pages excluding annexes.  Finally, the reports for Part 1 and Part 2 will be synthesised, and will provide key recommendations to guide UNICEF’s ongoing emergency response in South Sudan, as well as learning for the organization as a whole.

Norms and Standards

The guidance documents mentioned below are those that the Evaluation Team is expected to comply with:

- United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System 2016; (including impartiality, independence, quality, transparency, consultative process)

- Ethical Guidelines for UN Evaluations will guide the overall process

- UNICEF Ethical Guidelines and standards for research and evaluation (relevant information can be found here)

- The evaluation should incorporate the human rights-based and gender perspective and be based on Results Based Management principles and determine the Theory of Change being applied in the emergency

Governance, Roles & Responsibilities

The Evaluation Office will manage the evaluation in close collaboration with the South Sudan Country Office, the East and Southern Africa Regional Office, and relevant HQ Divisions. The Senior Evaluation Specialist for humanitarian evaluation will manage this process, under the guidance of the Evaluation Director. The Evaluation Office will commission a team of external independent consultants to undertake the evaluation, who will be supported by an Evaluation Specialist from the Evaluation Office. The Evaluation Office is ultimately responsible for the process and final quality of the evaluation.

A Reference Group for the evaluation was established when the evaluation was initiated, to ensure the relevance, accuracy and thus credibility and utility of the evaluation. The RG is made up of staff from SSCO, ESARO, PD, EMOPs, FRG, and Supply Divisions.  The Reference Group’s main responsibility will be to review and comment on key evaluation outputs (i.e. TOR, the inception report, emerging findings, and the draft and final reports). However, it will play an advisory role only; final decisions on the evaluation process and quality assurance of outputs rests with the Evaluation Office. The reference group will communicate through email and through virtual meetings.

The South Sudan Country Office will be responsible for hosting the evaluation team, providing a work space, and arranging interviews with key stakeholders. It will also assist with locating documentation and materials.

Deliverables

The Evaluation Team will generate the following outputs to be reviewed by the Evaluation Office and the Reference Group, and will be approved by the Evaluation Office before wider dissemination:

- An Inception Report intended to outline the team’s understanding of UNICEF's response to the humanitarian crisis in South Sudan, and a framework on priority issues and questions for further examination. It will include a data collection toolkit (including guides for key informant interviews and focus group discussions) to be used in the course of the evaluation;

- Power-point presentation that will be used by the Evaluation Team to present the preliminary findings in country;

- A Draft Report that outlines clear evidence-based findings, conclusions and recommendations, with a clear Executive Summary;

- A Workshop, to present the findings, conclusions and deliberate on the recommendations;

- A Final Report, with a clear Executive Summary of no more than 2,000 words. This will incorporate responses to the comments of the Reference Group members.

- A synthesis report (based on the main finding, conclusions and recommendations of Parts One and Two of the evaluation)

- Power-point presentation of the final synthesis report that will be used by the Evaluation Team to present findings in a set of consultative workshops.

Evaluation Team

UNICEF will recruit a team of five external consultants to conduct the evaluation: one team leader, two senior evaluators and two national consultants. Individuals that meet the following requirements, and are available for the evaluation period indicated, are invited to apply.  Individual contracts will be issued to each team member.

The team leader will be awarded a contract for 55 days for the Phase 2 evaluation plus 15 days for the synthesis process. S/he will be responsible for managing and leading the evaluation team, in designing the evaluation, undertaking the data collection and analysis, conducting the debriefing session and recommendations workshop, as well as preparing the evaluation deliverables and reports.

Specifically, the evaluation team leader will:

- Report to the evaluation manager in EO;

- Work full time on the evaluation throughout the site visits, and manage the evaluation team;

- Agree the work plan for all aspects of the evaluation with the evaluation manager;

- Conduct the evaluation as per UN Ethical Guidelines for Evaluation (2008), the UNEG Norms and Standards (2016), and UNICEF Ethical Research Guidelines involving children in humanitarian settings;

- Prepare the evaluation report according to the UNICEF-Adapted UNEG Evaluation Report Standards (2010), with all evaluation product(s) written in English;

- Ensure that the evaluation produces evidence and analysis to the highest possible standards;

- Flag any limitations/constraints to the evaluation manager at the earliest opportunity, so that, as far as possible, they can be addressed, with any outstanding limitations noted in the evaluation report;

- Propose and conduct the evaluation with appropriate methodologies;

- Ensure that confidentiality is maintained and that the evaluation does not increase physical or reputational risks for UNICEF stakeholders operating in complex humanitarian environments;

- Take responsibility for delivering the evaluation in accordance with the Terms of Reference;

- Ensure the quality of all the evaluation products.

The two senior evaluators will be awarded contracts for 50 days each. They will be responsible for helping design the evaluation, carrying out the desk review, undertaking the data collection and analysis, and drafting elements of the report.  The two national consultants will be awarded contracts for 15 days each. They will be responsible for carrying out data collection in the field and assist with data analysis. They will also be responsible for translation, where required.

The team will report to UNICEF’s Senior Evaluation Specialist for humanitarian evaluations at the UNICEF Evaluation Office at headquarters (New York), who will provide the overall guidance to the evaluation.

The Required Qualifications of the Team are included in Annex 1:

Workplan:

This evaluation phase will be undertaken from end of November 2018, with a synthesized report ready by end of August 2019. The table below provides an overview of the tentative timelines and main deliverables of this phase of the evaluation.

| Evaluation Phase II - Activities | Output | Due date |
| --- | --- | --- |
| Inception and data collection |  |  |
| Recruitment of Team Leader and Team members | Contracts finalized | 10/30/2018 |
| Activity 1: Inception discussions with CO, RO and HQ staff. initial data collection and desk review (incl. one week in-country mission to SS – (proposed for last week in November) | Inception Report (draft) | 01 Nov - 15 Dec |
| Activity 2: Finalisation of the evaluation matrix, methodology and work plan; development of the data collection materials; finalizing the inception report | Final inception report | 20 Jan, 2019 |
| Activity 3: In-country missions to South Sudan CO and Nairobi RO. Data collection: KI interviews (internal and external), field visits, partner discussions, community-level focus group discussions, identification of documentary evidence. | Trip Report/Development of Survey tools | 04 - 20 Feb |
| Activity 4: Any further data gathering e.g. online surveys, documentation, etc. | Analysis of Survey Results | 28 Feb |
| Analysis, report writing, consultation and communication of results |  |  |
| Activity 5: Data validation and analysis; initial write-ups of sector drafts (protection, education, CP) | KII notes Initial sector drafts | 01 - 09 March |
| Activity 6: Drafting workshop, week of 12th March | First draft of main report | 16 March |
| Activity 7: EO Review of first Draft of main Report | Comments from EO | 18 to 20 March |
| Activity 8: Draft report shared for review to Reference Group + meeting with RG members for TL to present the preliminary findings and conclusions, and have discussions | RG initial comments Presentation and discussions (S4B recording) | 27 March |
| Activity 9: Workshop in SSCO to discuss findings and conclusions, and to validate recommendations | Meeting minutes Validated recommendations | 2 April |
| Activity 10: Revise evaluation report considering the comments from RG and validation W/shop | 2nd draft report | 15 April |
| Activity 11: Revised evaluation draft report shared for final comments (more widely) | Final comments on evaluation report | 30 April |
| Activity 12: Finalization of Phase 2 evaluation report and requesting a Management Response (MR) | Finalizing report (Copy Edit + DT Publishing) | 1 May |
| Synthesis of Phase I and Phase II (aka Chapter One and Chapter Two) |  |  |
| Activity 13: Analysis of the two reports and writing the synthesis | draft report | 15 June |
| Activity 14: Synthesis report shared for comments to RG members | Consolidated comments | 30 June |
| Activity 15: Finalization of synthesis report, summary evaluation report, PowerPoint, etc. | Final report and other deliverables | 15 July |
| Activity 16: Report sent out for MR on recommendations that may have arisen from the Synthesis | Final Report | 30 July |
| Activity 16: Copy-editing and Design/Layout and approval of the final deliverables | Final Reports | 15 August |
| Activity 17: Final dissemination events | Formal MR request | 30 August 30 |

Annex 1: Required Qualifications for the Evaluation Team:

Team Leader

- extensive experience in emergency response, preferably with a UN agency

- experience evaluating humanitarian action, evaluating L3 emergencies preferred

- experience evaluating protection and/or education desirable

- knowledge of latest methods and approaches in humanitarian evaluation, especially participatory methods and accountability to affected populations

- familiarity with UNICEF’s emergency response, including the Core Commitments to Children preferred

- excellent oral and written communication skills (in English)

- knowledge of qualitative and quantitative methods

- experience managing a team

- experience with the ethics of evidence generation; experience collecting data from vulnerable groups; familiarity with ethical safeguards

Two Senior Evaluators

- extensive knowledge of one or more of the sectors or themes (Education, Child Protection, including GBV technical knowledge, and Centrality of Protection) being evaluated

- extensive experience in emergency response, preferably with a UN agency,

- a minimum of five years’ experience evaluating humanitarian action

- familiarity with UNICEF’s emergency response, including the Core Commitments to Children

- knowledge of qualitative and quantitative methods

- experience with the ethics of evidence generation; experience collecting data from vulnerable groups; familiarity with ethical safeguards

- Excellent ability to communicate and write in English

Two National consultants

- experience working on research, studies or evaluations

- experience in primary data collection in affected communities; including leading focus group discussion and participatory methods

- qualitative data analysis skills

- experience in programme monitoring

- experience with the ethics of evidence generation; experience collecting data from vulnerable groups; familiarity with ethical safeguards

- Good ability to communicate and write in English

Annex B	Evaluation matrix

| Evaluation Matrix |  |  |  |
| --- | --- | --- | --- |
| A. Programme relevance and appropriateness to context and needs | Sub questions | Indicators/means of analysis | Sources of verification |
| A1. What have been the main threats to children's security, well-being and development in the period January 2016 to December 2018? | General protection situation? Child protection threats? GBV threats? Education access and safety? | - Conflict, safety - Grave violations - Access to services - Displacement - Situation of women and girls - Family separation - GBV profile - Psychosocial wellbeing - Indicators for access to education | HNO 2016-2019 HAC 2016-2019 Education cluster needs assessment/analysis CP & GBV sub-cluster needs analysis UNICEF partners needs assessment Other background/ research documents Community FGDs |
| A2. How does this break down by time, location and demographic group (including camp, urban and rural populations; age group; gender)? | General protection situation? Child protection threats? GBV threats? Education access and safety? | Above indicators broke down by time, location and demographic group (including camp, urban and rural populations; age group; gender) | Documents listed above, plus: REACH infographic and other infographics HNO 2016-2019 HAC 2016-2019 Other background/ research documents |
| A3. What has been the scale, coverage and reach of UNICEF's L3 programme relative to needs/ vulnerability? | Scale, coverage and reach for CP needs? For GBV needs? For Education in Emergency needs? | CP, GBV and EiE targets versus needs over time broken down by areas and demographics | HNO 2016-2019 HRP 2016-2018 HAC 2016-2019 UNICEF Response plans/AWP Annual HAC reports |
| A4. Were the forms of intervention chosen by UNICEF the rights ones (sectors, sub-agendas), taking account of the roles and capacities of others? Adapted to changing needs? | Appropriate forms of intervention: - For CPiE? - For EiE? - For GBV? In themselves and relative to others. Relative to UNICEF learning/policies? | Analysis of programme components against assessed needs, roles of others, UNICEF policy and guidance. | Review of above documents, plus key informant interviews (UNICEF and other). |
| A5. Were targets set proportionate to need, in light of other capacities? Funding and resourcing issues? Was appropriate adaptation made of targets in response to changing needs? | Were targets proportionate to the needs, taking account of other roles and capacities: - For CPiE? - For EiE? - For GBV? | CPiE, GBV and EiE targets versus needs over time broken down by areas and demographics Analysis of the funding received vs. requested. | HNO 2016-2019 HAC 2016-2019 UNICEF Response plans/AWP Yearly reports against HAC 2016-2018 UNICEF monitoring data for CPiE, GBV and EiE |
| B. Strategy and programme design | Sub questions | Indicators/means of analysis | Sources of verification |
| B1. What sectoral strategies exist, how clear are they and how strong is their logic? | Clarity and cogency of strategies: - For CPiE? - For EiE? - For GBV? | Analysis of the Theory of Change (actual/ inferred) Coherence with Cluster strategies? | Sector strategies AWP HRP 2016-2018 Minutes of meetings with partners Minutes/ data on consultation with communities KIIs (UNICEF Sections staff, UNICEF partners) FGDs (community representatives, teachers, children and their families) |
| B2. How well designed are the corresponding interventions? Involvement of partners in strategy and design? Consultation with communities? | - For CPiE? - For EiE? - For GBV? | Involvement of partners in the development of strategy and programme design Extent to which communities’ views are collected and used in planning and adjustments | As above |
| B3. How well integrated have the various programme components been? Has the programme as a whole been coherent (particularly between EiE and CPiE)? | Links, synergies and disconnects between education and CP programmes? Between these and other programme components (including the child survival sectors)? | Links in strategies, programme design and planning. Evidence of linkages in partnership documents | Strategy documents Partnership documents UNICEF reports KIIs: UNICEF section, field staff, partners Field visits/ Observations/FGDs |
| B4. Has UNICEF found the right balance in its programme between camp/PoC, static and outreach approaches? | Right balance across programme: - For CPiE? - For EiE? - For GBV? | Review of percentage spend, and relative coverage vs need | Document review: Budgets and programme strategy Coverage figures Needs analysis KIIs: UNICEF and external |
| C: Programme performance: results and effectiveness | Sub questions | Indicators/ways of analysis | Sources of verification |
| C1. To what extent has UNICEF achieved its targets in each sector? | Targets achieved: - For CPiE? - For EiE? - For GBV? | Target achievement versus target set | UNICEF Sitreps 2016-18 VISION (Virtual Integrated System of Information) |
| C2. How effective have UNICEF's interventions been, measured against stated objectives? C3. What have been the outcomes from UNICEF and its partners’ interventions? Attributable direct and indirect effects? | Have appropriate CPiE, GBV and EiE services been available and accessible to those targeted? Are CPiE, GBV and EiE services used? Have they achieved their intended effect? How do we know? | Performance against CPiE, GBV and EiE indicators over time. Including significant changes in behaviour or attitudes. Evidence of durability of effect. | Programme monitoring data/VISION (Virtual Integrated System of Information) KIIs (UNICEF Sections staff, UNICEF partners) Feedback from community mobilisers and FGDs |
| D. Programme quality: compliance with CCCs and other standards/principles |  |  |  |
| D1. To what extent did UNICEF deliver against its CCC commitments? Where it did not, what were the main reasons? | CCS met: - For CPiE? - For EiE? Design, resources, access, relevance of CCCs? | Extent of compliance with relevant sectoral guidance and standards (CCCs, Sphere, INEE, CPMS, IASC GBV Guidelines etc.) Reasons for non compliance. | CCCs HRP, HAC and Country Programme Strategy Sector strategies KIIs (UNICEF Sections staff, UNICEF partners) Field visits/ Observations |
| D2. How accountable have UNICEF and its partners been to affected populations? What has been extent / quality of community engagement? | Adequacy of processes for AAP? Community involvement in needs analysis, programme design and implementation? | Review against accepted good practice in AAP and UNICEF policy | UNICEF sitreps Partner reports KIIs: field office staff and partners FGDs with affected communities |
| D3. Has the response been consistent with core principles of humanitarian action? | Humanity? Impartiality? Neutrality? Independence? Do no harm? | Response proportionate to and based solely on need? Comparison of response and severity maps. | As above plus relevant sources on principle (Code of Conduct, Sphere Humanitarian Charter, etc.) |
| D4. Has the UNICEF response been equitable? Have gender and human rights issues been properly addressed? | Equity of response? Related to reach etc. Underserved populations or social groups? | Extent to which vulnerability data collected and used Analysis of gender in strategies and implementation | Review of relevant UNICEF policies vs programme design Review of needs assessment and monitoring data |
| D5. Compliance with external sector-specific and general standards? | For response as a whole and for CPiE, EiE, GBV? | Comparison of programme design and implementation against relevant standards | Sphere, INEE standards Relevant protection standards Common Humanitarian Standard |
| E. Performance on cross-cutting agendas | Sub questions | Indicators/means of analysis | Sources of verification |
| E1. How well has UNICEF mainstreamed protection (applying the ‘centrality of protection’ principle)? Including Do no Harm | Evidence of protection-aware programming for response as a whole and specifically for CPiE, EiE, GBV? | Comparison of programme design and implementation against relevant standards | Centrality of protection policy (UNICEF and South Sudan specific) Sphere Principles Relevant protection standards/guidance |
| E2. To what extent has UNICEF contributed to resilience of individuals, communities and systems in relation to CPiE, EiE, GBV and protection generally? | Is ‘resilience’ defined for these agendas? Does UNICEF have ways of gauging progress? What progress towards the sustained provision of services through national / local institutions? | Evidence of self-reliance and positive coping mechanisms? Evidence of capacities built and systems strengthened? | UNICEF sitreps and reports KIIs with partners, local staff, community mobilisers FGDs with communities Field visit observations |
| E3. How far has UNICEF been able to meet its WHS commitments? Other organisational commitments? | Localisation? Multi-year approaches? Risk-informed programming? Other? | Comparison of programme design and implementation against key commitments | WHS commitments Organisational policy statements |
| E4. How effective has the communications and advocacy aspect of the UNICEF response been? | Achievement of influencing objectives and progress in areas of primary concern | Review of relevant policy & behaviour change relating to education and CP | UNICEF reports KIIs with cooperating partners |
| F: Data quality, needs analysis, programme monitoring, reporting |  |  |  |
| F1. How strong has been the situational and needs analysis underpinning UNICEF's programme and strategy decisions? | Sources of info: adequacy, reliability? Frequency of update? Survey data? Quality of UNICEF needs analysis? | Review of data sources | Document review: Needs analysis, survey results, reports from community mobilisers and partners |
| F2. How well has UNICEF monitored the delivery, quality & effectiveness of its programme? | Partner oversight? Quality assurance indicators and process? | Review of monitoring practice vs UNICEF policy and guidelines | Monitoring reports UNICEF guidelines KIIs: field staff and partners |
| F3. How well has UNICEF managed information and reported on its programme? | Efficiency of IM? Are the indicators used appropriate / useful? For EiE, CPiE. Are the reports used? Valued? | Review of IM and reporting practice vs UNICEF policy and guidelines | UNICEF external reports UNICEF policy and guidelines on IM and reporting KIIs: donors, cluster members, GoSS |
| G: Operational modalities: C4D, partnerships, IRRM | Sub questions | Indicators/means of analysis | Sources of verification |
| G1. How well has the C4D function worked to ensure programme appropriateness, effectiveness and accountability? | Effectiveness of C4D generally and in relation to CPiE and EiE? Effectiveness of the community mobilisation network? | C4D objectives vs outcomes | Programme strategy documents |
| G2. How well have UNICEF’s implementing partnerships worked? Does UNICEF have the right partnership model? | Choice / balance of partners? Quality of partnerships? Delivery by partnerships? Partner support and capacity building? Quality control and oversight issues? | UNICEF policy vs practice Principles of partnership vs practice Satisfaction levels of UNICEF and partners | Partner reports KIIs: UNICEF sections and field managers Partner interviews Partner survey |
| G3. How effective has UNICEF’s direct service delivery (CPiE, EiE) been through the IRRM mechanism | Coverage, quality, effectiveness - For CPiE? - For EiE? - For GBV? | Comparison with other delivery through other modalities Effectiveness MoV? | UNICEF IRRM reports and data KIIs: field /IRRM staff, partners |
| H: Coordination and collaboration with others |  |  |  |
| H1. How well has UNICEF performed its roles as Cluster Co-Lead and AOR Focal Point? | - For CPiE? - For EiE? | Performance vs commitments Perceptions of clusters members | Policy re cluster roles Cluster reports KIIs: Cluster members, UNICEF staff |
| H2. How well has UNICEF collaborated with others on these agendas (CPiE, EiE, GBV)? | Appropriate level and type of collaboration with GoSS? With UN partners? NGOs? | Strategy vs practice Perceptions of cooperating partners | Strategy documents KIIs: cooperating partners |
| J: Efficiency, timeliness, resourcing programme support |  |  |  |
| J1. How timely has the delivery of UNICEF’s programme been? | - For CPiE? - For EiE? - For GBV? | Planned vs actual delivery dates Actual vs needs | UNICEF plans and HAC reports Partner survey |
| J2. How well has the supply and logistics function supported the programme? | - For CPiE? - For EiE? - For GBV? | Review of lead times vs context Perception of partners | UNICEF reports KIIs: Partners/field staff Partner & staff surveys |
| J3. How well have resource mobilisation, HR and other support functions worked? | - For CPiE? - For EiE? - For GBV? | Delivery vs need and opportunity | UNICEF SMRs and EMT minutes Staff survey |
| J4: How efficient has the programme been? | Relative cost benefit? Programme process? Partnership process? | Reviews of costs, process and time | Sample partners contracts Staff & partner surveys |

# Annex C	Field interviews and focus groups: protocols & questions

Field Work and data collection – Protocols for Interviews and FGD

Key Informant and Partner Interviews

- Share with UNICEF well in advance the subjects/ organizations proposed to be interviewed to allow for as much as possible advance planning.

- Where possible request that UNICEF shares the evaluation description and guiding questions, either as part of or following an introductory email/message from UNICEF when requesting for the meeting.

- Aim to have the interview itself for approximately 45-minutes to an hour maximum. If the respondent’s time is limited, then suggest a 30 minute interview based on a simplified version of the suggested questions.

During the interview:

- Introduce yourself and the reason for the interview, relating back to the Evaluation Description and Guiding Questions.

- Explain that notes will be taken but the intention is not to cite any individual or partner organizational views: these will be anonymized in any published material.

- Please record the following information about key informants in each case: the location and date; the name and position of the person(s) being interviewed, and their time in post; plus their role as it relates to UNICEF’s programme.

- At the end of the interview remember to thank the respondent.

Interviews with implementing partners may include any or all of the following questions (plus others as appropriate):

- Can you please tell me about the partnership that you have with UNICEF?

  - How many years have you been working together in this partnership?

  - What does this partnership entail?

  - Do you think you have received adequate support, financial or otherwise to enable you implement your tasks well? If not, how can it be improved?

- In your opinion, how would you rate the performance of UNICEF during the period of your partnership?

- In your opinion, which are the 2 or 3 things UNICEF has done really well in the Child Protection/GBV/Education response (coordination and/or programme)? What 2 or 3 things UNICEF did not do so well (coordination and/or programme)? What if anything do you think UNICEF needs to urgently change/improve / address in its response (coordination and/or programme)? In which areas do you think UNICEF should focus in the future in your community

- Did UNICEF ask your organisation about your support needs? Were you or anyone else in your organisation asked about your views on the support that you receive from UNICEF?

- What does your organisation do if you want to contact UNICEF for more information related to your work? Who do you ask? Where do you go?

- Do you attend any meetings with staff from UNICEF? If yes, who participates in these meetings? What follow up is there from these meetings?

- Have you been told about what to do if you or someone you know has a complaint or an issue to raise about UNICEF?

- How do UNICEF’s reporting requirements compare to those of other partners or donors you may have?

- Do you have any suggestions for ways in which UNICEF might improve on its effectiveness?

Interviews/ Discussions with children/ minors

- With support from UNICEF & partners, modalities for engagement with children will be agreed prior to any discussions or meetings with the children themselves

- The evaluators will comply with local legislation regarding age of a child and any other circumstances that allow for informed consent. (Ref: South Sudan Child Act/ relevant documentation with such legislation guidelines)

- Assent from the child and consent from his/her parents or guardians will be sought. The child/ minor will be given a choice to agree or disagree to participate.

- The data collection tools will as much as possible be reflective of the children’s capacities and will be clearly explained.

- The participants will be made aware that their participation is voluntary. Dissent or unwillingness to participate will be respected and they should be made aware that they are allowed to withdraw from the exercise/ interview at any time without negative consequences.

Focus Group Discussions

Preparation

- The evaluation team will liaise with the UNICEF Country Office staff ahead of the field work and share the tentative schedule.

- The UNICEF country office/ field office and partners will conduct appropriate local consultation prior to ascertain and obtain informed consent from community leaders, representatives or heads of households with due consideration of the prevailing power structures and hierarchies within the communities and households.

- The UNICEF country office/ field office and partners will assist in the selection of beneficiaries and identification of community volunteers for the FGD and in the related preparations (finding venue, communicating with local community leaders etc.).

- Each FGD session should involve approximately 6-12 beneficiaries from the community. Separate discussions should be held with men and women. As much as possible the group should include a mix of young, middle-aged and older people

- In situations where populations have been displaced we should speak to both displaced people and those in the host community.

- It should be stressed that participation is entirely voluntary and has no bearing on whether participants will be included in future UNICEF programs.

- No names or addresses will be taken.

At the Focus Group Discussion

- Together with the UNICEF partners on the ground the evaluation team will meet and greet the local representatives in the community, to brief them on the evaluation.

- Before the meeting starts, briefly explain the purpose of the exercise and ask if there are any questions from the participants.

- Explain the independence of the exercise – we are working on behalf of UNICEF but are not ourselves UNICEF staff members. A written report will be produced for UNICEF, an edited version of which may subsequently be published.

- Explain that notes or recording of the discussion will be taken but views expressed will not be attributed to individuals. Participants should therefore feel free to air their views although confidentiality of information shared during the group discussion should be observed.

- It should also be stressed that all opinions matter and there are no right or wrong answers. Group members should not put others down when contributing to the discussion.

- Preferably the discussions should not be longer than 2hrs, however it is important at the start of the FGD to come to an agreement on the duration.

- Check that all those present consent to being part of the group discussion. Inform the participants that consent is negotiable and that they can withdraw at any point without any negative consequences.

- Remember to thank the participants at the end of the discussion.

Focus group discussions may include any or all of the following questions (plus others as appropriate):

- Have you ever heard of UNICEF before this encounter? (Yes or No). Could you tell me what comes to your mind when you hear about UNICEF?

- What type of support was provided in your community by UNICEF? Who received this support?

- Do you understand how decisions were made about the intended beneficiaries who would receive this support?

- How far do you think the support received has helped to meet the needs of your community?

- How has assistance been provided to you or those close to you? Could the assistance have been delivered in a better way?

- What are your views and opinions on the quality of the work undertaken by UNICEF in your community? How does this compare to previous years?

- What is your overall view on the way in which staff of UNICEF interacts with your community?

- What (else) would you like us to know about UNICEF’s work in your community?

Child Protection and Gender Based Violence specific questions

- Which are the main protection risks children in your community are exposed to?

- In which ways children are protected from these risks?

- What do you do if you find out that a child is separated from the family?

- What do you do if you hear a child (girl or boy) is being abused (e.g. being forced to marry, forced to work, forced to join armed groups, sexually abused or exploited, etc)? What do you do to prevent these abuses to occur and what else needs to be done?

- What do you do to protect children from landmines and other unexploded devices?

Additional questions for teachers and other education personnel

- What do you do if a child shows signs of distress (e.g. sudden change in behavior, aggressive, sudden crying, isolation, self harm,…)

- Did you receive training on psychosocial support? Which education strategies you use to promote children’s wellbeing?

- How does the school relate to other services to protect children? For example Child Friendly Spaces, Women friendly Spaces?

- What do you do to make sure that girls are safe in reaching the school and in the school?

# Annex D	Proposed field-mission activities

A. Field-level: visits to EiE, CPiE and GBV-related activities in PoC/camp and static programmes

- Activities including in each case:

- Discussion with UNICEF field staff

- Discussion with implementing partners

- Discussion with community mobilisers and outreach workers

- Discussion with cooperating partners (including UN, cluster and GoSS as appropriate)

- Focus group discussions (FGDs) with community members

- Informal conversations (as appropriate) with children and their parents at programme sites

- Attendance (if possible) at relevant coordination meetings

Site visits likely to include:

- PoCs and camps for internally displaced people

- Schools and temporary learning spaces

- Child Friendly Spaces

- Community meeting places

- Partner and government offices

B.	At Juba level:

- Key informant interviews (UNICEF and external)

- Juba PoC / UNMISS visit

Key informants to include:

UNICEF

- Rep/ Dep-Rep

- CP and Education section chiefs and relevant staff (given emergency focus)

- C4D, SPPME, Communications and IM, Field Office Chiefs, Head of Field operations & IRRM, Resource mobilisation, Supply/logistics, gender specialist

External

- Donors: USAID, ECHO, DfID, [and if time allows: CIDA, Danida, Sida, Norway?]

- Relevant GoSS Ministries: Education, Social Affairs

- UNMISS: civilian protection, MRM

- UNHCR as Protection Cluster lead, NRC co-lead

- UNFPA leads on GBV, child marriage etc. IRC co-leads

- UNOCHA re coordination and civilian protection

- Save the Children on CPiE, EiE; and as co-lead on CP

- Other key implementing partners on CPiE, EiE, GBV (not repeating inception meetings)

Plus:

Attendance if possible at relevant Cluster/sub-cluster meetings (Protection, Education)

Attendance if possible at HCT meeting

| Child Protection Programme Components | Suggested field visit activities | Priority |
| --- | --- | --- |
| Family tracing and reunification | 1. FTR pathways: KII with at least 3 implementing partners FGD with community members 2.Alternative care system: visit and KII with implementing partners | *** * |
| Psychosocial support | 1. Visit to examples of Community based PSS (CFSs?) and focused PSS in PoC and rural areas; static and mobile, for children and adolescents, implemented by 2 national and 2 international partners KII or FGD with implementing partners field staff 2. Examples of integration of PSS in education if any FGD with Teachers and parents | *** *** *** *** |
| Mine Risk Education | 1. Visit to example of MRE in CFSs (?) 2.Visit to example of MRE sessions at community level FGD with community members 3.Visit to example of MRE integrated in the Education programme FGD with Teachers and parents | * ** *** |
| GBV prevention | 1. Visit to Safe spaces in PoC and rural areas implemented by 2 national and 2 international partners KII or FGD with implementing partners field staff 2.Other risk mitigation initiatives (to be discussed with SSCO) 3.Examples of integration of GBV prevention in Education, PSS and other sectors KII or FGD with implementing partners field staff FGD with community members, Teachers and parents | *** *** *** *** *** *** |
| GBV response | 1.Case Management System: KII or FGD with implementing partners field staff FGD with community members, Teachers and parents 2.Other examples of GBV response suggested by SSCO | *** *** *** |
| CAFAAG | 1.Reintegration programme (examples to be selected by SSCO) KII or FGD with implementing partners field staff | *** |
| Community Care programme /CB Child protection | 1.Comunity based child protection mechanisms FGD with community members, Teachers, parents and adolescents 2.Other examples of CBCP suggested by SSCO | *** ** |

| Education Programme Components | Suggested field visit activities | Priority |
| --- | --- | --- |
| Distribution of school materials (school-in-a-box, recreation kits, blackboards) | Visit (observation)/ informal conversations in the sites were the material were distributed. Interview or FGD with implementing partners and with teachers and principals | *** ** |
| Teacher Training in EiE | Interview or FGD with implementing partners FGD with teachers and principals | ** *** |
| Parent-Teacher Association and school management committee members training to support EiE | Interview or FGD with implementing partners FGD with PTA and SMC | ** *** |
| Peace clubs / Sports for peace | Visit (observation)/ informal conversations in the sites were these activities are taking place. Interview or FGD with implementing partners / with teachers and principals / community mobilisers and outreach workers FGD with children/ parents | *** ** ** |
| School construction/ rehabilitation | Visit (observation)/ informal conversations in the sites were the School construction/ rehabilitation took place Interview or FGD with implementing partners and with teachers and principals | *** ** |
| Temporary learning spaces | Visit (observation)/ informal conversations in the sites were these activities are taking place Interview or FGD with implementing partners and with teachers FGD with students | *** ** ** |
| Children and adolescents (aged 3-18) with access to EiE | Visit (observation)/ informal conversations in the sites were these activities are taking place Interview or FGD with implementing partners and with teachers | *** *** |
| Teachers incentives | Interview or FGD with implementing partners and with teachers | ** |

# Annex E	Problem statements & implied theories of change

UNICEF South Sudan programme: Education in Emergencies

Problem Statement and Implied Theory of Change

Access to education

UNICEF RESPONSE

KEY CAUSAL FACTORS

OUTCOMES OF CONCERN

PROBLEM AREA

GPE work on infrastructure, capacity building, curriculum development (recovery/development)

Back to Learning initiative since 2015:

- Addresses the most urgent education needs in conflict-affected/insecure states

- Attempts to bridge humanitarian-development divide

- School and learning space provision

- Accelerated learning programme (ALP) for children who have missed schooling

- Focus on girls’ education

Education in Emergencies programme (EEP)

- Integrated with BTL

- Focus on children affected by severe humanitarian crises gaining access to quality education in a safe & protective environment

- Capacity building (in collaboration with GPE)

Integrated Essential Emergency Education Services (IEES) programme (from 2018):

- Builds on EEP

- Designed to increase retention of the most vulnerable boys and girls in schools by providing sustained learning opportunities and aims to improve the learning outcomes, level of protection, resilience and recovery of girls and boys living amidst violent conflict

- Shortage of qualified teachers: nearly 60% of teachers are untrained

- Major shortages of teaching/learning materials

- Limited teacher incentives

- Limited NGO capacity to deliver quality services

Systemic:

- Low GoSS investment

- Lack of infrastructure

- Shortage of teachers

- Teachers paid late, too little or not at all

Conflict-related:

- Damaged, looted or occupied schools

- Insecurity for staff /students

- School closures

- Population displacement

Economic and social:

- Weakening household economies

- Gender roles and expectations

- Related coping mechs

- Diminishing education service provision over evaluation period

- > 2 million primary-school aged children estimated to be out of school (2017)

- Drop out rate over 10%. Close to 1.3 million at risk of dropping out

- > 60 percent of primary- aged girls not in school

- Rise in numbers of unsupervised children => rise in protection concerns and harmful coping mechanisms.

Quality of education

Most children attending primary school do not achieve foundational literacy, numeracy and life skills

PROBLEM AREA

UNICEF RESPONSE

KEY CAUSAL FACTORS

OUTCOMES OF CONCERN

UNICEF South Sudan programme: Protection

Problem Statement and Implied Theory of Change

- Sexual and gender-based violence

- Child abduction

- Non-attendance at school (through fear)

- Threat posed by landmines and UXO

Violence against children and women

- Denial of access to humanitarian assistance by parties to the conflict

- Lack of protection from effects of conflict and crime

- Risks associated with normal activities

- Programming that is not risk-informed

- Psychosocial support:  dedicated psychosocial care to children with critical child protection challenges

- Community based child protection: strengthening community support groups to enhance child protection

- Family tracing and reunification of separated & unaccompanied children

- Release and reintegration of children associated with armed groups and armed forces (CAFAAG)

- Mine Risk Education: supporting education to protect children from landmines/explosive remnants of war

- Monitoring & Reporting Mechanism on grave violation (MRM)

- GBV mitigation: supporting risk mitigation efforts across UNICEF sectors and UNICEF-led clusters

- Clinical management of rape (CMR)

- Communities Care programme: promotes gender equitable social norms to prevent GBV & support survivors

Systemic:

- Absence of rule of law and related protections

- Rise in numbers of children unsupervised or out of school => increase in vulnerability & harmful coping mechanisms.

Conflict-related:

- Deliberate targeting of children by parties to conflict

- Continued prevalence of land mines and UXO

Economic and social:

- Inter-tribal animosities

- Weakening household economies

- Gender roles and expectations

- Related coping mechs

- Child recruitment

- Child marriage /forced marriage

- Forced displacement

Coercion of children and families

General protection concerns

- Deliberate deprivation of means of subsistence

- Exposure to risk of violence from conduct of conflict or from criminal activity

- Related fear and constraints on normal activity

- UNICEF’s own programme may expose children and their families to danger

For the purposes of this inception report, ‘the evaluation’ refers to Part Two of the overall evaluation unless otherwise indicated.

See https://reliefweb.int/report/south-sudan/report-commission-human-rights-south-sudan-ahrc37crp2

See for example https://www.unicef.org/southsudan/media_21563.html

UN Security Council Resolution 2304 (August 2016).

UNICEF South Sudan Country Office Report 2017

UNICEF HAC 2018, citing the IPC classification for November 2017

See for example https://www.unicef.org/southsudan/media_21563.html

Monitoring and Reporting Mechanism (MRM) – South Sudan Country Report, December 2017: Available: https://www.unicef.org/southsudan/MRM_brief_December_2017_040218.pdf

Global Initiative on Out-of-school Children: South Sudan Country Study, May 2018 (available:  http://uis.unesco.org/sites/default/files/documents/global-initiative-out-of-school-children-south-sudan-country-study.pdf )

ibid…

UNICEF Country Programme Document (CPD 2019-2021), presented to UNICEF Executive Board September 2018

ibid

UNICEF South Sudan, National Budget Brief 2017/2018, Republic of South Sudan.  Available: https://www.unicef.org/esaro/UNICEF_South_Sudan_--_2017_--_National_Budget_Brief.pdf

The Revitalized Agreement on the Resolution of the Conflict in the Republic of South Sudan (R-ARCSS)

2018 Report of the UN Commission on Human Rights in South Sudan (link above)

The 2018 Appeal targeted 6.5 million people with an overall appeal of US$1.7 billion, of which only around 60% was funded (Source: OCHA Financial Tracking Service, accessed 1st January 2019)

Figures as set out in the 2019 HAC. The related funding requirement is just under USD 180 million. The request for funds for the health component is US$15.5 million (58 per cent) lower compared with 2018. The HAC explains this as being due to ‘a reduction in the target for emergency interventions as part of a move towards development programming’.

UNICEF is the GPE Grant Agent for South Sudan – see: https://www.unicef.org/southsudan/Education_Briefing_Note_-_May_2018.pdf

UNICEF Strategic Moment of Reflection, October 2017

The Centrality of Protection in Humanitarian Action - Statement by the Inter Agency Standing Committee (IASC) Principals, 17 December 2013

March 2008. See http://www.unevaluation.org/document/detail/102. Clearance for the proposed protocols and questions for the field component (partner interviews and community-level focus group discussions) will be sought through UNICEF’s ethical review process.

Specific questions will be firmed up during the inception phase of the evaluation process

UNICEF Country Programme Document (CPD 2019-2021), presented to the UNICEF Executive Board in September 2018

See https://reliefweb.int/report/south-sudan/report-commission-human-rights-south-sudan-ahrc37crp2

Ibid

https://www.unicef.org/stories/making-south-sudans-families-whole-again

United Nations Mission in South Sudan (UNMISS) POC Update (21.01.2019 updated): See: https://unmiss.unmissions.org/sites/default/files/poc_sites_update_227_-_21_january_2019.pdf

In June 2017, the HCT established some suggested thresholds and consequences for local violations against aid workers and assets. See South Sudan HCT: Consequences for violations against humanitarian workers & assets. Position paper, endorsed 8 June 2017

A recent study by OCHA (2017) documented a range of bureaucratic access impediments (BAI) to humanitarian interventions in South Sudan. Restriction or denials of movement were perceived to have the greatest impact on response, despite being encountered less frequently than other impediments.

All of the above constraints are compounded by the sheer logistical challenges of delivering aid in South Sudan, particularly during the rainy season when roads may become impassable for months on end. This also adds greatly to the cost of delivery, including the cost of using transport alternatives like planes and helicopters.

OCHA South Sudan 2018 South Sudan Humanitarian Needs Overview: https://reliefweb.int/report/south-sudan/2018-south-sudan-humanitarian-needs-overview

OCHA, September 2017

See for example https://www.unicef.org/southsudan/media_21563.html

Monitoring and Reporting Mechanism (MRM) – South Sudan Country Report, December 2017: Available: https://www.unicef.org/southsudan/MRM_brief_December_2017_040218.pdf

UNICEF Country Programme Document, 2016.

CPD….

Japan Proposal, also see Violence Begets Violence, Justice Africa, May 2016.

Humanitarian Needs Overview 2016.

# Office of the Special Representative of the Secretary-General on Sexual Violence in Conflict, 18 December 2018

Global Initiative on Out-of-school Children: South Sudan Country Study, May 2018 (available:  http://uis.unesco.org/sites/default/files/documents/global-initiative-out-of-school-children-south-sudan-country-study.pdf )

ibid…

UNICEF Country Programme Document (CPD 2019-2021), presented to the UNICEF Executive Board in September 2018

ibid

UNICEF South Sudan, National Budget Brief 2017/2018, Republic of South Sudan.  Available: https://www.unicef.org/esaro/UNICEF_South_Sudan_--_2017_--_National_Budget_Brief.pdf

South Sudan Country Office Annual Report, 2017

https://www.unicef.org/southsudan/media_21183.html

UNICEF is the GPE Grant Agent for South Sudan – see: https://www.unicef.org/southsudan/Education_Briefing_Note_-_May_2018.pdf

UNICEF Strategic Moment of Reflection, October 2017

The Centrality of Protection in Humanitarian Action - Statement by the Inter Agency Standing Committee (IASC) Principals, 17 December 2013

“Rights Up Front” Detailed Action Plan – see: https://interagencystandingcommittee.org/system/files/detailed_hruf_plan_of_action.pdf

http://www.globalr2p.org/about_r2p

L3 evaluations are included in the plan for global evaluations (2018–2021), which makes provision for evaluating Level 3 emergencies from the corporate level, given the substantial investments being made by UNICEF in humanitarian action.

Protection Principles: http://www.spherehandbook.org/en/how-to-use-this-chapter-5/

It should be noted that SSCO has undertaken numerous reviews, assessments, surveys and some evaluations.  A number of evaluations are also being planned/scheduled for the next year, and these will need to be considered to maximise efficiencies and reduce duplications.

UNEG Norms and Standards for Evaluation, 2016. Available at: http://www.unevaluation.org/document/detail/1914

UNEG Ethical Guidelines, 2008. Available at: http://www.unevaluation.org/document/detail/102

UNICEF Procedure for Ethical Standards in Research, Evaluation, Data Collection and Analysis, 2015. https://www.unicef.org/supply/files/ATTACHMENT_IV-UNICEF_Procedure_for_Ethical_Standards.PDF

See https://www.unicef-irc.org/research/278/