Afya Bora ya Mama na Mtoto Project (2015-2018)

Final Evaluation

Final Inception Report

21 November 2019

# Table of Contents

Table of Contents	i

List of Figures	ii

List of Tables	ii

Acronyms	iii

1	Introduction	1

2	Background	1

2.1	Project Context	1

2.2	Project Description	1

2.2.1	Project Theory of Change	3

2.3	Evaluation Purpose and Objectives	7

2.3.1	Evaluation objectives	7

2.4	Evaluation Scope	7

2.4.1	Evaluation framework	8

2.4.1.1	Relevance	8

2.4.1.2	Equity and Gender	9

2.4.1.3	Effectiveness	10

2.4.1.4	Efficiency	12

2.4.1.5	Sustainability	12

2.4.2	Evaluability assessment	13

2.5	Audience of the Evaluation and Uses	17

3	Approach and Methodology	19

3.1	Approach	19

3.1.1	Evaluation design	19

3.1.2	Evaluation guidance	19

3.1.3	Evaluation principles	19

3.1.4	Ethical Consideration	20

3.2	Methodology	21

3.2.1	Quantitative data collection	21

3.2.1.1	Data sources	21

3.2.1.2	Tools and Techniques	21

3.2.2	Qualitative data collection	21

3.2.2.1	Data sources	22

3.2.2.2	Tools and Techniques	23

3.2.3	Sampling strategy and sample sizes	24

3.2.3.1	Inclusion and exclusion criteria	26

3.2.4	Data collection	27

3.2.4.1	Quantitative data	27

3.2.4.2	Qualitative data	27

3.2.5	Data management and analysis	28

4	Work Plan	29

4.1	Inception	29

4.2	Data Collection	29

4.3	Reporting and Validation	29

5	Quality Assurance and Risk Management	30

5.1	Quality Assurance Plan	30

5.1.1	Evaluation management	30

5.2	Potential Risks and management plan	31

5.3	Roles and Responsibilities of Key Stakeholders	31

5.4	Evaluation Team	32

Annexes	34

Annex 1: Terms of Reference	34

Annex 2: Evaluation Framework	35

Annex 3: List of People Consulted during the inception mission from [..] to […./October 2019]	44

Annex 4: Full List of Stakeholders to be Interviewed	45

Annex 5: Data Collection Tools	46

Annex 5.1: Quantitative Data Extraction Tools	46

Annex 5.2: Qualitative Tools	46

Annex 6: Key Dates for the Evaluation	47

Annex 7: Detailed Field Work Itinerary	49

## List of Figures

Figure 1: Anticipated results of the Afya Bora ya Mama na Mtoto project	2

Figure 2: Chronology of implementation of major activities of the project	3

Figure 3: Project problem tree	5

Figure 4: Theory of Change	6

## List of Tables

Table 1: Assumptions of the Afya Bora TOC	4

Table 2: Evaluation questions	7

Table 3: Summary of evaluation issues under relevance	9

Table 4: Summary of evaluation issues under equity and gender focus	10

Table 5: Summary of issues under effectiveness	12

Table 6: Summary of issues under sustainability	13

Table 7: Project Indicators that require redefinition and/or clear source of data	14

Table 8: Project Indicators with identifiable data sources	15

Table 9: Primary audience of the evaluation	17

Table 10: List of respondents and sample size	25

Table 11: Risk management matrix	30

Table 12: Stakeholder roles and responsibilities	31

Table 13: Evaluation team and roles and responsibilities	31

# Acronyms

| ANC | Antenatal Care |
| --- | --- |
| BEmONC | Basic Emergency Obstetrics Care |
| CBOs | Community Based Organisations |
| CEmONC | Comprehensive Emergency Obstetrics Care |
| CHMT | Council Health Management Team |
| CHV | Community Health Volunteer |
| DFATD | Department of Foreign Affairs Trade and Development |
| EmONC | Emergency Obstetrics Care |
| ERG | Evaluation Reference Group |
| FANC | Focussed Antenatal Care |
| GAC | Global Affairs Canada |
| GEROS | Global Evaluation Report Oversight System |
| HCW | Health Care Worker |
| HMIS | Health Management Information System |
| HPU | Health promotion unit |
| HRH | Human Resources for Health |
| MMR | Maternal Mortality Ratio |
| MNCH | Maternal New-born and Child Health |
| MOH | Ministry of Health |
| NGOs | Non-Governmental Organisations |
| OECD | Organisation for Economic Cooperation and Development |
| PNC | Post Natal Care |
| RMNCAH | Reproductive, Maternal New-born and Child and Adolescent Health |
| RMNCH | Reproductive, Maternal New-born and Child Health |
| SBCC | Social behaviour change communication |
| SDGs | Sustainable Development Goals |
| U5 | Children under the age of 5 years |
| UNEG | United Nations Evaluation Group |
| UNFPA | United Nations Population Fund |
| UNICEF | United Nations Children’s Fund |
| WASH | Water, Sanitation and Hygiene |
| ZNBTS | Zanzibar Blood Transfusion Service |
| ZSGRP II | Zanzibar Strategy for Growth and Reduction of Poverty ( |

# Introduction

This report presents the first deliverable of the Final Evaluation of Afya Bora ya Mama na Mtoto Project (2015-2019). It provides details of the evaluation team’s understanding of the project, summary of improvements made to enhance its evaluability, the proposed approach and methodology, work plan and other mechanisms to manage risk and ensure quality in the process and outputs. We use Afya Bora throughout the report as a short form of the full project name.

# Background

## Project Context

Prior to the initiation of the Afya Bora project in 2015 the maternal and child health status in Zanzibar was facing several challenges. These included but not limited to: 1) low contraceptive prevalence rate of 12.4%; 2) high family planning unmet need which stood at 35%; 3) the Maternal Mortality Ratio (MMR) record was 276 deaths per 100,000 live births in 2016; 4) and the neonatal death rate of 28 per 1000 live births (MOH, 2016). The MOH and project reports show that only 27.7 % of pregnant women made 4 visits in 2015. The under-five mortality was 56 per 1,000 live births in 2015 (TDHS 2015). Other indices showed that malnutrition –stunting in particular - a major underlying cause of child mortality was at 24% in 2015.

The significant rate of decline of the Infant Mortality Rate (IMR) had been observed but not with MMR. This was revealed during the review of the then Zanzibar Health Strategic Plan II (ZHRSP II) which was coming to an end in 2014. Other observations were a weak human resource base in terms of quantity and quality of skilled staff. The proportion of skilled health personnel providing quality essential health care package services with particular reference to primary level stood at 60%. Improper allocation, poor retention and motivation, inadequate and malfunctioning of the referral system and weak District Health Management Teams (DHMTs). However, 95% of the population lived within 5km to the nearest health facility.

The Revolutionary Government of Zanzibar is indeed reflected full commitment to address all the observed problems and in particular accelerate the reduction of Maternal, New-born and Child morbidity and mortality in Zanzibar as evidenced through its 2011 health policy, strategies and other documents that include the Zanzibar;

- 2011 health policy,

- Strategy for Growth and Reduction of Poverty (ZSGRP II) 2010-2015,

- Health Sector Strategic Plan III,

- Road Map Strategic Plan to Accelerate the Reduction of Maternal, New-born and Child Death in Zanzibar, 2008-2015 and One Plan.

This commitment is also strongly expressed in the  Zanzibar Reproductive, Maternal, New-born, Child and Adolescent Health Strategic Plan (2019-2023) which was recently prepared in recognition of the achievements and challenges faced in that endeavour in the past. On the other hand this is also supported by its partners including UNICEF and UNFPA. It is acknowledged that partners such as UNICEF and UNFPA have helped reduce mortality all over the world by working to reach the most vulnerable children and mothers respectively everywhere in the world of which Zanzibar is not an exception. The Afya Bora ya Mama na Mtoto (“A better health for mother and child”) project, launched in 2015, aimed at further improving the health and wellbeing of mothers and children. It targeted a total population of 1,441,183; an under 5 population of 236,944; 328,494 adolescents (10-19) and 371,453 women aged 15-49.

## Project Description

The Afya Bora ya Mama na Mtoto project was launched in 2015 and is designed to address maternal and child mortality, and in addition, improve health and overall well-being for mothers and children in Zanzibar. The project targets 75,000 pregnant women, 130,000 mothers/caregivers of children 0-59 months, 260,000 children 0-59 months and 130,000 adolescents covering all areas of Zanzibar. The project is funded by the Government of Canada to the tune of 15 million Canadian dollars. It is a UN joint programme between UNICEF/UNFPA and the Government of Zanzibar with Save the Children as the contracted NGO to facilitate implementation of the community health component. Figure 1 provides the results chain of project as depicted from the project design document. The project addresses health systems management and coordination, quality health service delivery for RMNCAH services and high quality nutrition interventions. The main outcome of the project is improved health and wellbeing of women and children in Zanzibar. This supported by two overarching intermediate outcomes that seek to:

- strengthen and ensure the health system delivers equitable and integrated health services including improvements in the referral system, and

- increase coverage of quality emergency obstetrics, new-born and child health services, including high impact nutrition interventions.

Coverage is increased ensuring strategic facilities are “service ready” (offering quality new-born, child and 24/7 EmONC services including emergency referral) and strengthening community health systems to promote RMNCH Care-seeking behaviour and positive health, nutrition and WASH practices.

Figure 1: Anticipated results of the Afya Bora ya Mama na Mtoto project

Source: Project Proposal to Canada - Department of Foreign Affairs, Trade and Development

The project has been implemented from March 2015 to October 2019. Key interventions and the chronology of implementation is presented in Figure 2. The chronology of implementation has great importance when evaluation of project performance is undertaken. For example, it may seem interventions under Immediate outcome 1.2 above may have been implemented in the last year of the project, therefore, the extent of evaluation of performance will need to take into account this time lag between implementation and evaluation. Secondly, a proportion of health workers have just completed their studies and are in post and therefore have had little time to demonstrate their capacity.

Figure 2: Chronology of implementation of major activities of the project

Source: Annual Progress Reports

### Project Theory of Change

A theory of change (TOC) was not part of the project design document. To fully map out the change trajectory required to address maternal, neonatal and child mortality in Zanzibar, the evaluation team therefore undertook a reconstruction of the TOC. The process began with the development of a Problem Tree to understand the core problem that the programme wanted to address and identifying the immediate and secondary causal factors. It included literature review, scoping interviews with key implementers and validation with the project’s stakeholders in Zanzibar during an inception workshop. Figure 3 provides an illustration of the problem tree.  Both supply and demand side constraints were observed to lead to the situation of high maternal, newborn and child mortality. Contextual factors that include underfunding, a poor Human Resources for Health (HRH) performance management system, weaknesses in planning and delivery of social behaviour change communication (SBCC) and poor linkage between community health system and the district health system were identified as the main secondary causes. On the demand side, limited support for community health volunteers, and inadequate attention to SBCC leads to continuation of:

- limited knowledge among families and communities on appropriate practices around maternal, new-born and child health and nutrition and WASH; and

- patriarchal and cultural system that relegates women’s role in decisions on maternal care and delivery and thus limiting their health seeking behaviour.

This in turn results in low maternal health seeking behaviour, poor WASH and child nutrition/feeding practices, and low family planning usage.  High cost of care especially when referral is involved, contributes to these outcomes leading to increased acute malnutrition and WASH related morbidity among children and birth complications which in turn result in child maternal and neonatal deaths respectively.

On the supply side, underfunding of RMNCH and a weak HRH performance management system all contribute to:

- Limited numbers, quality and low motivation and productivity of health staff;

- lack of appropriate equipment and maintenance and inadequate infrastructure;

- inadequate planning, management of RMNCH;

- lack of accurate data and information for evidence-based action; and

- frequent stock-outs of essential medicines and commodities.

Because of the lack of resources at facility level it was noted, in the Afya Bora project document, that facilities exhibited poor level and quality of care as per recommended clinical standards as well as poor and inadequate management of maternal and new-born complications. This was contributing to high rates of birth complications and obstetrics emergencies and maternal, neonatal and child deaths.

Based on this the Theory of Change for Afya Bora was determined as:

“IF community health services are strengthened with enhanced linkages with health facilities and the district health management system and that: 1) availability of appropriate equipment and supplies; 2) adequate and quality human resources in health facilities; 3) an effective information management system for RMNCH are put in place with all of this supported by government’s increased resource allocation for RMNCH THEN childcare will be improved and demand for RMNCH services increased, leading to lower birth complications and maternal, newborn and child deaths.

The TOC is presented in Figure 4.

Assumptions underpinning the TOC are presented in Table 1.

Table 1: Assumptions of the Afya Bora TOC

| Assumption | Effect |
| --- | --- |
| Demonstration and implementation of best practices will lead to eventual government ownership | Government increases resources for RMNCH to support continuation services thereby enhancing the project effect |
| The right calibre of health professionals are trained and 1) have sufficient institutional support to facilitate full utilisation of new skills and knowledge gained, and 2) will be and remain in post during the implementation period. | Will allow health staff to implement their new knowledge and skills efficiently and effectively. |
| CHVs will remain highly motivated and in post and deliver the full package of services – RMNCAH, WASH, and Nutrition. | Community mobilisation is sustained giving rise to changing attitudes and appropriate health seeking behaviour. |

Understanding of the TOC enhances the evaluation team’s assessment of the validity of Afya Bora’s project design and what changes may be required for a future similar project.  It also enables the team to fully understand the broadness of the project’s potential results, both negative and positive.

Figure 3: Project problem tree

Figure 4: Theory of Change

## Evaluation Purpose and Objectives

The primary focus of the evaluation is to generate substantive evidence and lessons learned on the relevance, effectiveness, efficiency, sustainability, gender and equity focus of the Afya Bora project. Further the evaluation findings and recommendations will be used to strengthen future anticipated project design, to inform the nation-wide scaling up of the project, the end-term review of Zanzibar Health Sector Strategic Plan (2013/14-2018/19) and the 2020 mid-term review of Zanzibar One Reproductive, Maternal, Newborn, Child and Adolescent Reproductive Health Strategic Plan (2018-2022).for the 2020 mid-term review of Zanzibar One Reproductive, Maternal, Newborn, Child and Adolescent Reproductive Health Strategic Plan (2018-2022).

### Evaluation objectives

The specific objectives of the evaluation are to:

- Determine the relevance, effectiveness, efficiency, sustainability, gender and equity focus of  the Afya Bora ya Mama na Mtoto project;

- Assess the integration of critical organizational principles and approaches, namely equity and gender in project planning, implementation, and monitoring.

- Document good practice, lessons learned and provide actionable recommendations for improved future anticipated project design, advocacy for scaling up as well as for the improvement of MoH strategies, MNCAH and Reproductive Health Plan of Zanzibar.

## Evaluation Scope

Evaluation criteria and Questions: Table 2 provides the questions to be answered by the evaluation as provided in the Terms of Reference. They are organised according to four OECD evaluation criteria of: relevance, effectiveness, efficiency, and sustainability. Impact was left out of the evaluation, as based on the duration of actual implementation, impact level results would be wide spread at this time. A fifth criterion of equity and gender focus, was added to the evaluation to interrogate specific issues on equity and gender and respond to SDGs principles.

Table 2: Evaluation questions

| Evaluation Criterion | Questions |
| --- | --- |
| Relevance | - To what extent are the project design, results and implementation strategies relevant to the national and local context, strategies, policies and programmes? |
| Effectiveness | - To what extent have the project’s objectives and intended results been achieved? - What are the factors that facilitate or inhibit the achievement of the project’s objectives and outcomes? - Which project activities had more significance to contribute to increased demand, coverage and uptake of quality emergency obstetric care, new-born and child health services, including high impact nutrition interventions? - To what extent has the project addressed accountability and ownership of implementing partners? - How adequate have UNICEF’s support been to the project, including from the perspectives of different partners at national and subnational levels? |
| Efficiency | - To what extent have the project management and coordination been efficient? |
| Sustainability | - What are the enabling as well as constraining factors that influence the sustainability of the project? - What could or should be done differently in future replication and scaling up of the project? - How will good practices generated from the project be brought in and sustained at both national and sub-national levels? - What are the good practices and key conditions for national scaling up of the project? |
| Equity and gender focus | - To what extent have the project design and interventions taken into account the most vulnerable and hard to reach populations? - To what extent have sex and disaggregated data been collected, monitored and analysed to inform the project? |

Evaluation period: the evaluation covers the period from inception in 2015 to project end on 30 November 2019. However, for data related to the Health Management Information System (HMIS), baseline will be for the period 1 January to 30 September 2019 while the end line will be for the sum of the period January 2018 to 30 September 2019. Selection of 9 months of the calendar year instead of the 12 as per the Ministry of Health’s reporting cycle, is due to the evaluation being under taken in November which precludes a full cycle assessment.  See further discussion under the evaluability assessment.

The evaluation covers both Unguja and Pemba islands targeted by the project.

### Evaluation framework

Based on evaluation questions in the TOR and presented in Table 2, an evaluation framework was developed presented in Annex 2. The evaluation framework has guided the development of tools for the evaluation and provides the lens through which the project will be evaluated. A summary of the evaluation framework is presented below.

#### Relevance

Under relevance the evaluation will assess the extent to which the programme is aligned to the national, local contexts strategies, policies and programmes. In this regard the evaluation will determine the extent to which the project is aligned to the: Zanzibar Health Sector Strategic Plan (2013/14– 2018/19), the Road Map to Accelerate Reduction in Maternal, New-born and Child Mortality in Zanzibar (2015-2018), the Zanzibar One RMNCAH Strategic Plan (2018-2022), UNDAP II and MKUZA III outcomes. At the local level, the evaluation will assess the extent to which the project was aligned to local government plans and programmes.

In addition to assessing relevance to local context, the evaluation will determine how the project responds to global priorities of UNICEF/UNFPA and GAC through the DFTAD priorities. For UNICEF the evaluation will determine the extent to which the project is aligned to UNICEF’s Global Strategy for Health (2016-2030) especially the two goals of:

1) End preventable maternal, new-born and child deaths; and

2) Promote the health and development of all children.

Focus will be put on how the programme addresses the five result areas for MNCH planning and programming: Health, Nutrition, HIV and AIDS, WASH and Social inclusion.

In relation to relevance to DFTAD’s priority themes for development, the evaluation will assess the extent to which the project is aligned to the theme of Securing the Future of Children and Youth with particular attention to two focus areas of “increasing child survival including maternal health” and “increasing safe and secure futures for children and youth”.  The evaluation will also address the extent to which the project responds to the Muskoka Initiative, a global effort being led by Canada to improve maternal, new-born, and child health.  This initiative involves multiple national and international partners and focuses on the following three “integrated” paths:

- Strengthening health systems to improve service delivery;

- Reducing the burden of disease; and

- Improving Nutrition.

Additional criteria to be reviewed will include the project’s attention to equity, gender, adolescents and disability. Table 3 provides the issues to be addressed under relevance.

Table 3: Summary of evaluation issues under relevance

| Evaluation Questions | Priority sub-questions/issues |
| --- | --- |
| To what extent are the project design, results and implementation strategies relevant to the national and local context, strategies, policies and programmes? | - Alignment to national priorities (policies and strategies) - Alignment to global initiatives including the five areas for MNCH - Alignment to UNFPA global priorities on RMNCAH. - Alignment to Government of Canada global Priorities - Flexibility of design to accommodate emerging issues e.g. decentralisation, new policies, new issues, SRH - Validity of assumptions for the Theory of Change - Target groups in relation to equity and drivers of maternal, neonatal and child mortality |

#### Equity and Gender

Equity will be assessed at three levels: The first level will be determining the criteria used to select facilities and whether these provided the project the greatest opportunity to address maternal and child deaths.  The second level will be equity in financial investments answering the question the  investments go where they were needed most. The third level concerns outreach to communities, determining how those in hard to reach areas, living with disabilities, and adolescents are benefiting from the project’s interventions. Gender will be assessed from two perspectives: 1) how gender was mainstreamed in the design of the project and its implementation including to what extent it was grounded on a gender analysis; and 2) how the project collected, monitored and analyzed sex disaggregated data to inform the project.

Table 4 provides the issues to be addressed under equity and gender focus.

Table 4: Summary of evaluation issues under equity and gender focus

| Evaluation Questions | Priority sub-questions/issues |
| --- | --- |
| - To what extent have the project design and interventions taken into account the most vulnerable and hard to reach populations? - To what extent have sex and disaggregated data been collected, monitored and analysed to inform the project? | - Criteria for identification of project areas: - Selection of facilities - Selection of areas for CHVs - Project investments: - Financial resource allocation vis a vis depth of challenge - Coverage and appropriateness/adequacy of support for groups left behind: - Adolescents - Hard to reach areas - Specific minorities - Success and failures in approaches to engage men in RMNCAH - Extent of use of sex disaggregated data - Extent gender analysis was a premise for investments under Afya Bora including (renovations, training, community mobilisation etc)? |

#### Effectiveness

The assessment of effectiveness will determine the extent to which the project’s objectives were achieved. In this assessment the evaluation team will be guided by the project’s log frame/results framework indicators for the outcome, intermediate outcome and immediate outcome results (as demonstrated earlier in the TOC and the results chain). Data to assess project achievement on set targets will be obtained from secondary sources including: health management information system for Zanzibar; and monitoring reports for the project. Data from the health information management system will inform indicators on Intermediate outcomes 1 and 2 and the outcome indicators. Only indicators that can be measured by data from the health management system will be measured (see section on Evaluability assessment).

In addition to determining achievement of the project targets, the TOR require the evaluation to investigate factors that facilitated or inhibited the achievement of the project’s objectives. First, the evaluation team will carry out an in-depth qualitative assessment of the individual, community, organisational and institutional factors that supported achievement of these results. Second, using qualitative primary data and literature review, the evaluation will determine the extent to which differences in implementation (if any) had a profound influence on the success of the project at different sites.

There is the question, “Which project activities had more significance to contribute to increased demand, coverage and uptake of quality emergency obstetric care, new-born and child health services, including high impact nutrition interventions?”. The evaluation will assess how each intervention contributed to results through a “fit for purpose” contribution analysis. In this analysis the evaluation team will map contribution of each activity to the immediate outcomes of the project and determine, in interviews with various project stakeholders, the relative contribution of these to observed results. This assessment will not be limited to interventions but will also seek to understand approaches to project implementation that had an influence in the observed results. This is a particularly important issue on lessons and design of a future project.

Ownership and accountability will be assessed in various ways. Stakeholder leadership and participation and initiatives to continue with project benefits will provide indicators for ownership. Intangible indicators such as motivation for project implementation will also be considered. The evaluation will determine provisions in the project implementation approach that enhance ownership. In assessing accountability (or responsibility for project performance) the evaluation will measure platforms and systems put in place by the project for shared accountability for project performance (Government, UNFPA and Save the Children). How this shared accountability worked in practice will be measured through determining how different stakeholders have undertaken their roles, and put in place mechanisms to ensure anticipated project performance is achieved.

Lastly, the adequacy of UNICEF’s support to the project will be measured in technical and financial support to project partners; how UNICEF utilised its global and regional experience to enhance project performance; coordination role and partner management. Perspectives of partners at national and sub-national levels will be particularly important in this assessment.

Table 5 lists the issues guiding the evaluation of effectiveness.

Table 5: Summary of issues under effectiveness

| Evaluation Questions | Priority sub-questions/issues |
| --- | --- |
| - To what extent have the project’s objectives and intended results been achieved? - What are the factors that facilitate or inhibit the achievement of the project’s objectives and outcomes? - Which project activities had more significance to contribute to increased demand, coverage and uptake of quality emergency obstetric care, new-born and child health services, including high impact nutrition interventions? - To what extent has the project addressed accountability and ownership of implementing partners? - How adequate have UNICEF’s support been to the project, including from the perspectives of different partners at national and subnational levels? | - Performance of log frame indicators - Key drivers and barriers of performance in Afya Bora: - Project design including capacity development approach (transformative vis a vis functional) - Project management - Implementer motivation - Extent of: - service referral by CHVs (RMNCH, Nutrition etc) - RMNCH services provided at facilities - Community perceptions on the quality of health care provided at health facilities - Contribution of each project component to desired results as well as combination of interventions - Mechanism for performance measurement and its effectiveness - Measures to ensure ownership including effectiveness - through demonstration of ownership - Adequacy and quality of management, and technical support from UNICEF |

#### Efficiency

In evaluation efficiency the TOR requires the evaluation to answer the question: “To what extent have the project management and coordination been efficient?”.  This will be assessed by investigating the following issues:

- Level of functionality and effectiveness of national and subnational coordination platforms;

- Staffing levels vis a vis the project’s scale and objectives;

- Platforms that exist for lessons sharing between partners and the benefits accruing;

- Monitoring systems put in place, their adequacy to provide information required for project management and how information from the monitoring system was used for project steering at all levels;

- Key drivers and constraints to coherence and coordination

#### Sustainability

Evaluation of sustainability will assess sustainability of interventions and benefits accruing from the interventions in the short medium and long term. Factors that support or inhibit sustainability will be assessed at the individual, organisational and institutional levels. Scalability of the project will also be a critical factor for determining sustainability in this respect, the evaluation will review the Financial and Technical feasibility for scalability.  The evaluation will also make recommendations on the key conditions for national scale up.

Table 6 provides a list of issues that form the evaluation of sustainability.

Table 6: Summary of issues under sustainability

| Evaluation Questions | Priority sub-questions/issues |
| --- | --- |
| What are the enabling as well as constraining factors that influence the sustainability of the project? What could or should be done differently in future replication and scaling up of the project? How will good practices generated from the project be brought in and sustained at both national and sub-national levels? What are the good practices and key conditions for national scaling up of the project? | - What components will be sustained in the: - Short - Medium - Long term - Individual, organisational and institutional factors supporting or constraining sustainability - What is required to support them: - Key assumptions - Provisions being put in place or in planning to support sustainability - Initiatives that can be scaled up: - What makes the initiative different? - What is required to transform them to a national programme? - What supports performance of the initiative? - What could potentially undermine it? |

### Evaluability assessment

Part of the inception period was dedicated to undertaking a rapid evaluability assessment of the project and devising appropriate methods to improve the quality of the evaluation. The rapid evaluability assessment focused on two of the components of an evaluability assessment: evaluability in practice which assesses availability of relevant information for the evaluation and data capacity management systems and evaluability in principle.  The evaluability in principle was enhanced by retrospectively developing the TOC and accompanying assumptions. The main focus of the evaluability assessment was on the evaluability in practice. To achieve this the evaluation team reviewed all the indicators required to inform performance of the project as presented in the log frame. The review resulted in some indicators being changed, removed or alternative proxies being added. Table 7 presents results of this assessment.

Table 7: Project Indicators that require redefinition and/or clear source of data

| Original indicator | Potential data source | Action/Remarks |
| --- | --- | --- |
| Number of youths utilized SRH/FP services | HMIS/DHIS2 Routine disaggregated data | Rephrased to: Number of youths receiving YFSs by type (education, counselling, FP counselling, FP acceptance, STI management; ANC services; PAC) |
| Proportion of health facilities with at least two health providers who have received training on distance learning IMCI and Essential New-born Care | Training reports; Annual reports | The MoH and project partners to compile a list of staff per facility as of October 2019, by training status (in project’s focus areas) |
| Proportion of health facilities conducting maternal and perinatal death reviews | RCH-IMCI focal person | Adopt the current indicators in HMIS: - Proportion of notified maternal deaths that are reviewed - Proportion of notified perinatal deaths that are reviewed |
| Proportion of HFs receiving 4 integrated RMNCH supportive supervision visits per year | Monitoring reports (integrated RCH program) | The IRCHP to share a list of supportive supervision visits made per facility per year |
| Number of districts with evidence based plans | M&E and/or Planning Unit reports | The MoH to share a list of “approved” list of districts with evidence-based plans per year |
| Proportion of skilled health care workers for RMNCH services (% increased) | Staffing and training reports/RCH | Rephrase the indicator to: Number and % increase in the number of HCWs trained in RMCAH. Depends on availability of training reports over the project’s duration |
| Number of Shehias reporting on community health volunteers activities per year | Health promotion unit (HPU)/Project partners report | Consider: Shehias that submitted at least 75% of expected reports in a year. Receive compiled performance list from the MoH |
| Number of pregnant women, caregivers of children under 5 years old and adolescents participating in promotional RMNCH, WASH and nutrition services per year | Health promotion unit (HPU)/Annual reports; | Compiled number of audience reached with promotional activities annually |
| Number of Health Care Professionals retained (following mid-term and long-term trainings) | Training and staffing reports, Annual reports | Rephrase to: Number of Health Care Professionals retained in their positions following supported mid-term and long-term trainings Consider: Total HCWs trained per facility over life of project Total HCWs still working in project sites |
| Number of students reached by teachers with RMNCH, WASH and nutrition messages per year | Health promotion unit (HPU)/Annual reports; | Availability of compiled school program reports |
| Number of persons reached with radio spots on RMNCH, WASH and nutrition messages per year | Media reports; Project annual reports | Availability of Mass media reach reports over life of the project |

Based on this assessment Table 8 represents the full list of quantitative indicators with available data to be incorporated in the evaluation.

Table 8: Project Indicators with identifiable data sources

| Indicators/variables | Data source/Type of reports | Baseline/Endline |
| --- | --- | --- |
| Proportion of pregnant women making 4 ANC visits | HMIS/DHIS2 Routine reports | 2015/2019 |
| Number and proportion of children (0-59 months) with severe acute malnutrition treated by OTC (outpatient therapeutic care) and ITC (inpatient therapeutic care) | HMIS/DHIS2 Routine reports | Yearly (trends) |
| Proportion of facilities without stock out of supply throughout a year | eLMIS reports (LMU) | 2015/2019 |
| Caesarean section rate | HMIS/DHIS2 Routine reports | 2015/2019 |
| Facility-based deliveries (in supported HFs) | HMIS/DHIS2 Routine reports | 2015/2019 |
| Proportion of HFs with star rating of 3 and above | Accreditation Reports (Health Sector secretariat) | 2015/2019 |
| Functional Blood Bank freezer and refrigerator | ZNBTS inventory/ physical assessment | Cross-sectional on day of visit |
| Number of blood donation sensitization activities per year | ZNBTS reports | Yearly |
| No. of ambulances procured/maintained | Functional Ambulance reports; Hand over Memo | Cumulative |
| Equipment and Supplies procured | Procurement and distribution reports | Cumulative |
| Infrastructure improvement - Number of EmONC sites refurbished - Number of YFSs refurbished | Refurbishment reports, Physical verification | Cumulative |
| Proportion and number of health facilities with at least one health worker trained to provide promotional RMNCH, WASH and Nutrition services | Training reports; Annual reports | Cumulative |
| Proportion and Number of Shehias with at least one community health volunteer trained to provide promotional RMNCH, WASH and Nutrition services - What proportion are still active? | Training reports; Annual reports. (also MoH reports) | Cumulative; latest CHVs report |
| Number of six-monthly (semi-annual) monitoring/reviewing meetings at Zonal level organized every year | Meetings reports per MoH sections; Annual reports | Annually |
| Infrastructure improvement - Number of EmONC sites refurbished - Number of YFSs refurbished | Refurbishment reports | Cumulative |
| Availability of Youth Friendly Services | Facility visit: YFSs reports and structured observation | July-Sept 2019 service statistics; day of visit observation |
| Availability of RMNCH equipment and Supplies | Facility visit: Quarterly inventory and supply chain reports | July-September 2019 stock out reports |
| Availability of trained HCWs in RMNCH, YFSs and Nutrition | Facility visit: Staffing list and training reports; Key informants | Cross-sectional |
| Availability of life saving services for mothers and new-borns (EmONC, KMC, care of the New-born) | Facility visit: Aggregate service statistics reports; physical space (readiness) | July-September 2019 services summary reports |
| Availability of functional referral system | Facility visit: Referral filing and reporting system | July-September 2019 |
| Improved infrastructure | Facility visit: Functional incinerators, placenta pit, Labour ward, Theatre (for CEmONC) | Cross-sectional |

## Audience of the Evaluation and Uses

Table 9 provides a list of primary audience of the evaluation.

Table 9: Primary audience of the evaluation

| Primary Audience | Interest |
| --- | --- |
| Zanzibar Ministry of Health | Performance of the project. Areas needing further support from the MoH after the project. Lessons to guide future projects. Recommendations to improve future similar projects. Requirements to ensure sustainability of benefits achieved. |
| Zanzibar Ministry of Finance and Planning | Overall performance of the project. Effectiveness of various components to be taken up by government. |
| GAC in Tanzania | Performance of the Project. Components taken up by the MOH. |
| UNICEF Tanzania Country Office | Performance of the project. Areas needing further support from the MoH after the project. Lessons to guide future projects. Recommendations to improve future similar projects. Requirements to ensure sustainability of benefits achieved. |
| UNFPA | Performance of the project. Areas needing further support from the MoH after the project. Lessons to guide future projects. Recommendations to improve future similar projects. Requirements to ensure sustainability of benefits achieved. |

# Approach and Methodology

## Approach

### Evaluation design

Based on the evaluability assessment the evaluation adopts a one-Shot Retrospective Design premised on a combination of recall and reconstruction of baseline especially for intermediate outcome indicators. This analysis will be undertaken for data that can be provided through the health management information system for Zanzibar or M&E system of the project. While the health management information will provide data on utilisation, to fully understand the project’s influence on equity an assessment of accessibility is required. In this regard qualitative interviews with project primary and secondary stakeholders will seek to reconstruct the baseline situation for different categories of individuals (adolescents, the poorest, those that live in remote areas, women and children with disability etc.) through recall.  The evaluation therefore uses qualitative and quantitative approaches.  Multiple data sources will be used to inform the evaluation in line with participants and stakeholders involved in the project’s implementation. The section on methodology details the key data sources and associated instruments.

### Evaluation guidance

Guided by the interests of UNICEF in the TOR and general UNICEF evaluation requirements for which our team adept, the evaluation will use the following UNEG guidance documents to frame methods:

- UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluations (2014);

- UNEG Ethical Guidelines for Evaluation (2008);

- UNEG Norms and Standards for Evaluation (2016)

- UNICEF Procedure for Ethical Standards in Research, Evaluation and Data Collection and Analysis (effective from 1st April, 2015);

- UNICEF-Adapted UNEG Evaluation Reports Standards– including the Global Evaluation Report Oversight System (GEROS);.

### Evaluation principles

Based on these guidance documents the evaluation adopts the following principles:

Independence, impartiality and credibility: External third party evaluations are premised on impartiality, independence and credibility of findings. As external evaluators, we have no interest in the outcome of the evaluation but more critically, ensure that our whole approach is underpinned by independence from the programme under assessment, its funders and its beneficiaries, which is a defining condition for a quality evaluation output. Therefore, the findings represent an independent opinion. The evaluation team have no prior interaction with the project or interests during its implementation and therefore no conflict of interest.

To enhance credibility of findings, data collection and reporting will be based on evidence obtained from the field. This evidence will be triangulated between sources including a validation process with stakeholders of the project. Any divergence from the evaluation’s view will require support of evidence from those that do not concur with the findings. Where points of disagreement arise, project staff will be requested to respond through a management response.

Transparency and Communication: We will conduct this review in a transparent manner ensuring that all stakeholders and beneficiaries understand the purpose and scope of this review process and are engaged and committed to the review’s success. We shall also communicate and consult with the team in charge of the review on a regular basis to update on progress and to alert the team of any challenges which we may encounter to remedy them as quickly as possible.

Quality: We will ensure that evaluation results are of high-quality based on a sound and tested methodology, which is comprehensive, evidence based, uses a mix of qualitative and quantitative methods appropriate to this assignment, and includes participation of key stakeholders and beneficiaries. The strength of our analysis and assessment is based on asking the right questions, speaking to relevant stakeholders, and collecting the required information, as well as extensive experience by our team members, to reach sound and justifiable conclusions and recommendations to meet the needs of the evaluation’s target audience. The structure and content of the report will be strongly influenced by GEROS.

Inclusiveness: all categories of beneficiaries of the project will contribute to the evaluation. As described in the methodology section, this takes into cognisance, disaggregation of age and sex and disability.

Fair power relations: duty bearers (MOH, health facility staff etc.) and rights holder (women beneficiaries) will be interviewed. Care will be taken to understand the power relations between the duty bearers and rights holders and its effect on project results. We shall ensure no one voice is emphasised over the other. Lastly, we acknowledge that the status of an evaluator can bring overbearing power on those being interviewed resulting in biased responses. We have taken note of this in our method – particularly using participatory methods that ensure the opinions of all participants are heard and noted.

Honesty and Integrity:  All findings and conclusions will be evidence based. Where evidence is inconclusive this will be highlighted in the findings.

Gender and human rights: gender and human rights will be incorporated in the evaluation in various ways. First the evaluation methodology will ensure rights holders and duty bearers are included in the process of data collection. Second, analysis of findings will be undertaken with a human rights lens especially regards access and utilisation of services. Third, the proposed data collection approach recognises the implications gender has in respect to women’s inability to express themselves in the presence of men. All data collected from primary and secondary data sources shall be sex disaggregated.

### Ethical Consideration

There are no major issues regarding the conduct of this evaluation which is not an intervention. No risk identified in participating in the study. So the participants’ safety is assured. All men, women and youth will have an equal chance to participate except in situations where a certain group or individuals ought to participate for an identifiable reason. However, the participants will have to sign a consent form to show that they are willingly participating in the evaluation and are not forced to participate or volunteer any information. The participants will be asked to participate with their full knowledge, do so voluntarily and with full consciousness give their consent. The study will be explained to the participants and asked to participate after consenting.  It will be explained to them that their views, ideas and values will be respected and kept confidential and anonymous. The data will be used only for the intended purpose and that the evaluation will be beneficial to them as the findings will enable the government offer better services to the mothers and children and ultimately improve the health and well-being of the Zanzibaris. The data will be elicited by trained personnel.

Some participants e.g. project workers or leaders who will be interviewed maybe interested parties in one way or the other and hence pose a conflict of interest. These will be identified and taken care of. Instead, similar questions will be asked or data sought from other multiple sources as well (triangulation). Finally, the UNICEF Guidelines on Ethical Research Involving Children and the UNICEF AGORA course on Ethics in Evidence Generation will be referred to.

Ethical clearance/approval will be sought from the Zanzibar Health Research Institute (ZHRI).

## Methodology

This section presents the methodology for the evaluation focusing on how the quantitative and qualitative data will be collected and analysed.

### Quantitative data collection

Quantitative data will be obtained through secondary sources. Variables will be extracted for indicators on RMNCH and Nutrition services coverage and utilization in health facilities, availability of infrastructure, equipment and supplies, and relevant outcome level indicators. These will be analysed to answer questions on effectiveness of the project. The endline data will consider a 12-month performance period based on the latest Government financial year (July 2018-June 2019). Where baseline data is needed, similar duration of a year before project activities were completely in action (July 2015-June 2016) will be considered.

#### Data sources

Secondary data will come from the national health management information system (HMIS/DHIS2), Health facility aggregated reports and inventories, project reports and monitoring data including CHVs reports, and management and supervision reports by the Ministry of Health and CHMTs.

#### Tools and Techniques

Variables to be collected are aligned to the performance measurement framework of the Afya Bora ya Mama na Mtoto project. The tools are structured around the data sources as presented in Table 8 above. The four tools measure project’s results at levels of outputs and outcomes, for both health systems and service provision.

- Quantitative tool 1 (QTT1): HMIS/DHIS2 Data Extraction Form. This tool will capture indicators that are routinely reported through the Health Management Information System (DHIS2). The applicable indicators/variables are detailed in Table 8 above.

- Quantitative tool 2 (QTT2): MoH Reports Summary Form: The tool will summarize variables/indicators from performance and management reports at various levels of the MoH structure at both national and subnational levels.

- Quantitative tool 3 (QTT3): Project data Summary Form: The tool will capture results from project performance reports and relevant documentation.

- Quantitative tool 4 (QTT4): Health Facility Assessment Tool: The tool will be used to collect quantitative data from selected health facilities during evaluation. Existing data services statistics and/or aggregate data will be summarized in the extraction form for evaluation purposes. The tool will also have a section on infrastructure and equipment observation at the health facility.

### Qualitative data collection

Qualitative data will be collected from multiple sources at national, district, facility and community level.

The assessment will be done with relevant stakeholders particularly informed relevance and effectiveness of the project including on best practices, challenges and lessons learned from implementation. It will help answering the questions regarding the extent the project design, implementation strategies and results were aligned to the national and local context, policies and program priorities. It will also validate the project’s achievement documented in program reports.

#### Data sources

Multiple stakeholders at:

National level

Data from project’s stakeholders at national level will be collected through key informant interviews (KIIs). This will target various categories of stakeholders including:

- Implementing partners: UNICEF; UNFPA; and Save the Children;;

- Ministry of Health Zanzibar (MoHZ);

- National referral hospital i.e. Mnazi Mmoja Hospital;

- HRH development/Training institutions: Midwifery schools and Medical and/or Para-Medical Schools (Principal/training coordinator); and

- Other Implementing partners in RMNCH: One or two partner(s) supporting RMNCH interventions in Zanzibar.

Subnational level

In this evaluation subnational level stakeholders are at district level. These stakeholders are expected to have been involved both as beneficiaries and implementers of the Afya Bora project. Hence, they will be a good source of information regarding achievement and administration of the project in respective districts. This will involve:

- Council Health Management Teams (CHMTs). In addition, one randomly selected member of the team will be interviewed to assess the impact of the project on health managers at district level.

- Community NGOs/CBOs.

Key informant interviews will be the main method of data collection for NGOs/CSOs while CHMT will be engaged through a combination of KIIs (only for the District Health Medical Officer (DMO)) and group discussions with members of the teams.

Facility level

Health facilities were reached with various interventions under the Afya Bora project. Individuals to be interviewed will include:

- Facility in-charge or RCH in-charge: For all sampled health facilities, either a facility in-charge or RCH in-charge will be interviewed to assess the contribution of the project to overall capacity and quality of RMNCH services. Data will be collected from these health facilities to inform how efficient the health management system is, including case management and analysing the drivers and constraints for varying levels of performance. This assessment will also focus on how HRH capacities have influenced the quality of services offered at each institution.

- RMNCH providers: group interviews will be conducted with providers of RMNCH and Nutrition services at one third of health facilities included in the study.

- Community program supervisor in all selected facilities (PHCU+). Through these interactions the evaluation will assess the contribution of the project to community-based services and facility-community linkage including emergency referrals.

Community level

For each facility (PHCU+) included in the evaluation, one Shehia (a community administrative unit) will be randomly sampled for data collection at community level. Stakeholders to be interviewed will include:

- Community and influential leaders: Various groups such as Shehas, religious leaders and/or other influential leaders at community level with be involved in key informant interviews. These leaders will be expected to provide information on community reception and involvement in project’s activities, coordination of project’s activities, as well as changes observed in coverage and quality of RMNCH and Nutrition services in respective communities. Where they exist, a male champion identified under the Afya Bora project will be interviewed.

- Community Health Volunteer (CHVs): Community health volunteers from sampled Shehia will be interviewed in a group using the FGD method to discover their involvement in the project’s activities as well as the interventions affected lives of people from their communities.

- Supervisors for community health volunteers: The supervisors of community health programs will be interviewed to understand the planning, implementation, monitoring and reporting of community activities under Afya Bora. They will also be a group to provide insights into the seen results from project’s interventions in respective communities.

- Mothers: Mothers of children aged 0-4 years will be involved in group interviews in sampled Shehias. The evaluation team will establish common issues that affected mothers with regards RMNCH, WASH and feeding/nutrition before the project and at the time of the evaluation and how the project was able to intervene or provide viable solutions to the challenges they faced. Further, information will be sought on the benefits accruing to them as a result of the project and the gaps they see as needing to be addressed in a future similar project.

- Fathers of children of less than 5 years: To assess the level of male involvement and factors associated with level of men’s support to RMNCAH services, the evaluation team will hold a focus group discussion with fathers of children of 0-59 months. The discussion will focus on their understanding of project’s benefits, their participation in care of women and children, and their perceived opportunities and challenges in improving RMNCAH, WASH and Nutrition.

- Adolescent girls and young women: A focus group discussion will be organized with adolescent girls and young women (15-24years) in sampled Shehias. The evaluation will assess their participation in: planning, implementing and monitoring youth friendly services in reproductive health; availability and accessibility of youth friendly services; and awareness on available youth friendly services in reproductive health.

- Adolescent boys and young men: From sampled Shehias, a cohort of young men (15-24yrs) will be interviewed through a focus group discussion to understand their perspective on RMCAH, awareness and access to youth friend services.

#### Tools and Techniques

Qualitative data collection from project’s stakeholders will be conducted using various tools and techniques including key informant interviews (KIIs), Focus Group Discussions (FGDs), and case studies. Selection of a tool to be used has considered the level of information expected and the interaction the participant had with the project. More account of such tools is as below:

Key Informant Interviews

Key Informant Interviews will be conducted with selected national, subnational, facility and community stakeholders of the project (UNICEF, UNFPA, GAC, MOH, District health managers/supervisors, facility managers and staff, influential leaders, CHV supervisors etc.). These specific groups of people should have particularly informed perspectives on the different aspects of the project being evaluated.  The interviews are loosely structured to allow the evaluators to follow emerging lines of inquiry that may not have not been anticipated at planning stage during the interviews. Key issues for KIIs are included in tools in Annex 5.

Focus Group Discussions

Focus groups discussions will be used to gain consensus on specific issues regarding project performance and outcomes as guided by the evaluation framework (Annex 2) and the tools in Annex 5. For example, through group discussions, the evaluation team will establish common issues that affected mothers/caregivers with regards RMNCH and feeding and nutrition before the project and at the time of the evaluation and how the project was able to intervene or provide viable solutions to the challenges they faced. Further, information will be sought on the benefits accruing to them as a result of the project and the gaps they see as needing to be addressed in a future similar project. Target groups for FGDs will include: CHVs, mothers, men, and young women and men.  While similar issues will be interrogated across all groups there will remain specific issues that will be relegated to a group. Focus Group guides are included under Annex 5.

Case Studies

During this evaluation, case studies will be used as a method of data collection, focusing on documentation of particular innovative interventions impacting lives of beneficiaries. These case studies will be particularly useful for understanding how some elements of the project were designed and executed to produce the observed impacts. These will also be used to further make a case for or against the design of the project and how it has come together to produce the observed impact. For this project, the consultants will document two case studies focusing on; the community health volunteers (CHVs) program and mentorship program for CEmONC improvement. From these two cases, the consultants will assess how project interventions addressed local problems, engaged key stakeholders, strengthening the health system, and analyse the influential factors to the different levels of performance. Furthermore, the consultants will also assess level of institutionalization of such interventions for sustainability.

At the beneficiary level, the case studies will also be designed in a way to track the interaction and influence of the holistic project interventions on lives of the beneficiaries concerned.

### Sampling strategy and sample sizes

National level: All institutions of interest as described under data sources (Section 3.2.2.1) will be interviewed. Specific individuals in these institutions will be purposive selected based on their participation in and knowledge of the project.

Sub-national level: Data will also be collected at subnational level from four selected districts in Unguja and Pemba islands (two in each island). This represents 36% of the 11 districts for the two islands.  For inclusivity and diversity, the selection of districts considered a mix of available health facilities supported under the project to cover for renovated PHCU+, non-renovated PHCU+, and hospitals including the national referral hospital. The selection also considered a mix of both urban-based and rural-based districts. The two districts selected for data collection in Unguja are Urban West (Magharibi B) and North A (Kaskazini A), whereas Wete and Mkoani will be visited in Pemba. A fifth district, Zanzibar Urban (Mjini) in Unguja, has been added to specifically enable the evaluation team to assess project performance at the national Hospital, Mnazi Mmoja Hospital.  There will be no district level interviews in Zanzibar Urban.

Seven health facilities have been selected for inclusion in the evaluation including:

- From Unguja

  - the national referral Hospital, Mnazi Mmoja Hospital, in Mjini;

  - Nungwi PHCU+ and Kivunge District Hospital in Kaskazini A; and

  - Fuoni Kibondeni in Magharibi B-Unguja.

- From Pemba

  - Junguni PHCU+ and Wete District Hospital both in Wete.; and

  - Kengeja PHCU+ in Mkoani District.

In districts where a PHCU+ and district hospital have been selected the intention is to assess the efficacy of the referral pathway and continuum of care. Specific individuals to be interviewed at each facility are presented in Annex 4.

Community level: From each selected PHCU+ facility one Shehia within its catchment area that has received the community health support (CHVs and CHV supervisors) will be randomly selected for the community visit. Accordingly, a total of four Shehias will be selected for community level data collection. Shehas, CHVs, and CHV supervisors from all four selected Shehias will be interviewed, whereas two religious leaders from two of the Shehias and two Champions from the other two Shehias will be conveniently selected to participate in interviews.   These specific Shehias will be finalised in consultation with UNICEF and Save the Children and included in the final itinerary. These specific Shehias will be finalised in consultation with UNICEF and Save the Children and included in the final inception report.

While influential leaders (Shehas/Religious leaders), and CHVs supervisors will be purposively selected, CHVs will be randomly selected from lists of CHVs in each selected Shehia to be shared by UNICEF and Save the Children.  Up to 10 CHVs will be involved in FGDs per selected Shehia facilitated by a moderator. Selection of community members to participate in FGDs will be done through self-selection, whereby Save the Children will mobilise community members to come and those that come will be  included in different categories of planned FGDs. Since each FGD requires a maximum of 10 participants, if more numbers turn up random selection of ten participants for the FGD will be undertaken for each category. Those not selected for interviews will be provided with refreshments and provide information on a few variables of interest and asked to go back home. This approach will limit positive bias in the selection of participants.

Table 10 below summarizes the type of respondents and respective sample size for qualitative data collection while Annex 4 provides a more specific and detailed list.

Table 10: List of respondents and sample size

| Level | Target | Data Collection Method | No. of interviews |
| --- | --- | --- | --- |
| National | UNFPA | Key Informant Interviews, Review of Literature and database information | 1 |
|  | UNICEF |  | 3 |
|  | GAC |  | 1 |
|  | Ministry of Health Officials (Maternal health, nutrition, WASH, Transport (for referral), Human Resources, Health promotion, Supply chain, and HMIS sections) |  | 4 |
|  | National Blood Transfusion Service |  | 1 |
|  | Health Training Institutions |  | 2 |
|  | National NGO Partner (Save the Children) |  | 1 |
| Subnational | NGOs/CBOs Partners (for community activities) | Key Informant Interviews and Review of Literature | 2 |
|  | Ministry of Health – District Medical Offices and RCH coordinators |  | 12 |
|  | District Hospitals and selected PHCU+ | KIIs with in-charges | 12 |
|  |  | FGDs with RMNCH providers | 4 |
|  |  | Case studies | 4 |
| Community | Community Health Volunteers | Focus Group Discussions | 4 |
|  | Community Health Volunteers Supervisors | Key Informant Interview | 4 |
|  | Community Health Volunteers | Case studies | 4 |
|  | Mothers/Caregivers | Focus Group Discussions | 4 |
|  | Adolescent girls and young women | Focus Group Discussions | 4 |
|  | Adolescent boys and young men | Focus Group Discussions | 4 |
|  | Mothers/Caregivers | Case studies | 4 |
|  | Shehas/Religious leaders/Champions | Key Informant Interviews | 4 |

#### Inclusion and exclusion criteria

Ministry of Health and subnational health managers: Key informant interviews will be conducted with heads of sections and/or districts and when they are not available, their officially designated officers for this purpose. Evaluators in collaboration with UNICEF will confirm on specific names of interviewees well in advance. The appointed officers will be required to have had held the office for not less than one year, to ensure that they had interaction with the project. Officers in position for a shorter period will be excluded from interviews.

UN agencies and Implementing partners: Participants from these institutions will be appointed by their respective organizations based on their experience and interaction with the Afya Bora project. Ideally the evaluation should speak to staff who have knowledge of the project from inception and implementation. In instances where these individuals have left Zanzibar or the organisation, efforts will be made through UNICEF to set up an appointment. However this will be discussed on a case by case basis. While those that have been with the project from the onset will be priority it does not preclude inclusion of those that joined the project midway and have valuable input in the process.  Nevertheless, officers that have interacted with the project for less than a year will not be eligible for interview.

Health facilities: Facilities to be include in the evaluation will be sampled from population of health facilities that were reached by project activities. Health facilities that were not part of the project interventions have not been considered for evaluation.

Health facility and community leaders: Health facility in-charges and community leaders will be included in the evaluation based on their roles. If they are not available to participate in the interview, they will be responsible for appointing a person to represent them.

Health workers: All health workers providing RMCH and Nutrition services at sampled facilities will be eligible for interview. Health workers that have been working at respective facilities for less than a year will be excluded from the study.

CHVs and CHV supervisors: Interviews with CHVs and CHVs supervisors will consider all those that have worked with the Afya Bora Project. Only CHVs and CHVs supervisors from sampled Shehias will be included in the evaluation. CHVs and/or CHVs supervisors that did not do community engagement activities, even if they had been trained by the project, will be excluded from the study.

Mothers and Care givers: Mothers and care givers of children aged less than 5 years will be included in focus group discussions. Those who have stayed in respective communities for less than a year will be excluded from the study.

Adolescent and young girls and boys: Adolescent and young girls and boys to be interviewed in FGDs will be aged 15-24 years. They must be residents of respective communities for at least the past one year.

### Data collection

The assessment will be tailored in such a way that maximum but focused amount of data will be collected to answer evaluation questions. Data collection will involve the consultants and qualified and experienced research assistants under direct support and supervision of technical consultants.

#### Quantitative data

Quantitative data will come from existing secondary sources particularly HMIS, facility services records, and project performance reports. Data collectors will use data abstraction forms to capture indicators of interest for this evaluation. The abstraction forms will capture key variables for project performance quantitative indicators. This will be aggregate data hence the data collectors will not be able to see any individual identifiers for service utilization data. For cross-sectional services coverage, the evaluation will consider data from the latest complete quarter of the project’s performance period (July-September 2019). For outcome/impact indicators, the evaluation will extract data for the latest the complete quarters of the year 2019 (January to September 2019). Where appropriate and available, comparative data for the similar period of the year before the intervention (January-September 2015) will be extracted for performance analysis.

#### Qualitative data

Qualitative data collection will be conducted in by the technical consultants assisted by research assistants. These assistants will undergo training on the tools before field work to ensure they are adept of the evaluation’s requirements. Tools for qualitative interviews at national and sub-national levels will be in both English and Kiswahili, with flexibility for interviews to discuss in the language of their choice. Tools for FGDs and KIIs at facility and community levels will be in Kiswahili. Translation from Swahili into English will occur during transcription into Word and kept securely until analysis is complete. Consent will be obtained to audio-record the sessions/and interviews and recorders will only be used if participants give their consent. In addition, field notes will be taken to capture non-verbal observations and to act as backup in case of failure/malfunction of the recorder. Translation and transcription will be verified by two study staff, for quality assurance. Interviewers/moderators will complete a cover sheet where they will document reflective notes following each interview/FGD. This will include, developing themes, summary of participants’ responses to specific topics and some exceptional quotations.

### Data management and analysis

Data will be analysed to show contribution of the project observed outcomes by first determining achievement of targets and second determining the causal chain.

Quantitative data: secondary data analysis will include before and after comparisons and time series assessment to determine points of divergence in trends and how the project influenced that divergence.

Qualitative data: all qualitative transcripts will be transcribed in excel according to respondents, themes and questions to prepare for analysis. Atlas ti, a qualitative data analysis software, will then be used to identify emerging themes from the data and the supporting quotations.

All primary data will be anonymised to ensure confidentiality. Access to this data will remain with the technical consultants. Upon completion of the evaluation all data will be handed over to UNICEF as part of the MDS’ contractual obligation.

# Work Plan

The evaluation is being undertaken in three phases: 1) inception, 2) data collection, 3) reporting and validation. A detailed list of activities and key dates are provided in Annex 6.

## Inception

This inception report is a culmination of the inception phase. It has been developed through a process that included: 1) documentary review of project related literature, studies and surveys to inform the RMNCH situation in Zanzibar and national policies and strategies on RMNCH to help the team understand the operating environment; 2) scoping mission that included interviews with primary stakeholders (Ministry of Health, UNICEF, UNFPA and a sub-contractor of UNICEF – Save the Children); 3) validation of quantitative data sources and review of evaluability of project indicators; and 4)  validation of the Theory of Change and assumptions, proposed evaluation questions, approach and methodology and the stakeholders to be included in the evaluation.

This inception provides the framework for the evaluation.

## Data Collection

While collection and collation of secondary data will occur throughout the evaluation period, primary data will be collected during the period 3-14 December 2019. It will include extensive interviews with stakeholders identified in this inception report on a wide ranging topics that respond to the evaluation questions as presented in the Annex 5. Annex 7 provides a detailed field itinerary to assist the Ministry of Health, UNICEF and UNFPA to mobilise stakeholders.

The data collection phase will culminate in the presentation of preliminary findings to stakeholders on the 13th of December 2019 before the team departs Zanzibar. This presentation, while not offering the full depth of findings will provide stakeholders the opportunity to validate the main findings that will be further developed during the reporting phase. While Zanzibar stakeholders will primarily attend this meeting, it is anticipated that concerned stakeholders from Dar es Salaam (Evaluation Manager, key persons from UNICEF and UNFPA) will also attend.

## Reporting and Validation

Once field work is completed the team will proceed to prepare the evaluation report. A preliminary report will be submitted end of January 2020 for the purposes of meeting critical requirements of the Ministry of Health. A full draft report will be submitted in February 2020. With a final report expected in April 2020. The ERG will review the report and provide comments which will be used to finalise the report. A presentation of the report is not anticipated as the costs for this activity have been spent in the scoping mission which was not part of the evaluation technical and financial proposal but regarded necessary by the Evaluation Reference Group.

# Quality Assurance and Risk Management

## Quality Assurance Plan

An elaborate work plan which describes all the activities, the implementation place, timing and the responsible team member is in place. The team leader will ensure that the plan is executed accordingly and a contingent plan has been developed to address any ensuing issues. The evaluation consultants are dependable and very well versed in the assignment.

The research team will be adequately trained and supervised closely throughout the data collection period. The data collected will be checked on a daily basis for correctness before compilation and computerized. Back up files will be maintained and stored by a supervisor or a senior evaluation team member. At least two consultants will be in the field and readily available for consultation and trouble shooting at any one time. The evaluation team leader will liaise with the Ministry of Health, UNICEF, UNFPA, Save the Children and the ERG whenever a need will arise.

As part of a well-established institution, Muthengo Development Solutions has standard QA procedures, which we instigate, proportionate to our needs as a small and growing development consultancy firm providing professional services. Our experience has shown that successful QA hinges upon: setting clear expectations based on terms of references from the onset; maintaining constant and open lines of communication; planning for various levels of review and revision, with clearly defined roles and responsibilities at each stage; and conducting regular performance reviews of staff and consultants, with 360 degree feedback.

QA will be important for effectively overseeing the activities under this assignment and ensuring our standards of quality. In practice, the QA procedures we would apply include:

- Open, communicative relationships with and timely reporting to UNICEF and its partners, involving a combination of face-to-face and virtual meetings.

- Through orientation/training of data collectors on methodology and tools.

- Comprehensive data processing/cleaning with use of statistical software for quantitative data;

- Internal Quality Control checks of products at each stage as well as deliverables before submission to the client. This includes careful review of data sets produced; and a second review of all reports/recommendations by the Team Leader.

- Regular team meetings led by the Team Leader and attended by the delivery team and finance/admin staff, as appropriate, with briefing, planning, joint analysis and collaboration.

- Reporting to key representatives of Muthengo Development Solutions Senior Management and the identification of key risks and monitoring via the project risk register.

- A Peer review system, which includes allocation of Senior Consultant outside the evaluation team as a technical reviewer, ensures all outputs are submitted after meeting internal quality standards.

### Evaluation management

The evaluation will be managed by UNICEF. An Evaluation Reference Group (ERG) has been set up. The Group will serve in an advisory capacity, its key role being to help strengthen the evaluation’s substantive grounding and its relevance to the Organization, and thereby increase its ultimate utility.  Key roles and responsibilities of the Evaluation Reference Group are in the Terms of Reference (Annex 1) but include among others: 1) evaluation technical guidance; 2) review and approval of evaluation outputs; and 3) validation of evaluation results.

The Evaluation Reference Group includes:

- Director of Department for Policy, Planning and Research, Ministry of Health (Zanzibar)

- Chief of Health section, UNICEF Tanzania

- Health Advisor, Global Affairs Canada

- Regional Health Advisor, UNICEF Eastern and Southern Africa

- Regional Evaluation Advisor, UNICEF Eastern and Southern Africa

- Chief, Zanzibar Field Office, UNICEF Tanzania

- Zanzibar Resident Programme Officer, UNFPA  Acknowledge role of UNICEF etc. including ERG

## Potential Risks and management plan

The political atmosphere is good and the timing is perfect. The team members /consultants will ensure that all steps are taken to minimize the potential for risk, and to have a plan in order to mitigate the risks. The table below outlines some of the risks anticipated, and how we will avoid / mitigate them based on our team’s extensive experience in conducting surveys in Tanzania and other countries in Eastern and Southern Africa. The following technical issues with regard to implementation of the evaluation plan may ensue and the mitigation measures are enlisted in Table 11.

Table 11: Risk management matrix

| Risk | Impact | Significance | Likelihood | Risk Management |
| --- | --- | --- | --- | --- |
| Datasets from the data management systems may be incompatible | May affect range of statistical analysis possible | Low | Low | Use multiple data sources |
| Difficulties in accessing data especially from ministries, partners | Delays in data analysis for matching while clearance is being sought | Clearly significant | Medium | Establish contact with relevant stakeholders, UNICEF to assist |
| Data or information collected may be damaged or lost | Re-collecting data may be expensive or difficult | Medium | Medium to Low | Various data capturing methods will be used including recorders |
| Respondent fatigue | Inaccuracies in data | Low | Low | Be clear on the purpose of the study Multiple sources of data |
| Enumerator fatigue | lack of concentration and high margin of error in inputting data | Medium | Low | Determine a reasonable workload per day per enumerator at survey pre-test. Work with experienced enumerators |

## Roles and Responsibilities of Key Stakeholders

This section provides the roles and responsibilities that are anticipated for each stakeholder to make the evaluation a success. These roles are in addition to those mentioned under evaluation management and relate mostly to evaluation preparation.

Table 12: Stakeholder roles and responsibilities

| Stakeholder | Expected Role |
| --- | --- |
| Ministry of Health | Mobilise stakeholders for interview at national level Mobilise, district health staff and health facilities for field data collection Provide all required health information system data |
| UNICEF | Main contact with the team on logistical arrangements and inputs required from different stakeholders in the evaluation Coordinate all stakeholders on logistical arrangements for field work Mobilise relevant staff for interviews Mobilise for community level interviews: CHVs, targeted community members etc. Provide all project relevant literature including: activity reports, financial reports and annual reports |
| UNFPA | Provide all required literature Mobilise relevant staff for interviews |

## Evaluation Team

The evaluation comprises an Evaluation Team Leader, Ngonidzaishe Marimo, MNCH Service Expert, Dr Dunstan Bishanga, Health Policy and Systems Expert, Dr Pasiens Mapunda, and a Project Manager, Tariro Mukupe.  Their roles and responsibilities are presented Table 13.

Table 13: Evaluation team and roles and responsibilities

| Position | Name | Roles and Responsibilities |
| --- | --- | --- |
| Team Leader & Evaluation Expert | Ngonidzaishe Marimo | - Coordinate and manage the evaluation processes including evaluation design, methodology, data collection and reporting. - Handles all communications with the client. - Responsible for all outputs/deliverables expected of the team by the client. |
| Health Policy and Systems Expert | Dr Pasiens Mapunda | - Assess the efforts of the project in strengthening health systems including coordination and referral systems. - Make evaluation conclusions and recommendations with regards to this component of the project. |
| MNCH Service Expert | Dr Dunstan Bishanga | - Assess the efforts of the project in supporting increasing coverage of quality MNCH services. - Make evaluation conclusions and recommendations with regards to this component of the project |

# Annexes

## Annex 1: Terms of Reference

## Annex 2: Evaluation Framework

| Evaluation Criteria | Key Questions | Indicators | Methods | Data Sources |
| --- | --- | --- | --- | --- |
| Relevance | To what extent are the project design, results and implementation strategies relevant to the national and local context, strategies, policies and programmes? | - Alignment to national priorities (policies and strategies) | Document Review KIIs | MOH officials Local Government UNICEF, UNFPA Zanzibar Health Sector Strategic Plan (2013/14– 2018/19), Road Map to Accelerate Reduction in Maternal, New-born and Child Mortality in Zanzibar (2015-2018), Zanzibar One RMNCAH Strategic Plan (2018-2022), UNDAP II and MKUZA III |
|  |  | - Alignment to UNICEF global priorities including the five areas for MNCH and UNFPA global priorities | Document Review KIIs | UNICEF, UNFPA Project Design document UNICEF’s Global Strategy for Health (2016-2030) |
|  |  | - Alignment to Government of Canada global priorities | Document Review KIIs | UNICEF, UNFPA, Embassy of Canada DFTAD Securing Children and Youth Muskoka Initiative |
|  |  | - Flexibility of design to accommodate emerging issues e.g. decentralisation, new policies, new issues, SRH | Document Review KIIs | MOH officials UNICEF, UNFPA, Save the Children Annual Reports |
|  |  | - Validity of assumptions for the Theory of Change | Document Review KIIs FGDs Case Studies | Annual Reports MOH officials UNICEF, UNFPA, Save the Children Health Workers in facilities Community Health Volunteers Pregnant women and those with children under 5 years |
|  |  | - Target groups in relation to equity and drivers of maternal, neonatal and child mortality | Document Review Secondary data HMIS KIIs FGDs Case Studies | Project design document Annual Reports DHIS2 MOH officials UNICEF, UNFPA, Save the Children |
| Equity and gender focus | To what extent have the project design and interventions taken into account the most vulnerable and hard to reach populations? | - Criteria for identification of project areas: - Selection of facilities - Selection of areas for CHVs | Documentary review KIIs | Project design document Annual reports MOH officials UNICEF, UNFPA, Save the Children |
|  |  | - Project investments: - Financial resource allocation vis a vis depth of challenge | Documentary review Secondary data analysis KII | DHIS2 Project Financial reports and budgets Activity reports and budgets MOH officials UNICEF, UNFPA, Save the Children |
|  |  | - Coverage and appropriateness/adequacy of support for groups left behind: - Adolescents - Hard to reach areas - Specific minorities | Document Review Secondary data HMIS KIIs FGDs Case Studies | Annual Reports MOH officials UNICEF, UNFPA, Save the Children Health Workers in facilities Community Health Volunteers Pregnant women and those with children under 5 years Adolescent girls and young women Men |
|  | To what extent have sex and disaggregated data been collected, monitored and analysed to inform the project? | - Extent of use of sex disaggregated data | Documentary review KII | Annual Reports MOH officials UNICEF, UNFPA, Save the Children |
|  |  | - Success and failures in approaches to engage men in RMNCAH | Documentary Review KII FGDs Case studies | Annual Reports MOH officials UNICEF, UNFPA, Save the Children Men |
|  |  | - Extent gender analysis was a premise for investments under Afya Bora including (renovations, training, community mobilisation etc) | Documentary review KII | Project design document Annual Reports MOH officials UNICEF, UNFPA, Save the Children |
| Effectiveness | To what extent have the project’s objectives and intended results been achieved? | - Performance of log frame indicators | Documentary review Secondary data analysis | Annual Reports DHIS2 |
|  | What are the factors that facilitate or inhibit the achievement of the project’s objectives and outcomes? | - Key drivers and barriers of performance in Afya Bora: - Project design including capacity development approach (transformative vis a vis functional) - Project management - Implementer motivation | Document Review KIIs FGDs Case Studies | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities Trained Health workers CHMT members Men Community Health Volunteers Pregnant women and those with children under 5 years |
|  | Which project activities had more significance to contribute to increased demand, coverage and uptake of quality emergency obstetric care, new-born and child health services, including high impact nutrition interventions? | - Extent of: - service referral by CHVs (RMNCH, Nutrition etc) - RMNCH services provided at facilities | Document Review Secondary data analysis KIIs and FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities Trained Health workers CHMT members Community Health Volunteers Pregnant women and those with children under 5 years |
|  |  | - Community perceptions on the quality of health care provided at health facilities | FGDs Case studies | Pregnant women and those with children under 5 years Men Adolescent girls and young women |
|  |  | - Contribution of each project component to desired results as well as combination of interventions | Document Review Secondary data analysis KIIs and FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities Trained Health workers CHMT members Men Community Health Volunteers Pregnant women and those with children under 5 years |
|  | To what extent has the project addressed accountability and ownership of implementing partners? | - Mechanism for performance measurement and its effectiveness | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities Trained Health workers CHMT members Men Community Health Volunteers Pregnant women and those with children under 5 years |
|  |  | - Measures to ensure ownership including effectiveness - through demonstration of ownership | Document Review KIIs FGDs | Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities CHMT members Community Health Volunteers |
|  | How adequate have UNICEF’s support been to the project, including from the perspectives of different partners at national and subnational levels? | - Adequacy and quality of management, and technical support from UNICEF | Document Review KIIs |  |
|  |  | - Perceptions of stakeholders on support from UNICEF | Document Review KIIs/FGDs | Annual Reports MOH officials, Health Worker Training Institutions UNFPA, Save the Children |
| Efficiency | To what extent have the project management and coordination been efficient? | - Level of functionality and effectiveness of national and subnational coordination platforms. | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children CHMT members Community Health Volunteers |
|  |  | - Was the staffing on the project commensurate with the scale and objectives? | Document Review KIIs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children CHMT members Community Health Volunteers |
|  |  | - Platforms that exist for lessons sharing between partners and the benefits accruing. | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions UNICEF, UNFPA, Save the Children |
|  |  | - Monitoring systems put in place, their adequacy to provide information required for project management and how information from the monitoring system was used for project steering at all levels. | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions UNICEF, UNFPA, Save the Children |
|  |  | - Key drivers and constraints to coherence and coordination. | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions UNICEF, UNFPA, Save the Children |
| Sustainability | What are the enabling as well as constraining factors that influence the sustainability of the project? | - What components will be sustained in the: - Short - Medium - Long term | Document Review KIIs FGDs | Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities CHMT members Community Health Volunteers |
|  |  | - Individual, organisational and institutional factors supporting or constraining sustainability | Document Review KIIs FGDs | Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities CHMT members Community Health Volunteers |
|  | How will good practices generated from the project be brought in and sustained at both national and sub-national levels? | - What is required to support them: - Key assumptions - Provisions being put in place or in planning to support sustainability | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities Trained Health workers CHMT members Men Community Health Volunteers Pregnant women and those with children under 5 years |
|  | What are the good practices and key conditions for national scaling up of the project? What could or should be done differently in future replication and scaling up of the project? | - Initiatives that can be scaled up: - What makes the initiative different? - What is required to transform them to a national programme? - What supports performance of the initiative? - What could potentially undermine it? | Document Review KIIs FGDs | Project Document Annual Reports MOH officials, Health Worker Training Institutions Local Government UNICEF, UNFPA, Save the Children Health Workers in facilities Trained Health workers CHMT members Men Community Health Volunteers Pregnant women and those with children under 5 years |

## Annex 3: List of People Consulted during the inception mission from [..] to […./October 2019]

| Name | Position | Organisation |
| --- | --- | --- |
| Dr Jamala Adam Taib | Director General | Ministry of Health, Revolutionary Government of Zanzibar |
| Ahlam Saeed Ali | Health Informatics | Ministry of Health, Revolutionary Government of Zanzibar, HMIS |
| Frederick Makanyaga | Statistician | Ministry of Health, Revolutionary Government of Zanzibar, HMIS |
| Dr Maha Damj | Chief of Zanzibar Field Office | UNICEF |
| Ramadhani Noor | Health Specialist, Zanzibar Field Office, | UNICEF |
| Batula Hassan Abdi | Programme Specialist , Reproductive Health | UNFPA |
| Azzah Nofly | Programme Analyst, SRH/HIV | UNFPA |
| Amanda Proctor | Zanzibar SCI Tz in charge | Save the Children |
| Asma Khamis | Programme Manager | Save the Children |
| Brenda Mshiwu | Health Nutrition Specialist | Save the Children |

## Annex 4: Full List of Stakeholders to be Interviewed

| No | National level | District level | Health Facility | Community level |
| --- | --- | --- | --- | --- |
|  | Key informants | Key informants | Key informants | Key informants |
| 1. | Director General of Health, MOH | DMO | Health facility in charge | Influential religious/traditional /opinion leader |
| 2. | Head of HPU Principal- CHS DVC-SUZA | 2.RMNCH Coordinator | Renovated and non-renovated RCMNH in-charge Maternity in charge | Sheha |
| 3. | Head of Nutrition | LGA leader District Director District Planning officer Community Development officer |  | Sheha |
| 4. | Head of IRCH Program coordinator |  |  |  |
| 5 | Head of RH | FGD CHMT members working with the project | FGD Trained HCWs | FGD CHVs |
| 6 | Head of Transport |  | CHV Supervisors | WRA |
| 7 | Head of Blood Bank |  |  |  |
| 8 | UNICEF |  |  | Men/Fathers |
| 9 | UNFPA |  |  | Young women/youth |
| 10 | SCI Tz |  |  | Young men/youth |
| 11 | Tertiary hospital-Mnazi mmoja Hospital MO I/C Maternity I/C *FGD- HCW trained? |  |  |  |

## Annex 5: Data Collection Tools

### Annex 5.1: Quantitative Data Extraction Tools

To be shared separately.

### Annex 5.2: Qualitative Tools

## Annex 6: Key Dates for the Evaluation

Inception Report Plan for Final Evaluation of Afya Bora ya Mama na Mtoto (2015 -2018)

Proposed work plan

| Activity | Responsibility | Date start | Date End | Progress |
| --- | --- | --- | --- | --- |
| Team meeting | All | 25/09/2019 | 25/09/2019 |  |
| Individual inputs to inception report | All | 26/09/2019 | 2/10/2019 |  |
| Submission of inputs to Team Leader | All | 01/10/2019 | 1/10/2019 |  |
| Review and consolidation of inputs by the Team Leader | Team Leader | 02/10/2019 | 04/10/2019 |  |
| Translation of tools | D. Bishanga Project Manager | 5/10/2019 | 8/10/2019 |  |
| Finalisation and Submission of Final Draft Inception Report (including research protocols) | Team Leader Project Manager | 11/10/2019 | 06/11/2019 |  |
| Review of Inception Report by the Evaluation Reference Group (ERG) | ERG | 06/11/2019 | 11/11/2019 |  |
| Receipt of Comments from ERG | ERG | 12/11/2019 | 12/11/2019 |  |
| Travel to Zanzibar | All | 27/10/2019 | 27/10/2019 |  |
| Inception Meetings with UNICEF, UNFPA Ministry of Health, and Save the Children | All | 28/10/2019 | 28/10/2019 |  |
| Review of Theory of Change and Evaluation Framework Meeting | All | 29/10/2019 | 29/10/2019 |  |
| Follow up meetings with other stakeholders and finalization of inception report and draft research protocol (IRB) | All Project Manager | 30/10/2019 | 30/10/2019 |  |
| Team meeting | All | 30/10/2019 | 30/10/2019 |  |
| Submission of Final Inception Report | Project Manager | 22/11/2019 | 22/11/2019 |  |
| Consolidation and Finalisation of the research protocol (IRB) | Team Leader; Zanzibar co-investigator | 6/11/2019 | 8/11/2019 |  |
| IRB Submission and Comments | DB Project Manager; Zanzibar co-investigator | 08/11/2019 | 22/11/2019 |  |
| Logistical planning for field work | Project Manager | 8/11/2019 | 22/11/2019 |  |
| Travel to Zanzibar | NM DB | 29/11/2019 | 29/11/2019 |  |
| Training of Research Assistants in Zanzibar | NM and DB DB | 30/11/2019 | 1/12/2019 |  |
| Field work in Dar es Salaam, Pemba and Unguja | Team Leader D. Bishanga P. Mapunga | 02/12/2019 | 11/12/2019 |  |
| Data processing and cleaning | All and Project Manager | 15/12/2019 | 27/12/2019 |  |
| Data analysis and consolidation | Team leader | 27/12/2019 | 31/12/2019 |  |
| Team members prepare and submit draft inputs to the analysis plan | All | 02/01/2020 | 10/1/2020 |  |
| Team leader review of draft inputs and compile | Team Leader | 13/1/2020 | 17/1/2020 |  |
| Team members review drafts based on comments from the team leader | All | 18/1/2020 | 22/01/2020 |  |
| Team Leader consolidates draft inputs into a full draft report for internal review | Team leader | 23/01/2020 | 28/01/2020 |  |
| Internal review of full draft Report | All | 29/02/2020 | 8/02/2020 |  |
| Team Leader incorporates comments from internal review | Team Leader | 10/02/2020 | 12/02/2020 |  |
| Editing and submission of Full Draft Report | Project Manager | 14/02/2020 | 14/02/2020 |  |
| ERG reviews draft report | ERG | 17/02/2020 | 6/03/2020 |  |

The dates for final report will be discussed with MoH and UNICEF.

## Annex 7: Detailed Field Work Itinerary

To be shared separately.

## Annex 8: Bibliography

UNICEF and UNFPA (2016) Annual Report of the Afya Bora Project 1 April 2015 – 30 April 2016. Report prepared for the Government of Canada.

UNICEF and UNFPA (2016) Annual Report of the Afya Bora Project 1 April 2016 – 30 April 2017. Report prepared for the Government of Canada.

UNICEF and UNFPA (2016) Annual Report of the Afya Bora Project 1 May 2017 – 30 April 2018. Report prepared for the Government of Canada.

UNICEF and UNFPA (2016) Annual Report of the Afya Bora Project 1 May 2018 – 30 April 2019. Report prepared for the Government of Canada.

The Revolutionary Government of Zanzibar (2019) Zanzibar Multisectoral Nutrition Action Plan (ZMNAP) 2019/20 – 2023/24.

The Revolutionary Government of Zanzibar (2019) Zanzibar Reproductive, Maternal, Newborn, Child and Adolescent Health Strategic Plan (2019 – 2023)

The Revolutionary Government of Zanzibar (2017) Mid-Term Review Report Zanzibar Health Sector Strategic Plan-III 2013/14-2018/19.

The Revolutionary Government of Zanzibar (2013) Zanzibar Health Sector Strategic Plan III 2013/14-2018/19.

The Revolutionary Government of Zanzibar (2017) Zanzibar Reproductive, Maternal, Newborn, Child and Adolescent Health Strategic Plan (2018 – 2022).

The Revolutionary Government of Zanzibar (2016) Zanzibar Strategy for Growth and Reduction Of Poverty (ZSGRPIII) (Mkuza III) 2016-2020.

UNICEF and UNFPA (2014) Accelerating Maternal, New-Born and Child Health in Zanzibar. Project Proposal to Canada - Department of Foreign Affairs, Trade and Development.

https://www.unicef.org/cbsc/files/Five_Results_Areas_for_MNCH.pdf

Full contribution analysis will not be undertaken however, using our experience will tailor make the assessment to needs of the evaluation.

Three dimensions are essential when undertaking an evaluability assessment. The 1- adequacy of the program design, including its clarity, coherence, feasibility and relevance, which is the evaluability in principle. The 2- availability of information, data capacity management system, which is the evaluability in practice. And the 3- conduciveness of the context for the evaluation, especially stakeholder’s and key users’ views and resources available