Final Project Evaluation

“Developing Community based Services for Children with Disabilities and their Families’’

(April 2010 –December 2013)

RFP 4-2013

Final Evaluation Report (vol.1)

December 2013

Camelia Gheorghe, Team Leader

Ozren Runic

ACKNOWLEDGEMENTS

The evaluation team acknowledges the valuable guidance and support provided by the management and staff of UNICEF Country Office in Serbia throughout the entire evaluation process.

The evaluation team also acknowledges the information and data generously provided by the Ministry of Labour, Employment and Social Policy, EU Delegation, the Republic Institute for Social Protection, SIPRU, Belgrade University, municipalities, centres for social work, other service providers, civil society organizations and parents of beneficiary children during interviews, site visits and focus groups, which were used as part of the analysis.

The evaluation team is also grateful for the information, critical insights and logistical support provided by the project consultants, regional mentors and local project managers.

The contents of this evaluation report are the sole responsibility of the contractor and can in no way be taken to reflect the views of UNICEF and of the European Union.

Name of the Project: Developing Community-based Services for Children with Disabilities and Their Families Timeframe of the evaluation: July-November 2013 Date of the report: December 2013 Country of project: Serbia Evaluators: Camelia Gheorghe and Ozren Runic Name and address of the company the report has been commissioned by: Promeso Consulting srl, 14, Decebal Blvd., 030967 Bucharest, Romania Name of the organisation commissioning the evaluation: UNICEF Serbia Name of UNICEF staff contact point for the evaluation: Vesna Dejanovic, Project Officer Child Protection

TABLE OF CONTENTS

Acronyms	5

Executive Summary	7

1. 	Context and Project Background	13

1.1	Project Context	13

1.2	 Project Description	18

2.	Evaluation of the Project	23

2.1	Purpose, Objectives and Scope	23

2.2	 Methodology	24

2.3	 Evaluation Design	31

3.	Findings and Analysis of Results	33

4.1	Relevance	33

4.2	Effectiveness	37

4.3	Efficiency	49

4.4	Impact	54

4.5	Sustainability	58

4.6	Human rights and cross-cutting issues	62

4.	Conclusions and Recommendations	67

4.1	Conclusions	67

4.2	Recommendations and Lessons Learnt	68

LIST OF TABLES

Table 1. Grouping of Questions and Issues in the Evaluation Matrix	28

Table 2. Performance Rating	28

Table 3. The Evaluation Sample	30

Table 4. Planned Results and Indicators of the Project	38

Table 5. Overview of Training Courses delivered by the Project	39

Table 6. Community-based Services supported by IPA 2008 Project	40

Table 7. Decrees, Rulebooks and Guidance Documents developed through the IPA Project	43

Table 8. Local Self-Governments Providing CBSS in 2012	45

Table 9. List of Recommendations	70

LIST OF BOXES

Box 1. Areas of By-Laws Development in Social Welfare, IPA 2008 Project	33

Box 2. Establishing and Running Day care Services	47

Box 3. Impact of the Project on Children with Disability in Foster Care	56

Box 4. Sustainability Challenges in City Municipalities	60

Box 5.  Holding Government Accountable for Implementing Adopted Policies	63

Box 6. ”Invisible” Children	65

LIST OF FIGURES

Figure 1. Children and Youth with Disabilities in Residential Care	14

Figure 2. Children and Youth with Disability in Foster Care	14

Figure 3. Key Characteristics of Children Placed in Formal Care (%, 2013)	46

# Acronyms

| Acronym | Description |
| --- | --- |
| BBI | Bernard Brunhes International |
| BCIF | Balkan Community Initiative Fund |
| CARDS | Community Assistance for Reconstruction, Development and Stabilisation |
| CBSS | Community-Based Social Services |
| CEDAW | Convention on the Elimination of all Forms of Discrimination against Women |
| CLDS | Centre for Liberal-Democratic Studies |
| CPAP | Country Programme Action Plan (UNICEF) |
| CRC | Committee on the Rights of the Child |
| CRIS | Current Research Information System (EU) |
| CSO | Civil Society Organisation |
| CSW | Centre for Social Work |
| DAC | Development Assistance Committee |
| DG | Directorate General (European Commission) |
| DFID | Department for International Development (UK Government) |
| DILS | Delivery of Improved Local Services |
| EC | European Commission |
| EQ | Evaluation Question |
| EU | European Union |
| EUD | Delegation of the European Union |
| EUR | Euro |
| HRBA | Human Rights-Based Approach |
| GDP | Gross Domestic Product |
| IPA | Instrument for Pre-Accession Assistance |
| IR | Inception Report |
| IT | Information Technology |
| LSG | Local Self-Government |
| MICS | Multiple Indicator Cluster Surveys |
| MIPD | Multi-annual Indicative Planning Document |
| MoLESP | Ministry of Labour, Employment and Social Policy |
| MODS | (Serbian abbreviation for) Network of CSOs for Children in Serbia |
| NGO | Non-Governmental Organisation |
| NYHQ | New York Headquarters |
| OECD | Organisation for Economic Cooperation and Development |
| PIU | Project Implementation Unit |
| ROM | Results Oriented Monitoring |
| RSD | Republic of Serbia Dinar |
| SIPRU | Social Inclusion and Poverty Reduction Unit |
| ToR | Terms of Reference |
| UK | United Kingdom |
| UN | United Nations |
| UNICEF | United Nations Children’s Fund |
| VAT | Value-Added Tax |

# Executive Summary

Project Description

The overall objective of the Project under evaluation ‘’Developing community based services for children with disabilities and their families’’ is to strengthen policy frameworks, institutional mechanisms and capacities so that community-based social services (CBSS) supporting children with disabilities can be developed and are responsive to the needs of these children and their families. The specific objective is to increase the number of children with disability benefiting from community services that are clearly contributing to their social inclusion.

The main purpose of the Project is to increase the number of children with disability benefiting from CBSS that are clearly contributing to their social inclusion, with two main expected results:

- Ministry of Labour, Employment and Social Policy (MoLESP) capacity strengthened to monitor, evaluate and supervise decentralized and well-targeted CBSS in Serbia (national level)

- Municipal authorities, service providers, centres for social work (CSW) and civil society activists capacitated to fulfil their respective roles in ensuring CBSS for families with children with disability are accessible and meet set standards and procedural guidelines (local level).

The target groups consist of Government employees at national and municipal levels, service-providers, staff of CSWs and Civil Society Organizations (CSOs). The final beneficiaries and rights-holders of the Project are children and youth with disability and their families who are in need of additional support for their social inclusion; unemployed women and youth to be trained and engaged in providing support to children with disability.

The Project under evaluation has a budget of 2.2 million EUR, out of which the EU contribution is 2 million Eur. It is implemented by UNICEF Serbia in cooperation with the MoLESP and a wide range of key partners. The Project is part of the EU Social Inclusion IPA 2008, which also includes a grant scheme for municipalities to set up and run community-based social services (CBSS). The duration of the Project was 44 months (April 2010 - December 2013)

Context of the Project

Serbia has made significant progress on a wide-ranging reform agenda, including progress towards achieving the national Millennium Development Goals, and modernisation of the legal framework. The opening of negotiations for EU membership will trigger more intense reforms, especially in public administration and justice. Meanwhile, the country is facing serious economic difficulties. The vulnerable groups of population have been disproportionately hit by the current economic crisis. Among them are families with children, especially those living in the southern Serbia, in rural areas and in the municipalities considered “devastated”. Children constitute 27.6% (160,586) of the total number of beneficiaries of CSWs. The number of children and youth with disability who are beneficiaries of the social welfare system increased from 10,718 in 2006 to 15,573 in 2011 as did the number of other social welfare beneficiaries. This increase put a big pressure on the social welfare system generally and on the CSWs in particular.

Of all children placed in formal care in the last five years (from 2006 to 2011), around 33% were children with disabilities, pointing to the lack of mechanisms and programs to ensure adequate and timely support for families to help them cope at times of crisis and prevent unnecessary family separation.

Over the last decade, progress has been made in the improvement of the Serbian social welfare system and its decentralisation. Significant results have been obtained since 2005 in the deinstitutionalisation of children without parental care. The development of the foster care network and CBSS facilitated this process. In 2008, the MoLESP – which has the overall responsibility for the system of social protection and social welfare and is also the lead-agency for child protection - signed a Memorandum of Understanding with UNICEF to develop community-based support for vulnerable children with a view to reducing the need for residential care. With the financial support of donors, most notably the EU, and the technical support of UNICEF, the MoLESP developed a ”Comprehensive Plan of Transformation of Residential Institutions for Children” (2008) to reduce the size of residential care institutions and develop new services for better quality care as well as professional development for staff in residential institutions, centres for family placement and CSWs.

Data from 2008 indicate that only 33 municipalities (out of 168) financed day-care services for children with disabilities for a number of 1,122 children were included, while home-help services were available to only 125 children with disabilities and their families. Since 2008, the number of services kept increasing, reaching more and more children, young persons and their families. Despite this progress, the number of children currently benefitting from community services is relatively small, while the CBSS for at-risk families with young children are under-developed. The delivery of social benefits and social services varies widely across Serbia. Many Local Self-Governments (LSGs) have modest budgets and lack capacity to map out needs and resources, design and implement social inclusion policies in a participative manner, commission specific services and review results. Efforts are needed to improve their capacity across the country to set up, diversify the typology and increase the quality of the CBSS. Further development of CBSS will also depend on the implementation of the draft decree on special purpose transfers, which would help ensure the development of CBSS in under-developed municipalities.

As far as the legal and policy framework is concerned, child welfare is incorporated in various strategies and laws regulating social welfare in general, primarily the Law on Financial Support for Families with Children (2002), the Social Welfare Strategy (2005), the Family Law (2005), and the most recent Social Welfare Law (2011). A priority is the implementation of the Social Welfare Law, which prioritizes community-care and limits residential care, brings non-state actors into the social service provision system and strengthens internal oversight and accountability systems. A new quality assurance system of social services providers is awaiting its enforcement, based on the recently adopted by-laws on service standards and licensing procedures for service providers as well as on modern supervision and inspection mechanisms. A better coordination of activities among related ministries is also needed to develop integrated/cross-sector social services. In general, the legal framework in Serbia is largely synchronized with European and international human rights standards, and the prospect of EU integration is driving the comprehensive reforms of the social sectors.

Purpose and objectives of the evaluation

The purpose of this evaluation is to evaluate the final (end) results and achievements of the Project in relation to the project logframe and Theory of Change. The specific objectives of the evaluation, as per ToR, are the following:

- Provide feedback to UNICEF Serbia office and its national counterparts on the soundness (defined as relevance, effectiveness, efficiency, sustainability) and impact of the Project approach in developing responsive community services for children with disability in order to reveal good practices and gaps in approaches, and evaluate Project impact following Project Plan, Project Logframe and Description of the Action.

- Extract general lessons learned and recommendations aimed at further enhancement of the child care system reform.

- Provide the Delegation of European Union to Serbia with information on impact of their specific support to Child Care System in Serbia

The evaluation covers the entire implementation period (22 April 2010 – 22 December 2013) at both national and local levels and all project components, following the way how the project has been conceptualized in the Social Inclusion IPA Fiche 2008, Description of Action, its Logframe and Theory of Change. The evaluation has been carried out during by a team of experts from Promeso Consulting (Romania), selected following competitive tender.

Evaluation methodology

The evaluation has been carried out in three consecutive phases: Inception/Desk Phase, Field Phase and Synthesis Phase.

In the Inception/Desk Phase, the team reviewed the entire IPA 2008 project documentation and the national policy papers, legislation, strategies and action plans in the area of child protection and social welfare. The desk phase also included extensive review of EU accession-related documents and reports as well as the documentation on reporting to international bodies and human rights conventions ratified by Serbia.

The Field Phase has been devoted to the collection of data from key stakeholders at national and local levels, based on the evaluation instruments developed during the Inception/Desk Phase. The semi-structured interviews with UNICEF management and representatives of all national project partners took place in Belgrade between 16 and 21 September 2013. For the site visits, which took place in the following week, the evaluation team has developed a set of criteria for representative sample selection based on typology of services and service providers, rural/urban regional balance, territorial distribution and development level of municipalities. Out of 10 clusters, 41 municipalities and 52 services the team has visited 2 clusters (Čoka and Aleksinac) and 6 municipalities and services, conducting two discussion groups with local implementation teams, LSGs representatives, service providers and professionals as well as two focus groups with beneficiary parents and families.

In the Synthesis phase, the team has applied the standard evaluation criteria analysis (relevance, efficiency, effectiveness, impact and sustainability) in combination with Human Rights-Based Approach in order to assess the achievement of planned results, draw informed conclusions and lessons as well as to provide meaningful and practical recommendations.

Main Findings and Conclusions

The Project is highly relevant for Serbia’s child care reforms and national policies for improving the lives of children with disability. It is in line with Serbia’s Social Welfare Strategy and the Plan of Action for Children while its primary objectives are tied to the implementation of the Social Welfare Law. It is highly relevant for Serbia’s international commitments deriving from the ratification of human rights standards and its status of EU candidate country. The Project addressed the most pressing needs of children with disability and their families as they were identified in the domestic and international reports and planning documents, which all recommend the development of community-based services. The capacity building activities had a high relevance for the advancement of child care reforms in the country as had the strengthening of monitoring and evidence-based policy making capacities for guiding the implementation of these reforms. The Project remained relevant over its entire lifetime. UNICEF is seen as best positioned to advocate and promote the children’s rights and get involved in the implementation of such projects.

The Project was effective in achieving its planned results and objectives. UNICEF’s partnership with MoLESP allowed for effective and coordinated development of complex legislation which were drafted and submitted for adoption according to project plans. Despite relatively low number (30%) of adopted drafts due to circumstances outside project control, the crucial rulebooks on quality standards and licensing of professionals and services were adopted by the MoLESP (following constant advocacy efforts by the Project team), which created the prerequisites for further development of CBSS. The effectiveness was particularly high in respect to production of studies and research papers which created a significant body of intelligence for further reform of child care in the country. The Project also strengthened the national system for continuous professional development. It effectively supported 52 CBSS serving 930 children and employing 300 people. The planned number of beneficiaries was achieved only in a proportion of 78%, caused by an over-estimation of the potential beneficiaries during the applications development, lack of quality standards at the time coupled with lack of local experience and benchmarks for new services. Overall, the Project speeded up the pace of reform by pushing the development of CBSS, an essential social welfare pillar.

Most of the planned Project activities have been delivered in an efficient and timely manner. The project implementation team produced high quality progress reports which were delivered within the set deadlines. UNICEF technical assistance to cluster applicants was implemented in time for efficient development and submission of grant proposals. The efficiency of the project delivery was enhanced by the extensive use of the local consultants, training and intensive mentoring provided to local PIUs and municipalities and, most significantly, by the introduction of the clustering concept which considerably simplified the process of procurement and funding transfers. The Project made no difference between the city municipalities and others; lacking in decision-making capacities and budget capabilities, the city municipalities lagged behind in all project implementation aspects: effectiveness, efficiency and especially sustainability. Certain flaws in the estimation of potential beneficiary numbers in the application planning phase have created a chain effect, resulting in an uneven use of human resources in a number of clusters. Overall, efficiency was facilitated by the excellent co-ordination between the project component implemented by UNICEF and the grant scheme managed by the EUD as well as by the synergy with projects financed by other donors.

The project had a general high impact level. It made a major contribution to increasing the number of children with disability benefiting from CBSS. The highest positive impact of the project is obvious in terms of parents’ satisfaction: 94.9% of parents were completely or mostly satisfied with the service after one year of using it. The beneficiary families, as rights-holders, reported improvements of quality of life as a result of service establishment, both for their children and other family members. Life of parents has shifted from isolation, unawareness of rights and distrust to openness toward increased socialization, awareness of service potential and inclusion in community activities. The project had an indirect effect of opening communication possibilities for experience exchange between parents which in some cases led to involvement in institutional decision making or creation of informal pressure groups to ensure community service sustainability. The mapping exercise which identified a significant number of children with disability in the targeted municipalities kept hidden and unregistered had a significant impact on the awareness of possibly large number of children in Serbia in similar situation who are in need of identification and outreach. Impact would have been higher in case the access issue for children in remote and rural localities was settled after the end of grant money. At national level, the Project had an important impact on the professional development of the MoLESP staff and of Institutes for Social Protection. The capacity of CSWs to handle the implementation of new legislation in terms of case management and referral, as well as of data collection and reporting remain at a low level, requiring further capacity building.

Most effects and outcomes of the Project are likely sustainable. The capacity building efforts including consultancy in legislative drafting at the national level have resulted in a comprehensive regulatory package for the establishment of new CBSS and significant improvement of the quality levels of the existing ones. All service providers will have to match the standards and provide licensed staff for the care of beneficiaries. The accredited training packages developed by the Project are already used by the Institute of Social Protection for the process of professional development of the service providers and CSW staff, required for their future licensing by the MoELSP, respectively the Chamber for Social Work. High sustainability prospects could be assigned to a set of practicums, tools and methodologies used in a number of studies, surveys and research papers developed during the Project. At the level of LSGs, essential is the financial sustainability of the services developed through the Project. Full or partial sustainability for 86.5% of the supported services has been ensured for at least one more year of operation. Sustainability of services is under major risk in two specific types of municipalities: the least developed municipalities which lack the needed financial means to run the respective CBSS and the so-called ‘city municipalities’ which have reduced competencies and are heavily reliant on city governments. It is hoped that the adoption of the Decree on special transfers would help the under-developed municipalities to keep running the established CBSS. Still, full enforcement of quality standards might discontinue some of the services, due to the inability of service providers to comply with the respective conditions, most vulnerable being the services run by NGOs. Weak inspection capacity at the national level to monitor the enforcement of the new standards is a matter of significant concern.

The Project had a major contribution to the promotion and realisation of child rights through opening access to community services tailored to the needs of most of its beneficiaries, impressive analytical work to provide evidence on the needs and rights of children which were breached, supporting oversight bodies at national level to strengthen their capacity to identify and report on discrimination of children with disability and inequality cases, developing the capacity of CSOs to network and advocate for child rights at local level, while holding the LSGs accountable. It had a positive contribution to the strengthening of the capacity of a wide range of Serbian duty-bearers to protect and fulfil child rights and to capacitating parents, as rights-holders, in terms of access to information about available services, better governance and, to a certain extent, enhancement of their skills to take care of their own children. The Project has however a limited role in equipping the weakest parents with the knowledge and abilities to claim and fully exercise their rights. The Project paid particular attention to women empowerment, through training and job creation in community services, women representing 83% of all employees of CBSS. More in-depth assessment of gender mainstreaming, empowerment and equality was hampered by the lack of gender disaggregated project indicators. The Project managed in almost all cases to ensure an equity focus by orienting EU grant and domestic investment towards the most under-developed municipalities of the country as well as by focusing its intervention on the most vulnerable children with disability and their families. However, some planning flaws in the local projects design phase and financial constraints after the project money came to an end restricted the access of some of the poorest and remotely located children, especially from rural areas.

Recommendations

The Report provides a number of key recommendations for the Serbian Government and LSGs, UNICEF, EU and other donors, based on the findings and conclusions of the evaluation, as follows:

Strategic Recommendations (S):

S1: Further invest in the development and diversification of country-wide community-based social services to contribute to the social inclusion of the most vulnerable children with disability and prevent separation from their families

S2: Develop a culture of lifelong learning within Centres for Social Work to ensure that managers and staff keep pace with reforms and are empowered to address the needs of children with disability at highest professional standards

S3: Support the formation of a competitive market of service providers to ensure best quality of care at affordable prices for children with disabilities and their families

S4: Strengthen the quality assurance system of the community-based services for children with disability

S5: Improve data gathering systems for monitoring of child care reform and informed policy-making for the benefit of children with disability

S6: Ensure that a more systematic Human Rights-Based Approach is used in the programming and implementation of future UNICEF projects targeting children and their families

Operational Recommendations (O):

O1: Carry out a country-wide identification of children with disabilities for evidence-based policy making and support action

O2: Adjust the approach to respite care to ensure its sustainability

O3: Develop a costing model for various community-based services addressing children with disability to guide local budgeting of services and benchmarking generally

O4: Include clear accountability criteria in future grant agreements with municipalities

The evaluation of the Project led to the following Lessons learnt:

- Legal (official) commitments of beneficiary institutions at national and local levels are key to successful implementation of initiatives related to social welfare reform.

- Concept of municipality clustering is very good for efficiency but less appropriate for effectiveness and sustainability.

- Implementation of local projects in the (so-called) city municipalities has to be carefully planned.

- Investing in academic and professional research as a back up to main activities brings significant returns.

- Child care reforms cannot succeed without a strong CSW network.

- Community-Based Services represent a significant breakthrough for child care, but most vulnerable and neglected children with disabilities could still be in danger.

# 1. 	Context and Project Background

## 1.1	Project Context

Serbia is an upper-middle income country which got the status of EU candidate country on 1 March 2012, on the basis of the Commission Opinion on Serbia’s membership application adopted in 2011. The accession negotiations will start as soon as the country achieves the necessary degree of compliance with the membership criteria, in line with the conditions of the Stabilisation and Association Process.

Serbia has made significant progress on a wide-ranging reform agenda, including progress towards achieving the national Millennium Development Goals, and modernisation of the legal framework. The opening of negotiations for EU membership will trigger more intense reforms, especially in public administration and justice.

Meanwhile, the country is facing serious economic difficulties due to the global economic crisis. In 2012, Serbia had a negative economic growth (-1.5 %), high inflation (11%), rising unemployment (up to 26 %) and a double digit current account deficit. A proportion of 9.2 % of Serbian population lives under the absolute poverty line (2010). The vulnerable groups of population have been disproportionately hit by the current economic crisis. Among them were families with children. The poverty rate of children below the age of 14 almost doubled from 7.3 in 2008 to 13.7% in 2010. Most disadvantaged were the children living in the southern part of the country, in rural areas and in the municipalities considered “devastated”.

The average percentage of social welfare beneficiaries among the total population in Serbia is 8.1. Children (0-18) constitute 27.6% (160,586) of the total number of beneficiaries of the Centres for Social Work (CSW), which are the main operational arm of the Ministry of Labour, Employment and Social Policy (MoLESP) functioning in nearly all municipalities in Serbia (140 centres). More than half of these children are categorized as socially and economically vulnerable (57%). The number of children and youth with disability who are beneficiaries of the social welfare system increased from 10,718 in 2006 to 15,573 in 2011 as did the number of other social welfare beneficiaries.

This increase has put a big pressure on the social welfare system generally and on the Centres for Social Work in particular. Their mandate is to assess the needs of beneficiaries and implement individual care plans, including referrals of children to foster care, residential institutions and community services. CSWs also administer cash assistance to poor and marginalized individuals and families. An important function of the CSW is to ensure inter-sectoral coordination and cooperation around key child protection issues at the local level. Although the total number of employees of CSWs increased by 6.4% in the period 2008 to 2011, it has not kept pace with the growing number of clients. Moreover, the number of specialized staff was significantly smaller, with only one per 4,033 inhabitants. Indeed, out of the total number of 3,235 employees, only 1,790 are professionals and specialists, such as social workers, psychologists, lawyers and pedagogues. The heavy workload of CSWs prevents many of them from fully implementing the case management approach, adopted in 2008.

The number of children with disabilities in residential care has decreased but at a much slower pace compared to the rest of children: 36 % compared to 63% overall reduction in the number of children without disabilities placed in institutions in the period 2000-2011. As a result, the proportion of institutionalised children with disabilities as compared to the children without disability has increased from 60.2% in 2000 to 69 % in 2011 (see Figure 1 below).

##### Figure 1. Children and Youth with Disabilities in Residential Care

Source: Ministry of Labour, Employment and Social Policy

Only 10.7% of all children and young persons in the foster care families were children with disabilities. Although the total number of children with disabilities in foster care families is on the increase (2005 – 276, 2011 – 590), their share has not changed significantly over time as illustrated by Figure 2.

##### Figure 2. Children and Youth with Disability in Foster Care

Source: Ministry of Labour, Employment and Social Policy

These indicators put Serbia among the countries with the lowest rate of institutionalization in Europe.  However, while fewer children end up in institutions, the overall number of children and young people placed in formal care continues to grow, with a 36 % increase recorded between 2000 and 2011.

Over the last decade, progress has been made in the improvement of the Serbian social welfare system and its decentralisation. Significant results have been obtained since 2005 in the deinstitutionalisation of children without parental care. The development of the foster care network and Community-Based Social Services (CBSS) facilitated this process. In 2008, the MoLESP – which has the overall responsibility for the system of social protection and social welfare and is also the lead-agency for child protection - signed a Memorandum of Understanding with UNICEF to develop community-based support for vulnerable children with a view to reducing the need for residential care. With the financial support of donors, most notably the EU, and the technical support of UNICEF, the MoLESP developed a ”Comprehensive Plan of Transformation of Residential Institutions for Children” (2008) to reduce the size of residential care institutions and develop new services for better quality care as well as professional development for staff in residential care institutions, centres for family placement and CSWs. Data from 2008 indicate that only 33 municipalities (out of 168) financed day-care services for children with disabilities for a number of 1,122 children were included, while home-help services were available to only 125 children with disabilities and their families. Since 2008, the number of services kept increasing, reaching more and more children, young persons and their families. Despite this progress, the number of children currently benefitting from community services is relatively small, while the CBSS for at-risk families with young children are under-developed. Moreover, current services cover do not always ensure a holistic approach of needs and multiple vulnerabilities that lead to family-child separation.

Important changes in the education legal framework in 2009 and 2010 allowed for more inclusive education. Practical implementation of inclusive education was supported through the Network for Inclusive Education, providing expert advice to schools and parents, developing best practices by problem solving and facilitating horizontal learning. Efforts to support functioning of Inter-Sectoral Commissions continued, with ISCs functional in 50% of municipalities. To facilitate continuity of reforms, UNICEF lobbied for further implementation of policy frameworks to prioritize equal access to quality education and initiated new strategic partnerships aimed at advancing inclusive education. Progress was made towards developing a monitoring framework, notably through UNICEF’s strategic partnership with the National Education Council and other national stakeholders. The monitoring framework is aimed to become part of the education quality assurance system, with complementary support from the World Bank.

- Despite this progress, ethnic origin, disability and poverty continue to act as obstacles in the access of children from disadvantaged groups to health, education and social welfare services. According to the EC Progress Report for 2012, “children’s rights, particularly the rights of those belonging to vulnerable groups such as Roma, poor children, children with disabilities, children without parental care and street children, are unevenly protected. Roma children are over-represented in the state care system. There are an increasing number of children living in poverty. Inclusive education is still not fully developed. The school drop-out rate is high among Roma children, children with disabilities and children living in remote areas”. The system of early and continuous support for the biological family to prevent child separation is underdeveloped. The child allowance programme is not well targeted.

- As already mentioned, the range of CBSS is unable to respond sufficiently well to the wide variety of needs of disadvantaged children. The delivery of social benefits and social services varies widely across Serbia. Many Local Self-Governments have modest budgets and lack capacity to map out needs and resources, design and implement social inclusion policies in a participative manner, commission specific services and review results. Efforts are needed to improve their capacity across the country to set up, diversify the typology and increase the quality of the CBSS. Further development of CBSS will also to a large extent depend on the implementation of the draft Decree on Special Purpose Transfers, which would help ensure the development of concrete services based at the community level, in line with local and national needs and priorities. It could support disadvantaged municipalities in planning, delivering and monitoring essential new services. While local self-governments are fully responsible for financing their community services, data show that on an average no more that 70% of the total cost is paid out of local budgets, with the rest covered by donors, national budget and other sources. Policy development and assistance from the Ministry of Finance will also have to address the current lack of guidelines and local capacity for social budgeting and accounting.

As far as the legal framework is concerned, child protection in Serbia is ensured through a number of sectors i.e. education, health, justice, law enforcement and social welfare, which together manage and implement a diverse range of protection related laws, regulations and services. At the moment, the country does not have a dedicated law on the protection of children’s rights. There is only a Plan of Action for Children, ”a strategic document of the Government of Serbia which defines the general policy of the Republic towards children through the year 2015”, but not updated since 2004 (the year of its adoption). Child welfare is thus incorporated in various strategies and laws regulating social welfare in general, primarily the Law on Financial Support for Families with Children (2002), the Social Welfare Strategy (2005), the Family Law (2005), and the most recent Social Welfare Law (2011).

The Social Welfare Development Strategy (2005) contains important provisions on the transformation of institutions for residential placement particularly for the children in conflict with the law, children with disabilities and children without parental care. It also regulates family placement and community-based support for families. Based on this national framework, local social welfare strategies have been adopted by 122 municipalities in Serbia.

A priority is the implementation of the Law on Social Welfare (2011), which aims to ensure better protection to the poorest and most vulnerable citizens, including marginalised children, through more efficient financial support such as earmarked transfers to underdeveloped municipalities for community services, promotion of active inclusion and decentralisation of services delivery. The Law prioritizes community-care and limits residential care (including a ban on institutionalization of children under three), brings non-state actors into the social service provision system and strengthens internal oversight and accountability systems. A new quality assurance system of social services providers is under implementation, based on the recently adopted by-laws on service standards and licensing procedures for service providers as well as on modern supervision and inspection mechanisms. A better coordination of activities among related ministries is also needed to develop integrated/cross-sector social services.

Serbia has ratified the United Nations Convention on the Rights of Persons with Disabilities in 2009. It has therefore committed to pay special attention to the particular vulnerabilities of children with disabilities and provide support and services to families of children with disabilities, to reduce the likelihood of abandonment, segregation and concealment. As mentioned above (Figures 2 and 3), too many children with disabilities are still in institutions, while a disproportionate low number are in foster case. Serbia has also ratified the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) which calls the country to end discrimination against girls and women in all forms and take measures to ensure equality between women and men.

In general, the legal framework in Serbia is largely synchronized with European and international human rights standards, and the prospect of EU integration is driving the comprehensive reforms of the social sectors. However, their implementation continues to be hampered by gaps and inefficiencies. Accountability for the implementation of laws and policies is weak. A notable example is in the area of discrimination. Despite strong anti-discrimination legislation, the existing discriminatory attitudes and prejudice have a negative impact on the realisation of children’s rights.  Children with disability are generally perceived as helpless and dependent on others, and there is continuing belief that children with mental disabilities should not be mixed with other children. Roma, poor persons and persons with disabilities are the main groups perceived to be most discriminated against.

Serbia has therefore put in place a number of important child rights accountability mechanisms, such as the Parliamentary Standing Committee on Child Rights (2012) to strengthen the National Assembly’s commitment to children’s rights and improve accountability by overseeing the implementation of relevant laws and regulations; The Ombudsman (2005), mandated to oversee and enhance the protection of human and minority rights and freedoms; The Commissioner for the Protection of Equality (2010) covering discrimination against children as part of its mandate.; The Office for Human and Minority Rights within the Government, with an important coordination role when it comes to addressing and reporting on implementation of international and European conventions.

However, The National Council for Child Rights, responsible for ensuring systematic coordination and monitoring of implementation of children’s rights by the executive branch of government, has not been operational for the last two years. “This constraint has necessitated UNICEF and other partners to facilitate inter-sectoral coordination through issue-specific or ad-hoc mechanisms, which are far less effective and have required significantly more work”.

Implementation of reforms in child welfare also requires an efficient data collection and monitoring system. Progress has been registered in strengthening the analytical and research capacities at national level, especially by improving the capacity of the Republic Institute for Social Protection on the matter. The availability of disaggregated data revealing disparities among vulnerable groups and by gender was significantly improved as a result of the repeated cycles of UNICEF-supported Multiple Indicator Cluster Survey (MICS). However, there are still gaps in the quality and disaggregation of data, also due to some domestic regulations, which constrains a thorough understanding of the nature and scope of some child protection issues and limits the possibility to analyse the effectiveness of the child protection policies and mechanisms. The harmonisation of Government’s system for collecting data on social and economic indicators with EU Standards will improve the national capacity to analyse important indicators and trends.

Serbia is supported in its efforts by several international organisations and donors, most notably UNICEF and the EU. The Human Resources Development Sector Fiches for IPA 2012 and 2013 include measures to support the social inclusion of the most vulnerable groups through more diversified CBSS, respectively measures to promote the social inclusion and poverty reduction of vulnerable and multiply disadvantaged groups with particular emphasis on children. Other donors with programmes supporting child protection and marginalised families are Italy, UN family, World Bank, Switzerland.

## 1.2	 Project Description

The Logframe of the project and the Theory of Change developed by UNICEF (see Annex 1) provide a clear picture of the main features of the project to be evaluated, its logic and results chain, which we resume below.

Overall and Specific Objectives

The overall objective of the Project ‘’Developing community based services for children with disabilities and their families’’ is to strengthen policy frameworks, institutional mechanisms and capacities so that community-based services supporting children with disabilities can be developed and are responsive to the needs of these children and their families.

The specific objective of the Project is to increase the number of children with disabilities that are benefiting from community services that are clearly contributing to their social inclusion.

Purpose and Expected Results

According to the Theory of Change, the main purpose of the Project is to increase the number of children with disabilities who are benefiting from community services that are clearly contributing to their social inclusion, with two main expected results:

- Ministry of Labour, Employment and Social Policy capacity strengthened to monitor, evaluate and supervise decentralized and well-targeted community based social protection services in the Republic of Serbia (national level)

- Municipal authorities, service providers, centres for social work and civil society activists capacitated to fulfil their respective roles in ensuring community services for families with children with disability are accessible and meet set standards and procedural guidelines (local level).

The main project outcomes target, as per Theory of Change, a wide range of national and local government institutions as well as interested civil society representatives, with an overall aim to provide effective CBSS for children with disability and their families. The Theory of Change further develops the two overarching results into a number of core activities for each implementation stage: three groups of activities at the national level (1.1 to 1.3) and four at the municipal level (2.1 to 2.4).

The national level activities are designed to develop a solid legal and regulatory framework for establishing CBSS for children with disability, practical capacity development mechanisms for their functioning as well as data gathering systems for monitoring their impact. The comprehensive approach to development of the legal foundation at the national level plans for a significant step in the reform of the child care system: it ascertains the minimum standards for the future establishment of CBSS in the entire country and not only for the single use of the grant phase of the project.

The set of activities at the local level is built around the EU IPA 2008 grants for establishing CBSS for children with disabilities in the 41 municipalities across Serbia. It is to be noted that these activities do not only focus on the grant recipients but plan for info sessions and capacity building support for all municipalities that are interested in clustering for the development of IPA grant application. For instance, the activity group 2.1 focused on “support to municipal governments to build capacities to select, manage and monitor service providers” represents a crucial link in the results chain which brings together the entire project framework in the form of practical support for establishment of the services at the local level and their effective management in the early stages of operational work. In a logical follow-up, the establishment of the services is coordinated to fall in line with implementation of the regulatory framework from the first Result-related activities (for example, activity group 2.2 Capacity building of service providers so that they can meet set minimum standards and apply procedures in line with guidelines). The results chain is completed by the activities intended to ensure long-term sustainability of the planned results in the form of support to CSWs for the development of their referral and data gathering capacities as well as crucial support to civil society and independent monitoring bodies (the Ombudsman office and the Commissioner for Equality) to strengthen their role of holding government accountable in implementing the adopted policies. Lastly, the entire set of activities outlined in the Theory of Change is oriented towards the impact and sustainability statement “Sustainable community services which provide quality care in line with children’s needs and contributing to their social inclusion”.

Target Groups and Final Beneficiaries

The target groups of the Project consist of Government employees at national and municipal levels, service-providers (including both state and non-state actors), staff of CSWs and Civil Society Organizations (CSOs).

The final beneficiaries and rights-holders of the Project are children and youth with disability and their families (including foster families and single parents at risk of abandoning their child) who are in need of additional support for their social inclusion. Other final beneficiaries are unemployed women (who should have an opportunity to work for community service providers after being trained within the Project) and youth (to be trained and given the opportunity to get engaged as volunteers providing support for children with disability).

Strategic Approach to implementation

The Project has been implemented at two levels: the national level and the municipal (and municipal-cluster) level:

- At the national level there have been three priority areas of work:

- Development of regulatory acts in the field of community-service provision by defining the service standards system, service-provider licensing system and the system of allocating ear-marked funding from national to local level;

- Assisting MoLESP to further develop procedures, guidelines and training packages focused on ensuring that set standards are implemented at local level by municipalities and service-providers;

- Capacity building of MoLESP to implement reforms in a results-oriented manner, including support for setting child welfare indicators, planning/agreeing annual targets and using policy-oriented studies for further policy making.

- At municipal/regional level, priority activities aimed at strengthening the capacity of key actors to facilitate development of quality community services: 41 municipal governments (responsible authorities for development, commissioning, monitoring of community services) grouped in 10 regions across Serbia, service providers (including NGOs and state-run service providers), CSWs (first point of contact and bodies responsible for referral) and civil society activists (whose role is to help put community services further up on the municipal agenda and empower beneficiaries to demand access to their rights).

Financing

The Project under evaluation is part of the Social Inclusion IPA 2008 which consists of three components:

- Technical support to MoLESP and municipal governments, ‘’Developing community based services for children with disabilities and their families’’, implemented by UNICEF on the basis of a Contribution Agreement (total value 2,222,222.00 EUR, out of which the EU contribution is 2,000,000 Eur ) – which is the subject of this evaluation.

- Grant scheme – grants for municipalities clustered within regions in Serbia, directly managed by EUD (total value 3,000,000 EUR);

- Public awareness campaign, implemented by Service contractor (Bernard Brunhes International) and managed by EUD (total value 500,000 EUR); and

Duration

The Project was originally designed to be implemented over a 36-month period (22 April 2010 – 22 April 2013), but it was officially extended in June 2012 for additional 8 months (non-cost extension with end date 22 December 2013). The extension was granted to allow harmonisation of the Project activities with the timeline of the EU Grant Scheme and a smooth continuation of UNICEF technical support to municipal governments and service providers.

The Project is thus in its final phase of implementation, having still to implement several training courses for case managers working in CSWs, a final project conference and final reporting.

Role of UNICEF

UNICEF was in charge of the technical and financial management of the Project and achievement of its objectives and estimated results. In order to do that, UNICEF has acted at national and local level.

At national level, it provided technical support for development of by-laws and other policy documents that regulate community-service provision. It supported the MoLESP in developing community service capacity-building packages and programmes for priority community services for families with children with disability as well as in defining child welfare indicators, mainstreaming them into regular data-gathering systems and using them for monitoring impact of reforms. It also supported the MoLESP in designing and implementing additional studies where more in-depth information / analysis was needed to guide implementation of reforms.

At local level, UNICEF assisted interested municipalities to select, manage and monitor service providers, to cluster regionally for service provision and to apply for and manage grants in a way that meets EU criteria.

It has also worked to increase the capacity of service providers to meet minimum standards and apply procedures in line with guidelines and CSWs to provide adequate support to families and referral of beneficiaries. Last but not least, UNICEF implemented specific activities aimed to strengthen civil society initiatives which are designed to make sure that community services are higher up the agenda of local governments.

Implementation partners

The MoLESP was the main implementation partner of UNICEF, which was supported to create a supportive and regulated environment for the development of community services.

In addition to the partnership with the MoLESP, other important partners which contributed to the implementation of the Project included:

- Republic Institute for Social Protection and Provincial (Vojvodina) Institute for Social Protection – by strengthening monitoring and reporting systems, developing standards of services and building capacities for delivery of community services;

- Centre for Social Policy and Social Work Research (Faculty of Political Sciences, University of Belgrade) – by policy research and documenting beneficiary perspective on positive outcomes of community services on social inclusion of children with disability and their families;

- Centre for Liberal-Democratic Studies - CLDS (social policy and research based think-thank organisation) – through policy research and capacity building of local actors in the area of mapping, financing and costing of community services;

- Amity (NGO) – through capacity building of local actors for outreach and mapping of the most excluded groups;

- Familia (NGO) – through research  on the results of deinstitutionalisation of children with disability;

- Association of Centres of Social Work (professional association) – by gathering evidence  on practitioners’ perspective on case-management application and capacity building needs;

- BCIF – Balkan Community Initiative Fund (NGO) – by building capacities of local CSOs to advocate for sustainability of financing for community services from local budgets;

- MODS (national network of child-rights NGOs), Ombudsman office and Commissioner for Equality – through more systematic monitoring and advocating for the rights of the most marginalized children.

The role of EU Delegation (EUD) was to provide the funds for the implementation of the Project, as well for the other two components of Social Inclusion IPA Fiche 2008 detailed above (grants and public awareness campaign) which are closely connected to the project under evaluation. It has also managed the grant scheme and the contract with the Service contractor (Bernard Brunhes International) for the campaign. The EU Delegation has been also in charge of monitoring the implementation of the Project in close cooperation with UNICEF and the MoLESP.

Implementation arrangements

The Project was managed, from a strategic point of view, by a Steering Committee chaired by the Ministry of Labour, Employment and Social Policy, as primary duty bearer, with representatives of the EUD and UNICEF as members.

The operational management was ensured by a Project Implementation Unit (PIU), based in UNICEF. For the local level component of the Project, a team of consultants have been recruited to work within the PIU to provide continuous technical and administrative assistance in conducting capacity building activities.

During the Project implementation, close coordination with other relevant actors have been ensured, primarily with:

- Cooperazione Italiana – providing support to the process of de-institutionalization of children, with a particular focus on children with disability;

- the Government’s DILS Project (Delivery of Improved Local Services) – focusing on the decentralization of health, education and social protection services (with a particular emphasis on its components related to strengthening of the MoLESP IT system and education inclusion);

- the MoLESP Project ‘’Creation and Implementation of Licensing System for Social Service Providers in Serbia’’ (financed by the Norwegian Government);

- the Social Inclusion and Poverty Reduction Unit (SIPRU) of the Government of Serbia – in the area of mapping community services and relevant inter-sectoral issues.

# 2.	Evaluation of the Project

## 2.1	Purpose, Objectives and Scope

Purpose

According to the Terms of Reference (ToR), appended as Annex 1 to this report, the purpose of this evaluation is to evaluate the final (end) results and achievements of the Project in relation to the project logframe and Theory of Change. The Project is in its final stage of implementation as mentioned in the previous chapter.

The results of the evaluation are aimed to inform the MoLESP in the further operationalization of the Action Plan for the implementation of the Social Welfare Law (adopted in 2011), especially as concerns the child care of the most disadvantaged children and their families. The knowledge generated by the evaluation is also aimed to be used by the independent oversight bodies and NGOs representing vulnerable children in strengthening their monitoring and advocacy role. The lessons learnt and good practices identified by the evaluation are hoped to be useful for Local Self-Governments, too,  in the further development of CBSS for the most deprived and marginalised children. The main evaluation findings and recommendations will be presented and discussed at the Final conference of the Project in December 2013.

Last but not least, this evaluation is a forward looking one as it aims to inform the potential future support that UNICEF, EU and other international organisations and donors could provide for the continuation of reforms in social welfare and in the development of CBSS in particular.

Objectives

The specific objectives of the evaluation, as per ToR, are the following:

| Specific Objective 1 |  | Provide feedback to UNICEF Serbia office and its national counterparts on the soundness (defined as relevance, effectiveness, efficiency, sustainability) and impact of the Project approach in developing responsive community services for children with disability in order to reveal good practices and gaps in approaches, and evaluate Project impact following Project Plan, Project Logframe and Description of the Action. |
| --- | --- | --- |
| Specific Objective 2 |  | Extract general lessons learned and recommendations aimed at further enhancement of the child care system reform. |
| Specific Objective 3 |  | Provide the Delegation of European Union to Serbia with information on impact of their specific support to Child Care System in Serbia |

As far as the scope of the evaluation is concerned, the Project evaluation covers the entire implementation period (22 April 2010 – 22 December 2013) at both national and local levels and all project components, following the way how the project has been conceptualized in the Social Inclusion IPA Fiche 2008, Description of Action, its Logframe and Theory of Change. These documents have been used as main reference documents for the evaluation,  as they capture the activities undertaken, the expected changes they were to produce and the intended impact, described also through outlined baselines and targets. Project monitoring data as well as other data sources listed in the ToR and in Annex 2 as well as the interviews with key stakeholders listed in Annex 3 informed the evaluation and enabled systematic assessment of the project achievements.

Given the fact that the Project has worked in 41 municipalities located in 10 regions across Serbia and considering the available resources and time, field consultations, interviews, focus groups and discussion groups have been carried out only in a selected number of sites, representing 20 % of the regions and municipalities targeted by the local level component of the Project. This sample is described in the following section. The evaluation has addressed the reducing equity gaps in access to community services that promote social inclusion for the most marginalized children with disabilities and their families.

## 2.2	 Methodology

2.2.1 The Methodological Approach

The methodology model which has been used for this evaluation aimed to utilize the best mix of data gathering tools to yield the most reliable and valid answers to the evaluation questions within the limits of resources and availability of data. The evaluation has been carried out in three consecutive phases: Inception/Desk Phase, Field Phase and Synthesis Phase.

I. Inception/Desk Phase

The evaluation commenced on 11 July 2013, after the conclusion of the contract between UNICEF Serbia and Promeso Consulting. The Inception Phase has coincided with the Desk Phase as per our technical proposal. UNICEF Serbia and various project partners and consultants have kindly provided a comprehensive set of documents, relevant for this evaluation.

The initial documentation review was understandably used to inform the evaluation team on the background and basic aspects of the project in order to establish its link with the national policies and Serbia’s international obligations in child care development. In that respect, the evaluation team reviewed the entire IPA 2008 project documentation (with focus on the component implemented by UNICEF), national policy papers, legislation, strategies and action plans in the area of child protection and social welfare. It has also reviewed the EC Progress Reports 2008-2012 and other accession-related papers, such as the “National Programme for the Integration of the Republic of Serbia into the European Union”, as well as the IPA Multiannual Indicative Programme Document 2011-2013 for Serbia and the Government’s ”Needs of the Republic of Serbia for International Assistance in the Period 2011-2013”. Attention was also given to the reports of projects financed by other donors that address the needs of children with disabilities, licensing of social service providers and decentralisation of social protection services, i.e. the Italian Development Cooperation, Norwegian Government and the World Bank. The full list of documents reviewed for the purpose of this evaluation is appended as Annex 2 to this report.

This documentation review phase was also used for the development of data collection and evaluation instruments to be used in the field and synthesis phases of the evaluation, including:

- Evaluation Matrix, grouping the evaluation questions under the five evaluation criteria (appended as Annex 4)

- Interview Guides for semi-structured interviews, focus groups and discussion groups (Annex 5)

- Performance Rating scale for Project’s relevance, effectiveness, efficiency, impact and sustainability as well as for the overall Project performance

- A Sample of projects for in-depth review, drawn up on the basis of several sampling criteria.

The Inception/Desk Phase (July-August 2013) ended with the drafting of the Inception Report, which included a revised methodology, a detailed work plan, the proposed Sample and the full set of data collection and evaluation tools. The Inception Report has been submitted to UNICEF Serbia on 19 August 2013.

II. Field Phase

This phase has been devoted to the collection of data from key stakeholders at national and local levels, based on the evaluation instruments developed during the Inception/Desk Phase. More specifically, the following activities have been carried out:

- semi-structured interviews with key stakeholders:

- UNICEF management and project team (PIU, national consultants and regional mentors);

- MoLESP: Secretary of State (Steering Committee member), Department for Family Welfare and Social Protection, Disability Fund, IT Department, DILS project manager, national consultant of the Norwegian project on licensing of social services providers;

- EU Delegation, as international financing institutions of the Project;

- implementation partners: Republic Institute for Social Protection, University of Belgrade, Centre for Liberal Democratic Studies, Amity, Familia, Association of CSWs, SIPRU;

- monitoring and advocacy partners: Ombudsman, Commissioner for Equality, MODS, TRAG Foundation (former BCIF), Office for Cooperation with Civil Society;

- Ministry of Education - cross-sector work on inclusive education, involving UNICEF and the Project;

- other: Chamber of Social Welfare, the Standing Conference of Towns and Municipalities.

- 6 site visits to Čoka, Novi Kneževac, Zemun (Čoka cluster), Aleksinac, Ražanj and Niš (Aleksinac cluster) for an in-depth review of the selected projects in the Sample;

- 2 discussion groups in Čoka and Aleksinac with project implementation teams, CSWs, service providers and representatives of municipalities during the site visits (one in each municipality cluster);

- 2 focus groups with parents/families (final beneficiaries) in Čoka and Aleksinac during the site visits (one in each municipality cluster);

The following methodological aspects need to be highlighted:

- Semi-structured interviews with key informants at national level have been used to collect qualitative data and capture various perspectives on the way the project addressed the complexity of issues in child care reform, how the project worked and how could have been worked better for advancing the implementation of reforms.

- Beyond the interviews at national level, the evaluation team designed a representative sample of local clusters for site visits out of the 10 clusters and 41 municipalities in which the project was conducted. The site visits were necessary to conduct interviews with stakeholders and beneficiaries at local level as well as to obtain factual evidence by visiting the respective community-based services i.e. technical capacities (location, working conditions, equipment) and contact with beneficiaries (general mood and satisfaction, current numbers of beneficiaries and employees, etc). The sampling criteria and justification for the selection of 2 clusters and 6 municipalities can be found below in section 2.2.3.

- The evaluation team wanted to receive in-depth feedback from as many stakeholders as possible during the site visits to the 6 municipalities and therefore it was often not possible to conduct semi-structured interviews with individual respondents. Therefore, the team organised discussion groups with project implementation teams, CSWs, service providers and representatives of municipalities in order to collect as many different views as possible for assessment of the project’s functioning and results at the local level. Two discussion groups were organized in Čoka and Aleksinac, one in each lead municipality of the visited cluster.

- Contact with the direct beneficiaries is crucial for the impact assessment. Given the timeframe for data collection and available resources, it was not feasible to conduct a survey of final beneficiaries at the national level. Instead, the evaluation team used the focus groups with parents/families (final beneficiaries) in Čoka and Aleksinac during the site visits to collect vital sample of impressions as well as the satisfaction surveys of final beneficiaries carried out by the Faculty of Political Science (University of Belgrade) - an excellent source of information and cost saving opportunity.

The Field Phase ended with a debriefing of UNICEF concerning the preliminary findings, conclusions and recommendations of the evaluation team. The debriefing took place on 27 September 2013.

III. Synthesis Phase

Information and facts collected during the first two phases have been analysed and integrated in this draft Evaluation Report in line with the ”UNICEF Evaluation Report Standards” (Evaluation Office, UNICEF NYHQ, September 2004). The analysis was based on the Evaluation Matrix and the Performance Rating scale developed during the Inception/Desk Phase of the evaluation process. More specifically, the five standard OECD/DAC evaluation criteria, set in the ToR, have been endosed by the evaluation team in the Inception Report for several reasons:

- they are sufficient to provide a sound assessment of the quality, value and significance of the aid intervention, are all necessary and equally important;

- they are fully appropriate for the evaluation purpose, after careful examination of the project’s logical framework and theory of change;

- they are in line with internationally recognised best practice for the final evaluation of a project and also consistent with the European Commission’s methodology for evaluating its external assistance (which is the donor of the project).

The project evaluation criteria have been approached as follows:

- Relevance: The assessment of the project relevance has been based on the analysis of the national and local context, the challenges of the child care reform process and the needs and priorities of various stakeholders and beneficiaries (e.g. legal framework, evidence-based policies, capacity building, etc.).

- Effectiveness: Using the project’s Logframe and Theory of change, the evaluation team analysed to what extent the results obtained following the implementation of activities have contributed to the attainment of the planned objectives. Using evidence collected during the first two phases of the evaluation, the report explains the factors that contributed or hampered the achievement of results in terms of supporting the development of regulatory framework and development of capacities of various stakeholders at national and local levels (MoLESP, institutes for social protection, local authorities, CSWs, service providers, independent state and non-state actors, etc.) to regulate, promote, set up, run, monitor and supervise (as the case) services for children with disability and their families. Analysis of coordination and synergy between the activities on national and local levels has been also done. In addition, the report discusses the indirect effects (positive or negative) of the Project.

- Efficiency: The report analysed how well UNICEF organized itself in delivering its work with regard to managerial and budget efficiency of the two pronged delivery modalities i.e. at national and at the municipality level. Analysis of efficiency was based on the assessment of outputs/activities in relation to project inputs, costs and planned timelines. The report also incorporates discussion of issues related to assessment of cost-effectiveness of CBSS developed within this Project. Synergy of the Project with the other two components of IPA 2008 Social Inclusion (grant scheme and public awareness campaign) and with similar interventions and projects was reviewed  as well.

- Impact: In the case of impact assessment, the key task of the evaluation team was to examine to what extent the project contributed to changes in the final beneficiaries’ well-being and social inclusion, especially of children with disability and their families. The team also assessed if the project has accelerated the pace of change and if it gave direction to reforms in the area of sustainable development of CBSS for children with disabilities and their families.

- Sustainability: The evaluation team reviewed the sustainability factors in terms of project design, process, implementation and national context. Sustainability was analysed from various perspectives: legal, institutional, capacity building, financial. Given the fact that the Project was not finished at the time of this evaluation, the assessment of sustainability focuses on the likelihood that outcomes and benefits generated by the project continue to exist without or with a lower level of external support. The report highlights the factors that facilitated or decreased the sustainability prospects of the results of the Project.

The Draft Evaluation Report has been released in the last week of October 2013. The feedback which will be received from UNICEF and other stakeholders will be incorporated in the Final Evaluation Report, due for end November 2013. The evaluation team will also prepare a material with the key evaluation findings and recommendations for dissemination and presentation on the occasion of the Final Project Conference, planned for the beginning of December 2013. The Synthesis Phase lasted for one month i.e. October 2013.

2.2.2 The Evaluation Questions and Performance Rating

The ToR specify:

- 26 Evaluation Questions (EQ) linked to the five evaluation criteria (relevance, effectiveness, efficiency, impact and sustainability);

- 4 EQ linked to human rights-based approach and several cross-cutting issues.

Based on this, a comprehensive Evaluation Matrix has been developed (Annex 4). All EQs – formulated as in the ToR or slightly reformulated - have been assigned to a specific evaluation criterion (see Table 1 below). In order to streamline the analysis of results and evaluation reporting, several EQs in the ToR have been merged into broader questions. As a result, a number of 24 EQs have been included in the Evaluation Matrix. For each EQ, one or several judgement criteria have been included as well as related quantitative and qualitative indicators, as the case. Sources of information and methods of data collection have been also introduced in the Matrix.

###### Table 1. Grouping of Questions and Issues in the Evaluation Matrix

| Group | Description | No. of EQ | EQ |
| --- | --- | --- | --- |
| EVALUATION CRITERIA |  |  |  |
| 1 | Relevance | 4 | EQ 1-4 |
| 2 | Effectiveness | 6 | EQ 5-10 |
| 3 | Efficiency | 3 | EQ 11-13 |
| 4 | Impact | 3 | EQ 14-16 |
| 5 | Sustainability | 5 | EQ 17-21 |
| CROSS-CUTTING ISSUES |  |  |  |
| 6 | Child rights, equity, gender and ethical issues | 3 | EQ 22-24 |

The overall rating of the Project performance has been determined by separately evaluating and ranking the five evaluation criteria specified in the ToR. Each criterion was assigned a scale point between 0 and 3. A descriptor corresponding to each scale point was also assigned. The average of the values for the evaluation criteria ratings was the overall project assessment rating. Fixed cut-off points were used to assign appropriate descriptors (highly satisfactory, satisfactory, moderately satisfactory, moderately unsatisfactory, unsatisfactory and highly unsatisfactory) to the aggregate numeric rating. The table below summarizes the approach and shows the relationship between the evaluation criteria, rating descriptors and scale points.

###### Table 2. Performance Rating

| Evaluation criterion | Definition according to the ToR | Rating descriptor | Scale point |
| --- | --- | --- | --- |
| Relevance | The extent to which the Project responded to the needs of stakeholders and beneficiaries. | Highly relevant Relevant Partly relevant Irrelevant | 3 2 1 0 |
| Effectiveness | The extent to which the Project met its outcomes as defined in the Project Logframe and Theory of Change. | Highly effective Effective Moderately effective Ineffective | 3 2 1 0 |
| Efficiency | The extent to which the management of the Project ensured timeliness and efficient utilization of resources. | Highly efficient Efficient Moderately efficient Inefficient | 3 2 1 0 |
| Impact | The extent to which the Project increased system’s capacities to ensure that more children with disability benefit from community-based services in a way which contributes to their social inclusion. | High impact level Good impact level Low impact level No impact | 3 2 1 0 |
| Sustainability | The extent to which the achieved Project outcomes are sustainable. | Most likely Likely Less likely Unlikely | 3 2 1 0 |
| Overall Rating (weighted average of above criteria) | Highly Satisfactory: overall weighted average 2.5 or more. Satisfactory: overall weighted average between 2.0 and less than 2.5. Moderately Satisfactory: overall weighted average between 1.5 and less than 2.0 Moderately Unsatisfactory: overall weighted average between 1.0 and less than 1.5 Unsatisfactory: overall weighted average between 0.5 and less than 1.0 Highly Unsatisfactory: overall weighted average less than 0.5. |  |  |

Given the fact that the project is financed by the EU, the evaluation team suggested the overall rating to follow the evaluation guidelines of DG Enlargement, as follows:

- Highly Satisfactory (overall weighted average of 2.5 or more) = The project achieved at least acceptable progress toward all major relevant objectives; very good cost-effectiveness level; high probability that the outcomes and impact will be sustainable; the project has been relevant over its lifetime; no major shortcomings identified.

- Satisfactory (overall weighted average between 2.0 and less than 2.5) = the project achieved acceptable progress toward all major relevant objectives;  no major shortfall has taken place; outcomes and impact will, on the whole, be sustainable; the project has been relevant over its lifetime and its implementation and operations have been efficient.

- Moderately Satisfactory (overall weighted average falls between 1.5 and less than 2.0) = the project achieved acceptable progress toward most of its major relevant objectives; even though there was a shortfall in achieving the estimated outcomes and impact and full sustainability is unlikely, some Project components achieved major benefits, for example, equivalent to at least half the level originally expected; the project has been relevant over its lifetime; no major shortcomings were identified.

- Moderately Unsatisfactory (overall weighted average falls between 1.0 and less than 1.5) = the project did not make acceptable progress on most of its major relevant objectives; low probability that achievements will be sustainable; (possibly) changes occurred throughout the life of the project, but no corresponding change of focus has been operated.

- Unsatisfactory (overall weighted average falls between 0.5 and less than 1.0) = the project did not make acceptable progress toward most of its major relevant objectives; very high costs; no or very low impact level; unsustainable achievements; major shortcomings were identified.

- Highly Unsatisfactory (overall weighted average is less than 0.5) = the project did not make acceptable progress toward any of its relevant objectives; negative effects may be apparent; major shortcomings were identified.

2.2.3 Evaluation sample

A number of 10  municipality clusters (regions), including 41 municipalities, have been selected by the EUD for grant financing (component A of IPA 2008 Social Inclusion). Each cluster consisted of 4 municipalities, with the exception of one case where 5 municipalities were engaged. They implemented a total of 52 services (29 home assistance, 17 day care, 4 respite care, 1 hypo-therapy and 1 accessible transportation) for 930 children (according to the final reports of the local projects). The selected projects were allocated similar grant amounts of approximately 300,000 EUR on average. The implementation duration was 20-24 months. Apart from desk review of relevant documentation, semi-structured interviews with key stakeholders and focus/discussion groups, the evaluation methodology included site visits to a sample of projects and municipalities for in-depth review. Indeed, given the time constraints of this evaluation and in line with usual evaluation practice as well as based on the ToR and further agreement with UNICEF, a sample of local projects has been constructed, based on several sampling criteria, as follows:

- Typology of services i.e. representation of the three main types of services financed by the grant scheme (home assistance, day care, respite care)

- Combination of services i.e. presence of at least two different services in the selected projects

- Rural/Urban regional balance i.e. projects implemented in Regions I Predominantly Urban and Regions III Predominantly Rural  (according to OECD definition)

- Territorial distribution of municipalities supported by the grant scheme to run CBSS (most municipalities involved in the 10 projects are located in Vojvodina - 30%, Central Serbia - 20%, Eastern Serbia - 20% and Southern Serbia - 20%)

- Development level of municipalities within the clusters i.e. inclusion of projects implemented by municipalities which belong to various development groups, according to the Serbian legislation, from Group 1 (most developed, with GDP/capita above the national average) to Group 4 (the most underdeveloped, with GDP/capita below 60% of the national average)

- Typology of service providers i.e. projects including services which are implemented by various service providers (Centres for Social Welfare – 61% of projects, NGOs – 30%, schools – 5%)

The Sample which resulted after the screening of all local projects against the sampling criteria above was composed of 2 projects (20% of the number of projects):

      - “Partnership across Serbia”, Čoka cluster (Čoka, Novi Kneževac, Topola, Zemun);

      - ”Step by Step towards Community”, Aleksinac cluster (Aleksinac, Ražanj, Crvenikrst, Gadžin Han).

These projects amount to € 577,823 (19.4% of the overall EU grant allocated for projects) which financed 9 Services (17% of total services) addressed to 150 children (16% of total) from 8 municipalities (19.5% of total number). The features of the sample are presented in Table 3.

###### Table 3. The Evaluation Sample

|  | Total | Čoka cluster | Aleksinac cluster |
| --- | --- | --- | --- |
| Total no. of projects | 2 | 1 | 1 |
| Typology of services (main types) - Home assistance - Day care - Respite care | 9 4 4 1 | 4 1 3 - | 4 3 1 1 |
| Combination of at least two services |  | yes | yes |
| Rural/Urban Regional Balance - Region I Predominantly Urban - Region III Predominantly Rural | 1 1 | Yes No | No Yes |
| Territorial distribution of municipalities - Vojvodina - Central Serbia - South-Eastern Serbia | 8 2 2 4 | 4 2 2 - | 4 - - 4 |
| Development level of municipalities - Group 1 - Group 2 - Group 3 - Group 4 | 2 2 1 3 | 1 2 1 - | 1 - - 3 |
| Typology of service providers - Centres for Social Welfare - NGOs - Schools | 6 1 1 | 2 1 1 | 4 - - |

2.2.4 Evaluation constraints

There have been some constraints which were faced by the evaluation team, as follows:

- a focus group with unemployed women (final beneficiaries), who benefitted of training to be potentially employed in community services as carers was planned in Zemun (Coka cluster); however, only two persons showed up (a men and a women) and were interviewed. The evaluation team has therefore relied on interviews with training providers who trained these women and on interviews with CSWs and other service providers which recruited and employed them for the delivery of services;

- the Project includes among its final beneficiaries “youth who will receive training and have the opportunity to engage as volunteers providing support for children with disability”; due to time constraints and difficulty of calling them together in a focus group, the evaluators were unable to meet such volunteers. Analysis of their involvement was therefore done based on the final reports of the clusters and interviews with several municipality representatives and service providers during the site visits.

## 2.3	 Evaluation Design

The evaluation was designed to assess the relevance, efficiency, effectiveness, impact and sustainability of the Project based on IPA 2008 Social Inclusion fiche, Description of Action and its Logframe and Theory of Change, including indicators that the Project planned to use for monitoring performance and attainment of estimated results.

The evaluation used a non-experimental design, as requested by the ToR, whereby the children with disability and their families (the so-called “treatment groups”) were compared before and after the project implementation. A counterfactual evaluation design has been impeded by the lack of reliable data both at the level of ’treatment’ and ’control’ groups, as explained in various sections of this report, and thus by the difficulties in constructing groups of reasonable numbers to mobilise the power of statistics.

The design of the evaluation methodology combined a Results-Based Management with a Human Rights-Based Approach to programming and evaluation i.e. achievement of planned results through morally-acceptable processes to realise human rights.

The Human Rights-Based Approach applied by the evaluation team was guided by five core principles: normativity, participation, non-discrimination, accountability and transparency, and by the Common Understanding on Human Rights-Based Approaches to Development Cooperation and Programming, approved by the United Nations Development Group in 2003:

- All programmes of development cooperation, policies and technical assistance should further the realization of human rights as laid down in the Universal Declaration of Human Rights and other international human rights instruments.

- Human rights standards contained in, and principles derived from, the Universal Declaration of Human Rights and other international human rights instruments guide all development cooperation and programming in all sectors and in all phases of the programming process.

- Development cooperation contributes to the development of the capacities of ‘duty bearers’ to meet their obligations and/or of ‘rights-holders’ to claim their rights.

Attention was also given to the evaluation of the gender mainstreaming, gender equality and women’s empowerment in the project, in line with Serbia’s international commitments, most notably CEDAW and UNICEF Gender Policy (2010) which states that UNICEF aims to work with partners to pursue gender equality and the equal rights of girls and boys “to contribute to poverty reduction and the achievement of the Millennium Development Goals through results-oriented, effective and coordinated action that achieves the protection, survival and development of girls and boys on an equal basis.”

The Evaluation assessed the extent to which the project outcomes contributed to the achievement of children’s rights and addressing of gender sensitive issues. In this respect, the Evaluation Matrix included specific evaluation questions, as follows:

- Has the project actively contributed to the promotion of child rights?

- Has the project reflected gender mainstreaming issues?

- To what extent and how the project ensured an equity focus? Was the design of the Project ethical? How was the balance of cost and benefits to participants (including possible negative impact) considered during the project implementation?

The evaluation used to the extent possible disaggregated data by gender and disability groups.

The evaluation team gave the opportunity and encouraged active participation of all key stakeholders in the evaluation process by providing data and information, indicating the top priorities for the continuation of reforms in the area of social welfare of children with disability and their families as well as by validating the findings and recommendations of this evaluation report. Given some evaluation constraints, women (trained to become carers) and youth (volunteers in CBSS delivery) have not been directly involved in the evaluation process; however, their perspective has been considered using indirect forms of assessment and consultation, as explained in chapter 2.2.4 above.

During data collection, the evaluation team ensured that the evaluation process is ethical and that participants in the process can openly express their opinions, protecting the confidentiality of their answers. All interviewed people were informed in advance about the purpose and the themes of the interviews, focus groups and discussion groups, as the case. A special attention was given during the focus groups with parents of children with disability to ensure that the questions were well understood and that the evaluation team is sensitive to beliefs, emotions and customs of participants. The evaluation results were disseminated to all key stakeholders and presented during the final project conference on 4 December 2013.

# 3.	Findings and Analysis of Results

## 4.1	Relevance

EQ: To what extent are by-laws and other policy documents, developed by the Project, that regulate community-service provision relevant for child-care reform process?

As noted in the first chapter of the report, the Republic of Serbia does not have a dedicated law on the protection of children’s rights and child welfare. The Plan of Action for Children (adopted in 2004) mentions the need to ”improve the position and the realisation of the rights of children with developmental difficulties” but rather in general terms, without sufficient precision as far as course of action is concerned. As a result, child welfare is incorporated in the strategies and laws regulating social welfare generally, most notably the Social Welfare Strategy (2005) and the Social Welfare Law (2011).

The by-laws and policy documents developed by the Project are mainly focused on implementation of the Social Welfare Law as it pertains to child welfare in the wider sense and development of legislative mechanisms for establishing CBSS for children with disability in particular. Based on the agreement and in close coordination with the MoLESP’s assistant minister and her team, UNICEF project staff focused on four areas of the Social Welfare Law implementation, as detailed in Box 1.

Box 1. Areas of By-Laws Development in Social Welfare, IPA 2008 Project - Setting standards for community-based services, including data-management and record-keeping. - Financing of services, including the development of mechanisms for ear-marked transfers to municipal governments, financial transfers (including disability allowance) as well as the design of mechanisms for costing of services and criteria for beneficiary participation in covering the costs of services. - Regulatory mechanisms, in terms of defining the mechanism for licensing of service providers. - Defining mechanisms for holding professionals in the system accountable, especially in relation to their direct work with beneficiaries. Source: Description of the Process for Developing By-Laws, UNICEF project document

The standards and other policy documents pertaining to CBSS have been designed to enable clear regulation of the establishment, operation and financing mechanisms for all services relevant to children with disability and their families, i.e. day-care, home help, child personal assistance, supported living,  residential placement, respite care and small group homes. The full list of developed by-laws, rulebooks, guidance documents and instructions is provided in Table 8 below. Their content is fully in line with the 2005 Social Welfare Development Strategy in terms of addressing the most pressing needs for the reform of social welfare: “The number of citizens in need of support due to physical and mental impairments exceeds the number which, usually as a result of the lack of other community-based services (day care centres, small group homes, etc.) resides in institutions, while their rights are endangered as a result of an inability to satisfy their basic needs in an adequate manner”. The strategy identifies the establishment of social services “which support life in the community” as one of the priority goals of the social welfare reform.

The relevance of by-laws and regulations developed by the Project can also be determined in respect to Serbia’s commitments for the observance of human rights standards and compliance with EU membership criteria. In its report presented to the Pre-sessional Working Group of the United Nations Committee on the Child Rights (2008), UNICEF underlined that ”the lack of family support service, affordable, child-friendly and community-based alternatives for children with disabilities is striking” and included in its Country Programme Action Plans (CPAP) specific support for ensuring availability of such services. In its Concluding Observations (2008), the Committee on the Rights of the Child noted “…the general lack of resources and specialized staff for children with disabilities. It is also concerned at the prevailing societal attitudes which are conducive to stigmatization of children with disabilities.” As mentioned in Chapter 1 of the report, Serbia has ratified the United Nations Convention on the Rights of Persons with Disabilities in 2009 and committed to pay special attention to the particular vulnerabilities of children with disability, including support and services to their families.

In its annual report on the progress of Serbia towards fulfilling EU membership criteria in 2009, the European Commission noted that the government started to take measures aimed at deinstitutionalization of mental healthcare (including children) and at developing and building the capacity of CBSS. However, the EC also concluded that “this reform is proceeding at a slow pace. The related community-based services remain insufficiently developed.” In 2010 and 2011, the European Commission again noted that the government managed to achieve certain progress in terms of establishment of CBSS for persons with disabilities, but as the year before, it added that “both resources and capacities need to be strengthened” and that ’the availability of community-based services across the country is still limited”.

Without any doubt, the set of more than thirty pieces of legislation and implementation tools including by-laws and decrees as well as soft law instruments (rulebooks, guides and instructions) developed under the Project and submitted to the MoLESP for adoption procedure are in line and highly relevant to the child care reform process as it is currently being implemented in Serbia (through the law on social welfare). The secondary legislation tools describe the minimum standards for all currently available types of services for children with disability (day care centres, respite care, home assistance etc.) while also allowing for the development of innovative services within the set standards. The relevance of the legislation for the child care reform process is further strengthened by the legislative focus on the professionals providing childcare services by setting personnel standards through development of accountability regulations. Perhaps the most important result of the by-laws development process is the financial regulation (decree) on ear-marked transfers from the national budget to the poorest and least developed municipalities, aimed at ensuring sustainability of services.

EQ: How relevant for child-care reform are community service capacity-building packages / programmes for priority community services that support families with children with disability? How relevant for the child-care reforms are capacity building activities implemented within the project?

The need for “increasing professional competencies of social welfare employees” especially in terms of “education in the application of new standards, accreditation of new programmes and services, licensing, and the introduction of a system for professional advancement” has been clearly identified in Serbia’s Social Welfare Development Strategy from 2005. The strategy does not include explicit baseline information on capacities, training programmes and employee standards; however it calls for the “creation and accreditation of educational training packages, plans and programmes, for educating social welfare professionals”. The strategy is basically indicating that the training content and formats for social welfare reform were either out of date or lacking at the time. The afore mentioned Concluding Observations of the Committee on the Rights of the Child from 2008 note that “the lack of a systematic support system and multisectoral service provision” in supporting children with disability and their families is also due to “lack of well-trained social workers.”

The situation in terms of educational and training needs has become additionally complex in 2008 when the Rulebook on the organization, norms and standards of the CSW introduced a case management approach which required a new set of skills from state social workers. Although the Republic and Provincial Institutes for Social Protection immediately delivered a series of case management trainings for the social workers, the process is still on-going with estimated 200 employees yet to be trained in the practical application of the 2008 Rulebook. One of the Project deliverables, a research conducted by the Association of Centres for Social Work (partner in the Project), focusing on the implementation of the 2008 Rulebook indicates that more than 30% of the CSWs’ case managers are not satisfied with the clarity of procedures, suggesting further training and development of additional manuals. The Annual Reports of the Republic Institute for Social Protection indicate that the providers of child welfare services (CSWs’ employees but also other providers such as NGOs) have a continuous need for development and availability of accredited training programs which would accompany the new regulations for implementation of the Social Welfare Law.

The capacity building packages developed by UNICEF and the Institutes for Social Protection, as partners in the Project, have covered three main aspects of training support to direct service providers and stakeholders in local self-governments: 1) establishment and management of child care services (including development of EU grant applications and management); 2) identification and supporting families of children with disability; and 3) capacity building of CSWs’ professionals for the process of case management and referral. The legacy of centralized governance in Serbia, which was in place for many decades, is a system-wide weakness of the local self-governments and not only in the field of social welfare. Local self-governments, crucial duty-bearers at local level, are in charge of setting up and financing social services at municipal level. However, many other competencies in social welfare, especially in terms of cash benefits, are dependent on the central institutions and the national budget, resulting in low capacities at the local level and general political lack of interest of municipalities in developing community-based services. Therefore the capacity building packages which included trainings on EU grant application development and grant management were essential, as a first step in setting up the new services and remodelling the existing ones. A number of CBSS for children with disability that were developed through the Project, such as home assistance, child personal assistance and respite care, are essentially pilot efforts since they are being introduced for the first time into the Serbian social welfare system. As a result, four training packages focused on the development and running of the new services according to the adopted standards are of highest relevance for initiation of the system-wide child care reform process. Manuals and guidebooks developed by the Provincial Institute for Social Protection, partner in the Project, for setting up of new services are of essential importance for further capacity development efforts in the municipalities which are not covered by the project.

Identification of children with disability who did not previously use any of the CBSS or social welfare benefits is of utmost importance for the successful continuation of childcare reform in Serbia. During the field visits, the evaluation team learnt about many examples of children who did not leave home confinement for years due to stigmatization or lack of support to their families. There is no reliable data on the number of “invisible” children with disability in Serbia as the only available source of information is in the form of crude numbers on cash benefits for some families and these numbers are also plagued by huge exclusion and inclusion errors as recently indicated by a research on the child allowance program in Serbia. The UNICEF Project team correctly projected that hundreds of children with disability, in need of support, are waiting for identification since rural and hardly accessible areas were largely excluded from the CSWs cash benefit numbers. In addition, even the families without financial difficulties were not able to be registered by the system simply due to the lack of services in the respective municipality or lack of professional support in overcoming social stigmatization and exclusion. In that respect, the trainings provided by Amity NGO (partner in the Project) to the CSWs and municipal workers as well as to volunteers were highly relevant for achieving one of the main project goals oriented towards the identification and inclusion of the “invisible” children with disability - one of the most disadvantaged and marginalised category of rights-holders among the children population in Serbia - in at least one of the new services provided in the municipality. Last but not least, the design of the trainings to meet the needs of social workers for better case management and referral skills, as identified in numerous national and international documents cited above, is certainly relevant and critical for successful access of the most vulnerable children to CBSS.

EQ: To what extent are groups of activities related to strengthening monitoring and evidence-based policy making capacities relevant for guiding implementation of child-care reforms?

The lack of relevant data in respect to the provision of social welfare is not only an issue in respect to children and children with disability but a more system-wide problem in the social welfare organization in Serbia. The CSWs have, until recently, registered their data in hard copy formats which were difficult to interpret and use for informed policy reform decisions at central or local government levels. The need for development of data collection and monitoring mechanisms has been acknowledged back in 2004 in the National Plan of Action for Children which foresaw specific activities for the ”development and on-going monitoring of defined poverty indicators for children”. It was also clearly highlighted in the Social Welfare Development Strategy (2005) and the Concluding Observations of the Committee on the Rights of the Child from 2008, which recommends the Government to ”collect adequate statistical data on children with disabilities and use such disaggregated data in developing a comprehensive and specific national policy on disability which promotes equal opportunities of persons with disabilities in society”. In its Concluding Comments (2007), the Committee on the Elimination of Discrimination against Women also noted that Serbia lacks information and statistics about particularly vulnerable groups of women, such as disabled girls and women “who often suffer from multiple forms of discrimination”.

It is however unrealistic to expect that a project dedicated to children with disabilities would address the numerous systematic problems of data collection and child welfare indicators development at significant scale. Indeed, the Project activities were more intended to coordinate and assist other national and donor initiatives aimed at developing social welfare indicators and databases (UNICEF support for Development Information database, UNICEF-supported MICS, Government’s DILS project, SIPRU work on monitoring social inclusion and on developing a monitoring framework for inclusive education, etc.).

In addition, the UNICEF Project team and MoLESP commissioned a number of studies which would provide the fundamental quantitative and qualitative data needed for effective continuation of the child care reform in Serbia. The research studies supported by the Project are markedly relevant as the first steps in creating reliable indicators and data collection mechanisms in the area of social protection of children in Serbia and of children with disability in particular.

The whole lot of Project activities devoted to strengthening monitoring and evidence-based policy making capacities were relevant and consistent with UNICEF CPAP 2011-2015 for Serbia, which aims to assist the national authorities use a reliable sex-disaggregated data system for planning, budgeting and monitoring to address child poverty and social exclusion”.

## 4.2	Effectiveness

EQ: Have the planned results been achieved to date (quantitative and qualitative)?

According to the main planning documents of the Project, including the Description of Action, its Logical Framework and Theory of Change, there have been two overarching results which UNICEF strived to achieve through numerous multilevel sets of activities (see Table 4 below).

###### Table 4. Planned Results and Indicators of the Project

| Results | Objectively verifiable indicators |
| --- | --- |
| Result 1: Ministry of Labour and Social Policy capacity strengthened to monitor, evaluate and supervise decentralized and well-targeted community-based social protection services in the Republic of Serbia | - Regulatory documents on community service standards, service-provider licensing and financing of service provision developed and adopted. - Data for child welfare indicators available in official data gathering systems and accessible. |
| Result 2: Local Municipal authorities, service providers, centres for social work and civil society activists capacitated to full-fill their respective roles in ensuring community services for families with children with disability are accessible and meet set standards | - Number of community services for children with disabilities and number of beneficiaries continually on the increase in 2010, 2011 and 2012. - Number of children in institutions continually drops. - Municipal governments fund services in line with minimum standards. |

Source: Project Logframe

The main set of activities pertaining to Result 1 supported the MoLESP in their efforts to implement the complex Social Welfare Law (2011), especially in respect to regulating provision of the community services under the new legislation (Activity 1.1). Simultaneously with support to the legislative process, UNICEF assisted the Ministry, as major duty-bearer for children’s rights at national level, and the Republic and Provincial Institutes for Social Protection in developing community service capacity building packages (Activity 1.2), including training programmes, manuals, and instructions, for effective establishment and enforcement of quality standards for new and existing municipal services dedicated to children in need. For the achievement of Result 1, UNICEF has also implemented a series of activities related to the development of child welfare indicators (Activity 1.3) and their mainstreaming into the regular data gathering systems of the MoLESP and the social welfare system in general. The responses to the next Evaluation Questions on project effectiveness provide details on achievements related to the regulatory documents, continuous professional development and child welfare indicators.

The second large set of activities pertaining to Result 2 of the Project included technical assistance provided by UNICEF and its project implementation partners in order to initiate the EU grant application process, support the establishment of community services and ensure their efficient functioning over the course of the project in the 41 awarded municipalities. During the first year of implementation, the project team conducted 9 one-day info sessions on EU grants and 4 one-day workshops on project proposal development, creation of clusters and community services for representatives of 173 municipalities. Out of that number, 93 (53%) were involved into the organized system of support through trainings and mentoring aimed to develop project applications following the call for proposals launched by the EUD for IPA 2008 EU grant scheme. As a result of the selection process, the EUD awarded grants to 10 clusters (41 municipalities) out of 22 clusters (89 municipalities) which applied. Data collected by the evaluation team from the interviews at the EUD and field visits to the two municipality clusters included in the evaluation sample suggest that the mentoring and assistance provided by UNICEF was crucial for successful application development. The initial information sessions and trainings were used by municipality representatives to exchange ideas on clustering and even conclude first unofficial commitments in terms of future partnerships and application development. Upon establishment of initial relations among partner municipalities, the project team provided essential assistance in terms of developing formal agreements between the partners which defined the lead municipality and established local PIUs. This was especially important in terms of determining the modality for the flow of funds within the cluster, aiding timely implementation of the planned activities. With establishment of clusters and successful completion of the grant application procedure as well as with the delivery a three-day training on financial management and reporting for EU grants complemented by on-going technical assistance from regional mentors, UNICEF and MoLESP managed to achieve most of the project objectives set for first stage of the project implementation (Year 1), namely in respect to Activity 2.1 on supporting municipal governments ”to cluster regionally for service provision and to apply for and manage grants in a way that meets EU criteria”.

Another set of activities within Result 2 was related to building municipal capacities to “select, manage and monitor service providers” (Activity 2.1) and the capacity of service providers so that ”they can meet set minimum standards and apply procedures in line with guidelines” (Activity 2.2). This was a crucial stage for establishment of the CBSS for children with disabilities and their effective running over the course of the project. The activities began with a series of trainings on mapping the most excluded children with disability in the selected clusters, in order to determine the exact numbers of potential beneficiaries and ensure an equitable coverage of the most needy. Through mapping and needs assessment conducted in all 41 municipalities, a number of 1,202 children with disability were identified. The mapping exercise was closely followed by the delivery of a series of training courses designed through Activity 1.2 at the national level. Trainings were all aimed to respond to the drafted by-laws and established quality standards for services, while promoting child rights in a systematic manner. A number of 98 courses totalling 1,313 training hours for 1,952 participants from municipal governments and service providers have been delivered until September 2013 (see Table 5).

###### Table 5. Overview of Training Courses delivered by the Project

| Main topics | No. of courses | Training hours | No. and category of trainees |
| --- | --- | --- | --- |
| 1. Training provider/facilitator: UNICEF |  |  |  |
| Commissioning of services | 1 | 13 | 70 municipal representatives |
| Selection, managing and monitoring service providers | 1 | 6 | 30 LSGs, mentors |
| 2. Training provider: Republican Institute for Social Protection |  |  |  |
| TOTs | 5 | 95 | 40 social welfare professionals |
| Day care | 10 | 160 | 227 LSGs, service managers/providers, CSWs |
| Managing volunteers | 4 | 60 | 67 service managers, CSWs |
| Training for volunteers | 1 | 12 | 17 service managers, CSWs |
| Supporting families with children with disability | 4 | 48 | 67 service providers, CSWs |
| Supported living | 2 | 28 | 26 LSGs, service managers/providers |
| Scale for assessing functioning capabilities of users | 21 | 126 | 579 case managers and supervisors |
| 3. Training provider: Provincial Institute for Social Protection |  |  |  |
| Respite care | 2 | 24 | 22 service managers, professionals |
| Home help | 10 | 128 | 143 service providers, professionals |
| Direct care-givers | 9 | 216 | 138 care-givers, professionals |
| 4. Training provider: NGO Amity |  |  |  |
| Mapping of the most excluded children with disability | 10 | 70 | 185 LSGs, service providers, CSWs, local project coordinators |
| 5. Training provider: CLDS |  |  |  |
| Beneficiary prioritising and participation in service costs | 5 | 52 | 108 LSGs, service providers, CSWs, local project coordinators |
| Service costing | 3 | 15 | 99 LSGs, service providers, CSWs, local project coordinators |
| 6. Various other training providers |  |  |  |
| Cluster-specific topics (e.g. Montessori methods, psychomotor re-education, hippo rehabilitation) | 10 | 260 | 156 professionals and care-givers from various municipality clusters |

Source: Theory of Change. Annual project reports. Data provided by UNICEF project team

All planned capacity building actions for municipalities and training providers have been completed, less the ones for case managers on knowledge and skills in social care (Activity 2.3) which were postponed for October-November 2013 (project extension period) due to postponed decision on the revision of the Rulebook for CSWs. Although justified for objective reasons, this delay could have been an important cause for certain flaws in the referral and prioritising of access to services for the most disadvantaged children with disability and their families, as detailed below under the Evaluation Question on equity.

With assistance of the capacity building activities, the 41 municipalities established 52 community-based services (17 day care centres, 29 home assistance services, 4 respite care, 1 hippo rehabilitation and 1 accessible transportation), run by 43 different service providers across Serbia (see Annex 6) and employing 300 people. Table 6 presents the number of (planned and actual) beneficiaries and employees by type of service and location. It can be noted that the planned number of 1,191 beneficiaries has been achieved only in a proportion of 78% (930), which has decreased even more after the end of grant financing, as noted in various municipalities which were visited by the evaluation team.

###### Table 6. Community-based Services supported by IPA 2008 Project

| No. | Type of service | No. of services | Location | No. of beneficiaries |  | No. of employees |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Planned | Achieved |  |
| 1 | Day Care Centre | 17 | Bor, Kladovo, Vrnjačka Banja, Trstenik, Aleksinac, Paraćin, Dimitrovgrad, Čoka, Vlasotince, Bela Palanka, Babušnica, Pećinci, Čajetina, Kosjerić, Ruma, Novi Kneževac, Zemun | 274 | 272 | 113 |
| 2 | Home Assistance | 29 | Negotin, Žagubica, Vrnjačka Banja, Prokuplje, Gornji Milanovac, Crveni krst, Ražanj, Gadžin Han, Paraćin, Topola, Despotovac, Rekovac, Ćićevac, Svrljig, Dimitrovgrad, Vlasotince, Bela Palanka, Babušnica, Užice, Kikinda, Požega, Nova Crnja, Žitište, Sečanj, Stara Pazova, Irig, Knjаževac, Boljevac, Pirot | 724 | 527 | 157 |
| 3 | Respite Care | 4 | Aleksinac, Vlasotince, Ivanjica, Knjаževac | 165 | 92 | 23 |
| 4 | Hyppo Rehabilitation | 1 | Dimitrovgrad | 16 | 20 | 6 |
| 5 | Accessible transportation | 1 | Užice | 12 | 19 | 1 |
|  | TOTAL | 52 |  | 1,191 | 930 (78%) | 300 |

Source: Final projects reports. Various information and data provided by UNICEF project team

The largest discrepancies in planned and achieved numbers of beneficiaries are tied to specific types of services, namely the respite care (56% achievement of the target, with the biggest gaps in Aleksinac and Knjаževac) and home assistance (73% achievement, mainly due to underachievements in Vrnjačka Banja, Žitište and Kikinda) – see Annex 7.

During the field visits to Čoka and Aleksinac clusters, the evaluation team was able to identify different causes behind these gaps. For example, the respite care service in Aleksinac was established according to plan, but due to the pronounced difficulties in access given the rural nature of the municipality, the professionals employed in the service would often spend long periods of time without visitations by interested beneficiaries (6 out of 70 planned). The situation had a detrimental impact on the sustainability of the service upon project completion as it was discontinued. The dedicated staff of the CSW Aleksinac which also runs a day care service found a temporary solution in transforming the respite care into an emergency service where professionals are paid on daily and hourly basis when the need for emergency respite service arises.

Difficulty of access appears to be a key factor for reduction in the numbers of beneficiaries in several cases and especially after the end of grant financing: Day care centre in Novi Kneževac is operating below capacity due to inability of the disadvantaged families living in remote locations to make daily visits to the centre; Ražanj municipality home assistance has difficulties in maintaining the service as their caretakers have to use public transport which does not reach even half of the identified beneficiaries; Zemun day care centre is experiencing reduction in beneficiaries due to inability of the most endangered families to obtain daily bus passes.

At the same time, there is undoubtedly a misplanning issue in the design of the respective services, acknowledged also by the UNICEF monitoring team: ”The greatest discrepancy occurs with respite care services, where the planned number of users was unrealistically high and where utilization of the capacities should be measured in number of nights stayed, rather than in number of users”. Such flaws in planning often happen in case of setting up new services, such as respite care or home assistance in this project, where local expertise is low and benchmarking is lacking or unknown at municipality level. According to interviews with UNICEF project staff, the technical assistance provided to municipalities was mainly related to writing the project proposal according to EC procedures rather than the design of specific services as such. Moreover, no quality standards were available at the time when the project applications were submitted to guide the design of the respective services in terms of staffing, coverage capacity, endowment, activities, quality assurance.

Another area which would have required more attention from the project staff is related to the engagement of volunteers in the provision of CBSS. The service managers and service providers have been trained in managing volunteers, respectively in teaching volunteers on working with children with disability and their families. A Guide has been developed in this respect. According to the final reports of the clusters, a number of 165 volunteers have been involved in the actual work with children with disability. Although UNICEF has not committed through the Description of Action to engage a specific number of volunteers in the provision of CBSS, it is to be noted the big discrepancy between the achieved number of 165 and the planned number of 4,000 volunteers in the IPA 2008 Social Inclusion Project Fiche.

Achievements under Activity 2.4 aimed at strengthening civil society initiatives and advocacy for community services are analysed in the response to another Evaluation Question below How effective was the project in building capacities for an efficient and successful monitoring and advocacy for child-care reforms?

EQ: To what extent has the Project contributed to creating a regulatory framework needed for community-service provision?

Table 7 below presents a synthesis of UNICEF internal monitoring reports, EC Results-Oriented Monitoring (ROM) reports and evaluation team findings in terms of the secondary legislation (rulebooks, decrees, guides and instructions) drafted during the project, as part of Activity 1.1, as well as the stage of adoption by the MoLESP and the Republic of Serbia Government.

###### Table 7. Decrees, Rulebooks and Guidance Documents developed through the IPA Project

| No. | Category and Title of the Document | Status (September 2013) |
| --- | --- | --- |
| I | FINANCING |  |
| 1.1-1.3 | Set of three acts related to social financial assistance | Adopted |
| 1.4 | Decree on ear-marked transfers | Finalized by MoLESP. In formal procedure of adoption |
| 1.5 | Decree on methodology for costing of services financed from the national budget | Drafted and submitted to MoLESP |
| 1.6 | Rulebook on criteria for infrastructure investments/maintenance/equipment for social welfare institutions | Drafted and submitted to MoLESP |
| 1.7 | Rulebook on annual programmes of work of social welfare institutions | Drafted and submitted to MoLESP |
| 1.8 | Rulebook on criteria on participation of beneficiaries in payment of service costs | Drafted and submitted to MoLESP |
| 1.9 | Instruction for commissioning (tendering) of community services | Drafted and submitted to MoLESP |
| II | SERVICE STANDARDS |  |
| 2.1 | Rulebook on service standards (day-care, home help, personal assistance, supported living, shelters, residential placement, respite care, small group homes) | Adopted |
| 2.2 | Rulebook on counselling / therapeutic services | Drafted and submitted to MoLESP |
| 2.3 | Guidance for service standards implementation, including: a) Tool for assessment of the service standards implementation; b) Tool for the assessment of the intensity of support needed for an individual beneficiary | Drafted and submitted to MoLESP |
| III | REGULATORY MECHANISMS |  |
| 3.1 | Rulebook on groups / types of professional assignments in social protection | Adopted |
| 3.2 | Rulebook on ID cards of social welfare inspectors | Adopted |
| 3.3 | Rulebook on ID cards of professionals in centres for social work | Adopted |
| 3.4 | Rulebook on evidence and documentation (including set of formats) | Drafted and submitted to MoLESP |
| 3.5 | Rulebook on referral to social welfare services | Drafted and submitted to MoLESP |
| 3.6 | Rulebook on accreditation of training programmes | Drafted and submitted to MoLESP |
| 3.7 | Rulebook on performance assessment and professional development | Drafted and submitted to MoLESP |
| 3.8 | Rulebook on licensing of professionals | Zero drafts supported by IPA – Adopted |
| 3.9 | Rulebook on licensing of service providers |  |
| 3.10 | Guidance on inspection | Drafted and submitted to MoLESP |
| 3.11 | Guidance on complaint procedures | Drafted and submitted to MoLESP |
| 3.12 | Guidance on performance assessment and criteria for professional development | Drafted and submitted to MoLESP |
| 3.13 | Guidance on professional assignments of institutes for social protection | Drafted and submitted to MoLESP |
| 3.14 | Guidance for evidence and documentation for: a) Day-care services and services supporting independent living; b) Residential placement, shelters and respite care | Drafted and submitted to MoLESP |
| IV | WORK ACCOUNTABILITY |  |
| 4.1 | Rulebook on forbidden behaviours of professional staff | Adopted |
| 4.2 | Rulebook minimum work duties in case of strike for social welfare institutions established/financed by national budget | Adopted |
| 4.3 | Rulebook on working discipline (model) | Developed and submitted to MoLESP, available as MODEL on the MoLESP website |
| 4.4 | Rulebook on minimum work duties to be performed in the case of a strike for social welfare institutions established and financed from the provincial and local level budgets (model) |  |

In accordance with the data presented in the table, UNICEF Year 3 Annual Report lauds “finalization of all planned secondary legislation to the Social Welfare Law - both by-laws (rulebooks and decrees) and soft-law regulations (guides and instructions) needed for its implementation” as well as the fact that “piloting of new services for children with disability and their families have been finalized and integrated into the rulebook on service standards – home help, respite care, child personal assistants and small group homes.” The evaluation team finds that full percentage of the planned rule-books, decrees, guides and instructions have been drafted and submitted to MoLESP over the course of the project, but only 30% (9 out of 30) have been adopted so far, mostly due to extenuating circumstances discussed below.

The latest ROM report from 2011 has noted that support to project implementation could be affected by the general elections in Serbia in May of 2012. The formation of the new government and resulting management changes in the MoLESP have inevitably influenced the process of adoption of the drafted regulations. Nevertheless, UNICEF staff made every effort possible to support the MoLESP in minimizing the impact of the internal changes on the process of adoption of the secondary legislation to the Social Welfare Law. In that respect, the evaluation team has found that the crucial pieces of legislation necessary for the future functioning of the community services developed by the project have been adopted in time, notably the Rulebook on Service Standards (day care centres, respite etc.) and the Rulebooks on licensing of professionals and service providers (in synergy with the project supported by the Norwegian Embassy).

It is also necessary to point out that the majority of stakeholders, especially those in the least developed municipalities, dedicate most attention to the Decree on the “ear-marked” or special transfers that has been in the closing stages of the adoption procedure in September 2013. The Decree on special transfers is crucial for the poorest and so-called “devastated” municipalities, namely belonging to categories III and IV in government’s municipality development classification. The often unstable and volatile political scene at the local level in Serbia, with frequent changes of local governments, results in modifications of local budgets where social services are always of secondary concern. Therefore, the Decree on special transfers provides these municipalities with direct financial assistance from the national budget specially reserved for continuation of the established social services and ensuring a great deal of financial certainty for the service providers. Although primarily important for sustainability aspect of the UNICEF project, the creation and supposedly imminent adoption of the ear-marked transfers decree is of outmost importance in achievement of the Results 1 and 2 and of the overall objective of “strengthening policy frameworks, institutional mechanisms and capacities so that CBSS supporting children with disabilities can be developed and are responsive to the needs of these children and their families.” The evaluation team received strong assurances from the MoLESP State Secretary (member of the Project Steering Committee) that upon the completion of consultation with the Ministry of Finance, the Decree on special transfers would be considered in the upcoming draft of the state budget for 2014. In this respect the set of project actions grouped under Activity 1.1 ’Technical support for development of by-laws and other policy documents that regulate community-service provision’ could be considered as fully implemented with UNICEF staff exercising every possible mean within their Project implementation mandate to push for adoption of as many regulatory instruments as possible within the Project timeframe.

EQ: To what extent the Project contributed to strengthening the national level capacity to monitor, supervise and report on child-care reforms and services provision for children with disability and their families?

The Project plan included a number of initiatives which targeted national capacities to monitor, supervise and report on child care reforms and service provision. Beside capacity building in the Ministry itself, as main duty-bearer, the members of the social inspectorate department were included in two monitoring missions providing them with a chance to apply the new Rulebook on Service Standards in practice for the first time. Pertaining to Result 1, UNICEF has planned to ”Support MoLESP in defining child welfare indicators, mainstreaming them into regular data-gathering systems and using them for monitoring impact of reforms” (Activity 1.3). This particular activity appears to represent a specific challenge due to general social welfare system weaknesses (as explained above) in the multiple dimensions of the collection, monitoring and analysis of data from CSWs. For that reason, UNICEF decided to integrate the work on child welfare indicators with the work on developing the main body of social welfare indicators at the MoLESP as a part of the implementation of the Social Welfare Law. However, even if fully introduced, the new child welfare indicators have no means to be introduced on the ground due to lack of technical capacities in the CSWs to apply the indicators and collect data according to the revised formats. Although the CSWs have been supposedly supplied with the networking hardware components by the DILS project, the corresponding software for data collection has not been installed completely, forcing the CSWs to base their reporting toward MoLESP and the Republic Institute for Social Protection on e-mail communication and even hard-copy reports. In the light of the above, the project goal to use mainstreamed child welfare indicators for regular reporting seems to have been overly ambitious.

Nevertheless, the project implementation team did its best to encourage the process of monitoring and data gathering, both by revising the formats to ensure better disaggregation of data collection by the CSWs and by commissioning a number of independent studies which would serve as situation analysis and baselines for the future application of the child welfare indicators.

This primarily applies to the “Mapping of the community based social services in Serbia” conducted by CLDS and SIPRU, which provided full information on the status and characteristics of the community services, including the profile of beneficiaries disaggregated by age, gender, disability and urban/rural residence as well as type and number of services per municipality and service providers (CSW, NGO or others). Completed in June 2013, the mapping exercise identified over 170 CBSS for children, providing  mainly day care for children with disabilities (in 71 municipalities) and home help (in 37 municipalities). According to the study, these services were established by LSGs and predominantly run by the Centres for Social Work - CSWs (70% on average). Despite important progress since 2008, the study indicated that the number of children benefitting from services is relatively small, while the CBSS for at-risk families with young children are under-developed (Table 8).

###### Table 8. Local Self-Governments Providing CBSS in 2012

| Name of Service | No. of LSGs* |
| --- | --- |
| Day care for children with disabilities | 71 |
| Day care /Centre for children and young people with behaviour problems | 10 |
| Home assistance for children with disabilities | 37 |
| Children shelter | 9 |
| Shelter for the victims of family violence (“safe house“) – children users | 15 |
| Supported living for children leaving care and youth with disability | 20 |
| Drop-in centre for children | 5 |
| Respite care | 11 |

* Serbia has 174 municipalities

Source: Centre for Liberal Democratic Studies, “Mapping of the community based social services in Serbia”, 2013

The CLDS carried out additional studies related to the financing and costing of community services. NGO Familia (specialized in disability, alternative family care and research, another project partner) conducted a study on the outcomes of de-institutionalisation of children and their placement in small homes communities. At the same time, the Association of Centres for Social Work carried out a survey on the application of the Rulebook for CSWs adopted in 2008 which introduced the system of referrals and case management, identifying a number of shortcomings in case management related to individual planning and regular revisiting of plans, including for children at risk of neglect or abuse.

The Faculty of Political Science (Belgrade University) produced two studies on the impact of community-based services on the children with disabilities and their families, respectively on decision-making regarding custody and care of children to prevent family separation. Research found that of all children placed in formal care in the last five years (from 2006 to 2011), around 33% were children with disabilities (see Figure 3 below). It also showed that there is a lack of mechanisms and programs to ensure adequate and timely support for families to help them cope at times of crisis and prevent unnecessary family separations.

##### Figure 3. Key Characteristics of Children Placed in Formal Care (%, 2013)

Source: Preliminary data from the Study “Praćenje Uzroka, Procesa Donošenja Odluka I Ishoda za Decu u Sistemu Socijalne Zaštite”, Faculty of Political Science, University of Belgrade,  July 2013

The data gathered through project activities provides a valuable body of baseline information however it is still not integrated into a systematic database. Further capacity building efforts are required to strengthen the CSWs for accurate data gathering and reporting, especially in terms of indicators on children with disabilities and their families. The current situation creates great hardships for the analytical team at the Republic Institute for Social Protection which managed to improve the quality of the annual reports despite the obvious data collection problems.

EQ: How successful was the project in strengthening the national level system for continuous professional development related to supporting families with children with disability?

In order to jump start the implementation of the drafted and adopted legislative acts, rule-books and guides, UNICEF has worked with the Republic Institute for Social Protection (Activity 1.2) on developing a set of 10 accredited training packages for the provision of community services for children with disabilities (by professionals and volunteers) according to the quality standards designed through the Project as well (see Annex 8 for a full overview of the training packages and their accreditation). The training content has been adapted to various audiences of trainees, namely municipalities, service managers, service providers, and care-givers. Four of the training packages were tailor-made to the provision of a particular community-service (day care, home assistance, respite care, supported living) and accredited for use in the process of licensing of the social work professionals.

The work on the development and application of the training packages and the experience of both Institutes for Social Protection in supervising and supporting service provision in 41 municipalities led to development of 6 guides/practicums. The evaluation team found that guides and practicums are used as practical tools by service providers in setting up and running services in compliance with the new minimum service standards.

Box 2. Establishing and Running Day care Services Out of 41 IPA 2008 grantees, the Municipality of Čoka was among the first local self-governments to complete the procedure of adopting the municipal decisions necessary for the rapid deployment of funds and setting up of day care centre. The procedures and cooperation mechanisms from Čoka were used as an explanatory illustration by the Institute for Social Protection in the Practicum devoted to day care service establishment and management.

Within the activity focused on development of by-laws and soft legislation (Activity 1.1), the project consultants and MoLESP partners have drafted Rulebooks on licencing of professionals and service providers (zero drafts, further refined by the Norwegian project). Once adopted, they enabled the newly established Chamber for Social Welfare to start the process of licencing social welfare professionals. The licencing system based on professional credits will require the professionals to constantly improve their professional capacities in order to keep and renew their professional licences. The training packages on services for children with disabilities developed within the project and accredited by the Republic Institute for Social Protection will represent an essential part of the professional development process as they would be included in the credit gathering system.

As mentioned before, Activity 2.3 aimed at capacity building of the CSWs through training of the case managers is yet to be finalised as it was first prolonged to Year 3 of the implementation and then transferred into the extension period of the project.

EQ: How effective was the project in building capacities for an efficient and successful monitoring and advocacy for child-care reforms?

In the third year of project implementation, an Action Plan for the implementation of the Social Welfare Law was finalized and submitted to MoLESP for adoption. The document is aimed to serve as a planning and monitoring tool, providing  MoLESP with a clear road-map to better design its yearly programme plans and ensure smooth implementation of the new law as well as to act as a major national actor in the promotion, respect and fulfilment of child rights in Serbia.

UNICEF has also supported the improvement of capacities of independent bodies to monitor the child welfare reform process and hold government accountable for implementing adopted policies in compliance with human rights standards and Serbia’s commitments (Activity 2.4). At the national level, the project supported the Ombudsman’s office and the Commissioner for Equality in order to strengthen their capacities for monitoring and analytical reporting on the status of the most marginalized children (especially concerning rights of children with disabilities in residential care and cases of discrimination). As a result, the independent bodies released five child-related monitoring reports which were communicated with the Parliamentary Committee on the Rights of the Child. The project activities contributed to the Commissioner of Equality’s first Special Report on Discrimination of Children in Serbia (focused on the most marginalized and vulnerable groups of children). The Ombudsman’s office has resumed the work on consolidating the legislation on children rights and drafting the first law specifically focused on children’s rights and welfare in Serbia.

The project has also supported the Network of Civil Society Organizations for Children in Serbia (MODS) in broadening its membership base, establishing a secretariat and defining the platform for advocating for the most marginalized and endangered children. Over the past three years, MODS has grown into a significant NGO network which was recognized by the national government as a partner in the child welfare reform dialogue. The network managed to influence policies and decisions which are over and beyond the objectives of the UNICEF project such as Value-Added Tax (VAT) refunds on baby equipment, mainstreaming of inclusive education into the Strategy for Education 2020, promotion of child/youth participation in decision-making. On the local level, the project supported 10 NGOs to conduct advocacy initiatives and campaigning towards ensuring the sustainability of the new CBSS and social inclusion of children with disabilities and their families. However, apart from MODS, the capacities of NGOs at the local level, both as independent monitors and potential service providers, remain very low, especially in smaller towns and rural communities. In that respect, there is a significant gap between the NGOs capacity in the big cities of Belgrade and Novi Sad and the civil society organizations in South Serbia which require additional support and capacity strengthening in order to effectively monitor and provide alternatives to CSWs as service providers.

EQ: Has the project provided any additional (not directly planned by the Project) significant contribution/ outcomes towards development of alternatives at community level and social inclusion of children with disability?

Interviewed stakeholders pointed to some unforeseen additional effects of the project, such as the instant networking of municipalities for sharing experience on CBSS, some public pressure put on municipality authorities to set up and run social services for vulnerable people as in the neighbour municipality and development of self-help initiatives among parents with disabled children, as follows:

- Two formal associations set up: Parents  association in Svrljig (Cluster Knjazevac) and Parents association in Cajetina (Cluster Užice).

- Six informal groups operating within the Clubs of Parents: Knjazevac, Boljevac, Pirot, Bor municipality, Kladovo and Ivanjica.

- Užice City Association of blind persons and persons with visual impairment, formed by the parents of children with visual impairment.

The evaluation team has been also informed that initiatives for setting up parents’ associations started in Zemun (Cluster Čoka) and Kosjeric (Cluster Užice) as well. According to the views of various interviewed stakeholders, it would have been very beneficial if such initiatives were part of the Project as such, in order to provide more systematic and professional help to parents, as rights-holders, to advocate for policy change, claim their children’s rights and obtain redress. This opinion is fully shared by the evaluation team.

Another additional positive outcome of the Project identified by the evaluation team was the development of a one-day training programme on the ’application of the scale for assessment of functional capabilities of users and definition of required support level’. The design of this training programme directly builds on the Rulebook on Service Standards which introduces a concept of '4-level intensity support' as well as on an easy-to-use instrument for initial functional assessment of beneficiaries, both supported by the project. The training program was later on developed by the same group of consultants who worked on the development of this tool and submitted for accreditation. The training was then delivered by the Republic Institute for Social Protection to a number of 579 case managers by end September-beginning of October 2013. It is planned to provide this training to an additional number of 793 case managers, thus covering all these specialists from all CSWs.

## 4.3	Efficiency

EQ: How well have the implementation of activities been managed? To what extent are activities implemented as scheduled? What management and monitoring tools have been used?

Based on the Logical Framework and Theory of Change objectives and result indicators, the project’s monitoring system was integrated at several implementation levels depending on the type and scope of its activities. The implementation of the annual project plans has been observantly examined by the internal monitoring teams which, apart from UNICEF staff, included partner and donor representatives. The internal monitoring missions were guided by the monitoring framework guidelines and project logframe indicators which were clearly presented in the Monitoring Tables attached to each annual report.  In total, the project had three internal monitoring rounds, three external ROM missions and produced three annual reports with the final report in the drafting phase. The evaluation team has also found that the contracted activities with individual partners (such as research studies and NGO activities) had their own monitoring tools, including guidelines for their application, with a view to ensuring partner accountability and provide timelines coordinated with the overall project implementation dynamics. Overall, the monitoring and reporting of the project were carefully designed to ensure the proper implementation of activities according to the project planning documents. The findings presented below detail further the assessment of the evaluation team related to monitoring and reporting  and the overall management of the Project in the light of various efficiency issues.

There were three ROM missions during the project implementation and reports have registered that implementation of activities was in line with the work plan with no major delays. Successful and timely completion of activities has to be commended as a significant achievement of the UNICEF project management team and their partners, having in mind that the project required coordination of complex activities at national and local government levels. As already noted in the effectiveness criteria analysis, there were unforeseen circumstances which hampered the process of adoption of the drafted decrees, rule-books, instructions and guidance documents. In that respect it was not realistic to expect from the implementation team to influence or hasten the process of government restructuring after the elections in March of 2012. However, in spite of the aggravating circumstances for the process of by-law adoption, UNICEF and their partners in MoLESP managed to push the adoption of crucial pieces of legislation (notably the Rulebook on quality standards of services) which enabled timely implementation of the grant scheme at the local level. As far as training of case managers is concerned, the causes for delays have been already explained above and are mainly related to the postponed revision of applicable Rulebook for CSWs, outside the scope of this project.

The responsibilities for efficient management of the grant scheme for establishment of the community based services were shared between EUD and UNICEF. The project implementation team through its capacity building activities provided crucial assistance for timely and efficient preparation and submission of the grant applications which were of sufficient quality for the selection of 10 grantee clusters.

The clustering of municipalities was a distinguished efficiency feature and innovative for Serbia due to its lack of regional level administration. This particular implementation modality has exhibited a number of positive elements such as economies of scale and budget efficiency, easier access to funding, mutual learning and exchange of experience. At the same time, it posed certain challenges. During site visits, the evaluation team has been presented with evidence where the agreements between leading municipalities in the cluster and the partner municipalities appeared unclear in terms of budgetary appropriations for the respective services. In other words, the agreements did not specify the details of the established service and its related funding requirement; indeed, they were formulated in rather general terms. This led to a lack of transparency in respect to the overall cluster budget needed for accountability, monitoring and evaluation purposes i.e. certain cluster budgets do not provide details on the distribution of the professionals and specialists for each service, appropriated under human resources expenses (e.g. Čoka cluster, Paraćin cluster). As a result, some representatives of partner municipalities reported in the interviews that the lead municipalities appeared to be somewhat constricted in control of the joined budget. However, in the majority of cases, the clustering model significantly assisted the process of procurement and funding distribution. The model allowed for rapid establishment of multiple CBSS in the cluster members, avoiding the administration trap of concluding contracts with 41 municipalities individually which would have definitely slowed down the implementation process.

The process of monitoring and reporting has also benefitted of the clustering model. The monitoring teams, composed of UNICEF consultants, EUD and MoLESP inspectors were able to visit multiple municipalities in a very short time. The reporting scheme worked in a circular manner where cluster members contributed to overall cluster reports, creating 10 instead of 41 report documents. In general, monitoring and reporting activities were conducted according to the project plan with regular reviewing of the quarterly reports submitted by municipalities and structured field monitoring visits. The monitoring visits were conducted in three rounds of 2-3 days of field visits to each of the 10 clusters and were especially significant due to the fact that they included inspectors from the MoLESP who will continue with their oversight functions upon the project completion. The resulting monitoring reports represent a significant source of information for project progress tracking and effectiveness/efficiency issues due to very concise and clear comments and recommendations for remedial action by the visiting MoLESP inspectors. However, the evaluation team was unable to find substantial evidence on the field that the inspectors’ observations and recommendations have been always followed by the service providers of tagged services. Indeed, the reports contain a number of constantly repeating remarks and findings on shortcomings on the same services in the three rounds of monitoring exercise. It seems that the inspectors do not have sufficient leverage for the enforcement of their recommendations, but it is hoped that the full implementation of the new standards will equip them with better tools in this respect. The monitoring team of UNICEF performed anyhow an excellent work in terms of adequate identification and accurate reporting of the challenges in the delivery of the newly established services.

Annual narrative and financial reports were produced on time and represent an important point of reference for the evaluation purposes and future planning of municipal, governmental and UNICEF initiatives as well as for donors. They are well structured and include monitoring tables of planned/achieved activities and indicators, based on the Logical Framework and Theory of Change, which provide an excellent image of progress of the project at national and local levels. The final reports from the ten clusters were timely produced with assistance of the regional mentors and UNICEF consultants and were made readily available for the purposes of this evaluation.

The numerous trainings, coordination meetings and workshops delivered by UNICEF to the regional mentors, PIUs and municipality representatives (23 events totalling 180 hours for 905 participants) enhanced the local capacity for work planning, project management, financial management, procurement, monitoring and reporting, hence a high quality of project management and reporting by the clusters.

EQ: How well have the financial resources been used / were funds managed in a cost-effective manner / what is the correlation between funds utilized and outputs / results achieved / could the same results be achieved with less resources?

With EUD oversight over the grant process, there were no significant irregularities in the process of financial management of activities planned in the grant applications. This is especially evident in terms of procurement of supplies such as transportation vehicles, furniture, equipment, etc. However, the majority of project activities were dependent on the timely deployment and efficient use of professionals and skilled workers to be engaged in the processes of by-laws drafting, development of research studies, carrying out of surveys and mapping exercises, respectively in community service functioning as service managers, educators, therapists and care-givers. The use of professional consultants and researchers at the national level was both highly effective and efficient since they were top professionals in their branches who were commissioned for tasks most suitable to their particular specializations. This resulted in a timely production of high quality deliverables. For example, the Faculty of Political Science within Belgrade University conducted a study using multiple survey and research techniques in two different rounds, with the final report timely produced in the closing stages of the project; or the Mapping of Social Services study produced by CLDS and used by the Republic Institute for Social Protection for improvement of the database and analytical capacities.

The efficient manner of human resources use at the national level did not fully transfer to the local level where the evaluation team noticed three main challenges:

- Several municipalities overestimated the number of beneficiaries for the services, resulting in too many employees in the service in comparison to the number of actual beneficiaries, which created a lack of balance among clusters and even within the same cluster and affected the efficiency of some local projects compared to others (see Annex 7, i.e. 6 employees in Zagubica home assistance service for 8 beneficiaries compared to Gornji Milanovac home assistance serving 20 beneficiaries with the same number of employees; day care centre in Kladovo providing services to 21 beneficiaries compared to Trstenik where they serve 36 beneficiaries with 5 employees in both municipalities). As already explained above, the lack of quality standards at the time when project applications were developed is a significant factor which counts for certain flaws in the design and staffing of community services.

- The project paid for salaries of the local officials and staff involved in the coordination and monitoring of CBSS. It is however unclear to what extent these people performed activities in the project which were not part of their regular job description and which would have justified extra payments from the project. It is mainly the case of directors of CSWs and municipal council members in charge of social welfare issues.

- There are large variations in the level of salaries paid to project staff for the same level of responsibility, tasks and type of labour contract. The obvious case is that of the local project managers, whose monthly salaries vary from 500 Eur (Dimitrovgrad cluster) to 1,200 Eur (Čoka cluster) or even 1,500 Eur (Vrnjačka Banja cluster) for a full-time job. There are examples of significant differences also at the level of monthly salaries for professionals and care-givers e.g. from 250 Eur (Kikinda, Vlasotince, Babušnica) to 504 Eur (Irig, Stara Pazova) for a full-time job as care-giver in a home assistance service. Justification for the set high level of salary is either missing or unclear: “The Project Manager fee is estimated concerning knowledge and experience needed for such complex project”.

In the light of the above, resolving efficiency issues related to human resources at local level seems to have been a missed opportunity in certain respects since a larger proportion of the grant money could have been spent for improving the quality of CBSS. It is to be noted that the salary issues were beyond UNICEF direct responsibility or control, as those were part of another component of IPA 2008 project managed by the EUD, i.e. the grant scheme.

In general, cost-effectiveness of CBSS set up or supported by the project is difficult to assess also due to the lack of benchmarks to guide the budgeting of services i.e. in relation to similar services in Serbia or in countries with similar challenges. UNICEF has acknowledged this shortcoming and addressed it through the project by commissioning studies on mapping, financing and costing of social services across Serbia. The study Expenditures of Community-Based Services for Children and Unit Costs (Centre for Liberal-Democratic Studies, 2012) “serves as an indication to the MoLESP in planning earmarked transfers for the development of community-based services, but also to local governments in planning their budgets, and especially in implementing the new Law on Social Protection – with regard to commissioning of social services through public tendering” (see also Annex 9 for an overview of services costing). From now on, the country has a detailed and comprehensive set of benchmarks which could be used, along with quality standards and practicums, for the design of community-based services in an effective and efficient manner.

As far as disbursements are concerned, EU CRIS data indicate that payments were done timely and with regularity, both to UNICEF and local clusters, indicating that progress was, with few exceptions, in line with the set implementation schedule.

EQ: Did the project ensure co-ordination with the other two components of IPA 2008 Social Inclusion and with other similar interventions to encourage synergy and avoid overlaps?

As all components of IPA 2008 Social Inclusion project were inter-related, the MoLESP and UNICEF agreed with the EUD that “a single Steering Committee be established which will be responsible to guide and oversee all three segments of the work related to IPA Social Inclusion 2008”. There has been excellent co-ordination between the project component implemented by UNICEF and the grant scheme component managed by the EUD. UNICEF has made available technical assistance in time to support local applications development for the call for proposals. The Contribution Agreement with UNICEF has been extended to overlap with the duration of the Grant Contracts signed between the EUD and the 10 municipality clusters, ensuring assistance from UNICEF until the end of the implementation of local projects. The coordination with the public information campaign component (implemented through a Service Contract concluded by the EUD with BBI) has not been however optimal. The campaign ended before the grant scheme component yielded any significant results which were worth being disseminated. To be noted is that the indicators in the IPA 2008 Social Inclusion project fiche have not been transposed in their entirety into the Contribution Agreement with UNICEF and in the Service Contract with BBI, leaving outside important indicators for which no clear accountability was set.

The overall IPA 2008 Social Inclusion project was built on the experience, lessons learnt and tested models of previous projects. It has been complementary with and a continuation of the EU CARDS “Transforming Residential Institutions for Children and Developing Sustainable Alternatives” project, which UNICEF implemented in partnership with the MoLESP (2008-2011). This ensured a realistic design of the project, based on clearly identified needs and a smooth start. Staff continuity in UNICEF and the ministry has also contributed to setting up an efficient working mechanism between both institutions, allowing clear communication and decision-making channels. IPA 2008 is also a continuation of a joint DFID-Norwegian project ”Support to the Implementation of the Social Welfare Strategy” which developed the legal framework and tested some quality standards for services, with Norwegian, EU and UNDP funding, within the framework of 122 local social policy plans. The joint project has also triggered other two projects on the accreditation of training programmes for social professions and licensing of social services providers, both funded by Norway. According to officials from the MoLESP and consultants interviewed for the purpose of this evaluation, there was an excellent coordination of the IPA 2008 project (component implemented by UNICEF) with the Norwegian project “Creation and Implementation of the Licencing System for Social Services Providers” as far as the development of Rulebooks on licensing of professionals and service providers were concerned. UNICEF project team developed the first drafts of these documents, which were further refined and developed by the team of the Norway-supported project.

The IPA project has been also well connected with another project implemented by UNICEF and financed by Italy on de-institutionalization of children, in particular those with disabilities. Standards for small group homes were successfully piloted through the Italian project and integrated into the Rulebook on Service Standards supported through IPA Project. The project has assisted the Working group on inter-sectoral committees (in charge of  assessing additional support required for education of children who may have learning difficulties, disabilities or behavioural problems, according to the Law on the Basis of the Education System) through the development of standards for child personal assistants for education inclusion. These standards were later on integrated into the Rulebook on Service Standards. The project staff from UNICEF has also cooperated with SIPRU in the design of a monitoring framework for inclusive education. In addition, coordination with DILS project was done in respect of the development of regulations on evidence and data management. In this way, synergy with other projects has been ensured which avoided unnecessary overlaps and waste of resources.

## 4.4	Impact

EQ: To what extent has the project contributed to increasing the number of children with disabilities benefiting from community-based services? Were there any elements which could hamper the impact of assistance?

As indicated in the Relevance section above, a number of national strategies, social welfare legislation and international documents have identified the lack of the CBSS for children with disability and called for their development and increase. The lack of data on the number of children with disabilities in Serbia is also due to the fact that there are insufficient local capacities to provide relevant data and help identify the children that are excluded from the system of social protection. It is not uncommon for the community services which are not part of the state system (CSWs), mostly established and run by CSOs, to appear and disappear in very short periods of time depending on the external donor support. Therefore, one of the most significant challenges for UNICEF in the planning phases of the project was to establish a reliable baseline in terms of both the number of functioning CBSS and the number of children with disability benefiting from them. The only official source of data available for pre-2010 period is the Republic Institute for Social Protection’s Report on the work of CSWs for 2008-2009 and UNICEF estimates for the Project document. Accordingly, “53 municipalities financed or partially financed day care centres, out which 33 were specialized for children with disabilities with a total of 1,122 beneficiaries.” According to the 2010 report issued by the Institute, the number of services has slightly increased to 59 with 1,416 beneficiaries; the report is however unclear as to the type of newly established day care centres, their specialization for the children with disability or the means of their financing (state or donor). The only other type of community-based service provided by the state CSWs prior to 2010 was the so-called “home help” which was provided in 78 municipalities in 2008 but with only 1.3% of 6,384 users being children (125 beneficiaries). This type of community service in Serbia is traditionally overwhelmingly provided to the elderly beneficiaries. The situation in 2010 has even deteriorated since only 1.1% (148 children) registered as beneficiaries out of 13,272 total service users. The common characteristic for both types of services was the lack of regulations and minimum standards for service providers which further complicated data gathering and establishment of clear baselines. Without official figures on the number of children with disability requiring extra assistance, UNICEF made an estimate based on its analysis, experience and former projects that there are 45,000 children in need of extra-support i.e. about 3% of the total child population (1,500,000). The estimated number indicates that even with attainment of the planned beneficiaries in the IPA project, a large percentage of children with disability in Serbia will remain without access to community support. However, the Project represents a critical initial effort to reach the children in need and raise awareness about their required social inclusion.

As mentioned before, the Project supported the establishment of 52 services in 41 municipalities; out of that number, 39 (75%) of them are completely new services while 12 (25%) were existing services which were further improved and developed. The increase of service provision is especially evident in respect to home assistance service which was negligible before 2010 and which represented more than half of the number of the newly established services (29 of 52 services or 55.8%). As noted in the Effectiveness section, the number of planned beneficiaries was 1,191, according to the latest figures provided by UNICEF, while the actual number of served children with disability was 930. Out of that number, the survey conducted by the NGO Amity in May 2012 suggest that 673 children with disabilities were using CBSS for the first time.

There were a number of difficulties which hampered the impact of assistance and reduced the number of beneficiaries during the project implementation and immediately after the project completion in spring of 2013. Some of these difficulties have been already described in the Effectiveness section. Let us recall that the most significant difficulty impacting beneficiary numbers even during the project implementation was the lack of access for the remotely located beneficiaries, especially in rural areas.

It is important to note that despite these difficulties, the Project succeeded to considerably increase of the number of children with disabilities benefiting from CBSS: taking the most optimistic estimate of the Republic Institute for Social Protection from 2010 according to which 1,416 children with disabilities were using community services, the number of children which started using the services for the first time in their life due the Project represents an increase of 47.5% (by 673). In comparison to 2008 estimate of 1,122 beneficiaries, the increase in the number of children using CBSS is by almost 60%.

Beyond the statistical data, it is important to note that the Project introduced completely new services (respite care) and created an unprecedented support environment consisting of national and municipal legislation and regulations (quality standards and social protection decisions) and capacitated the personnel to provide optimal conditions for child care services.

EQ: What is the project contribution to further continual decrease of number of children with disability in residential care, particularly those with severe / complex disabilities?

The Project was not directly related to the de--institutionalization of children with disability but represented an initiative which was well positioned to create possible alternatives to residential care. Although Serbia is a country with a very low rate of institutionalization of children with disability, there has been a constant but somehow slow decrease in the period from 2008 to 2012. According to the data provided by UNICEF and the Republic Institute for Social Protection, the official number of children with disability in residential care in 2008 was 1,587 while that number decreased to 1,218 in 2012. Within the Project, UNICEF has commissioned a study to the Republic Institute for Social Protection “Trends and Characteristics of Institutional Placement of Children with Disabilities in the period 2000-2011.” The study finds out that the (relatively low) number of children with disabilities placed in residential care itself is not at the heart of the problem, but the conditions of their institutionalization. Children are often placed in large residential institutions together with adults with minimal conditions for effective treatment and severe reduction in the quality of life. The study concludes that the institutional environment creates “negative effects on children’s psychological and social development” with suggestion that alternative care solutions should become a priority in the process of deinstitutionalization. The development of alternative care primarily through CBSS is considered among the primary tools for preventing child institutionalization. In addition to Institute’s study and within the Project activities, NGO Familia has conducted a research on the effects of small home communities on the children from the large Kulina institution who were unable to return to their biological families. The research came to similar conclusions on the importance of alternative CBSS for children with disabilities.

In respect to Project’s contribution to the reduction of the number of institutionalised children with disability, the evaluation team found that it may be too early to establish a clear correlation between the two processes. UNICEF project team has made an extra effort to provide the evaluation with information on the institutionalization trends between 2008 and 2012 in the 41 targeted municipalities. Although showing a certain reduction in the number of institutionalized children from 162 to 91 (-71), the data comes from two different sources (Republic Institute and Statistics Bureau) and therefore remains inconclusive for a valid comparison. Nevertheless, the triangulation of research studies, official statistical documents and field interviews of the evaluation exercise demonstrates a positive trend in the reduction of children in residential institutions located in the targeted municipalities which can be only further accelerated with improvement of quality standards in the existing CBSS and establishment of the new services in other municipalities.

Box 3. Impact of the Project on Children with Disability in Foster Care The evaluation team was somewhat surprised to find a number of foster parents attending the two focus groups organized during the site visits (due to low percentage of children with disability taken into foster care). The foster parents we had an opportunity to talk to have emphasized the importance of the community-based services for the children who were moved from the institutions to foster care. For example, a foster parent from Čoka has shared with the team that the aggression level and basic motor skills of a boy aged 6 taken from an institution in Belgrade have vastly diminished, respectively improved in the Čoka day care centre. The self-aggression (beating on the head and chest) has almost disappeared while the boy successfully learned basic self-feeding and hygiene skills which were non-existent during his placement in the institution.

EQ: Was the project successful in improving the quality of life and social inclusion of children with disabilities and their families reached through community services?

Measuring the difference in the quality of life and social inclusion of children with disability and their families which were reached by the Project activities was carefully planned by the UNICEF project team. The Political Science Faculty of the University of Belgrade was commissioned to undertake an in-depth study of the impact of CBSS on children with disability and their families. The Faculty conducted an elaborate study, using qualitative and quantitative methodology with two rounds of surveys and interviews conducted in 2011 and 2012. The research was carried out in 35 municipalities, with the first round of data gathering conducted at the beginning of the community service operation and the second round after one year of continuous use of the CBSS. The research included a survey with 358 respondents (mostly family members) and 11 focus groups with 49 parents (only 9 eventually used due to irregularities in 2 groups). Respecting necessary privacy and confidentiality standards with parental consent, the researchers also conducted interviews with 20 children beneficiaries (with more than half of the children in need of constant supervision 54.4%). The family member respondents were mostly mothers (85%) from low income families who are unemployed and rely on some form of CSW social welfare assistance (42% child benefits and 58% care and assistance benefit). The research team used a number of statistical instruments and satisfaction measurement scales to analyse and present the gathered data; in this respect, the study represents an invaluable source of information and reference not only for the purpose of assessing the Project’s impact but also in terms of a wider context of child welfare reform in respect to children with disability and their families.

According to this study, 94.9% of users are completely or mostly satisfied with the service after one year of using it. The qualitative analysis is presented from three perspectives of service satisfaction: parental in respect to children, parental in respect to quality of family life and the children’s perspective. The qualitative findings of the study are overwhelmingly positive in all three aspects of community-based service impact:

- Parental views in respect to children: general mood (the children are much happier, have less occurrences of aggression and are in a better mood); bonding (the children have bonded with service personnel); self-reliance and confidence (depending on disability, it ranges from self-feeding and basic hygiene to public speaking); improvement of social skills etc.

- Parental views in respect to quality of family life: more time for personal obligations; more time for other family members; socializing with other parents (sharing problems and experiences).

- Children’s perspective: children like to come to the day centre and spend time there; time spent in transportation, where organized, is having great positive effects since many of children do not spent much time outside their homes; positive reaction of parents to child’s activities in the centre etc.

The challenges the parents have pointed out mostly relate to issues of access (transportation to day care service, home assistance frequency), versatility of services (most municipalities have only one service available) as well as specialized aid within the service (in most cases lack of speech and physiotherapists). In terms of social environment, the study finds a large percentage of parents stating that they do not feel stigmatized (42.9%) by their communities, however in a more concerning majority of cases (57%) the parents feel excluded from the community with only basic acceptance of the nearest relatives (23.7%) or complete isolation, exclusion and avoidance by community members.

Within the scope of the field visits to the sampled clusters, the evaluation team has conducted focus groups with 7 parents from Čoka and 16 parents from Gazdin Han, Aleksinac, Ražanj and Crveni Krst-Nis. It also interviewed 2 parents during the visit of the day care centre in Zemun. In discussion with parents, the evaluation team made very similar findings to those stated in the Faculty of Political Science study. Nevertheless, a number of impact related findings from the focus groups need to be highlighted, while some of the others (especially in terms of the social inclusion) are inclined to emphasize the challenges that the parents face more profoundly than it is the case in the Political Science Department study:

- Parents have noticed life-altering improvements with the children after the time spent in the day care services, especially in cases where specialized therapists have been working with the children, depending on the type of disability, experiences range from advanced social interactions and integration into elementary schools to maintaining basic hygiene without assistance;

- Parents have more time for their regular errands and for maintaining relationship with other family members and friends, although in some cases they suggested that extension of working hours would enable them to find jobs and contribute to service financing (3-4 hours of day care or home assistance in majority of services is not sufficient for that purpose);

- Access for the most endangered families and those located in remote rural areas remains the greatest challenge for sustainability of the established services (Novi Kneževac day care, Zemun day care, Ražanj, Gadžin Han and Crveni Krst home assistance);

- Services which have been started but discontinued represent a significant source of frustration for the families, once the children get used to them (for example, the respite care in Aleksinac and stoppage of work during the three months of summer in Čoka day care centre);

- The biggest disappointment surely comes in cases where the services operated for 12-18 months during the project implementation and have been closed down soon after the expiry of project funds without clear indication if the service will continue (home assistance in Gadžin Han and Crveni Krst – Nis).

## 4.5	Sustainability

EQ: To what extent the legislative framework developed and policy documents produced provide a ground for sustainable development of quality community services and particularly in less developed regions in Serbia?

UNICEF’s support for the legislative framework in respect to the Project objectives and contribution to implementation of the 2011 Social Welfare Law has been described at length in the Effectiveness section above. It has been pointed out that about 30% (9 out of 30) of the drafted by-laws and rule-books have so far been officially adopted. However, it is important to stress that this one third of the adopted regulations include key pieces of legislation which are allowing for standardization and improvement of the CBSS according to the Social Welfare Law. The Rulebook on Service Standards has outlined a set of basic preconditions for the establishment of CBSS for children with disability which were introduced in Serbia for the first time through the project such as respite care and personal assistance. The adoption of the rulebook allowed for more relevant accredited training packages and programmes and full use of the practicums and guides for community service establishment and running developed by the Republic and Provincial Institutes for Social Protection. Of no less importance for further development of the CBSS are the adopted Rule-books on Licensing of social work professionals and Licensing of service providers. The first has enabled the Chamber of Social Welfare to initiate the process of licensing thereby influencing the CSW personnel to take more interest in the new quality standards and Social Welfare Law rules and regulations. The licensing procedure will also create conditions where CSW case managers are more likely to take interest in the series of trainings remaining to be performed under the capacity development activities. The adoption of the Rulebook on Licensing of the service providers has already inspired discussions and exchange of ideas in the stakeholder community especially between the NGOs (MODS) and the MoLESP in terms of the minimum conditions which the service providers need to achieve in the next three years.

In terms of the sustainability of the services in the least developed municipalities, the issue still hanging in the balance is the adoption of the Decree on special transfers (or ear-marked funding). The municipalities participating in the grant scheme of IPA 2008 Project have issued Decisions on Social Protection which officially established the new services as formal budget lines of the LSGs. The official status of the community services enabled parent associations and informal parent groups to create certain pressure on municipal representatives in a number of places where sustainability was put in question upon project expiry. However, the official decisions and budget lines do not represent an automatic assurance of sustainability when funding is not available, especially in the least developed municipalities where social services are first in the line of cuts in times of financial crisis or sudden changes in municipal government (which is a common occurrence at local level government in Serbia). For that reason, a number of stakeholders from the LSGs, CSWs and NGOs have stressed the utmost importance of passing the Decree on special transfers. MoLESP has provided assurances that the decree will be considered in the national budget draft for 2014.

EQ: To what extent national level mechanisms strengthened for monitoring and capacities improved for reporting on child-care reforms are likely to continue being effective beyond the project time-frame?

The social inspectors from MoLESP have been included by UNICEF in the two rounds of the monitoring visits to each of the ten clusters. While the joined visits were important capacity building exercises for both the inspectors and the community services visited, it remains unclear if the same intensity of the monitoring by MoLESP will continue after the project has finished. Another concern is the lack of any institutional follow-up on the reoccurring irregularities that have been identified and recorded by the MoLESP inspectors. The main reason seems to be the understaffing of the ministry’s inspectorate department and therefore its inability to effectively cover the 174 units of the LSG in Serbia. At local level, the Project established regular reporting lines between the community services and LSGs and it is a reasonable expectation that the reporting will continue in those municipalities that have guaranteed budgetary appropriations for 2014. However, UNICEF project team and local NGOs have pointed out that LSGs have insufficient capacities for active monitoring of the CBSS. Coupled with weak inspection capacity at the national level, there is a clear concern about the government’s capacity (at both national and local levels) to monitor and evaluate the enforcement of the adopted secondary legislation and quality standards.

UNICEF has worked extensively with the Republic Institute for Social Protection in order to improve its capacities for developing child welfare indicators and data gathering on the CBSS from the CSWs and other service providers. There are obvious improvements in the scope, complexity and quality of the annual reports on the work of the CSWs issued by the Republic Institute for Social Protection. However, collection of accurate data remains a challenge at the local level, partly due to low reporting capacities of the CSWs but also due to slow implementation of other projects which targeted social welfare data collection systems (namely DILS project).

EQ: What is the likeliness that local municipalities will continue financing community services that target the most marginalized families with children with disability?

The Description of Action (page 22) identified a major financial sustainability risk from the very beginning: “The modest budgetary resources municipalities could potentially ear-mark for community services are even smaller, due to economic crisis”. As well, all three annual reports of the Project have pointed to the sustainability of the services as one of the most important challenges of this Project. UNICEF has made every possible effort to ensure the sustainability of its actions at the national and local levels, especially in terms of continuation of the established CBSS. As already mentioned in the report, UNICEF insistence on adopting the Decisions on Social Protection effectively establishing the services in the municipal budges had a significant impact on increasing the chances of service survival beyond Project completion. However there are at least two reasons which caused the CBSS in a number of municipalities to come into jeopardy of closing down or to already be discontinued after the project funding depleted, as follows:

- Least developed municipalities which cannot maintain services without external funding or national budget aid (special transfers) due to severe budget shortages (for example Gadžin Han and Prokuplje home assistance);

- Municipalities within a larger city government (Zemun - Belgrade and Crveni Krst - Nis) which cannot secure reliable funding continuation due to reduced competencies for social welfare policy making and budgetary appropriations.

While there are some positive indications that the first set of sustainability issues may be addressed by adoption of the special transfers legislation at the national level, the second problem is far more complex. The cluster members from the larger cities did not make sustainability arrangements with the city governments prior to project implementation which led to city government’s refusal to automatically continue the financing of the established service upon project completion (see Box 4).

Box 4. Sustainability Challenges in City Municipalities In Crveni Krst municipality (part of the city of Nis), the local government opened an official budget line for the home assistance service and the local CSW is waiting the city government decision to continue the delivery of the service. Nevertheless, the service has been discontinued since March 2013 and there is no clear indication if the city government will approve the continuation and to transfer the necessary funds. The situation in the city municipality of Zemun (part of Belgrade) is worse since the municipality did not open a budget line for the service continuation, while the City Council for Social Welfare gave no indication on further funding of the service. Unlike Crveni Krst, the Zemun community service still operated from July (when the EU grant ended) to October 2013, thanks to the unbelievable enthusiasm of the professional staff working there, although they were not paid for the past six months. The operation of the day care centre in Zemun was unsustainable and the discontinuation of the service was imminent.

Annex 7 provides an overview of the sustainability prospects for all ten clusters and 41 municipalities. The data on the current status of services is based on a combination of information sources: final monitoring report, EUD Impact Evaluation Survey IPA 2008 (March 2013), data provided by UNICEF project staff and regional mentors, evaluation findings during and after the field mission. Out of 52 services supported by the project, the following have been completely discontinued: Vrnjacka Banja home assistance, Prokuplje home assistance, Gadžin Han home assistance, Crveni Krst home assistance, Aleksinac respite care, Knjazevac respite care and Zemun day care centre. It has to be noted that respite care services will adjust to assist the day care centres but without full-time staff or hours of operation. Apart from the services which have been completely stopped due to the lack of funding, a number of other services transferred to municipal funding have reduced their capacities and quality of service upon project completion. The evaluation team has noticed capacity reductions in all clusters and municipalities visited on the field phase, except the day care centre in Aleksinac which still functions with full capacity and quality: Novi Kneževac day care centre operates with reduced capacity due to access issues; Čoka day care centre has been closed for three months and lost its specialized therapists (physiotherapist and speech therapist) and it also has medium terms issues with accommodation; Ražanj home assistance operates with reduced capacity due to access issues.

In summary, the Project succeeded in ensuring full or partial sustainability for 45 out of 52 services or 86.5% for at least one more year of operation. If the evaluation team findings from the field sample are extrapolated to the remaining municipalities, it is safe to assume that a large number of services have reduced their capacity and lowered the quality of service upon project expiry. However, qualitative findings suggest that, even with reduced capacity, the CBSS developed by the Project create significant positive differences for the quality of life of the targeted beneficiaries. For instance, families whose children use Čoka day care centre have reported that the service has reduced in quality due to lack of specialized therapists, however they were delighted and grateful when the CSW reopened the service after the summer break. There are also excellent examples such as the day care centres in Aleksinac and Stara Pazova as well as personal assistance service in Kikinda which continue to operate with full capacity and full satisfaction of children and their families.

However, it should be noted that the full enforcement of quality standards might discontinue some of the services, due to the inability of service providers to comply with the respective conditions. Most exposed are the services run by NGOs which face big difficulties in ensuring the right premises for their functioning.

EQ: To what extent are new knowledge and skills integrated into regular activities of professionals working with children with disability and their families whether they work as service providers or case-managers in centres for social work?

In the Effectiveness section above, we have pointed out that UNICEF planned and conducted a large number of seminars, trainings and workshops for service managers and service providers in collaboration with the Republic and Provincial Institutes for Social Protection. In 75% of cases where the services were established for the first time, the trainings were an essential precondition for service commencement. According to the findings of the evaluation team, most members of PIUs and professionals employed in the services report positive experience from the trainings in terms of knowledge acquisition and skills development. The usefulness of the trainings was especially highlighted by the professional therapists, for example the physiotherapist from Aleksinac day care who commended the Montessori programme training he attended and which he now uses in his daily sessions with the children. The mapping exercise and training were particularly useful for the CSW case managers as they gained knowledge on recognition and identification of families who might have children with disabilities at home in need of extra-help. The educational trainings for the care-givers provided an essential set of basic skills for women who were previously employed in industrial sectors. Based on the comments of the parents and families, it could be concluded that the care-givers are good for supporting with basic needs, but home service could be vastly improved if they improve their skills and knowledge in terms of providing basic therapy to children as done in the day care centres.

To be noted is that all training programmes delivered with Project support, less the ones provided by the CLDS, are accredited. The MoLESP and municipalities could thus continue to use such trainings beyond the lifetime of the Project.

UNICEF plans for training of case managers in CSW have been transferred to Year 3 and will be implemented in the extension period mainly due to the postponement in the revision of the necessary rulebook and development of accredited training packages. The final set of trainings for CSW professionals needs to be fully implemented due to the pressing need of their transition from the service provider to the primary focal point for assessments and referrals within the new system established by the Law on Social Welfare and revised Rulebook on CSWs. Indeed, given the underdeveloped market of service providers, most of the services are at the moment provided by the CSWs, while their main mandate is of a different nature.

EQ: Are independent national and local actors more likely to consistently monitor and advocate for the rights of the most marginalized?

In terms of Project results, it has been pointed out that the independent oversight bodies and CSOs were strengthened their capacities to monitor the implementation of child care reform and advocate for the sustainability of the Project results. On the national level, UNICEF has successfully cooperated with Ombudsman’s office in terms of advancing the child care reform agenda and supporting the office in its strive to draft a dedicated law on the promotion, protection and realisation of children’s rights, emphasizing the rights of children with disabilities (there are no special norms for these children in the current social welfare law). The Commissioner for Equality produced a first Special Report on Discrimination of Children in Serbia. The report, submitted and presented in the Parliament in November 2013, is essential in creating the prerequisites for raising institutional awareness at the national level on the large numbers of unidentified or “invisible” children with disabilities in need of access of CBSS. Both institutions are highly likely to continue their monitoring and advocacy work on the child care reform. The relatively centralized location of national oversight bodies and their limited human capacities demanded a solid network of local actors to provide independent monitoring information from the field and raise the alarm bells for the patterns and cases of discrimination and neglect. In this respect, a significant Project achievement was the strengthening of MODS, which resulted in several important advocacy initiatives as discussed in the Effectiveness section.

However the monitoring and advocacy capacities of the independent actors at the local level remain rather weak. The Project annual reports have indicated that the official municipal capacities for monitoring and evaluation are virtually non-existent; when this fact is coupled with weak capacities of CSOs, the monitoring and advocacy initiatives beyond the three largest cities (Belgrade, Novi Sad, Nis) are not likely to produce the necessary amount of information for the independent oversight bodies at the national level. Moreover, the current model of international support to CSOs is going to be soon replaced with more accountable but also more complex access to funding as Serbia gets closer to the European Union. A large number of CSOs, including the centrally located ones, are not prepared for significant shifts in terms of their funding opportunities and accountability. The international organizations, including UNICEF, would do well to use the remaining time until Serbia gets into the EU and assist the CSO sector in its transition to the new funding models, including promotion of partnerships with municipal governments.

## 4.6	Human rights and cross-cutting issues

EQ: Has the project actively contributed to the promotion of child rights?

The Project has a major contribution to the promotion and realisation of child rights. It did so through:

- opening access to CBSS, well tailored to the needs of most of its beneficiaries;

- impressive analytical work to provide evidence on the needs and rights of children which were breached;

- supporting oversight bodies at national level to strengthen their capacity to identify and report on discrimination of children with disability and inequality cases;

- developing the capacity of CSOs to network and advocate for child rights at local level, while holding the LSGs accountable.

Box 5. Holding Government Accountable for Implementing Adopted Policies - MODS adopted a platform for advocating; two thematic sub-groups formed. Network produced reports on a) child and youth led participation in decision making process at local level, b) VAT on baby equipment, c) cash benefits for children, d) inclusive education. - Cooperation of MODS with the independent state institutions (Ombudsman and Commissioner for the Protection of equality) initiated and established, as well as cooperation with the key government ministries for the implementation of child rights (education, health and social protection), and the Parliamentary Committee for Child Rights established. - 10 CSOs successfully implemented local advocacy initiatives aimed at (contributing to) ensuring sustainable financing of community services (in 10 out of 41 municipalities). - 5 child-related monitoring missions / reports issued by Ombudsman office and Commissioner for Equality and communicated to the decision makers - 2 policy briefs/position papers on child-related issues - the first special report on discrimination of children in Serbia, with focus on the most marginalized groups of children Source: UNICEF Theory of Change

Over the Project lifetime, UNICEF has influenced significant shifts in thinking in Serbia about child rights norms and biases related to children with disability, as acknowledged by the numerous stakeholders consulted for the purpose of this evaluation. However, sustainable outcomes require changes of practices and ingrained cultural norms and values which cannot be easily achieved in a 3-year time frame, especially at municipality level, take time to happen. The discontinuation of CBSS in several municipalities indicates the lack of priority given by those municipalities to issues of marginalisation and social exclusion of children with disability and their families.

The Project had nevertheless a positive contribution to the strengthening of the capacity of a wide range of Serbian duty-bearers (MoLESP, Institutes for Social Protection, oversight national bodies, CSWs, CSOs, etc.) to protect and fulfil child rights, as well as to report on progress against various international human rights standards generally.

The Project also had a positive contribution to capacitating parents, as rights-holders, in terms of access to information about available services, better governance and, to a certain extent, enhancement of their skills to take care of their own children. Although several parents’ associations emerged as an indirect effect of the Project which could theoretically put pressure on LSGs to continue the running of services, its role has been limited in equipping the weakest parents with the knowledge and abilities to claim and fully exercise their rights. This is an important aspect of the Human Rights-Based Approach in the programming of UN support which has been overlooked in the Description of Action, most likely due to the already set scope and boundaries in the IPA 2008 Project Fiche i.e. the reference document for the Description of Action.

The Project has been guided by the overarching human rights principles of non-discrimination, equality, accountability, rule of law and inclusion. The participation principle was not sufficiently well represented mainly due to the lack of explicit and concrete involvement of parents, in their double capacity of duty-bearers and rights-holders, in the Project planning and implementation work. The principles of progressive realization of human rights and use of maximum available resources by duty-bearers were implicit in the implementation of the Project. The empowerment principle worked generally well at the level of duty-bearers, notably for female care-givers and professionals engaged in the CBSS.

EQ: Has the project reflected gender mainstreaming issues?

In the IPA 2008 Social Inclusion Project Fiche of the EUD, one of the indicators was “a total of 1,000 women licensed as service providers at the local level among targeted municipal clusters by 2012”. According to the same document, these women were supposed to be “victims of family violence, Roma women, women in rural areas, older population of women that have the least chance of employability” and who would benefit of educational courses to enable them obtain a licence for the provision of social services. This indicator (dating back 2008, when the Project Fiche was designed) has not been transposed in the Contribution Agreement concluded with UNICEF and corresponding Description of Action for good reasons: according to the Rulebook on Licensing of Service Providers, a service provider should comply with very strict conditions for being licensed, which are impossible to be met by the categories of vulnerable women mentioned in the IPA 2008 Project Fiche; the same applies to the licensing conditions of social welfare professionals. UNICEF has however agreed to include in the Description of Action unemployed women among the final beneficiaries, but without any quantitative or qualitative reflection in a specific Project indicator: “unemployed women who will receive training for provision of support to families with children with disability, and have the opportunity to work for community service providers”.

Project indicators in the Description of Action were gender-blind. The Project Advisory Group was supposed “to ensure that criteria for gender sensitivity, anti-discrimination and equal opportunities is integrated into the funding of community services, irrespective of the source of funding (EC, Lottery Fund, ear-marked transfers, SIF etc.)”. The evaluation team did not identify any evidence that this was the case. The UNICEF project team confirmed that the Advisory Group was “an unofficial group that was consulted regarding what the grants scheme should focus on and made the decision on which Community based services were to be piloted through the Grants Scheme”.

As mentioned in the previous sections of the report, training was provided to 138 care-givers (all women), totalling 216 hours of training (Table 6) and were highly regarded by the trainees for their practical content and ability to develop new skills in a very short period of time. As far as employment is concerned, the evaluation team was informed that 83% of employees of CBSS were women with many of them coming from very poor backgrounds. From this perspective, it could be assessed that the Project paid particular attention to women empowerment.

As far as beneficiaries of CBSS are concerned, the latest figures provided by UNICEF indicate a percentage of 56% boys and 42% girls with disability. Without knowing the total number of children with disability in Serbia and their gender distribution for reasons explained in other section of this report, and without having a gender-based vulnerability profile of these children, it is difficult to judge to what extent gender mainstreaming has been ensured in the provision of CBSS.

An important achievement of the Project in terms of gender mainstreaming was the strengthened analytical capacity of the Republic Institute for Social Protection, whose latest annual reports use gender disaggregated data.

EQ: To what extent and how the project ensured an equity focus? Was the design of the Project ethical? How was the balance of cost and benefits to participants (including possible negative impact) considered during the project implementation?

The Project planned to ensure an equity focus by orienting EU grant and domestic investment towards the most under-developed municipalities of the country as well as by focusing its intervention on the most vulnerable children with disability and their families. The evaluation team considers that the Project has in most cases succeeded to do so.

A proportion of 76% (31 municipalities) of granted municipalities were under-developed, according to the Decision on the establishment of unified list of the development of regions and self-government units for 2010 (Government of Serbia session, 26 July  2010). Moreover, the Project has instrumental in the development of the draft Decree on Special Transfers (ear-marked funding to the most under-developed municipalities) and advocacy for its adoption. The decree is expected to be adopted by the end of 2013 and be considered in the budgeting exercise for 2014.

In the Description of Action, UNICEF acknowledged that “where services exist, the access of the most marginalized children (either marginalized because of more severe disability or by poverty) is questionable. Although no “hard” data is available, experience from the ground seems to indicate that the beneficiaries of day centres are usually children and youth with moderate disability and often from families that are not under the poverty-line”. As the goal was to ensure support especially to the most marginalised children with disability and their families, the Project has strived to first identify them and analyse their needs, and secondly to train service providers on prioritising access. In this respect, the design of the Project and its activities had a strong equity and ethical focus.

Box 6. ”Invisible” Children Prior to implementation of Project there were no reliable data on the number of children with disability outside state institutions. The only vague indication for the municipal officials working on grant applications (assisted by the UNICEF regional mentors) were data from the CSWs and existing day care centres and elementary schools. The CSWs held data only on families receiving other poverty or child related cash-benefit assistance while data for existing community services relied on estimates from bilateral donors, charity organizations and informal parents networks. The population in remote and rural areas had limited or no access to the CSWs mostly located in the urban municipality centres. In this respect there was a realistic danger that the children that are most marginalized or with most severe disability remain unidentified and without access to the newly established services. For that reason, a series of trainings on identification of the most excluded children with disability and their families was conducted by the project partner NGO Amity which led to the identification of 673 children with disabilities in the 41 targeted municipalities who have never used any kind of community-based service. According to Amity, the number of the most vulnerable children with disabilities who were not registered by any state institution (social, health or educational) and who were eventually included in the IPA supported community-based services was 246 children.

However, some planning flaws in the local projects design phase and financial constraints after the project money came to an end restricted the access of some of the poorest and remotely located children, especially from rural areas. Although the home assistance service was specifically designed for the most vulnerable beneficiaries, this goal has not been always reached due to a number of reasons identified by the evaluation team, as follows:

- transportation means planned and provided mainly in cluster lead municipalities while outlaying partners suffered of access difficulties (observed in both field visits in Čoka and Aleksinac clusters); the same issue hampers predominantly rural municipalities with day care centres which did not plan for transportation of children with multiple disadvantages (disability, poverty, location);

- most home assistance care-givers have been previously unemployed women who were paid a salary in the Project equivalent to the minimum wage per economy, therefore without means to provide or cover their own transportation; unreliable public transport prevents care-givers from visiting remotely located beneficiaries (Ražanj, Crveni Krst);

- post-project service sustainability with a number of services stopping work or reducing service (mostly in home assistance) immediately upon project completion (discussed at length in the Sustainability section); in some services (e.g. Zemun, Aleksinac), the evaluation team met parents of children with moderate disability who were well above the poverty line, which put in question the referral and prioritisation of access by the CSWs for the most disadvantaged children and their families, especially in time of limited post-project resources. Timely training of case managers in CSWs (part of the Project) and efficient functioning of the local Inter-Sectoral Committees might have led to a better referral and equity in access.

# 4.	Conclusions and Recommendations

## 4.1	Conclusions

Relevance

The Project “Developing Community-based Services for Children with Disabilities and their Families” is highly relevant for Serbia’s child care reforms and national policies for improving the lives of children with disability as it addressed the most pressing needs of the reform. The Project is in line with Serbia’s Social Welfare Strategy and the Plan of Action for Children while its primary objectives are tied to the implementation of the recently adopted Social Welfare Law. It is highly relevant for Serbia’s international commitments deriving from the ratification of the Convention on the Rights of the Child, CEDAW  and Convention on the Rights of Persons with Disabilities and its status of EU candidate country. The Project remained relevant over its entire lifetime, as documented by the annual progress reports of the EC. UNICEF is seen as best positioned to advocate and promote the the rights of children with disability in partnership with the Government of Serbia and other key national counterparts and donors.

Effectiveness

The Project was effective in achieving the results and objectives as outlined in the Logical Framework and the Theory of Change. UNICEF’s partnership with MoLESP allowed for effective and coordinated development of the complex secondary legislation documents which were drafted and submitted for adoption according to project plans.The planned number of beneficiaries was achieved only partially (78%), due to an over-estimation in some local projects. The lack of quality standards at the time coupled with lack of experience and benchmarks for new services are factors which made the applications not always feasible in terms of estimated indicators. Almost all planned capacity building actions for municipalities and training providers have been completed. The Project effectively prepared the municipalities for their new roles in social welfare provision. Overall, the Project speeded up the pace of reform, especially by pushing the development of community-based services, an essential pillar of the social welfare system besides the cash benefits assistance.

Efficiency

Most of the planned Project activities have been delivered in an efficient and timely manner substantiated by high quality progress reports. The clustering concept of grant delivery worked very well for cost-effectiveness (simplified public procurements and funds transfers) and exchange of experience but with challenges in terms of joint decision making and budget transparency. The project did not take into consideration the special status of the “city municipalities” which lagged behind in all project implementation aspects due to reduced competencies and budgetary appropriations. In certain cases, the over-estimation of potential beneficiary numbers resulted in uneven use of human resources and reduced cost-effectiveness. Efficiency has been facilitated by the excellent co-ordination between the project component implemented by UNICEF and the grant scheme component managed by the EUD as well as by the synergy with projects financed by other donors.

Impact

The project had a general high impact level, making a major contribution to increasing the number of children with disabilities benefiting from community-based services. The findings indicate a positive trend in the reduction of children in residential institutions located in the municipalities where community-based services function, although this co-relation is not directly established. The beneficiary families, as rights-holders, reported significant improvements in the quality of life for their children and family members as a result of service establishment as well increased socialization and engagement in community activities. Impact would have been higher in case the access issue for children in remote and rural localities was better addressed. The mapping exercise conducted by the Project worked well for identification of children in grant municipalities but highlighted the likely high number of children in Serbia who are still in need of identification and outreach. Although the impact on the national level was very high in terms of legislative development, the capabilities of the CSW network to handle the implementation of the new legislation in terms of case management and referral system, as well as of data collection and reporting are rather low, requiring further capacity building interventions.

Sustainability

Most effects and outcomes of the Project are likely sustainable especially in terms of a comprehensive regulatory package for the establishment of new community-based social services at the national level. The capacity building tools, accredited training programs, practicums and research methodologies and materials developed with project’s partners are already in use or could easily be used for future establishment of similar community services. The majority of grant receiving municipalities have ensured sustainability of the established services for 2014, with strong indications of permanent financing; however, the least developed municipalities will face difficulties to ensure sustainability without the Decree on Special Transfers. The most significant sustainability issues are registered in “city municipalities” where services were stopped, requiring alternative financing solutions. Full enforcement of quality standards might discontinue some of the services, due to the inability of service providers to comply with the respective conditions, most vulnerable being the services run by NGOs. Weak inspection capacity at national level to monitor and evaluate the enforcement of adopted secondary legislation and quality standards is a matter of significant concern.

Human rights and Cross-cutting issues

The Project had a major contribution to the promotion and realisation of child rights through opening access to community services, supporting oversight bodies to identify and report on discrimination of children with disability and developing the capacity of CSOs to network and advocate for child rights at local level. It had a positive contribution to the strengthening of the capacity of a wide range of Serbian duty-bearers to protect and fulfil child rights and to capacitating parents, as rights-holders, in terms of access to information about available services and better governance. The Project paid particular attention to women empowerment, through training and job creation in community services. It managed in almost all cases to ensure an equity focus by orienting EU grant and domestic investment towards the most under-developed municipalities as well as by focusing its intervention on the most vulnerable children with disability and their families. However, some planning flaws in the local projects design phase and financial constraints after the project money came to an end restricted the access of some of the poorest and remotely located children, especially from rural areas.

## 4.2	Recommendations and Lessons Learnt

4.2.1 Recommendations

Table 9 below provides a number of key recommendations based on the findings and conclusions of the evaluation as well as based on consultation with all key stakeholders that were interviewed during the field phase. Each interview, focus group and discussion group has checked the perceptions of various stakeholders (MoLESP, Republican Institute for Social Protection, independent oversight bodies, municipalities, CSWs, service providers, professionals, parents, CSOs) concerning the top   priorities of the child-care reform in Serbia that needs to be addressed in the coming years and consequently the role each of these stakeholders should play (see also Interview Guides in Annex 5).

Validation of recommendations was planned to be done in two phases: 1) by UNICEF and the MoLESP, as key stakeholders, following submission of the draft report; and 2) by other stakeholders, during the final project conference. No comment has been formulated by the UNICEF and the MoLESP concerning the recommendations included in the draft report, meaning an implicit agreement of proposals. During the final project conference, which took place on 4-5 December 2013, the participants (most of them already interviewed by the evaluation team) were provided with a summary of the evaluation report and the Team Leader made a presentation in the plenary on the main conclusions, recommendations and lessons learnt. The participants have validated the findings and adhered to the recommendations made by the evaluation team.

Recommendations are divided into two categories, as follows:

Each recommendation has an addressee and a proposed timing.

###### Table 9. List of Recommendations

| No | Recommendation | Addressee | Timing |
| --- | --- | --- | --- |
| Strategic (S) |  |  |  |
| S1 | Further invest in the development and diversification of country-wide community-based social services to contribute to the social inclusion of the most vulnerable children with disability and prevent separation from their families The support provided by UNICEF, EU and other donors for the development of community-based social services for children with disability should continue in order to assist the Serbian authorities at central and local level to cope with a number of challenges during the years to come, as follows: a) expansion of CBSS to all municipalities across the country; b) diversification of the range of CBSS according to the needs of the vulnerable children with disability in parallel with increasing their quality; d) development of a cross-sectoral approach among social, health and education systems in service delivery and development of joint standards for cross-sectoral services based on inter-ministerial cooperation; e) mainstreaming of the most successful services in the social welfare system across the country; f) promote inter-municipality partnerships in the development of CBSS to ensure economies of scale and budget efficiency through a multiplier effect, based on transparent budget appropriations for each partner and accountability rules; g) enforcement of future legal provision for ear-marked transfers to under-developed municipalities for setting up and running CBSS. The most at-risk families caring for children with disabilities should become a focus of future projects design either through enhancement of home assistance service efforts or creation of family centres offering a more comprehensive support to most vulnerable beneficiaries in a family friendly environment. | MoLESP and LSGs, with the support of UNICEF, EU and other donors | As from 2013 |
| S2 | Develop a culture of lifelong learning within Centres for Social Work (CSW) to ensure that managers and staff keep pace with reforms and are empowered to address the needs of children with disability at highest professional standards Managers and staff of CSW, especially case managers, should be provided access to up-to-date learning opportunities for personal and professional development. Of particular importance is the need for strengthening CSWs capacities to work with parents (biological and foster) to raise their parental skills and provide informed and professional referral decisions (including those of Inter-Sectoral Committees for inclusive education, where CSWs are represented) as well as correct prioritising of access to various services. In this respect, the package of accredited trainings still to be delivered to CSW case managers could be put of good use. Monitoring of learning outcomes and continuous improvement of knowledge and skills should be a priority. Regular skills profiling to check gaps between the existing expertise and demand deriving from reforms implementation and from beneficiaries should be carried out to inform the staff development policy of the respective institutions. An internship system for young social workers is also recommended to be established. | MoLESP and Institutes for Social Protection, with the support of UNICEF, EU and other donors | 2013-2014 |
| S3 | Support the formation of a competitive market of service providers to ensure best quality of care at affordable prices for children with disabilities and their families In cooperation with government partners, UNICEF should encourage the development of a free market of community service providers, whereby CSOs take a more prominent role in the delivery of services and CSWs monopoly is diminished. The CSW network is overburdened by its double role as a referral and case management agent as well as a service provider, which is increasingly resulting in low quality of both aspects of their work. The new legislation and regulations on the service establishment and quality standards have created the necessary conditions for diversification of service providers which should be used to open competition for government subsidies (special transfers) and available donor funds for improvement of the community services for children with disabilities. Furthermore, the project has identified a number of families using state services who are not socially endangered and would be willing to engage in co-payment options for alternative care if such options are offered. This would reduce the pressure on the CSWs and the services provided by the state-funded institutions for the most marginalized and socially deprived children and families. Still, support to CSOs providing CBSS is badly needed to comply with quality standards and get the licensing for service provision. | MoLESP, Institutes for Social Protection, UNICEF, EU and other donors | 2014-2015 |
| S4 | Strengthen the quality assurance system of the community-based services for children with disability In the Project annual reports and the clusters monitoring reports, concern has been raised as to the low capacity of social inspectors from the MoLESP and municipalities to ensure a systematic and professional monitoring of the services with a view to their compliance with quality standards. The inspection department, a centralised structure within the Ministry, does not have the physical capacity to cover all services across the country, while municipalities lack dedicated staff for carrying out quality assurance tasks. As pointed out by many interviewed stakeholders, there is no effective oversight and monitoring mechanism at the local level. Due to the complexity of the problem, the MoLESP should consider conducting a feasibility study in order to analyse various options and scenarios for strengthening quality assurance of the services established through the project and the future services that will have to conform to the new regulations and standards. The study is expected to provide an informed guidance for decision-makers to pursue various policy options, either in the form of decentralised MoLESP inspection (setting up of municipality inspectorates) or possibly social auditing (external audit, contracted out by state bodies, based on international experience). Citizens’ oversight mechanisms could be also envisaged. | MoLESP, Academia and national think tanks, independent monitoring bodies, CSOs | 2014 |
| S5 | Improve data gathering systems for monitoring of child care reform and informed policy-making for the benefit of children with disability The evaluation report findings indicate that UNICEF has worked to the best of its abilities to assist MoLESP and Institutes for Social Protection in defining child welfare indicators and mainstream them into regular data collection systems. However, the data gathering systems for social welfare policy-making faces problematic issues at higher levels of government due to the lack of electronic information sharing among the ministries and slow implementation of large government projects for improvement of data collection (such as DILS). The IPA 2008 Project provided excellent alternatives for filling the information gaps by commissioning surveys and research studies which helped create certain baselines in terms of current situation in community service provision, approximate numbers of children at risk (mapping of services and beneficiaries), costing of services and analysis of impact on the lives of families and children. It is evident that further support is required for the MoLESP and Institutes for Social Protection to effectively use these results of the current project and create political and practical initiatives for linkage and access to other existing government databases. Horizontal electronic communication also needs to be improved between the MoLESP and Institutes for Social Protection in order to facilitate analysis and inform better policy making. Vertical line of support also needs concrete assistance especially in terms of CSW’s staff capacities to use indicators and collect relevant and reliable information within their reporting mandate. | MoLESP, Ministries of Health, Education and Internal Affairs, Directorate for Digital Agenda, Institutes for Social Protection, with donors support | 2014-2016 |
| S6 | Ensure that a more systematic Human Rights-Based Approach (HRBA) is used in the programming and implementation of future UNICEF projects targeting children and their families UNICEF has strived to ensure a good equity focus, promotion of child rights and gender mainstreaming in the Project. It has not always succeeded, as honestly acknowledged during the interviews with the evaluation team, mainly due to the project framework set by the IPA 2008 Fiche and CSWs failure to prioritise access adequately for the most disadvantaged children with disabilities. Nevertheless, it is strongly suggested that a systematic HRBA is used by UNICEF in future projects, which will ensure better and comprehensive targeting of support to the most needy, equity focus, a more transparent and empowering programming process for both duty-bearers and rights-holders, increased accountability for results and better effectiveness and sustainability of UNICEF interventions. The process should be guided by the UN Common Understanding on Human Rights-Based Approaches to Development Cooperation and Programming. An adequate level of disaggregation of indicators per gender, residence, wealth, social affiliation, etc. should be used. Assessment of rights’ holders capacity to claim rights should be part of the situational analysis, translated further in measurable support actions. | UNICEF | When programming new initiatives |
| Operational (O) |  |  |  |
| O1 | Carry out a country-wide identification of children with disabilities for evidence-based policy making and support action The mapping of “invisible children” done by the Project in the targeted municipalities and the data gathered by the CSWs and through newly established services clearly indicate that there are significant numbers of children with disabilities in need beyond the 41 municipalities in which the Project was implemented. By extrapolation, it is estimated that more than 1,000 children with disabilities are still unknown to any national or independent social service provider or other governmental institution (health, education). MoLESP should make further use of the tools developed in the current project and launch a country-wide initiative, possibly with UNICEF assistance, to identify the children with disabilities and assist the families in making the first steps in terms of their social inclusion and access to the nearest available services. CSWs and local civil society organizations should be capacitated to provide further assistance and devise means to remain in contact with the families and provide them with further support once the initial steps have been taken. | Local self government, CSWs, national network for children rights, local CSOs | Planning in 2014, delivery in 2015 |
| O2 | Adjust the approach to respite care to ensure its sustainability Notably the innovative respite care service has been the least successful in terms of in-project effectiveness and post-project sustainability. However, the evaluation findings based on triangulation of sources have proved that the need for respite care remains especially in terms of support to prevention of separation and deinstitutionalisation efforts. The families have also indicated huge dissatisfaction in cases where the services were discontinued and expressed interest in supporting their continuation. The MoLESP and UNICEF should rethink their approach to introduction of respite care both in terms of the scope and harmonization with other services: due to low numbers of beneficiaries on the municipal level perhaps a regional approach should be considered coupled with the family centre model discussed in S1 above. | MoLESP and UNICEF | 2015 |
| O3 | Develop a costing model for various community-based services addressing children with disability to guide local budgeting of services and benchmarking generally The project has supported a study on the costing of community-based services in Serbia and the effort in this direction should be continued in order to broaden and deepen the subject for the benefit of the accurate financial estimations in local budgets, but also in future projects. There is considerable variation of costs for similar services, which is not always due to local consumption prices and the like. The process would be greatly facilitated by the existence of service standards, but also benefit from international experience. The commissioning of such analytical work would be a logical follow-up to the activities already conducted in the Project and would serve the construction of field-grounded benchmarking for further expansion and improvement of services across the country. | Academia and national think tanks, Institutes for Social Protection, with support from UNICEF |  |
| O4 | Include clear accountability criteria in future grant agreements with municipalities There have been several situations in the Project when estimated indicators have been largely unmet, notably those concerning the number of beneficiaries. According to the information made available to the evaluation team, no grant deductions have been operated by the EUD for this misachievement. Given the status of candidate country of Serbia and the need to prepare for the very strict accountability rules and regulations governing the EU structural funding, it is recommended that much stricter performance criteria and accountability discipline are embedded in the future grant schemes addressed to local public administration. In case of projects done in partnership (clusters), the budget of the project should be designed in a transparent manner, with clear appropriations for each partner and based on a partnership agreement, signed by all partners, which sets the individual responsibilities of each partner, its financial contribution to the project, the reporting lines and accountability rules. If city municipalities are members of the partnership, an authorised signature from the city will be needed to endorse commitments done by the respective municipality. | EU Delegation | Whenever future grant schemes are designed |

4.2.2 Lessons Learnt

- Legal (official) commitments of beneficiary institutions at national and local levels are key to successful implementation of initiatives related to social welfare reform. The decree on special transfers for funding of community-based services in the least developed municipalities is still carefully weighted by the MoLESP and the Ministry of Finance. However, once adopted, it will represent a serious commitment on behalf of the government for sustainability of the established services, at least in the most disadvantaged areas of the country. The decisions on social protection adopted by the municipalities were an essential prerequisite for successful implementation of the project at the local level and preparation of the municipalities for their future role in social welfare reform. The decisions also served as a legal protection for the established services in terms of their functioning during the project and their short term sustainability. They also provided a pressure tool for beneficiaries (families) and civil society organizations in their struggle to improve the standards, quality and ensure continued existence of the established services.

- Concept of municipality clustering is very good for efficiency but less appropriate for effectiveness and sustainability. The design of the grant component, based on municipality clustering, provided significant advantages for project delivery and efficient coverage of a large number of municipalities. The model allowed for rapid procurement and fund transfers as well as for easier monitoring and reporting procedures which were conducted in an efficient and timely manner. However, it appears that clusters exhibited a certain lack of balance in favour of the lead municipalities as well as unsustainable form for future cooperation: unlike the decisions on social protection, the contracts between municipalities were lacking in form and content as well as any functional value beyond the project expiry. The evaluation team found very little evidence that the municipalities continued with cooperation on exchange of experiences or mutual assistance after completion of the project activities.

- Implementation of local projects in the (so-called) city municipalities has to be carefully planned. The problems the Project faced in the city municipalities, especially in terms of sustainability, is a significant lesson for future project when in comes to self-government arrangements in Serbia’s large cities. The success the project enjoyed with the Decisions on social protection made in the grant municipalities should have been replicated in the relationship between the city government and participating municipalities. Without a legal obligation or an official decision at the level of city government (Belgrade and Niš), the project resulted in city municipalities facing significant challenges in terms of future financing and functioning at the expense of most disadvantaged and marginalised children with disabilities and their families.

- Investing in academic and professional research as a back up to main activities brings significant returns. UNICEF has invested in a number of surveys, professional papers and research studies over the course of the Project, which provided an invaluable intellectual support and evidence not only for the main Project activities but for the future implementation of the child care reform in Serbia. In a situation where the objective of creating effective data collection and monitoring systems for the community-based services faced significant difficulties due to lack of capacities at national and local institutions, the academic research and civil society tools proved a valuable alternative source of information for the existing gaps. This especially refers to social services mapping exercises, children with disability identification tools and surveys studies related to the quality of the established services.

- Child care reforms cannot succeed without a strong CSW network. The CSW network received a certain capacity building boost through the Project activities but their structural institutional inefficiency and still weak competencies represent a considerable obstacle for efficient referral and prioritising of access of the most needy children as well as for the future improvement of the community-based services and implementation of the child care reform. The Rulebook on CSW adopted in 2008 introduced the case management mechanisms into an obsolete system of social welfare institutions on the local level which resulted in an overburdened staff and overstretched capacities of CSWs to maintain their role of case managers and service providers at the same time. The CSWs will require additional support in order to improve their capacities for identification of children with disabilities and their referral to the appropriate community-based services as well as for accurate reporting back to the Republic Institute for Social Protection for evidence-based policy-making.

- Community-Based Services represent a significant breakthrough for child care, but most vulnerable and neglected children with disabilities could still be in danger. The interviews of the evaluation team and independent surveys conducted through the project have recorded high satisfaction levels with the services by both the children and their families. There are significant improvements not only in the daily lives of the user families but also in their inclusion in social activities which they did not experience before. However the mapping exercises, research activities as well as home assistance and day care experiences have showed that there is a considerable number of children with disabilities in Serbia who are still not benefiting from any type of assistance and are most likely kept hidden by the families. Unfortunately the reduced capacities or discontinuation of activities in a number of services upon project expiry will in the first place effect the poorest, most vulnerable and disadvantaged children who were the primary beneficiaries in the project design. Accurate mapping of the most vulnerable children, correct referral and prioritising of access by CSWs, careful planning of support according to needs (including outreach facilities, professional therapists, etc.) and empowerment of parents to claim their rights are essential prerequisites which should accompany the community-based services.

Statistical Office of the Republic of Serbia http://webrzs.stat.gov.rs

Centre for Liberal-Democratic Studies, “Impact of the Crisis on the Labour Force Market and Living Standards in Serbia”, Belgrade, 2010

Municipalities with average GDP per capita at less than 50% of the national level (40 out of 174 municipalities)

Republic Institute for Social Protection, “Report on the Work of CSWs in Serbia in the year 2011”, Belgrade, 2012

UNICEF Serbia, “Mid-Term Review Report of 2011-2015 Country Programme of Cooperation Between the Government of Serbia and UNICEF”,  draft version, Belgrade, June 2013

Republic Institute for Social Protection, “Report on the Work of CSWs in Serbia in the year 2011”, Belgrade, 2012

http://www.devinfolive.info/profilelauncher/serbia/?lang=en, accessed on 18 October 2013

Ministry of Labour, Employment and Social Policy data

e.g. assessment of a child enrolled in school conducted in the mother tongue, delivery of pre-school education in minority language in certain conditions, provisions for inclusion of children with learning difficulties in the mainstream education, etc.

local mechanisms to provide additional support to children for education inclusion.

UNICEF Serbia, “Country Office Annual Report 2012”, `Belgrade, January 2013

European Commission, “Serbia 2012 Progress Report”, Commission Staff Working Document, Brussels, 10.10.2012, SWD (2012) 333

Republic of Serbia, “Plan of Action for Children”, Belgrade, 2004

CESID and UNDP, Report on Public Opinion Research “Citizens’ Attitudes towards Discrimination in Serbia”, Belgrade, December 2012

UNICEF Serbia, “Mid-Term Review Report of 2011-2015 Country Programme of Cooperation Between the Government of Serbia and UNICEF”,  draft version, Belgrade, June 2013

Administrative data on Roma and children with disabilities are lacking due to regulations which prohibit the collection of ethnicity data and the complexity of definitions of disability.

The Logframe is part of the “Description of Action” which was the basis for concluding a Contribution Agreement between UNICEF with the EU Delegation.

An initial Theory of Change has been appended to the ToR of this evaluation. UNICEF Serbia provided the evaluation team an updated version of the document in October 2013 which is appended in Annex 1 of this Evaluation Report.

Activities 1 and 2 in the IPA 2008 Project Fiche

Activity 3 in the IPA 2008 Project Fiche

Activity 4 in the IPA 2008 Project Fiche

Čoka, Novi Kneževac, Zemun (Čoka cluster), Aleksinac, Ražanj and Niš (Aleksinac cluster)

European Commission, “DG ELARG Evaluation Guide”, Directorate E – Evaluation Unit, November 2008

OECD Regional Typology Directorate for Public Governance and Territorial Development, OECD June 2011

The Republic of Serbia Government Regulation on Regional Development of Regions and Local Self-governing units for 2013

UNICEF, “Working for an Equal Future. UNICEF Policy on Gender Equality and the Empowerment of Girls and Women”, New York, May 2010

During the first two years of Project implementation, the assistant minister was In charge of the project, as member of the Steering Committee. After the elections in 2012 and consequent government reshuffle, that role was assigned to (new) state secretary.

Republic of Serbia Government, “Social Welfare Development Strategy”, Official Gazette of the Republic of Serbia no. 55/05 and 71/05 – Correction, 2005, page 8

Ibid, page 5

UNICEF Serbia Country Office, ”UNICEF comments on child rights issues in Serbia. Report presented to the Pre-sessional Working Group of the United Nations Committee on the Child Rights”, January 2008

UNICEF, “Country Programme Action Plan 2011-2015 between The Government of the Republic of Serbia and UNICEF”, Belgrade, December 2010, Outcome 1, Output 1.2

Committee on the Rights of the Child, forty-eighth session, “Concluding Observations of the Committee on the Rights of the Child: Republic of Serbia”, 6 June 2008, page11

European Commission, ”Serbia 2009 Progress Report”, Commission Staff Working Document Brussels, 14.10.2009, SEC(2009) 1339

European Commission, ”Serbia 2010 Progress Report”, Commission Staff Working Document, Brussels, 9 November 2010, SEC(2010) 1330

European Commission, ”Analytical Report”, Commission Staff Working Document, Brussels, 12.10.2011, SEC(2011) 1208

Rulebook on Service Standards

Republic of Serbia Government, “Social Welfare Development Strategy”, Official Gazette of the Republic of Serbia no. 55/05 and 71/05 – Correction, 2005, page 13.

Ibid.

Committee on the Rights of the Child, forty-eighth session, “Concluding Observations of the Committee on the Rights of the Child: Republic of Serbia”, 6 June 2008, page 9

Republic Institute for Social Protection, “Strengthening key system functions of relevance for providing support to children with disability”, Project Proposal Document, Belgrade, May 2013

Milanović, M., Vasić. M., Čeperković, R., “Assessment of the implementation of the rulebook on organization, normative provisions and standards of work in CSW – from the perspective of CSW practitioners”, Association of Centres for Social Work, December 2012

Available at http://www.zavodsz.gov.rs, accessed 10 October 2013

UNICEF Serbia Country Office,“ Developing Community-based Services for Children with Disabilities and their Families. Annual report for Year 3 of Implementation”, covering the period 22 April 2012-22 April 2013

Republic of Serbia Government, “Social Welfare Development Strategy”, Official Gazette of the Republic of Serbia no. 55/05 and 71/05 – Correction, 2005

Interviews in the MoLESP, CSWs and the Republican Institute for Social Protection

Gordana Matković and Boško Mijatović, “Program of child allowances in Serbia. Analysis and proposals for improvement”, CLDS I UNICEF, 2012

Interviews in the MoLESP, CSWs and the Republican Institute for Social Protection

Republic of Serbia, “Plan of Action for Children”, Belgrade, 2004, page 27

Committee on the Rights of the Child, forty-eighth session, “Concluding Observations of the Committee on the Rights of the Child: Republic of Serbia”, 6 June 2008, para 49(a)

The Committee on the Elimination of Discrimination against Women, Thirty-eighth session, “Concluding comments of the Committee on the Elimination of Discrimination against Women: Serbia”, 2007, para 37

UNICEF, “Country Programme Action Plan 2011-2015 between The Government of the Republic of Serbia and UNICEF”, Belgrade, December 2010, Outcome 1, Output 1.4

UNICEF Description of Action

Activity 3 in IPA 2008 Project Fiche. See also Chapter 1.2 of this report.

Annual project reports Years 1, 2, 3 and Theory of Change

To be noted is that some people attended several training events, so 1,952 refers to the number of participations.

Less courses, seminars and events organised by UNICEF for local PIUs and regional mentors aimed at project management.

All courses are accredited less those provided by CLDS

e.g.facilitation skills, managing volunteers, supporting families with children with disability, supervisory support to service providers

26 CSWs (61%), 13 citizens associations (30%), 2 schools for education of children with disability (5%), 1 Institute for education of children and youth (2%) and 1 Red Cross (2%)

Western Serbia 10%, Central Serbia 20%, Eastern Serbia 20%, Southern Serbia 20% and Vojvodina 30%

It does not include employment in local PIUs.

According to the final figures provided by UNICEF to the evaluation team in October 2013; 1,212 planned beneficiaries according to the approved projects for the municipalities; 1,182 according to the Final Monitoring Report in April 2013

UNICEF, “IPA 2008 Social Inclusion. Final Monitoring Report”, April 2013

UNICEF Year 3 Annual Project Report, 2013

ROM Report 2011

UNICEF Description of Action

UNICEF Description of Action and Theory of Change

The Centre for Liberal-Democratic Studies, “Mapping of the community based social services in Serbia”, Belgrade, 2013

The Centre for the Liberal-Democratic Studies, “Financing of Social Protection in the Republic of Serbia on the Local Self Government Level”, Belgrade, 2013

NGO Familia and Faculty of Philosophy Nis, ”Impact of small home communities on children with disabilities”, Nis, 2013

Milanović, M., Vasić. M., Čeperković, R., “Assessment of the implementation of the rulebook on organization, normative provisions and standards of work in CSW – from the perspective of CSW practitioners”, Associations of Centres for Social Work, December 2012

Faculty of Political Science, Department of Social Work, ““Impact of the Community-Based Services on Children with Disabilities and Their Families”, Belgrade, 2013

Faculty of Political Science, Department of Social Work, “Praćenje Uzroka, Procesa Donošenja Odluka I Ishoda za Decu u Sistemu Socijalne Zaštite”, University of Belgrade,  July 2013

Practicum for Day care service for children with disabilities, Practicum for Home help service for children with disabilities, Practicum for Respite care service for children with disabilities, Practicum for Supported living service for children leaving care and youth with disabilities, Guide for involving volunteers in community services for children with disabilities, Guide for direct caregivers working with children with disabilities

Interviews at the CSW Aleksinac and CSW Crveni Krst Nis.

Interview with MODS network coordinator

Note of the Child Protection Officer (UNICEF) submitted to the evaluation team

According to the final annual report the fourth round of monitoring began on 11th March and should have been finalized by 22nd May 2013. It included representatives of the EU Delegation finance department.

This was especially evident in the case of the day care service located in the basement of the elementary school Veljko Radmanovic in Zemun. Although the monitoring team specifically stated that the service should immediately be relocated due to the highly inadequate conditions and relationships between the service provider and host institution, the Zemun service has continued to operate in unacceptable and even dangerous conditions for the beneficiaries at the time of the evaluation visit in September 2013.

Service providers are granted a transition period of 2 years in order to comply with the standards. In case of failure to respect the standards, the respective service provider will lose its licensing and the service will be no longer be authorised to function.

Vrnjačka Banja Project Application, Annex III Budget, Justification, budgetary line 1.1.1

This is also acknowledged by the grant selection committee which expressed its concerns in the evaluation sheet, but with no actual follow-up from the EUD. For instance, for Čoka application they wrote: “Most of the budget will be allocated for the human resources honoraria – almost 60% and it doesn’t seem well and rationally planned. It could be considerate if the same results can be achieved with less staff…”. In other projects, the percentage of grant allocated for human resources is even higher, exceeding 70% in Stara Pazova and Knjazevac.

Centre for Liberal-Democratic Studies, “Expenditures of Community-Based Services for Children and Unit Costs”, Belgrade, 2012

Current Research Information System (EU)

UNICEF, “Description of Action”, page 15

e.g. “at least 4,000 youth have contributed as volunteers in providing assistance to most vulnerable categories of society at the local level in Serbia, by 2013”, “overall, a total of 1,000 women licensed as service providers at the local level among targeted municipal clusters by 2012”, etc.

Ministry of Labour, Employment and Social Protection, “Final Report of the project Creation and Implementation of the Licencing System for Social Services Providers”, Belgrade, March 2011

SeCons, “Final Assessment of the Project Support to the De-institutionalization of Children, in particular those with disabilities, in the Republic of Serbia”, Belgrade, February 2013

Republic Institute for Social Protection, “Report on the work of CSWs for 2008”, Belgrade, 2009, page 37

Ibid, page 38

Ibid. page 36

UNICEF Description of Action

Republic Institute for Social Protection, “Report on the Work of Residential Institutions for Children and Youth in 2011”, Belgrade, 2012, and UNICEF Theory of Change

Republic Institute for Social Protection, “Trends and Characteristics of institutional Placement of Children with Disabilities in the period 2000-2011”, Belgrade, 2012. Research Summary page 2

NGO Familia and Faculty of Philosophy Nis, ”Impact of small home communities on children with disabilities”, Nis, 2013

Faculty of Political Science, “Impact of the Community-Based Services on Children with Disabilities and Their Families”, Belgrade, 2013, page10

Ibid. page 22

Ibid. page 23

Ibid. page 80

Ibid. page 119

Ibid. pages 120-121

The Special Report on Discrimination of Children in Serbia will be presented to the Parliament

e.g. the predominance of the reimbursement principle according to which grant money is released based on proofs of actually spent money by the beneficiary prior to the submission of the reimbursement request, far lower levels of advance payments (if any), penalties for underachievement of indicators, etc.

UNICEF, “Description of Action”

E-mail of UNICEF Child Protection Specialist dated 23 September 2013

UNICEF Annual Report Year 1

Ibid.

NGO Amity, “Final report on technical support for the UNICEF project Developing community based services for children with disabilities and their families – outreach and mapping”, Belgrade, 2012, page 2

Committees set up at municipality level, including in its membership the local CSWs, and which are in charge of assessing additional support required for education of children with learning difficulties, disabilities or behavioural problems.

Based on the Performance Scoring detailed in the methodology of the evaluation.